3GPP TSG RAN3 meeting #124	                                              R3-243661

Fukuoka, Japan, 22nd – 26th May 2024

Agenda item: 	    10.1

Source: 	China Unicom, CMCC (WI Rapporteur)

Title: 	Workplan for Rel-19 SON_MDT Enhancement

Document for:	Information

1	Introduction

At RAN#102, the new Work Item on Data Collection for SON_MDT in NR standalone and MR-DC phase 4 was agreed [1]. As WI Rapporteur, in this contribution, we recommend a work plan for RAN2 and RAN3. The workplan captures dependencies among tasks and timeline for RAN2/3.

The WID [1] introduced the following objectives in the core part:

The objective of this work item is to specify data collection enhancement in NR standalone and MR-DC for SON/MDT purpose. The specific objectives of this work item are: - MRO enhancement for R18 mobility mechanisms, including, Lower layer triggered mobility (LTM), CHO with candidate SCGs, subsequent CPAC [RAN3, RAN2]: - Specification of the inter-node information exchange, including possible enhancements to interfaces [RAN3] - Identify and specify necessary UE reporting to enhance the mobility parameter tuning [RAN2] - Support of SON/MDT enhancements for [RAN3, RAN2]: - Intra-NTN mobility - Network Slicing - Support of the leftovers in Rel-18 SON/MDT [RAN3, RAN2]: - RACH optimization for SDT - MHI Enhancement for SCG Deactivation/Activation - MRO for MR-DC SCG failure If needed, co-operate with RAN1, SA2, SA5, CT4.

2	Workplan

2.1	Timeline

Table 1 summarizes a timeline for RAN2 and RAN3 while the timeline is based on the time budget approved at RAN#102 in [2].

Table 1: Timeline for RAN2, 3 efforts

| TSG/WG | Meeting Number | Date | TU | Task |
| --- | --- | --- | --- | --- |
| RAN2 | #125bis | Apr. 2024 | 0.5 | In the first meeting, RAN2 can start working on the following items considering the limited TU: 1. Discussion on the scenario of MRO enhancement for R18 mobility mechanisms, where LTM can be prioritized. 2. Discussion on leftover features from R18 with corresponding specification impacts: - MHI enhancement with SCG activation/deactivation - RA report enhancement for SDT -Approval of the work plan -Update BL CRs if needed. |
| RAN3 | #123bis | Apr. 2024 | 1.5 | RAN3 can start working on the following items: - Discussion on the scenario and high-level solutions of MRO enhancement for R18 mobility mechanisms, including, Lower layer triggered mobility (LTM), CHO with candidate SCGs, subsequent CPAC, - Discussion on the scenario and high-level solutions for supporting SON/MDT enhancements for intra-NTN mobility - Discussion on the scenario and high-level solutions for supporting SON/MDT enhancements for network slicing Discussion on leftover features from R18 with corresponding specification impacts: MRO for MR-DC SCG failure - Approval of the work plan - Discuss and agree on the BL CR assignment -Update BL CRs if needed. |
| RAN2 | #126 | May 2024 | 0.5 | 1. Discussion on leftover features from R18 with corresponding specification impacts: - MHI enhancement with SCG activation/deactivation - RA report enhancement for SDT 2. Discussion on the scenario of MRO enhancement for R18 mobility mechanisms, where LTM can be prioritized. -Coordinate with other working groups, e.g. taking RAN3’s agreements into consideration and send the LS if needed |
| RAN3 | #124 | May 2024 | 1.5 | Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements, coordinate with other working groups, and send the LS if needed 1.MRO enhancements - Discussion on scenarios of near failure LTM. - Discussion on scenarios for the differentiation of too early LTM, too late LTM and LTM to wrong cell. - Discussion on MRO for CHO with candidate SCG failure and near failure cases, focusing on NR-DC - Discussion on the scenarios of failure in S-CPAC. The optimization of non-failure scenarios 2. Intra-NTN Mobility - Discussion on logged MDT enhancement based on scenarios for intra-NTN - Discussion on MRO for intra-NTN failure scenarios 3. Network slicing - Discussion on logged MDT and immediate MDT enhancements based on scenarios for network slicing 4. Leftovers - Discussion on scenario of RACH optimization for SDT - Check RAN2 progress regarding support MRO for SCG failure in EN-DC, NGEN-DC and NE-DC scenarios. -Update BL CRs if needed. |
| RAN2 | #127 | Aug. 2024 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #125 | Aug. 2024 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #127bis | Oct. 2024 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #125bis | Oct. 2024 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #128 | Nov. 2024 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #126 | Nov. 2024 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #129 | Feb. 2025 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #127 | Feb. 2025 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #129bis | Apr. 2025 | 0.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN3 | #127bis | Apr. 2025 | 1.5 | -Continue stage-2 and stage-3 discussion and support for the SON/MDT enhancements -Coordinate with other working groups, and send the LS if needed -Update BL CRs if needed. |
| RAN2 | #130 | May 2025 | 0.5 | Finalize Stage-2 discussion |
| RAN3 | #128 | May 2025 | 1.5 | Finalize Stage-2 discussion |
| RAN2 | #131 | Aug. 2025 | 0.5 | Finalize Stage-3 discussion |
| RAN3 | #129 | Aug. 2025 | 1.5 | Finalize Stage-3 discussion |
| RAN | #109 | Sep. 2025 |  | Functional freeze |

Note that the detailed work plan for the meetings after May will be updated based on the progress.

3	Summary

Proposal 1: RAN3 working group is kindly asked to endorse the workplan.

4   References

- RP-234038: New WID: Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4; TSG RAN Meeting #102, Edinburgh, Scotland, Dec 11-15, 2023

- RP-232744, Status of time budgets for RAN1/2/3/4 ongoing and new WIs/SIs after RAN #102, TSG RAN Meeting #102, Edinburgh, Scotland, Dec 11-15, 2023