3GPP TSG-RAN WG4 Meeting #106	R4-2302939

Athens, Greece, Feb 27th – March 3rd 2023

Source:	China Telecom, Intel Corporation

Title:	Work plan for NR demodulation performance evolution WI

Agenda Item:	9.18

Document for:	Approval

Introduction

In RAN #95e meeting, the new WI on NR demodulation performance evolution was approved, and the latest revised WID was approved in [1] at RAN #97e.

This contribution presents a work plan aiming to find an appropriate contributing timeline for each work task. The TP/CR work split will be added in the future meetings.

Work item objectives

The following objectives are copied from the WID in [1]:

- Evaluate and specify advanced receiver to cancel inter-user interference for MU-MIMO

  - Phase I: Study the performance gain, reference receiver assumption, interference modeling, testability, required signalling overhead, as well as impact on other WGs

    - Further discuss reference receiver assumption with below candidates

      - E-MMSE-IRC

      - R-ML

    - Target scenario: Focus on slot based transmission

  - Phase II (if any pending on the conclusion for phase I):

    - Specify PDSCH demodulation requirements under MU-MIMO scenario with advanced receiver

      - Note: As baseline, performance requirements shall be specified under single reference receiver assumption. This baseline can be revisited at RAN #100 if necessary.

- Specify absolute physical layer throughput requirements with link adaptation

  - Note: Rel-17 RAN4 study outcome documented in section 5.10 of TR 37.901-5 is a starting point for this objective

Work Plan

With the target completion date of January 2024 at RAN4#109-bis, the following work plan is proposed.

Note that the work plan will be updated if needed with the update on RAN4 meeting plan.

Table 1	Work plan for NR demodulation performance evolution WI

|  | RAN4#105 (Nov 2022) | RAN4#106 (Feb 2023) | RAN4#106b (Apr 2023) | RAN4#107 (May 2023) | RAN4#108 (Aug 2023) | RAN4#108b (Oct 2023) | RAN4#109 (Nov 2023) | RAN4#109b (Jan 2024) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Advanced receiver for MU-MIMO (Note 1) |  | Phase I: - Discussion and initial agreement on the link level simulation assumptions including: interference modeling methodology, reference receiver assumption and others if any | Phase I: - Agreement on the baseline link level simulation assumptions - Collection of initial simulation results | Phase I: - Collection of simulation results - Update of link simulation assumptions if needed - Tentative conclusion on Phase I. | Phase I: - Collection of updated simulation results if any - Conclusion on Phase I. Phase II: - Initial discussion on the parameters for defining requirements | Phase II: - Agreement on the parameters for defining requirements - Collection of initial simulation results | Phase II: - Update of the parameters for defining requirements if needed - Collection of ideal and impairment simulation results - Draft CRs endorsed | Phase II: - Collection of updated ideal and impairment results - CRs agreed |
| Absolute physical layer throughput requirements with link adaptation (Note 2) | - Discussion on test scope, simulation assumptions and test parameters | - Agreement on baseline assumptions, test parameters and test metrics - Collection of updated & additional simulation results if any | - Collection of updated & additional simulation results if any | - Agreement on the test requirement value - CRs agreed |  |  |  |  |
| Note 1: Considering the start of this work was delayed by 1 quarter, the phase I conclusion as well as the work item completion is proposed to be extended by 1 quarter. Note 2: According to [2], this work targets to be completed within 6 months. And extension of 1 more meeting is proposed. |  |  |  |  |  |  |  |  |

Simulation results collection work split

|  | Responsibility |
| --- | --- |
| Advanced receiver for MU-MIMO | China Telecom |
| Absolute physical layer throughput requirements with link adaptation | Intel |

TP work split

To be added

CR work split

To be added

Reference

RP-222300, Revised WID on NR demodulation performance evolution, China Telecom, RAN #97e, Sep 2023.

RP-220068, Summary for RAN Rel-18 Package: RAN chair (Qualcomm), RAN4 chair (Huawei), RAN #95e, March 2022.