3GPP TSG-RAN WG4 Meeting #116-bis	R4-2515086

Prague, CZ, 13th – 17th October 2025

Source:	Nokia, Samsung, Huawei, T-Mobile USA, Ericsson

Title:	Workplan for Rel20 UE RF enhancements Ph5

Agenda item:	7.1.2

Document for:	Approval

Introduction

Based on the agreed WID [1], this contribution propose the RAN4 workplan of Rel-20 WI for UE RF enhancements (NR_UE_RF_Ph5-Core) to guide the detailed RF (both UE RF and BS RF) and Demod work targets for the upcoming meetings. To facilitate the readability, the objectives from the core part of the WID are copied below.

High power UE (HPUE) for NR single carrier operation - Specify the UE RF requirements for single carrier TDD to support 4Tx for CPE/FWA UE with 4x26dBm PA configurations - Co-existence study for ACLR, specify ACLR requirements if needed - Specify the UE RF requirements including maximum output power (MOP), MPR requirements, etc. - Supporting 4x4 UL MIMO and TxD - Specify the band specific requirements for exemplary bands - Example bands: n41, n77/n78, n79, n104 - Maximum output power is up to 32 dBm - RAN4 to determine whether to reuse PC1 or introduce new power class - PC1.5 with 2Tx for FDD bands for handheld and FWA UE - Specify the UE RF requirements including maximum output power (MOP), MPR requirements, etc. - Supporting 2x2 UL MIMO and TxD - Baseline PA configuration: 2 x 26 dBm - Specify the band specific requirements for exemplary bands - Example bands: n1, n25 - PC1.5 1Tx for TDD bands for FWA UE - Study the possibility of applying PC1.5 with 2Tx MPR/A-MPR requirements to PC1.5 with 1Tx, if feasible, specify the corresponding UE RF requirements, including maximum output power (MOP), MPR/A-MPR requirements, etc. - Baseline PA configuration: 1 x 29 dBm - Example bands: n41, n77/n78, n79 - This work is to start in 2026 Q4 - 2Tx for TDD bands for FWA UE - Study the possibility of applying PC1 with 4Tx A-MPR/MPR requirements to PC1 with 2Tx, if feasible, specify the corresponding UE RF requirements, including maximum output power (MOP), MPR/A-MPR requirements, etc. - Baseline PA configuration: 2 x 29 dBm - Example bands: n41, n77/n78, n79, n104 - Maximum output power is up to 32 dBm - RAN4 to determine whether to reuse PC1 or introduce new power class - This work is to start in 2026 Q4 6MHz channel bandwidth - Specify the generic core requirements to support 6 MHz NR FR 1 channel bandwidth [RAN 4] - Only include 15 kHz SCS - Specify the spectrum utilization - Specify UE RF requirements for UL and DL - Specify BS RF requirements (OTA and conducted) for UL and DL - Specify the band specific requirements to introduce 6 MHz for NR band n5, n8, n12, n85, n29 [RAN 4] - BS and UE Channel bandwidth per operating band - UE reference sensitivity - When needed - Additional Maximum Power Reduction (A-MPR) - Once RAN 4 has introduced the new channel bandwidth, RAN 2 will introduce the necessary signalling for this channel bandwidth [RAN 2] - Note This should be similar to the signalling for 7 MHz channel bandwidth - Once RAN 4 has introduced the new channel bandwidth, RAN 3 will introduce the necessary signalling for this channel bandwidth [RAN 3] - Note This should be similar to the signalling for 7 MHz channel bandwidth NOTE: Once this WI is completed, the 6 MHz bandwidth can be introduced also for other bands (not addressed in this WI) via the appropriate basket WI. The support of 6MHz bandwidth is release independent. General for all the areas - Specify release independence requirements for the core part in TS 38.307, if needed and feasible. Power enhancement with relaxed UE Tx EVM and advanced BS receiver - Note: Discuss both 5G-Adv and 6G reduced UE MPR values with the relaxed Tx EVM requirement as part of 6G study. RAN4 will further discuss and finalize (if agreed) the scope and other necessary details (e.g. NW control of this feature) in 2025.Q4 under 6G agenda items. It will be further decided in RAN#113 (Sep, 2026) whether or not there will be a follow up Rel-20 WI under 5G-Adv. For 5G-Adv, solution should not be AI based and there should not be any impact to RAN1.

Discussion

As of the current TU sheet shown in Table 1, the core part ends in RAN4#122 i.e., before March 2027 RANP#115. This gives us total of nine meetings to finish the core part of this work. According to the WID, work on some of the HPUE objectives will start from 2026 Q4. Further, there is a RAN#113 (Sep, 2026) checkpoint for objective related to power enhancement with relaxed UE Tx EVM and advanced receiver, before it can start in RAN4. These restrictions are taken care in the workplan.

Table 1 TU budget

|  |  | 116bis | 117 | 118 | 118bis | 119 | 120 | 120bis | 121 | 122 | 122bis | 123 | 124 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Core part | R4RF | 0.5 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.5 | 0.25 |  |  |  |
|  | R4RD |  |  |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  |  |
| Perf. Part | R4RD |  |  |  |  |  |  |  |  | 0.25 | 0.25 | 0.25 | 0.25 |

| Meeting title | Dates | Location | Proposed workplan |
| --- | --- | --- | --- |
| 3GPPRAN4#116-bis | 13 Oct - 17 Oct 2025 | Prague, CZ | - Work kick-off in RAN4 - Formulation of the workplan - HPUE: 4 Tx for TDD bands for CPE/FWA - Initial discussion on the need for co-existence simulation - Initial discussion on reuse PC1 or define new power class. - HPUE: PC1.5 with 2 Tx for FDD bands - Initial discussion on general requirements - 6 MHz - Discuss and conclude spectrum utilization - Discussion on BS/UE general requirements - Discuss A-MPR simulation assumptions - Discuss and conclude CR workload split for BS CRs |
| 3GPPRAN4#117 | 17 Nov - 21 Nov 2025 | Dallas, US | - HPUE: 4 Tx for TDD bands for CPE/FWA - Finalize co-existence simulation assumptions if required - Finalize power class discussion - Finalize MPR/A-MPR simulation assumptions - Discuss other band independent requirements including support of 4x4 UL MIMO and TxD. - HPUE: PC1.5 with 2 Tx for FDD bands - Finalize MPR/A-MPR simulation assumptions - 6 MHz - Discuss and finalize UE REFSENS requirement - Discuss and conclude A-MPR simulation assumptions - Discuss A-MPR simulation results - Conclude BS requirements |
| 3GPPRAN4#118 | 09 Feb - 13 Feb 2026 | Gothenburg, SE | - HPUE: 4 Tx for TDD bands for CPE/FWA - Discuss MPR/A-MPR results - Discuss other band independent requirements including support of 4x4 UL MIMO and TxD. - HPUE: PC1.5 with 2 Tx for FDD bands - Discuss MPR/A-MPR results - Discuss other band independent requirements including support of 2x2 UL MIMO and TxD. - 6 MHz - Discuss and aim for agreement on A-MPR limits - Endorse BS draftCRs - Work split for HPUE objectives |
| 3GPPRAN4#118-bis | 13 Apr - 17 Apr 2026 | Malta, Europe | - HPUE: 4 Tx for TDD bands for CPE/FWA - Discuss MPR/A-MPR results - Discuss other band independent requirements including support of 4x4 UL MIMO and TxD. - HPUE: PC1.5 with 2 Tx for FDD bands - Discuss MPR/A-MPR results - Discuss other band independent requirements including support of 2x2 UL MIMO and TxD. - 6 MHz - Agreement on A-MPR limits - Endorse remaining draft CRs - Release independence discussion |
| 3GPPRAN4#119 | 18 May - 22 May 2026 | China, CN | - HPUE: 4 Tx for TDD bands for CPE/FWA - Finalize MPR/A-MPR results - Finalize other band independent requirements including support of 4x4 UL MIMO and TxD. - HPUE: PC1.5 with 2 Tx for FDD bands - Finalize MPR/A-MPR results - Finalize other band independent requirements including support of 2x2 UL MIMO and TxD. - 6 MHz - Agree all CRs |
| 3GPPRAN4#120 | 24 Aug - 28 Aug 2026 | Maastricht, NL | - HPUE: 4 Tx for TDD bands for CPE/FWA - Endorse draft CRs - Release independence discussion. - HPUE: PC1.5 with 2 Tx for FDD bands - Endorse draft CRs - Release independence discussion. |
| 3GPPRAN4#120-bis | 12 Oct - 16 Oct 2026 | South Korea, KR | - HPUE: PC1.5 with 1 Tx for TDD bands - Discuss and agree on any required assumptions regarding reuse of PC1.5 2Tx requirements - HPUE: 2Tx for TDD bands for FWA - Discuss and agree on any required assumptions regarding reuse of PC1 or new power class - Discuss and agree on any required assumptions regarding applicability of PC1 4Tx requirements. - Power enhancement with relaxed UE Tx EVM - Any related issues |
| 3GPPRAN4#121 | 16 Nov - 20 Nov 2026 | Calgary, CA | - HPUE: PC1.5 with 1 Tx for TDD bands - Finalize discussion and agree on draft CRs. - Release independence discussion. - HPUE: 2Tx for TDD bands for FWA - Finalize discussion and agree on draft CRs. - Release independence discussion. - Power enhancement with relaxed UE Tx EVM - Agree draft CRs if applicable. - Release independence discussion if applicable. |
| 3GPPRAN4#122 | 25 Feb - 29 Feb 2027 | Japan, JP | - Finalize the big CR - Agree on release independence |

Agree and approve the proposed work plan for the core part.

Conclusion

The following Observations and Proposals were made:

Proposal 1: Agree and approve the proposed work plan for the core part.

- References

- RP-252942, New WID: UE RF enhancements for NR FR1, Phase 5, vivo, RAN meeting #109, Sep 2025.