## Cover sheet
3GPP TSG-RAN WG5 Meeting #103 | [8 empty] | R5-242689
Fukuoka, Japan, 20 - 24 May 2024
Agenda Item: | 7.5.2
Source: | China Telecom, ZTE
Title: | WP for LTE_CA_R17-UEConTest
Work item code: | LTE_CA_R17-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of the present work item is to develop RF, RRM and protocol test cases for Rel-17 LTE CA configurations. The scope of this work item is conformance testing of all Rel-17 LTE CA configurations specified by 3GPP TSG RAN WG4. The introduction of the CA configurations into the 3GPP TSG RAN WG5 test specification is dependent on the progress of the associated core and performance work items in 3GPP TSG RAN WG4.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases / configurations (Note 1) | Number of new test cases / configurations | Comments
Overall completion |  | 50% (+20%)
Completion Compensation |  | -
| Note 1: | Only test cases / configurations completed for all applicable WP areas and sub-areas are counted. For completed test cases / configurations per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations | Comments
SA Option 2 (SA NR) (FR1) |  | 30%
FR1 |  | 30%
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS:Area Scope | TS/Area | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations | FR1
[5 empty] | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations
NEW TEST CASES
5 References
[1] RP-232260 | New WID on UE Conformance - Rel-17 LTE CA Configurations
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [11 empty] | TS STATUS INPUT
WI | DL Configuration | UL configuration(s) | Type of change | Interested Operator | Resposible Company | Status | Target | TDOC(s) | Comments | Weight | WP item completion level | 36.508: Test frequencies | 36.521-1 | 36.521-2 | 36.521-3 | 36.523-1 | 36.523-2 | 36.523-3 | 36.903 | 36.904 | 36.905: | 37.571-1 | 37.571-3 | 37.571-5
880087 | CA_38A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_38C-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_26A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_26A-38C | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_3C-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_3C-20A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_2A-8A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_2A-2A-7C | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_2A-2A-13A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_2A-2A-7A-7A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_7A-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_7A-7A-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_7C-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_7A-25A-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_7A-7A-25A-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_7C-25A-25A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_25A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_46A_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_46C_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_46D_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_46E_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_48A_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_48C_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_48D_53A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_30A-48A | - | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#102(Feb-24) | R5-241853 R5-240941 R5-241874 R5-240937 R5-240939 R5-240938 R5-242701 R5-242712 |  | 1 | 100% | 30% | 80% | 40% |  |  | 30% |  |  |  | 100%
880087 | CA_2C-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_3A-3A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_3A-8B | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_3A-3A-8B | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_7A-8B | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_7A-7A-8B | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_40A-40A-42A-42A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_40A-40A-42C | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_40A-42A-42A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_40C-42A-42A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_40A-40A-42A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_2A-2A-46E | CA_2A | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_2A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_1A-1A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_1A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_3A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_7A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880087 | CA_1A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-13A-66A-66B | CA_66B | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-5A-48A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-5A-48C |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-5A-48D |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-13A-48C | CA_48C | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-48C-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-48D-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-48E-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_5A-48C-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_5A-48C-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_5A-48D-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_5A-48D-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_13A-48C-66A | CA_48C | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_13A-48C-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_13A-48D-66A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-38A-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-38C-66A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-12A-66A-66A | CA_66A-66A | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_12A-30A-66A-66A | CA_66A-66A | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-2A-12A-30A | CA_2A-2A | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-2A-12A-66A | CA_2A-2A | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-2A-5A-30A | CA_2A-2A | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-2A-12A-66A-66A | CA_2A-2A | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3A-8A-41A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3A-20A-38A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3A-40A-41A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-28A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7C-28-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3C-7A-8A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-3C-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3C-8A-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-3C-20A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3C-8A-20A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3C-8A-20A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3C-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3C-20A-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-12A-66A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-2A-5A-7A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-2A-7A-66A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-8A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-40A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_8A-40A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-8A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-8A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-8A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_8A-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_8A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-2A-7A-7A-13A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-2A-7C-13A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-2A-7A-13A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_5A-7A-7A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-5A-7A-7A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-7A-13A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-7A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7C-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-25A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-7A-25A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7C-25A-25A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3C-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-3C-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-2A-29A-66A | - | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#102(Feb-24) | R5-241853 R5-240941 R5-241874 R5-240937 R5-241202 R5-240938 R5-242782 |  | 1 | 80% |  | 80% | 40% |  |  | 30% |  |  |  | 30%
880088 | CA_2A-29A-66A-66A | - | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#102(Feb-24) | R5-241853 R5-240941 R5-241874 R5-240937 R5-240938 R5-242782 |  | 1 | 80% |  | 80% | 40% |  |  | 30%
880088 | CA_2A-2A-29A-66A-66A | - | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#102(Feb-24) | R5-241853 R5-240941 R5-240937 R5-241202 R5-240938 R5-242782 |  | 1 | 60% |  | 80% |  |  |  | 30% |  |  |  | 30%
880088 | CA_2A-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_2A-7C-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_5A-7A-7A-28A |  | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3A-3A-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-1A-3A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-1A-3C-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-1A-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-3A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-7A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3A-7A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3A-28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-3A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-7A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_1A-28A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_3A-7A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880088 | CA_7A-28A-40D | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-5A-7A-7A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3C-7A-8A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7A-8A-20A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7A-8A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7A-8A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7A-8A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7A-8A-40C | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7C-20A | CA_7C | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7C-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7A-28A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3C-7A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-3A-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-1A-3C-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-1A-3A-7A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-7A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3C-8A-20A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3C-8A-20A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-8A-20A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3C-8A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3C-8A-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-3A-8A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-8A-40C | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-8A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3C-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3C-20A-38A | CA_3C | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3C-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-3A-40A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-5A-7A-7A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-8A-20A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-8A-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-8A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-8A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-8A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-8A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-8A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-8A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-7A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-8A-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-8A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-8A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-8A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_1A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-2A-5A-7A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-5A-7A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-5A-7A-7A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-5A-7A-66A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-5A-7C-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-7A-12A-66A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-7C-13A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-7A-7A-13A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-7A-28A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-7C-28A-66A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_2A-2A-29A-30A-66A | - | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#102(Feb-24) | R5-241853 R5-240941 R5-241874 R5-240937 R5-241202 R5-240938 R5-242782 |  | 1 | 80% |  | 80% | 40% |  |  | 30% |  |  |  | 30%
880089 | CA_3A-5A-7A-7A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_3A-7A-8A-20A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_3A-7A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_3A-7A-8A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_3A-7A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_3A-7A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_3A-7A-28A-40A-40A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_3A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_3A-8A-40A-41A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_3A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_7A-8A-20A-28A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_7A-8A-20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_7A-8A-20A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_7A-8A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_7A-8A-20A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_7A-8A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_7A-8A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_7A-20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_7A-20A-28A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_7A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_8A-20A-28A-32A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880089 | CA_8A-20A-32A-38A | - | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_30A-48A | CA_30A-48A | New LTE CA Config | Sporton | Bureau Veritas (amy.tao@bureauveritas.com) | Ongoing | RAN5#102(Feb-24) | R5-241853 R5-240941 R5-241874 R5-240937 R5-240939 R5-240938 R5-242701 R5-242712 |  | 1 | 100% | 30% | 80% | 40% |  |  | 30% |  |  |  | 100%
880090 | CA_8A-20A | CA_8A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_8A-28A | CA_8A-28A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_3A-38A | CA_3A-38A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_1A-40A | CA_1A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_1A-40A-40A | CA_1A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_1A-40C | CA_1A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_1A-40D | CA_1A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_3A-40A-40A | CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_3A-40D | CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_3A-40C | CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_28A-40A | CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_28A-40A-40A | CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_28A-40A-40A | CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_28A-40D | CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_28A-40C | CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_3C-26A | CA_3C CA_3A-26A | New LTE CA Config |  |  | Pending |  |  |  | 1
880090 | CA_7C-26A | CA_7C CA_7A-26A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_3C-7A-8A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3C-38A | CA_1A-3A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_3C-8A-38A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3C-20A | CA_1A-3A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_3C-8A-20A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-8A-20A | CA_1A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_3A-8A-20A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-8A-38A | CA_1A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3C-7A-8A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3C-8A-38A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3A-8A-20A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3C-8A-20A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3A-20A-38A | CA_1A-3A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3C-20A-38A | CA_1A-3A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3A-7A-38A | CA_1A-3A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-7A-8A-38A | CA_1A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_3A-7A-8A-38A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-8A-20A-38A | CA_1A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_3A-8A-20A-38A | CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A_3A_7A_8A_38A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A_3A_8A_20A_38A | CA_1A-3A CA_1A-8A CA_3A-8A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_3A-20A-38A | CA_3A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-20A-38A | CA_1A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-7A-20A-38A | CA_1A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_3A-7A-20A-38A | CA_3A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3A-7A-20A-38A | CA_1A-3A CA_1A-20A CA_3A-20A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3A-40A | CA_1A-40A CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_3A-28A-40A | CA_3A-40A CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3A-40A-40A | CA_1A-3A CA_1A-40A CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_3A-28A-40A-40A | CA_3A-28A CA_3A-40A CA_28A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3A-40D | CA_1A-40A CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
880091 | CA_1A-3A-40C | CA_1A-40A CA_3A-40A | New LTE CA Config |  |  | Pending |  |  |  | 1
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.