## R5#106
3GPP TSG RAN WG5 (RAN5) Meeting #106 | [9 empty] | R5-250015
Athens, Greece, 17 - 21 February 2025
WI Progress and Target Completion Date Review
Source: RAN5 Chair
To: RAN5
Purpose: For Endorsement
UIC | WI Name | Rel | Tdoc# | Pre TCD | pre % | post % | post TCD | change (mths) | Rapporteur | other comments
830083 | UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | Rel-16 | R5-250116 | 2025-06-01 | 61% | 63% | 2025-06-01 |  | CMCC
880069 | UE Conformance Test Aspects - 5G V2X with NR sidelink | Rel-16 | R5-250722 | 2025-06-01 | 85% | 87% | 2025-06-01 |  | Huawei
900056 | UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations | Rel-17 | R5-250426 | 2025-12-01 | 11% | 11% | 2025-12-01 |  | Huawei
911003 | UE Conformance Test Aspects - NR-based access to unlicensed spectrum | Rel-16 | R5-250543 | 2025-03-01 | 94% | 100% | 2025-03-01 |  | Qualcomm
950062 | UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 | Rel-17 | R5-250421 | 2025-12-01 | 63% | 63% | 2025-12-01 |  | Huawei
960074 | UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) | Rel-17 | R5-250537 | 2025-06-01 | 86% | 89% | 2025-06-01 |  | Qualcomm
960080 | UE Conformance - NR support for high speed train scenario in frequency range 2 | Rel-17 | R5-251421 | 2025-06-01 | 68% | 69% | 2025-12-01 | +6 | Samsung
960083 | UE Conformance - NR Sidelink Relay | Rel-17 | R5-250993 | 2025-03-01 | 70% | 80% | 2026-03-01 | +3 | CATT
960084 | UE Conformance - NR Sidelink enhancement | Rel-17 | R5-250991 | 2025-03-01 | 40% | 50% | 2025-09-01 | +6 | CATT
960089 | UE Conformance Test Aspects - NR RRM enhancement | Rel-16 | R5-250601 | 2025-06-01 | 80% | 85% | 2025-06-01 |  | Apple
1000050 | UE Conformance - Additional NR bands for UL-MIMO in Rel-18 | Rel-18 | R5-250168 | 2025-06-01 | 74% | 76% | 2025-06-01 |  | China Unicom
1000051 | UE Conformance - High power UE (power class 2) for NR FR1 FDD single band | Rel-18 | R5-250170 | 2025-06-01 | 31% | 33% | 2025-06-01 |  | China Unicom
1000054 | UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-250764 | 2025-06-01 | 80% | 85% | 2025-06-01 |  | China Telecom
1000056 | UE Conformance - UE Conformance - Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL | Rel-17 | R5-250424 | 2025-06-01 | 9% | 20% | 2025-06-01 |  | Huawei
1000057 | UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-251112 | 2025-06-01 | 76% | 76% | 2025-06-01 |  | Huawei
1020087 | UE Conformance - Air-to-ground network for NR | Rel-18 | R5-250111 | 2025-06-01 | 64% | 64% | 2025-06-01 |  | CMCC
1020088 | UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | Rel-18 | R5-251422 | 2025-06-01 | 77% | 100% | 2025-03-01 | -3 | Huawei
1030060 | UE Conformance - NR support for dedicated spectrum less than 5MHz for FR1 | Rel-18 | R5-250500 | 2025-12-01 | 46% | 65% | 2025-12-01 |  | Nokia
1030061 | UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | Rel-18 | R5-251221 | 2025-06-01 | 72% | 90% | 2025-06-01 |  | China Telecom
1030062 | UE Conformance - Enhanced support of reduced capability NR devices plus CT1 | Rel-18 | R5-250172 | 2025-12-01 | 53% | 64% | 2025-12-01 |  | China Unicom
1030063 | UE Conformance - XR (eXtended Reality) enhancements for NR plus CT1 aspects | Rel-18 | R5-250619 | 2025-12-01 | 60% | 71% | 2025-12-01 |  | Nokia
1030064 | UE Conformance - Introduction of 900 MHz LTE band in the US | Rel-18 | R5-250254 | 2025-03-01 | 85% | 85% | 2025-06-01 | +3 | Nokia
1030065 | UE Conformance - NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | Rel-18 | R5-251202 | 2025-03-01 | 40% | 40% | 2025-06-01 | +3 | Apple
1030066 | UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 | Rel-18 | R5-250429 | 2025-06-01 | 34% | 35% | 2025-12-01 | +6 | Huawei
1030067 | UE Conformance - Network energy savings for NR | Rel-18 | R5-250807 | 2025-12-01 | 54% | 73% | 2025-12-01 |  | Huawei
1030069 | UE Conformance - Further NR coverage enhancements | Rel-18 | R5-250859 | 2025-12-01 | 29% | 30% | 2025-12-01 |  | China Telecom
1030070 | UE Conformance - Multi-carrier enhancements for NR | Rel-18 | R5-250828 | 2025-12-01 | 87% | 88% | 2025-12-01 |  | China Telecom
1030071 | UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | Rel-18 | R5-251049 | 2025-12-01 | 38% | 38% | 2025-12-01 |  | Samsung
1030072 | UE Conformance - NR MIMO evolution for downlink and uplink | Rel-18 | R5-251051 | 2025-12-01 | 37% | 50% | 2025-12-01 |  | Samsung
1030073 | UE Conformance - IoT (Internet of Things) NTN (non-terrestrial network) enhancements plus CT1 aspects | Rel-18 | R5-250106 | 2025-12-01 | 47% | 56% | 2025-12-01 |  | CMCC
1040102 | UE Conformance 4Rx for NR bands for FWA UEs (up to 2.6GHz) and handheld UEs (1GHz to 2.6GHz) | Rel-18 | R5-251070 | 2025-06-01 | 52% | 95% | 2025-06-01 |  | ZTE
1040103 | UE Conformance - Mobile Terminated-Small Data Transmission (MT-SDT) for NR | Rel-18 | R5-250369 | 2025-12-01 | 40% | 65% | 2025-12-01 |  | Qualcomm
1040104 | UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC | Rel-18 | R5-250149 | 2026-06-01 | 18% | 39% | 2026-06-01 |  | CMCC
1040105 | UE Conformance - NR demodulation performance evolution | Rel-18 | R5-250408 | 2025-12-01 | 41% | 57% | 2025-12-01 |  | China Telecom
1040106 | UE Conformance - Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects | Rel-18 | R5-250766 | 2025-12-01 | 5% | 17% | 2025-12-01 |  | China Telecom
1040107 | UE Conformance - Expanded and improved NR positioning | Rel-18 | R5-250591 | 2026-06-01 | 5.6% | 7% | 2026-06-01 |  | CATT
1040108 | UE Conformance - Further NR mobility enhancements | Rel-18 | R5-250065 | 2025-12-01 | 40% | 55% | 2025-12-01 |  | MediaTek
1040110 | UE Conformance - Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | Rel-18 | R5-250067 | 2025-06-01 | 95% | 95% | 2025-12-01 |  | MediaTek
1040111 | UE Conformance - Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies | Rel-18 | R5-251205 | 2025-06-01 | 30% | 70% | 2025-06-01 |  | Apple
1040112 | UE Conformance - Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR UEs | Rel-18 | R5-251423 | 2025-06-01 | 65% | 65% | 2025-06-01 |  | Apple
1040113 | UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | Rel-18 | R5-250541 | 2025-12-01 | 9% | 20% | 2025-12-01 |  | Qualcomm
1050128 | UE Conformance - Protocol enhancements for Mission Critical Services (MCPTT, MCVideo, MCData) for Rel-17 | Rel-17 | R5-250838 | 2025-12-01 | 16% | 23% | 2025-12-01 |  | Ericsson
1050129 | UE Conformance - Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | Rel-18 | R5-250830 | 2025-12-01 | 67% | 69% | 2025-12-01 |  | China Telecom
1050130 | UE Conformance - NR NTN (non-Terrestrial Networks) enhancements plus CT aspects | Rel-18 | R5-250545 | 2025-12-01 | 6% | 10% | 2025-12-01 |  | Qualcomm
1050131 | UE Conformance - New bands and bandwidth allocation for LTE based 5G terrestrial broadcast | Rel-18 | R5-250539 | 2025-12-01 | 5% | 15% | 2025-12-01 |  | Qualcomm
1050132 | UE Conformance - Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | Rel-18 | R5-250069 | 2025-12-01 | 10% | 35% | 2025-12-01 |  | MediaTek
1050133 | UE Conformance - IMS Data Channel for NG RTC (Real Time Communication) | Rel-18 | R5-250867 | 2025-12-01 | 5% | 21% | 2025-12-01 |  | Huawei
1060075 | UE Conformance - Alignment of eCall over IMS with CEN | Rel-19 | R5-250371 | 2025-12-01 |  | 80% | 2025-06-01 |  | Qualcomm
1060076 | UE Conformance - New NR FDD bands for RedCap (Reduced Capability) in Rel-18 | Rel-18 | R5-251420 | 2025-09-01 |  | 100% | 2025-03-01 | -6 | Ericsson
1060077 | UE Conformance - Enhancements of NR Multicast and Broadcast Services including CT aspects | Rel-18 | R5-250995 | 2025-12-01 |  | 5% | 2025-12-01 |  | CATT