## Slide 1: Discussion of SA2 TU planning for Rel-20
Andy Bennett
SA WG2 Chair

## Slide 2: SA2 Rel-20 TU planning discussion
The main milestones for Rel-20 have mostly been decided
  Rel-20 content defined: June 2025
  5G-Advanced Stage 2 80%: June 2026
  5G-Advanced Stage 2 100%: September 2026
  6G Study 100%: December 2026 or March 2027 (TBD)
The focus of SA2 TU planning should be on the period March 2025 – September 2026
  This covers the time from the earliest possible existence of SA-approved Rel-20 Study or Work Items until the Stage 2 100% complete deadline
A possible timeline for 5G-Advanced topics is shown on the next slide
  It includes an interim deadline for completion of Rel-20 5G Advanced studies in February 2026

## Slide 3: Potential 5G Advanced timeline in Rel-20
It is important to note that any 5G Advanced study items approved by SA in June would have just 4 meetings until the suggested SA2 study completion target of February 2026
  It is important then that larger study + normative items will need to be approved by SA in March
The study completion target is required to ensure sufficient number of meetings to complete the normative work (and even so, only gives 3 meetings for this)
Stage 2 100% completion is intended to mean that there are no exceptions
  This is likely to be a challenge for anything more than a small/medium sized study + work item
 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Meetings | SA#106 | SA2 ad hoc | SA2#167 | SA#107 | SA2#168 | SA2#169 | SA#108 |  | SA2#170 | SA#109 | SA2#171 | SA2#172 | SA#110 | TBD | SA2#173 | SA#111 | SA2#174 | SA2#175 | SA#112 |  | SA2#176 | SA#113 | SA2#177 | SA2#178 | SA#114
Rel-19 Milestones | Stage 2 100% |  |  |  |  |  |  |  |  | Stage 3 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rel-20 milestones and events | 5GA WS |  |  | 6G WS Some SA2 5GA content |  |  | 5GA Stage 1 100% Rel-20 Content defined |  |  |  |  |  |  |  | Rel-20 5GA study 100% | 6G FS Stage 1 100% |  |  | 5GA Stage 2 80% |  |  | 5GA Stage 2 100% |  |  | 6G Study 100% (TBC)
5GA timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Preparation Phase |  |  | #1 |  | #2 | #3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Study Phase |  |  |  |  | #1 | #2 |  |  | #3 |  | #4 | #5 |  |  | #6 |  |  |  |  |  |  |  |  |  | 
Normative phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | #1 | #2 |  |  | #3 |  |  |  | 
Maintenance phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | #1 | #2 | 

## Slide 4: Potential 6G timeline in Rel-20
This shows the meetings available for the 6G study work
The timeline extends beyond when the 5G-Advanced work needs to be completed
 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Meetings | SA#106 | SA2 ad hoc | SA2#167 | SA#107 | SA2#168 | SA2#169 | SA#108 |  | SA2#170 | SA#109 | SA2#171 | SA2#172 | SA#110 | TBD | SA2#173 | SA#111 | SA2#174 | SA2#175 | SA#112 |  | SA2#176 | SA#113 | SA2#177 | SA2#178 | SA#114
Rel-19 Milestones | Stage 2 100% |  |  |  |  |  |  |  |  | Stage 3 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rel-20 milestones and events | 5GA WS |  |  | 6G WS Some SA2 5GA content |  |  | 5GA Stage 1 100% Rel-20 Content defined |  |  |  |  |  |  |  | Rel-20 5GA study 100% | 6G FS Stage 1 100% |  |  | 5GA Stage 2 80% |  |  | 5GA Stage 2 100% |  |  | 6G Study 100% (TBC)
6G study timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Preparation Phase |  |  |  |  | #1 | #2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Study Phase |  |  |  |  |  |  |  |  | #1 |  | #2 | #3 |  |  | #4 |  | #5 | #6 |  |  | #7 |  | #8 | #9 | 

## Slide 5: Some comments on the previous slide
The Rel-20 TU’s include “preparation” time, in other words time required to discuss the draft SIDs and WIDs
6 TU’s expected for this Rel-20 preparation in April and May 2025
So the TU budget that can be allocated to Rel-20 5GA and 6G SIDs and WIDs is 156 – 8 = 148 TU’s
For 5G Advanced TU planning the TU estimates included in the approved SIDs should show study and normative TU’s as the same
  Our experience in Rel-19 again indicates that this should be the approach taken

## Slide 6: Some comments on what a TU is
Throughout these capacity planning slides Time Units (TU’s) have been used as the measure, but it is worth pointing out what TU’s actually are
An SA2 meeting is mostly run as three parallel streams
There are typically 4 plenary sessions through the week, including one at the start and one at the end – these are not included in the capacity planning
During Monday to Wednesday 12 sessions are split into 3 parallel streams
  Sessions on Thursday and Friday are for revisions and are not counted for release planning purposes
Thus for capacity planning purposes there are 12 x 3 = 36 Time Units (TU’s)
If any of the 12 sessions do not run as 3 parallel streams then the number of available TU’s is reduced
1 session with a single stream = 3 TU’s

## Slide 7: Implications of the previous slide
Running any topic (eg a 5G Advanced study item or 6G study work) as a single stream is very expensive from a TU point of view
This means it is essential that pre-Rel-20 maintenance, 5G Advanced and 6G topics are scheduled in parallel streams
An example session plan for a meeting in Q3 is shown on the right (for illustration purposes only)
Delegation heads should plan for this when assigning delegates to topics
 | Q3 2025 | Possible example session plan |  |  |  | 
 | Mon | Tue | Wed | Thur | Fri | 
Q0 |  |  |  |  |  | 
Q1 | Opening plenary |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
Q2 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
Q3 |  |  |  | rev | Closing plenary | 
 |  |  |  | rev |  | 
 |  |  |  | rev |  | 
Q4 |  |  | rev | rev |  | 
 |  |  | rev | rev |  | 
 |  |  | rev | rev |  | 
Q5 |  |  | Work plan, etc | Work plan, etc |  | 
 | 3 | 0 | 0 |  |  | 3
 | 3 | 4 | 2 |  |  | 9
 | 1 | 4 | 5 |  |  | 10
 | 2 | 4 | 2 |  |  | 8
 |  |  |  |  |  | 30
 |  | Pre-Rel-19 Maintenance |  |  |  | 
 |  | Rel-19 Maintenance |  |  |  | 
 |  | Rel-20 5GA |  |  |  | 
 |  | Rel-20 6G |  |  |  | 

## Slide 8: Different time split scenarios
There has been discussion of how the TU budget in Rel-20 should be divided between 5G Advanced and 6G
The analysis here looks only at the period from March 2025 to September 2026
Some planning assumptions
  9 ordinary meetings in this period
  148 TU’s available for SI/WI TU budgets (excludes TU’s for SID/WID discussion during meetings)
  5G Advanced studies complete latest by March 2026 (gives 3 meetings for normative work)
  Maximum 2 TU’s per meeting per item for 5G Advanced items
  Study TU’s = Normative TU’s for 5G Advanced items
  Maximum TU’s for a 5G Advanced item = 14 (7 study + 7 normative)

## Slide 9: Different time split scenarios
The following slides show different scenarios for how the TU budgets would look for different percentages allocated between March 2025 and September 2026

## Slide 10: TU split scenarios
The example below shows a TU plan if there was an approximately 50:50 split between 5G Advanced and 6G (between March 2025 and September 2026)
Note that TEI20 (5G Advanced) is accounted separately
 |  |  | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 |  | 2026 |  | 2026 | 2026 | 
 |  | Totals (between March 2025 and September 2026) | Jan #166 AHE | Feb #167 Athens | Apr #168 Goteborg | May #169 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Stage 2 80% complete | Aug #176 EU | Stage 2 100% complete | Oct #177 EU | Nov #178 US | 6G Study complete (TBD)
 | TU count | 324 | 31.5 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 |  | 36 |  | 36 | 36 | 
 | TU's for pre Rel-19 | 29 | 8 | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 |  | 3 | 3 | 
 | TU's for Rel-19 | 62 | 23.5 | 18 | 13 | 13 | 9 | 6 | 6 | 4 | 4 | 4 |  | 3 |  | 3 | 3 | 
 | TU's for Rel-20 (ex TEI20) | 156 | 0 | 3 | 10 | 10 | 15 | 18 | 19 | 21 | 21 | 21 |  | 21 |  | 15 | 15 | 
 | Buffer TU's | 62 | N/A | 10 | 9 | 9 | 6 | 7 | 6 | 6 | 6 | 6 |  | 7 |  | 6 | 6 | 
20.x | Rel-20 maintenance | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 9 | 9 | 
20.x | Rel-20 5GA SIDs/WIDs | 75 |  |  | 6 | 6 | 9 | 9 | 9 | 9 | 9 | 9 |  | 9 |  |  |  | 
20.x | Rel-20 6G SID(s) | 73 |  |  |  |  | 6 | 9 | 10 | 12 | 12 | 12 |  | 12 |  | 15 | 15 | 
20.x | TEI20 | 12 |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  | 2 |  |  |  | 
30.2 | Submissions for TEI20 | 3 |  |  |  | For info | 3 |  |  |  |  |  |  |  |  |  |  | 
30.7 | 5GA SIDs/WIDs for Rel-20 (prep) | 2 |  | 3 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  | 
30.8 | 6G SID(s) for Rel-20 (prep) | 6 |  |  | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 11: TU split scenarios
Shifting 2 TU’s per meeting from 5G Advanced to 6G changes the proportions to around 60% for 6G and 40% for 5G Advanced (excluding TEI20)
 |  |  | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 |  | 2026 |  | 2026 | 2026 | 
 |  | Totals (between March 2025 and September 2026) | Jan #166 AHE | Feb #167 Athens | Apr #168 Goteborg | May #169 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Stage 2 80% complete | Aug #176 EU | Stage 2 100% complete | Oct #177 EU | Nov #178 US | 6G Study complete (TBD)
 | TU count | 324 | 31.5 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 |  | 36 |  | 36 | 36 | 
 | TU's for pre Rel-19 | 29 | 8 | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 |  | 3 | 3 | 
 | TU's for Rel-19 | 62 | 23.5 | 18 | 13 | 13 | 9 | 6 | 6 | 4 | 4 | 4 |  | 3 |  | 3 | 3 | 
 | TU's for Rel-20 (ex TEI20) | 156 | 0 | 3 | 10 | 10 | 15 | 18 | 19 | 21 | 21 | 21 |  | 21 |  | 15 | 15 | 
 | Buffer TU's | 62 | N/A | 10 | 9 | 9 | 6 | 7 | 6 | 6 | 6 | 6 |  | 7 |  | 6 | 6 | 
20.x | Rel-20 maintenance | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 9 | 9 | 
20.x | Rel-20 5GA SIDs/WIDs | 61 |  |  | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 |  | 7 |  |  |  | 
20.x | Rel-20 6G SID(s) | 87 |  |  |  |  | 8 | 11 | 12 | 14 | 14 | 14 |  | 14 |  | 15 | 15 | 
20.x | TEI20 | 12 |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  | 2 |  |  |  | 
30.2 | Submissions for TEI20 | 3 |  |  |  | For info | 3 |  |  |  |  |  |  |  |  |  |  | 
30.7 | 5GA SIDs/WIDs for Rel-20 (prep) | 2 |  | 3 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  | 
30.8 | 6G SID(s) for Rel-20 (prep) | 6 |  |  | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 12: TU split scenarios
On the other hand, shifting 2 TU’s per meeting from 6G 5G Advanced to changes the proportions to around 40% for 6G and 60% for 5G Advanced (excluding TEI20)
 |  |  | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 |  | 2026 |  | 2026 | 2026 | 
 |  | Totals (between March 2025 and September 2026) | Jan #166 AHE | Feb #167 Athens | Apr #168 Goteborg | May #169 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Stage 2 80% complete | Aug #176 EU | Stage 2 100% complete | Oct #177 EU | Nov #178 US | 6G Study complete (TBD)
 | TU count | 324 | 31.5 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 |  | 36 |  | 36 | 36 | 
 | TU's for pre Rel-19 | 29 | 8 | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 |  | 3 | 3 | 
 | TU's for Rel-19 | 62 | 23.5 | 18 | 13 | 13 | 9 | 6 | 6 | 4 | 4 | 4 |  | 3 |  | 3 | 3 | 
 | TU's for Rel-20 (ex TEI20) | 156 | 0 | 3 | 10 | 10 | 15 | 18 | 19 | 21 | 21 | 21 |  | 21 |  | 15 | 15 | 
 | Buffer TU's | 62 | N/A | 10 | 9 | 9 | 6 | 7 | 6 | 6 | 6 | 6 |  | 7 |  | 6 | 6 | 
20.x | Rel-20 maintenance | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  | 9 | 9 | 
20.x | Rel-20 5GA SIDs/WIDs | 89 |  |  | 6 | 6 | 11 | 11 | 11 | 11 | 11 | 11 |  | 11 |  |  |  | 
20.x | Rel-20 6G SID(s) | 59 |  |  |  |  | 4 | 7 | 8 | 10 | 10 | 10 |  | 10 |  | 15 | 15 | 
20.x | TEI20 | 12 |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 |  | 2 |  |  |  | 
30.2 | Submissions for TEI20 | 3 |  |  |  | For info | 3 |  |  |  |  |  |  |  |  |  |  | 
30.7 | 5GA SIDs/WIDs for Rel-20 (prep) | 2 |  | 3 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  | 
30.8 | 6G SID(s) for Rel-20 (prep) | 6 |  |  | 3 | 3 |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 13: Impacts of TU allocation scenarios
TU allocations between March 2025 and September 2026 |  |  |  |  | 
6G:5G Advanced split | TU’s for 6G | TU’s for 6G per meeting | TU’s for 5GA | TU’s for 5GA per meeting | Comments
60:40 | 87 | 8 rising to 14 | 61 | Typically 7 | Would allow 2 large and 5 small 5GA items
50:50 | 73 | 6 rising to 12 | 75 | Typically 9 | Would allow 4 large and 3 small 5GA items
40:60 | 59 | 4 rising to 10 | 89 | Typically 11 | Would allow 6 large and 1 small 5GA items
In addition to the above there are 12 TU’s planned for TEI20 items (5G Advanced) |  |  |  |  | 
Note 1: A large item is assumed to be 12 – 14 TU’s and a small item is assumed to be 7 TU’s (total of study + normative)
Note 2: Large items will need to start in Q2 to allow sufficient meetings to schedule the work