## Slide 1: SA WG5 Rel-20 work planning
Zou Lan, SA5 Chair, Huawei

## Slide 2: SA5 Rel-20 capacity summary
SA5 capacity :
  Max TUs : 124 (OAM) / 80 (Charging)
    Additional buffer TUs: 61(OAM)/40(CH)
  Max number of SIs/WIs: 10~15 (OAM) / 6~10 (Charging)
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 12~8 TU
  Adopt 1:1 on TU allocation portion of 5GA part/6G part in Rel-20
Assumptions
  Start: Jun 2025, End: Mar 2027 (21 months)
  One track for OAM and One track for Charging
  Number of meetings: 10
  Expected total TUs per meeting (for all releases)(with Q5 included): 18.5 (OAM) / 12 (Charging)
  Total TUs (for all releases): 185 (OAM) / 120 (Charging)
  TUs for maintenance of past releases: 35 (OAM) / 20 (Charging)

## Slide 3
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA SID definition
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
RAN1
RAN Completion (RAN2/3/4core)
#116
RAN4 C.def.
RAN4 Perf
RP Content def.
2025
2026
2027
5GA ASN.1 & Open APIs
St.3 SID def. TBD
Release 20 5GA timeline
Note: All starting dates are indicative
Workshops
5GA RAN & SA
RAN WG SID def.
St.2 SID def.
Release 20 5GA timeline with SA5
SA5 (5GA OAM/CH Prime) management St.+Norm Stage1/2/3
OAM/CH Prime
SID def.
①
②
SA5 (OAM/CH Stage 2/Stage3 supporting) SA&RAN (SA5)
OAM/CH Supporting
SID def.(if needed)
OAM/CH prime feature:
Some WIDs and All prime SIDs to be agreed no later than May.2025(SA5#161) and target for approval in Jun.2025 (SA#108).
It’s recommended to take max 6~9 months for study phase if normative work is planned for Rel-20.
Start of Rel-20 prime study: right after Jun.2025 (SA#108/SA5#161)
End of Rel-20 prime normative:
Dec.2026 (SA#114/SA5#170)
OAM/CH supporting to network feature(SA5 is ready to support network features pending the availability of inputs from other WGs)
All supporting studies/normative WIDs to be agreed no later than May.2026 (SA5#167) and target for approval in Jun.2026 (SA#112).
Start of Rel-20 supporting study (if needed): right after Jun.2026 (SA#112/SA5#167)
End of Rel-20 supporting normative: Mar.2027 (SA#115/SA5#171)
①
②
(updated SA5 based on SP-250420)
Workshops 5GA SA5
3GPP SA5
Timeline

## Slide 4: SA5 Rel-20 5G-A candidate topics and TU budget
1. Total TU number for 5GA is 62 TU.
2. See S5-252442 for the consolidated list.
NOTE: A Topic may result in one or more SIDs.
No. | Rel-20 OAM Prime Topics | TU | Rel-20 OAM Support Topics | TU | Rel-20 CH Prime Topics | TU | Rel-20 CH Support Topics | TU
1 | Intent driven management enhancement | 8 | AdNRM | 4 |  |  | Charging Aspects of CAPIF | 1
2 | AIML management enhancement | 8 | PM/KPI/Trace/MDT/QoE/SON enhancement | 5 |  |  |  | 
3 | NDT enhancement | 4 | NWDAFM | 2 |  |  |  | 
4 | SBMA enhancement | 8 | XR management | 2 |  |  |  | 
5 | Energy efficiency enhancement | 5 |  |  |  |  |  | 
6 | MDA enhancement | 4 |  |  |  |  |  | 
7 | Data Management enhancement | 4 |  |  |  |  |  | 
8 | MExpo enhancement | 4 |  |  |  |  |  | 
9 | CCL enhancement | 4 |  |  |  |  |  | 

## Slide 5
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
Workshop 6G TSGs
CT & St. 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop SA1 on IMT-2030 use cases
#116
SA1 6G Study(ies)
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/5/6 6G SID def. TBD
RAN2/3/4 6G Study(ies)
Release 20 (FS) 6G timeline
or
TBD
Note: All starting dates are indicative
SA3/4/5/6 6G Study(ies)TBD
Release 20 6G timeline with SA5
SA5 6G SID def.
SA5 6G Study(ies)
3GPP SA5
Timeline
Workshops 6G SA5
SA5 6G SI Rel-20:
Start of Rel-20 study: Sep.2025 (SA#109/SA5#163)
End of Rel-20 study: Mar.2027 (SA#115/SA5#171) (end time may be adjusted according to overall 3GPP time plan)
(updated SA5 based on SP-250420)

## Slide 6: Rel-20 6G management features workshop
Scope: 6G related new management features including OAM/CH prime features and management support to new network features.
  Workshop#1: Online presentation on potential topics and directions (4 TUs)
    Jun 25, 2025 13:00-15:00 UTC
    Jun 26, 2025 13:00-15:00 UTC
Agenda
  Opening of the workshop
  Contributions from 3GPP member companies
    Contributions on potential Rel-20 management use cases and requirements, etc.
    Up to one contribution per company
  Chairman's summary and open discussion
  Closing of the workshop
  Please feel free to contact Chair if you plan to provide presentation, and it will be helpful to make better planning for this activity.

## Slide 7: SA5 Rel-20 6G Content Definition steps
Following SA content definition steps guidance in SP-241738 :
Discussion and Guidance for Rel-20 6G Scope: The content proposals for SA5 Rel-20 6G being discussed during the SA5 Rel-20 6G Workshop in June.
  The potential topics should be categorized by prime and supporting topics.
  Maximum 62 TUs available for OAM, Maximum 40 TUs available for CH
  The study of 6G should start with 1 study item for OAM and 1 study item for CH.
  Moderator:
    OAM Moderator: Wang Zhao Ning (China Unicom)
    Charging Moderator: Mo Zhi wei (China Telecom)
Moderated Email Discussions: Moderated Email Discussions to develop SID details corresponding to the Rel-20 6G topics identified in the prime/supporting feature list. The focus will be on defining technical objectives, work tasks, and estimated budgets for each task. These discussions are planned to start after SA5#161.
Approval of Selected Rel-20 6G SID: Companies may submit the SID to SA5#162 for WG agreement. SA5 targets to submit SIs to SA#109 for approval. Ideally, the Rel-20 6G SID for approval at this step should have no dependencies on Rel-20 work in RAN and SA. SID for approval should follow the guidance on Rapporteurship (see SP-230746).
WG commences Rel-20 6G SI Work: After the approval of the SID at SA#109, SA5 will start working on the approved SID during Q4 meetings.

## Slide 8: Thank you!

## Slide 9: SA5 calendar with OAM TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (8:00~8:55) (If needed) | NA | Breakout (opt.) | Breakout (opt.) | Breakout (opt.) | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | Revision session | 
Assumption:
Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 18.5 TUs

## Slide 10: TU Budget for SA5 OAM
Assumptions for SA5 OAM :
  6 ordinary meeting per year.
  Rel-20 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  OAM revision sessions normally planned to be in Thursday Q4 and Q5 (initial assump.)
  Statistics:
    1 parallel (OAM) stream per session => 18.5 TUs per meeting (incl. 2 TUs as buffer) = 185
    Assume Maintenance + Buffer = 33% => ~ 61 TU
    Resulting total TUs avail. f. SI/WI: 10 meetings x 18.5 sessions = 185 TU minus 61 => 124 TU
    With 15 SI/WI => Average 8 TU per SI/WI (0.8/meeting).

## Slide 11: SA5 Rel-20 OAM TU planning (Jan.2025~Mar.2027)
 | Maintenance+R18/R19 | R19 | R20 | R21 preparation | Buffer (revision session)
Jan.2025~Jun.2025: SA5#159~#161 (3 meetings) (5GA OAM/CH Prime SID def.) | 1.5 TU*3 meetings= 4.5 TU (CRs) | 13 TU*3 meetings= 39 TU | 2 TU*3 meetings = 6 TU | NA | 2 TU*3=6 TU
Jun.2025~Sep.2025: SA5#162 (1 meeting) (Rel-19 stage-3 freeze, first meeting for Rel-20 6G OAM/CH SID def.) | 1.5 TU (CRs) | 13 TU | 2 TU | NA | 2 TU
Oct.2025~Dec.2026: SA5#163~#169 (7 meetings) (OAM/CH Prime stage-3 freeze) SA5#165~#167 (3 meetings) (5GA OAM/CH Supporting SID def.) | 2.5 TU*7 meetings= 17.5 TU (CRs) | NA | 14 TU*7 meetings = 98 TU | NA | 2 TU*7=14 TU
Jan. 2027~Mar.2027: SA5#170~#171 (2 meetings) (5GA OAM/CH Supporting stage-3 freeze) (6G study completion) | 1.5 TU*2 meetings = 3 TU (CRs) | NA | 12 TU*2 meetings = 24 TU | 3 TU*2 meetings = 6 TU | 2 TU*2=4 TU
Total=185 TU | 22 TU | 13 TU | 124 TU | 6TU | 20 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 18.5 TUs
  Buffer = 2 TUs
  OAM = 16.5 TUs
    Maintenance CRs + remaining Rel-19 work (TU allocation will decrease over time )
    Rel-21 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-20 SIDs / WIDs
Total TUs allocated to Rel-20 SIDs / WIDs = 124 TUs

## Slide 12: SA5 calendar with CH TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (8:00~8:55) (If needed) |  | Breakout (opt.) | Breakout (opt.) |  | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Offline session | CH Closing | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Offline session | CH Closing | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Social evening | Offline session (Opt.) | CH Closing(Opt.) | 
Assumption:
Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary and offline TUs) = 12 TUs

## Slide 13: TU Budget for SA5 CH
Assumptions for SA5 CH :
  6 ordinary meeting per year.
  Rel-20 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  CH revision sessions normally planned to be in Thursday Q1 and Q2 (initial assump.),CH closing plenary planned to be in Thursday Q3 and Q4.
  Detail statistics:
    1 (CH) stream per session => 12 TUs per meeting (incl. 2 TUs as buffer) = 120
    Assume Maintenance + Buffer = 33% as in SA2 => ~ 40 TU
    Resulting total TUs avail. f. SI/WI: 10 meetings x 10 sessions = 120 TU minus 40 => 80 TU
    With 10 SI/WI => Average 8 TU per SI/WI (0.8/meeting).
  Note: TU capacity for CH could be extended if more topics are proposed.

## Slide 14: SA5 Rel-20 CH TU planning (Jan.2025~Mar.2027)
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 12 TUs
  Buffer = 2 TUs
  CH = 10 TUs
    Maintenance CRs + remaining Rel-19 work (TU allocation will decrease over time )
    Rel-21 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-20 SIDs / WIDs
Total TUs allocated to Rel-20 SIDs / WIDs = 80 TUs
 | Maintenance+R18/R19 | R19 | R20 | R21 preparation | Buffer (revision session)
Jan.2025~Jun.2025: SA5#159~#161 (3 meetings) (5GA OAM/CH Prime SID def.) | 1.5 TU*3 meetings= 4.5 TU (CRs) | 7.5 TU*3 meetings= 22.5 TU | 1 TU*3 meetings = 3 TU | NA | 2 TU*3=6 TU
Jun.2025~Sep.2025: SA5#162 (1 meeting) (Rel-19 stage-3 freeze, first meeting for Rel-20 6G OAM/CH SID def.) | 1.5 TU (CRs) | 6.5 TU | 2 TU | NA | 2 TU
Oct.2025~Dec.2026: SA5#163~#169 (7 meetings) (OAM/CH Prime stage-3 freeze) SA5#165~#167 (3 meetings) (5GA OAM/CH Supporting SID def.) | 1.5 TU*2 meetings+ 1 TU*5 meetings = 8 TU (CRs) | NA | 8.5 TU*2 meetings + 9 TU *5 meetings = 62 TU | NA | 2 TU*2=4 TU
Jan. 2027~Mar.2027: SA5#170~#171 (2 meetings) (5GA OAM/CH Supporting stage-3 freeze) (6G study completion) | 1 TU*2 meetings = 2 TU (CRs) | NA | 8 TU*2 meetings = 16 TU | 1 TU*2 meetings = 2 TU | 2 TU*2=4 TU
Total=120 TU | 11.5 TU | 6.5 TU | 80 TU | 2 TU | 20 TU