## Slide 1
Puneet Jain
SA Chair
SA Rel-19 Content Definition : Next Steps

## Slide 2: Rel-19 Content Definition Process (From SA#100)
TSG#101
TSG#102
TSG#103
TSG#104
TSG#105
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#99
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2026
Stage-3 (CT & SA)
Stage-2 Study/Work Phase
Rel-19 Content Approval
SA Rel-19
Workshop
TSG#100
June
2023
Now
100%
SA1 Stage-1 80%
ASN.1 / Open API
Stage-1 Freeze
Selected Rel-19 SID/WID Approval
Rel-19 Final Package Approval
Stage-2 Freeze
Stage-3 Freeze
Rel-19 complete
MED
Moderated Email Discussions
MED
WG starts working on Rel-19 SID/WID approved at SA#101
Rel-19 Scope Discussion / Guidance to WG
Source: SP-230720
TSG SA Meeting #SP-101, 11 - 15 Sep 2023, Bengaluru, India

## Slide 3: SA2 Rel-19 candidate topics (from SA#100)
Source: SP-230759
S.No. | Rel-19 Core Topics | Rel-19 Miscellaneous Topics
1 | Satellite Architecture Enhancements | SBA framework enhancement / 5GS enhancement for Cloud Native Deployment
2 | XRM Enhancements and Metaverse | Network Slicing
3 | AI/ML Enhancements | 5G SA Roaming services and Intermediaries (GSMA 5MRR request)
4 | Multi-access (Dual 3GPP + ATSSS Enh) | Traffic Management (Monitoring + MASQUE + QUIC)
5 | Integrated Sensing and Communication | Enhancements in handling of Radio Capabilities
6 | Ambient IoT | 5GC enhancements for IP routing
7 | Energy Efficiency / Energy Saving as a Service | Enhancing Emergency Services when Zero CS network coverage
8 | IMS and NG_RTC enhancements | NPN enhancements
9 | Edge Computing Enhancements | Ranging Phase 2
10 | Proximity Services enhancements | LCS enhancements
11 | TSC/URLLC/TRS enhancements | Mobile VPN
12 | Network Sharing | Architecture Enhancements for Energy Utilities
13 | User identities + identification of device behind RG/AP | eUEPO (UE Policy) Enhancements
14 | 5G Femto | Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services
15 | UAS enhancements | RVAS (Roaming Value-Added Services)
16 | VMR Enhancements | 
17 | UPEAS Enhancements | 
TSG SA Meeting #SP-101, 11 - 15 Sep 2023, Bengaluru, India

## Slide 4: Guidance to SA2 on Rel-19 work planning
All “core” topics (see SP-230759) will have moderated discussion during Q3 2023. The list of work task under “Brief Description and Key Objectives” in SP-230759 serves as a starting point for the moderated discussion and can be updated during the process.
It is proposed to endorse the following list of “core” topics (see SP-230759) as candidates in SA#100 for which SA2 should strive to submit SID in SA#101 (as per normal consensus). Remaining topics may also be submitted to SA#101 for approval if agreed. If SA2 cannot come to an agreement on these items for SA#101 then they can come for approval at SA#102.
  Satellite Access
  Ambient IoT
  AI/ML enhancements
  Multi-access (Dual 3GPP + ATSSS Enh)
  Energy Efficiency / Energy Saving as a Service
  XRM and Metaverse
  IMS and NG_RTC enhancements
If approval of the resulting SIDs is possible in SA#101 then work can start on them in Q4 2023.
SA2 should not allocate more than 50% of over all Rel-19 TU budget (for selected SIDs shown in bullet #2).
The remaining “core” topics (not covered in bullet #2) will also have moderated discussion during Q3, 2023 and any resulting SIDs are targeted for approval in SA#102.
The miscellaneous topics (see SP-230759) will be candidate for moderated discussion during Q4 2023.
The final decision on the complete set of SIDs for Rel-19 (and the work tasks and TU budget of each SID) will be taken in SA#102.
Source: SP-230765
TSG SA Meeting #SP-101, 11 - 15 Sep 2023, Bengaluru, India

## Slide 5: SA2 Technically Endorsed Rel-19 SIDs
SA2#158 has allocated considerable time and resources for discussion on following topics and endorsed SIDs for further work -
  Satellite Access - Julius
  Ambient IoT - Tricci
  AI/ML enhancements – Haris
  Multi-access (Dual 3GPP + ATSSS Enh) - Krisztian
  Energy Efficiency / Energy Saving as a Service - Jungshin
  XRM and Metaverse - Devaki
  IMS and NG_RTC enhancements - Michele
SA#101 will further discussed the SIDs submitted by the moderator. Goal is to approve the SIDs for inclusion to Rel-19 content. Work can be scheduled by SA2 during Q4. We may have drafting sessions, if needed.
Objective is to allocate ~50% (or less) of available SA2 Rel-19 TU budget.
No blanket/placeholders kind of WT that has either no TU estimates, or unrealistic/unknown TU estimates in due to the RAN dependencies. WT should have clear and realistic TU estimates.
There is no downscoping/deprioitization of WT from these SIDs. WT that are removed from SA#101 can be added in SA#102 to the SA#101 approved SIDs.
TSG SA Meeting #SP-101, 11 - 15 Sep 2023, Bengaluru, India

## Slide 6: SIDs not Endorsed and had limited discussion at SA2#158
SA2#158 has good discussion on following topics but could not technically endorsed anything -
  Integrated Sensing and Communication
  Edge Computing Enhancements
  Proximity Services enhancements
  TSC/URLLC/TRS enhancements
  Network Sharing
  User identities + identification of device behind RG/AP
  5G Femto
  UAS enhancements
  VMR Enhancements
  UPEAS Enhancements
SA#101 will further discussed the SIDs submitted by the moderator. Goal is to see if we can create a baseline version for further discussion at SA2. Stretch goal will be to approve one or more of these SIDs.
Objective is to allocate ~50% (or less) of available SA2 Rel-19 TU budget.
No blanket/placeholders kind of WT that has either no TU estimates, or unrealistic/unknown TU estimates in due to the RAN dependencies. WT should have clear and realistic TU estimates.
There is no downscoping of WT from these SIDs. More WT can be added in SA#102 to the SA#101 approved SIDs.
  For further discussion: whether the WT can divided into 2 categories – a) WT can be brought back at SA#102; b) WT that are deprioritized and will not come back at next meeting.
TSG SA Meeting #SP-101, 11 - 15 Sep 2023, Bengaluru, India

## Slide 7: Topics for which no Moderated Email Discussion (MED) occurred in Q3
These encompass 15 miscellaneous Rel-19 topics, as indicated in the slide #2.
If there are items that have garnered increased interest, they may be discussed and added to the miscellaneous list.
A select number of items from miscellaneous list will be designated for Moderated Email Discussion (MED) in Q4. A specific cap "X" will be determined at SA#101 for the number of miscellaneous items eligible for MED in Q4, “X” is expected to be a low single-digit number.
SA2 will undertake MED on these “X” topics in Q4 and submit SA2 agreed SID for approval at SA#102.
TSG SA Meeting #SP-101, 11 - 15 Sep 2023, Bengaluru, India