## Slide 1: FS_RAILSS Status Update Study on Supporting of Railway Smart Station Services
Andrew Min-gyu Han
Hansung University
FS_RAILSS Rapporteur
3GPP TSG-SA WG1 Meeting #92e
Electronic Meeting, 10 - 19 November 2020
Notes: 1

## Slide 2: FS_RAILSS Progress
Progress made at this meeting
  Emergency use case is added
Work/Study Item Completion: 15%
Controversial issues
  None
Notes: 1

## Slide 3: FS_RAILSS Planning
Planning for subsequent meetings
  SA1#92+1 (Feb 2021): 35%
    Define use cases, deduce requirements and analysis their gaps
  SA1#92+2 (May 2021): 70%
    Define use cases, deduce requirements and analysis their gaps
  SA1#92+3 (Aug 2021): 100%
    Evaluate the requirements and analysis their gaps
Notes: 1

## Slide 4: Work plan between meetings
Email discussion
  Define use cases, discuss on potential requirements and analysis their gaps
Telephone conference
  TBD
Notes: 1

## Slide 5: FS_RAILSS Completion Date
Current expected completion dates:
  For information: SA#92 (06/2021)
  For approval: SA#93 (09/2021)
Have these dates been changed at this meeting? yes
  If yes, previous target completion dates:
    For information: <06/2020> SA#88
    For approval: <09/2020> SA#89
Notes: 1

## Slide 6: FS_RAILSS History
This WI has been approved at SA#85
  Approved WID is in tdoc SP-190838
History of completion rates
  SA1#88-1 (08/2019): 0%
  SA1#92-2 (11/2020): 15%
Notes: 1