## Slide 1: FS_MUSIM and MUSIM Status Report
Sašo Stojanovski
Intel Corporation

## Slide 2: FS_MUSIM Status at SA#91-e
WI Code | Work Item Title | WP | Target Date | WID#
FS_MUSIM | Study on system enabler for Multi-USIM devices | 90% > 95% | Mar, 21 | SP-200091
Progress since SA#90-e:
  4 pCRs agreed related to KI#1 and KI#3
  Conclusions agreed on
    Use of Service Request + TAU for support of the NAS Busy procedure and NAS Leaving procedure for EPS
    Paging Cause applied only for UEs operating in MUSIM mode
    Clarification on derivation of Paging Cause
    Clean-up of Editor’s notes
  LS sent to RAN2 on assumptions for Paging Cause
  RAN impacts and dependencies:
  Several potential MUSIM enablers still depend on progress in RAN WGs, e.g.:
    RRC-based Busy Indication, enabling paging reception for 5GS, leaving procedure for 5GS
Next steps:
  Conclude items with RAN dependency as part of normative work

## Slide 3: MUSIM Status at SA#91-e
Progress since SA#90-e:
  WID update agreed to remove an Editor’s note related to KI#2
  2 CRs agreed to TS 23.401 (introduction of Paging Cause, Leaving procedure)
  1 CR agreed to TS 23.501 (introduction of Paging Cause)
  1 CR agreed to TS 23.502 (introduction of Paging Cause)
  1 CR agreed to TS 23.228 (use of PPD for Paging Cause)
  RAN impacts and dependencies:
  Still awaiting RAN feedback on the following
    RRC-based Busy Indication, enabling paging reception for 5GS, RRC-based leaving for 5GS
  SA3 impacts:
  Check SA2 working assumptions against SA3 study conclusions
Next steps:
  Progress CRs for the uncovered functionality (e.g. functional description, capability exchange, busy procedure, etc.)
  Progress CRs as per the feedback from other WGs (e.g. RAN2 on RRC-based leaving and/or busy procedure)
WI Code | Work Item Title | WP | Target Date | WID#
MUSIM | System enablers for Multi-USIM devices | 0% > 20% | June, 21 | SP-200978

## Slide 4: FS_MUSIM/MUSIM status after SA2#143E
  RAN impacts and dependencies:
  All three key issues have remaining RAN dependency that requires RAN coordination:
    KI#1: RRC-based Busy Indication for 5GS
    KI#2: Enabling of paging reception for 5GS
    KI#3: RRC-based leaving for 5GS
  A final decision expected from RAN plenary on “no-EUTRA impact”.
  SA3 dependencies:
  Check SA2 working assumptions against SA3 study conclusions.
Contentious Issue:
  None.
Focus for the Next Meeting (SA2#144E):
  Ahead of SA2#144E: Organize a conference call to:
    organize normative work (e.g. identify impacted clauses, call for volunteers, etc.).
  During SA2#144E:
    Focus on normative work on concluded items.
    Conclude the study on the remaining open items with RAN dependency
    No new solutions / concepts are accepted
Overall Plan:
  Normative work expected to be completed by SA#92
Risks:
  Further RAN progress required in 2021Q2 to allow for conclusion of items with RAN dependencies.
  SA3 progress could impact the agreed solutions in SA2.