## Slide 1: FS_VMR_Ph2 Status Report
Qualcomm Incorporated
S2-2405637

## Slide 2: FS_VMR_Ph2 status after SA2#162 (1/2)
General
  TR 23.700-06 v.0.3.0 was created based on approved contributions.
  12 contributions agreed (including new solution proposals, and interim conclusions).
  1 LS to RAN3 (cc RAN2) was agreed.
  1.0 TU used and 1.0 TU left for the Study Phase.
11 new solutions documented addressing Key Issues#1 and #3 to #6 (of the agreed KIs):
  Key Issue #1: Architectural enhancements for the support of a MWAB
  Key Issue #2: Authorization of a MWAB and configuration of MWAB
  Key Issue #3: Control of UE's access to 5GS via a wireless access backhaul
  Key Issue #4: Efficient mobility and service continuity when served by MWAB
  Key Issue #5: Support of location services for UEs when MWAB(s) is involved
  Key Issue #6: Support of Emergency services for UEs via a MWAB
1 Interim conclusion on KI#2 above was agreed (S2-2405787)
  RAN impacts and dependencies:
  1 LS (S2-2405822) to RAN3 and cc RAN2 was agreed, with specific questions and invitation for TR solutions reviews.
Other WG dependencies
  Charging support is expected to be handled by SA5, and security to be handled by SA3.
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR_Ph2 | Study on Vehicle Mounted Relays Phase 2 | 40% > 75% | Jun, 24 | SP-240493

## Slide 3: FS_VMR_Ph2 status after SA2#162 (2/2)
Contentious Issue:
  None.
Focus of the Next Meeting (SA2#163):
  KI evaluation and conclusions - based on NWM discussion of the principles.
  WID draft discussion.
  Solution updates and EN resolutions.
Overall Plan:
  SA2#160-Ah-Hoc-e Jan’24: 0.5 TU (TR skeleton, Scope, Assumptions, Key Issues)
  SA2#161 (Athens) Feb’24: 0.5 TU (New KIs, KI updates; New solutions)
  SA2#162 (China) Apr’24: 1.0 TU (last chance for new solutions; solution updates, initial evaluations/Start coord with RAN)
  SA2#163 (Jeju) May’24: 1.0 TU (Solution updates; evaluations; conclusions, send TR for approval; WID approval – Send TR to RAN for review)
  SA2#164 (EU) Aug’24: 0.5 TU ( Normative work, coordination with RAN – If needed, finalize remaining TR conclusions)
  SA2#165 (India) Oct’24: 1.0 TU (Normative work, coordination with RAN)
  SA2#166 (Orlando) Nov’24: 1 TU (Normative work, coordination with RAN)
 |  |  |  | Jan, 24 | Feb.24 | Apr. 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24 | 
SID/WID | Study TU | Normative TU | Total TU | #160 | #161 | #162 | #163 | #164 | #165 | #166 | Total used TU
FS_VMR_Ph2 | 3 | 2.5 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 1 | 1 | 5.5

## Slide 4: FS_VMR_Ph2 status at SA#104
Progress since SA#103:
  TR 23.700-06 v.0.3.0 was created based on approved contributions.
  12 contributions to the TR were agreed (including new solutions, and interim conclusions).
  1 LS to RAN3 (cc RAN2) was agreed.
  1 TU used and 1.0 TU left for the Study Phase.
Impacts and dependencies on other WGs:
  RAN impacts or dependencies identified for Key Issue #1, #2, #3, #4, #5
Next steps:
  Conclude KI#1 to #6.
  WID discussion and approval.
  Update solution principles based on RAN feedbacks.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 06/03/2024 | 40% | SP-240493 | 75% |