## Slide 1: AIML_CN Status Report
vivo (Rapporteur) MediaTek Inc. (Rapporteur)

## Slide 2: AIML_CN status after SA#109
General
  94 papers were submitted, 1 LS out, 17 agreed, 3 merged.
  KI#1: 1 LS out on indication of LMF-based AIML Positioning, 4 agreed, 3 merged
  KI#2: 9 agreed, KI#3 2 agreed, KI#4 2 agreed.
  Impacts and dependence with other WGs:
  consent/privacy aspects resolved (in coordination with SA3).
Controversial issues
  None
Next Steps
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 25/03/2025 | 98 | SP-240991 | 100 | 
1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 2024/6/6 | 100% | SP-241936 | 100% | 

## Slide 3: AIML_CN status after SA2#172 (1/2)
General
  49 papers were submitted, 1 LS out, 4 agreed, 3 merged.
  KI#1: 1 LS out on indication of LMF-based AIML Positioning, 4 agreed, 3 merged
  Impacts and dependence with other WGs:
  consent/privacy aspects resolved (in coordination with SA3).
Controversial issues
  None
Next Steps
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 25/03/2025 | 98 | SP-240991 | 100 | 
1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 2024/6/6 | 100% | SP-241936 | 100% | 

## Slide 4: AIML_CN status after SA2#172 (2/2)
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR 23.700-84 TR Skeleton, Arch Assumptions, scope, Initial KIs use case(s)
SA2#161 | Feb 2024 | 1.5 | 1.5 | Final KI/use case updates + Initial Solutions, Attempt to close new Key Issue and new UC.
SA2#162* | Apr 2024 | 1 | 1 | Solution updates and new solution(s)
SA2#163 | May 2024 | 1 | 1 | Final solution updates and final Evaluations + Conclusions
SA2#164 | Aug 2024 | 1.5 | 1 | Normative work per KI conclusion
SA2#165 | Oct 2024 | 1.5 | 1.5 | Normative work per KI conclusion
SA2#166 | Nov 2024 | 1.5 | 1.5 | Normative work per KI conclusion
SA2#166—Ad Hoc-e | Jan 2025 | 2 | 2 | Normative work per KI conclusion (exception)
SA2#167 | Feb 2025 | 2 | 2 | Normative work per KI conclusion (exception)
SA2#168 | Apr 2025 | 1 | 1 | Maintenance
SA2#169 | May 2025 | 1 | 1 | Maintenance
SA2#170 | Aug 2025 | 0.5 | 0.5 | Maintenance
SA2#171 | Oct 2025 | 0.5 | 0.5 | Maintenance
SA2#172 | Nov 2025 | 0.5 | 0.5 | Maintenance
SA2#173 | Feb 2026 | TBD |  | Maintenance
Total 12 TUs
  4 TUs for Study Phase
  8 TUs for Normative Work (4 for exception)

## Slide 5: Substantial Issues
Issue # | Description | Identified in | Resolution | Resolved in
1 | Whether the LCS privacy check and/or User Consent check is needed for AI positioning? | SA2#166 | Align with the agreement of SA#3 | SA2#170

## Slide 6: Annex
Status report for SA2#167/168/169/170/171

## Slide 7: AIML_CN status after SA2#171 (1/2)
General
  45 papers were submitted, 13 agreed, 5 merged.
  KI#2: 9 agreed, KI#3 2 agreed, KI#4 2 agreed.
  Impacts and dependence with other WGs:
  consent/privacy aspects resolved (in coordination with SA3).
Controversial issues
  None
Next Steps
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 25/03/2025 | 98 | SP-240991 | 99 | 
1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 2024/6/6 | 100% | SP-241936 | 100% | 
Notes: KI#1:
KI#2: ;
KI#3: .
General: ;

## Slide 8: AIML_CN status after SA2#170 (1/2)
General
  71 papers were submitted, 2 LS out, 7 agreed, 5 merged.
  KI#1: 2 LS out, 7 agreed, 5 merged
    LS out to CT3 to answer the questions raised by CT3 .
    LS out to RAN2 to asks RAN2 to provide feedback on whether the ground truth data and its related data (e.g., quality indicator of ground truth data, time stamp of ground truth data) can be provided from UE to the LMF by reusing the LPP protocol.
  Impacts and dependence with other WGs:
  consent/privacy aspects resolved (in coordination with SA3).
Controversial issues
  None
Next Steps
  Maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 25/03/2025 | 98 | SP-240991 | 99 | 
1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 2024/6/6 | 100% | SP-241936 | 100% | 
Notes: KI#1:
KI#2: ;
KI#3: .
General: ;

## Slide 9: AIML_CN status after SA2#169 (1/2)
General
  85 papers were submitted, 9 agreed, 1 LS out, 5 postponed.
  KI#1: 2 agreed, 5 postponed.
  KI#4: 1 LS out, 7 agreed.
  Impacts and dependence with other WGs:
  Impact SA3: consent/privacy aspects need to be resolved, in coordination with SA3.
Controversial issues
  None
Next Steps
  Maintenance
  KI#1 to align with SA3 for user consent and decide on use of privacy profile
  KI#1/3/4 to answer CT3 LS IN
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 25/03/2025 | 98 | SP-240991 | 99 | 
1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 2024/6/6 | 100% | SP-241936 | 100% | 
Notes: KI#1:
KI#2: ;
KI#3: .
General: ;

## Slide 10: AIML_CN status after SA2#168 (1/2)
General
  91 papers were submitted, 10 agreed, 1 LS out, 1 endorsed, 2 merged, 4 postponed.
  KI#1: 2 agreed, 1 LS out, 1 endorsed, 1 merged, 4 postponed
    LS out to answer SA WG 5, about the mechanisms to collect AI/ML positioning relevant data.
  KI#2: 7 agreed, 1 merged
  KI#3: 1 agreed
  Impacts and dependence with other WGs:
  Impact SA3: consent/privacy aspects need to be resolved, in coordination with SA3
Controversial issues
  None
Next Steps
  Maintenance
  KI#1 to align with SA3 based on SA3 feedback (for user consent), align with SA5 LS IN (for OAM model training), align with RAN (for detailed reference)
  KI#4 to answer CT4 LS IN
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 25/03/2025 | 98 | SP-240991 | 99 | 
Notes: KI#1: 1 LS Out, 1 endorsed, 2 agreed, 1 merged, 4 postponed;
KI#2: 7 agreed, 1 merged;
KI#3: 1 agreed.
General: 91 submitted, 10 agreed, 1 LS out, 1 endorsed, 1 merged, 4 postponed;

## Slide 11: AIML_CN status after SA2#167 (1/2)
General
  116 papers were submitted, 26 were agreed, 1 were approved, 8 were merged, 4 were postponed.
  KI#1: 11 were agreed, 1 were approved, 2 were merged, 3 were postponed
  KI#2: 12 were agreed, 5 were merged, 1 were postponed
  KI#3: 2 were agreed, 1 merged
  KI#4: 1 were agreed
  Impacts and dependence with other WGs:
  RAN Impact on KI#1
    Any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs and coordination with RAN is needed.
    Feedback from RAN1/RAN2/RAN3 for the current progress of case 2b and case 3b to handle/specify the corresponding procedures in SA2 e.g. data collection from RAN and/or UE.
  Impact SA3: consent/privacy aspects need to be resolved, in coordination with SA3
Controversial issues
  None
Next Steps
  Maintenance
  KI#1 to align with RAN and SA3 based on RAN/SA3 feedback
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040033 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 25/03/2025 | 85 | SP-240991 | 98 | 
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed