## Slide 1: Work Planning At SA2 97
SA WG2 Chairman (Samsung)

## Slide 2: Progress Dashboard Legend
Topic Acronym
TR Phase
Normative Phase
Status
Approved Time Budget
Used Time Budget
Number of Sessions
100%
In Progress
At Risk
Highly At Risk
Complete
SA2 agrees further time is not needed
SA2 96
SA2 97
OVER Time Budget

## Slide 3: Work Item Progress Dashboard
MTCe-SDDTE
MTCe-UEPCOP
P4C-F
P4C-TI
ProSe
GCSE_LTE
UPCON
WLAN_NS
ABC
LIMONET
FS_CNO
FS_SaMOG*
FS_WORM
BusTi
IMS_RegCon
TR Phase
Normative Phase
Status
100%
100%
* includes anticipated normative phase
0.5 over

## Slide 4: Maintenance Progress
3GPP Pkt Access
PCC/QoS
Non-3GPP Access
IMS-Related + Other
IMS
Reserved
Status

## Slide 5: TEI12 Progress
3GPP Pkt Access
PCC/QoS
Non-3GPP Access
IMS-Related + Other
IMS
Reserved
Status
Given the ambitious schedule and large amount of work, should we consider TEI12 'nice to have' and not assume we will have time for it?

## Slide 6: Update Work Plan for SA 60 (1/3)
Work Item | Finish Date | Comp % was | Comp % now | Budget @SA 59 | Budget @SA 60 | Notes
FS_UMONC | Rel-13 | 70% | 70% | 0 | 0 | Confirm Date
GCSE_LTE TR | SA 62 | 0% |  | 10 | 5 | 
GCSE_LTE TS | SA 62 | 0% | 0% | 4 | 4 | 
IMS_RegCon | SA 60 | 20% |  | 3 | 1 | 
UPCON TR | SA 61 | 10% |  | 10 | 4 | 
UPCON TS | SA 61 | 0% | 0% | 6 | 6 | 
LIMONET-SIPTO | SA 60 | 95% |  | 1 | 0 | 
MTCe-SDDTE TR | SA 62 | 55% |  | 7 | 2 | 
MTCe-SDDTE TS | SA 62 | 0% | 0% | 7 | 7 | 
MTCe-UEPCOP TR | SA 62 | 60% |  | 3 | 2 | 
MTCe-UEPCOP TS | SA 62 | 0% | 0% | 1.5 | 1.5 | 

## Slide 7: Update Work Plan for SA 60 (2/3)
Work Item | Finish Date | Comp % was | Comp % now | Budget @SA 59 | Budget @SA 60 | Notes
P4C-F TR | SA 62 | 70% |  | 1.5 | 0 | 0.5 over budget!
P4C-F TS | SA 62 | 0% | 0% | 4 | 4 | 
P4C-TI TR | SA 62 | 45% |  | 2 | 1 | verify 'done'
P4C-TI TS | SA 62 | 0% |  | 4 | 3.75 | verify 'done'
BusTI TR | SA 60 | 79% |  | 0 | 0 | 
BusTI TS | SA 62 | 0% |  | 2 | 0.5 | 
WLAN_NS TR | SA 62 | 30% |  | 7 | 1.5 | 
WLAN_NS TS | SA 62 | 0% | 0% | 4 | 4 | 
ProSe TR | SA 61 | 3% |  | 17 | 7.5 | 
ProSe TS | SA 62 | 0% | 0% | 10 | 10 | 
ABC | SA 62 | 0% |  | 3.5 | 1.5 | 

## Slide 8: Update Work Plan for SA 60 (3/3)
Work Item | Finish Date | Comp % was | Comp % now | Budget @SA 59 | Budget @SA 60 | Notes
FS_CNO | SA 62 | 20% |  | 3 | 1 | 
FS_WORM | SA 60 | 20% |  | 3.5 | 2.5 | Change the date.
FS_SaMOG | SA 62 | 66% |  | 4 | 1 | TS phase (4 budget agreed) not shown. A SaMOG phase 2 WID will precede normative work.
<new item?> |  | - | 0% | - |  | 
<new item?> |  | - | 0% | - |  | 
<new item?> |  | - | 0% | - |  | 
<new item?> |  | - | 0% | - |  | 
<new item?> |  | - | 0% | - |  |