3GPP SA4-e (AH) Video SWG post 126	S4aV230109

Online, December 2023

Agenda item: 	3.11

Source: 	China Mobile Com. Corporation, Qualcomm Incorporated, ZTE

Title: 	Draft Time Plan for the FS_3DV Study Item

Document for	Discussion

Introduction

The FS_3DV work item has the following objectives:

- Identify emerging capturing/acquisition and display technologies and the associated formats (number of views, depth, alpha, resolution, etc.) for smartphones and glasses to support beyond 2D formats with market relevance within the next years beyond the findings already documented in TR 26.928, TR 26.998 and TS 26.119.

- Document different 3D video related end-to-end reference workflows to support real-time communication, split rendering, real-time 2D-to-3D conversion, network-assisted 3D content synthesis and rendering, messaging and/or streaming services for devices supporting the above technologies. This includes 3D video formats (resolution, frame rates, color space...), encoding and decoding considerations and delivery aspects.

- Define concrete evaluation scenarios (test conditions, KPIs, Metrics, test sequences) based on the above reference workflows and document the performance of existing 3GPP codecs (AVC, HEVC, multiple HEVC encoders/decoders, MV-HEVC), and identify potential new formats to address better compression efficiency and/or improved quality.

Note 1: Prioritize 3D video that have been standardized or incorporated into 3GPP services (such as

Stereo 3D, multi-view, and RGBD). The current state-of-the-art, including Dynamic Mesh and

Implicit Neural 	Representation, can be evaluated but will be treated as low priority.

- Document interoperability requirements, traffic charactertistics and QoS requirements to support the above work flows and evaluate the feasibility of new formats with different services, considering the performance indicators such as encoding and decoding complexity, network resource consumption, bandwidth utilization, and interoperability considerations.

Note 2: Prioritize network and service considerations when evaluating existing video profiles from

3GPP or other standards for their commercial feasibility in supporting 3D RTC over 5G/5G-A.

- Identify gaps and deficiencies of existing codecs, offering recommendations to enhance video specification and capabilities.

- Identify potential areas for normative work as the next phase and communicate with other 3GPP WGs regarding relevant aspects related to the study.

Time Plan

The following time plan for the execution of the FS_3DV study item objectives is proposed in the following table.

| Meeting | Study on 3D Video in Real-time Communication |
| --- | --- |
| SA4#127 (29 January - 2 February 2024, Sophia-Antipolis, FR) | - Agree New Study Item “3D Video in 5G Services” in S4 -XXXXXX |
| SA#103 (19 - 22 March 2024, FR) | - Approve New Study Item ”3D Video in 5G Services” in SP-XXXXXX |
| SA4#127-bis-e (08 - 12 April 2024, online) | - Define and agree initial work and time plan - Agree Specification skeleton and Scope for TR XXXX - Initiate work on: - Document emerging capturing/acquisition and display technologies and the associated formats - Reference 3D video related end-to-end workflow for devices supporting the above technologies |
| Post SA4#127-bis-e AHG calls | - Progress work on: - Document emerging capturing/acquisition and display technologies and the associated formats - Reference 3D video related end-to-end workflow for devices supporting the above technologies |
| SA4#128 (20 - 24 May 2024, Korea) | - Initiate work on: - Define evaluation scenario - For each scenario, agree and document - Relevant and exemplary test conditions and material, including test sequences. - Performance of existing 3GPP codecs - Identify potential new formats - Evaluate the feasibility of new formats with different services |
| Post SA4#128 AHG calls | - Progress work on building the test environment and evaluating the 3D Video format |
| SA4#129-e (19 - 23 August 2024, online) | - Initiate work on: - Collect and review the initial evaluation results and identify any open issues . - Documenting interoperability requirements, traffic charactertistics and QoS requirements to support the above work flows |
| Post SA4#129 AHG calls | - Progress work on: - Document evaluation results - Document relevant requirements to support the above work flows. |
| SA4#130 (18 - 22 November 2024, Orlando) | - Identify gaps and deficiencies of existing codecs, offering recommendations to enhance video specification and capabilities. - Initiate work on potential related normative work and conclusions - Agree on TR XXX to be sent to SA plenary for information |
| SA#106 (10 - 13 December 2024, Madrid) | - Present TR XXX to SA for information |
| SA4#131 (17 - 21 February 2025, Geneva) | - Complete work on identify potential related normative work and conclusions - Complete all remaining open issues - Communicate with other 3GPP working groups and external organizations, if necessary - Agree on TR XXX to be sent to SA plenary for approval |
| SA#107 (11 - 14 March 2025, Korea) | - Send TR XXX to SA for Approval |

Proposal

We propose the above Work Plan for the SA4 team's consideration.