## On Network
Color-code legend: Topic R14 status | Description
Indicates that no company(s) is assigned to do the work. -Unlikely to make the R14 time frame.
Company assigned to do the work -Complexity and/or unclear desired behavior puts R14 completion at risk
Company assigned to do the work -Highly likely to be completed in R14 time frame
Topic R14 status | Functionality | Subclause in 24.379 | Subclause in 23.379 | Subclause in 23.280 | Contributors and Plan Company/Name/Target Mtg. | Comments
First-to-answer call setup (with and without floor control) | client procedures | overlay existing private call procedures | 10.15.3 First-to-answer call setup (procedure) |  | Samsung/Ricky/CT1#102 | -The final result is a private call, with the first of a list of targeted users to answer being the terminating client. -if using floor control, call request may or may not include an implicit floor request -overlay of existing private call procedures chosen -stage 2 information flows TBD -on-network only -stage 2 config parameter needed for authorisation
| server procedures | overlay existing private call procedures | 10.15.2 information flow TBD |  | Samsung/Ricky/CT1#102
Updating the selected MC service user profile for an MC service | client procedures | 7.2.x |  | Information elements: 10.1.4.2.10-11 for selecting active user profile case 10.1.4.7 (selected user profile procedure) | BlackBerry/Andrew/CT#102 24.384 contributor TBD | -not eMCPTT specific, applies to all MC services -The MC service user profile that is to be selected as the active MC service user profile for an MC service upon request by an MC service user. -downloading of pre-selected profile instantiated in R13 stage 3 MCPTT. -selection of active MCPTT user proflile new for R14 -possible stage 3 speciication approach: Maybe eMCPTT creates the common procedures and specific procedure for MCPTT. MCData and MCVideo refer to TS 24.379 for the common parts? We have no new TS for the other common stuff. Q9: replicate active profile selection profile procedures in MCPTT, Video and Data TSs or create a common procedure in 24.484?
| server procedures | 7.3.x |  |  | BlackBerry/Andrew/CT#102 24.384 contributor TBD
Ambient listening call (remotely or locally initiated) | client procedures | 11.1.a.b | 10.14.2.1-10.14.2.5 Information flows for ambient listening call 10.14.3.1 Remotely initiated ambient listening call setup 10.14.3.2 Locally initiated ambient listening call setup 10.14.3.3 Ambient listening call release – server initiated 10.14.3.4 Remotely initiated ambient listening call release – "listening" user initiated 10.14.3.5 Ambient listening call release – "listened to" user initiated |  | Motorola/bob/CT1#102 | -a type of a private MCPTT call that only allows a "listened to" user to transmit media to a "listening" user such that there is no indication on the MCPTT UE of the "listened to" user about the call and the media transmission. -media only flows from the "listened to" user to the "listening" user -a new sub-type of private call? remotely-initiated: -listend-to user not aware that they're being listened to -can be released by the MCPTT Admin( assume this is an authorised user?) -can be released by the "listening" user, not the listened to user locally-initiated: -both parties are aware of the ambient listening call -can be released by the MCPTT Admin( assume this is an authorised user?) -can be released by the the "listening" user -can be released by the "listened-to" user Auth checks require parameter(s) - needed from SA6
| server procedures | 11.1.a.c. |  |  | Motorola/bob/CT1#102
MCPTT private call-back request | client procedures | 11.1.e.f | 10.7.4.1.1-10.7.4.1.4 information flows 10.7.4.2 MCPTT private call call back request within one MCPTT system 10.7.4.3 MCPTT private call call back cancel request within one MCPTT system 10.7.4.4 MCPTT private call call back request fulfillment within one MCPTT system A.3-2 "Authorized to make a private call back request" "Authorized to cancel a private call back request" |  | Samsung/Ricky/CT1#102 | -needs minor changes to the terminating client procedures to clear the stored flag for call-back
| server procedures | 11.1.e.g |  |  | Samsung/Ricky/CT1#102
Floor control for audio cut-in enabled group | client procedures | N/A | 10.9.1.5 Floor control for audio cut-in enabled group Table A.4-2: Group configuration data (on network): Audio cut-in policy (enabled/disabled) |  | Motorola/bob/CT1#103 24.380 contributor TBD | -If the cut-in policy is enabled, the interrupter will immediately get the floor from the current talker, who will receive Floor Revoke. -no floor queueing -applies to chat and pre-arranged models -likely very small 24.379 impact, most work in 24.380 if an emergency or imminent peril call would take place on an audio cut-in enabled group, cut-in policy in effect for all users.
| server procedures | N/A |  |  | Motorola/bob/CT1#10324.380 contributor TBD
Remotely initiated MCPTT call | client procedures | TBD | 10.16 Remotely initiated MCPTT call 10.16.2.1, 10.16.2.2 message information elements 10.16.3.1 procedures |  | Samsung/Ricky/? | -allows an authorized user to cause a remote MCPTT UE to initiate a call by itself, without its user explicitly initiating the call. -applicable to both PRIVATE and GROUP calls. - can optionally be visible or not visible to the remote MCPTT user -can be used for covert scenarios, when a responder is injured or a MCPTT UE has been stolen -the targeted client has the floor indefinitely, or until the max group or private call timer expires. Q7: how/when does the call end?
| server procedures | TBD |  |  | Samsung/Ricky/?
Authorized user remotely changes another MCPTT user’s selected MCPTT group – mandatory mode | client procedures | TBD | 10.4.2.1-10.4.2.3 information flows 10.4.3 Authorized user remotely changes another MCPTT user’s selected MCPTT group – mandatory mode (procedure) A-3.2 "List of MCPTT users whose selected groups are authorized to be remotely changed" |  | Motorola/bob/CT1#103 | Q22: stage 2 - what assumptions do we place on the current session in progress (if any). For example, if the user already has a group session on Group A which he initiated on his selected group, and the authorised user changes that user's selected group, what is the impact on the current session on the old selected group?
| server procedures | TBD |  |  | Motorola/bob/CT1#103
Entering MCPTT emergency alert area (geographically triggered alert) | client procedures | TBD | 10.6.2.2.3b: information flow definition not yet defined 10.9.3.6: has client location reporting procedure 10.6.2.6.3.3: client enters pre-defined alert area procedure | 10.9.3.6 23.280: location service-related | Motorola/Bob/ | -MCPTT server configured with trigger areas -MCPTT server sends indication to client when it enters a configured trigger area -MCPTT server performs the geofencing functionality -assume client sends emergency alert as per its normal configuration, no binding between the group targeted and the trigger area -Note that here is an editor's note in Stage 2 about the client possibly triggering this procedure locally due to moving into a pre-defined area. Q4: How are the trigger areas configured? No appropriate parameters in the 23.379 config tables. Assume the trigger areas are dynamic and can come and go quickly and require near real-time notifications. More Q5: 10.6.2.2.3b information flow currently a place holder only, needs definition. SA6 clarification needed. -up to date location needed -how to configure the areas in real time?
| server procedures | 13? |  |  | Motorola/Bob/
Enhanced MCPTT group call setup procedure with MBMS bearer | client procedures | TBD | 10.10.6 Enhanced MCPTT group call setup procedure with MBMS bearer |  | Motorola/bob/CT1#103 | -likely impacts both 24.379 and 24.380, requires investigation
| server procedures | TBD |  |  | Motorola/bob/CT1#103
Location management (new procedures) | client procedures | TBD |  | Information flows: 10.9.2.4 Location reporting trigger 10.9.2.5 Location information subscription request 10.9.2.6 Location information subscription response 10.9.2.7 Location information notification Procedures: 10.9.3.3 Client-triggered location reporting procedure 10.9.3.4 Location reporting cancel procedure 10.9.3.5 Location information subscription procedure 10.9.3.6 Usage of location information procedure 10.9.3.6.1 Event-trigger location information notification procedure 10.9.3.6.2 On-demand usage of location information procedure | TBD
| server procedures | TBD |  |  | TBD
Broadcast group call (updated procedures for set-up of group-broadcast group calls and user-broadcast group calls) | client procedures | TBD | 10.6.2.5 Broadcast group call |  |  | Detailed procedures for set-up of group-broadcast group calls and user-broadcast group calls were added in by David Cypher, so may need changes to broadcast group calls
TBD
| server procedures | TBD |  |  | TBD
Geographically triggered affiliation/de-affiliation | client procedures | TBD |  | 10.8.3.1, pre-condition 4 A.4-1, "Geographic area within which affiliation to the group is permitted (see NOTE 7)" "Geographic area outside which de-affiliation from the group is mandatory (see NOTE 7)" | TBD | -Note that this functionality impacts eMCPTT but equally impacts the other MC services. NOTE 7 = "The geographic area may consist of a union of regions that are non-contiguous or contain holes." Q10: what about exception conditions, e.g., should the client be de-affiliated when exiting the area if a call is in progress, in-progress imminent peril call or in-progress emergency with the result being the termination of the in-progress call? -this paramteer needs to be checked each time a user is attempting to affiliate to a group Q12: is there a missing parameter, e.g., "Geographic area inside which affiliation to the group is triggered", or is the Geographic area within which affiliation to the group is permitted (see NOTE 7)" intended for this purpose? 10.8.3.1, pre-condition 4, "an explicit affiliation caused either by the MC service user or determined by a trigger event such as the MC service UE coming within a permitted geographic operational area of an MC service group." 10.8.4.2 de-affiliation, precondition 2: "an explicit de-affiliation requested either by the MC service user or determined by a trigger event such as the MC service UE moving outside a permitted geographic operational area of an MC service group." -it is solely the responsibility of the client to monitor the client's location and when leavings the area permitted for affiliation execute the de-affiliation
| server procedures | TBD |  |  | TBD
Location of current talker | client procedures | TBD | 10.6.2.7 location of current talker A.3-1 "Authorisation to provide location information to other MCPTT users on a call when talking" |  |  | questions include freshness of location info, granularity of location
TBD/24.380
| server procedures | TBD |  |  | TBD/24.380
Temporary group call - user regroup | client procedures | TBD | 10.6.2.8 Temporary group call – user regroup (procedure) 10.6.2.8.2 Call setup 10.6.2.8.3 Call end Information elements impacted: 10.6.2.2.7 10.6.2.2.9 10.6.2.2.14 10.6.2.2.14a |  | TBD | -can be initiated by an authorized user inviting a list of MCPTT users -group ID for this temporary group may be obtained during call setup, or prior to call setup -The users being invited are implicitly affiliated to this temporary group during call setup, and can be implicitly de-affiliated with the release of the group call -call is terminated by either the MCPTT server releasing the call or the authorized user ending the call. -release of the call may be followed by release of the temporary group ID
| server procedures | TBD |  |  | TBD
Updating the pre-selected MCPTT user profile | client procedures | TBD |  | 10.1.4.2.8-10.1.4.2.9 (information flows for updating pre-selected user profile) 10.1.4.6 (procedure) | 24.384 contributor TBD | -not eMCPTT specific, applies to all MC services -Note that this functionality is in the realm of the configuration management client and configuration management server -issue: stage 3 information flow and R13 implementation may be out of sync (i.e., index vs. profile name) Q8: where to document (i.e., in the individual TSs or common procedure in 24.484?)
| server procedures | TBD |  |  | 24.384 contributor TBD
NOTE 1: References to tables A.4-x in the "Subclause in 23.379" or "Subclause in 23.280" columns above are to parameters which are expected to be specified in TS 24.481
NOTE 2: References to tables A.3-x in the "Subclause in 23.379" or "Subclause in 23.280" columns above are to parameters which are expected to be specified in TS 24.483 and TS 24.484
NOTE 3: Topics First-to-answer call setup (with and without floor control), MCPTT private call-back request, Ambient listening call and Updating the selected MC service user profile for an MC service had completion percentages ranging from 70% to 100% by the end of CT1#102.