## Sheet1
ID | Unique_ID | Name | Acronym | Outline Level | Release | Resource Names | Start | Finish | % Complete | Hyperlink | Status Report | WI rapporteur name | WI rapporteur e-mail | Notes | Impacted TSs and TRs | TSG approved | PCG approved | TSG stopped | PCG stopped | Created | last modif
1 | 0 | Work Plan 3GPP version March 26th 2019 |  | 1 | Rel-16 |  | 2019-03-07 | 2019-03-07 | 0% | [10 empty] | 2015-01-15 | 2015-03-05
2 | 0 | Includes the WIDs approved at TSG#83 |  | 1 | Rel-16 |  | 2019-03-07 | 2019-03-07 | 0% | [10 empty] | 2018-03-15 | NA
3 | 0 | Next: Rel-16 St.2: 06/19, St.3: 12/19. Rel-17: St.1 80% ready 09/19, 100% 12/19; St.2: 09/20 |  | 1 | Rel-16 |  | 2019-03-07 | 2019-03-07 | 0% | [10 empty] | 2015-08-12 | NA
4 | 0 |  |  | 1 | Rel-16 |  | 2019-03-07 | 2019-03-07 | 0% | [10 empty] | 2017-03-03 | NA
5 | 0 | Release 17 | - | 1 | Rel-17 |  | 2016-03-15 | 2016-03-15 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
6 | 0 | Release 17 on Use of 5G by different sectors ("verticals") | - | 1 | Rel-17 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
7 | 810017 | Study on Asset Tracking Use Cases | FS_5G_ATRAC | 1 | Rel-17 | S1 | 2018-09-06 | 2019-06-14 | 45% | SP-180922 |  | Thierry Berisot, NOVAMINT | tberisot@novamint.com | 4/12/18: 0%->15; 14/3/19: 15%->45 | 22.836 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
8 | 810016 | Study on Communication Services for Critical Medical Applications | FS_CMED | 1 | Rel-17 | S1 | 2018-09-06 | 2019-09-13 | 65% | SP-180783 |  | Mathieu Lagrange, b<>com | mathieu.lagrange@b-com.com | 4/12/18: 0%->15; 14/3/19: 15%->65 | 22.826 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
9 | 820025 | Study on application layer support for Factories of the Future in 5G network | FS_FFAPP | 1 | Rel-17 | S6 | 2019-03-07 | 2020-03-12 | 5% | SP-181139 |  | Shao Weixiang, ZTE Corporation | shao.weixiang@zte.com.cn | 14/3/19: 0%->5 | new | 82 |  |  |  | 2018-12-06 | 2019-03-14
10 | 820011 | Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | FS_ID_UAS_SA2 | 1 | Rel-17 | S2 | 2018-12-06 | 2020-03-12 | 0% | SP-181114 |  | Qualcomm Incorporated, Stefano Faccin | sfaccin@qti.qualcomm.com |  |  | 82 |  |  |  | 2018-12-06 | NA
11 | 820026 | Study on application layer support for Unmanned Aerial System (UAS) | FS_UASAPP | 1 | Rel-17 | S6 | 2018-12-06 | 2019-12-13 | 0% | SP-181252 |  | Niranth Amogh, Huawei | namogh@huawei.com |  | new | 82 |  |  |  | 2018-12-06 | NA
12 | 810019 | Study on enhancement for Unmanned Aerial Vehicles (UAVs) | FS_EAV | 1 | Rel-17 | S1 | 2018-09-06 | 2019-12-13 | 70% | SP-180909 |  | Qun Wei, China Unicom | weiqun5@chinaunicom.cn | 4/12/18: 0%->20; 14/3/19: 20%->70 | 22.829 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
13 | 0 | Release 17 other Features | - | 1 | Rel-17 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
14 | 830017 | Verification-modified Calling Name Display | VMOD_DISPLAY | 1 | Rel-17 | S1 | 2019-03-07 | 2019-03-21 | 100% | SP-190085 |  | Hala Mowafy, Ericsson | Hala.Mowafy@ericsson.com | 14/3/19: 0%->100 | 22.173 |  |  |  |  | 2017-12-15 | 2019-03-14
15 | 820003 | Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 1 | Rel-17 | S4 | 2018-12-13 | 2020-12-18 | 0% | SP-180985 |  | Ye-Kui Wang , Huawei Technologies Co. Ltd. | yekui.wang@huawei.com | 7/3/19: 0%->5% | 26.114; 26.223 |  |  |  |  | 2019-03-14 | NA
16 | 830005 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 1 | Rel-17 | S4 | 2019-03-07 | 2020-12-04 | 0% | SP-190040 |  | Stéphane Ragot, Orange | stephane.ragot@orange.com |  | 26.260, new |  |  |  |  | 2019-03-14 | NA
17 | 830026 | Integration of ONAP and 3GPP 5G management framework | ONAP3GPP | 1 | Rel-17 | S5 | 2019-03-07 | 2020-03-05 | 0% | SP-190139 |  | SMITH David K., AT&T | DS9930@att.com |  | 28.540; 28.622; 28.623; 28.532 |  |  |  |  | 2019-03-14 | NA
18 | 0 | Release 17 other Studies | - | 1 | Rel-17 |  | 2016-03-15 | 2016-03-15 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
19 | 810018 | Study on enhanced Relays for Energy eFficiency and Extensive Coverage | FS_REFEC | 1 | Rel-17 | S1 | 2018-09-06 | 2019-06-14 | 40% | SP-180785 |  | Jose Luis Almodovar Chico, KPN | jose.almodovarchico@tno.nl | 4/12/18: 0%->20; 14/3/19: 20%->40 | 22.866 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
20 | 800015 | Study on Network Controlled Interactive Service in 5GS | FS_NCIS | 1 | Rel-17 | S1 | 2018-06-06 | 2019-03-14 | 85% | SP-180341 |  | YANG Ning, Oppo | yangning@oppo.com | 6/8/18: 22.842 added;; 10/9/18: 0%->25; 4/12/18: 25%->60; 14/3/19: 60%->85 | 22.842 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
21 | 800014 | Study on Audio-Visual Service Production | FS_AVPROD | 1 | Rel-17 | S1 | 2018-06-06 | 2019-06-12 | 80% | SP-181015 |  | Roland Beutler, EBU | Roland.Beutler@swr.de | 6/8/18: 22.827 added;; 10/9/18: 0%->10; 4/12/18: 10%->50; 14/12/18: WID:SP-180340->SP-181015; 14/12/18: FCD:03/19->06/19; 14/3/19: 50%->80 | 22.827 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
22 | 831002 | Study on Support for Multi-USIM Devices | FS_MUSIM | 1 | Rel-17 |  | 2018-12-06 | 2020-03-12 | 1% |  | - | [8 empty] | 2019-03-14 | NA
23 | 830019 | Study on Support for Multi-USIM Devices | FS_MUSIM | 2 | Rel-17 | S1 | 2019-03-07 | 2019-09-06 | 5% | SP-190091 | - | Liao, Ellen C, Intel | ellen.c.liao@intel.com | 14/3/19: 0%->5 | New |  |  |  |  | 2019-03-14 | 2019-03-14
24 | 820012 | Study on system enablers for multi-SIM devices | FS_MUSIM | 2 | Rel-17 | S2 | 2018-12-06 | 2020-03-12 | 0% | SP-190248 |  | Sašo Stojanovski, Intel | saso stojanovski intel com) | 21/3/19: WID:SP-181251->SP-190248 | 23.761 | 82 |  |  |  | 2018-12-06 | 2019-03-21
25 | 780005 | Study on Multimedia Priority Service (MPS) Phase 2 | FS_MPS2 | 1 | Rel-17 | S1 | 2017-12-15 | 2019-09-12 | 80% | SP-170996 |  | Singh, Ray P; Vencore Labs | rsingh@vencorelabs.com | 16/3/18: 0%->10; 7/6/18: 10%->30; 10/9/18: 30%->50; 4/12/18: 50%->65; 12/12/18: FCD:03/19->09/19. Rel-16->Rel-17; 14/3/19: 65%->80 | 22.854 | 78 | 40 |  |  | 2017-12-15 | 2019-03-14
26 | 830018 | Study on Support for Minimization of service Interruption | FS_MINT | 1 | Rel-17 | S1 | 2019-03-07 | 2019-09-05 | 0% | SP-190090 | - | SungDuck Chun; LG Electronics | sungduck.chun@lge.com |  | New |  |  |  |  | 2019-03-14 | NA
27 | 830020 | Study on enhancements for cyber-physical control applications in vertical domains | FS_eCAV | 1 | Rel-17 | S1 | 2019-03-07 | 2019-09-05 | 5% | SP-190092 | - | Michael Bahr, Siemens AG | bahr et siemens dod com | 14/3/19: 0%->5 | New |  |  |  |  | 2019-03-14 | 2019-03-14
28 | 830030 | Study on Architectural enhancements for 5G multicast-broadcast services | FS_5MBS | 1 | Rel-17 | S2 | 2019-03-07 | 2020-06-12 | 0% | SP-190242 |  | Dario Serafino Tonesi, Huawei | dario.tonesi@huawei.com |  | New |  |  |  |  | 2019-03-14 | NA
29 | 830031 | Study on service-based support for SMS in 5GC | FS_SB_SMS | 1 | Rel-17 | S2 | 2019-03-07 | 2019-12-05 | 0% | SP-190184 |  | George Foti | George dot Foti at ericsson dot com |  | New |  |  |  |  | 2019-03-14 | NA
30 | 830032 | Study on enhancement of support for Edge Computing in 5GC | FS_enh_EC | 1 | Rel-17 | S2 | 2019-03-07 | 2020-03-05 | 0% | SP-190185 |  | Hui Ni, Huawei | Hui.ni@huawei.com |  | New |  |  |  |  | 2019-03-14 | NA
31 | 830008 | Study on Application Architecture for enabling Edge Applications | FS_EDGEAPP | 1 | Rel-17 | S6 | 2019-03-07 | 2019-12-05 | 0% | SP-190065 |  | Nishant Gupta, Samsung | nishant.gup@samsung.com |  | New |  |  |  |  | 2019-03-14 | NA
32 | 830033 | Study on System enhancement for Proximity based Services in 5GS | FS_5G_ProSe | 1 | Rel-17 | S2 | 2019-03-07 | 2020-06-12 | 0% | SP-190186 |  | Qiang Deng, CATT | dengqiang1@catt.cn |  | New |  |  |  |  | 2019-03-14 | NA
33 | 830034 | Study on UPF enhancement for control and SBA | FS_UPCAS | 1 | Rel-17 | S2 | 2019-03-07 | 2020-03-06 | 0% | SP-190187 |  | Dan Wang, China Mobile | wangdanyjy@chinamobile.com |  | New |  |  |  |  | 2019-03-14 | NA
34 | 0 | Release 16 Features and related studies | - | 1 | Rel-16 |  | 2016-03-15 | 2016-03-15 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
35 | 0 | Enhancement of Ultra-Reliable (UR) Low Latency Communications (URLLC) | - | 1 | Rel-16 |  | 2017-12-15 | 2017-12-15 | 31% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
36 | 830098 | Enhancement of URLLC support in the 5G Core network | 5G_URLLC | 1 | Rel-16 | S2 | 2017-12-15 | 2019-06-20 | 59% | SP-181122 |  | Hui Ni, Huawei | Hui.ni@huawei.com | 14/3/19: 0%->50 | 23.501; 23.502; 23.503 | 82 |  |  |  | 2018-12-06 | 2019-03-14
37 | 790008 | Study on enhancement of URLLC supporting in 5GC | FS_5G_URLLC | 2 | Rel-16 | S2 | 2018-03-15 | 2018-12-14 | 90% | SP-180118 |  | Hui Ni, Huawei | Hui.ni@huawei.com | 7/6/18: 0%->15; 6/8/18: 23.725 added;; 10/9/18: 15%->60; 7/12/18: 60%->85; 14/3/19: 85%->90 | 23.xyz; 23.725 | 79 | 40 |  |  | 2018-03-15 | 2019-03-14
38 | 780030 | Study on EPC support for Mobility with Low Latency Communication | FS_LLC_Mob | 2 | Rel-16 | S2 | 2017-12-15 | 2018-09-14 | 75% | SP-171069 |  | Chris PUDNEY | chris dot pudney at vodafone dot com | 16/3/18: 0%->35; 7/6/18: 35%->75 | new 23.739 | 78 | 40 |  |  | 2017-12-15 | 2018-06-07
39 | 790009 | Study on enht of systems using EPS for UR and Availability using commodity equipment | FS_EPS_URACE | 2 | Rel-16 | S2 | 2018-03-15 | 2018-12-14 | 10% | SP-180119 |  | Chris Pudney | chris.pudney@vodafone.com | 7/6/18: 0%->10; 6/8/18: 23.736 added; | new; 23.736 | 79 | 40 |  |  | 2018-03-15 | 2018-08-06
40 | 810036 | Study on the security of URLLC for 5GS | FS_5G_URLLC_SEC | 2 | Rel-16 | S3 | 2018-09-06 | 2019-06-12 | 65% | SP-180910 |  | Rong Wu, Huawei Technologies | Raina.wu@huawei.com | 7/12/18: 0%->20; 20/3/19: FCD:019->06/19; 20/3/19: 20%->65 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-20
41 | 820019 | Stage 2 of 5G_URLLC | 5G_URLLC | 2 | Rel-16 | S2 | 2018-12-13 | 2019-06-20 | 50% | SP-181122 |  | Hui Ni, Huawei | Hui.ni@huawei.com | 14/3/19: 0%->50 | 23.501; 23.502; 23.503 | 82 |  |  |  | 2018-12-06 | 2019-03-14
42 | 830074 | Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC) | NR_L1enh_URLLC | 1 | Rel-16 | R1 | 2018-06-15 | 2020-09-15 | 23% | RP-190726 |  | Huawei | [7 empty] | 2019-03-26 | NA
43 | 800095 | Study on physical layer enhancements for NR UR Low Latency Cases | FS_NR_L1enh_URLLC | 2 | Rel-16 | R1 | 2018-06-15 | 2019-03-15 | 100% | RP-181477 |  | Huawei |  | TR 38.8xx; 26/3/19: 0%->100 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
44 | 830174 | Core part: Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC) | NR_L1enh_URLLC-Core | 2 | Rel-16 | R1 | 2019-03-01 | 2020-03-01 | 0% | RP-190726 |  | Huawei | [7 empty] | 2019-03-26 | NA
45 | 830274 | Perf. part: Physical Layer Enhancements for NR Ultra-Reliable and Low Latency Communication (URLLC) | NR_L1enh_URLLC-Perf | 2 | Rel-16 | R4 | 2019-03-01 | 2020-09-15 | 0% | RP-190726 |  | Huawei | [7 empty] | 2019-03-26 | NA
46 | 830080 | Support of NR Industrial Internet of Things (IoT) | NR_IIOT | 1 | Rel-16 | R2 | 2018-06-15 | 2020-03-01 | 27% | RP-190728 |  | Nokia | [7 empty] | 2019-03-26 | NA
47 | 810060 | Study on channel modeling for indoor industrial scenarios | FS_IIIOT_CM | 2 | Rel-16 | R1 | 2018-09-14 | 2019-09-13 | 0% | RP-182138 |  | Ericsson |  |  |  | 81 | 41 |  |  | 2018-09-25 | NA
48 | 800098 | Study on NR Industrial Internet of Things (IoT) | FS_NR_IIOT | 2 | Rel-16 | R2 | 2018-06-15 | 2019-03-15 | 100% | RP-181479 |  | Nokia |  | TR 38.8XX?; 6/8/18: 38.825 added;; 26/3/19: 0%->100 | 38.825 | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
49 | 830180 | Core part: Support of NR Industrial Internet of Things (IoT) | NR_IIOT-Core | 2 | Rel-16 | R2 | 2019-03-01 | 2020-03-01 | 0% | RP-190728 |  | Nokia | [7 empty] | 2019-03-26 | NA
50 | 820999 | 5GS Enhanced support of Vertical and LAN Services | - | 1 | Rel-16 |  | 2017-12-15 | 2017-12-15 | 31% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
51 | 750004 | Study on Communication for Automation in Vertical Domains | FS_CAV | 1 | Rel-16 | S1 | 2017-03-02 | 2018-03-15 | 100% | SP-170169 |  | Walewski, Joachim, Siemens AG | joachim.walewski@siemens.com | 7/6/17: 0%->30; 25/8/17: FCD:12/17->03/18; 11/9/17: 30%->65; 15/12/17: 65%->85; 16/3/18: 85%->95; 7/6/18: 95%->100 | 22.804 | 75 | 38 |  |  | 2017-03-02 | 2018-06-07
52 | 800007 | Service requirements for cyber-physical control applications in vertical domains | cyberCAV | 1 | Rel-16 | S1 | 2018-06-06 | 2018-09-14 | 100% | SP-180321 |  | Joachim W. Walewski (Siemens) |  | 10/9/18: 5%->40; 4/12/18: 40%->100 | 22.261; 22.104 | 80 | 41 |  |  | 2018-06-06 | 2018-12-04
53 | 830042 | 5GS Enhanced support of Vertical and LAN Services | Vertical_LAN | 1 | Rel-16 | S2 | 2018-06-06 | 2019-12-12 | 30% | SP-181120 |  | Devaki Chandramouli, Nokia | Devaki.chandramouli@nokia.com |  |  | 82 |  |  |  | 2018-12-06 | 2018-06-14
54 | 800028 | Study on 5GS Enhanced support of Vertical and LAN Services | FS_Vertical_LAN | 2 | Rel-16 | S2 | 2018-06-06 | 2018-12-14 | 92% | SP-180507 |  | Devaki Chandramouli, Nokia | Devaki.chandramouli@nokia.com | 10/9/18: 0%->25; 7/12/18: 25%->88; 14/3/19: 88%->92 | 23.734 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
55 | 820017 | Stage 2 of Vertical_LAN | Vertical_LAN | 2 | Rel-16 | S2 | 2018-12-13 | 2019-06-24 | 43% | SP-181120 |  | Devaki Chandramouli, Nokia | Devaki.chandramouli@nokia.com | 14/3/19: 0%->43 | 23.501; 23.502; 23.503 | 82 |  |  |  | 2018-12-06 | 2019-03-14
56 | 810038 | Study on Security for 5GS Enhanced support of Vertical and LAN Services | FS_Vertical_LAN_SEC | 2 | Rel-16 | S3 | 2018-09-06 | 2019-06-12 | 65% | SP-180697 |  | Jerichow, Anja (Nokia) | anja.jerichow@nokia.com | 7/12/18: 0%->10; 20/3/19: FCD:019->06/19; 20/3/19: 10%->65 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-20
57 | 830010 | CT aspects of Vertical_LAN | Vertical_LAN | 2 | Rel-16 | ct | 2019-03-14 | 2019-12-12 | 0% | CP-190195 |  | WON, Sung Hwan, Nokia | sung.won@nokia.com | [6 empty] | 2018-12-06 | 2018-06-14
58 | 830035 | CT1 aspects of Vertical_LAN | Vertical_LAN | 3 | Rel-16 | C1 | 2019-03-14 | 2019-12-12 | 0% | CP-190195 |  | WON, Sung Hwan, Nokia | sung.won@nokia.com |  | 23.122; 24.368; 24.501; 24.526 |  |  |  |  | 2018-12-06 | 2018-06-14
59 | 830036 | CT3 aspects of Vertical_LAN | Vertical_LAN | 3 | Rel-16 | C3 | 2019-03-14 | 2019-12-12 | 0% | CP-190195 |  | WON, Sung Hwan, Nokia | sung.won@nokia.com |  | 29.122; 29.507; 29.508; 29.512; 29.513; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.554; 29.561; 29.594; 29.061 |  |  |  |  | 2018-12-06 | 2018-06-14
60 | 830037 | CT4 aspects of Vertical_LAN | Vertical_LAN | 3 | Rel-16 | C4 | 2019-03-14 | 2019-12-12 | 0% | CP-190195 |  | WON, Sung Hwan, Nokia | sung.won@nokia.com |  | 23.003; 23.008; 29.502; 29.503; 29.505; 29.509; 29.510; 29.518; 29.571; 29.244; 29.281 |  |  |  |  | 2018-12-06 | 2018-06-14
61 | 820027 | Service Enabler Architecture Layer for Verticals | SEAL | 1 | Rel-16 | S6 | 2018-12-06 | 2019-06-13 | 60% | SP-181141 |  | Basavaraj (Basu) Pattan, Samsung | basavarajjp@samsung.com | 14/3/19: 0%->60 | new 23.434 | 82 |  |  |  | 2018-12-06 | 2019-03-14
62 | 820067 | NR-based access to unlicensed spectrum | NR_unlic | 1 | Rel-16 | R1 | 2098-05-20 | 2119-12-15 | 47% | RP-190706 |  | Qualcomm |  | 26/3/19: WID:RP-182878->RP-190706 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
63 | 750045 | Study on NR-based access to unlicensed spectrum | FS_NR_unlic | 2 | Rel-16 | R1 | 2017-03-15 | 2018-12-14 | 100% | RP-181339 |  | Qualcomm |  | TR 38.8XX19/6/17: WID: RP-170828->RP-171416; 30/6/17: 32.889 added;; 19/9/17: WID: RP-171416->RP-17202127/3/18: Compl:0%->10%; 27/6/18: Compl:10%->40%; 27/6/18: CD:Fri 15/06/18->Sat 15/12/18; 16/1/19: 40%->100 | 32.889 | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
64 | 820167 | Core part: NR-based access to unlicensed spectrum | NR_unlic-Core | 2 | Rel-16 | R1 | 2018-12-15 | 2019-12-15 | 0% | RP-190706 |  | Qualcomm |  | 26/3/19: WID:RP-182878->RP-190706 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
65 | 820267 | Perf. part: NR-based access to unlicensed spectrum | NR_unlic-Perf | 2 | Rel-16 | R4 | 2018-12-15 | 2019-12-15 | 0% | RP-190706 |  | Qualcomm |  | 26/3/19: WID:RP-182878->RP-190706 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
66 | 800006 | LAN support in 5G | 5GLAN | 1 | Rel-16 | S1 | 2017-06-05 | 2018-12-14 | 99% | SP-180593 |  | Almodovar Chico, Jose Luis, KPN | jose.almodovarchico@tno.nl |  | 22.261; 22.278 | 80 | 41 |  |  | 2018-06-06 | NA
67 | 760007 | Study on LAN Support in 5G | FS_5GLAN | 2 | Rel-16 | S1 | 2017-06-05 | 2018-03-15 | 100% | SP-170456 |  | Nasielski, Jack, Qualcomm Incorporated | jackn@qti.qualcomm.com | 11/9/17: 0%->35; 15/12/17: 35%->65; 16/3/18: 65%->100 | 22.821; | 76 | 39 |  |  | 2017-06-03 | 2018-03-16
68 | 800047 | Stage 1 of 5GLAN | 5GLAN | 2 | Rel-16 | S1 | 2018-06-06 | 2018-12-14 | 100% | SP-180593 |  | Almodovar Chico, Jose Luis, KPN | jose.almodovarchico@tno.nl | 10/9/18: 40%->75; 10/9/18: FCD:09/18->12/18; 4/12/18: 75%->100 | 22.261; 22.278 | 80 | 41 |  |  | 2018-06-06 | 2018-12-04
69 | 830024 | Study on non-public networks management | FS_OAM_NPN | 1 | Rel-16 | S5 | 2019-03-07 | 2019-12-05 | 0% | SP-190137 |  | ZHANG, Kai, Huawei | kai.zhangkai@huawei.com |  | New |  |  |  |  | 2019-03-14 | NA
70 | 0 | Cellular IoT support and evolution | - | 1 | Rel-16 |  | 2016-06-18 | 2016-06-18 | 17% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
71 | 770038 | Study on Cellular IoT support and evolution for the 5G System | FS_CIoT_5G | 1 | Rel-16 | S2 | 2017-09-08 | 2018-12-14 | 95% | SP-180614 |  | Sebastian Speicher | sspeiche@qti.qualcomm.com | 11/09/17: rapporteur change; 15/12/17: 23.724 added;; 16/3/18: 0%->20; 7/6/18: 20%->50; 15/6/18: WID:SP-170801->SP-180614; 15/6/18: FCD:09/18->12/18; 10/9/18: 50%->70; 7/12/18: 70%->95 | New; 23.724 | 77 | 39 |  |  | 2017-09-08 | 2018-12-07
72 | 830043 | Cellular IoT support and evolution for the 5G System | 5G_CIoT | 1 | Rel-16 | S2 | 2018-12-13 | 2019-12-12 | 7% | SP-181118 | [9 empty] | 2018-12-06 | NA
73 | 820015 | Stage 2 of 5G_CIoT | 5G_CIoT | 2 | Rel-16 | S2 | 2018-12-13 | 2019-06-20 | 50% | SP-181118 |  | Sebastian Speicher | sspeiche@qti.qualcomm.com | 14/3/19: 0%->50 | 23.501; 23.502 | 82 |  |  |  | 2018-12-06 | 2019-03-14
74 | 830013 | CT aspects of 5G_CIoT | 5G_CIoT | 2 | Rel-16 | ct | 2019-03-14 | 2019-12-12 | 0% | CP-190198 |  | Mahmoud Watfa; Qualcomm Incorporated | mwatfa@qti.qualcomm.com | [6 empty] | 2018-12-06 | NA
75 | 830038 | CT1 aspects of 5G_CIoT | 5G_CIoT | 3 | Rel-16 | C1 | 2019-03-14 | 2019-12-12 | 0% | CP-190198 |  | Mahmoud Watfa; Qualcomm Incorporated | mwatfa@qti.qualcomm.com |  | 23.122; 24.250; 24.301; 24.368; 24.501; 27.007 |  |  |  |  | 2018-12-06 | NA
76 | 830039 | CT3 aspects of 5G_CIoT | 5G_CIoT | 3 | Rel-16 | C3 | 2019-03-14 | 2019-12-12 | 0% | CP-190198 |  | Mahmoud Watfa; Qualcomm Incorporated | mwatfa@qti.qualcomm.com |  | 29.122; 29.522; 29.525; 29.222; 29.512; 29.513; 29.514 |  |  |  |  | 2018-12-06 | NA
77 | 830040 | CT4 aspects of 5G_CIoT | 5G_CIoT | 3 | Rel-16 | C4 | 2019-03-14 | 2019-12-12 | 0% | CP-190198 |  | Mahmoud Watfa; Qualcomm Incorporated | mwatfa@qti.qualcomm.com |  | 23.008; 29.274; 29.502; 29.503; 29.505; 29.518 |  |  |  |  | 2018-12-06 | NA
78 | 830041 | CT6 aspects of 5G_CIoT | 5G_CIoT | 3 | Rel-16 | C6 | 2019-03-14 | 2019-12-12 | 0% | CP-190198 |  | Mahmoud Watfa; Qualcomm Incorporated | mwatfa@qti.qualcomm.com |  | 31.102; 31.111 |  |  |  |  | 2018-12-06 | NA
79 | 800033 | Study on evolution of Cellular IoT security for the 5G System | FS_CIoT_sec_5G | 1 | Rel-16 | S3 | 2018-06-06 | 2019-09-12 | 75% | SP-180440 |  | Noamen Ben Henda | noamen.ben.henda@ericsson.com | 6/8/18: 33.861 added;; 7/12/18: 5%->30; 20/3/19: 30%->75; 20/3/19: FCD:019->09/19 | New; 33.861 | 80 | 41 |  |  | 2018-06-06 | 2019-03-20
80 | 760040 | Study on MBMS User Services for IoT | FS_MBMS_IoT | 1 | Rel-16 | S4 | 2017-06-05 | 2018-09-14 | 100% | SP-170592 |  | Cedric thienot, Expway | cedric (dot) thienot (at) expway (dot) com | 11/9/17: 0%->10; 15/12/17: 10%->30; 16/3/18: 30%->80; 16/3/18: FCD:03/18->06/18; 7/6/18: 80%->90; 7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15; 10/9/18: 90%->100 | 26.8xx | 76 | 39 |  |  | 2017-06-03 | 2018-09-10
81 | 800083 | Additional MTC enhancements for LTE | LTE_eMTC5 | 1 | Rel-16 | R1 | 2018-06-15 | 2020-06-15 | 0% | RP-190770 |  | Ericsson |  | RAN3 impact?; 16/1/19: WID:RP-181450->RP-182891; 26/3/19: WID:RP-182891->RP-190770 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
82 | 800183 | Core part: Additional MTC enhancements for LTE | LTE_eMTC5-Core | 2 | Rel-16 | R1 | 2018-06-15 | 2019-12-15 | 0% | RP-190770 |  | Ericsson |  | RAN3 impact?; 26/3/19: WID:RP-182891->RP-190770 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
83 | 800283 | Perf. part: Additional MTC enhancements for LTE | LTE_eMTC5-Perf | 2 | Rel-16 | R4 | 2018-06-15 | 2020-06-15 | 0% | RP-190770 |  | Ericsson |  | 26/3/19: WID:RP-182891->RP-190770 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
84 | 800084 | Additional enhancements for NB-IoT | NB_IOTenh3 | 1 | Rel-16 | R1 | 2018-06-15 | 2020-06-15 | 0% | RP-190757 |  | Huawei |  | RAN3 impact?; 16/1/19: WID:RP-181451->RP-182902; 26/3/19: WID:RP-182902->RP-190757 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
85 | 800184 | Core part: Additional enhancements for NB-IoT | NB_IOTenh3-Core | 2 | Rel-16 | R1 | 2018-06-15 | 2019-12-15 | 0% | RP-190757 |  | Huawei |  | RAN3 impact?; 26/3/19: WID:RP-182902->RP-190757 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
86 | 800284 | Perf. part: Additional enhancements for NB-IoT | NB_IOTenh3-Perf | 2 | Rel-16 | R4 | 2018-06-15 | 2020-06-15 | 0% | RP-190757 |  | Huawei |  | 26/3/19: WID:RP-182902->RP-190757 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
87 | 810050 | 5G message service | 5GMSG | 1 | Rel-16 | S1 | 2016-06-18 | 2018-12-14 | 100% | SP-180772 |  |  |  |  | 22.262 | 81 | 41 |  |  | 2018-09-06 | NA
88 | 770004 | Study on 5G message service for MIoT | FS_5GMSG | 2 | Rel-16 | S1 | 2016-06-18 | 2018-09-14 | 100% | SP-170704 |  | Zheng, Jianping, China Mobile | zhengjianping@chinamobile.com | 15/12/17: 22.824 added;; 15/12/17: 0%->25; 16/3/18: 25%->60; 10/9/18: 60%->95; 4/12/18: 95%->100 | New; 22.824 | 77 | 39 |  |  | 2017-09-08 | 2018-12-04
89 | 810014 | Message Service Within the 5G System requirements | MSGin5G | 2 | Rel-16 | S1 | 2018-09-06 | 2018-12-14 | 100% | SP-180920 |  | Zheng, Jianping, China Mobile | zhengjianping@chinamobile.com | 4/12/18: 0%->100 | 22.262; 22.261 | 81 | 41 |  |  | 2018-09-06 | 2018-12-04
90 | 0 | Advanced V2X support | - | 1 | Rel-16 |  | 2017-06-05 | 2017-06-05 | 45% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
91 | 790002 | Study on Improvement of V2X Service Handling | FS_V2XIMP | 1 | Rel-16 | S1 | 2018-03-15 | 2018-06-14 | 100% | SP-180247 |  | SungDuck Chun; LG Electronics | sungduck.chun@lge.com | 7/6/18: 0%->75; 10/9/18: 75%->95; 4/12/18: 95%->100 | 22.886 | 79 | 40 |  |  | 2018-03-15 | 2018-12-04
92 | 820024 | Improvement of V2X service Handling | V2XIMP | 1 | Rel-16 | S1 | 2018-10-25 | 2018-12-04 | 100% | SP-181013 |  | SungDuck Chun; LG Electronics | sungduck.chun@lge.com | 4/12/18: 0%->95; 14/3/19: 95%->100 | 22.186 | 82 |  |  |  | 2018-12-04 | 2019-03-14
93 | 780025 | Study on application layer support for V2X services | FS_V2XAPP | 1 | Rel-16 | S6 | 2017-12-15 | 2018-09-14 | 100% | SP-171071 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 16/3/18: 0%->45; 14/6/18: 45%->75; 10/9/18: 75%->95; 7/12/18: 95%->100 |  | 78 | 40 |  |  | 2017-12-15 | 2018-12-07
94 | 810020 | Application layer support for V2X services | V2XAPP | 1 | Rel-16 | S6 | 2018-09-06 | 2019-06-14 | 65% | SP-180898 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 7/12/18: 0%->25; 14/3/19: 25%->65 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
95 | 760043 | Study on architecture enhancements for 3GPP support of advanced V2X services | FS_eV2XARC | 1 | Rel-16 | S2 | 2017-06-05 | 2018-12-14 | 95% | SP-180733 | SP-170412 | LaeYoung Kim, LG Electronics | laeyoung.kim@lge.com | 11/9/17: 0%->20; 15/12/17: Changed Rel-15->Rel-16; 16/3/18: WID:SP-170379->SP 170590; 16/3/18: 20%->25; 7/6/18: 25%->35; 10/9/18: 35%->58; 10/9/18: FCD:09/18->12/18; 2/10/18: WID:SP 170590->SP-180733; 7/12/18: 58%->88; 14/3/19: 88%->95 | 23.786 | 76 | 39 |  |  | 2017-06-03 | 2019-03-14
96 | 820018 | Architecture enhancements for 3GPP support of advanced V2X services | eV2XARC | 1 | Rel-16 | S2 | 2018-12-13 | 2019-06-14 | 30% | SP-181121 |  | LaeYoung Kim, LG Electronics | laeyoung.kim@lge.com | 14/3/19: 0%->30 | 23.501; 23.502; 23.503; 23.285 | 82 |  |  |  | 2018-12-06 | 2019-03-14
97 | 800096 | Study on NR Vehicle-to-Everything (V2X) | FS_NR_V2X | 1 | Rel-16 | R1 | 2018-06-15 | 2019-03-15 | 100% | RP-190224 |  | LG Electronics |  | TR 38.8XX; compare SA1 REL-15 SI FS_eV2X, RAN1 REL-15 SI FS_LTE_NR_V2X_eval, SA2 REL-16 SI FS_eV2XARC, SA1 REL-16 SI FS_V2XIMP; 26/3/19: WID:RP-181480->RP-190224; 26/3/19: 0%->100 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
98 | 770029 | Study on V2X Media Handling and Interaction | FS_mV2X | 1 | Rel-16 | S4 | 2017-09-08 | 2019-09-12 | 70% | SP-170799 |  | Jung, Kyunghun, Samsung Electronics Co., Ltd | kyunghun.jung@samsung.com | 15/12/17: 26.985 added;; 15/12/17: 0%->30; 16/3/18: 30%->50; 22/3/18: FCD:09/18->12/18; 7/6/18: 50%->60. 14/06/18: Moved from Rel-15; 10/9/18: 60%->80; 13/12/18: 80%->60; 13/12/18: FCD:12/18->09/19; 12/3/19: 60%->70 | New; 26.985 | 77 | 39 |  |  | 2017-09-08 | 2019-03-12
99 | 830023 | Study on Security Aspects of 3GPP support for Advanced V2X Services | FS_eV2X_Sec | 1 | Rel-16 | S3 | 2019-03-07 | 2019-09-05 | 0% | SP-190108 |  | Joonwoong Kim, LG Electronics | joonwoong.kim@lge.com |  | New |  |  |  |  | 2019-03-14 | NA
100 | 830078 | 5G V2X with NR sidelink | 5G_V2X_NRSL | 1 | Rel-16 | R1 | 2019-03-01 | 2020-09-15 | 0% | RP-190766 |  | LG Electronics | [7 empty] | 2019-03-26 | NA
101 | 830178 | Core part: 5G V2X with NR sidelink | 5G_V2X_NRSL-Core | 2 | Rel-16 | R1 | 2019-03-01 | 2020-03-01 | 0% | RP-190766 |  | LG Electronics | [7 empty] | 2019-03-26 | NA
102 | 830278 | Perf. part: 5G V2X with NR sidelink | 5G_V2X_NRSL-Perf | 2 | Rel-16 | R4 | 2019-03-01 | 2020-09-15 | 0% | RP-190766 |  | LG Electronics | [7 empty] | 2019-03-26 | NA
103 | 0 | 5G Location and Positionning Services | - | 1 | Rel-16 |  | 2017-06-05 | 2017-06-05 | 56% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
104 | 800013 | 5G positioning services | 5G_HYPOS | 1 | Rel-16 | S1 | 2017-06-05 | 2018-12-14 | 100% | SP-180329 |  | Ries, Lionel, ESA | lionel.ries at esa.int |  | 22.261 | 80 | 41 |  |  | 2018-06-06 | NA
105 | 760006 | Study on positioning use cases | FS_5G_HYPOS | 2 | Rel-16 | S1 | 2017-06-05 | 2018-06-15 | 100% | SP-170589 |  | Ries, Lionel, ESA | lionel.ries@esa.int | 11/9/17: 0%->10; 15/12/17: 10%->50; 15/12/17: FCD:03/18->06/18; 16/3/18: 50%->75; 7/6/18: 75%->90; 10/9/18: 90%->100 | 22.872 | 76 | 39 |  |  | 2017-06-03 | 2018-09-10
106 | 800049 | Stage 1 of 5G_HYPOS | 5G_HYPOS | 2 | Rel-16 | S1 | 2018-06-06 | 2018-12-14 | 100% | SP-180329 |  | Ries, Lionel, ESA | lionel.ries at esa.int | 10/9/18: 0%->50; 10/9/18: FCD:09/18->12/18; 4/12/18: 50%->100 | 22.261 | 80 | 41 |  |  | 2018-06-06 | 2018-12-04
107 | 0 | Enhancement to the 5GC LoCation Services | 5G_eLCS | 1 | Rel-16 | S2 | 2017-12-15 | 2019-12-13 | 40% | SP-181119 |  | Ming Ai, CATT | aiming@catt.cn |  | 23.501; 23.502 | 82 |  |  |  | 2018-12-06 | NA
108 | 780028 | Study on Enhancement to the 5GC Location Services | FS_eLCS | 2 | Rel-16 | S2 | 2017-12-15 | 2019-03-14 | 100% | SP-180734 |  | Ming Ai, CATT | aiming@catt.cn | 16/3/18: 0%->15; 7/6/18: 15%->45; 10/9/18: 45%->55; 10/9/18: FCD:12/18->03/19; 2/10/18: WID:SP-170937->SP-180734; 7/12/18: 55%->100 | new 23.731 | 78 | 40 |  |  | 2017-12-15 | 2018-12-07
109 | 810035 | Study on Security of the enhancement to the 5GC location services | FS_eLCS_Sec | 2 | Rel-16 | S3 | 2018-09-06 | 2019-12-13 | 50% | SP-180694 |  | Wei Zhou, CATT | zhouwei@catt.cn | 7/12/18: 0%->5; 20/3/19: 5%->50 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-20
110 | 820016 | Stage 2 of 5G_eLCS | 5G_eLCS | 2 | Rel-16 | S2 | 2018-12-13 | 2019-06-20 | 45% | SP-181119 |  | Ming Ai, CATT | aiming@catt.cn | 14/3/19: 0%->45 | 23.501; 23.502 | 82 |  |  |  | 2018-12-06 | 2019-03-14
111 | 830003 | CT aspects of 5G_eLCS | 5G_eLCS | 2 | Rel-16 | ct | 2019-03-07 | 2019-12-05 | 0% | CP-190014 |  | Tingfang Tang, CATT | tangtingfang@catt.cn | [6 empty] | 2018-12-06 | NA
112 | 830044 | CT1 aspects of 5G_eLCS | 5G_eLCS | 3 | Rel-16 | C1 | 2019-03-07 | 2019-12-05 | 0% | CP-190190 |  | Tingfang Tang, CATT | tangtingfang@catt.cn |  | 24.501; 27.007 |  |  |  |  | 2018-12-06 | NA
113 | 830045 | CT3 aspects of 5G_eLCS | 5G_eLCS | 3 | Rel-16 | C3 | 2019-03-07 | 2019-12-05 | 0% | CP-190190 |  | Tingfang Tang, CATT | tangtingfang@catt.cn |  | 29.522; 29.122 |  |  |  |  | 2018-12-06 | NA
114 | 830046 | CT4 aspects of 5G_eLCS | 5G_eLCS | 3 | Rel-16 | C4 | 2019-03-07 | 2019-12-05 | 0% | CP-190190 |  | Tingfang Tang, CATT | tangtingfang@catt.cn |  | 24.080; 29.518; 29.572; 29.503; 29.505 |  |  |  |  | 2018-12-06 | NA
115 | 830077 | NR positioning support | NR_pos | 1 | Rel-16 | R1 | 2018-06-15 | 2020-09-15 | 18% | RP-190752 |  | Intel | [7 empty] | 2019-03-26 | NA
116 | 800092 | Study on NR positioning support | FS_NR_pos | 2 | Rel-16 | R1 | 2018-06-15 | 2019-03-15 | 100% | RP-181399 |  | Intel |  | TR 38.8xx; 26/3/19: 0%->100 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
117 | 830073 | Study on local NR positioning in NG-RAN | FS_NR_local_pos | 2 | Rel-16 | R3 | 2019-03-01 | 2019-12-15 | 0% | RP-190754 |  | CMCC | [7 empty] | 2019-03-26 | NA
118 | 830177 | Core part: NR positioning support | NR_pos-Core | 2 | Rel-16 | R1 | 2019-03-01 | 2020-03-01 | 0% | RP-190752 |  | Intel | [7 empty] | 2019-03-26 | NA
119 | 830277 | Perf. part: NR positioning support | NR_pos-Perf | 2 | Rel-16 | R4 | 2019-03-01 | 2020-09-15 | 0% | RP-190752 |  | Intel | [7 empty] | 2019-03-26 | NA
120 | 0 | UE radio capability signalling optimization | - | 1 | Rel-16 |  | 2018-06-06 | 2018-06-06 | 17% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
121 | 800025 | Study on optimisations on UE radio capability signalling | FS_RACS | 1 | Rel-16 | S2 | 2018-06-06 | 2018-12-14 | 100% | SP-180599 |  | Haris Zisimopoulos, Qualcomm Incorporated | harisz@qti.qualcomm.com | 10/9/18: 0%->40; 7/12/18: 40%->70; 14/3/19: 70%->100 | New | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
122 | 830027 | Optimisations on UE radio capability signalling | RACS | 1 | Rel-16 | S2 | 2019-03-07 | 2019-06-06 | 0% | SP-190180 |  | Haris Zisimopoulos | harisz@qti.qualcomm.com |  | 23.501; 23.502; 23.401 |  |  |  |  | 2019-03-14 | NA
123 | 830079 | Optimisations on UE radio capability signalling – NR/E-UTRA Aspects | RACS-RAN | 1 | Rel-16 | R2 | 2018-06-15 | 2020-03-01 | 43% | RP-190657 |  | MediaTek | [7 empty] | 2019-03-26 | NA
124 | 800097 | Study on optimisations on UE radio capability signalling – NR/E-UTRA Aspects | FS_RACS_RAN | 2 | Rel-16 | R2 | 2018-06-15 | 2019-03-15 | 100% | RP-181459 |  | MediaTek |  | TR 37.8xx; related SA2 SI FS_RACS was started at SA #80 ; 6/8/18: 37.873 added;; 26/3/19: 0%->100 | 37.873 | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
125 | 830179 | Core part: Optimisations on UE radio capability signalling – NR/E-UTRA Aspects | RACS-RAN-Core | 2 | Rel-16 | R2 | 2019-03-01 | 2020-03-01 | 0% | RP-190657 |  | MediaTek | [7 empty] | 2019-03-26 | NA
126 | 0 | Satellite Access in 5G | - | 1 | Rel-16 |  | 2017-09-08 | 2017-09-08 | 35% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
127 | 800010 | Integration of Satellite Access in 5G | 5GSAT | 1 | Rel-16 | S1 | 2017-09-08 | 2018-09-14 | 100% | SP-180326 |  | MICHEL, Cyril, Thales | cyril.michel@thalesaleniaspace.com |  | 22.261 | 80 | 41 |  |  | 2018-06-06 | NA
128 | 770002 | Study on using Satellite Access in 5G | FS_5GSAT | 2 | Rel-16 | S1 | 2017-09-08 | 2018-06-15 | 100% | SP-170702 |  | MICHEL, Cyril | cyril.michel@thalesaleniaspace.com | 15/12/17: 22.822 added;; 15/12/17: 0%->30; 15/12/17: FCD:12/17->06/18; 16/3/18: 30%->70; 7/6/18: 70%->100 | New; 22.822 | 77 | 39 |  |  | 2017-09-08 | 2018-06-07
129 | 800048 | Stage 1 of 5GSAT | 5GSAT | 2 | Rel-16 | S1 | 2018-06-06 | 2018-09-14 | 100% | SP-180326 |  | MICHEL, Cyril, Thales | cyril.michel@thalesaleniaspace.com | 10/9/18: 0%->95; 4/12/18: 95%->100 | 22.261 | 80 | 41 |  |  | 2018-06-06 | 2018-12-04
130 | 800026 | Study on architecture aspects for using satellite access in 5G | FS_5GSAT_ARCH | 1 | Rel-16 | S2 | 2018-06-06 | 2019-09-12 | 50% | SP-181253 |  | MICHEL, Cyril | cyril.michel@thalesaleniaspace.com | 10/9/18: 0%->15; 10/9/18: FCD:06/19->03/19; 7/12/18: 15%->35; 14/12/18: WID:SP-180505->SP-181253; 14/12/18: FCD:03/19->09/19; 14/3/19: 35%->50 | New | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
131 | 800099 | Study on solutions for NR to support non-terrestrial networks (NTN) | FS_NR_NTN_solutions | 1 | Rel-16 | R3 | 2018-06-15 | 2019-12-15 | 0% | RP-190710 |  | Thales |  | TR 38.8xx; compare REL-15 SI FS_NR_nonterr_nw; 26/3/19: WID:RP-181370->RP-190710 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
132 | 830025 | Study on management and orchestration aspects with integrated satellite components in a 5G network | FS_5GSAT_MO | 1 | Rel-16 | S5 | 2019-03-14 | 2019-12-12 | 0% | SP-190138 |  | MICHEL, Cyril, THALES | cyril.michel@thalesaleniaspace.com |  | New |  |  |  |  | 2019-03-14 | NA
133 | 0 | Enablers for Network Automation Architecture for 5G | - | 1 | Rel-16 |  | 2017-06-05 | 2017-06-05 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
134 | 830047 | Enablers for Network Automation for 5G | eNA | 1 | Rel-16 | S2 | 2017-06-05 | 2019-12-05 | 48% | SP-181123 |  | Xiaobo Wu, Huawei Technologies | wuxiaobo@huawei.com |  | 23.501; 23.502; 23.503 | 82 |  |  |  | 2018-12-06 | NA
135 | 760047 | Study of enablers for Network Automation for 5G | FS_eNA | 2 | Rel-16 | S2 | 2017-06-05 | 2018-12-14 | 94% | SP-180792 |  | Xiaobo Wu, Huawei Technologies | wuxiaobo@huawei.com | 16/3/18: FCD:09/18->06/18; 16/3/18: 0%->15; 7/6/18: 15%->30; 15/6/18: WID:SP-170383->SP-180613; 15/6/18: FCD:06/18->09/18; 10/9/18: 30%->50; 10/9/18: FCD:09/18->12/18; 2/10/18: WID:SP-180613->SP-180792; 7/12/18: 50%->90; 14/3/19: 90%->94 | new 23.791 | 76 | 39 |  |  | 2017-06-03 | 2019-03-14
136 | 820020 | Stage 2 of eNA | eNA | 2 | Rel-16 | S2 | 2018-12-06 | 2019-06-17 | 50% | SP-181123 |  | Xiaobo Wu, Huawei Technologies | wuxiaobo@huawei.com | 14/3/19: 0%->50 | 23.501; 23.502; 23.503 | 82 |  |  |  | 2018-12-06 | 2019-03-14
137 | 830009 | CT aspects of eNA | eNA | 2 | Rel-16 | ct | 2019-03-07 | 2019-12-05 | 0% | CP-190194 |  | Yali Yan, Huawei | yanyali@huawei.com |  |  | 82 |  |  |  | 2018-12-06 | NA
138 | 830048 | CT3 aspects of eNA | eNA | 3 | Rel-16 | C3 | 2019-03-07 | 2019-12-05 | 0% | CP-190194 |  | Yali Yan, Huawei | yanyali@huawei.com |  | 29.122; 29.508; 29.514; 29.520; 29.522; 29.523; 29.554 | 82 |  |  |  | 2018-12-06 | NA
139 | 830049 | CT4 aspects of eNA | eNA | 3 | Rel-16 | C4 | 2019-03-07 | 2019-12-05 | 0% | CP-190194 |  | Yali Yan, Huawei | yanyali@huawei.com |  | 29.244; 29.510; 29.518; 29.503; 29.505 | 82 |  |  |  | 2018-12-06 | NA
140 | 0 | Wireless and Wireline Convergence Enhancement | - | 1 | Rel-16 |  | 2017-06-05 | 2017-06-05 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
141 | 760044 | Study on the Wireless and Wireline Convergence for the 5G system architecture | FS_5WWC | 1 | Rel-16 | S2 | 2017-06-05 | 2018-12-14 | 100% | SP-170380 |  | Marco Spini, Huawei Technologies | m.spini@huawei.com | 11/9/17: 0%->15; 15/12/17: Changed Rel-15->Rel-16; 16/3/18: 15%->25; 7/6/18: 25%->35; 10/9/18: 35%->60; 10/9/18: FCD:06/18->12/18; 7/12/18: 60%->100 | 23.716 | 76 | 39 |  |  | 2017-06-03 | 2018-12-07
142 | 800031 | Study on the security of the Wireless and Wireline Convergence for the 5G system architecture | FS_5WWC_SEC | 1 | Rel-16 | S3 | 2018-06-06 | 2019-09-12 | 60% | SP-180438 |  | He Li, Huawei Technologies | LIHE2@HUAWEI.COM | 6/8/18: 33.807 added;; 10/9/18: 0%->5; 7/12/18: 5%->30; 20/3/19: 30%->60; 20/3/19: FCD:019->09/19 | New; 33.807 | 80 | 41 |  |  | 2018-06-06 | 2019-03-20
143 | 830050 | Wireless and Wireline Convergence for the 5G system architecture | 5WWC | 1 | Rel-16 |  | 2018-12-06 | 2019-12-15 | 7% | SP-181117 |  | Marco Spini, Huawei Technologies | m.spini@huawei.com |  | 23.501; 23.502; 23.503 | 82 |  |  |  | 2018-12-06 | NA
144 | 820014 | Stage 2 of 5WWC | 5WWC | 2 | Rel-16 | S2 | 2018-12-06 | 2019-06-13 | 50% | SP-181117 |  | Marco Spini, Huawei Technologies | m.spini@huawei.com | 14/3/19: 0%->50 | 23.501; 23.502; 23.503 | 82 |  |  |  | 2018-12-06 | 2019-03-14
145 | 820014 | CT aspects of 5WWC | 5WWC | 2 | Rel-16 | ct | 2019-03-07 | 2019-12-05 | 0% | CP-190200 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | [6 empty] | 2018-12-06 | NA
146 | 820014 | CT1 aspects of 5WWC | 5WWC | 3 | Rel-16 | C1 | 2019-03-07 | 2019-12-05 | 0% | CP-190200 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 24.501; 24.502; 24.526 |  |  |  |  | 2018-12-06 | NA
147 | 820014 | CT3 aspects of 5WWC | 5WWC | 3 | Rel-16 | C3 | 2019-03-07 | 2019-12-05 | 0% | CP-190200 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 29.512; 29.513; 29.514; 29.507; 29.122; 29.522 |  |  |  |  | 2018-12-06 | NA
148 | 820014 | CT4 aspects of 5WWC | 5WWC | 3 | Rel-16 | C4 | 2019-03-07 | 2019-12-05 | 0% | CP-190200 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 23.003; 29.518; 29.502; 29.509; 29.244; 29.503; 29.571; 29.505 |  |  |  |  | 2018-12-06 | NA
149 | 830082 | NG interface usage for WWC | 5WWC-NG_interface | 2 | Rel-16 | R3 | 2019-03-01 | 2019-12-15 | 0% | RP-190772 |  | Huawei | [7 empty] | 2019-03-26 | NA
150 | 830182 | Core part: NG interface usage for WWC | 5WWC-NG_interface-Core | 3 | Rel-16 | R3 | 2019-03-01 | 2019-12-15 | 0% | RP-190772 |  | Huawei | [7 empty] | 2019-03-26 | NA
151 | 0 | Mission Critical, Public Warning, Railways and Maritime | - | 1 | Rel-16 |  | 2016-09-19 | 2016-09-19 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
152 | 790024 | Study on MC services access aspects | FS_MCSAA | 1 | Rel-16 | S6 | 2018-03-15 | 2019-06-12 | 75% | SP-181135 |  | Joakim Åkesson, Ericsson | Joakim.akesson@ericsson.com | 19/4/18: 0%->5; 14/6/18: 5%->15; 15/6/18: WID:SP-180163->SP-180385; 15/6/18: FCD:12/18->03/19; 6/8/18: 23.778 added;; 10/9/18: 15%->25; 7/12/18: 25%->70; 14/12/18: WID:SP-180385->SP-181135; 14/3/19: FCD:03/19->06/19; 14/3/19: 70%->75 | new TR 23.xxx; 23.778 | 79 | 40 |  |  | 2018-03-15 | 2019-03-14
153 | 800024 | Study into discreet listening and logging for mission critical services | FS_MCLOG | 1 | Rel-16 | S6 | 2018-06-06 | 2019-06-12 | 75% | SP-181138 |  | Chater-Lea, David, Motorola Solutions | david.chater-lea@motorolasolutions.com | 6/8/18: 23.784 added;; 10/9/18: 0%->10; 7/12/18: 10%->50; 7/12/18: FCD:03/19->06/19; 14/12/18: WID:SP-180384->SP-181138; 14/3/19: 50%->75 | New; 23.784 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
154 | 810055 | Study on location enhancements for mission critical services | FS_enhMCLoc | 1 | Rel-16 | S6 | 2018-09-14 | 2019-09-12 | 45% | SP-180921 |  | Dom Lazara, Motorola Solutions | dom.lazara@motorolasolutions.com | 7/12/18: 0%->20; 14/3/19: 20%->45; 14/3/19: FCD:03/19->09/19 |  | 81 | 41 |  |  | 2018-09-14 | 2019-03-14
155 | 800022 | Enhanced Mission Critical Push-to-talk architecture phase 2 | enh2MCPTT | 1 | Rel-16 | S6 | 2018-06-06 | 2019-06-12 | 60% | SP-190068 |  | Dom Lazara; Motorola Solutions | Dom.Lazara@motorolasolutions.com | 10/9/18: 0%->5; 7/12/18: 5%->35; 14/3/19: 35%->60; 14/3/19: FCD:03/19->06/19; 21/3/19: WID:SP-180382->SP-190068 | 23.280; 23.379; 23.281; 23.282; 23.283 | 80 | 41 |  |  | 2018-06-06 | 2019-03-21
156 | 830051 | Enhancements to Functional architecture and information flows for Mission Critical Data | eMCData2 | 1 | Rel-16 | S6 | 2018-06-06 | 2019-12-12 | 43% | SP-180378 |  | Shih, Jerry, AT&T | jerry.shih@att.com | 10/9/18: 0%->10; 7/12/18: 10%->40 |  | 80 | 41 |  |  | 2018-06-06 | 2018-12-07
157 | 800018 | Stage 2 of eMCData2 | eMCData2 | 2 | Rel-16 | S6 | 2018-06-06 | 2019-06-14 | 75% | SP-180378 |  | Shih, Jerry, AT&T | jerry.shih@att.com | 10/9/18: 0%->10; 7/12/18: 10%->40; 14/3/19: 40%->75 | 23.280; 23.282 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
158 | 830014 | CT aspects of eMCData2 | eMCData2 | 2 | Rel-16 | C1 | 2019-03-14 | 2019-12-12 | 0% | CP-190199 |  | Val Oprescu (AT&T) | vo4887@att.com |  | 24.282; 24.582; 24.483; 24.484; 24.zzz |  |  |  |  | 2018-06-06 | NA
159 | 800023 | Study on Mission Critical services support over 5G System | FS_MCOver5GS | 1 | Rel-16 | S6 | 2018-06-06 | 2019-09-12 | 35% | SP-181136 |  | Verweij, Kees, The Police of the Netherlands | kees.verweij@politie.nl | 6/8/18: 23.783 added;; 10/9/18: 0%->5; 7/12/18: 5%->35; 7/12/18: FCD:03/19->09/19; 14/12/18: WID:SP-180383->SP-181136. 03/19: Rel corrected (was shown as Rel-17) | New; 23.783 | 80 | 41 |  |  | 2018-06-06 | 2018-12-14
160 | 810004 | MCData File Distribution support over xMB | MC_XMB | 1 | Rel-16 | S4 | 2018-09-06 | 2019-06-07 | 90% | SP-180665 |  | Thiénot Cédric, Expway | cedric.thienot@expway.com | 7/12/18: 0%->80; 7/3/19: 80%->90; 7/3/19: FCD:03/19->06/19 | 26.348 | 81 | 41 |  |  | 2018-09-06 | 2019-03-07
161 | 810011 | Protocol enhancements for Mission Critical Services | MCProtoc16 | 1 | Rel-16 | C1 | 2018-09-06 | 2019-12-20 | 40% | CP-182110 |  | AXELL, Jörgen | jorgen.axell@ericsson.com | 7/12/18: 0%->20; 14/3/19: 20%->40 | 24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 24.980 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
162 | 800053 | MBMS APIs for Mission Critical Services | MBMSAPI_MCS | 1 | Rel-16 | S6 | 2017-06-05 | 2019-03-14 | 96% | SP-180380 |  | Ling Zhang, TD Tech Ltd. | zhangling@td-tech.com |  | New | 80 | 41 |  |  | 2018-06-06 | NA
163 | 760051 | Study on MBMS APIs for MC Services | FS_MBMSAPI_MC | 2 | Rel-16 | S6 | 2017-06-05 | 2018-06-15 | 100% | SP-180237 |  | Ling Zhang, TD Tech Ltd | zhangling@td-tech.com | 12/7/17: WID:SP-170596->SP-170598; 11/9/17: 0%->10; 15/12/17: 10%->20; 15/12/17: Changed Rel-15->Rel-16; 16/3/18: 20%->60; 23/3/18: WID:SP-170598->SP-180237; 23/3/18: FCD:03/18->06/18; 14/6/18: 60%->100 | new 23.792 | 76 | 39 |  |  | 2017-06-03 | 2018-06-14
164 | 800020 | Stage 2 of MBMS APIs for MC Services | MBMSAPI_MCS | 2 | Rel-16 | S6 | 2018-06-06 | 2019-03-14 | 90% | SP-180380 |  | Ling Zhang, TD Tech Ltd. | zhangling@td-tech.com | 6/8/18: 23.479 added;; 10/9/18: 0%->15; 7/12/18: 15%->65; 14/3/19: 65%->90 | New; 23.479 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
165 | 800019 | Enhanced Mission Critical System Migration and Interconnection | eMCSMI | 1 | Rel-16 | S6 | 2018-06-06 | 2019-06-12 | 50% | SP-180379 |  | Chater-Lea, David; Motorola Solutions | david.chater-lea@motorolasolutions.com | 10/9/18: 0%->5; 7/12/18: 5%->10; 7/12/18: FCD:03/19->06/19; 14/3/19: 10%->50 | 23.280; 23.379; 23.281; 23.282; 23.283 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
166 | 810054 | Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems | eMCCI | 1 | Rel-16 |  | 2018-06-06 | 2019-06-14 | 40% |  |  | Monnes, Peter, Harris Corporation | pmonnes@harris.com |  |  | 80 | 41 |  |  | 2018-09-10 | NA
167 | 800021 | Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems | eMCCI | 2 | Rel-16 | S6 | 2018-06-06 | 2019-06-14 | 40% | SP-180680 |  | Monnes, Peter, Harris Corporation | pmonnes at harris dot com | 10/9/18: 0%->5; 2/10/18: WID:SP-180381->SP-180680; 7/12/18: 5%->15; 14/3/19: 15%->40 | 23.283 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
168 | 800016 | Stage 3 for MC Communication Interworking with Land Mobile Radio Systems | MCCI_CT | 1 | Rel-16 | C1 | 2018-06-06 | 2019-09-12 | 60% | CP-190203 |  | Monnes, Peter, Harris Corporation | pmonnes@harris.com | 10/9/18: 5%->15; 7/12/18: 15%->45; 10/12/18: FCD:12/18->06/19; 10/12/18: WID:CP-181187->CP-183247. 06/03/19: both name and acronym changed (was MCCI3); 14/3/19: 45%->60; 18/3/19: WID:CP-183248->CP-190203; 18/3/19: FCD:019->09/19 | 24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 | 80 | 41 |  |  | 2018-06-06 | 2019-03-18
169 | 820040 | Mission Critical system migration and interconnection | MCSMI_CT | 1 | Rel-16 | C1 | 2018-12-13 | 2019-12-12 | 0% | CP-190143 |  | Dom Lazara, Motorola Solutions | dom.lazara@motorolasolutions.com | ; 18/3/19: FCD:019->12/19; 18/3/19: WID:CP-183244->CP-190143 | 24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 | 82 |  |  |  | 2018-12-07 | 2019-03-18
170 | 800032 | Mission Critical Services Security Enhancements | MCXSec | 1 | Rel-16 | S3 | 2018-06-06 | 2019-09-12 | 0% | SP-180596 |  | Woodward, Tim, Motorola Solutions, Inc |  | 10/9/18: 0%->40; 7/12/18: 40%->50; 20/3/19: FCD:019->09/19; 20/3/19: 50%->0 | 33.18 | 80 | 41 |  |  | 2018-06-06 | 2019-03-20
171 | 780003 | Enhancements of Public Warning System | ePWS | 1 | Rel-16 |  | 2016-09-19 | 2019-12-13 | 41% | SP-170998 |  | Hyounhee Koo, SyncTechno Inc. | koo at synctechno dot com | 16/3/18: 0%->100 |  | 80 | 41 |  |  | 2017-12-15 | 2018-03-16
172 | 730005 | Study on enhancements of Public Warning System | FS_ePWS | 2 | Rel-16 | S1 | 2016-09-19 | 2017-09-14 | 100% | SP-160733 |  | SyncTechno Inc., Hyounhee Koo | koo at synctechno dot com | 22.xxx; 1/12/16: 0%->5; 2/3/17: 5%->45; 7/6/17: 45%->75; 30/6/17: 22.869 added;; 25/8/17: 75%->95; 15/12/17: 95%->100 | 22.869 | 73 | 37 |  |  | 2016-09-19 | 2017-12-15
173 | 800052 | Stage 1 of ePWS | ePWS | 2 | Rel-16 | S1 | 2017-12-15 | 2018-12-14 | 100% | SP-170998 |  | Hyounhee Koo, SyncTechno Inc. | koo at synctechno dot com | 16/3/18: 0%->100 |  | 80 | 41 |  |  | 2017-12-15 | 2018-03-16
174 | 810012 | CT aspects of enhancements of Public Warning System | ePWS | 2 | Rel-16 | ct | 2018-09-06 | 2019-12-13 | 0% | CP-182228 |  | TaeHyeon Kim, SyncTechno Inc. | kim at synctechno dot com |  |  | 81 | 41 |  |  | 2018-09-06 | NA
175 | 810053 | Study on stages 2 and 3 of enhancements of ePWS | ePWS | 3 | Rel-16 | C1 | 2018-09-10 | 2019-06-14 | 30% | CP-182228 |  | TaeHyeon Kim, SyncTechno Inc. | kim at synctechno dot com | 7/12/18: 0%->10; 21/3/19: 10%->30 | New | 81 | 41 |  |  | 2018-09-10 | 2019-03-21
176 | 810047 | CT1 aspects of ePWS | ePWS | 3 | Rel-16 | C1 | 2018-09-06 | 2019-06-14 | 0% | CP-182228 |  | TaeHyeon Kim, SyncTechno Inc. | kim at synctechno dot com | 14/3/19: 0%->30 | 23.041 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
177 | 810048 | CT4 aspects of ePWS (Possible impacts) | ePWS | 3 | Rel-16 | C4 | 2018-09-06 | 2019-12-13 | 0% | CP-182228 |  | TaeHyeon Kim, SyncTechno Inc. | kim at synctechno dot com |  | 29.168 | 81 | 41 |  |  | 2018-09-06 | NA
178 | 760054 | Mobile Communication System for Railways 2 | MONASTERY2 | 1 | Rel-16 |  | 2017-06-05 | 2019-06-14 | 95% | SP-170451 |  | Merkel, Juergen, Nokia | juergen.merkel@nokia.com | 15/12/17: 10%->35 | New 22.289; 22.280; 22.281; 22.282; 22.179 | 76 | 39 |  |  | 2017-06-03 | 2017-12-15
179 | 760005 | Study on MONASTERY2 | FS_FRMCS2 | 2 | Rel-16 | S1 | 2017-06-05 | 2019-06-14 | 100% | SP-170588 |  | Merkel, Juergen, Nokia | juergen.merkel@nokia.com | 15/12/17: 35%->50; 16/3/18: 50%->80; 7/6/18: 80%->85; 10/9/18: FCD:06/18->06/19; 4/12/18: 85%->100 | New 22.889 | 76 | 39 |  |  | 2017-06-03 | 2018-12-04
180 | 790023 | Study on application architecture for the Future Railway Mobile Communication System (FRMCS) Phase 2 | FS_FRMCS2_SA6 | 2 | Rel-16 | S6 | 2018-03-15 | 2019-03-12 | 100% | SP-181133 |  | Oettl, Martin, Nokia | martin(dot)oettl(at)nokia(dot)com | 19/4/18: 0%->5; 14/6/18: 5%->15; 6/8/18: 23.796 added;; 10/9/18: 15%->20; 7/12/18: 20%->65; 7/12/18: FCD:12/18->03/19; 14/3/19: 65%->100 | TR 23.cde; 23.796 | 79 | 40 |  |  | 2018-03-15 | 2019-03-14
181 | 760004 | Stage 1 of MONASTERY2 | MONASTERY2 | 2 | Rel-16 | S1 | 2017-06-05 | 2018-12-14 | 100% | SP-170451 |  | Merkel, Juergen, Nokia | juergen.merkel@nokia.com | 16/3/18: 35%->55; 7/6/18: 55%->70; 7/6/18: FCD:06/18->12/18; 10/9/18: 70%->75; 4/12/18: 75%->100 | New 22.289; 22.280; 22.281; 22.282; 22.179 | 76 | 39 |  |  | 2017-06-03 | 2018-12-04
182 | 830007 | Application Architecture for MONASTERY2 | MONASTERY2 | 2 | Rel-16 | S6 | 2019-03-14 | 2019-06-13 | 0% | SP-190064 |  | Oettl, Martin, Nokia | martin(dot)oettl(at)nokia(dot)com |  | 23.280; 23.379; 23.281; 23.282 |  |  |  |  | 2019-03-14 | NA
183 | 800011 | Maritime Communication Services over 3GPP System | MARCOM | 1 | Rel-16 | S1 | 2016-09-19 | 2018-12-13 | 100% | SP-180594 |  | Hyounhee Koo, SyncTechno Inc | koo at synctechno dot com |  | 22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468 | 80 | 41 |  |  | 2018-06-06 | NA
184 | 730007 | Study on Maritime Communication Services over 3GPP system | FS_MARCOM | 2 | Rel-16 | S1 | 2016-09-19 | 2018-06-15 | 100% | SP-170453 |  | SyncTechno Inc., Hyounhee Koo | koo at synctechno dot com | 22.xxx; 1/12/16: 0%->10; 2/3/17: 10%->15; 2/3/17: WID:SP-160556->SP-170166; 10/3/17: FCD:06/17->06/20; 21/3/17: 22.819 added;; 8/6/17: WID:SP-170166->SP-170453; 25/8/17: 15%->35; 15/12/17: 35%->55; 16/3/18: 55%->75; 7/6/18: 75%->95; 10/9/18: 95%->100 | 22.819 | 73 | 37 |  |  | 2016-09-19 | 2018-09-10
185 | 800051 | Stage 1 of MARCOM | MARCOM | 2 | Rel-16 | S1 | 2018-06-06 | 2018-12-13 | 100% | SP-180594 |  | Hyounhee Koo, SyncTechno Inc | koo at synctechno dot com | 10/9/18: 0%->70; 4/12/18: 70%->95; 14/3/19: 95%->100 | 22.119; 22.179; 22.280; 22.281; 22.282; 22.261; 22.346; 22.468 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
186 | 0 | Streaming and TV | - | 1 | Rel-16 |  | 2016-12-01 | 2019-06-05 | 68% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
187 | 800008 | Enhancement of LTE for Efficient delivery of Streaming Service | eLSTR | 1 | Rel-16 | S1 | 2016-12-01 | 2018-09-14 | 100% | SP-180322 |  | Xia, Xu, China Telecom | xiaxu.bri@chinatelecom.cn |  | 22.278; 22.115 | 80 | 41 |  |  | 2018-06-06 | NA
188 | 740001 | Study on eLSTR | FS_eLESTR | 2 | Rel-16 | S1 | 2016-12-01 | 2018-03-15 | 100% | SP-160960 |  | China Telecommunications, XIA Xu | xiaxu@ctbri.com.cn | 2/3/17: 0%->20; 7/6/17: 20%->50; 11/9/17: 50%->70; 15/12/17: 70%->75; 15/12/17: FCD:09/17->03/18; 16/3/18: 75%->100 | 22.833 | 74 | 38 |  |  | 2016-12-01 | 2018-03-16
189 | 800054 | Stage 1 of eLSTR | eLSTR | 2 | Rel-16 | S1 | 2018-05-08 | 2018-09-14 | 100% | SP-180322 |  | Xia, Xu, China Telecom | xiaxu.bri@chinatelecom.cn | 15/6/18: FCD:06/18->09/18; 10/9/18: 90%->100 | 22.278; 22.115 | 80 | 41 |  |  | 2018-06-06 | 2018-09-10
190 | 800001 | Enhancements to Framework for Live Uplink Streaming | E-FLUS | 1 | Rel-16 | S4 | 2018-06-06 | 2019-09-20 | 45% | SP-180285 |  | Lo, Charles, Qualcomm Incorporated | clo@qti.qualcomm.com | 10/9/18: 0%->20; 7/12/18: 20%->40; 7/3/19: 40%->45; 7/3/19: FCD:03/19->09/19 | 26.238; 26.939 | 80 | 41 |  |  | 2018-06-06 | 2019-03-07
191 | 810003 | Coverage and Handoff Enhancements for Multimedia | CHEM | 1 | Rel-16 | S4 | 2018-09-06 | 2019-06-07 | 80% | SP-180664 |  | Nikolai Leung | nleung@qti.qualcomm.com | 7/12/18: 0%->70; 7/3/19: 70%->80; 7/3/19: FCD:03/19->06/19 | 26.114 | 81 | 41 |  |  | 2018-09-06 | 2019-03-07
192 | 770027 | Study on QoE metrics for VR | FS_QoE_VR | 1 | Rel-16 | S4 | 2017-09-08 | 2019-09-20 | 55% | SP-170614 |  | Ericsson (Gunnar Heikkilä | gunnar.heikkila@ericsson.com | 15/12/17: 26.929 added;; 15/12/17: 26.119 added;; 15/12/17: FCD:06/18->09/18; 15/12/17: 0%->10; 16/3/18: 10%->15; 7/6/18: 15%->20; 7/6/18: FCD:09/18->12/18. 14/06/18: Moved from Rel-15; 10/9/18: 20%->25; 12/3/19: 25%->55; 12/3/19: FCD:12/18->09/19 | New; 26.929; 26.119 | 77 | 39 |  |  | 2017-09-08 | 2019-03-12
193 | 760039 | Study on 5G enhanced Mobile Broadband Media Distribution | FS_5GMedia_Distribution | 1 | Rel-16 | S4 | 2017-06-05 | 2018-09-14 | 75% | SP-170334 |  | Bouazizi, Imed, Samsung Electronics Co., Ltd., | i (dot) Bouazizi (at) Samsung (dot) com | 11/9/17: 0%->10; 15/12/17: FCD:03/18->06/20; 15/12/17: 10%->25; 16/3/18: 25%->60; 7/6/18: 60%->70; 7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15; 10/9/18: 70%->75 | 26.8xx | 76 | 39 |  |  | 2017-06-03 | 2018-09-10
194 | 820002 | Media streaming architecture | 5GMSA | 1 | Rel-16 | S4 | 2018-12-06 | 2019-06-12 | 0% | SP-180984 |  | Frédéric GABIN | Frederic.gabin@ericsson.com |  | 26.501; 26.233 | 82 |  |  |  | 2018-12-07 | NA
195 | 810040 | Media Handling Extensions for 5G Conversational Services | 5G_MEDIA_MTSI_ext | 1 | Rel-16 | S4 | 2017-06-05 | 2019-09-13 | 78% | SP-180663 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com |  | 26.114 | 81 | 41 |  |  | 2018-09-06 | NA
196 | 760041 | Study on Media Handling Aspects of Conversational Services in 5G Systems | FS_5G_MEDIA_MTSI | 2 | Rel-16 | S4 | 2017-06-05 | 2018-09-15 | 100% | SP-170336 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com | 11/9/17: 0%->5; 15/12/17: 5%->35; 16/3/18: 35%->55; 16/3/18: FCD:03/18->09/18; 7/6/18: 55%->80. 14/06/18: Moved from Rel-15; 10/9/18: 80%->100 | 26.919 | 76 | 39 |  |  | 2017-06-03 | 2018-09-10
197 | 810002 | Media Handling Extensions for 5G Conversational Services | 5G_MEDIA_MTSI_ext | 2 | Rel-16 | S4 | 2018-09-06 | 2019-09-13 | 50% | SP-180663 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com | 7/12/18: 0%->35; 7/3/19: 35%->50 | 26.114 | 81 | 41 |  |  | 2018-09-06 | 2019-03-07
198 | 770031 | Study on EVS Float Conformance Non Bit-Exact | FS_EVS_FCNBE | 1 | Rel-16 | S4 | 2017-09-08 | 2018-09-14 | 100% | SP-170618 |  | Fabrice Plante, Intel | fabrice.m.plante@intel.com | 15/12/17: 26.843 added;; 15/12/17: 0%->50; 16/3/18: 50%->60; 16/3/18: FCD:03/18->06/18; 7/6/18: 60%->70; 7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15; 10/9/18: 70%->100 | New; 26.843 | 77 | 39 |  |  | 2017-09-08 | 2018-09-10
199 | 820001 | EVS Floating-point Conformance for Non Bit-Exact | EVS_FCNBE | 1 | Rel-16 | S4 | 2018-06-06 | 2019-09-12 | 25% | SP-180983 |  | Fabrice, Plante, Intel | fabrice.m.plante@intel.om | ; 7/3/19: 0%->25; 7/3/19: 0%->25; 7/3/19: 0%->25. CANNOT CHANGE STARTING DATE… Real one: Thu 06/12/18 | 26.444 | 82 |  |  |  | 2018-06-06 | 2019-03-07
200 | 800003 | Addition of HLG HDR to TV Video Profiles | HLG_HDR | 1 | Rel-16 | S4 | 2018-06-06 | 2018-09-14 | 100% | SP-180287 |  | Paul Szucs, Sony Europe Limited | paul.szucs@sony.com | 10/9/18: 0%->100 | 26.116; 26.346; 26.234 | 80 | 41 |  |  | 2018-06-06 | 2018-09-10
201 | 0 | User Identities, Authentication, multi-device | - | 1 | Rel-16 |  | 2017-12-15 | 2017-12-15 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
202 | 800012 | User Identities and Authentication | UIA | 1 | Rel-16 | S1 | 2017-12-15 | 2018-09-14 | 100% | SP-180328 |  | Bischinger, Kurt; Deutsche Telekom | kurt.bischinger@t-mobile.at |  | 22.101; 22.115 | 80 | 41 |  |  | 2018-06-06 | NA
203 | 780004 | Study on a Layer for User Centric Identifiers and Authentication | FS_LUCIA | 2 | Rel-16 | S1 | 2017-12-15 | 2018-06-14 | 100% | SP-170995 |  | Bischinger, Kurt; Deutsche Telekom | kurt.bischinger@t-mobile.at | 16/3/18: 0%->60; 7/6/18: 60%->90; 10/9/18: 90%->100 | 22.904 | 78 | 40 |  |  | 2017-12-15 | 2018-09-10
204 | 800050 | Stage 1 of User Identities and Authentication | UIA | 2 | Rel-16 | S1 | 2018-06-06 | 2018-09-14 | 100% | SP-180328 |  | Bischinger, Kurt; Deutsche Telekom | kurt.bischinger@t-mobile.at | 10/9/18: 0%->100 | 22.101; 22.115 | 80 | 41 |  |  | 2018-06-06 | 2018-09-10
205 | 810044 | Multi-device and multi-identity | MuD | 1 | Rel-16 | S1 | 2018-06-06 | 2019-06-14 | 24% | SP-180315 |  | Peter Bleckert, Ericsson | Peter.Bleckert@ericsson.com |  |  | 80 | 41 |  |  | 2018-06-06 | NA
206 | 800004 | Stage 1 of Multi-device and multi-identity | MuD | 2 | Rel-16 | S1 | 2018-06-06 | 2018-09-14 | 100% | SP-180315 |  | Peter Bleckert, Ericsson | Peter.Bleckert@ericsson.com | 10/9/18: 85%->90; 4/12/18: 90%->100 | 22.173 | 80 | 41 |  |  | 2018-06-06 | 2018-12-04
207 | 810010 | CT aspects of Multi-device and multi-identity | MuD | 2 | Rel-16 | ct | 2018-09-06 | 2019-06-14 | 10% | CP-182227 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com |  |  | 81 | 41 |  |  | 2018-06-06 | NA
208 | 810045 | CT1 aspects of Multi-device and multi-identity | MuD | 3 | Rel-16 | C1 | 2018-09-06 | 2019-06-14 | 15% | CP-182227 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | 7/12/18: 0%->10; 14/3/19: 10%->15 | 24.173; 24.229; 24.167 | 81 | 41 |  |  | 2018-06-06 | 2019-03-14
209 | 810046 | CT3 aspects of Multi-device and multi-identity | MuD | 3 | Rel-16 | C3 | 2018-09-06 | 2019-06-14 | 5% | CP-182227 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | 7/12/18: 0%->5 | 29.165 | 81 | 41 |  |  | 2018-06-06 | 2018-12-07
210 | 0 | Slicing | - | 1 | Rel-16 |  | 2017-09-08 | 2017-09-08 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
211 | 0 | Enhancement of Network Slicing | eNS | 1 | Rel-16 |  | 2018-03-15 | 2019-12-05 | 30% | SP-181232 |  | ZTE, Tricci So | tso at ztetx dot com | [6 empty] | 2018-12-06 | NA
212 | 790011 | Study on Enhancement of Network Slicing | FS_eNS | 2 | Rel-16 | S2 | 2018-03-15 | 2018-12-14 | 100% | SP-180503 |  | ZTE, Tricci So | tso at ztetx dot com | 7/6/18: 0%->10; 15/6/18: WID:SP-180121->SP-180503; 6/8/18: 23.740 added;; 10/9/18: 10%->50; 7/12/18: 50%->85; 7/12/18: 85%->; 14/3/19: 85%->100 | new; 23.740 | 79 | 40 |  |  | 2018-03-15 | 2019-03-14
213 | 820023 | Stage 2 of eNS | eNS | 2 | Rel-16 | S2 | 2018-12-13 | 2019-06-20 | 60% | SP-181232 |  | ZTE, Tricci So | tso at ztetx dot com | 14/3/19: 0%->60 |  | 82 |  |  |  | 2018-12-06 | 2019-03-14
214 | 830011 | CT aspects of eNS | eNS | 2 | Rel-16 | ct | 2019-03-07 | 2019-12-05 | 0% | CP-190196 |  | Fei Lu, ZTE | lu.fei1@zte.com.cn | [6 empty] | 2018-12-06 | NA
215 | 830052 | CT1 aspects of eNS | eNS | 3 | Rel-16 | C1 | 2019-03-07 | 2019-12-05 | 0% | CP-190196 |  | Fei Lu, ZTE | lu.fei1@zte.com.cn |  | 24.501 |  |  |  |  | 2018-12-06 | NA
216 | 830053 | CT3 aspects of eNS | eNS | 3 | Rel-16 | C3 | 2019-03-07 | 2019-12-05 | 0% | CP-190196 |  | Fei Lu, ZTE | lu.fei1@zte.com.cn |  | 29.061; 29.561 |  |  |  |  | 2018-12-06 | NA
217 | 830054 | CT4 aspects of eNS | eNS | 3 | Rel-16 | C4 | 2019-03-07 | 2019-12-05 | 0% | CP-190196 |  | Fei Lu, ZTE | lu.fei1@zte.com.cn |  | 29.502; 29.503; 29.505; 29.509; 29.518 |  |  |  |  | 2018-12-06 | NA
218 | 810051 | Business Role Models for Network Slicing | BRMNS | 1 | Rel-16 | S1 | 2017-09-08 | 2018-12-13 | 100% | SP-180773 |  | Covell, Betsy, Nokia | betsy.covell@nokia.com |  | 22.261 | 81 | 41 |  |  | 2018-09-06 | NA
219 | 770005 | Study on Business Role Models for Network Slicing | FS_BMNS | 2 | Rel-16 | S1 | 2017-09-08 | 2018-09-14 | 100% | SP-180169 |  | Covell, Betsy, Nokia | betsy.covell@nokia.com | 15/12/17: 22.830 added;; 15/12/17: 0%->10; 15/3/18: WID:SP-170705->SP-180169; 16/3/18: 10%->50; 7/6/18: 50%->75; 10/9/18: 75%->95; 4/12/18: 95%->100 | New; 22.830 | 77 | 39 |  |  | 2017-09-08 | 2018-12-04
220 | 810015 | Business Role Models for Network Slicing | BRMNS | 2 | Rel-16 | S1 | 2018-09-06 | 2018-12-13 | 100% | SP-180773 |  | Covell, Betsy, Nokia | betsy.covell@nokia.com | 10/9/18: 0%->95; 4/12/18: 95%->100 | 22.261 | 81 | 41 |  |  | 2018-09-06 | 2018-12-04
221 | 810034 | Study on Security aspects of Enhancement of Network Slicing | FS_eNS_SEC | 1 | Rel-16 | S3 | 2018-09-06 | 2019-06-12 | 65% | SP-180692 |  |  | Suresh.p.nair@nokia.com | 7/12/18: 0%->15; 20/3/19: 15%->65; 20/3/19: FCD:019->06/19 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-20
222 | 810022 | Study on tenancy concept in 5G networks and network slicing management | FS_TENANCYC | 1 | Rel-16 | S5 | 2018-09-06 | 2019-06-14 | 26% | SP-180815 |  | ZHU, Lei (Huawei | Lei.zhu@huawei.com | 7/12/18: 0%->20; 14/3/19: 20%->26 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
223 | 810031 | Enhancement of performance assurance for 5G networks including network slicing | 5G_SLICE_ePA | 1 | Rel-16 | S5 | 2018-09-06 | 2019-12-12 | 60% | SP-190247 |  | Xiaowei Sun (China Mobile) |  | 7/12/18: 0%->30; 17/1/19: WID:SP-180843->SP-180906; 14/3/19: 30%->60; 21/3/19: FCD:06/19->12/19; 21/3/19: WID:SP-180906(->SP-190141)->SP-190247 | 28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623 | 81 | 41 |  |  | 2018-09-06 | 2019-03-21
224 | 820029 | Study on Charging Aspects of Network Slicing | FS_NETSLICE_CH | 1 | Rel-16 | S5 | 2018-12-13 | 2019-09-12 | 30% | SP-181065 |  | Chen Shan, Huawei | chenshan@huawei.com | 14/3/19: 0%->30; 14/3/19: FCD:06/19->09/19 |  | 82 |  |  |  | 2018-12-07 | 2019-03-14
225 | 0 | Other cross-TSG Release 16 Features | - | 1 | Rel-16 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
226 | 760003 | Provision of Access to Restricted Local Operator Services by Unauthenticated UEs | PARLOS | 1 | Rel-16 |  | 2016-12-01 | 2019-12-12 | 55% | SP-170449 |  | Covell, Betsy Nokia | betsy.covell@nokia.com | 16/03/18: Moved to Rel-16 as per SA2 chair indication that St 2 work to be shifted from Rel-15 to Rel-16 | 22.115; 22.101; 22.228 | 76 | 38 |  |  | 2017-06-03 | 2017-06-07
227 | 740002 | Study on Stage 1 of PARLOS | FS_PARLOS | 2 | Rel-15 | S1 | 2016-12-01 | 2018-09-10 | 100% | SP-160904 |  | Covell, Betsy | betsy.covell@nokia.com | 1/12/16: 0%->75; 2/3/17: 75%->100; 10/9/18: FCD:03/17->09/18 | 22.82 | 74 | 38 |  |  | 2016-12-01 | 2018-09-10
228 | 760071 | Stage 1 of PARLOS | PARLOS | 2 | Rel-16 | S1 | 2017-05-10 | 2017-06-08 | 100% | SP-170449 |  | Covell, Betsy Nokia | betsy.covell@nokia.com | 7/6/17: 0%->100 | 22.115; 22.101; 22.228 | 76 | 39 |  |  | 2017-06-03 | 2017-06-07
229 | 760046 | Study on Stage 2 for PARLOS | FS_PARLOS | 2 | Rel-16 | S2 | 2017-06-05 | 2018-09-14 | 100% | SP-180501 |  | Nokia (Nicolas Drevon | nicolas.drevon@nokia.com | 11/9/17: 0%->20; 16/3/18: FCD:12/17->12/18.; 16/3/18: 20%->45; 23/3/18: WID:SP-170382->SP-180116; 23/3/18: FCD:12/18->06/18; 7/6/18: 45%->70; 15/6/18: WID:SP-180116->SP-180501; 15/6/18: FCD:06/18->09/18; 10/9/18: 70%->100 | 23.715 | 76 | 39 |  |  | 2017-06-03 | 2018-09-10
230 | 810008 | Stage 2 of PARLOS | PARLOS | 2 | Rel-16 | S2 | 2018-09-06 | 2019-03-15 | 95% | SP-180738 |  | Nokia (Nicolas Drevon | nicolas.drevon@nokia.com) | 14/3/19: 0%->95 | 23.401; 23.203; 23.221; 23.228; 23.167 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
231 | 800035 | Study on Security Aspects of PARLOS | FS_PARLOS | 2 | Rel-16 | S3 | 2018-06-06 | 2019-09-12 | 55% | SP-180442 |  | Greg Schumacher, Sprint | Gregory.schumacher@sprint.com | 6/8/18: 33.815 added;; 10/9/18: 0%->5; 7/12/18: 5%->50; 20/3/19: FCD:018->09/19; 20/3/19: 50%->55 | New; 33.815 | 80 | 41 |  |  | 2018-06-06 | 2019-03-20
232 | 830012 | CT aspects of PARLOS | PARLOS | 2 | Rel-16 | ct | 2019-03-14 | 2019-12-12 | 0% | CP-190197 |  | Liu, Jennifer; Nokia | Jennifer.Liu@nokia.com | [6 empty] | 2018-09-06 | NA
233 | 830062 | CT1 aspects of PARLOS | PARLOS | 3 | Rel-16 | C1 | 2019-03-14 | 2019-12-12 | 0% | CP-190197 |  | Liu, Jennifer; Nokia | Jennifer.Liu@nokia.com |  | 24.301; 24.008; 23.122; 24.368; 24.167; 24.229; 27.007 |  |  |  |  | 2018-09-06 | NA
234 | 830063 | CT3 aspects of PARLOS | PARLOS | 3 | Rel-16 | C3 | 2019-03-14 | 2019-12-12 | 0% | CP-190197 |  | Liu, Jennifer; Nokia | Jennifer.Liu@nokia.com |  | 29.212; 29.213; 29.214 |  |  |  |  | 2018-09-06 | NA
235 | 830064 | CT4 aspects of PARLOS | PARLOS | 3 | Rel-16 | C4 | 2019-03-14 | 2019-12-12 | 0% | CP-190197 |  | Liu, Jennifer; Nokia | Jennifer.Liu@nokia.com |  | 29.228; 29.229; 29.274 |  |  |  |  | 2018-09-06 | NA
236 | 830065 | CT6 aspects of PARLOS | PARLOS | 3 | Rel-16 | C6 | 2019-03-14 | 2019-12-12 | 0% | CP-190197 |  | Liu, Jennifer; Nokia | Jennifer.Liu@nokia.com |  | 31.102; 31.103 |  |  |  |  | 2018-09-06 | NA
237 | 820043 | Enhancing Topology of SMF and UPF in 5G Networks | ETSUN | 1 | Rel-16 |  | 2017-09-08 | 2019-12-06 | 46% | SP-181116 | [5 empty] | 82 |  |  |  | 2018-12-05 | NA
238 | 770039 | Study on ETSUN | FS_ETSUN | 2 | Rel-16 | S2 | 2017-09-08 | 2018-12-14 | 100% | SP-180731 |  | Laurent Thiebaut (Nokia) | Laurent.thiebaut@nokia.com | 15/12/17: 23.726 added;; 16/3/18: 0%->25; 7/6/18: 25%->40; 10/9/18: 40%->65; 10/9/18: FCD:09/18->12/18; 2/10/18: WID:SP-170743->SP-180731; 2/10/18: FCD:12/18->12/18; 7/12/18: 65%->100 | 23.726 | 77 | 39 |  |  | 2017-09-08 | 2018-12-07
239 | 820013 | Stage 2 of ETSUN | ETSUN | 2 | Rel-16 | S2 | 2018-12-07 | 2019-06-17 | 45% | SP-181116 |  |  |  | 14/3/19: 0%->45 |  | 82 |  |  |  | 2018-12-05 | 2019-03-14
240 | 830002 | CT aspects of ETSUN | ETSUN | 2 | Rel-16 | ct | 2019-03-08 | 2019-12-06 | 0% | CP-190192 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com | [6 empty] | 2018-12-05 | NA
241 | 830055 | CT3 aspects of ETSUN | ETSUN | 3 | Rel-16 | C3 | 2019-03-08 | 2019-12-06 | 0% | CP-190192 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  | 29.508; 29.561 |  |  |  |  | 2018-12-05 | NA
242 | 830056 | CT4 aspects of ETSUN | ETSUN | 3 | Rel-16 | C4 | 2019-03-08 | 2019-12-06 | 0% | CP-190192 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  | 29.244; 29.502; 29.510; 29.518; 29.281 |  |  |  |  | 2018-12-05 | NA
243 | 820044 | Access Traffic Steering, Switch and Splitting support in the 5G system architecture | ATSSS | 1 | Rel-16 |  | 2017-06-05 | 2019-12-09 | 41% | SP-181124 |  | So, Tricci, ZTE | tso@ztetx.com |  | 23.501; 23.502; 23.503 | 82 |  |  |  | 2018-12-06 | NA
244 | 760052 | Study on ATSSS | FS_ATSSS | 2 | Rel-16 | S2 | 2017-06-05 | 2018-12-14 | 100% | SP-180732 |  | So, Tricci, ZTE | tso@ztetx.com | 11/9/17: 0%->100; 14/9/17: 100%->10; 15/12/17: Changed Rel-15->Rel-16; 16/3/18: 10%->20; 7/6/18: 20%->40; 10/9/18: 40%->70; 10/9/18: FCD:09/18->12/18; 2/10/18: WID:SP-170411->SP-180732; 2/10/18: FCD:12/18->12/18; 7/12/18: 70%->100 | new 23.793 | 76 | 39 |  |  | 2017-06-03 | 2018-12-07
245 | 820021 | Stage 2 of ATSSS | ATSSS | 2 | Rel-16 | S2 | 2018-12-14 | 2019-06-21 | 45% | SP-181124 |  | So, Tricci, ZTE | tso@ztetx.com | 14/3/19: 0%->45 | 23.501; 23.502; 23.503 | 82 |  |  |  | 2018-12-06 | 2019-03-14
new |  | (IETF) TCP Extensions for Multipath Operation with Multiple Addresses (draft-ietf-mptcp-rfc6824bis) | ATSSS |  | Rel-16 | S2 |  |  | 80%
new |  | (IETF) 0-RTT TCP Convert Protocol (draft-ietf-tcpm-converters) | ATSSS |  | Rel-16 | S2 |  |  | 30%
246 | 830016 | CT aspects of ATSSS | ATSSS | 2 | Rel-16 | ct | 2019-03-11 | 2019-12-09 | 0% | CP-190201 |  | ZHOU, Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn | [6 empty] | 2018-12-06 | NA
247 | 830057 | CT1 aspects of ATSSS | ATSSS | 3 | Rel-16 | C1 | 2019-03-11 | 2019-12-09 | 0% | CP-190201 |  | ZHOU, Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn |  | 24.501; 24.526; 24.502 |  |  |  |  | 2018-12-06 | NA
248 | 830058 | CT3 aspects of ATSSS | ATSSS | 3 | Rel-16 | C3 | 2019-03-11 | 2019-12-09 | 0% | CP-190201 |  | ZHOU, Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn |  | 29.512; 29.513 |  |  |  |  | 2018-12-06 | NA
249 | 830059 | CT4 aspects of ATSSS | ATSSS | 3 | Rel-16 | C4 | 2019-03-11 | 2019-12-09 | 0% | CP-190201 |  | ZHOU, Xingyue (Joy), ZTE | zhou.xingyue@zte.com.cn |  | 29.244; 29.502; 29.503; 29.505; 29.518; 29.510; 23.008 |  |  |  |  | 2018-12-06 | NA
250 | 810041 | Single radio voice continuity from 5GS to 3G | 5G_SRVCC | 1 | Rel-16 |  | 2018-03-15 | 2020-06-01 | 25% | SP-180737 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn |  | 23.216; 23.501; 23.502 | 81 | 41 |  |  | 2018-09-06 | NA
251 | 790010 | Study for single radio voice continuity from 5GS to 3G | FS_5G-SRVCC | 2 | Rel-16 | S2 | 2018-03-15 | 2018-06-15 | 100% | SP-180239 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn | 7/6/18: 0%->80; 6/8/18: 23.756 added;; 10/9/18: 80%->100 | 23.756 | 79 | 40 |  |  | 2018-03-15 | 2018-09-10
252 | 810007 | Single radio voice continuity from 5GS to 3G | 5G_SRVCC | 2 | Rel-16 | S2 | 2018-09-06 | 2019-03-14 | 100% | SP-180897 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn | 14/3/19: 0%->100 | 23.216; 23.501; 23.502 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
253 | 820008 | Security aspects of single radio voice continuity from 5GS to UTRAN | 5GS_UTRAN_SEC | 2 | Rel-16 | S3 | 2018-12-13 | 2019-06-12 | 20% | SP-181037 |  | Feng Gao, China Unicom | gaofeng149@chinaunicom.cn | 20/3/19: 0%->20 | 33.501 | 82 |  |  |  | 2018-12-13 | 2019-03-20
254 | 820069 | RAN aspects of 5G_SRVCC | SRVCC_NR_to_UMTS | 2 | Rel-16 | R2 | 2018-12-15 | 2019-12-15 | 0% | RP-190713 |  | China Unicom |  | no Perf. part; 26/3/19: WID:RP-182811->RP-190713 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
255 | 820169 | Core part: Single Radio Voice Call Continuity from 5G to 3G | SRVCC_NR_to_UMTS-Core | 3 | Rel-16 | R2 | 2018-12-15 | 2019-12-15 | 0% | RP-190713 |  | China Unicom |  | no Perf. part; 26/3/19: WID:RP-182811->RP-190713 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
256 | 830270 | Perf. part: Single Radio Voice Call Continuity from 5G to 3G | SRVCC_NR_to_UMTS-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2020-06-01 | 0% | RP-190713 |  | China Unicom | [7 empty] | 2019-03-26 | NA
257 | 810049 | Remote Identification of Unmanned Aerial Systems | ID_UAS | 1 | Rel-16 |  | 2018-03-15 | 2018-12-14 | 100% | SP-180771 |  | Eddy HALL, Qualcomm incorporated | edhall@qti.qualcomm.com |  |  | 81 | 41 |  |  | 2018-09-06 | NA
258 | 790005 | Study on Remote Identification of Unmanned Aerial Systems | FS_ID_UAS | 2 | Rel-16 | S1 | 2018-03-15 | 2018-09-14 | 100% | SP-180172 |  | Eddy Hall; Qualcomm Incorporated | edhall@qti.qualcomm.com | 7/6/18: 0%->60; 10/9/18: 60%->100 | 22.825 | 79 | 40 |  |  | 2018-03-15 | 2018-09-10
259 | 810013 | Stage 1 of Remote Identification of Unmanned Aerial Systems | ID_UAS | 2 | Rel-16 | S1 | 2018-09-06 | 2018-12-14 | 100% | SP-180771 |  | Eddy HALL, Qualcomm incorporated | edhall@qti.qualcomm.com | 10/9/18: 0%->5; 4/12/18: 5%->100 | 22.125 | 81 | 41 |  |  | 2018-09-06 | 2018-12-04
260 | 820045 | Enhancements to the Service-Based 5G System Architecture | 5G_eSBA | 1 | Rel-16 | S2 | 2018-03-15 | 2019-12-12 | 37% | SP-181125 | [5 empty] | 82 |  |  |  | 2018-12-06 | NA
261 | 790007 | Study on Enhancements to the Service-Based 5G System Architecture | FS_eSBA | 2 | Rel-16 | S2 | 2018-03-15 | 2018-12-14 | 100% | SP-180231 |  | Tao Sun (China Mobile) | suntao@chinamobile.com | 7/6/18: 0%->15; 6/8/18: 23.742 added;; 10/9/18: 15%->60; 7/12/18: 60%->100 | 23.xxx; 23.742 | 79 | 40 |  |  | 2018-03-15 | 2018-12-07
262 | 820022 | Stage 2 of 5G_eSBA | 5G_eSBA | 2 | Rel-16 | S2 | 2018-12-13 | 2019-06-20 | 50% | SP-181125 |  | Tao Sun (China Mobile) | suntao@chinamobile.com | 14/3/19: 0%->50 | 23.501; 23.502; 23.503 | 82 |  |  |  | 2018-12-06 | 2019-03-14
263 | 830001 | CT aspects of 5G_eSBA | 5G_eSBA | 2 | Rel-16 | ct | 2019-03-14 | 2019-12-12 | 0% | CP-190191 |  | Song Yue (China Mobile) | songyue at chinamobile dot com | [6 empty] | 2018-12-06 | NA
264 | 830060 | CT3 aspects of 5G_eSBA | 5G_eSBA | 3 | Rel-16 | C3 | 2019-03-14 | 2019-12-12 | 0% | CP-190191 |  | Song Yue (China Mobile) | songyue at chinamobile dot com |  | 29.507; 29.508; 29.513; 29.512; 29.514; 29.519; 29.520; 29.521; 29.523; 29.525; 29.551; 29.554 |  |  |  |  | 2018-12-06 | NA
265 | 830061 | CT4 aspects of 5G_eSBA | 5G_eSBA | 3 | Rel-16 | C4 | 2019-03-14 | 2019-12-12 | 0% | CP-190191 |  | Song Yue (China Mobile) | songyue at chinamobile dot com |  | 29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.518; 29.531; 29.540; 29.571; 29.572; 29.573 |  |  |  |  | 2018-12-06 | NA
266 | 780029 | Study on Enhanced IMS to 5GC Integration | FS_eIMS5G | 1 | Rel-16 | S2 | 2017-12-15 | 2019-06-14 | 70% | SP-180736 |  | Joul, Chris, T-Mobile USA | chris <dot> joul <at> t-mobile <dot> com | 16/3/18: 0%->20; 7/6/18: 20%->40; 10/9/18: FCD:09/18->06/19; 2/10/18: WID:SP-171052->SP-180736; 14/3/19: 40%->70 | new 23.794 | 78 | 40 |  |  | 2017-12-15 | 2019-03-14
267 | 830028 | SBA aspects of enhanced IMS to 5GC integration | eIMS5G_SBA | 1 | Rel-16 | S2 | 2019-03-14 | 2019-06-13 | 0% | SP-190181 |  | T-Mobile USA, Christopher Joul |  |  | 23.501; 23.502; 23.503; 23.228 |  |  |  |  | 2019-03-14 | NA
268 | 830081 | Private Network Support for NG-RAN | NG_RAN_PRN | 1 | Rel-16 | R3 | 2019-03-01 | 2020-03-01 | 0% | RP-190729 |  | China Telecom | [7 empty] | 2019-03-26 | NA
269 | 830181 | Core part: Private Network Support for NG-RAN | NG_RAN_PRN-Core | 2 | Rel-16 | R3 | 2019-03-01 | 2020-03-01 | 0% | RP-190729 |  | China Telecom | [7 empty] | 2019-03-26 | NA
270 | 810039 | Media Handling Aspects of RAN Delay Budget Reporting in MTSI | E2E_DELAY | 1 | Rel-16 | S4 | 2017-12-15 | 2019-12-12 | 37% | SP-180662 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com |  | 26.114 | 81 | 41 |  |  | 2018-09-06 | NA
271 | 780022 | Study on E2E_DELAY | FS_E2E_DELAY | 2 | Rel-16 | S4 | 2017-12-15 | 2018-09-14 | 100% | SP-170837 |  | Oyman, Ozgur, Company: Intel, | ozgur.oyman@intel.com | 16/3/18: 0%->10; 7/6/18: 10%->60; 10/9/18: 60%->100 | new | 78 | 40 |  |  | 2017-12-15 | 2018-09-10
272 | 810001 | Stage 2 of E2E_DELAY | E2E_DELAY | 2 | Rel-16 | S4 | 2018-09-06 | 2019-06-07 | 85% | SP-180662 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com | 7/12/18: 0%->75; 7/3/19: 75%->85; 7/3/19: FCD:03/19->06/19 | 26.114 | 81 | 41 |  |  | 2018-09-06 | 2019-03-07
273 | 830004 | CT Aspects of E2E_DELAY | E2E_DELAY | 2 | Rel-16 | ct | 2019-03-14 | 2019-12-12 | 0% | CP-190193 |  | Luetzenkirchen, Thomas, Intel | Thomas.luetzenkirchen@intel.com | [6 empty] | 2018-09-06 | NA
274 | 830066 | CT1 Aspects of E2E_DELAY | E2E_DELAY | 3 | Rel-16 | C1 | 2019-03-14 | 2019-12-12 | 0% | CP-190193 |  | Luetzenkirchen, Thomas, Intel | Thomas.luetzenkirchen@intel.com |  | 24.229 |  |  |  |  | 2018-09-06 | NA
275 | 830067 | CT3 Aspects of E2E_DELAY | E2E_DELAY | 3 | Rel-16 | C3 | 2019-03-14 | 2019-12-12 | 0% | CP-190193 |  | Luetzenkirchen, Thomas, Intel | Thomas.luetzenkirchen@intel.com |  | 29.162 |  |  |  |  | 2018-09-06 | NA
276 | 830068 | CT4 Aspects of E2E_DELAY | E2E_DELAY | 3 | Rel-16 | C4 | 2019-03-14 | 2019-12-12 | 0% | CP-190193 |  | Luetzenkirchen, Thomas, Intel | Thomas.luetzenkirchen@intel.com |  | 23.334; 29.334; 29.238; 23.333; 29.333 |  |  |  |  | 2018-09-06 | NA
277 | 830069 | Enhancements for Common API Framework for 3GPP Northbound APIs | eCAPIF | 1 | Rel-16 |  | 2018-03-15 | 2019-09-20 | 56% | SP-181137 |  | Basavaraj Pattan, Samsung | basavarajjp@samsung.com | 7/6/18: 0%->15; 10/9/18: 15%->30; 7/12/18: 30%->45; 7/12/18: FCD:12/18->06/19; 13/12/18: WID:SP-180161->SP-181137 | 23.222 | 79 | 40 |  |  | 2018-03-15 | 2018-12-13
278 | 790022 | Stage 2 for eCAPIF | eCAPIF | 2 | Rel-16 | S6 | 2018-03-15 | 2019-06-12 | 80% | SP-181137 |  | Basavaraj Pattan, Samsung | basavarajjp@samsung.com | 7/6/18: 0%->15; 10/9/18: 15%->30; 7/12/18: 30%->45; 7/12/18: FCD:12/18->06/19; 13/12/18: WID:SP-180161->SP-181137; 14/3/19: 45%->80 | 23.222 | 79 | 40 |  |  | 2018-03-15 | 2019-03-14
279 | 830022 | Security aspects of eCAPIF | eCAPIF | 2 | Rel-16 | S3 | 2019-03-14 | 2019-09-20 | 0% | SP-1901240 |  | Rajavelsamy Rajadurai, Samsung | rajvel{@]samsung.com |  | 33.122 |  |  |  |  | 2019-03-14 | NA
280 | 800055 | Study on User Data Interworking, Coexistence and Migration | FS_UDICoM | 1 | Rel-16 | S2 | 2018-06-15 | 2019-06-12 | 75% | SP-190148 |  | Susana Sabater (Vodafone | susana.sabater@vodafone.com | 10/9/18: 0%->30; 2/10/18: WID:SP-180620->SP-180735; 7/12/18: 30%->80; 14/12/18: FCD:12/18->03/20; 14/3/19: 80%->100; 21/3/19: WID:SP-181110->SP-190148; 21/3/19: FCD:019->06/19 | 23.732; new | 80 | 41 |  |  | 2018-06-15 | 2019-03-21
281 | 830029 | User data interworking, Coexistence and Migration | UDICOM | 1 | Rel-16 | S2 | 2019-03-14 | 2019-06-14 | 0% | SP-190182 |  | Alessio Casati, Nokia | Alessio.casati@nokia.com |  | 23.501; 23.502; 23.228 |  |  |  |  | 2019-03-14 | NA
282 | 0 | NR-related Release 16 Features | - | 1 | Rel-16 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
283 | 830075 | UE Power Saving in NR | NR_UE_pow_sav | 1 | Rel-16 | R1 | 2018-06-15 | 2020-09-15 | 0% | RP-190727 |  | CATT | [7 empty] | 2019-03-26 | NA
284 | 800094 | Study on UE power saving in NR | FS_NR_UE_pow_sav | 2 | Rel-16 | R1 | 2018-06-15 | 2019-06-15 | 0% | RP-181463 |  | CATT |  | TR 38.8xx |  | 80 | 41 |  |  | 2018-06-27 | NA
285 | 830175 | Core part: UE Power Saving in NR | NR_UE_pow_sav-Core | 2 | Rel-16 | R1 | 2019-03-01 | 2020-03-01 | 0% | RP-190727 |  | CATT | [7 empty] | 2019-03-26 | NA
286 | 830275 | Perf. part: UE Power Saving in NR | NR_UE_pow_sav-Perf | 2 | Rel-16 | R4 | 2019-03-01 | 2020-09-15 | 0% | RP-190727 |  | CATT | [7 empty] | 2019-03-26 | NA
287 | 820070 | Integrated access and backhaul for NR | NR_IAB | 1 | Rel-16 |  | 2017-03-15 | 2020-03-06 | 41% | RP-190712 |  | Qualcomm |  | follow-up WI of REL-16 SI FS_NR_IAB; 26/3/19: WID:RP-182882->RP-190712 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
288 | 750047 | Study onNR_IAB | FS_NR_IAB | 2 | Rel-16 | R2 | 2017-03-15 | 2018-12-14 | 100% | RP-181349 |  | Qualcomm |  | TR 38.8XX; 30/6/17: 38.874 added;; 19/9/17: WID: RP-170831->RP-171880; 8/1/18: WID: RP-171880->RP-17229027/3/18: Compl:0%->20%; 27/6/18: Compl:20%->50%; 27/6/18: CD:Fri 15/06/18->Sat 15/12/18;; 16/1/19: 50%->100 | 38.874 | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
289 | 820170 | Core part: NR_IAB | NR_IAB-Core | 2 | Rel-16 | R2 | 2019-03-07 | 2020-03-06 | 0% | RP-190712 |  | Qualcomm |  | follow-up WI of REL-16 SI FS_NR_IAB; 26/3/19: WID:RP-182882->RP-190712 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
290 | 820270 | Perf. Part: NR_IAB | NR_IAB-Perf | 2 | Rel-16 | R4 | 2019-03-07 | 2020-03-06 | 0% | RP-190712 |  | Qualcomm |  | 26/3/19: WID:RP-182882->RP-190712 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
291 | 830021 | Study on Security for NR_IAB | FS_NR_IAB_Sec | 2 | Rel-16 | S3 | 2019-03-11 | 2019-09-09 | 0% | SP-190106 |  | Rajavelsamy Rajadurai, Samsung, | rajvel{@]samsung.com |  | New |  |  |  |  | 2019-03-14 | NA
292 | 800072 | Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R16 | 1 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190714 |  | Huawei |  | basket WI; TR 37.716-00-00; note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands; 26/3/19: WID:RP-182559->RP-190714 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
293 | 800172 | Core part: Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R16-Core | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190714 |  | Huawei |  | basket WI; TR 37.716-00-00; note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands; 26/3/19: WID:RP-182559->RP-190714 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
294 | 800272 | Perf. part: Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R16-Perf | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190714 |  | Huawei |  | basket WI; 26/3/19: WID:RP-182559->RP-190714 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
295 | 800057 | NR intra-band Carrier Aggregation |  | 1 | Rel-16 |  | 2018-06-15 | 2019-12-15 | 0% | [6 empty] | 80 | 41 |  |  | 2018-06-27 | NA
296 | 800073 | Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R16_intra | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190689 |  | Ericsson |  | basket WI; TR 38.716-01-01; 16/1/19: WID:RP-181426->RP-182256; 26/3/19: WID:RP-182256->RP-190689 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
297 | 800173 | Core part: Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R16_intra-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190689 |  | Ericsson |  | basket WI; TR 38.716-01-01; 26/3/19: WID:RP-182256->RP-190689 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
298 | 800273 | Perf. part: Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R16_intra-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190689 |  | Ericsson |  | basket WI; 26/3/19: WID:RP-182256->RP-190689 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
299 | 800074 | Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2) | NR_CADC_R16_2BDL_xBUL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190494 |  | ZTE |  | basket WI; TR 38.716-02-00; 16/1/19: WID:RP-180817->RP-182501; 26/3/19: WID:RP-182501->RP-190494 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
300 | 800174 | Core part: Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2) | NR_CADC_R16_2BDL_xBUL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190494 |  | ZTE |  | basket WI; TR 38.716-02-00; 26/3/19: WID:RP-182501->RP-190494 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
301 | 800274 | Perf. part: Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2) | NR_CADC_R16_2BDL_xBUL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190494 |  | ZTE |  | basket WI; 26/3/19: WID:RP-182501->RP-190494 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
302 | 830099 | NR inter-band Carrier Aggregation |  | 1 | Rel-16 |  | 2019-03-01 | 2020-06-01 | 0% | [10 empty] | 2019-03-26 | NA
303 | 830083 | UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | NR_CADC_NR_LTE_DC_R16-UEConTest | 2 | Rel-16 | R5 | 2019-03-01 | 2020-06-01 | 0% | RP-190321 |  | CMCC | [7 empty] | 2019-03-26 | NA
304 | 830095 | Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL | NR_CA_R16_3BDL_1BUL | 2 | Rel-16 | R4 | 2019-03-01 | 2020-03-01 | 0% | RP-190692 |  | CATT | [7 empty] | 2019-03-26 | NA
305 | 830195 | Core part: Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL | NR_CA_R16_3BDL_1BUL-Core | 3 | Rel-16 | R4 | 2019-03-01 | 2020-03-01 | 0% | RP-190692 |  | CATT | [7 empty] | 2019-03-26 | NA
306 | 830295 | Perf. part: Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL | NR_CA_R16_3BDL_1BUL-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2020-03-01 | 0% | RP-190692 |  | CATT | [7 empty] | 2019-03-26 | NA
307 | 830096 | Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL | NR_CADC_R16_3BDL_2BUL | 2 | Rel-16 | R4 | 2019-03-01 | 2020-03-01 | 0% | RP-190693 |  | ZTE | [7 empty] | 2019-03-26 | NA
308 | 830196 | Core part: Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL | NR_CADC_R16_3BDL_2BUL-Core | 3 | Rel-16 | R4 | 2019-03-01 | 2020-03-01 | 0% | RP-190693 |  | ZTE | [7 empty] | 2019-03-26 | NA
309 | 830296 | Perf. part: Rel-16 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with 2 bands UL | NR_CADC_R16_3BDL_2BUL-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2020-03-01 | 0% | RP-190693 |  | ZTE | [7 empty] | 2019-03-26 | NA
310 | 831000 | New bands for New Radio | NR_band_n65 | 1 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-182258 |  | Dish Network |  | 16/1/19: WID:RP-181445->RP-182258 |  | 80 | 41 |  |  | 2018-06-27 | 2019-01-16
311 | 800077 | Band 65 for New Radio | NR_band_n65 | 2 | Rel-16 | R4 | 2018-06-15 | 2018-12-15 | 0% | RP-190360 |  | Dish Network |  | 16/1/19: WID:RP-181445->RP-182258; 26/3/19: WID:RP-182258->RP-190360 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
312 | 800177 | Core part: Band 65 for New Radio | NR_band_n65-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2018-12-15 | 0% | RP-190360 |  | Dish Network |  | 26/3/19: WID:RP-182258->RP-190360 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
313 | 800277 | Perf. part: Band 65 for New Radio | NR_band_n65-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2018-12-15 | 0% | RP-190360 |  | Dish Network |  | 26/3/19: WID:RP-182258->RP-190360 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
314 | 820073 | Introduction of NR band n18 | NR_n18 | 2 | Rel-16 | R4 | 2018-12-13 | 2019-12-13 | 0% | RP-190173 |  | KDDI |  | 26/3/19: WID:RP-182826->RP-190173 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
315 | 820173 | Core part: Introduction of NR band n18 | NR_n18-Core | 3 | Rel-16 | R4 | 2018-12-13 | 2019-12-13 | 0% | RP-190173 |  | KDDI |  | 26/3/19: WID:RP-182826->RP-190173 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
316 | 820273 | Perf. part: Introduction of NR band n18 | NR_n18-Perf | 3 | Rel-16 | R4 | 2018-12-13 | 2019-12-13 | 0% | RP-190173 |  | KDDI |  | 26/3/19: WID:RP-182826->RP-190173 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
317 | 820077 | Introduction of NR band n48 | NR_n48 | 2 | Rel-16 | R4 | 2018-12-13 | 2019-06-01 | 0% | RP-182865 |  | US Cellular |  |  |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
318 | 820177 | Core part: Introduction of NR band n48 | NR_n48-Core | 3 | Rel-16 | R4 | 2018-12-13 | 2019-03-18 | 0% | RP-182865 |  | US Cellular |  |  |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
319 | 830271 | Perf. part: Introduction of NR band n48 | NR_n48-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2019-06-01 | 0% | RP-190140 |  | Nokia | [7 empty] | 2019-03-26 | NA
320 | 830090 | Introduction of NR band n14 | NR_n14 | 2 | Rel-16 | R4 | 2019-03-01 | 2019-06-01 | 0% | RP-190165 |  | AT&T | [7 empty] | 2019-03-26 | NA
321 | 830190 | Core part: Introduction of NR band n14 | NR_n14-Core | 3 | Rel-16 | R4 | 2019-03-01 | 2019-06-01 | 0% | RP-190165 |  | AT&T | [7 empty] | 2019-03-26 | NA
322 | 830290 | Perf. part: Introduction of NR band n14 | NR_n14-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2019-06-01 | 0% | RP-190165 |  | AT&T | [7 empty] | 2019-03-26 | NA
323 | 830091 | Introduction of NR band n30 | NR_n30 | 2 | Rel-16 | R4 | 2019-03-01 | 2019-06-01 | 0% | RP-190166 |  | AT&T | [7 empty] | 2019-03-26 | NA
324 | 830191 | Core part: Introduction of NR band n30 | NR_n30-Core | 3 | Rel-16 | R4 | 2019-03-01 | 2019-06-01 | 0% | RP-190166 |  | AT&T | [7 empty] | 2019-03-26 | NA
325 | 830291 | Perf. part: Introduction of NR band n30 | NR_n30-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2019-06-01 | 0% | RP-190166 |  | AT&T | [7 empty] | 2019-03-26 | NA
326 | 830097 | Introduction of NR band n259 | NR_n259 | 2 | Rel-16 | R4 | 2019-03-01 | 2019-12-15 | 0% | RP-190765 |  | Ericsson | [7 empty] | 2019-03-26 | NA
327 | 830197 | Core part: Introduction of NR band n259 | NR_n259-Core | 3 | Rel-16 | R4 | 2019-03-01 | 2019-12-15 | 0% | RP-190765 |  | Ericsson | [7 empty] | 2019-03-26 | NA
328 | 830297 | Perf. part: Introduction of NR band n259 | NR_n259-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2019-12-15 | 0% | RP-190765 |  | Ericsson | [7 empty] | 2019-03-26 | NA
329 | 831001 | New Radio Band-related topics | NR_band_n65 | 1 | Rel-16 | R4 | 2018-12-13 | 2020-09-15 | 0% | RP-182258 |  | Dish Network |  | 16/1/19: WID:RP-181445->RP-182258 |  | 80 | 41 |  |  | 2018-06-27 | 2019-01-16
330 | 830087 | RF requirements for NR frequency range 1 (FR1) | NR_RF_FR1 | 2 | Rel-16 | R4 | 2019-03-01 | 2020-06-01 | 0% | RP-190759 |  | Huawei | [7 empty] | 2019-03-26 | NA
331 | 830187 | Core part: RF requirements for NR frequency range 1 (FR1) | NR_RF_FR1-Core | 3 | Rel-16 | R4 | 2019-03-01 | 2020-03-01 | 0% | RP-190759 |  | Huawei | [7 empty] | 2019-03-26 | NA
332 | 830287 | Perf. part: RF requirements for NR frequency range 1 (FR1) | NR_RF_FR1-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2020-06-01 | 0% | RP-190759 |  | Huawei | [7 empty] | 2019-03-26 | NA
333 | 830088 | Add support of NR DL 256QAM for frequency range 2 (FR2) | NR_DL256QAM_FR2 | 2 | Rel-16 | R4 | 2019-03-01 | 2020-09-15 | 0% | RP-190760 |  | China Telecom | [7 empty] | 2019-03-26 | NA
334 | 830188 | Core part: Add support of NR DL 256QAM for frequency range 2 (FR2) | NR_DL256QAM_FR2-Core | 3 | Rel-16 | R4 | 2019-03-01 | 2020-03-01 | 0% | RP-190760 |  | China Telecom | [7 empty] | 2019-03-26 | NA
335 | 830288 | Perf. part: Add support of NR DL 256QAM for frequency range 2 (FR2) | NR_DL256QAM_FR2-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2020-09-15 | 0% | RP-190760 |  | China Telecom | [7 empty] | 2019-03-26 | NA
336 | 830089 | NR RF requirement enhancements for frequency range 2 (FR2) | NR_RF_FR2_req_enh | 2 | Rel-16 | R4 | 2019-03-01 | 2020-03-01 | 0% | RP-190761 |  | Nokia | [7 empty] | 2019-03-26 | NA
337 | 830189 | Core part: NR RF requirement enhancements for frequency range 2 (FR2) | NR_RF_FR2_req_enh-Core | 3 | Rel-16 | R4 | 2019-03-01 | 2020-03-01 | 0% | RP-190761 |  | Nokia | [7 empty] | 2019-03-26 | NA
338 | 830092 | Introduction of an NR SUL (supplemental uplink) band with same uplink frequency range as NR band n5 | NR_SUL_UL_n5 | 2 | Rel-16 | R4 | 2019-03-01 | 2019-09-15 | 0% | RP-190390 |  | Huawei | [7 empty] | 2019-03-26 | NA
339 | 830192 | Core part: Introduction of an NR SUL (supplemental uplink) band with same uplink frequency range as NR band n5 | NR_SUL_UL_n5-Core | 3 | Rel-16 | R4 | 2019-03-01 | 2019-09-15 | 0% | RP-190390 |  | Huawei | [7 empty] | 2019-03-26 | NA
340 | 830292 | Perf. part: Introduction of an NR SUL (supplemental uplink) band with same uplink frequency range as NR band n5 | NR_SUL_UL_n5-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2019-09-15 | 0% | RP-190390 |  | Huawei | [7 empty] | 2019-03-26 | NA
341 | 820074 | Adding wider channel bandwidths in NR band n7 | NR_n7_BW | 2 | Rel-16 | R4 | 2018-12-13 | 2019-09-13 | 0% | RP-190137 |  | BT |  | no Perf. part; 26/3/19: WID:RP-182827->RP-190137 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
342 | 820174 | Core part: Adding wider channel bandwidths in NR band n7 | NR_n7_BW-Core | 3 | Rel-16 | R4 | 2018-12-13 | 2019-09-13 | 0% | RP-190137 |  | BT |  | no Perf. part; 26/3/19: WID:RP-182827->RP-190137 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
343 | 830093 | Addition of wider channel bandwidth in NR band n38 | NR_n38_BW | 2 | Rel-16 | R4 | 2019-03-01 | 2019-12-15 | 0% | RP-190392 |  | Huawei | [7 empty] | 2019-03-26 | NA
344 | 830193 | Core part: Addition of wider channel bandwidth in NR band n38 | NR_n38_BW-Core | 3 | Rel-16 | R4 | 2019-03-01 | 2019-12-15 | 0% | RP-190392 |  | Huawei | [7 empty] | 2019-03-26 | NA
345 | 830293 | Perf. part: Addition of wider channel bandwidth in NR band n38 | NR_n38_BW-Perf | 3 | Rel-16 | R4 | 2019-03-01 | 2019-12-15 | 0% | RP-190392 |  | Huawei | [7 empty] | 2019-03-26 | NA
346 | 820075 | Addition of 30MHz channel bandwidth for NR band n41 | NR_n41_BW | 2 | Rel-16 | R4 | 2018-12-13 | 2019-06-18 | 0% | RP-190174 |  | KDDI |  | 26/3/19: WID:RP-182828->RP-190174 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
347 | 820175 | Core part: Addition of 30MHz channel bandwidth for NR band n41 | NR_n41_BW-Core | 3 | Rel-16 | R4 | 2018-12-13 | 2019-06-18 | 0% | RP-190174 |  | KDDI |  | 26/3/19: WID:RP-182828->RP-190174 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
348 | 820275 | Perf. part: Addition of 30MHz channel bandwidth for NR band n41 | NR_n41_BW-Perf | 3 | Rel-16 | R4 | 2018-12-13 | 2019-06-18 | 0% | RP-190174 |  | KDDI |  | 26/3/19: WID:RP-182828->RP-190174 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
349 | 820076 | Adding wider channel bandwidths in NR band n50 | NR_n50_BW | 2 | Rel-16 | R4 | 2018-12-13 | 2019-06-18 | 0% | RP-182829 |  | Huawei |  | no Perf. part |  | 82 |  |  |  | 2019-01-16 | NA
350 | 820176 | Core part: Adding wider channel bandwidths in NR band n50 | NR_n50_BW-Core | 3 | Rel-16 | R4 | 2018-12-13 | 2019-06-18 | 0% | RP-182829 |  | Huawei |  | no Perf. part |  | 82 |  |  |  | 2019-01-16 | NA
351 | 800085 | Enhancements on MIMO for NR | NR_eMIMO | 1 | Rel-16 | R1 | 2018-06-15 | 2020-09-15 | 0% | RP-182863 |  | Samsung |  | 16/1/19: WID:RP-181453->RP-182863 |  | 80 | 41 |  |  | 2018-06-27 | 2019-01-16
352 | 800185 | Core part: Enhancements on MIMO for NR | NR_eMIMO-Core | 2 | Rel-16 | R1 | 2018-06-15 | 2019-12-15 | 0% | RP-182863 |  | Samsung |  |  |  | 80 | 41 |  |  | 2018-06-27 | NA
353 | 800285 | Perf. part: Enhancements on MIMO for NR | NR_eMIMO-Perf | 2 | Rel-16 | R4 | 2018-06-15 | 2020-09-15 | 0% | RP-182863 |  | Samsung |  |  |  | 80 | 41 |  |  | 2018-06-27 | NA
354 | 800087 | NR mobility enhancements | NR_Mob_enh | 1 | Rel-16 | R2 | 2018-06-15 | 2019-12-15 | 0% | RP-190489 |  | Intel |  | 26/3/19: WID:RP-181433->RP-190489 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
355 | 800187 | Core part: NR mobility enhancements | NR_Mob_enh-Core | 2 | Rel-16 | R2 | 2018-06-15 | 2019-12-15 | 0% | RP-190489 |  | Intel |  | 26/3/19: WID:RP-181433->RP-190489 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
356 | 800287 | Perf. part: NR mobility enhancements | NR_Mob_enh-Perf | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190489 |  | Intel |  | 26/3/19: WID:RP-181433->RP-190489 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
357 | 820068 | 2-step RACH for NR | NR_2step_RACH | 1 | Rel-16 | R1 | 2018-12-15 | 2019-12-15 | 0% | RP-190711 |  | ZTE |  | WI was created after REL-16 SI FS_NR_NOMA was completed; 26/3/19: WID:RP-182894->RP-190711 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
358 | 820168 | Core part: 2-step RACH for NR | NR_2step_RACH-Core | 2 | Rel-16 | R1 | 2018-12-15 | 2019-12-15 | 0% | RP-190711 |  | ZTE |  | WI was created after REL-16 SI FS_NR_NOMA was completed; 26/3/19: WID:RP-182894->RP-190711 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
359 | 820268 | Perf. part: 2-step RACH for NR | NR_2step_RACH-Perf | 2 | Rel-16 | R4 | 2018-12-15 | 2019-06-20 | 0% | RP-190711 |  | ZTE |  | 26/3/19: WID:RP-182894->RP-190711 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
360 | 0 | Release 16 Features impacting both LTE and NR | - | 1 | Rel-16 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
361 | 800088 | LTE-NR & NR-NR Dual Connectivity and NR Carrier Aggregation enhancements | LTE_NR_DC_CA_enh | 1 | Rel-16 | R2 | 2018-06-15 | 2020-06-15 | 0% | RP-190452 |  | Ericsson |  | RAN3 impact?; 26/3/19: WID:RP-181469->RP-190452 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
362 | 800188 | Core part: LTE-NR & NR-NR Dual Connectivity and NR CA enhancements | LTE_NR_DC_CA_enh-Core | 2 | Rel-16 | R2 | 2018-06-15 | 2019-12-15 | 0% | RP-190452 |  | Ericsson |  | RAN3 impact?; 26/3/19: WID:RP-181469->RP-190452 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
363 | 800288 | Perf. part: LTE-NR & NR-NR Dual Connectivity and NR CA enhancements | LTE_NR_DC_CA_enh-Perf | 2 | Rel-16 | R4 | 2018-06-15 | 2020-06-15 | 0% | RP-190452 |  | Ericsson |  | 26/3/19: WID:RP-181469->RP-190452 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
364 | 820079 | High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band) | ENDC_UE_PC2_TDD_TDD | 1 | Rel-16 | R4 | 2018-12-13 | 2019-12-13 | 0% | RP-190315 |  | CMCC |  | 26/3/19: WID:RP-182877->RP-190315 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
365 | 820061 | Study on high power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | FS_ENDC_UE_PC2_FDD_TDD | 2 | Rel-16 | R4 | 2018-12-13 | 2019-06-18 | 0% | RP-190167 |  | China Unicom |  | EN-DC = E-UTRA-NR Dual Connectivity; TR 37.8xx; 26/3/19: WID:RP-182895->RP-190167 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
366 | 820179 | Core part: High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band) | ENDC_UE_PC2_TDD_TDD-Core | 2 | Rel-16 | R4 | 2018-12-13 | 2019-12-13 | 0% | RP-190315 |  | CMCC |  | 26/3/19: WID:RP-182877->RP-190315 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
367 | 820279 | Perf. part: Power class 2 UE for EN-DC (1 LTE TDD band + 1 NR TDD band) | ENDC_UE_PC2_TDD_TDD-Perf | 2 | Rel-16 | R4 | 2018-12-13 | 2019-12-13 | 0% | RP-190315 |  | CMCC |  | 26/3/19: WID:RP-182877->RP-190315 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
368 | 790054 | eNB(s) Architecture Evolution for E-UTRAN and NG-RAN | LTE_NR_arch_evo | 1 | Rel-16 | R3 | 2018-03-15 | 2019-12-13 | 15% | RP-180531 |  | China Unicom |  | follow-up WI of REL-15 SI FS_LTE_arch_evo |  | 79 | 40 |  |  | 2018-03-27 | NA
369 | 790154 | Core part: eNB(s) Architecture Evolution for E-UTRAN and NG-RAN | LTE_NR_arch_evo-Core | 2 | Rel-16 | R3 | 2018-03-15 | 2019-12-13 | 15% | RP-181375 |  | China Unicom |  | follow-up WI of REL-15 SI FS_LTE_arch_evo; 27/6/18: Compl:0%->15%; 27/6/18: CD:Fri 15/06/18->Sun 15/12/19; 27/6/18: WID: RP-180531->RP-181375; 27/6/18: Release: Rel-15->Rel-16; 6/8/18: 37.470 to 473 and 36.470 to 473 added; | 37.470; 37.471; 37.472; 37.473; 36.470; 36.471; 36.472; 36.473 | 79 | 40 |  |  | 2018-03-27 | 2018-08-06
370 | 820080 | LTE/NR spectrum sharing in Band 41/n41 frequency range | NR_n41_LTE_41_coex | 1 | Rel-16 | R4 | 2018-12-13 | 2019-06-18 | 0% | RP-190175 |  | KDDI |  | no Perf. part; changes will happen only on NR side; 26/3/19: WID:RP-182883->RP-190175 |  | 82 |  |  |  | 2019-03-26 | 2019-03-26
371 | 820180 | Core part: LTE/NR spectrum sharing in Band 41/n41 frequency range | NR_n41_LTE_41_coex-Core | 2 | Rel-16 | R4 | 2018-12-13 | 2019-06-18 | 0% | RP-190175 |  | KDDI |  | no Perf. part; changes will happen only on NR side; 26/3/19: WID:RP-182883->RP-190175 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
372 | 800078 | 29 dBm UE Power Class for LTE band 41 and NR Band n41 | LTE_NR_B41_Bn41_PC29dBm | 1 | Rel-16 | R4 | 2018-06-15 | 2019-06-15 | 0% | RP-190502 |  | Sprint |  | no Perf. part; 26/3/19: WID:RP-181655->RP-190502 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
373 | 800178 | Core part: 29 dBm UE Power Class for LTE band 41 and NR Band n41 | LTE_NR_B41_Bn41_PC29dBm-Core | 2 | Rel-16 | R4 | 2018-06-15 | 2019-06-15 | 0% | RP-190502 |  | Sprint |  | no Perf. part; 7/3/19: WID:RP-181460->RP-181655; 26/3/19: WID:RP-181655->RP-190502 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
374 | 800058 | Dual Connectivity (EN-DC) |  | 1 | Rel-16 |  | 2018-06-15 | 2019-12-15 | 0% | [6 empty] | 80 | 41 |  |  | 2018-06-27 | NA
375 | 800066 | Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL) | DC_R16_1BLTE_1BNR_2DL2UL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190705 |  | NTT DOCOMO |  | basket WI; TR 37.716-01-01; 16/1/19: WID:RP-181447->RP-182567; 26/3/19: WID:RP-182567->RP-190705 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
376 | 800166 | Core part: Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL) | DC_R16_1BLTE_1BNR_2DL2UL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-13 | 0% | RP-190705 |  | NTT DOCOMO |  | basket WI; TR 37.716-01-01; 26/3/19: WID:RP-182567->RP-190705 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
377 | 800266 | Perf. part: Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL) | DC_R16_1BLTE_1BNR_2DL2UL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190705 |  | NTT DOCOMO |  | basket WI; 26/3/19: WID:RP-182567->RP-190705 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
378 | 800067 | Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_2BLTE_1BNR_3DL2UL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190379 |  | Huawei |  | basket WI; TR 37.716-02-01; 16/1/19: WID:RP-181357->RP-182557; 26/3/19: WID:RP-182557->RP-190379 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
379 | 800167 | Core part: Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_2BLTE_1BNR_3DL2UL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190379 |  | Huawei |  | basket WI; TR 37.716-02-01; 26/3/19: WID:RP-182557->RP-190379 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
380 | 800267 | Perf. part: Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_2BLTE_1BNR_3DL2UL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190379 |  | Huawei |  | basket WI; 26/3/19: WID:RP-182557->RP-190379 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
381 | 800068 | Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_3BLTE_1BNR_4DL2UL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190159 |  | Ericsson |  | basket WI; TR 37.716-03-01; 16/1/19: WID:RP-181407->RP-182257; 26/3/19: WID:RP-182257->RP-190159 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
382 | 800168 | Core part: Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_3BLTE_1BNR_4DL2UL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190159 |  | Ericsson |  | basket WI; TR 37.716-03-01; 26/3/19: WID:RP-182257->RP-190159 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
383 | 800268 | Perf. part: Dual Connectivity (EN-DC) of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_3BLTE_1BNR_4DL2UL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190159 |  | Ericsson |  | basket WI; 26/3/19: WID:RP-182257->RP-190159 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
384 | 800069 | Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_4BLTE_1BNR_5DL2UL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190294 |  | Nokia |  | basket WI; TR 37.716-04-01; 16/1/19: WID:RP-181001->RP-182534; 26/3/19: WID:RP-182534->RP-190294 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
385 | 800169 | Core part: Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_4BLTE_1BNR_5DL2UL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190294 |  | Nokia |  | basket WI; TR 37.716-04-01; 26/3/19: WID:RP-182534->RP-190294 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
386 | 800269 | Perf. part: Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_4BLTE_1BNR_5DL2UL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190294 |  | Nokia |  | basket WI; 26/3/19: WID:RP-182534->RP-190294 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
387 | 800070 | Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_5BLTE_1BNR_6DL2UL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-180997 |  | Samsung |  | basket WI; TR 37.716-05-01 |  | 80 | 41 |  |  | 2018-06-27 | NA
388 | 800170 | Core part: Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_5BLTE_1BNR_6DL2UL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-180997 |  | Samsung |  | basket WI; TR 37.716-05-01 |  | 80 | 41 |  |  | 2018-06-27 | NA
389 | 800270 | Perf. part: Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL) | DC_R16_5BLTE_1BNR_6DL2UL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-180997 |  | Samsung |  | basket WI |  | 80 | 41 |  |  | 2018-06-27 | NA
390 | 800071 | Dual Connectivity (EN-DC) of x bands (x=1, 2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R16_xBLTE_2BNR_yDL2UL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190151 |  | LG Electronics |  | basket WI; TR 37.716-00-02; 16/1/19: WID:RP-180777->RP-182302, "x=1" added; 26/3/19: WID:RP-182302->RP-190151 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
391 | 800171 | Core part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R16_xBLTE_2BNR_yDL2UL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190151 |  | LG Electronics |  | basket WI; TR 37.716-00-02; 26/3/19: WID:RP-182302->RP-190151 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
392 | 800271 | Perf. part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R16_xBLTE_2BNR_yDL2UL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190151 |  | LG Electronics |  | basket WI; 26/3/19: WID:RP-182302->RP-190151 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
393 | 0 | LTE-related Release 16 Features | - | 1 | Rel-16 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
394 | 790057 | E-UTRA 2.4 GHz TDD Band for US | LTE_TDD_2400_US | 1 | Rel-16 | R4 | 2018-03-15 | 2019-06-18 | 75% | RP-182405 |  | Globalstar |  | new LTE TDD band for 2483.5 to 2495MHz; compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US; 6/8/18: 36.791 added;; 16/1/19: WID:RP-180583->RP-182405 | 36.791 | 79 | 40 |  |  | 2018-03-27 | 2019-01-16
395 | 790157 | Core part: E-UTRA 2.4 GHz TDD Band for US | LTE_TDD_2400_US-Core | 2 | Rel-16 | R4 | 2018-03-15 | 2018-12-15 | 100% | RP-182405 |  | Globalstar |  | new LTE TDD band for 2483.5 to 2495MHz; compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US; 6/8/18: 36.791 added;; 16/1/19: 0%->100 | 36.791 | 79 | 40 |  |  | 2018-03-27 | 2019-01-16
396 | 790257 | Perf. part: E-UTRA 2.4 GHz TDD Band for US | LTE_TDD_2400_US-Perf | 2 | Rel-16 | R4 | 2018-03-15 | 2018-12-15 | 100% | RP-182405 |  | Globalstar |  | new LTE TDD band for 2483.5 to 2495MHz; compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US; 16/1/19: 0%->100 |  | 79 | 40 |  |  | 2018-03-27 | 2019-01-16
397 | 820063 | UE Conformance Test Aspects - E-UTRA 2.4 GHz TDD Band for US (Band 53) | LTE_TDD_2400_US-UEConTest | 2 | Rel-15 | R5 | 2018-12-13 | 2019-06-18 | 0% | RP-182406 |  | Globalstar |  | tested: REL-15 WI LTE_TDD_2400_US-Core |  | 82 |  |  |  | 2019-01-16 | NA
398 | 800059 | LTE intra-band Carrier Aggregation (CA) |  | 1 | Rel-16 |  | 2018-06-15 | 2020-06-19 | 0% | [6 empty] | 80 | 41 |  |  | 2018-06-27 | NA
399 | 800060 | Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y) | LTE_CA_R16_intra | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190157 |  | Ericsson |  | basket WI; TR 36.716-01-01; 16/1/19: WID:RP-180806->SP-182255; 26/3/19: WID:RP-182255->RP-190157 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
400 | 800160 | Core part: Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y) | LTE_CA_R16_intra-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-13 | 0% | RP-190157 |  | Ericsson |  | basket WI; TR 36.716-01-01; 26/3/19: WID:RP-182255->RP-190157 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
401 | 800260 | Perf. part: Rel-16 LTE intra-band CA for x CC DL/y CC UL including contiguous and non-contiguous spectrum (x>=y) | LTE_CA_R16_intra-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190157 |  | Ericsson |  | basket WI; 26/3/19: WID:RP-182255->RP-190157 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
402 | 800061 | Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL | LTE_CA_R16_2BDL_1BUL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190500 |  | Qualcomm |  | basket WI; TR 36.716-02-01; 16/1/19: WID:RP-181441->RP-182345; 26/3/19: WID:RP-182345->RP-190500 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
403 | 800161 | Core part: Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL | LTE_CA_R16_2BDL_1BUL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190500 |  | Qualcomm |  | basket WI; TR 36.716-02-01; 26/3/19: WID:RP-182345->RP-190500 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
404 | 800261 | Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL | LTE_CA_R16_2BDL_1BUL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190500 |  | Qualcomm |  | basket WI; 26/3/19: WID:RP-182345->RP-190500 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
405 | 800062 | Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL | LTE_CA_R16_3BDL_1BUL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190375 |  | Huawei |  | basket WI; TR 36.716-03-01; 16/1/19: WID:RP-181436->RP-182553; 26/3/19: WID:RP-182553->RP-190375 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
406 | 800162 | Core part: Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL | LTE_CA_R16_3BDL_1BUL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190375 |  | Huawei |  | basket WI; TR 36.716-03-01; 26/3/19: WID:RP-182553->RP-190375 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
407 | 800262 | Perf. part: Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL | LTE_CA_R16_3BDL_1BUL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190375 |  | Huawei |  | basket WI; 26/3/19: WID:RP-182553-> |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
408 | 800063 | Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL | LTE_CA_R16_xBDL_1BUL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190138 |  | Nokia |  | basket WI; TR 36.716-04-01; 16/1/19: WID:RP-181408->RP-182330; 26/3/19: WID:RP-182330->RP-190138 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
409 | 800163 | Core part: Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL | LTE_CA_R16_xBDL_1BUL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190138 |  | Nokia |  | basket WI; TR 36.716-04-01; 26/3/19: WID:RP-182330->RP-190138 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
410 | 800263 | Perf. part: Rel-16 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL | LTE_CA_R16_xBDL_1BUL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190138 |  | Nokia |  | basket WI; 26/3/19: WID:RP-182330->RP-190138 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
411 | 800064 | Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL | LTE_CA_R16_2BDL_2BUL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190377 |  | Huawei |  | basket WI; TR 36.716-02-02; 16/1/19: WID:RP-181356->RP-182555; 26/3/19: WID:RP-182555->RP-190377 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
412 | 800164 | Core part: Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL | LTE_CA_R16_2BDL_2BUL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190377 |  | Huawei |  | basket WI; TR 36.716-02-02; 26/3/19: WID:RP-182555->RP-190377 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
413 | 800264 | Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL | LTE_CA_R16_2BDL_2BUL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-13 | 0% | RP-190377 |  | Huawei |  | basket WI; 26/3/19: WID:RP-182555->RP-190377 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
414 | 800065 | Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL | LTE_CA_R16_xBDL_2BUL | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190150 |  | LG Electronics |  | basket WI; TR 36.716-00-02; 16/1/19: WID:RP-180778->RP-182301; 26/3/19: WID:RP-182301->RP-190150 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
415 | 800165 | Core part: Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL | LTE_CA_R16_xBDL_2BUL-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-13 | 0% | RP-190150 |  | LG Electronics |  | basket WI; TR 36.716-00-02; 26/3/19: WID:RP-182301->RP-190150 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
416 | 800265 | Perf. part: Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL | LTE_CA_R16_xBDL_2BUL-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190150 |  | LG Electronics |  | basket WI; 26/3/19: WID:RP-182301->RP-190150 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
417 | 810061 | UE Conformance Test Aspects – Rel-16 LTE CA configurations | LTE_CA_R16-UEConTest | 2 | Rel-16 | R5 | 2018-09-14 | 2020-06-19 | 0% | RP-182648 |  | Ericsson |  | 16/1/19: WID:RP-181605->RP-182648 |  | 81 | 41 |  |  | 2018-09-25 | 2019-01-16
418 | 830076 | LTE-based 5G terrestrial broadcast | LTE_terr_bcast | 1 | Rel-16 | R1 | 2018-06-15 | 2020-06-01 | 27% | RP-190732 |  | Qualcomm | [7 empty] | 2019-03-26 | NA
419 | 800091 | Study on LTE-based 5G terrestrial broadcast | FS_LTE_terr_bcast | 2 | Rel-16 | R1 | 2018-06-15 | 2019-03-15 | 100% | RP-181342 |  | Qualcomm |  | TR 36.7xx; 26/3/19: 0%->100 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
420 | 830176 | Core part: LTE-based 5G terrestrial broadcast | LTE_terr_bcast-Core | 2 | Rel-16 | R1 | 2019-03-01 | 2019-12-15 | 0% | RP-190732 |  | Qualcomm | [7 empty] | 2019-03-26 | NA
421 | 830276 | Perf. part: LTE-based 5G terrestrial broadcast | LTE_terr_bcast-Perf | 2 | Rel-16 | R4 | 2019-03-01 | 2020-06-01 | 0% | RP-190732 |  | Qualcomm | [7 empty] | 2019-03-26 | NA
422 | 830094 | Power class 2 UE for LTE bands 31 and 72 | LTE_PC2_B31_B72 | 1 | Rel-16 | R4 | 2019-03-01 | 2019-09-15 | 0% | RP-190665 |  | Nokia | [7 empty] | 2019-03-26 | NA
423 | 830194 | Core part: Power class 2 UE for LTE bands 31 and 72 | LTE_PC2_B31_B72-Core | 2 | Rel-16 | R4 | 2019-03-01 | 2019-09-15 | 0% | RP-190665 |  | Nokia | [7 empty] | 2019-03-26 | NA
424 | 830294 | Perf. part: Power class 2 UE for LTE bands 31 and 72 | LTE_PC2_B31_B72-Perf | 2 | Rel-16 | R4 | 2019-03-01 | 2019-09-15 | 0% | RP-190665 |  | Nokia | [7 empty] | 2019-03-26 | NA
425 | 800056 | Additional LTE bands |  | 1 | Rel-16 |  | 2018-06-15 | 2019-12-15 | 0% | [6 empty] | 80 | 41 |  |  | 2018-06-27 | NA
426 | 800075 | Additional LTE bands for UE category M1 and/or NB1 in Rel-16 | LTE_bands_R16_M1_NB1 | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190332 |  | Ericsson |  | basket WI; 16/1/19: WID:RP-181006->RP-182768; 26/3/19: WID:RP-182768->RP-190332 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
427 | 800175 | Core part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16 | LTE_bands_R16_M1_NB1-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190332 |  | Ericsson |  | basket WI; 26/3/19: WID:RP-182768->RP-190332 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
428 | 800275 | Perf. part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16 | LTE_bands_R16_M1_NB1-Perf | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190332 |  | Ericsson |  | basket WI; 26/3/19: WID:RP-182768->RP-190332 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
429 | 800076 | Additional LTE bands for UE category M2 and/or NB2 in Rel-16 | LTE_bands_R16_M2_NB2 | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190333 |  | Ericsson |  | basket WI; no Perf. part; 16/1/19: WID:RP-181007->RP-182769; 26/3/19: WID:RP-182769->RP-190333 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
430 | 800176 | Core part: Additional LTE bands for UE category M2 and/or NB2 in Rel-16 | LTE_bands_R16_M2_NB2-Core | 3 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190333 |  | Ericsson |  | basket WI; no Perf. part; 26/3/19: WID:RP-182769->RP-190333 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
431 | 800079 | Further performance enhancement for LTE in high speed scenario | LTE_high_speed_enh2 | 1 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-181482 |  | NTT DOCOMO |  |  |  | 80 | 41 |  |  | 2018-06-27 | NA
432 | 800179 | Core part: Further performance enhancement for LTE in high speed scenario | LTE_high_speed_enh2-Core | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-181482 |  | NTT DOCOMO |  |  |  | 80 | 41 |  |  | 2018-06-27 | NA
433 | 800279 | Perf. part: Further performance enhancement for LTE in high speed scenario | LTE_high_speed_enh2-Perf | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-181482 |  | NTT DOCOMO |  |  |  | 80 | 41 |  |  | 2018-06-27 | NA
434 | 800082 | Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | NR_CLI_RIM | 1 | Rel-16 | R1 | 2018-06-15 | 2019-06-15 | 0% | RP-190700 |  | LG Electronics |  | 16/1/19: WID:RP-181431->RP-182864; 26/3/19: WID:RP-182864->RP-190700 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
435 | 800182 | Core part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | NR_CLI_RIM-Core | 2 | Rel-16 | R1 | 2018-06-15 | 2019-06-15 | 0% | RP-190700 |  | LG Electronics |  | 26/3/19: WID:RP-182864->RP-190700 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
436 | 800282 | Perf. part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR | NR_CLI_RIM-Perf | 2 | Rel-16 | R4 | 2018-06-15 | 2019-06-15 | 0% | RP-190700 |  | LG Electronics |  | 26/3/19: WID:RP-182864->RP-190700 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
437 | 800086 | DL MIMO efficiency enhancements for LTE | LTE_DL_MIMO_EE | 1 | Rel-16 | R1 | 2018-06-15 | 2019-12-15 | 0% | RP-182901 |  | Huawei |  | 16/1/19: WID:RP-181485->RP-182901 |  | 80 | 41 |  |  | 2018-06-27 | 2019-01-16
438 | 800186 | Core part: DL MIMO efficiency enhancements for LTE | LTE_DL_MIMO_EE-Core | 2 | Rel-16 | R1 | 2018-06-15 | 2019-12-15 | 0% | RP-182901 |  | Huawei |  |  |  | 80 | 41 |  |  | 2018-06-27 | NA
439 | 800286 | Perf. part: DL MIMO efficiency enhancements for LTE | LTE_DL_MIMO_EE-Perf | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-182901 |  | Huawei |  |  |  | 80 | 41 |  |  | 2018-06-27 | NA
440 | 830085 | Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO | 1 | Rel-14 | R5 | 2019-03-01 | 2019-09-15 | 0% | RP-190650 |  | Ericsson | [7 empty] | 2019-03-26 | NA
441 | 830185 | UE Conformance Test Aspects - Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO-UEConTest | 2 | Rel-14 | R5 | 2019-03-01 | 2019-09-15 | 0% | RP-190650 |  | Ericsson | [7 empty] | 2019-03-26 | NA
442 | 820071 | Transfer of Iuant interface specifications from 25-series to 37-series | Iuant_transfer | 1 | Rel-16 | R3 | 2018-12-13 | 2019-03-18 | 100% | RP-190160 |  | Huawei |  | administrative WI that transfers REL-8 to REL-15 25.46x specs (formerly created for UMTS, later misused for LTE and recently extended to NR) into 37 series specs affecting UMTS, LTE and NR turning 25.46x specs into pointers to 37 series specs; no Perf.... |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
443 | 820171 | Core part: Transfer of Iuant interface specifications from 25-series to 37-series | Iuant_transfer-Core | 2 | Rel-16 | R3 | 2018-12-13 | 2019-03-18 | 100% | RP-190160 |  | Huawei |  | administrative WI that transfers REL-8 to REL-15 25.46x specs (formerly created for UMTS, later misused for LTE and recently extended to NR) into 37 series specs affecting UMTS, LTE and NR turning 25.46x specs into pointers to 37 series specs; no Perf.... |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
444 | 820072 | Direct data forwarding between NG-RAN and E-UTRAN nodes for inter-system mobility | Direct_data_fw_NR | 1 | Rel-16 | R3 | 2018-12-13 | 2019-06-18 | 0% | RP-182886 |  | Ericsson |  | no Perf. part |  | 82 |  |  |  | 2019-01-16 | NA
445 | 820172 | Core part: Direct data forwarding between NG-RAN and E-UTRAN nodes for inter-system mobility | Direct_data_fw_NR-Core | 2 | Rel-16 | R3 | 2018-12-13 | 2019-06-18 | 0% | RP-182886 |  | Ericsson |  | no Perf. part |  | 82 |  |  |  | 2019-01-16 | NA
446 | 800089 | Even further mobility enhancement in E-UTRAN | LTE_feMob | 1 | Rel-16 | R2 | 2018-06-15 | 2019-12-15 | 0% | RP-190272 |  | China Telecom |  | compare REL-14 WI LTE_eMob; 26/3/19: WID:RP-181475->RP-190272 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
447 | 800189 | Core part: Even further mobility enhancement in E-UTRAN | LTE_feMob-Core | 2 | Rel-16 | R2 | 2018-06-15 | 2019-12-15 | 0% | RP-190272 |  | China Telecom |  | compare REL-14 WI LTE_eMob; 26/3/19: WID:RP-181475->RP-190272 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
448 | 800289 | Perf. part: Even further mobility enhancement in E-UTRAN | LTE_feMob-Perf | 2 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-190272 |  | China Telecom |  | 26/3/19: WID:RP-181475->RP-190272 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
449 | 820078 | 410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | LTE410_Europe_PPDR | 1 | Rel-16 | R4 | 2018-12-13 | 2019-12-13 | 0% | RP-182898 |  | Nokia |  |  |  | 82 |  |  |  | 2019-01-16 | NA
450 | 820178 | Core part: 410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | LTE410_Europe_PPDR-Core | 2 | Rel-16 | R4 | 2018-12-13 | 2019-12-13 | 0% | RP-182898 |  | Nokia |  |  |  | 82 |  |  |  | 2019-01-16 | NA
451 | 820278 | Perf. part: 410 - 430 MHz E-UTRA FDD Band(s) for LTE PPDR and PMR/PAMR in Europe | LTE410_Europe_PPDR-Perf | 2 | Rel-16 | R4 | 2018-12-13 | 2019-12-13 | 0% | RP-182898 |  | Nokia |  |  |  | 82 |  |  |  | 2019-01-16 | NA
452 | 0 | All other Release 16 Features | - | 1 | Rel-16 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
453 | 830086 | Introduction of GSM, UTRA, E-UTRA and NR capability set(s) (CS(s)) to the multi-standard radio (MSR) specifications | MSR_GSM_UTRA_LTE_NR | 1 | Rel-16 | R4 | 2019-03-01 | 2019-09-15 | 0% | RP-190642 |  | Ericsson | [7 empty] | 2019-03-26 | NA
454 | 830186 | Core part: Introduction of GSM, UTRA, E-UTRA and NR capability set(s) (CS(s)) to the multi-standard radio (MSR) specifications | MSR_GSM_UTRA_LTE_NR-Core | 2 | Rel-16 | R4 | 2019-03-01 | 2019-09-15 | 0% | RP-190642 |  | Ericsson | [7 empty] | 2019-03-26 | NA
455 | 830286 | Perf. part: Introduction of GSM, UTRA, E-UTRA and NR capability set(s) (CS(s)) to the multi-standard radio (MSR) specifications | MSR_GSM_UTRA_LTE_NR-Perf | 2 | Rel-16 | R4 | 2019-03-01 | 2019-09-15 | 0% | RP-190642 |  | Ericsson | [7 empty] | 2019-03-26 | NA
456 | 810021 | Volume Based Charging Aspects for VoLTE | VBCLTE | 1 | Rel-16 | S5 | 2018-09-06 | 2019-06-14 | 50% | SP-180813 |  | Chen, Ai, China Mobile | chenai@chinamobile.com | 14/3/19: 0%->50 | 32.251; 32.260; 32.298; 32.299 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
457 | 790003 | Enhancements to IMS for new real time communication services | enIMS | 1 | Rel-16 | S1 | 2018-03-15 | 2018-12-14 | 100% | SP-180137 |  | China Mobile, Hui Cai | caihui at chinamobile dot com | 7/6/18: 0%->25; 10/9/18: 25%->50; 10/9/18: FCD:09/18->12/18; 4/12/18: 50%->100 | 22.261; 22.468; 22.228; 22.280; 22.281; 22.282; 22.179 | 79 | 40 |  |  | 2018-03-15 | 2018-12-04
458 | 820028 | Enhancement of 5G PCC related services | en5GPccSer | 1 | Rel-16 | C3 | 2018-12-13 | 2019-12-19 | 10% | CP-183246 |  | Xiaoyun Zhou, Huawei | zhouxiaoyun8@huawei.com | ; 14/3/19: 0%->10 | 29.507; 29.512; 29.513; 29.514; 29.551; 29.594; 29.214; 29.519 | 82 |  |  |  | 2018-12-07 | 2019-03-14
459 | 810023 | Energy efficiency of 5G | EE_5G | 1 | Rel-16 | S5 | 2018-09-06 | 2019-12-13 | 40% | SP-180819 |  | CORNILY, Jean-Michel, ORANGE | jeanmichel.cornily@orange.com | 7/12/18: 0%->20; 14/3/19: 20%->40 | 28.540; 28.541; 28.552; 28.554 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
460 | 820039 | Signalling Improvements for Network Efficiency in 5GS | SINE_5G | 1 | Rel-16 | C1 | 2018-12-13 | 2019-12-12 | 50% | CP-190142 |  | Shu, Lin | shulin@huawei.com | ; 14/3/19: 0%->50; 18/3/19: FCD:019->12/19; 18/3/19: WID:CP-183085->CP-190142 | 24.501; 24.301; 24.368; 27.007; 24.008 | 82 |  |  |  | 2018-12-07 | 2019-03-18
461 | 790001 | New Services and Markets Technology Enablers – Phase 2 | SMARTER_Ph2 | 1 | Rel-16 | S1 | 2018-03-15 | 2018-12-14 | 100% | SP-180589 |  | Li, Alice, Vodafone | alice.li@vodafone.com | 7/6/18: WID:SP-180138->SP-180313; 7/6/18: 0%->10; 10/9/18: 10%->40; 4/12/18: 40%->100 | 22.261; 22.278 | 79 | 40 |  |  | 2018-03-15 | 2018-12-04
462 | 780055 | 5G Voice Service Continuity | 5GVSC | 1 | Rel-16 | S1 | 2017-12-21 | 2018-03-13 | 100% | SP-171077 |  | Qun Wei, China Unicom | weiqun5@chinaunico.cn | 16/3/18: 0%->100 | 22.261 | 78 | 40 |  |  | 2017-12-21 | 2018-03-16
463 | 790015 | Security Assurance Specification for 5G | SCAS_5G | 1 | Rel-16 | S3 | 2018-03-15 | 2019-09-13 | 60% | SP-180689 |  | Marcus Wong, Huawei Technologies | mwong@huawei.com | 27/3/18: added: 33.514; 33.513; 33.511; 33.512; 33.515 ; 6/8/18: 33.511 to 515 added;; 10/9/18: 0%->10; 2/10/18: WID:SP-180238->SP-180689; 7/12/18: 10%->20; 20/3/19: 20%->60 | 33.216; 33.926; 33.515; 33.511; 33.512; 33.513; 33.514; 33.515 | 79 | 40 |  |  | 2018-03-15 | 2019-03-20
464 | 800030 | 5GS Transfer of Policies for Background Data Transfer | xBDT | 1 | Rel-16 | S2 | 2018-06-06 | 2018-12-14 | 0% | SP-180509 |  | Takeshi Usui KDDI | ta-usui@kddi.com |  | 23.501; 23.502; 23.503 | 80 | 41 |  |  | 2018-06-06 | NA
465 | 770020 | Service Interactivity | SerInter | 1 | Rel-16 | S4 | 2017-09-08 | 2019-06-14 | 70% | SP-170796 |  | Lo, Charles, Qualcomm Incorporated | clo@qti.qualcomm.com | 15/12/17: 0%->10; 16/3/18: 10%->20; 7/6/18: 20%->40; 7/6/18: FCD:06/18->12/18. Moved from Rel-15; 10/9/18: 40%->50; 7/12/18: 50%->60; 7/3/19: 60%->70; 7/3/19: FCD:12/18->06/19 | TS 26.346; TS 26.247; TS 26.347 | 77 | 39 |  |  | 2017-09-08 | 2019-03-07
466 | 770024 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 1 | Rel-16 | S4 | 2017-09-08 | 2019-12-13 | 25% | SP-170611 |  | Gibbs, Jon, Huawei Technologies Co Ltd | jon.gibbs@oblisco.com | 15/12/17: added :26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997; 15/12/17: 0%->5; 16/3/18: 5%->10; 7/6/18: 10%->15; 10/9/18: 15%->20; 7/3/19: 20%->25 | 26.114, new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997 | 77 | 39 |  |  | 2017-09-08 | 2019-03-07
467 | 800002 | Alternative EVS implementation using updated fixed-point basic operators | Alt_FX_EVS | 1 | Rel-16 | S4 | 2018-06-06 | 2018-12-14 | 100% | SP-180286 |  | Pawate, Raj, Cadence Design Systems Inc | pawateb@cadence.com | 6/8/18: 26.452 added;; 10/9/18: 0%->20; 7/12/18: 20%->90; 7/3/19: 90%->100 | 26.441; 26.442; 26.444; 26.445; 26.446; 26.447; 26.449; 26.450; 26.451; 26.952; 26.452 | 80 | 41 |  |  | 2018-06-06 | 2019-03-07
468 | 800046 | Shared Data Handling on Nudm and Nudr | Shared_Data | 1 | Rel-16 | C4 | 2018-06-06 | 2018-12-14 | 100% | CP-181136 |  | Wiehe, Ulrich, Nokia | ulrich.wiehe@nokia.com | 10/9/18: 0%->90; 10/12/18: 90%->100 | 29.503; 29.505; 29.504 | 80 | 41 |  |  | 2018-06-06 | 2018-12-10
469 | 790019 | Usage of CAPIF for xMB API | CAPIF4xMB | 1 | Rel-16 | S4 | 2018-03-15 | 2018-12-14 | 100% | SP-180031 |  | Thorsten Lohmar, Ericsson LM | Thorsten.lohmar@ericsson.com | 7/6/18: 0%->25; 6/8/18: 26.348 added;; 10/9/18: 25%->40; 7/12/18: 40%->100 | 26.346, new; 26.348 | 79 | 40 |  |  | 2018-03-15 | 2018-12-07
470 | 800009 | Policy delivery to UE for background data transfer | PDBDT | 1 | Rel-16 | S1 | 2018-05-08 | 2018-06-15 | 100% | SP-180324 |  | Takatsugu Kito, KDDI | ta-kito at kddi dot com | 10/9/18: 90%->100 | 22.261 | 80 | 41 |  |  | 2018-06-06 | 2018-09-10
471 | 790004 | QoS Monitoring | QoS_MON | 1 | Rel-16 | S1 | 2018-03-15 | 2018-12-14 | 100% | SP-180141 |  | Amar Deol | amar.deol@huawei.com | 7/6/18: 0%->60; 10/9/18: 60%->85; 10/9/18: FCD:06/18->12/18; 4/12/18: 85%->100 | TS 22.261 | 79 | 40 |  |  | 2018-03-15 | 2018-12-04
472 | 800005 | Inter-RAT Mobility requirements for real time service | MOBRT | 1 | Rel-16 | S1 | 2018-06-06 | 2018-09-14 | 100% | SP-180592 |  | Yang Xu, Oppo | xuyang@oppo.com | 10/9/18: 70%->100 | 22.261 | 80 | 41 |  |  | 2018-06-06 | 2018-09-10
473 | 760058 | Management of QoE measurement collection | QOED | 1 | Rel-16 | S5 | 2017-06-05 | 2019-09-12 | 55% | SP-181069 |  | Petersen, Robert, Ericsson | robert <dot> petersen <at>ericsson<dot>ericsson | 30/6/17: 28.309 added;; 30/6/17: 28.308 added;; 30/6/17: 28.307 added;; 30/6/17: 28.406 added;; 11/9/17: 0%->5; 15/12/17: 5%->15; 16/3/18: 15%->25; 7/6/18: FCD:06/18->12/18. 16/6/16: moved from Rel-15; 10/9/18: 25%->30; 7/12/18: 30%->40; 13/12/18: FCD:... | 32.101; 32.103; 6 new TS; 28.309; 28.308; 28.307; 28.406; 28.405; 28.404 | 76 | 39 |  |  | 2017-06-07 | 2019-03-14
474 | 760059 | Study on network policy management for mobile networks based on NFV scenarios | FS_NETPOL | 1 | Rel-15 | S5 | 2017-06-05 | 2018-06-14 | 100% | SP-170593 |  | China Mobile Jinglei Liu | liujinglei@chinamobile.com | 30/6/17: 32.871 added;; 11/9/17: 0%->20; 15/12/17: 20%->30; 16/3/18: 30%->35; 7/6/18: 35%->100 | new; 32.871 | 76 | 39 |  |  | 2017-06-05 | 2018-06-07
475 | 810025 | Network policy management for mobile networks based on NFV scenarios | NETPOL | 1 | Rel-16 | S5 | 2018-09-06 | 2019-09-13 | 10% | SP-180821 |  | China Mobile Hao Zhang | zhanghao@chinamobile.com | 7/12/18: 0%->10 | New | 81 | 41 |  |  | 2018-09-06 | 2018-12-07
476 | 810027 | Intent driven management service for mobile network | IDMS_MN | 1 | Rel-16 | S5 | 2018-09-06 | 2019-06-14 | 30% | SP-180899 |  | Zou Lan, Huawei | zoulan@huawei.com | 7/12/18: 0%->20; 14/3/19: 20%->30 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
477 | 810024 | OAM aspects of LTE and WLAN integration | OAM_LTE_WLAN | 1 | Rel-16 | S5 | 2018-09-06 | 2019-06-14 | 100% | SP-180820 |  | Yizhi Yao, Intel Corporation | yizhi dot yao at intel dot com | 7/12/18: 0%->50; 14/3/19: 50%->100 | 32.425; 28.621; 28.622; 28.623; 28.657; 28.658; 28.659 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
478 | 810026 | Methodology for 5G management specifications | METHOGY | 1 | Rel-16 | S5 | 2018-09-06 | 2019-03-15 | 85% | SP-180822 |  | Groenendijk, Jan, Ericsson | jan<dot>Groenendijk<at>ericsson<dot>com | 7/12/18: 0%->60; 14/3/19: 60%->85 | New; 32.156 | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
479 | 820030 | Nchf Online and Offline charging services | OFSBI_CH | 1 | Rel-16 | S5 | 2018-12-13 | 2019-09-19 | 40% | SP-181066 |  | Zhu Lei, Huawei | Zhulei@huawei.com | ; 14/3/19: 0%->40 | 32.240; 32.255; 32.290; 32.291; 32.298 | 82 |  |  |  | 2018-12-07 | 2019-03-14
480 | 820031 | Charging Enhancement of 5GC interworking with EPC | 5GIEPC_CH | 1 | Rel-16 | S5 | 2018-12-13 | 2019-09-19 | 30% | SP-181067 |  | Chen Shan, Huawei | chenshan@huawei.com | ; 14/3/19: 0%->30 | 32.255; 32.291; 32.298 | 82 |  |  |  | 2018-12-07 | 2019-03-14
481 | 820032 | NRM enhancements | eNRM | 1 | Rel-16 | S5 | 2018-12-13 | 2019-09-12 | 10% | SP-190140 |  | Jing Ping, Nokia | jing.ping@nokia-sbell.com | ; 14/3/19: 0%->10; 21/3/19: WID:SP-181068 ->SP-190140; 21/3/19: FCD:019->09/19 | 28.540; 28.541; 28.622 ; 28.623; 28.620 | 82 |  |  |  | 2018-12-07 | 2019-03-21
482 | 820033 | Network Exposure Charging in 5G System Architecture | 5GS_Ph1_NEFCH | 1 | Rel-16 | S5 | 2018-12-13 | 2019-12-19 | 20% | SP-181070 |  | Tornkvist, Robert, Ericsson | robert(dot)tornkvist(at)Ericsson(dot)com | ; 14/3/19: 0%->20 | 32.240; 32.254; 32.290; 32.291; 32.298 | 82 |  |  |  | 2018-12-07 | 2019-03-14
483 | 820034 | Charging AMF in 5G System Architecture Phase 1 | 5GS_Ph1_AMFCH | 1 | Rel-16 | S5 | 2018-12-13 | 2019-12-19 | 20% | SP-181071 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | ; 14/3/19: 0%->20 | 32.240; 32.290; 32.291; 32.298; 32.297 | 82 |  |  |  | 2018-12-07 | 2019-03-14
484 | 820035 | Discovery of management services in 5G | 5GDMS | 1 | Rel-16 | S5 | 2018-12-13 | 2019-06-19 | 25% | SP-181072 |  | Attila Horvat, Huawei Technologies Sweden AB | attila.horvat@huawei.com | ; 14/3/19: 0%->25 | 28.533; 28.532; 28.531 | 82 |  |  |  | 2018-12-07 | 2019-03-14
485 | 820036 | Trace Management in the context of Services Based Management Architecture | TM_SBMA | 1 | Rel-16 | S5 | 2018-12-13 | 2019-06-19 | 0% | SP-181073 |  | Andrianov, Anatoly, Nokia | anatoly.andrianov@nokia.com |  | 32.421; 32.422; 28.530; 28.532; 28.533; 28.540; 28.541 | 82 |  |  |  | 2018-12-07 | NA
486 | 820005 | Lawful Interception Rel-16 | LI16 | 1 | Rel-16 | S3LI | 2018-12-13 | 2019-12-19 | 0% | SP-181210 |  | Alex Leadbeater, BT | alex.leadbeater@bt.com |  | 33.107; 33.108; 33.126; 33.127; 33.128 | 82 |  |  |  | 2018-12-07 | NA
487 | 820038 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc16 | 1 | Rel-16 | C1 | 2018-12-13 | 2019-12-19 | 25% | CP-183084 |  | Leis, Peter, Nokia | peter.leis@nokia.com | ; 14/3/19: 0%->25 | 23.218; 24.229; 24.930; 29.163; 29.165; 29.292 | 82 |  |  |  | 2018-12-07 | 2019-03-14
488 | 820041 | Stage-3 5GS NAS protocol development | 5GProtoc16 | 1 | Rel-16 | C1 | 2018-12-13 | 2019-12-19 | 25% | CP-183087 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com |  | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 | 82 |  |  |  | 2018-12-07 | NA
489 | 820049 | Stage-3 5GS NAS protocol development general aspects | 5GProtoc16 | 2 | Rel-16 | C1 | 2018-12-13 | 2019-12-19 | 25% | CP-183087 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ; 14/3/19: 0%->25 | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 | 82 |  |  |  | 2018-12-07 | 2019-03-14
490 | 820050 | Stage-3 5GS NAS protocol development for support for non-3GPP accesses | 5GProtoc16-non3GPP | 2 | Rel-16 | C1 | 2018-12-13 | 2019-12-19 | 25% | CP-183087 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ; 14/3/19: 0%->25 | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.229; 24.301; 24.302; 24.305; 24.368; 24.501; 24.502; 24.526; 27.007 | 82 |  |  |  | 2018-12-07 | 2019-03-14
491 | 820042 | Stage-3 SAE Protocol Development for Rel16 | SAES16 | 1 | Rel-16 | C1 | 2018-12-13 | 2019-12-19 | 25% | CP-183088 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com |  | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 82 |  |  |  | 2018-12-07 | NA
492 | 820046 | Stage-3 SAE Protocol Development for Rel16 general aspects | SAES16 | 2 | Rel-16 | C1 | 2018-12-13 | 2019-12-19 | 25% | CP-183088 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com | 14/3/19: 0%->25 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 82 |  |  |  | 2018-12-07 | 2019-03-14
493 | 820047 | Stage-3 SAE Protocol Development for Rel16 for CS Fallback in EPS | SAES16-CSFB | 2 | Rel-16 | C1 | 2018-12-13 | 2019-12-19 | 25% | CP-183088 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com | 14/3/19: 0%->25 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 82 |  |  |  | 2018-12-07 | 2019-03-14
494 | 820048 | Stage-3 SAE Protocol Development Rel16 for support for non-3GPP accesses | SAES16-non3GPP | 2 | Rel-16 | C1 | 2018-12-13 | 2019-12-19 | 25% | CP-183088 |  | Aghili, Behrouz, InterDigital Communications | behrouz.aghili@interdigital.com | 14/3/19: 0%->25 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 82 |  |  |  | 2018-12-07 | 2019-03-14
495 | 770050 | (Small) Technical Enhancements and Improvements for Rel-16 | TEI16 | 1 | Rel-16 |  | 2017-09-11 | 2018-12-14 | 100% | [6 empty] | 77 | 41 |  |  | 2015-06-15 | 2015-06-15
496 | 800100 | (IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (RFC 8446) | TEI16 | 2 | Rel-16 | S3-IETF | 2017-09-11 | 2018-12-14 | 100% | [6 empty] | 80 | 41 |  |  | 2018-06-27 | NA
497 | 0 | Release 16 Studies with no corresponding Feature | - | 1 | Rel-16 |  | 2016-03-15 | 2016-03-15 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
498 | 0 | Release 16 Studies on 5G/5GS/5GC/NR | - | 1 | Rel-16 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
499 | 800029 | Study on system architecture for next generation real time communication services | FS_NG_RTC | 1 | Rel-16 | S2 | 2018-06-06 | 2019-03-14 | 0% | SP-180508 |  | Yi Jiang | jiangyi at chinamobile dot com |  | New | 80 | 41 |  |  | 2018-06-06 | NA
500 | 800034 | Study on Security Aspects of the 5G Service Based Architecture | FS_SBA_Sec | 1 | Rel-16 | S3 | 2018-06-06 | 2019-09-12 | 65% | SP-180598 |  | Hans Christian Rudolph, Deutsche Telekom AG | hans-christian.rudolph@telekom.de | 6/8/18: 33.855 added;; 10/9/18: 65%->75; 7/12/18: 75%->76; 20/3/19: 76%->65; 20/3/19: FCD:018->09/19 | New; 33.855 | 80 | 41 |  |  | 2018-06-06 | 2019-03-20
501 | 810030 | Study on Self-Organizing Networks (SON) for 5G | FS_SON_5G | 1 | Rel-16 | S5 | 2018-09-06 | 2019-06-14 | 40% | SP-180827 |  | Joey Chou, Intel | joey<dot>chou<at>intel<dot>com | 7/12/18: 0%->10; 14/3/19: 10%->40 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
502 | 800044 | Study on Load and Overload Control of 5GC Service Based Interfaces | FS_LOLC | 1 | Rel-16 | C4 | 2018-06-06 | 2019-06-14 | 50% | CP-181195 |  | Sridhar Bhaskaran (Huawei) | sridhar.bhaskaran@huawei.com | 6/8/18: 22.943 added;; 10/9/18: 0%->5; 10/12/18: 5%->25; 14/3/19: 25%->50 | New; 22.943 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
503 | 790014 | Study on security aspects of single radio voice continuity from 5G to UTRAN | FS_5G_UTRAN_SEC | 1 | Rel-16 | S3 | 2018-03-15 | 2019-03-15 | 100% | SP-180209 |  | Feng Gao, China Unicom | gaofeng149@chinaunicom.cn | 27/3/18: 33.856 added;; 7/6/18: 0%->50; 10/9/18: 50%->79; 7/12/18: 79%->100 | 33.856 | 79 | 40 |  |  | 2018-03-15 | 2018-12-07
504 | 780023 | Study on supporting 256-bit algorithms for 5G | FS_256_Algo | 1 | Rel-16 | S3 | 2017-12-15 | 2018-09-14 | 100% | SP-171054 |  | Evans, Tim, Vodafone Group | tim.evans1@vodafone.com | 16/3/18: 0%->30; 7/6/18: 30%->55; 10/9/18: 55%->60; 7/12/18: 60%->100 | new | 78 | 40 |  |  | 2017-12-15 | 2018-12-07
505 | 800045 | Study on IETF QUIC Transport for Service Based Interfaces | FS_QUIC | 1 | Rel-16 | C4 | 2018-06-06 | 2019-06-12 | 75% | CP-183245 |  | Sridhar Bhaskaran (Huawei) | sridhar.bhaskaran@huawei.com | 6/8/18: 29.893 added;; 10/9/18: 0%->40; 10/12/18: FCD:03/19->06/19; 10/12/18: 40%->50; 10/12/18: WID:CP-181194->CP-183245; 14/3/19: 50%->75 | New; 29.893 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
506 | 780001 | Study on User Plane Protocol in 5GC | FS_UPPS | 1 | Rel-16 | C4 | 2017-12-15 | 2019-06-14 | 70% | CP-182052 |  | Satoru Matsushima, SoftBank Corp | satoru.matsushima@g.softbank.co.jp | 16/3/18: 0%->5; 2/10/18: WID:CP-173160->CP-182052; 2/10/18: FCD:09/18->06/19; 14/3/19: 20%->70 | 29.892 | 78 | 40 |  |  | 2017-12-15 | 2019-03-14
507 | 790012 | Study on Application Awareness Interworking between LTE and NR | FS_AAI_LTE_NR | 1 | Rel-16 | S2 | 2018-03-15 | 2019-03-14 | 30% | SP-180122 |  | Biao Long, China Telecom | longb.gd@chinatelecom.cn | 7/6/18: 0%->30; 6/8/18: 23.727 added; | new; 23.727 | 79 | 40 |  |  | 2018-03-15 | 2018-08-06
508 | 800090 | Study on NR beyond 52.6 GHz | FS_NR_beyond_52GHz | 1 | Rel-16 | RP | 2018-06-15 | 2018-09-14 | 0% | RP-181435 |  | Intel |  |  | 38.8xx | 80 | 41 |  |  | 2018-08-06 | NA
509 | 800093 | Study on remote interference management for NR | FS_NR_RIM | 1 | Rel-16 | R1 | 2018-06-15 | 2018-12-15 | 100% | RP-181430 |  | CMCC |  | TR 38.8xx; see follow-up REL-16 WI NR_CLI_RIM; 16/1/19: 0%->100 |  | 80 | 41 |  |  | 2018-06-27 | 2019-01-16
510 | 801000 | Study on RAN-centric data collection and utilization for LTE and NR | FS_LTE_NR_data_collect | 1 | Rel-16 | R3 | 2018-06-01 | 2019-06-01 | 0% | RP-181456 |  | CMCC |  | TR 37.8XX, related to SON, MDT |  | 80 | 41 |  |  | 2018-06-27 | NA
511 | 801001 | Study on radiated metrics and test methodology for the verification of multi-antenna reception performance of NR UEs | FS_NR_MIMO_OTA_test | 1 | Rel-16 | R4 | 2018-06-15 | 2019-12-15 | 0% | RP-181402 |  | CATR |  | related REL-15 SI FS_NR_test_methods |  | 80 | 41 |  |  | 2018-06-27 | NA
512 | 801002 | Study on evaluation for 2 RX exception in Rel-15 vehicle mounted UE for NR | FS_NR_2RX_vehUE | 1 | Rel-16 | R4 | 2018-06-01 | 2018-12-15 | 100% | RP-181467 |  | Samsung |  | TR 38.8XX; 16/1/19: 0%->100 |  | 80 | 41 |  |  | 2018-06-27 | 2019-01-16
513 | 750044 | Study of test methods for New Radio | FS_NR_test_methods | 1 | Rel-16 | R4 | 2017-03-15 | 2018-09-14 | 100% | RP-180546 |  | Intel |  | TR 38.8XX; 19/6/17: Compl:0%->10%; 19/6/17: WID: RP-170824->RP-171021; 30/6/17: 38.810 added;19/9/17: Compl:10%->15%19/9/17: WID: RP-171021->RP-171828; 8/1/18: Compl:15%->20%27/3/18: Compl:20%->45%27/3/18: CD:Thu 15/ ; 2; 16/1/19: 75%->100 | 38.81 | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
514 | 750046 | Study on Non-Orthogonal Multiple Access (NOMA) for NR | FS_NR_NOMA | 1 | Rel-16 | R1 | 2017-03-15 | 2018-12-14 | 100% | RP-181403 |  | ZTE |  | TR 38.8XX; 19/6/17: WID: RP-170829->RP-171043; 30/6/17: 32.812 added;; 27/6/18: Compl:0%->40%; 27/6/18: CD:Fri 15/06/18->Sat 15/12/18; 27/6/18: WID: RP-171043->RP-181403;; 16/1/19: 40%->100 | 32.812 | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
515 | 810032 | Study on 5G security enhancement against false base stations | FS_5GFBS | 1 | Rel-16 | S3 | 2018-09-06 | 2019-09-12 | 50% | SP-180690 |  | Ivy Guo, Apple | ivy_guo@apple.com | 7/12/18: 0%->10; 20/3/19: FCD:019->09/19; 20/3/19: 10%->50 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-20
516 | 810033 | Study of KDF negotiation for 5G System Security | FS_5GS_KDF | 1 | Rel-16 | S3 | 2018-09-06 | 2019-06-14 | 100% | SP-180691 |  | Ahmad Muhanna | ahmad.muhanna@huawei.com | 7/12/18: 0%->55; 20/3/19: 55%->100 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-20
517 | 760053 | Study on Long Term Key Update Procedures | FS_LTKUP | 1 | Rel-16 | S3 | 2017-06-05 | 2018-12-14 | 100% | SP-170413 |  | Evans, Tim, Vodafone | tim.evans1@vodafone.com | 11/9/17: 0%->10; 15/12/17: 10%->70; 15/12/17: FCD:12/17->03/18; 16/3/18: 70%->90; 16/3/18: FCD:03/18->06/18; 7/6/18: FCD:06/18->12/18. 10/9/18: moved from Rel-15 as per SP-180687; 7/12/18: 90%->100 | Internal TR | 76 | 39 |  |  | 2017-06-03 | 2018-12-07
518 | 820010 | Study on Long Term Key Update Process (LTKUP) Detailed solutions | FS_LTKUP_Detail | 1 | Rel-16 | S3 | 2018-12-13 | 2019-09-19 | 60% | SP-181038 |  | Evans, Tim, Vodafone | tim.evans1@vodafone.com | 20/3/19: 0%->60; 20/3/19: 0%->60 |  | 82 |  |  |  | 2018-12-06 | 2019-03-20
519 | 820006 | Study on User Plane Integrity Protection | FS_UP_IP_Sec | 1 | Rel-16 | S3 | 2018-12-13 | 2019-09-19 | 15% | SP-181035 |  | Evans, Tim, Vodafone | tim.evans1@vodafone.com | 20/3/19: 0%->15; 20/3/19: 0%->15 |  | 82 |  |  |  | 2018-12-06 | 2019-03-20
520 | 810006 | Study on eXtended Reality (XR) in 5G | FS_5GXR | 1 | Rel-16 | S4 | 2018-10-02 | 2019-12-13 | 35% | SP-180667 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 2/10/18: Moved from Rel-17. 17/01/19: acronym corrected from FS_XR5G; 12/3/19: 0%->35 | 26.9xx | 81 | 41 |  |  | 2018-09-06 | 2019-03-12
521 | 820060 | Study on 7 - 24 GHz frequency range for NR | FS_7to24GHz_NR | 1 | Rel-16 | R4 | 2018-12-13 | 2019-12-13 | 0% | RP-190373 |  | Huawei |  | TR. 38.8xx; 26/3/19: WID:RP-182884->RP-190373 |  | 82 |  |  |  | 2019-01-16 | 2019-03-26
522 | 820009 | Study on authentication enhancements in 5GS | FS_AUTH_ENH | 1 | Rel-16 | S3 | 2018-12-13 | 2019-09-19 | 5% | S3-183745 |  | Ben Henda, Noamen, Ericsson | noamen.ben.henda@ericsson.com. | 07/19: Rel corrected, was wrongly allocated to Rel-17; 20/3/19: 0%->5 | new | 82 |  |  |  | 2018-12-06 | 2019-03-20
523 | 830006 | Study on UEs Supporting Handset Mode with Non-Traditional Earpieces | FS_HaNTE | 1 | Rel-16 | S4 | 2019-03-14 | 2019-09-12 | 0% | SP-190041 |  | Schevciw, Andre, Qualcomm Incorporated | aschevci@qti.qualcomm.com |  | New |  |  |  |  | 2019-03-14 | NA
524 | 830072 | Study on enhancement for disaggregated gNB architecture | FS_enh_disagg_gNB | 1 | Rel-16 | R3 | 2019-03-01 | 2019-12-15 | 0% | RP-190702 |  | China Telecom | [7 empty] | 2019-03-26 | NA
525 | 0 | Release 16 other Studies | - | 1 | Rel-16 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
526 | 800027 | Study on supporting Flexible Local Area Data Network | FS_FLADN | 1 | Rel-16 | S2 | 2018-06-06 | 2019-03-14 | 0% | SP-180506 |  | LG Electronics, | hyuns.kim@lge.com | 10/9/18: FCD:12/18->03/19 | New | 80 | 41 |  |  | 2018-06-06 | 2018-09-10
527 | 800036 | Study on authentication and key management for applications based on 3GPP credential in 5G | FS_AKMA | 1 | Rel-16 | S3 | 2018-06-06 | 2019-09-12 | 60% | SP-180443 |  | Jin Peng, China Mobile | pengjin@chinamobile.com | 6/8/18: 33.835 added;; 7/12/18: 5%->20; 20/3/19: 20%->60; 20/3/19: FCD:019->09/19 | New; 33.835 | 80 | 41 |  |  | 2018-06-06 | 2019-03-20
528 | 770003 | Study on enhancements to IMS for new real time communication services | FS_enIMS | 1 | Rel-16 | S1 | 2017-09-08 | 2017-12-15 | 100% | SP-170703 |  | China Mobile, Hui Cai | caihui at chinamobile dot com | 11/9/17: 0%->20; 15/12/17: 22.823 added;; 15/12/17: 20%->75; 16/3/18: 75%->100 | New; 22.823 | 77 | 39 |  |  | 2017-09-08 | 2018-03-16
529 | 800037 | Study on protocol enhancement for real time communication | FS_PROTIMP | 1 | Rel-16 | S5 | 2018-06-06 | 2019-03-14 | 0% | SP-180597 |  | Olaf Pollakowski, Nokia | olaf.pollakowski@nokia.com | 6/8/18: 28.823 added; | New; 28.823 | 80 | 41 |  |  | 2018-06-06 | 2018-08-06
530 | 800038 | Study on integration of ONAP and 3GPP configuration management services for 5G networks | FS_ONAPCINT | 1 | Rel-16 | S5 | 2018-06-06 | 2019-03-14 | 100% | SP-181075 |  | Li Gang, Ericsson | gang.g.li@ericsson.com | 10/9/18: 0%->5; 7/12/18: 5%->60; 14/12/18: WID:SP-180388->SP-181075; 14/3/19: 60%->100 | New | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
531 | 780031 | Study on integration of ONAP DCAE and 3GPP management architecture | FS_ONAPDCAE | 1 | Rel-16 | S5 | 2017-12-15 | 2019-03-15 | 100% | SP-181074 |  | ORANGE (Jean-Michel Cornily | jeanmichel.cornily@orange.com | 16/3/18: 0%->10; 27/3/18: 28.900 added;; 7/6/18: 10%->20; 7/6/18: FCD:09/18->03/19; 15/6/18: WID:SP-170948->SP-180389; 10/9/18: 20%->35; 7/12/18: 35%->80; 14/12/18: WID:SP-180389->SP-181074; 14/3/19: 80%->100 | 28.9 | 78 | 40 |  |  | 2017-12-15 | 2019-03-14
532 | 800039 | Study on management aspects of edge computing | FS_MAN_EC | 1 | Rel-16 | S5 | 2018-06-06 | 2019-03-14 | 50% | SP-180390 |  | Joey Chou, Intel | joey<dot>chou<at>intel<dot>com | 6/8/18: 28.803 added;; 10/9/18: 0%->10; 7/12/18: 10%->20; 14/3/19: 20%->50 | New; 28.803 | 80 | 41 |  |  | 2018-06-06 | 2019-03-14
533 | 760045 | Study on encrypted traffic detection | FS_ENTRADE | 1 | Rel-16 | S2 | 2017-06-05 | 2019-06-12 | 70% | SP-181111 |  | Chi Ren, China Unicom | renchi1@chinaunicom.cn | ; 15/12/17: Changed Rel-15->Rel-16; 16/3/18: WID:SP-170381->SP-170934; 16/3/18: 0%->20; 7/6/18: 20%->70; 14/12/18: FCD:09/18->06/19. Name changed | new 23.787 | 76 | 39 |  |  | 2017-06-03 | 2018-12-14
534 | 750048 | Study on self-evaluation towards IMT-2020 submission | FS_5G_eval | 1 | Rel-16 | ITU-R AH | 2016-12-14 | 2019-06-14 | 35% | RP-181318 |  | Huawei |  | TR 38.9XX; 19/6/17: CD:Sat 15/09/18->Fri 15/06/18; 19/6/17: WID: RP-170832->RP-171451; 19/6/17: Release: Rel-16->Rel-15; 8/1/18: Compl:0%->15%27/3/18: Compl:15%->25%; 27/6/18: Compl:25%->35%; 27/6/18: CD:Fri 15/0 |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
535 | 780060 | Study on 6 GHz for LTE and NR | FS_6GHz_LTE_NR | 1 | Rel-16 | RP | 2017-12-15 | 2018-12-14 | 30% | RP-190681 |  | Ericsson |  | SI under RAN leadership; TR 37.8XX27/3/18: Compl:0%->25%27/3/18: WID: RP-172804->RP-180168; 27/3/18: 37.890 added;; 27/3/18: 37.107 added;; 27/6/18: Compl:25%->30%; 27/6/18: CD:Fri 15/; 26/3/19: WID:RP-181019->RP-190681 | 37.890; 37.107 | 78 | 40 |  |  | 2018-01-08 | 2019-03-26
536 | 810029 | Study on management aspects of communication services | FS_CSMAN | 1 | Rel-16 | S5 | 2018-09-06 | 2019-06-14 | 70% | SP-180923 |  | Groenendijk, Jan, Ericsson | jan<dot>Groenendijk<at>ericsson<dot>com. | 7/12/18: 0%->40; 14/3/19: 40%->70 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-14
537 | 810037 | Study on SECAM and SCAS for 3GPP virtualized network products | FS_VNP_SECAM_SCAS | 1 | Rel-16 | S3 | 2018-10-02 | 2019-09-13 | 20% | SP-180696 |  | Minpeng Qi, China Mobile | qiminpeng@chinamobile.com | 2/10/18: Moved from Rel-17; 7/12/18: 0%->5; 20/3/19: 5%->20 | New | 81 | 41 |  |  | 2018-09-06 | 2019-03-20
538 | 820007 | Study on Security Impacts of Virtualisation | FS_SIV | 1 | Rel-16 | S3 | 2018-12-13 | 2019-09-19 | 2% | SP-181236 |  | Alex Leadbeater, BT Plc | alex.leadbeater@bt.com | 20/3/19: 0%->2; 20/3/19: 0%->2 |  | 82 |  |  |  | 2018-12-06 | 2019-03-20
539 | 810005 | Study on Typical Traffic Characteristics of Media Services | FS_TyTrac | 1 | Rel-16 | S4 | 2018-10-02 | 2019-12-13 | 45% | SP-180666 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 2/10/18: Moved from Rel-17; 12/3/19: 0%->45 | 26.9xx | 81 | 41 |  |  | 2018-09-06 | 2019-03-12
540 | 820037 | Study on non-file-based trace reporting | FS_OAM_RTT | 1 | Rel-16 | S5 | 2018-12-06 | 2019-06-12 | 0% | SP-181076 |  | Andrianov, Anatoly, Nokia | anatoly.andrianov@nokia.com |  |  | 82 |  |  |  | 2018-12-07 | NA
541 | 820004 | Study on ambient noise test methodology for evaluation of acoustic UE performance | FS_ANTeM | 1 | Rel-16 | S4 | 2018-12-06 | 2019-12-12 | 0% | SP-180986 |  | Jan Reimes, HEAD acoustics GmbH | jan.reimes@head-acoustics.de | 12/3/19: 0%->10 |  | 82 |  |  |  | 2018-12-07 | 2019-03-12
542 | 0 | Release 15 Features | - | 1 | Rel-15 |  | 2016-03-15 | 2016-03-15 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
543 | 0 | Release 15 Features on 5G | - | 1 | Rel-15 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
544 | 740005 | 5G System - Phase 1 | 5GS_Ph1 | 1 | Rel-15 |  | 2016-06-09 | 2019-06-14 | 92% | SP-160958 |  | China Mobile, Tao Sun | suntao@chinamobile.com | 15/12/17: 23.503 added; |  | 74 | 38 |  |  | 2016-12-01 | 2017-12-15
545 | 750019 | Study on Charging Aspects of 5G System Architecture Phase 1 | FS_5GS_Ph1_CH | 2 | Rel-15 | S5 | 2017-03-03 | 2017-12-15 | 100% | SP-170953 |  | Chen, Shan, Huawei | chenshan@huawei.com | 7/6/17: 0%->15; 11/9/17: 15%->60; 11/9/17: WID:SP-170128->SP-170659; 15/12/17: 60%->100; 21/12/17: WID:SP-170659->SP-170953 |  | 75 | 38 |  |  | 2017-03-03 | 2017-12-21
546 | 720005 | (Stage 1 of 5G) New Services and Markets Technology Enablers | SMARTER | 2 | Rel-15 | S1 | 2016-06-09 | 2017-03-15 | 100% | SP-160364 |  | Li, Alice | alice.li@vodafone.com | Resulting from FS_SMARTER; 19/9/16: 0%->55; 6/10/16: 22.261 added; 1/12/16: FCD:09/16->03/20; 1/12/16: 55%->75; 2/3/17: 75%->90; 7/6/17: 90%->100 | 22.261 | 72 | 37 |  |  | 2016-06-09 | 2017-06-07
547 | 740061 | Stage 2 of 5G System - Phase 1 | 5GS_Ph1 | 2 | Rel-15 | S2 | 2016-12-01 | 2017-12-14 | 100% | SP-160958 |  | China Mobile, Tao Sun | suntao@chinamobile.com | 3/3/17: 0%->30; 7/6/17: 30%->55; 11/9/17: 55%->75; 21/12/17: 75%->95; 11/6/18: 95%->100 | 23.401, 23.167, 23.271, 23.002; 23.228, 23.401, 23.167, 23.271, 23.502, 23.501; 23.503 | 74 | 38 |  |  | 2016-12-01 | 2018-06-11
548 | 750016 | Security aspects of 5G System - Phase 1 | 5GS_Ph1-SEC | 2 | Rel-15 | S3 | 2017-03-02 | 2018-06-15 | 100% | SP-180693 |  | NTT DOCOMO, Alf Zugenmaier | alf.zugenmaier@hm.edu | 7/6/17: 0%->10; 11/9/17: 10%->30; 15/12/17: 30%->65; 21/12/17: WID:SP-170234->SP-170881; 16/3/18: 65%->85; 16/3/18: FCD:03/18->06/18; 7/6/18: 85%->95; 10/9/18: WID:SP-170881->100; 10/9/18: 95%->100; 2/10/18: WID:SP-170881->SP-180693 | 33.501; 33.401; 33.210; 33.310; 33.220 | 75 | 38 |  |  | 2017-03-02 | 2018-10-02
549 | 750025 | CT aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 2 | Rel-15 | ct | 2017-03-03 | 2018-06-14 | 99% | CP-183243 |  | Song Yue (China Mobile) | songyue at chinamobile.com | 6/17: WID:CP-170204->CP-171105; 9/17: WID:CP-171105->CP-172034. Rapp changed, impacted TS clarified; 12/17: added: 24.501 ; 24.502 ; 29.520 added; 29.514; 29.513 ; 29.520a; 29.514a; 12/17: 29.519 added; 29.516 added;; : 2.. 3/18: 29.554 added;29.59; 6/... | 24.501; 24.502; 29.520; 29.514; 29.513; ; 29.520a; 29.514a; 29.519; 29.516; 29.512; 29.508; 29.507; 29.551; 29.554; 29.522; 24.568; 29.521; 29.525; 29.524; 29.523 | 75 | 38 |  |  | 2017-03-03 | 2018-12-10
550 | 750026 | Studies on CT1 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 |  | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 18/12/17: WID:CP-172034->CP-173161 | 23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007 | 75 | 38 |  |  | 2017-03-03 | 2017-12-18
551 | 770042 | Study on 5G Network selection | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail; 11/9/17: 10%->55; 15/12/17: 55%->80; 16/3/18: 80%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2018-03-16
552 | 770043 | Study on 5G Mobility management | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail; 11/9/17: 40%->70; 15/12/17: 70%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2017-12-15
553 | 770044 | Study on 5G Session management | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail; 11/9/17: 35%->75; 15/12/17: 75%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2017-12-15
554 | 770045 | Study on 5G Non-3GPP access networks | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail; 11/9/17: 15%->55; 15/12/17: 55%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2017-12-15
555 | 770046 | Study on 5G Interworking with EPC | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail; 11/9/17: 15%->45; 15/12/17: 45%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2017-12-15
556 | 770047 | Study on 5G System core network impact on services, network functions and capabilities | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail; 11/9/17: 20%->65; 15/12/17: 65%->85; 16/3/18: 85%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2018-03-16
557 | 770048 | Study on 5G Network slicing | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | Task introduced as per CT1's chair e-mail; 11/9/17: 10%->45; 15/12/17: 45%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2017-12-15
558 | 780008 | CT1 aspects of 5G System - Phase 1 (normative work) | 5GS_Ph1-CT | 3 | Rel-15 | C1 | 2017-12-15 | 2018-06-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007 | 75 | 38 |  |  | 2017-03-03 | 2017-09-08
559 | 780009 | 5G Network selection | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-12-15 | 2018-06-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 16/3/18: 0%->60; 7/6/18: 60%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2018-06-07
560 | 780010 | 5G Mobility management | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-12-15 | 2018-06-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->25; 16/3/18: 25%->70; 7/6/18: 70%->95; 10/9/18: 95%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2018-09-10
561 | 780011 | 5G Session management | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-12-15 | 2018-06-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->35; 16/3/18: 35%->85; 7/6/18: 85%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2018-06-07
562 | 780012 | 5G Non-3GPP access networks | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-12-15 | 2018-06-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->20; 16/3/18: 20%->60; 7/6/18: 60%->95; 10/9/18: 95%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2018-09-10
563 | 780013 | 5G Interworking with EPC | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-12-15 | 2018-06-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->20; 16/3/18: 20%->60; 7/6/18: 60%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2018-06-07
564 | 780014 | 5G System core network impact on services, network functions and capabilities | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-12-15 | 2018-06-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->10; 16/3/18: 10%->70; 7/6/18: 70%->90; 10/9/18: 90%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2018-09-10
565 | 780015 | 5G Network slicing | 5GS_Ph1-CT | 4 | Rel-15 | C1 | 2017-12-15 | 2018-06-14 | 100% | CP-183243 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->10; 16/3/18: 10%->60; 7/6/18: 60%->100 |  | 77 | 39 |  |  | 2017-03-03 | 2018-06-07
566 | 750027 | Study on CT3 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 | C3 | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Fernandez, Susana (Ericsson) | Susana.Fernandez at ericsson.com | 5/6/17: 0%->20; 15/12/17: 20%->95; 22/3/18: 95%->100 | 29.213; 29.214; 29.219; 29.122 | 75 | 38 |  |  | 2017-03-03 | 2018-03-22
567 | 790044 | CT3 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 | C3 | 2017-12-15 | 2018-06-14 | 100% | CP-183243 |  | Fernandez, Susana (Ericsson) | Susana.Fernandez at ericsson.com | 5/6/17: 0%->20; 15/12/17: 20%->95; 7/6/18: 35%->70; 7/6/18: 70%->100 | 29.213; 29.214; 29.219; 29.122 | 75 | 38 |  |  | 2017-03-03 | 2018-06-07
568 | 750028 | CT4 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 | C4 | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Landais, Bruno (Nokia) | Bruno.Landais at nokia.com | 5/6/17: 0%->5; 11/9/17: 5%->25; 15/12/17: 25%->45; 16/3/18: 45%->50; 7/6/18: 50%->95; 10/9/18: 95%->99; 10/12/18: 99%->100 | 23.003; 23.008; 23.380; 29.281; 29.272; 29.274; 29.303 | 75 | 38 |  |  | 2017-03-03 | 2018-12-10
569 | 750029 | Study on CT6 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 | C6 | 2017-03-03 | 2017-12-14 | 100% | CP-183243 |  | Amandeep Virk from Qualcomm |  | 5/6/17: 0%->10; 11/9/17: 10%->60; 15/12/17: 60%->85; 22/3/18: 85%->95; 7/6/18: 95%->100 |  | 75 | 38 |  |  | 2017-03-03 | 2018-06-07
570 | 790043 | CT6 aspects of 5G System - Phase 1 | 5GS_Ph1-CT | 3 | Rel-15 | C6 | 2018-03-16 | 2018-06-14 | 100% | CP-183243 |  | Landais, Bruno (Nokia) | Bruno.Landais at nokia.com | 5/6/17: 0%->5; 11/9/17: 5%->25; 15/12/17: 25%->45; 16/3/18: 45%->50; 16/3/18: 0%->20; 7/6/18: 20%->90; 10/9/18: 90%->95. 10/9/18: 95->100 as per CT81 discussions; 10/12/18: 100%->95; 11/12/18: 95%->100 | 23.003; 23.008; 23.380; 29.281; 29.272; 29.274; 29.303 | 75 | 38 |  |  | 2017-03-03 | 2018-12-11
571 | 800081 | UE Conformance Test Aspects – 5G System Non-3GPP Access | 5GS_Ph1-CT_n3GPPA-UEConTest | 2 | Rel-15 | R5 | 2018-06-15 | 2019-03-15 | 0% | RP-181032 |  | Motorola |  | tested: non-3GPP Access part of REL-15 WI 5GS_Ph1-CT (note: 3GPP Access part of 5GS_Ph1-CT is already covered in REL-15 WI 5GS_NR_LTE-UEConTest); |  | 80 |  |  |  | 2018-06-27 | NA
572 | 760029 | IMS impact due to 5GS IP-CAN | 5GS_Ph1-IMSo5G | 2 | Rel-15 | ct | 2017-09-04 | 2018-06-15 | 100% | CP-180094 |  | Song Yue (China Mobile) | songyue (at) chinamobile (dot) com | 8/9/17: WID:CP-171103->CP-172033; FCD: 12/17->06/18; 19/3/18: WID:CP-172033->CP-180094 |  | 76 | 39 |  |  | 2017-06-02 | 2018-03-19
573 | 770017 | CT1 aspects of IMSo5G | 5GS_Ph1-IMSo5G | 3 | Rel-15 | C1 | 2017-09-04 | 2018-06-15 | 100% | CP-180094 |  | Song Yue, China Mobile | songyue@chinamobile.com | 14/9/17: 0%->10; 15/12/17: 10%->65; rapporteur changed; 20/3/18: 65%->75; 7/6/18: 75%->95; 10/9/18: 95%->100 | 24.229; 24.167 | 77 | 39 |  |  | 2017-03-03 | 2018-09-10
574 | 770018 | CT3 aspects of IMSo5G | 5GS_Ph1-IMSo5G | 3 | Rel-15 | C3 | 2017-09-04 | 2018-06-15 | 100% | CP-180094 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/6/18: 0%->80; 10/9/18: 80%->100 | 29.213; 29.214 | 77 | 39 |  |  | 2017-03-03 | 2018-09-10
575 | 770019 | CT4 aspects of IMSo5G | 5GS_Ph1-IMSo5G | 3 | Rel-15 | C4 | 2017-09-04 | 2018-06-15 | 100% | CP-180094 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/6/18: 0%->100 | 23.008; 29.228; 29.229; 29.328; 29.329; 23.003 | 77 | 39 |  |  | 2017-03-03 | 2018-06-07
576 | 780034 | Service Based Interface for 5G Charging | 5GS_Ph1-SBI_CH | 2 | Rel-15 | S5 | 2017-12-15 | 2018-09-14 | 100% | SP-170951 |  | Chen, Shan, Huawei | chenshan@huawei.com | 16/3/18: 0%->15; 7/6/18: 15%->55; 7/6/18: FCD:06/18->09/18; 10/9/18: 55%->100 | TS 32.240; TS 32.298 | 78 | 40 |  |  | 2017-12-15 | 2018-09-10
577 | 780035 | Data Charging in 5G System Architecture Phase 1 | 5GS_Ph1-DCH | 2 | Rel-15 | S5 | 2017-12-15 | 2018-09-14 | 100% | SP-170952 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | 16/3/18: 0%->10; 7/6/18: 10%->60; 7/6/18: FCD:06/18->09/18; 10/9/18: 60%->100 | TS 32.240 | 78 | 40 |  |  | 2017-12-15 | 2018-09-10
578 | 810028 | SMS Charging in 5G System Architecture Phase 1 | 5GS_Ph1-SMSCH | 2 | Rel-15 | S5 | 2018-09-06 | 2018-12-14 | 100% | SP-180824 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | 7/12/18: 0%->100 | 32.240; 32.274; 32.290; 32.291; 32.299; 32.298 | 81 |  |  |  | 2018-09-06 | 2018-12-07
579 | 800040 | Charging for IMS over 5G System Architecture Phase 1 | 5GS_Ph1_IMSCH | 2 | Rel-15 | S5 | 2018-05-07 | 2018-06-15 | 100% | SP-180391 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | 7/6/18: 0%->100 | 32.240; 32.260; 32.299; 32.298 | 80 |  |  |  | 2018-06-06 | 2018-06-07
580 | 800041 | UE Conformance Test Aspects - CT6 aspects of 5G System | 5GS_Ph1_UEConTest | 2 | Rel-15 | C6 | 2018-06-07 | 2019-06-14 | 5% | CP-183242 |  | Azem, Dania (COMPRION GmbH) | DAzem@comprion.com | 10/12/18: 0%->5; 10/12/18: 5%->; 10/12/18: WID:CP-181187->CP-183242 | 31.121 ; 31.124 | 80 |  |  |  | 2017-03-02 | 2018-12-10
581 | 750035 | EPC enhancements to support 5G New Radio via Dual Connectivity | EDCE5 | 1 | Rel-15 |  | 2017-03-02 | 2018-03-15 | 100% | SP-170583 |  | Chris Pudney, Vodafone Group | Chris Pudney, Vodafone Group | 9/6/17: WID:SP-170058->SP-170583 |  | 75 | 38 |  |  | 2017-03-02 | 2017-06-09
582 | 750012 | SA2 aspects of EDCE5 | EDCE5 | 2 | Rel-15 | S2 | 2017-03-02 | 2017-09-14 | 100% | SP-170583 |  | Chris Pudney, Vodafone Group |  | 7/6/17: 0%->55; 11/9/17: 55%->90; 15/12/17: 90%->100 |  | 75 | 38 |  |  | 2017-03-02 | 2017-12-15
583 | 750036 | SA3 aspects of EDCE5 | EDCE5 | 2 | Rel-15 | S3 | 2017-03-02 | 2017-09-14 | 100% | SP-170233 |  | Adrian Escott, Qualcomm Incorporated |  | 7/6/17: 0%->60; 11/9/17: 60%->70; 15/12/17: 70%->100 |  | 75 | 38 |  |  | 2017-03-02 | 2017-12-15
584 | 760001 | CT aspects of EDCE5 | EDCE5-CT | 2 | Rel-15 | ct | 2017-06-05 | 2017-12-14 | 100% | CP-173038 |  | Jesús de Gregorio, Ericsson | jesus.de.gregorio@ericsson.com | 18/12/17: WID:CP-171045->CP-173038 |  | 76 | 39 |  |  | 2017-06-05 | 2017-12-18
585 | 760068 | CT1 aspects of EDCE5 | EDCE5-CT | 3 | Rel-15 | C1 | 2017-06-05 | 2017-12-14 | 100% | CP-173038 |  | Jesús de Gregorio, Ericsson | jesus.de.gregorio@ericsson.com | 14/9/17: 0%->65; 15/12/17: 65%->100 | 24.301; 27.007 | 76 | 39 |  |  | 2017-06-05 | 2017-12-15
586 | 760069 | CT3 aspects of EDCE5 | EDCE5-CT | 3 | Rel-15 | C3 | 2017-06-05 | 2017-12-14 | 100% | CP-173038 |  | Jesús de Gregorio, Ericsson | jesus.de.gregorio@ericsson.com |  | 29.212; 29.213; 29.214; 29.215; 29.201 | 76 | 39 |  |  | 2017-06-05 | NA
587 | 760070 | CT4 aspects of EDCE5 | EDCE5-CT | 3 | Rel-15 | C4 | 2017-06-05 | 2017-12-14 | 100% | CP-173038 |  | Jesús de Gregorio, Ericsson | jesus.de.gregorio@ericsson.com | 11/9/17: 0%->50; 15/12/17: 50%->100 | 23.008; 29.272; 29.230; 29.002; 29.305; 29.274 | 76 | 39 |  |  | 2017-06-05 | 2017-12-15
588 | 760062 | Charging aspects of EDCE5: PS Charging enhancements to support 5G New Radio via Dual Connectivity | EDCE5-CH | 2 | Rel-15 | S5 | 2017-06-05 | 2018-03-15 | 100% | SP-170487 |  | Törnkvist, Robert, Ericsson | robert.tornkvist(at)ericsson.com | 15/12/17: 0%->20; 16/3/18: 20%->100 | 32.251; 32.298; 32.299 | 76 | 39 |  |  | 2017-06-05 | 2018-03-16
589 | 750067 | New Radio Access Technology | NR_newRAT | 1 | Rel-15 | R1 | 2017-03-15 | 2019-06-14 | 52% | RP-190213 |  | NTT DOCOMO |  | follow-up WI of REL-14 SI FS_NR_newRAT completed at RAN #75; 30/6/17: 38.425 added;; 14/9/17: WID:RP-170855->RP-171485; 15/12/17: added: 38.305; 38.113; 37.863-04-01; 37.863-03-01; 37.863-02-01; 38.820-04-01; 38.820-03-01; 38.820-02-01; 15/12/17: 37.32... | 38.425; 38.424; 38.423; 38.422; 38.421; 38.420; 38.305; 38.113; 37.863-04-01; 37.863-03-01; 37.863-02-01; 38.820-04-01; 38.820-03-01; 38.820-02-01; 37.324; 37.872; 37.864-11-22; 37.866-00-02 | 75 | 38 |  |  | 2017-03-21 | 2019-03-26
590 | 750167 | Core part: New Radio Access Technology | NR_newRAT-Core | 2 | Rel-15 | R1 | 2017-03-15 | 2018-12-14 | 92% | RP-190213 | RP-181466 | NTT DOCOMO |  | follow-up WI of REL-14 SI FS_NR_newRAT; 19/6/17: Compl:0%->22%19/6/17: WID: RP-170855->RP-171485; 30/6/17 & 12/6/17: impacted specs added19/9/17: Compl:22%->50%19/9/17: WID: RP-171485->RP-172115; 15/12/17: added: 38.818; 37.865-01-01; 37.834-01-01; 37.... | 37.340;37.834-01-01;37.863-05-01;37.864-41-21;37.865-01-01;38.101;38.104;38.12?;38.201/2;38.211/2;38.213to215;38.300;38.304to307;38.321to323;38.331;38.401;38.410to414;38.455;38.470to475;38.815;38.817-01-02;38.818; 38.113; 29.413; 37.864-11-22; 38.415 | 75 | 38 |  |  | 2017-03-21 | 2019-03-26
591 | 750267 | Perf. part: New Radio Access Technology | NR_newRAT-Perf | 2 | Rel-15 | R4 | 2017-03-15 | 2019-06-14 | 20% | RP-190213 |  | NTT DOCOMO |  | follow-up WI of REL-14 SI FS_NR_newRAT completed at RAN #75; 19/6/17: WID: RP-170855->RP-171485; 12/7/17: 38.133 added;; 12/7/17: 38.141 added;; 19/9/17: WID: RP-171485->RP-172115; 15/12/17: 38.101-4 added; 8/1/18: WID: RP-172115->RP-172834; 27/3/18: W... | 38.133; 38.141; 38.101-4; 38.171 | 75 | 38 |  |  | 2017-03-21 | 2019-03-26
592 | 750072 | LTE connectivity to 5G-CN | LTE_5GCN_connect | 1 | Rel-15 | R2 | 2017-03-15 | 2018-12-20 | 99% | RP-171432 |  | Huawei |  | no Perf. part; 14/9/17: WID:RP-170840->RP-171432 |  | 75 | 38 |  |  | 2017-03-21 | 2017-09-14
593 | 750172 | Core part: LTE connectivity to 5G-CN | LTE_5GCN_connect-Core | 2 | Rel-15 | R2 | 2017-03-15 | 2018-09-14 | 100% | RP-180860 | RP-180862 | Huawei |  | no Perf. Part19/6/17: Compl:0%->5%19/6/17: WID: RP-170840->RP-17143219/9/17: Compl:5%->10%; 8/1/18: Compl:10%->20%; 27/3/18: Compl:20%->30%; ; 27/6/18: Compl:30%->99%; 7/3/19: 99%->100 |  | 75 | 38 |  |  | 2017-03-21 | 2019-03-07
594 | 761205 | Perf. part: LTE connectivity to 5G-CN | LTE_5GCN_connect-Perf | 2 | Rel-15 | R4 | 2017-06-20 | 2018-12-20 | 100% | RP-180860 | RP-180862 | Huawei |  | 16/1/19: 0%->100 |  | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
595 | 760087 | UE Conformance Test Aspects - 5G system with NR and LTE | 5GS_NR_LTE-UEConTest | 1 | Rel-15 | R5 | 2017-06-15 | 2018-12-14 | 15% | RP-181206 |  | Ericsson |  | ; 19/9/17: Compl:0%->2%; 15/12/17: impacted specs add; 15/12/17: 38.508-2 added;; ; | 38.507-1; 38.533; 38.522; 38.521-1-2-3; 38.508; 38.509; 38.903; 38.905; 38.523-1-2-3; ; 38.508-2 | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
596 | 0 | Release 15 Features on V2X | - | 1 | Rel-15 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
597 | 750003 | Enhancement of 3GPP support for V2X scenarios | eV2X | 1 | Rel-15 |  | 2016-06-09 | 2017-03-22 | 100% | SP-170158 |  | Chun, SungDuck, LG Electronics | sungduck.chun@lge.com |  |  | 75 | 38 |  |  | 2017-03-02 | NA
598 | 720003 | Study on Enhancement of 3GPP support for V2X services | FS_eV2X | 2 | Rel-15 | S1 | 2016-06-09 | 2016-12-15 | 100% | SP-160370 |  | LG Electronics, SungDuck Chun | sungduck.chun@lge.com | 19/9/16: 30%->70; 6/10/16: 22.886 added; 1/12/16: 70%->95; 2/3/17: 95%->100 | 22.886 | 72 | 37 |  |  | 2016-06-09 | 2017-03-02
599 | 750002 | Stage 1 of Enhancement of 3GPP support for V2X scenarios | eV2X | 2 | Rel-15 | S1 | 2017-01-09 | 2017-03-22 | 100% | SP-170158 |  | Chun, SungDuck, LG Electronics | sungduck.chun@lge.com | 7/6/17: 90%->100 | 22.186 | 75 | 38 |  |  | 2017-03-02 | 2017-06-07
600 | 750075 | V2X new band combinations for LTE | LTE_V2X_CA_bands | 1 | Rel-15 | R4 | 2017-03-15 | 2018-06-15 | 100% | RP-170752 |  | LG Electronics |  | no Perf. part; 12/7/17: 36.787 added; | 36.787 | 75 | 38 |  |  | 2017-03-21 | 2017-07-12
601 | 750175 | Core part: V2X new band combinations for LTE | LTE_V2X_CA_bands-Core | 2 | Rel-15 | R4 | 2017-03-15 | 2018-06-15 | 100% | RP-180328 |  | LG Electronics |  | no Perf. part; 19/6/17: Compl:0%->20%; 19/9/17: Compl:20%->40%; 8/1/18: Compl:40%->50%; 27/3/18: Compl:50%->70%; |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
602 | 750062 | Enhancements on LTE-based V2X Services | LTE_eV2X | 1 | Rel-15 | R1 | 2017-03-15 | 2018-12-14 | 99% | RP-171069 |  | Huawei |  | follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #75; 14/9/17: WID:RP-170798->RP-171069 |  | 75 | 38 |  |  | 2017-03-21 | 2017-09-14
603 | 750162 | Core part: V2X phase 2 based on LTE | LTE_eV2X-Core | 2 | Rel-15 | R1 | 2017-03-15 | 2018-09-14 | 99% | RP-171740 | RP-180858 | Huawei |  | follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #75; 19/6/17: Compl:0%->15%; 30/6/17: 36.788 added;; 19/9/17: Compl:15%->30% 8/1/18: Compl:30%->55%27/3/18: Compl:55%->75% | 36.788 | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
604 | 750262 | Perf. Part: V2X phase 2 based on LTE | LTE_eV2X-Perf | 2 | Rel-15 | R4 | 2017-03-15 | 2018-12-14 | 100% | RP-182549 |  | Huawei |  | follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #7519/6/17: WID: RP-170798->RP-17106919/9/17: WID: RP-171069->RP-171740; 27/6/18: Compl:0%->5%; 16/1/19: 5%->100; 16/1/19: WID:RP-171740->RP-182549 |  | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
605 | 700045 | Study on security aspects for LTE support of V2X services | FS_V2XLTE_ARC | 1 | Rel-15 | S3 | 2015-09-07 | 2017-06-15 | 100% | SP-150852 |  | Huawei, Marcus Wong | mwong@huawei.com | 11/12/15: WID:SP-150715->SP-150743. 28/01/16: typo on name corrected, WD corrected (was SP-150743); 7/3/16: 0%->10; 19/9/16: 10%->65; 1/12/16: 65%->85; 6/3/17: 85%->90; 21/3/17: FCD shifted, moved from Rel-14; 21/3/17: FCD:09/16->06/17; 8/8/18: 90%->100 | TR 33.885 | 70 | 36 |  |  | 2015-12-07 | 2018-08-08
606 | 0 | Release 15 Features on Ultra/Highly Reliable Low Latency Communication | - | 1 | Rel-15 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
607 | 770037 | EPC support for E-UTRAN Ultra Reliable Low Latency Communication | EPS_URLLC | 1 | Rel-15 | S2 | 2017-09-08 | 2018-03-15 | 100% | SP-170811 |  | Chris PUDNEY | chris dot pudney at vodafone dot com | 15/12/17: WID:SP-170797->SP-170811; 15/12/17: 0%->15; 20/3/18: 15%->100 | 23.401; 23.214; 23.203 | 77 | 39 |  |  | 2017-09-08 | 2018-03-20
608 | 750061 | Highly Reliable Low Latency Communication for LTE | LTE_HRLLC | 1 | Rel-15 | R1 | 2017-03-15 | 2018-12-15 | 46% | RP-171489 |  | Ericsson |  | 14/9/17: WID:RP-170796->RP-171489 |  | 75 | 38 |  |  | 2017-03-21 | 2017-09-14
609 | 750161 | Core part: Highly Reliable Low Latency Communication for LTE | LTE_HRLLC-Core | 2 | Rel-15 | R1 | 2017-03-15 | 2018-09-14 | 99% | RP-181259 | RP-180693 | Ericsson |  | ; 19/6/17: WID: RP-170796->RP-171489; 8/1/18: Compl:0%->10%; 8/1/18: WID: RP-171489->RP-172845; 27/3/18: Compl:10%->30%; 27/6/18: Compl:30%->99%; 27/6/18: CD:Fri 15 |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
610 | 750261 | Perf. part: Highly Reliable Low Latency Communication for LTE | LTE_HRLLC-Perf | 2 | Rel-15 | R4 | 2017-03-15 | 2018-12-15 | 0% | RP-181259 |  | Ericsson |  | ; 19/6/17: WID: RP-170796->RP-171489; 8/1/18: WID: RP-171489->RP-172845; 27/6/18: WID: RP-172845->RP-181259 |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
611 | 0 | Release 15 Features on improvements of Mission Critical (MC) | - | 1 | Rel-15 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
612 | 720057 | Study on MC system migration and interconnect between MCPTT systems | FS_MCSMI | 1 | Rel-15 | S6 | 2016-06-13 | 2017-06-12 | 100% | SP-160880 |  | Chater-Lea, David |  | 28/7/16: 23.781 added; 19/9/16: WID:SP-160340->SP-160526; FCD: 09/16->12/16; 19/9/16: 0%->40; 1/12/16: WID:SP-160526->SP-160880; 1/12/16: 40%->48; 9/12/16: FCD:12/16->06/17, Rel-14->Rel-15; 3/3/17: 48%->60; 7/6/17: 60%->100 | New TR 23.781 | 72 | 37 |  |  | 2016-09-16 | 2017-06-07
613 | 720058 | Study on MC Communication Interworking between LTE and non-LTE Systems | FS_MCCI | 1 | Rel-15 | S6 | 2016-06-13 | 2017-06-12 | 100% | SP-160881 |  | Monnes, Peter (Harris Corp.) |  | 28/7/16: 23.782 added; 19/9/16: WID:SP-160341->SP-160527; 19/9/16: 0%->20; 1/12/16: WID:SP-160527->SP-160881; 1/12/16: 20%->22; 9/12/16: FCD:12/16->06/17, Rel-14->Rel-15; 3/3/17: 22%->50; 7/6/17: 50%->90; 11/9/17: 90%->100 | New TR 23.782 | 72 | 37 |  |  | 2016-06-13 | 2017-09-11
614 | 720083 | Study on MC Security Enhancements | FS_MC_Sec | 1 | Rel-15 | S3 | 2016-06-17 | 2018-03-15 | 100% | SP-170416 |  | Haigh, Peter, CESG | peter.haigh@cesg.gsi.gov.uk | 28/7/16: 33.280 added; 28/7/16: 39.880 added; 19/9/16: WID:SP-160374->SP-160567. FCD: 12/16->03/17; 1/12/16: 0%->35; 6/3/17: FCD:03/17->06/17; 6/3/17: 35%->60; 7/6/17: FCD:06/17->12/17 (Rel-14->Rel-15);60%->65; 8/6/17: WID:SP-160567->SP-170416; 11/9/17 | TR 33.xxx; 33.280; 39.880 | 72 | 37 |  |  | 2016-06-17 | 2018-03-16
615 | 760050 | MC Communication Interworking between LTE and non-LTE Systems (Stage 3 in Rel16) | MCCI | 1 | Rel-15 | S6 | 2017-06-05 | 2017-12-14 | 100% | SP-170578 |  | Monnes, Peter, Harris Corporation | pmonnes at harris dot com | 11/9/17: 0%->40; 15/12/17: 40%->87; 16/3/18: 87%->100. 10/9/18: moved from Rel-15 since too late for St 3 in Rel-15 as said in CT81. 12/9/18: moved back to Rel-15, while St.3 will be Rel-16 | New TS 23.283; TS 23.280; TS 23.379; TS 23.282 | 76 | 39 |  |  | 2017-06-03 | 2018-03-16
616 | 780002 | Removal of 'over LTE' limitation from Mission Critical Specifications | MCOver | 1 | Rel-15 | S1 | 2017-11-15 | 2017-12-15 | 100% | SP-180354 |  | Kees Verweij ;The Police of the Netherlands | KeesdotVerweijatPolitiedotNL | 7/6/18: WID:SP-170986->SP-180354 | 22.179; 22.280; 22.281; 22.282; 22.468 | 78 | 40 |  |  | 2017-12-15 | 2018-06-07
617 | 750021 | Enhancements to MCPTT functional architecture and information flows | enhMCPTT | 1 | Rel-15 |  | 2017-03-03 | 2018-06-15 | 100% | SP-170248 |  | Dom Lazara, Motorola Solutions | dom.lazara@motorolasolutions.com | 21/3/17: impacted TS/TR added; 7/6/17: 0%->25 | TS 23.280 + TS 23.379 | 75 | 38 |  |  | 2017-03-03 | 2017-06-07
618 | 770008 | Stage 2 of enhMCPTT | enhMCPTT | 2 | Rel-15 | S6 | 2017-03-03 | 2017-12-14 | 100% | SP-170248 |  | Dom Lazara, Motorola Solutions | dom.lazara@motorolasolutions.com | 21/3/17: impacted TS/TR added; 7/6/17: 0%->25; 11/9/17: 25%->45; 15/12/17: 45%->100 | TS 23.280 + TS 23.379 | 75 | 38 |  |  | 2017-03-03 | 2017-12-15
619 | 770009 | Stage 3 of enhMCPTT | enhMCPTT-CT | 2 | Rel-15 | C1 | 2017-09-08 | 2018-06-15 | 100% | CP-172030 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com | 15/12/17: 0%->10; 7/6/18: 10%->20; 10/9/18: 20%->80; 7/12/18: 80%->85; 10/12/18: 85%->100 | 24.379; 24.380; 24.481; 24.482; 24.483; 24.484 | 77 | 39 |  |  | 2017-03-03 | 2018-12-10
620 | 750022 | Enhancements to MC Data Functional architecture and information flows | eMCData | 1 | Rel-15 |  | 2017-03-03 | 2018-06-15 | 100% | SP-170462 |  | David Freeman, Home Office | david@dnf-consulting.co.uk | 21/3/17: impacted TS/TR added; 7/6/17: 0%->10; 8/6/17: WID:SP-170249->SP-170462 | 23.280 + TS 23.282 | 75 | 38 |  |  | 2017-03-03 | 2017-06-08
621 | 770010 | Stage 2 of eMCData | eMCData | 2 | Rel-15 | S6 | 2017-03-03 | 2017-12-14 | 100% | SP-170462 |  | David Freeman, Home Office | david@dnf-consulting.co.uk | 21/3/17: impacted TS/TR added; 7/6/17: 0%->10; 8/6/17: WID:SP-170249->SP-170462; 11/9/17: 10%->15; 15/12/17: 15%->100 | 23.280 + TS 23.282 | 75 | 38 |  |  | 2017-03-03 | 2017-12-15
622 | 770011 | Stage 3 of eMCData | eMCData-CT | 2 | Rel-15 | C1 | 2017-09-08 | 2018-06-15 | 100% | CP-172146 |  | HASON, Baruh | Baruh.Hason@motorolasolutions.com | 20/3/18: 0%->30; 7/6/18: 30%->85; 10/12/18: 85%->100 | 24.282; 24.582; 24.481; 24.483; 24.484 | 77 | 39 |  |  | 2017-03-03 | 2018-12-10
623 | 760048 | Enhancements to MC Video Functional architecture and information flows | eMCVideo | 1 | Rel-15 |  | 2017-06-05 | 2018-06-15 | 100% | SP-170401 |  | Niranth Amogh, Huawei Telecommunications (India | namogh@huawei.com | 7/6/17: 0%->10 | 23.280; 23.281 | 76 | 39 |  |  | 2017-06-03 | 2017-06-07
624 | 770012 | Stage 2 of eMCVideo | eMCVideo | 2 | Rel-15 | S6 | 2017-06-05 | 2017-12-14 | 100% | SP-170401 |  | Niranth Amogh, Huawei Telecommunications (India | namogh@huawei.com | 7/6/17: 0%->10; 11/9/17: 10%->60; 15/12/17: 60%->100 | 23.280; 23.281 | 76 | 39 |  |  | 2017-06-03 | 2017-12-15
625 | 770013 | Stage 3 of eMCVideo | eMCVideo-CT | 2 | Rel-15 | ct | 2017-09-08 | 2018-06-15 | 100% | CP-181084 |  | WEI, Haitao | weihaitao@huawei.com | 7/6/18: WID:CP-172032->CP-181084 |  | 77 | 39 |  |  | 2017-06-03 | 2018-06-07
626 | 770014 | CT1 aspects of eMCVideo | eMCVideo-CT | 3 | Rel-15 | C1 | 2017-09-08 | 2018-06-15 | 100% | CP-181084 |  | WEI, Haitao | weihaitao@huawei.com | 20/3/18: 0%->25; 7/6/18: 25%->100; 12/6/18: 100%->99; 10/9/18: 99%->100 | 24.281; 24.581; 24.481; 24.483; 24.484 | 77 | 39 |  |  | 2017-06-03 | 2018-09-10
627 | 770015 | CT3 aspects of eMCVideo | eMCVideo-CT | 3 | Rel-15 | C3 | 2017-12-05 | 2018-06-15 | 100% | CP-181084 |  | WEI, Haitao | weihaitao@huawei.com | 10/9/18: 0%->100 | 29.165; 29.213; 29.214 | 77 | 39 |  |  | 2017-06-03 | 2018-09-10
628 | 770016 | CT6 aspects of eMCVideo | eMCVideo-CT | 3 | Rel-15 | C6 | 2017-12-05 | 2018-06-15 | 100% | CP-181084 |  | WEI, Haitao | weihaitao@huawei.com | 10/9/18: 0%->100 | 31.102; 31.103 | 77 | 39 |  |  | 2017-06-03 | 2018-09-10
629 | 760067 | MC Security Enhancements | eMCSec | 1 | Rel-15 | S3 | 2017-06-05 | 2018-06-15 | 100% | SP-170415 |  | Haigh, Peter, NCSC |  | 15/12/17: 0%->80; 15/12/17: FCD:12/17->03/18; 21/12/17: FCD:03/18->05/18. Exception in SP-171056; 16/3/18: 80%->90; 16/3/18: FCD:05/18->06/18; 7/6/18: 90%->100 | 33.18 | 76 | 39 |  |  | 2017-06-07 | 2018-06-07
630 | 750023 | MBMS usage for MC communication services | MBMS_Mcservices | 1 | Rel-15 | S6 | 2017-03-03 | 2018-06-07 | 100% | SP-170686 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com | 21/3/17: impacted TS/TR added; 7/6/17: 0%->45; 8/9/17: WID:SP-170075->SP-170686; 8/9/17: FCD:09/17->12/17; 11/9/17: 45%->70; 15/12/17: 70%->95; 16/3/18: 95%->100. Problem with % complete when set as Parent Feature. Has to be left as independent item… | TS 23.280 + TS 23.281 + TS 23.282 + TS 23.379 | 75 | 38 |  |  | 2017-03-03 | 2018-03-16
631 | 800043 | Stage 2 for MBMS_Mcservices | MBMS_Mcservices | 1 | Rel-15 | S6 | 2017-03-03 | 2017-12-15 | 100% | SP-170686 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com | 21/3/17: impacted TS/TR added; 7/6/17: 0%->45; 8/9/17: WID:SP-170075->SP-170686; 8/9/17: FCD:09/17->12/17; 11/9/17: 45%->70; 15/12/17: 70%->95; 16/3/18: 95%->100 | TS 23.280 + TS 23.281 + TS 23.282 + TS 23.379 | 75 | 38 |  |  | 2017-03-03 | 2018-03-16
632 | 800017 | Stage 3 for MBMS_Mcservices | MBMS_Mcservices_ | 1 | Rel-15 | C1 | 2018-04-09 | 2018-06-07 | 100% | CP-183105 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com | 12/6/18: 10%->30; 10/9/18: 30%->70; 7/12/18: 70%->100 | 24.281; 24.282; 24.379; 24.380; 24.581; 24.380 | 80 | 41 |  |  | 2018-06-06 | 2018-12-10
633 | 760049 | MC system migration and interconnection | MCSMI | 1 | Rel-15 | S6 | 2017-06-05 | 2017-12-14 | 100% | SP-170577 |  | Chater-Lea, David; Motorola Solutions | david.chater-lea@motorolasolutions.com | 12/7/17: WID:SP-170402->SP-170577; 11/9/17: 0%->20; 15/12/17: 20%->80; 16/3/18: 80%->100 | TS 23.280; TS 23.379; TS 23.281; TS 23.282; 24.885 | 76 | 39 |  |  | 2017-06-03 | 2018-03-16
634 | 770007 | Protocol enhancements for Mission Critical Services | MCProtoc15 | 1 | Rel-15 | C1 | 2017-09-08 | 2018-06-15 | 100% | CP-172145 |  | Jörgen Axell |  | 14/9/17: 0%->15; 15/12/17: 15%->40; 20/3/18: 40%->70; 7/6/18: 70%->100 |  | 77 | 39 |  |  | 2017-09-08 | 2018-06-07
635 | 0 | Release 15 Features on MTC-IoT | - | 1 | Rel-15 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
636 | 730050 | Battery Efficient Security for very low Throughput MTC Devices | BEST_MTC_Sec | 1 | Rel-15 | S3 | 2016-09-19 | 2018-03-15 | 100% | SP-160569 |  | Evans, Tim, VODAFONE Group Plc. |  | 6/10/16: 33.163 added 6/3/17: FCD:12/16->09/17; 6/3/17: 0%->20. Moved from Rel-14.; 7/6/17: 20%->95; 15/12/17: FCD:09/17->03/18; 16/3/18: 95%->100 | 33.401, 43.020, 33.220; 33.163 | 73 | 37 |  |  | 2016-09-19 | 2018-03-16
637 | 780016 | AT Commands for CIoT-Ext | AT_CIoT-Ext | 1 | Rel-15 | C1 | 2017-12-15 | 2018-06-14 | 100% | CP-173083 |  | Bakker, John-Luc (Blackberry) | jbakker@blackberry.com | 20/3/18: 0%->20; 7/6/18: 20%->100 | 27.007 | 78 | 40 |  |  | 2017-12-15 | 2018-06-07
638 | 750059 | Even further enhanced MTC for LTE | LTE_eMTC4 | 1 | Rel-15 | R1 | 2017-03-15 | 2018-12-14 | 100% | RP-171427 |  | Ericsson |  | WI LTE_feMTC-Core got a 3 months exception granted by RAN #75 to complete in REL-14; note: RAN #75 approved WID RP-170732 with working agreement; 14/9/17: WID:RP-170732->RP-171427 |  | 75 | 38 |  |  | 2017-03-21 | 2017-09-14
639 | 750159 | Core part: Even further enhanced MTC for LTE | LTE_eMTC4-Core | 2 | Rel-15 | R1 | 2017-03-15 | 2018-09-14 | 100% | RP-172811 | RP-181213 | Ericsson |  | WI LTE_feMTC-Core got a 3 months exception granted by RAN #75 to complete in REL-14; note: RAN #75 approved WID RP-170732 with working agreement; 19/6/17: Compl:0%- 19/9/ 8/1 2 ;; 16/1/19: 97%->100 |  | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
640 | 750259 | Perf. part: Even further enhanced MTC for LTE | LTE_eMTC4-Perf | 2 | Rel-15 | R4 | 2017-03-15 | 2018-12-14 | 100% | RP-172811 |  | Ericsson |  | note: RAN #75 approved WID RP-170732 with working agreement19/6/17: WID: RP-170732->RP-171427; 8/1/18: WID: RP-171427->RP-172811; 27/6/18: Compl:0%->50%; 16/1/19: 50%->100 |  | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
641 | 750066 | Further NB-IoT enhancements | NB_IOTenh2 | 1 | Rel-15 | R1 | 2017-03-15 | 2018-12-14 | 98% | RP-182389 |  | Huawei |  | follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76; note: RAN #75 approved WID RP-170852 with working agreement; 14/9/17: WID:RP-170852->RP-171428 |  | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
642 | 750166 | Core part: Further NB-IoT enhancements | NB_IOTenh2-Core | 2 | Rel-15 | R1 | 2017-03-15 | 2018-09-14 | 95% | RP-182389 | RP-180851 | Huawei |  | follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76; note: RAN #75 approved WID RP-170852 with working agreement;1 8/1/12 ; |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
643 | 750266 | Perf. part: Further NB-IoT enhancements | NB_IOTenh2-Perf | 2 | Rel-15 | R4 | 2017-03-15 | 2018-12-14 | 100% | RP-182389 |  | Huawei |  | follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76; note: RAN #75 approved WID RP-170852 with working agreement; 8/1 ;; 26/3/19: 30%->100 |  | 75 | 38 |  |  | 2017-03-21 | 2019-03-26
644 | 0 | Release 15 Features related to WLAN | - | 1 | Rel-15 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
645 | 750010 | Inclusion of WLAN direct discovery technologies as an alternative for ProSe direct discovery | ProSe_WLAN_DD | 1 | Rel-15 |  | 2016-11-15 | 2018-03-15 | 100% | SP-160957 |  | Intel Corporation; Ana Lucia Pinheiro | ana.lucia.a.pinheiro@intel.com | 1/12/16: 0%->100 | 22.278 | 74 | 38 |  |  | 2016-12-01 | 2016-12-01
646 | 740003 | Stage 1 of ProSe_WLAN_DD | ProSe_WLAN_DD | 2 | Rel-15 | S1 | 2016-11-15 | 2016-12-15 | 100% | SP-160957 |  | Intel Corporation; Ana Lucia Pinheiro | ana.lucia.a.pinheiro@intel.com | 1/12/16: 0%->100 | 22.278 | 74 | 38 |  |  | 2016-12-01 | 2016-12-01
647 | 750011 | Stage 2 of ProSe_WLAN_DD | ProSe_WLAN_DD_Stage2 | 2 | Rel-15 | S2 | 2017-03-02 | 2017-06-15 | 100% | SP-170057 |  | Intel, Sašo Stojanovski | saso.stojanovski@intel.com | 6/3/17: 0%->55; 7/6/17: 55%->100 |  | 75 | 38 |  |  | 2017-03-02 | 2017-06-07
648 | 760026 | Stage 3 of ProSe_WLAN_DD | ProSe_WLAN_DD_Stage3 | 2 | Rel-15 | ct | 2017-06-02 | 2017-12-06 | 100% | CP-173084 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 18/12/17: WID:CP-171102->CP-173084 |  | 76 | 39 |  |  | 2017-06-02 | 2017-12-18
649 | 760027 | CT1 aspects of ProSe_WLAN_DD | ProSe_WLAN_DD_Stage3 | 3 | Rel-15 | C1 | 2017-06-02 | 2017-12-06 | 100% | CP-173084 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 14/9/17: 0%->60; 15/12/17: 60%->100 | 24.334 | 76 | 39 |  |  | 2017-06-02 | 2017-12-15
650 | 760028 | CT4 aspects of ProSe_WLAN_DD | ProSe_WLAN_DD_Stage3 | 3 | Rel-15 | C4 | 2017-06-02 | 2017-12-06 | 100% | CP-173084 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 15/12/17: 0%->100 | 29.345; 29.230; 23.008 | 76 | 39 |  |  | 2017-06-02 | 2017-12-15
651 | 780045 | Charging of ProSe_WLAN_DD | ProSe_WLAN_DD-CH | 2 | Rel-15 | S5 | 2017-12-15 | 2018-03-15 | 100% | SP-170947 |  | Yizhi Yao, Intel Corporation | yizhi.yao@intel.com | 15/12/17: 0%->40; 16/3/18: 40%->100 | 32.277; 32.298; 32.299 | 74 | 38 |  |  | 2016-12-01 | 2018-03-16
652 | 760020 | Complementary Features for Voice services over WLAN | VoWLAN | 1 | Rel-15 |  | 2016-06-13 | 2018-06-14 | 100% | SP-170378 | [5 empty] | 76 | 39 |  |  | 2017-06-02 | NA
653 | 720082 | Study on Complementary Features for Voice services over WLAN | FS_VoWLAN | 2 | Rel-15 | S2 | 2016-06-13 | 2017-03-15 | 100% | SP-160506 |  | Nokia (Nicolas Drevon | nicolas.drevon@nokia.com | 28/7/16: 23.751 added; 19/9/16: 0%->10., 7/12/16: moved from Rel-14, according to SP-160806; 6/3/17: 10%->80; 7/6/17: 80%->100 | 23.751 | 72 | 37 |  |  | 2016-06-17 | 2017-06-07
654 | 760021 | Stage 2 of VoWLAN | VoWLAN | 2 | Rel-15 | S2 | 2017-05-09 | 2017-06-08 | 100% | SP-170378 |  | Drevon Nicolas, Nokia | nicolas.drevon@nokia.com | 15/12/17: 0%->100 | 23.402 | 76 | 39 |  |  | 2017-06-02 | 2017-12-15
655 | 760022 | CT aspects of VoWLAN | VoWLAN-CT | 2 | Rel-15 | ct | 2017-06-02 | 2018-06-14 | 100% | CP-181083 |  | Jennifer Liu (Nokia) | Jennifer.Liu at nokia.com | 7/6/18: WID:CP-171101->CP-181083 |  | 76 | 39 |  |  | 2017-06-02 | 2018-06-07
656 | 760023 | CT1 aspects of VoWLAN | VoWLAN-CT | 3 | Rel-15 | C1 | 2017-06-02 | 2018-06-14 | 100% | CP-181083 |  | Jennifer Liu (Nokia) | Jennifer.Liu at nokia.com | 14/9/17: 0%->70; 15/12/17: 70%->100 | 24.302 ; 24.312 ; 24.244 | 76 | 39 |  |  | 2017-06-02 | 2017-12-15
657 | 760024 | CT4 aspects of VoWLAN | VoWLAN-CT | 3 | Rel-15 | C4 | 2017-06-02 | 2018-06-14 | 100% | CP-181083 |  | Jennifer Liu (Nokia) | Jennifer.Liu at nokia.com | 7/6/18: 0%->100 | 29.274 | 76 | 39 |  |  | 2017-06-02 | 2018-06-07
658 | 760025 | CT6 aspects of VoWLAN | VoWLAN-CT | 3 | Rel-15 | C6 | 2017-06-02 | 2018-06-14 | 100% | CP-181083 |  | Jennifer Liu (Nokia) | Jennifer.Liu at nokia.com | 7/6/18: 0%->100 | 31.102 | 76 | 39 |  |  | 2017-06-02 | 2018-06-07
659 | 0 | Release 15 Features on Virtual Reality (VR) | - | 1 | Rel-15 |  | 2016-03-01 | 2016-03-01 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
660 | 710014 | Study on Virtual Reality | FS_VR | 1 | Rel-15 | S4 | 2016-03-01 | 2017-09-12 | 100% | SP-160084 |  | Gilles TENIOU, Orange | gilles.teniou@orange.com | 11/6/16: 0%->10; 19/9/16: 10%->40, FCD: 12/16->03/17; 1/12/16: FCD:03/17->06/17; 1/12/16: 40%->35; 14/12/16: 35%->45; 14/12/16: FCD:06/17->09/17; 6/3/17: 45%->55; 7/6/17: 55%->70; 11/9/17: 70%->100 | TR 26.918 | 71 | 36 |  |  | 2016-03-01 | 2017-09-11
661 | 770030 | Study on 3GPP codecs for VR audio | FS_CODVRA | 1 | Rel-15 | S4 | 2017-09-08 | 2017-12-15 | 100% | SP-170617 |  | Toftgård, Tomas, Ericsson | tomas.toftgard@ericsson.com | 15/12/17: 0%->100; 15/12/17: FCD:09/17->12/17 | 26.918 | 77 | 39 |  |  | 2017-09-08 | 2017-12-15
662 | 770022 | Test Methodologies for the Evaluation of Perceived Listening Quality in Immersive Audio Systems | LiQuImAS | 1 | Rel-15 | S4 | 2017-09-08 | 2018-09-14 | 100% | SP-170609 |  | Schevciw, Andre – Qualcomm Incorporated | aschevci@qti.qualcomm.com | 15/12/17: added: 26.861; 26.261; 26.260; 26.259; 15/12/17: 0%->15; 16/3/18: 15%->20; 7/6/18: 20%->35; 7/6/18: FCD:06/18->09/18; 10/9/18: 35%->100 | New; 26.861; 26.261; 26.260; 26.259 | 77 | 39 |  |  | 2017-09-08 | 2018-09-10
663 | 770023 | Addition of HDR to TV Video Profiles | HDR | 1 | Rel-15 | S4 | 2017-09-08 | 2017-12-15 | 100% | SP-170610 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 15/12/17: 0%->100 | TS 26.116; TS 26.346; TS 26.234; TS 26.247; TS 26.244 | 77 | 39 |  |  | 2017-09-08 | 2017-12-15
664 | 770025 | Virtual Reality Profiles for Streaming Media | VRStream | 1 | Rel-15 | S4 | 2017-09-08 | 2018-09-14 | 100% | SP-180893 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 15/12/17: 26.118 added;; 15/12/17: 0%->25; 16/3/18: 25%->40; 7/6/18: 40%->60; 7/6/18: FCD:06/18->09/18; 10/9/18: 60%->100; 2/10/18: WID:SP-170612->SP-180893 | 26.118; 26.818; 26.247; 26.346; 26.234 | 77 | 39 |  |  | 2017-09-08 | 2018-10-02
665 | 0 | Release 15 other Features | - | 1 | Rel-15 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
666 | 790016 | Forward compatibility for 3GPP Diameter Charging Applications | FWDCA | 1 | Rel-15 | S5 | 2018-03-15 | 2018-06-15 | 100% | SP-180076 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | 7/6/18: 0%->100 | 32.251; 32.277; 32.299 | 79 | 40 |  |  | 2018-03-15 | 2018-06-07
667 | 790017 | Diameter Overload Control Mechanisms for Charging | DOCME_CH | 1 | Rel-15 | S5 | 2018-03-15 | 2018-09-14 | 100% | SP-180077 |  | Törnkvist, Robert, Ericsson | robert(dot)tornkvist(at)Ericsson(dot)com | 7/6/18: 0%->10; 7/6/18: FCD:06/18->09/18; 10/9/18: 10%->100 | 32.299 | 79 | 40 |  |  | 2018-03-15 | 2018-09-10
668 | 790018 | Charging aspects of WLAN access in EPC | WAEPC_CH | 1 | Rel-15 | S5 | 2018-03-15 | 2018-06-15 | 100% | SP-180078 |  | Gardella, Maryse, Nokia | maryse.gardella@nokia.com | 7/6/18: 0%->100 | 32.251; 32.260; 32.299; 32.298 | 79 | 40 |  |  | 2018-03-15 | 2018-06-07
669 | 790020 | FEC and ROHC Activation for GCSE over MBMS | FRASE | 1 | Rel-15 | S4 | 2018-03-15 | 2018-09-14 | 100% | SP-180206 |  | Bouazizi, Imed, Samsung Electronics Co., Ltd | i.bouazizi@samsung.com. | 7/6/18: 0%->30; 7/6/18: FCD:06/18->09/18; 10/9/18: 30%->100 | 26.346, new | 79 | 40 |  |  | 2018-03-15 | 2018-09-10
670 | 790021 | Media Handling Aspects of 5G Conversational Services | 5G_MTSI_Codecs | 1 | Rel-15 | S4 | 2018-03-15 | 2018-09-14 | 100% | SP-180650 |  | Oyman, Ozgur, Company: Intel | ozgur.oyman@intel.com | 7/6/18: 0%->60; 7/6/18: FCD:06/18->09/18; 10/9/18: 60%->100; 2/10/18: WID:SP-180033->SP-180650 | 26.114; 26.223 | 79 | 40 |  |  | 2018-03-15 | 2018-10-02
671 | 790025 | SRVCC for terminating call in pre-alerting phase | bSRVCC_MT | 1 | Rel-15 |  | 2018-03-15 | 2018-06-14 | 100% | CP-180153 |  | Song Yue (China Mobile) | songyue (at) chinamobile (dot) com |  |  | 79 | 40 |  |  | 2018-03-16 | NA
672 | 790026 | CT1 aspects of bSRVCC_MT | bSRVCC_MT | 2 | Rel-15 | C1 | 2018-03-15 | 2018-06-14 | 100% | CP-180153 |  | Song Yue (China Mobile) | songyue (at) chinamobile (dot) com | 16/3/18: 0%->80; 7/6/18: 80%->100 | 24.237; 24.008 | 79 | 40 |  |  | 2018-03-16 | 2018-06-07
673 | 790027 | CT3 aspects of bSRVCC_MT | bSRVCC_MT | 2 | Rel-15 | C3 | 2018-03-15 | 2018-06-14 | 100% | CP-180153 |  | Song Yue (China Mobile) | songyue (at) chinamobile (dot) com | 22/3/18: 0%->95; 10/9/18: 95%->100 | 29.165 | 79 | 40 |  |  | 2018-03-16 | 2018-09-10
674 | 790035 | Increasing the number of EPS bearers | INOBEAR | 1 | Rel-15 |  | 2018-03-16 | 2018-06-15 | 100% | SP-171044 |  | Andy.Bennett, Samsung | a <dot> bennett <at> Samsung.com |  | 23.401; 23.167 | 78 | 40 |  |  | 2017-12-15 | NA
675 | 780027 | Stage 2 of INOBEAR | INOBEAR | 2 | Rel-15 | S2 | 2018-03-16 | 2018-06-15 | 100% | SP-171044 |  | Andy.Bennett, Samsung | a <dot> bennett <at> Samsung.com |  | 23.401; 23.167 | 78 | 40 |  |  | 2017-12-15 | NA
676 | 790036 | Stage 3 of INOBEAR | INOBEAR-CT | 2 | Rel-15 | ct | 2018-03-16 | 2018-06-15 | 100% | CP-180098 |  | Samsung, Lalith Kumar | lalith.kumar@samsung.com |  |  | 79 | 40 |  |  | 2017-12-15 | NA
677 | 790037 | CT1 aspects of INOBEAR | INOBEAR-CT | 3 | Rel-15 | C1 | 2018-03-16 | 2018-06-15 | 100% | CP-180098 |  | Samsung, Lalith Kumar | lalith.kumar@samsung.com | 7/6/18: 0%->100 | 24.301; 24.007 | 79 | 40 |  |  | 2017-12-15 | 2018-06-07
678 | 790038 | CT4 aspects of INOBEAR | INOBEAR-CT | 3 | Rel-15 | C4 | 2018-03-16 | 2018-06-15 | 100% | CP-180098 |  | Samsung, Lalith Kumar | lalith.kumar@samsung.com | 7/6/18: 0%->100 | 29.274 | 79 | 40 |  |  | 2017-12-15 | 2018-06-07
679 | 780070 | Increased number of E-UTRAN data bearers | INOBEARRAN | 1 | Rel-15 | R2 | 2017-12-15 | 2018-09-14 | 99% | RP-172835 |  | Samsung |  |  |  | 78 | 40 |  |  | 2018-01-08 | 2018-01-08
680 | 780170 | Core part: Increased number of E-UTRAN data bearers | INOBEARRAN-Core | 2 | Rel-15 | R2 | 2017-12-15 | 2018-09-14 | 99% | RP-180569 |  | Samsung |  | 27/3/18: WID: RP-172835->RP-180569; 27/6/18: Compl:0%->99%; 27/6/18: |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
681 | 780019 | Remote UE access via relay UE | REAR | 1 | Rel-15 |  | 2016-03-01 | 2018-06-15 | 100% | SP-160511 |  | Huawei, Laurence Meriau | laurence.meriau@huawei.com | Previously known as "wearable devices"; 9/6/16: 0%->100; 9/6/16: WID:SP-160231->SP-160371 | 22.278, 22.115 | 71 | 36 |  |  | 2016-03-11 | 2016-06-09
682 | 740007 | Study on architecture enhancements to ProSe UE-to-Network Relay | FS_REAR | 2 | Rel-15 | S2 | 2016-12-01 | 2017-09-14 | 100% | SP-160961 |  | Dario Serafino Tonesi, Huawei | dario.tonesi@huawei.com | 1/12/16: 0%->5. Study on Stage 2 for REAR. When normative work completed, Stage 1 and Stage 2 shall be in the same release; 6/3/17: 5%->30; 7/6/17: 30%->60; 11/9/17: 60%->95; 15/12/17: 95%->100 | 23.733 | 74 | 38 |  |  | 2016-12-01 | 2017-12-15
683 | 750017 | Study on security aspects of enhancements to ProSe UE-to-Network Relay | FS_REAR_Sec | 2 | Rel-15 | S3 | 2017-03-02 | 2018-06-15 | 100% | SP-170270 |  |  | lihe2@huawei.com | 7/6/17: 0%->15; 11/9/17: 15%->50; 15/12/17: 50%->79; 16/3/18: 79%->99; 16/3/18: FCD:03/18->06/18; 7/6/18: 99%->100 |  | 75 | 38 |  |  | 2017-03-02 | 2018-06-07
684 | 710047 | Stage 1 for REAR | REAR | 2 | Rel-15 | S1 | 2016-03-01 | 2016-06-15 | 100% | SP-160511 |  | Huawei, Laurence Meriau | laurence.meriau@huawei.com | Previously known as "wearable devices"; 9/6/16: 0%->100; 9/6/16: WID:SP-160231->SP-160371; 15/12/17: moved Rel-14->Rel-15 | 22.278, 22.115 | 71 | 36 |  |  | 2016-03-11 | 2017-12-15
685 | 780046 | Enhanced VoLTE performance | eVoLP | 1 | Rel-15 |  | 2016-12-01 | 2018-06-15 | 100% | [6 empty] | 78 | 40 |  |  | 2017-12-15 | NA
686 | 780026 | Stage 2 of eVoLP | eVoLP | 2 | Rel-15 | S2 | 2017-10-12 | 2017-12-15 | 100% | SP-170935 |  | Xiaobo Wu, Huawei | wuxiaobo@ huawei.com |  | 23.401; 23.203 | 78 | 40 |  |  | 2017-12-15 | NA
687 | 780044 | CT aspects on enhanced VoLTE performance | eVoLP-CT | 2 | Rel-15 |  | 2017-12-15 | 2018-06-14 | 100% | CP-173109 |  | Yan, Yali, Huawei | yanyali@huawei.com |  |  | 78 | 40 |  |  | 2017-12-15 | NA
688 | 780042 | CT3 aspects of EvoLP | eVoLP-CT | 3 | Rel-15 | C3 | 2017-12-15 | 2018-06-14 | 100% | CP-173109 |  | Yan, Yali, Huawei | yanyali@huawei.com | 16/3/18: 0%->100 | 29.212; 29.213 | 78 | 40 |  |  | 2017-12-15 | 2018-03-16
689 | 780043 | CT4 aspects of EvoLP | eVoLP-CT | 3 | Rel-15 | C4 | 2017-12-15 | 2018-06-14 | 100% | CP-173109 |  | Yan, Yali, Huawei | yanyali@huawei.com | 7/6/18: 0%->100 | 29.274 | 78 | 40 |  |  | 2017-12-15 | 2018-06-07
690 | 770051 | Study on enhanced VoLTE performance | FS_eVoLP | 2 | Rel-15 |  | 2016-12-01 | 2018-06-15 | 100% | SP-160833 |  | Fabrice Plante, Intel | fabrice.m.plante@intel.com | 1/12/16: 0%->5; 6/3/17: 5%->50; 7/6/17: 50%->60; 11/9/17: 60%->100 | 23.759 | 74 | 38 |  |  | 2016-12-01 | 2017-09-11
691 | 740006 | S2 aspects of FS_eVoLP | FS_eVoLP | 3 | Rel-15 | S2 | 2016-12-01 | 2017-09-14 | 100% | SP-160833 |  | Xiaobo Wu |  | 1/12/16: 0%->5; 6/3/17: 5%->50; 7/6/17: 50%->60; 11/9/17: 60%->100; 15/12/17: rapporteur changed | 23.759 | 74 | 38 |  |  | 2016-12-01 | 2017-12-15
692 | 770052 | S4 aspects of FS_eVoLP | FS_eVoLP | 3 | Rel-15 | S4 | 2017-09-14 | 2018-06-15 | 100% | SP-170615 |  | Venkatraman, Atti, Qualcomm Incorporated | vatti@qti.qualcomm.com | 15/12/17: 26.959 added;; 15/12/17: 0%->50; 16/3/18: 50%->75; 16/3/18: FCD:03/18->06/18; 7/6/18: 75%->100 | 26.959 | 77 | 39 |  |  | 2017-09-14 | 2018-06-07
693 | 710006 | Unlicensed Spectrum Offloading System | USOS | 1 | Rel-15 |  | 2016-02-01 | 2018-03-15 | 100% | SP-160117 | SP-170526 | Edward Hall, Qualcomm Incorporated | edhall@qti.qualcomm.com | 08/09/17: Moved from Rel-14 |  | 71 | 36 |  |  | 2016-03-01 | 2016-03-01
694 | 740008 | Study on unlicensed spectrum offloading system enhancements | FS_USOS | 2 | Rel-15 | S2 | 2016-12-01 | 2017-06-15 | 100% | SP-160835 |  | Haris Zisimopoulos, Qualcomm Incorporated | harisz@qti.qualcomm.com | 1/12/16: 0%->10; 6/3/17: 10%->30; 7/6/17: 30%->90; 11/9/17: 90%->100 | TR 23.729 | 74 | 38 |  |  | 2016-12-01 | 2017-09-11
695 | 770006 | Stage 1 of USOS | USOS | 2 | Rel-15 | S1 | 2016-02-01 | 2016-03-01 | 100% | SP-160117 | SP-170526 | Edward Hall, Qualcomm Incorporated | edhall@qti.qualcomm.com |  | 22.101, 22.115 | 71 | 36 |  |  | 2016-03-01 | 2016-03-01
696 | 770036 | Stage 2 of USOS | USOS | 2 | Rel-15 | S2 | 2017-09-08 | 2017-12-15 | 100% | SP-170740 |  | Haris Zisimopoulos | harisz@qti.qualcomm.com | 15/12/17: 0%->100 | TS 23.401; TS 23.203 | 77 | 39 |  |  | 2017-09-08 | 2017-12-15
697 | 770001 | Stage 3 of USOS | USOS-CT | 2 | Rel-15 | C4 | 2017-09-08 | 2018-03-15 | 100% | CP-172028 |  | Lena Chaponniere, Qualcomm Incorporated | lguellec@qti.qualcomm.com | 15/12/17: acronym corrected to USOS-CT as per the approved WID; 18/12/17: 0%->60; 16/3/18: 60%->100 | 23.008; 29.272; 29.230; 29.002; 29.305; 29.274 | 77 | 39 |  |  | 2016-03-01 | 2018-03-16
698 | 750007 | Mobile Communication System for Railways | MONASTERY | 1 | Rel-15 |  | 2016-06-09 | 2018-06-15 | 100% | SP-170163 |  | Merkel, Juergen, Nokia | juergen.merkel@nokia.com |  |  | 75 | 38 |  |  | 2017-03-02 | NA
699 | 720004 | Study on Future Railway Mobile Communication System | FS_FRMCS | 2 | Rel-15 | S1 | 2016-06-09 | 2017-06-15 | 100% | SP-170166 |  | Merkel, Juergen | Merkel, Juergen - Nokia Networks | 19/9/16: 0%->25; 6/10/16: 22.989 added; 1/12/16: 25%->40; 1/12/16: WID:SP-160371->SP-160903; 9/12/16: FCD:12/16->3/201. WID was in SP-160903; 2/3/17: 40%->80; 2/3/17: FCD:03/17->06/17; 7/6/17: 80%->100 | 22.989 | 72 | 37 |  |  | 2016-06-09 | 2017-06-07
700 | 750024 | Study on Application Architecture for the Future Railway Mobile Communication System (stage 2) | FS_FRMCS_ARCH | 2 | Rel-15 | S6 | 2017-03-03 | 2017-12-14 | 100% | SP-170269 |  | Oettl, Martin, Nokia | martin(dot)oettl(at)nokia(dot)com | 21/3/17: added impacted TR; 7/6/17: 0%->10; 11/9/17: 10%->50; 15/12/17: 50%->100 | new TR 23.790 | 75 | 38 |  |  | 2017-03-03 | 2017-12-15
701 | 750006 | Stage 1 of MONASTERY | MONASTERY | 2 | Rel-15 | S1 | 2017-03-02 | 2017-06-15 | 100% | SP-170697 |  | Merkel, Juergen, Nokia | juergen.merkel@nokia.com | 7/6/17: 0%->10; 8/9/17: WID:SP-170163->SP-170697; 11/9/17: 10%->100 | 22.280; 22.179 | 75 | 38 |  |  | 2017-03-02 | 2017-09-11
702 | 770040 | Stage 2 of MONASTERY | MONASTERY | 2 | Rel-15 | S6 | 2017-09-08 | 2017-12-15 | 100% | SP-170756 |  | Oettl, Martin, Nokia | martin(dot)oettl(at)nokia(dot)com | 14/9/17: SA6 and not SA2; 15/12/17: 0%->100 | 23.280; 23.379 | 77 | 39 |  |  | 2017-09-08 | 2017-12-15
703 | 790031 | Stage 3 of MONASTERY | MONASTERY | 2 | Rel-15 | ct | 2018-03-16 | 2018-06-15 | 100% | CP-182202 |  | Leis, Peter (Nokia) | peter(dot)leis(at)nokia(dot)com | 10/9/18: WID:CP-180097->CP-182202 |  | 79 | 40 |  |  | 2018-03-16 | 2018-09-10
704 | 790032 | CT1 aspects of MONASTERY | MONASTERY | 3 | Rel-15 | C1 | 2018-03-16 | 2018-06-15 | 100% | CP-182202 |  | Leis, Peter (Nokia) | peter(dot)leis(at)nokia(dot)com | 16/3/18: 0%->40; 7/6/18: 40%->85; 10/9/18: 85%->100 | 24.379; 24.380; 24.481; 24.483; 24.484 | 79 | 40 |  |  | 2018-03-16 | 2018-09-10
705 | 790033 | CT3 aspects of MONASTERY | MONASTERY | 3 | Rel-15 | C3 | 2018-03-16 | 2018-06-15 | 100% | CP-182202 |  | Leis, Peter (Nokia) | peter(dot)leis(at)nokia(dot)com | 10/9/18: 0%->100 | 29.165 | 79 | 40 |  |  | 2018-03-16 | 2018-09-10
706 | 790034 | DELETED - CT6 aspects of MONASTERY | MONASTERY | 3 | Rel-15 | C6 | 2018-03-16 | 2018-06-15 | 100% | CP-182202 |  | Leis, Peter (Nokia) | peter(dot)leis(at)nokia(dot)com | 10/9/18: 0%->100 | 31.102; 31.103 | 79 | 40 |  |  | 2018-03-16 | 2018-09-10
707 | 790013 | Security Architecture of MONASTERY | MONASTERY_SEC | 2 | Rel-15 | S3 | 2018-01-11 | 2018-03-16 | 100% | SP-180052 |  | Woodward, Tim, Motorola Solutions |  | 16/3/18: 0%->100 | 33.18 | 79 | 40 |  |  | 2018-03-15 | 2018-03-16
708 | 760030 | PS Data Off Phase 2 | PS_DATA_OFF2 | 1 | Rel-15 |  | 2017-03-02 | 2018-06-14 | 100% | SP-170246 |  | Murhammer, Leopold, Deutsche Telekom AG | leopold.murhammer@t-mobile.at |  |  | 75 | 38 |  |  | 2017-03-02 | NA
709 | 750008 | Stage 2 of PS Data Off Phase 2 | PS_DATA_OFF2 | 2 | Rel-15 | S2 | 2017-03-02 | 2017-12-15 | 100% | SP-170246 |  | Murhammer, Leopold, Deutsche Telekom AG | leopold.murhammer@t-mobile.at | 7/6/17: 0%->10; 11/9/17: 10%->85; 15/12/17: 85%->100; 15/12/17: FCD:09/17->12/17 |  | 75 | 38 |  |  | 2017-03-02 | 2017-12-15
710 | 760031 | Stage 3 of PS Data Off Phase 2 | PS_DATA_OFF2-CT | 2 | Rel-15 | ct | 2017-06-02 | 2018-06-14 | 100% | CP-181082 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 18/12/17: WID:CP-171104->CP-173162; 7/6/18: WID:CP-173162->CP-181082 |  | 76 | 39 |  |  | 2017-06-02 | 2018-06-07
711 | 760032 | CT1 aspects of PS Data Off Phase 2 | PS_DATA_OFF2-CT | 3 | Rel-15 | C1 | 2017-06-02 | 2018-06-14 | 100% | CP-181082 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/6/18: 0%->100 | 24.008; 24.301; 27.007; 24.229; 24.368; 24.167; 24.173; 24.275; 24.341; 24.390; 24.391 | 76 | 39 |  |  | 2017-06-02 | 2018-06-07
712 | 760033 | CT4 aspects of PS Data Off Phase 2 | PS_DATA_OFF2-CT | 3 | Rel-15 | C4 | 2017-06-02 | 2018-06-14 | 100% | CP-181082 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 15/12/17: 0%->100 | 29.272; 29.274; 29.328; 29.329; 29.228; 29.229; 23.008 | 76 | 39 |  |  | 2017-06-02 | 2017-12-15
713 | 760034 | CT6 aspects of PS Data Off Phase 2 | PS_DATA_OFF2-CT | 3 | Rel-15 | C6 | 2017-06-02 | 2018-06-14 | 100% | CP-181082 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/6/18: 0%->100 | 31.102; 31.103; 31.111 | 76 | 39 |  |  | 2017-06-02 | 2018-06-07
714 | 760035 | Northbound APIs for SCEF – SCS/AS Interworking | NAPS | 1 | Rel-15 |  | 2017-03-02 | 2018-06-15 | 100% | SP-170240 |  | Vaidya, Maulik, Huawei | Maulik.vaidya@huawei.com | 6/3/17: 0%->10 |  | 75 | 38 |  |  | 2017-03-02 | 2017-03-06
715 | 750009 | Stage 2 of NAPS | NAPS | 2 | Rel-15 | S2 | 2017-03-02 | 2017-09-15 | 100% | SP-170240 |  | Zhu Fenqin, Huawei | zhufenqin@huawei.com | 6/3/17: 0%->10; 7/6/17: 10%->85; 30/6/17: 29.122 added;; 11/9/17: 85%->100; 15/12/17: rapoprteur changed | 29.122 | 75 | 38 |  |  | 2017-03-02 | 2017-12-15
716 | 780006 | Stage 3 of NAPS | NAPS-CT | 2 | Rel-15 | C3 | 2017-06-02 | 2018-06-14 | 100% | CP-173112 |  | Yan, Yali, Huawei, | yanyali@huawei.com | 5/6/17: 0%->25; 8/9/17: WID:CP-171143->CP-172057; 11/9/17: 25%->40; 11/9/17: 40%->90. 18/12/17: WID corrected; 18/12/17: WID:CP-171143 ->CP-173112 | 29.336; 29.128; 29.230 | 78 | 40 |  |  | 2017-06-02 | 2017-12-18
717 | 760036 | CT3 aspects of NAPS | NAPS-CT | 3 | Rel-15 | C3 | 2017-06-02 | 2018-06-14 | 100% | CP-173112 |  | Yan, Yali, Huawei, | yanyali@huawei.com | 5/6/17: 0%->25; 8/9/17: WID:CP-171143->CP-172057; 11/9/17: 25%->40; 11/9/17: 40%->90; 15/12/17: 90%->65. 18/12/17: WID corrected; 16/3/18: 65%->72; 7/6/18: 72%->85; 7/6/18: 85%->95; 10/9/18: 95%->100 | 29.336; 29.128; 29.230 | 76 | 39 |  |  | 2017-06-02 | 2018-09-10
718 | 780007 | CT4 aspects of NAPS | NAPS-CT | 3 | Rel-15 | C4 | 2017-06-02 | 2018-06-14 | 100% | CP-173112 |  | Yan, Yali, Huawei, | yanyali@huawei.com | 7/6/18: 95%->100 |  | 78 | 40 |  |  | 2017-06-02 | 2018-06-07
719 | 770032 | Security aspects of NAPS | NAPS-Sec | 2 | Rel-15 | S3 | 2017-09-08 | 2018-03-16 | 100% | SP-170635 |  | Zhao, Xuwen, Huawei | zhaoxuwen@huawei.com | 15/12/17: 0%->60; 16/3/18: 60%->100 | 33.187 | 77 | 39 |  |  | 2017-09-08 | 2018-03-16
720 | 760063 | Carging aspects of NAPS | NAPS-CH | 2 | Rel-15 | S5 | 2017-09-08 | 2018-06-15 | 100% | SP-170488 |  | Chen, Shan, Huawei | chenshan@huawei.com | 30/6/17: 32.254 added;; 11/9/17: 0%->10; 15/12/17: 10%->20; 16/3/18: 20%->50; 7/6/18: 50%->100 | New TS; impact 32.240; 32.298; 32.299; 32.254 | 76 | 39 |  |  | 2017-06-05 | 2018-06-07
721 | 770049 | Common API Framework for 3GPP Northbound APIs | CAPIF | 1 | Rel-15 |  | 2017-03-10 | 2018-06-15 | 100% | SP-170798 |  | Suresh Chitturi, Samsung | s.chitturi@samsung.com | 15/12/17: 23.222 added; | New; 23.222 | 77 | 39 |  |  | 2017-09-08 | 2017-12-15
722 | 750031 | Study on CAPIF | FS_CAPIF | 2 | Rel-15 | S6 | 2017-03-10 | 2017-09-14 | 100% | SP-170405 |  | Suresh Chitturi, Samsung | s.chitturi@samsung.com | 21/3/17: added impacted TR; 7/6/17: 0%->35; 8/6/17: WID:SP-170279->SP-170405; 11/9/17: 35%->70; 15/12/17: 70%->100 | new TR 23.722 | 75 | 38 |  |  | 2017-03-10 | 2017-12-15
723 | 770041 | Stage 2 of CAPIF | CAPIF | 2 | Rel-15 | S6 | 2017-09-08 | 2017-12-15 | 100% | SP-170798 |  | Suresh Chitturi, Samsung | s.chitturi@samsung.com | 15/12/17: 0%->95; 16/3/18: 95%->100 | New | 77 | 39 |  |  | 2017-09-08 | 2018-03-16
724 | 790042 | Stage 3 of CAPIF | CAPIF-CT | 2 | Rel-15 | C3 | 2018-03-16 | 2018-06-15 | 100% | CP-180151 |  | Nishant Gupta, Samsung | nishant.gup@samsung.com | 16/3/18: 0%->10; 27/3/18: 29.222 added; 19/4/18: CAPIF->CAPIF-CT; 7/6/18: 10%->35; 7/6/18: 35%->85; 10/9/18: 85%->100 | 29.122; 29.116; 29.222 | 79 | 40 |  |  | 2018-03-16 | 2018-09-10
725 | 780024 | Security aspects of CAPIF | CAPIF-Sec | 2 | Rel-15 | S3 | 2017-12-15 | 2018-06-14 | 100% | SP-171051 |  | Rajavelsamy Rajadurai, Samsung | rajvel{@]samsung.com | 16/3/18: 0%->40; 7/6/18: 40%->100 |  | 78 | 40 |  |  | 2017-12-15 | 2018-06-07
726 | 760066 | Management and orchestration of 5G networks and network slicing | NETSLICE | 1 | Rel-15 | S5 | 2016-06-13 | 2018-09-14 | 100% | SP-180816 |  | Jan Groenendijk, Ericsson | jan<dot>groenendijk<at>ericsson<dot>com | 21/12/17: WID:SP-170586->SP-170960. Name changed from "Management of Network Slicing in Mobile Networks, Concepts, Use cases and Requirements"; 27/3/18: 32.159 added;; 6/8/18: 32.159 added;; 8/8/18: WID:SP-170960->SP 180124; 2/10/18: WID:SP 180124->SP-... | 32.101; 32.103; new; 32.159; 32.159 | 76 | 39 |  |  | 2017-06-05 | 2018-10-02
727 | 780056 | General aspects of NETSLICE | NETSLICE | 2 | Rel-15 | S5 | 2016-06-13 | 2018-09-14 | 100% | SP-180816 |  | Jan Groenendijk, Ericsson | jan<dot>groenendijk<at>ericsson<dot>com | 21/12/17: created from the Feature level, since SP-170960 contains its own specs and completions; 16/3/18: 46%->60; 7/6/18: 60%->85; 7/6/18: FCD:06/18->09/18; 8/8/18: WID:SP-170960->SP 180124; 10/9/18: 85%->100 | 32.101; 32.103; 28.530 | 76 | 39 |  |  | 2017-06-05 | 2018-09-10
728 | 720048 | Study on management and orchestration of network slicing for next generation network | FS_MONETS | 2 | Rel-15 | S5 | 2016-06-13 | 2017-09-12 | 100% | SP-160394 |  | Ericsson , Robert Petersen |  | 28/7/16: 28.801 added; 19/9/16: 0%->10; 1/12/16: 10%->25; 6/3/17: FCD:03/17->06/17; 6/3/17: 25%->60; 21/3/17: moved from rel-14; 7/6/17: FCD:06/17->09/17; 7/6/17: 60%->90; 11/9/17: 90%->100 | 32.8xx; 28.801 | 72 | 37 |  |  | 2016-06-13 | 2017-09-11
729 | 770033 | Study on security aspect of 5G Network Slicing Provisioning | FS_NETSLICE_MGT_Sec | 2 | Rel-15 | S3 | 2017-09-08 | 2018-06-15 | 100% | SP-170636 |  | SA3: Huawei | lei.zhongding@huawei.com | 11/9/17: 0%->5; 15/12/17: 33.811 added;; 15/12/17: 5%->20. Acronym corrected.; 16/3/18: 20%->30; 7/6/18: 30%->100 | 33.811 | 77 | 39 |  |  | 2017-09-08 | 2018-06-07
730 | 760065 | Provisioning of network slicing for 5G networks and services | NETSLICE-PRO_NS | 2 | Rel-15 | S5 | 2017-06-05 | 2018-09-14 | 100% | SP-180818 |  | Zhang Kai, Huawei | kai.zhangkai@huawei.com | 15/12/17: 0%->15; 21/12/17: WID:SP-170580->SP-170955; 16/3/18: 15%->40; 27/3/18: 28.532 added;; 7/6/18: 40%->80; 7/6/18: FCD:06/18->09/18; 10/9/18: 80%->100; 2/10/18: WID:SP-170955->SP-180818 | 28.531 | 76 | 39 |  |  | 2017-06-05 | 2018-10-02
731 | 780037 | Network Resource Model (NRM) for 5G networks and network slicing | NETSLICE-5GNRM | 2 | Rel-15 | S5 | 2017-12-15 | 2018-09-14 | 100% | SP-180812 |  | Nokia (Jing Ping | jing.ping@nokia-sbell.com | 16/3/18: 0%->25; 7/6/18: 25%->60; 7/6/18: FCD:06/18->09/18; 10/9/18: 60%->100; 2/10/18: WID:SP-170956->SP-180812 | 28.657; 28.658; 28.659; 28.707; 28.708; 28.709 | 78 | 40 |  |  | 2017-12-15 | 2018-10-02
732 | 780038 | Performance Assurance for 5G networks including network slicing | NETSLICE-ADPM5G | 2 | Rel-15 | S5 | 2017-12-15 | 2018-09-14 | 100% | SP-180814 |  | Yizhi Yao, Intel Corporation | yizhi dot yao at intel dot com | 16/3/18: 0%->10; 7/6/18: 10%->50; 7/6/18: FCD:06/18->09/18; 10/9/18: 50%->100; 2/10/18: WID:SP-170957->SP-180814 | 32.404 | 78 | 40 |  |  | 2017-12-15 | 2018-10-02
733 | 780039 | Management and virtualization aspects of 5G networks | NETSLICE-MNFV5G | 2 | Rel-15 | S5 | 2017-12-15 | 2018-09-14 | 100% | SP-170958 |  | Joey Chou, Intel | joey<dot>chou<at>intel<dot>com | 16/3/18: 0%->25; 7/6/18: 25%->75; 7/6/18: FCD:06/18->09/18; 10/9/18: 75%->100 | 28.500; 28.510; 28.511; 28.512; 28.513; 28.515; 28.516; 28.517; 28.518; 28.520; 28.521; 28.522; 28.523; 28.525; 28.526; 28.527; 28.528 | 78 | 40 |  |  | 2017-12-15 | 2018-09-10
734 | 780040 | 5G Trace management | NETSLICE-5GTRACE | 2 | Rel-15 | S5 | 2017-12-15 | 2018-06-07 | 100% | SP-170959 |  | Nokia (Anatoly Andrianov | anatoly.andrianov@nokia.com | 7/6/18: 0%->100 | 32.421; 32.422; 32.423; 32.441; 32.442; 32.446 | 78 | 40 |  |  | 2017-12-15 | 2018-06-07
735 | 810009 | CT aspects of 5G Trace management | NETSLICE-5GTRACE-CT | 2 | Rel-15 | ct | 2018-09-06 | 2018-09-06 | 100% | CP-182051 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  |  | 81 | 41 |  |  | 2018-09-06 | NA
736 | 810042 | CT3 aspects of 5G Trace management | NETSLICE-5GTRACE-CT | 3 | Rel-15 | C3 | 2018-09-06 | 2018-09-06 | 100% | CP-182051 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com | 10/9/18: 0%->100 | 29.507; 29.512 | 81 | 41 |  |  | 2018-09-06 | 2018-09-10
737 | 810043 | CT4 aspects of 5G Trace management | NETSLICE-5GTRACE-CT | 3 | Rel-15 | C4 | 2018-09-06 | 2018-09-06 | 100% | CP-182051 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com | 10/9/18: 0%->100 | 29.502; 29.503; 29.505; 29.509; 29.518; 29.540; 29.571; 29.244; 29.274 | 81 | 41 |  |  | 2018-09-06 | 2018-09-10
738 | 780041 | Fault Supervision for 5G networks and network slicing | NETSLICE-FS5G | 2 | Rel-15 | S5 | 2017-12-15 | 2018-09-14 | 100% | SP-180817 |  | Zhu Weihong, ZTE | zhu.weihong@zte.com.cn | 16/3/18: 0%->20; 7/6/18: 20%->60; 7/6/18: FCD:06/18->09/18; 10/9/18: 60%->100; 2/10/18: WID:SP-170961->SP-180817 | 28.545 | 78 | 40 |  |  | 2017-12-15 | 2018-10-02
739 | 790039 | Policy and Charging for Volume Based Charging | PC_VBC | 1 | Rel-15 |  | 2016-12-01 | 2018-06-15 | 100% | [6 empty] | 78 | 40 |  |  | 2018-03-16 | NA
740 | 780017 | Study on Policy and Charging for Volume Based Charging | FS_PC_VBC | 2 | Rel-15 | C3 | 2016-12-01 | 2017-12-15 | 100% | CP-172135 |  | Huang, Zhenning, China Mobile | huangzhenning <at> chinamobile <dot> com | 6/3/17: 0%->30; 21/3/17: 29.827 added;; 5/6/17: 30%->60; 8/9/17: WID:CP-160822->CP-172058; 11/9/17: FCD:06/17->12/17 | TR 29.827 | 74 | 38 |  |  | 2016-12-01 | 2017-09-11
741 | 740057 | CT3 aspects of FS_PC_VBC | FS_PC_VBC | 3 | Rel-15 | C3 | 2016-12-01 | 2017-12-15 | 100% | CP-172135 |  | Huang, Zhenning, China Mobile | huangzhenning <at> chinamobile <dot> com | 6/3/17: 0%->30; 21/3/17: 29.827 added;; 5/6/17: 30%->60; 8/9/17: WID:CP-160822->CP-172058; 11/9/17: FCD:06/17->12/17; 15/12/17: 60%->61; 15/12/17: 61%->100 | TR 29.827 | 74 | 38 |  |  | 2016-12-01 | 2017-12-15
742 | 780018 | CT1 aspects of FS_PC_VBC | FS_PC_VBC | 3 | Rel-15 | C1 | 2016-12-01 | 2017-12-15 | 100% | CP-172135 |  | Huang, Zhenning, China Mobile | huangzhenning <at> chinamobile <dot> com | 15/12/17: 0%->100 | TR 29.827 | 74 | 38 |  |  | 2016-12-01 | 2017-12-15
743 | 790040 | CT1 aspects of PV_VBC | PC_VBC | 2 | Rel-15 | C1 | 2018-03-16 | 2018-06-15 | 100% | CP-180051 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | 7/6/18: 0%->100 | 24.605; 24.147 | 79 | 40 |  |  | 2018-03-16 | 2018-06-07
744 | 790041 | CT3 aspects of PV_VBC | PC_VBC | 2 | Rel-15 | C3 | 2018-03-16 | 2018-06-15 | 100% | CP-180051 |  | Huang Zhenning (China Mobile) | huangzhenning (at) chinamobile (dot) com | 7/6/18: 0%->100 | 29.212; 29.213; 29.214 | 79 | 40 |  |  | 2018-03-16 | 2018-06-07
745 | 760037 | Framework for Live Uplink Streaming | FLUS | 1 | Rel-15 | S4 | 2017-06-05 | 2018-06-14 | 100% | SP-170824 |  | Park, Kyungmo, SK Telecom | kyungmo.park@sk.com | 30/6/17: 26.238 added;; 11/9/17: 0%->10; 15/12/17: 10%->85; 15/12/17: FCD:12/17->06/18; 21/12/17: WID:SP-170576->SP-170824; 16/3/18: 85%->90; 7/6/18: 90%->100 | New TS; 26.238 | 76 | 39 |  |  | 2017-06-03 | 2018-06-07
746 | 770034 | Self-Organizing Networks (SON) for Active Antenna System (AAS) deployment management | OAM_SON_AAS | 1 | Rel-15 | S5 | 2017-09-08 | 2018-06-15 | 100% | SP-170658 |  | Nokia (Weixing Wang) | weixing.wang@nokia-sbell.com | 15/12/17: 0%->80; 10/9/18: 80%->100 | 28.627; 28.628; 28.629; 28.658; 28.659 | 77 | 39 |  |  | 2017-09-08 | 2018-09-10
747 | 740011 | Server and Network Assisted DASH for 3GPP Multimedia Services | SAND | 1 | Rel-15 | S4 | 2016-12-01 | 2017-09-14 | 100% | SP-170031 | SP-170687 | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 3/3/17: WID:SP-160779->SP-170031; 6/3/17: 0%->15; 7/6/17: 15%->60; 11/9/17: 60%->100 | TS 26.247, 26.233 | 74 | 38 |  |  | 2016-12-01 | 2017-09-11
748 | 770021 | SAND for MBMS | SAND4M | 1 | Rel-15 | S4 | 2017-09-08 | 2018-06-15 | 100% | SP-170827 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 15/12/17: 0%->50; 15/12/17: FCD:12/17->03/18; 21/12/17: WID:SP-170608->SP-170827; 16/3/18: 50%->60; 16/3/18: FCD:03/18->06/18; 7/6/18: 60%->100 | TS 26.247; TS 26.346; TS 26.347; TR26.946 | 77 | 39 |  |  | 2017-09-08 | 2018-06-07
749 | 780036 | Management Enhancement for EPC CUPS | ME_CUPS | 1 | Rel-15 | S5 | 2017-12-15 | 2018-09-14 | 100% | SP-170954 |  | Huawei (ZHU, Lei | lei.zhu@huawei.com | ASN.1-type of WID, hence later than St3, indpt of CUPS Rel-14; 16/3/18: 0%->5; 7/6/18: 5%->60; 10/9/18: 60%->100 | 32.426; 32.455; 28.658; 28.707; 28.708; 28.709 | 78 | 40 |  |  | 2017-12-15 | 2018-09-10
750 | 760038 | Enhanced QoE Reporting for MTSI | EQoE_MTSI | 1 | Rel-15 | S4 | 2017-06-05 | 2018-03-15 | 100% | SP-170333 |  | Gunnar Heikkilä, Ericsson LM | gunnar.heikkila@ericsson.com | 11/9/17: 0%->10; 15/12/17: 10%->80; 16/3/18: 80%->100 | TS 26.114 | 76 | 39 |  |  | 2017-06-03 | 2018-03-16
751 | 760012 | Enhanced Calling Name Service | eCNAM | 1 | Rel-15 |  | 2016-09-15 | 2018-03-14 | 100% | SP-160548 |  | Hala Mowafy, Ericsson |  | 1/12/16: 0%->100 | 22.173 | 73 | 37 |  |  | 2016-09-19 | 2016-12-01
752 | 730006 | Stage 1 of eCNAM | eCNAM | 2 | Rel-15 | S1 | 2016-09-15 | 2016-12-15 | 100% | SP-160548 |  | Hala Mowafy, Ericsson |  | 1/12/16: 0%->100; 30/6/17: 24.196 added; | 22.173; 24.196 | 73 | 37 |  |  | 2016-09-19 | 2017-06-30
753 | 760013 | CT aspects of eCNAM | eCNAM-CT | 2 | Rel-15 | ct | 2017-06-02 | 2018-03-14 | 100% | CP-171181 |  | Mowafy, Hala. Ericsson | hala.mowafy@ericsson.com |  |  | 76 | 39 |  |  | 2017-06-02 | NA
754 | 760014 | CT1 aspects of eCNAM | eCNAM-CT | 3 | Rel-15 | C1 | 2017-06-02 | 2018-03-14 | 100% | CP-171181 |  | Mowafy, Hala. Ericsson | hala.mowafy@ericsson.com | 14/9/17: 0%->40; 15/12/17: 40%->85; 20/3/18: 85%->100 | 24.259; 24.604; 24.606; 24.607; 24.608; 24.610; 24.611; 24.615; 24.616; 24.629; 24.642; 24.647; 24.654 | 76 | 39 |  |  | 2017-06-02 | 2018-03-20
755 | 760015 | CT3 aspects of eCNAM | eCNAM-CT | 3 | Rel-15 | C3 | 2017-06-02 | 2018-03-14 | 100% | CP-171181 |  | Mowafy, Hala. Ericsson | hala.mowafy@ericsson.com | 7/6/18: 0%->100 | 29.165 | 76 | 39 |  |  | 2017-06-02 | 2018-06-07
756 | 750001 | Enhancement of background data transfer | eBT | 1 | Rel-15 | S1 | 2017-01-16 | 2017-03-08 | 100% | SP-170161 |  | Atsushi Minokuchi, NTT DOCOMO | minokuchi at nttdocomo dot com |  | 22.101 | 75 | 38 |  |  | 2017-03-02 | NA
757 | 760016 | Stage-3 SAE Protocol Development - Phase 6 | SAES6 | 1 | Rel-15 | C1 | 2017-06-02 | 2018-06-18 | 100% | CP-171100 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com |  | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 76 | 39 |  |  | 2016-03-02 | NA
758 | 760017 | SAES6 CS Fallback in EPS | SAES6-CSFB | 2 | Rel-15 | C1 | 2017-06-02 | 2018-06-18 | 100% | CP-171100 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com | 14/9/17: 0%->20; 15/12/17: 20%->55; 16/3/18: 55%->80; 7/6/18: 80%->100 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 76 | 39 |  |  | 2016-03-02 | 2018-06-07
759 | 760018 | SAES6 for support for non-3GPP accesses | SAES6-non3GPP | 2 | Rel-15 | C1 | 2017-06-02 | 2018-06-18 | 100% | CP-171100 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com | 14/9/17: 0%->20; 15/12/17: 20%->55; 16/3/18: 55%->80; 7/6/18: 80%->100 | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 76 | 39 |  |  | 2016-03-02 | 2018-06-07
760 | 760019 | SAE Protocol Development (Stage 3) - Phase 6 | SAES6 | 2 | Rel-15 | C1 | 2017-06-02 | 2018-06-18 | 100% | CP-171100 |  |  |  | 14/9/17: 0%->20; 15/12/17: 20%->55; 16/3/18: 55%->80; 7/6/18: 80%->100 |  | 72 | 37 |  |  | 2015-03-24 | 2018-06-07
761 | 730051 | Security Assurance Specification for eNB network product class | SCAS_eNB | 1 | Rel-15 | S3 | 2016-09-19 | 2017-12-12 | 100% | SP-160570 |  | Marcus Wong, Huawei Technologies | mwong@huawei.com | 6/10/16: 33.216 added; 1/12/16: 0%->5; 6/3/17: 5%->25. Moved from Rel-14.; 7/6/17: FCD:06/17->12/17; 7/6/17: 25%->75; 11/9/17: 75%->100 | TS 33.117, TR 33.926; 33.216 | 73 | 37 |  |  | 2016-09-19 | 2017-09-11
762 | 720075 | Security Assurance Specification for PGW network product class | SCAS_PGW | 1 | Rel-15 | S3 | 2016-06-17 | 2017-12-12 | 100% | SP-160481 |  | Peng Jin, China Mobile | pengjin@chinamobile.com | 28/7/16: 33.250 added; 19/9/16: 0%->10; 6/10/16: 33.216 added; 1/12/16: 10%->40. 06/03/17: moved from Rel-14.; 6/3/17: 40%->80; 7/6/17: FCD:06/17->12/17; 7/6/17: 80%->95; 11/9/17: 95%->100 | 33.250; 33.216 | 72 | 37 |  |  | 2016-06-17 | 2017-09-11
763 | 750005 | HPLMN Radio Access Technology deployment Optimisation in Network Selection | HORNS | 1 | Rel-15 | S1 | 2017-03-02 | 2017-06-15 | 100% | SP-170277 |  | Eddy Hall, Qualcomm Incorporated | edhall@qti.qualcomm.com | 7/6/17: 75%->100 |  | 75 | 38 |  |  | 2017-03-02 | 2017-06-07
764 | 760008 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc9 | 1 | Rel-15 | ct | 2017-06-02 | 2018-06-15 | 99% | CP-171098 |  | Dr. Belling, Thomas, Nokia | Thomas.Belling@nokia.com |  |  | 76 | 39 |  |  | 2016-06-11 | NA
765 | 760009 | CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc9 | 2 | Rel-15 | C1 | 2017-06-02 | 2018-06-13 | 100% | CP-171098 |  | Dr. Belling, Thomas, Nokia | Thomas.Belling@nokia.com | 14/9/17: 0%->40; 15/12/17: 40%->60; 16/3/18: 60%->80; 7/6/18: 80%->100 | 23.218; 24.229; 24.930 | 76 | 39 |  |  | 2014-12-04 | 2018-06-07
766 | 760010 | (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc9 | 2 | Rel-15 | C1-IETF | 2017-06-02 | 2018-06-15 | 100% | CP-171098 |  | Dr. Belling, Thomas, Nokia | Thomas.Belling@nokia.com |  |  | 76 | 39 |  |  | 2014-12-04 | NA
(IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id) | (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id)
768 | 780048 | (IETF) P-Visited-Network header updated (was: draft-jesske-update-p-visited-network ) | IMSProtoc9 | 3 | Rel-15 | C1-IETF | 2017-06-02 | 2018-06-15 | 100% |  |  | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de | 27/6/18: 0%->100 |  | 78 | 40 |  |  | 2017-12-18 | 2018-06-27
769 | 760011 | CT3 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc9 | 2 | Rel-15 | C3 | 2017-06-02 | 2018-06-13 | 100% | CP-171098 |  | Dr. Belling, Thomas, Nokia | Thomas.Belling@nokia.com | 15/12/17: 0%->40; 7/6/18: 40%->85; 10/9/18: 85%->100 | 29.163; 29.165; 29.949 | 76 | 39 |  |  | 2015-04-02 | 2018-09-10
770 | 750014 | Lawful Interception Rel-15 | LI15 | 1 | Rel-15 |  | 2017-03-02 | 2019-03-12 | 89% | SP-170839 |  | Alex Leadbeater, BT | alex.leadbeater@bt.com | 21/12/17: WID:SP-170039->SP-170839; 16/3/18: 10%->20 |  | 75 | 38 |  |  | 2016-07-27 | 2018-03-16
771 | 750015 | Deleted - Study on R15 Lawful Interception Service | FS_15LIS | 2 | Rel-15 | S3LI | 2017-03-02 | 2018-09-14 | 100% | SP-170040 |  | Gerry McQuaid, Vodafone | Gerald.McQuaid@vodafone.com | 12/7/17: 0%->5; 11/9/17: 5%->10; 16/3/18: 24%->35; 7/6/18: 35%->70; 7/6/18: FCD:06/18->09/18; 10/9/18: 70%->85. 17/01/19: deleted as per Alex's e-mail 13 Nov. Was at 85% |  | 75 | 38 | 82 |  | 2016-07-27 | 2018-09-10
772 | 750013 | Normative work on Lawful Interception Rel-15 | LI15 | 2 | Rel-15 | S3LI | 2017-03-02 | 2019-03-12 | 80% | SP-170839 |  | Alex Leadbeater, BT | alex.leadbeater@bt.com | 12/7/17: 0%->5; 15/12/17: 5%->10; 10/9/18: 17%->40; 7/12/18: FCD:12/18->03/19; 7/12/18: 40%->75; 20/3/19: 75%->80 |  | 75 | 38 |  |  | 2016-07-27 | 2019-03-20
773 | 750068 | DL interference mitigation for UMTS | UTRA_DL_IM | 1 | Rel-15 | R2 | 2017-03-15 | 2017-06-15 | 100% | RP-170703 |  | Qualcomm |  | no Perf. part |  | 75 | 38 |  |  | 2017-03-21 | 2017-03-21
774 | 750168 | Core part: DL interference mitigation for UMTS | UTRA_DL_IM-Core | 2 | Rel-14 | R2 | 2017-03-15 | 2017-06-15 | 100% | RP-171136 | RP-171135 | Qualcomm |  | no Perf. part19/6/17: Compl:0%->100% |  | 75 | 38 |  |  | 2017-03-21 | 2017-06-19
775 | 760055 | Control and monitoring of Power, Energy and Environmental (PEE) parameters in Radio Access Networks (RAN) | PEE_CMON | 1 | Rel-15 | S5 | 2017-06-05 | 2018-03-15 | 100% | SP-170479 |  | Jean-Michel CORNILY, ORANGE |  | 30/6/17: 28.306 added;; 30/6/17: 28.305 added;; 30/6/17: 28.304 added;; 11/9/17: 0%->20; 15/12/17: 20%->80; 16/3/18: 80%->100 | New TSs, TS 52.402; TS 32.405; TS 32.425; TS 32.101; TS 32.103; 28.306; 28.305; 28.304 | 76 | 39 |  |  | 2017-06-03 | 2018-03-16
776 | 760082 | Simplified HS-SCCH for UMTS | UTRA_simple_HSSCCH | 1 | Rel-15 | R6 | 2017-03-15 | 2017-12-15 | 100% | RP-171443 |  | Ericsson |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
777 | 750077 | Study on a simplified HS-SCCH for UMTS | FS_UTRA_simple_HSSCCH | 2 | Rel-15 | R1 | 2017-03-15 | 2017-06-15 | 100% | RP-171477 |  | gerardo.agni.medina.acosta@ericsson.com | gerardo.agni.medina.acosta@ericsson.com | 19/6/17: Compl:0%->100%; 30/6/17: 25.709 added; | 25.709 | 75 | 38 |  |  | 2017-03-21 | 2017-06-30
778 | 760182 | Core part: Simplified HS-SCCH for UMTS | UTRA_simple_HSSCCH-Core | 2 | Rel-15 | R6 | 2017-06-15 | 2017-12-15 | 100% | RP-172720 | RP-172306 | Ericsson |  | 11/9/17: 0%->85; 15/12/17: 85%->100; 8/1/18: WID: RP-171443->RP-172720; |  | 76 | 39 |  |  | 2017-06-16 | 2018-01-08
779 | 760057 | Charging for enhancement to Flexible Mobile Service Steering (eFMSS) | eFMSS_CH | 1 | Rel-15 | S5 | 2017-06-05 | 2017-12-14 | 100% | SP-170482 |  | Long,Biao, China Telecom | longb.gd@chinatelecom.cn. | 11/9/17: 0%->70; 15/12/17: 70%->100 | TS 32.251; TS 32.298; TS 32.299 | 76 | 39 |  |  | 2017-06-03 | 2017-12-15
780 | 780020 | Receive acoustic output test in the presence of background noise | RAOT | 1 | Rel-15 | S4 | 2017-12-15 | 2018-06-15 | 100% | SP-170835 |  | ISBERG, Peter, Sony Mobile Communications | peter.isberg [at] sony.com | 16/3/18: 0%->80; 16/3/18: FCD:03/18->06/18; 7/6/18: 80%->100 | 26.131; 26.132 | 78 | 40 |  |  | 2017-12-15 | 2018-06-07
781 | 780021 | Speech quality in the presence of ambient noise for super-wideband and fullband modes | SPAN | 1 | Rel-15 | S4 | 2017-12-15 | 2018-09-14 | 100% | SP-170836 |  | Reimes, Jan – HEAD acoustics GmbH | jan.reimes@head-acoustics.de | 16/3/18: 0%->50; 7/6/18: 50%->80; 7/6/18: FCD:06/18->09/18; 10/9/18: 80%->100 | 26.131 | 78 | 40 |  |  | 2017-12-15 | 2018-09-10
782 | 780032 | REST Solution Sets | REST_SS | 1 | Rel-15 |  | 2016-09-19 | 2036-09-24 | 3% | SP-170950 | [5 empty] | 78 | 41 |  |  | 2017-12-15 | NA
783 | 730057 | Study on a RESTful HTTP-based Solution Set | FS_OAM_RESTFUL | 2 | Rel-15 | S5 | 2016-09-19 | 2017-12-12 | 100% | SP-160613 |  | Nokia: Pollakowski, Olaf | olaf.pollakowski@nokia.com | 6/10/16: 32.866 added; 1/12/16: 0%->5; 7/6/17: 5%->45; 7/6/17: FCD:06/17->12/17; 11/9/17: 45%->80; 15/12/17: 80%->100 | 32.866 | 73 | 37 |  |  | 2016-09-19 | 2017-12-15
784 | 780033 | REST Solution Sets (normative work) | REST_SS | 2 | Rel-15 | S5 | 2017-12-15 | 2018-09-14 | 100% | SP-170950 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com | 16/3/18: 0%->20; 7/6/18: 20%->70; 7/6/18: FCD:06/18->09/18; 10/9/18: 70%->100 | 32.101 | 78 | 40 |  |  | 2017-12-15 | 2018-09-10
785 | 800114 | (IETF) JSON Schema: A Media Type for Describing JSON Documents (draft-handrews-json-schema) | REST_SS | 2 | Rel-15 | S5-IETF | 2017-12-15 | 2036-09-24 | 0% | SP-170950 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com |  |  | 80 | 41 |  |  | 2018-07-10 | NA
786 | 800115 | (IETF) JSON Schema Validation: A Vocabulary for Structural Validation of JSON (draft-handrews-json-schema-validation) | REST_SS | 2 | Rel-15 | S5-IETF | 2017-12-15 | 2036-09-24 | 0% | SP-170950 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com |  |  | 80 | 41 |  |  | 2018-07-10 | NA
787 | 800116 | (IETF) JSON Hyper-Schema: A Vocabulary for Hypermedia Annotation of JSON (draft-handrews-json-schema-hyperschema) | REST_SS | 2 | Rel-15 | S5-IETF | 2017-12-15 | 2036-09-24 | 0% | SP-170950 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com |  |  | 80 | 41 |  |  | 2018-07-10 | NA
788 | 790028 | Enhancements to Call spoofing functionality | eSPECTRE | 1 | Rel-15 | C1 | 2018-03-15 | 2018-09-14 | 75% | CP-180096 |  | Axell, Jörgen, Ericsson | Jorgen.Axell@ericsson.com |  |  | 79 | 41 |  |  | 2018-03-16 | NA
792 | 750033 | (Small) Technical Enhancements and Improvements for Rel-15 | TEI15 | 1 | Rel-15 |  | 2017-03-17 | 2018-06-15 | 25% | [6 empty] | 68 | 35 |  |  | 2015-06-15 | 2015-06-15
793 | 800102 | (IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (RFC8446) | TEI15 | 2 | Rel-15 | S3-IETF | 2017-03-17 | 2018-06-15 | 100% | [6 empty] | 80 | 41 |  |  | 2018-06-27 | NA
794 | 750034 | (Small) Test Technical Enhancements and Improvements for Rel-15 | TEI15_Test | 1 | Rel-15 |  | 2017-03-17 | 2017-12-15 | 100% | - |  | - | - | Created upon demand of RAN5 | - | 75 | 38 |  |  | 2015-01-12 | 2016-02-24
795 | 0 | Release 15 Features on LTE improvements | - | 1 | Rel-15 |  | 2000-01-01 | 2000-01-01 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
796 | 770067 | UL data compression in LTE | LTE_UDC | 1 | Rel-15 | R2 | 2000-01-03 | 2019-03-15 | 99% | RP-172076 |  | CATT |  |  |  | 77 | 39 |  |  | 2017-09-19 | NA
797 | 770167 | Core part: UL data compression in LTE | LTE_UDC-Core | 2 | Rel-15 | R2 | 2000-01-03 | 2018-09-14 | 99% | RP-180914 | RP-180912 | CATT |  | ; 8/1/18: Compl:0%->70%; 8/1/18: CD:Mon 03/01/00->Thu 15/03/18; 27/3/18: Compl:70%->99%27/3/1 ; 27/6/18: CD:Fri 15/06/18->Sat 15/09/18; |  | 77 | 39 |  |  | 2017-09-19 | 2018-06-27
798 | 800080 | UE Conformance Test Aspects - UL Data Compression in LTE | LTE_UDC-UEConTest | 2 | Rel-15 | R5 | 2018-06-15 | 2019-03-15 | 100% | RP-190311 |  | CATT |  | tested: REL-15 WI LTE_UDC-Core; 26/3/19: WID:RP-180918->RP-190311; 26/3/19: 0%->100 |  | 80 | 41 |  |  | 2018-06-27 | 2019-03-26
799 | 770068 | LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C | LTE_CA_4DL4UL_B41_B41_B42_B42 | 1 | Rel-15 | R4 | 2017-09-15 | 2018-03-15 | 100% | RP-172030 |  | KDDI |  |  |  | 77 | 39 |  |  | 2017-09-19 | NA
800 | 770168 | Core part:LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C | LTE_CA_4DL4UL_B41_B41_B42_B42-Core | 2 | Rel-15 | R4 | 2017-09-15 | 2018-03-15 | 100% | RP-180151 |  | KDDI |  | 15/12/17: 36.715-04 added;; 8/1/18: Compl:0%->80%27/3/18: Compl:80%->100%; | 36.715-04 | 77 | 39 |  |  | 2017-09-19 | 2018-03-27
801 | 770268 | Perf. part:LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C | LTE_CA_4DL4UL_B41_B41_B42_B42-Perf | 2 | Rel-15 | R4 | 2017-09-15 | 2018-03-15 | 100% | RP-180151 |  | KDDI |  | ; 27/3/18: Compl:0%->100%; |  | 77 | 39 |  |  | 2017-09-19 | 2018-03-27
802 | 770069 | Additional LTE bands for UE category M1 and/or NB1 in Rel-15 | LTE_bands_R15_M1_NB1 | 1 | Rel-15 | R4 | 2017-09-15 | 2018-06-15 | 100% | RP-172077 |  | Ericsson |  |  |  | 77 | 39 |  |  | 2017-09-19 | NA
803 | 770169 | Core part: Additional LTE bands for UE category M1 and/or NB1 in Rel-15 | LTE_bands_R15_M1_NB1-Core | 2 | Rel-15 | R4 | 2017-09-15 | 2018-06-15 | 100% | RP-180262 |  | Ericsson |  | ; 8/1/18: Compl:0%->99%27/3/18: WID: RP-172077->RP-180262; 27/6/18: Compl:99%->100% |  | 77 | 39 |  |  | 2017-09-19 | 2018-06-27
804 | 770269 | Perf. part: Additional LTE bands for UE category M1 and/or NB1 in Rel-15 | LTE_bands_R15_M1_NB1-Perf | 2 | Rel-15 | R4 | 2017-09-15 | 2018-06-15 | 100% | RP-180262 |  | Ericsson |  | ; 27/3/18: Compl:0%->99% ; 27/6/18: Compl:99%->100% |  | 77 | 39 |  |  | 2017-09-19 | 2018-06-27
805 | 780066 | UE Conformance Test aspects - LTE bands with UE category M1 and/or NB1 in Rel-15 | LTE_bands_R15_M1_NB1-UEConTest | 2 | Rel-15 | R5 | 2017-12-15 | 2018-06-15 | 100% | RP-172713 |  | Ericsson |  | tested: REL-15 WI LTE_bands_R15_M1_NB1-Core27/3/ ; |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
806 | 770070 | Additional LTE bands for UE category M2 and/or NB2 in Rel-15 | LTE_bands_R15_M2_NB2 | 1 | Rel-15 | R4 | 2017-09-15 | 2018-12-14 | 54% | RP-172078 |  | Ericsson |  |  |  | 77 | 39 |  |  | 2017-09-19 | NA
807 | 770170 | Core part: Additional LTE bands for UE category M2 and/or NB2 in Rel-15 | LTE_bands_R15_M2_NB2-Core | 2 | Rel-15 | R4 | 2017-09-15 | 2018-06-15 | 100% | RP-180261 |  | Ericsson |  | ; 8/1/18: Compl:0%->99%; 27/3/18: WID: RP-172078->RP-180261; 27/6/18: Compl:99%->100% |  | 77 | 39 |  |  | 2017-09-19 | 2018-06-27
808 | 780067 | UE Conformance Test aspects - LTE bands with UE category M2 and/or NB2 in Rel-15 | LTE_bands_R15_M2_NB2-UEConTest | 2 | Rel-15 | R5 | 2017-12-15 | 2018-12-14 | 20% | RP-172714 |  | Ericsson |  | tested: REL-15 WI LTE_bands_R15_M2_NB2-Core; 27/ ; |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
809 | 770071 | Extended-Band12 new E-UTRA Band | Ext_B12_LTE | 1 | Rel-15 | R4 | 2017-09-15 | 2019-06-01 | 80% | RP-172111 |  | Ericsson |  |  |  | 77 | 39 |  |  | 2017-09-19 | NA
810 | 770171 | Core part: Extended-Band12 new E-UTRA Band | Ext_B12_LTE-Core | 2 | Rel-15 | R4 | 2017-09-15 | 2018-03-15 | 100% | RP-180159 |  | Ericsson |  | 15/12/17: 37.761 added;; 8/1/18: Compl:0%->25%; 27/3/18: Compl:25%->100%; | 37.761 | 77 | 39 |  |  | 2017-09-19 | 2018-03-27
811 | 770271 | Perf. part: Extended-Band12 new E-UTRA Band | Ext_B12_LTE-Perf | 2 | Rel-15 | R4 | 2017-09-15 | 2018-03-15 | 100% | RP-180159 |  | Ericsson |  | ; 8/1/18: WID: RP-172111->RP-17262527/3/18: Compl:0%->100% |  | 77 | 39 |  |  | 2017-09-19 | 2018-03-27
812 | 830084 | UE Conformance Test Aspects - Extended-Band12 new E-UTRA Band (Band 85) | Ext_B12_LTE-UEConTest | 2 | Rel-15 | R5 | 2019-03-01 | 2019-06-01 | 0% | RP-190510 |  | Ericsson | [7 empty] | 2019-03-26 | NA
813 | 710073 | Stopped - Signalling reduction to enable light connection for LTE | LTE_LIGHT_CON | 1 | Rel-15 |  | 2016-03-15 | 2018-03-15 | 100% | RP-171459 |  | Huawei |  | no Perf. part; 14/9/17: WID:RP-160540->RP-160937; 14/9/17: WID:RP-160937->RP-171459 |  | 71 | 36 |  |  | 2016-03-22 | 2017-09-14
814 | 710173 | Stopped - Core part: Signalling reduction to enable light connection for LTE | LTE_LIGHT_CON-Core | 2 | Rel-15 | R2 | 2016-03-15 | 2018-03-15 | 100% | RP-171459 |  | Huawei |  | no Perf. part; 1/7/16: Compl:0%->10%; 1/7/16: CD:Thu 15/12/16->Wed 15/03/17; 1/7/16: WID: RP-160540->RP-16093726/9/16: Compl:10%->30%; 20/12/16: Compl:30%->75%; 20/12/16: Stat Rep: --> 21/3/17: Compl:75%->79% 21/3/17: CD:W ; 27/6/ |  | 71 | 36 |  |  | 2016-03-22 | 2018-06-27
815 | 750032 | Stopped - Study on Stage 2 of LTE_LIGHT_CON | FS_LTE_LIGHT_CON | 2 | Rel-15 | S2 | 2017-03-10 | 2017-06-15 | 100% | SP-170280 |  | Sašo Stojanovski , intel | saso.stojanovski@intel.com | 21/3/17: 23.723 added;; 7/6/17: 0%->55. Stopped at 55%, set at 100% artificially | 23.723 | 75 | 38 |  |  | 2017-03-10 | 2017-06-07
816 | 740045 | Stopped - Stage 3 of LTE_LIGHT_CON | LTE_LIGHT_CON-CT | 2 | Rel-15 | ct | 2016-12-01 | 2017-03-14 | 100% | CP-160703 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  |  | 74 | 38 |  |  | 2016-12-01 | NA
817 | 740046 | Stopped - CT1 aspects of LTE_LIGHT_CON | LTE_LIGHT_CON-CT | 3 | Rel-15 | C1 | 2016-12-01 | 2017-03-14 | 100% | CP-160703 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 6/3/17: 0%->25; 11/9/17: 25%->0 | 24.008, 24.301, 29.118, 24.368, 27.007 | 74 | 38 |  |  | 2016-12-01 | 2017-09-11
818 | 740047 | Stopped - CT4 aspects of LTE_LIGHT_CON | LTE_LIGHT_CON-CT | 3 | Rel-15 | C4 | 2016-12-01 | 2017-03-14 | 100% | CP-160703 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 29.274, 29.272 | 74 | 38 |  |  | 2016-12-01 | NA
819 | 740048 | Stopped - CT6 aspects of LTE_LIGHT_CON | LTE_LIGHT_CON-CT | 3 | Rel-15 | C6 | 2016-12-01 | 2017-03-14 | 100% | CP-160703 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/3/17: 0%->100 | 31.102 | 74 | 38 |  |  | 2016-12-01 | 2017-03-07
820 | 710074 | Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS) | AASenh_BS_LTE_UTRA | 1 | Rel-15 |  | 2016-03-15 | 2018-09-14 | 71% | RP-161668 |  | Huawei |  | follow-up WI of REL-13 WI AAS_BS_LTE_UTRA; 14/9/17: WID:RP-160548->RP-161668 | 37.843 | 71 | 36 |  |  | 2016-03-22 | 2017-09-14
821 | 710174 | Core part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS) | AASenh_BS_LTE_UTRA-Core | 2 | Rel-15 | R4 | 2016-03-15 | 2017-12-15 | 100% | RP-171745 | RP-172345 | Huawei |  | follow-up WI of REL-13 WI AAS_BS_LTE_UTRA1/7/16: Compl:0%->5%1/7/16: CD:Fri 15/09/17->Wed 15/03/1726/9/16: Compl:5%->10% 20/12/16: Compl:10%->20%21/3/17: Compl:20%->40% ; |  | 71 | 36 |  |  | 2016-03-22 | 2018-01-08
822 | 710274 | Perf. part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS) | AASenh_BS_LTE_UTRA-Perf | 2 | Rel-15 | R4 | 2016-03-15 | 2018-09-14 | 50% | RP-181297 |  | Huawei |  | 1/7/16: WID: RP-160548->RP-1609401/7/16: Release: Rel-15->Rel-14; 26/9/16: WID: RP-160940->RP-161668 20/12/16: Stat Rep: -->; 21/3/17: Compl:0%->10%; |  | 71 | 36 |  |  | 2016-03-22 | 2018-06-27
823 | 720091 | Shortened TTI and processing time for LTE | LTE_sTTIandPT | 1 | Rel-15 |  | 2016-06-15 | 2019-06-20 | 89% | RP-161299 |  | Ericsson |  |  |  | 72 | 37 |  |  | 2016-07-08 | 2016-06-22
824 | 720191 | Core part: Shortened TTI and processing time for LTE | LTE_sTTIandPT-Core | 2 | Rel-15 | R1 | 2016-06-15 | 2018-09-14 | 99% | RP-171468 | RP-181008 | Ericsson |  | 26/9/16: Compl:0%->5%; 20/12/16: Compl:5%->10%21/3/17: Compl:10%->30%19/6/17: Compl:30%->65%19/6/17: CD: 19/9/17: Compl:65%->75%; 8/1/18: Compl:75%->99%; 8/1/18: CD:Fri 15/12/17->F ; 27/6/18: CD:Fri 15/06/1 |  | 72 | 37 |  |  | 2016-07-01 | 2018-06-27
825 | 720291 | Perf. part: Shortened TTI and processing time for LTE | LTE_sTTIandPT-Perf | 2 | Rel-15 | R4 | 2016-09-14 | 2018-09-14 | 100% | RP-171468 |  | Ericsson |  | ; 26/9/16: WID: RP-161299->RP-161922; 20/12/16: WID: RP-161922->RP-16201421/3/17: WID: RP-162014->RP-170113; 19/6/17: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:0%->33%; 27/6/18: Compl:33%->60%; 26/3/19: 60%->100 |  | 72 | 37 |  |  | 2016-07-01 | 2019-03-26
826 | 820064 | UE Conformance Test Aspects - Shortened TTI and processing time for LTE | LTE_sTTIandPT-UEConTest | 2 | Rel-15 | R5 | 2018-12-15 | 2019-06-20 | 0% | RP-182429 |  | Huawei |  | tested: REL-15 WI LTE_sTTIandPT-Core | [5 empty] | 2019-01-16 | NA
827 | 740072 | 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe | LTE450_Europe_PPDR | 1 | Rel-15 |  | 2016-12-15 | 2018-03-15 | 100% | RP-162514 |  | Airbus |  | 21/3/17: 36.748 added; | 36.748 | 74 | 38 |  |  | 2016-12-20 | 2017-03-21
828 | 740172 | Core part: 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe | LTE450_Europe_PPDR-Core | 2 | Rel-15 | R4 | 2016-12-15 | 2017-09-15 | 100% | RP-162514 |  | Airbus |  | 21/3/17: Compl:0%->10%; 19/6/17: Compl:10%->75%; 19/9/17: Compl:75%->100% |  | 74 | 38 |  |  | 2016-12-20 | 2017-09-19
829 | 740272 | Perf. part: 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe | LTE450_Europe_PPDR-Perf | 2 | Rel-15 | R4 | 2016-12-15 | 2017-09-15 | 100% | RP-162514 |  | Airbus |  | 19/6/17: Compl:0%->50%19/9/17: Compl:50%->100% |  | 74 | 38 |  |  | 2016-12-20 | 2017-09-19
830 | 770065 | UE Conformance Test Aspects - 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe (Band 72) | LTE450_Europe_PPDR-UEConTest | 2 | Rel-15 | R5 | 2017-09-15 | 2018-03-15 | 100% | RP-180528 |  | Airbus |  | ; 8/1/18: Compl:0%->77%; 27/3/18: Compl:77%->100%; |  | 77 | 39 |  |  | 2017-09-19 | 2018-03-27
831 | 740074 | E-UTRA 700MHz in Europe for Broadband-PPDR (Public Protection and Disaster Relief) | LTE700_Europe_PPDR | 1 | Rel-15 |  | 2016-12-15 | 2018-03-15 | 83% | RP-162534 |  | Airbus |  |  |  | 74 | 38 |  |  | 2016-12-20 | 2016-12-20
832 | 740174 | Core part: E-UTRA 700MHz in Europe for Broadband-PPDR | LTE700_Europe_PPDR-Core | 2 | Rel-15 | R4 | 2016-12-15 | 2017-09-15 | 100% | RP-170212 |  | Airbus |  | 21/3/17: Compl:0%->25%; 19/6/17: Compl:25%->80%; 19/9/17: Compl:80%->100% |  | 74 | 38 |  |  | 2016-12-20 | 2017-09-19
833 | 740274 | Perf. part: E-UTRA 700MHz in Europe for Broadband-PPDR | LTE700_Europe_PPDR-Perf | 2 | Rel-15 | R4 | 2016-12-15 | 2017-03-15 | 0% | RP-170212 |  | Airbus |  | 21/3/17: CD:Thu 15/06/17->Wed 15/03/17 |  | 74 | 38 |  |  | 2016-12-20 | 2017-03-21
834 | 770066 | UE Conformance Test Aspects - E-UTRA 700MHz in Europe for Broadband-PPDR | LTE700_Europe_PPDR-UEConTest | 2 | Rel-15 | R5 | 2017-09-15 | 2018-03-15 | 100% | RP-180529 |  | Airbus |  | ; 8/1/18: Compl:0%->64%27/3/18: Compl:64%->100%; |  | 77 | 39 |  |  | 2017-09-19 | 2018-03-27
835 | 740075 | FDD operating band in the L-band for LTE | LTE_FDD_L_Band | 1 | Rel-15 |  | 2016-12-15 | 2018-09-14 | 87% | RP-162536 |  | NTT DOCOMO |  | 21/3/17: 36.751 added; | 36.751 | 74 | 38 |  |  | 2016-12-20 | 2017-03-21
836 | 740175 | Core part: FDD operating band in the L-band for LTE | LTE_FDD_L_Band-Core | 2 | Rel-15 | R4 | 2016-12-15 | 2017-09-15 | 100% | RP-171403 |  | NTT DOCOMO |  | 21/3/17: Compl:0%->50%; 19/6/17: Compl:50%->99%; 19/9/17: Compl:99%->100% |  | 74 | 38 |  |  | 2016-12-20 | 2017-09-19
837 | 740275 | Perf. part: FDD operating band in the L-band for LTE | LTE_FDD_L_Band-Perf | 2 | Rel-15 | R4 | 2016-12-15 | 2017-09-15 | 100% | RP-171403 |  | NTT DOCOMO |  | 19/6/17: Compl:0%->99%19/6/17: CD:Thu 15/06/19/9/17: Compl:99%->100% |  | 74 | 38 |  |  | 2016-12-20 | 2017-09-19
838 | 780062 | UE Conformance Test Aspects - FDD operating band in the L-band for LTE | LTE_FDD_L_band-UEConTest | 2 | Rel-15 | R5 | 2017-12-15 | 2018-09-14 | 60% | RP-180145 |  | NTT DOCOMO |  | tested: REL-15 WI LTE_FDD_L_Band-Core27/3/18: Compl: ; |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
839 | 740076 | LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20 | LTE_SDL_1500ext | 1 | Rel-15 |  | 2016-12-15 | 2017-09-15 | 100% | RP-162556 |  | Qualcomm |  | 21/3/17: 36.934 added;; 21/3/17: 36.753 added; | 36.934; 36.753 | 74 | 38 |  |  | 2016-12-20 | 2017-03-21
840 | 740176 | Core part: LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20 | LTE_SDL_1500ext-Core | 2 | Rel-15 | R4 | 2016-12-15 | 2017-09-15 | 100% | RP-171389 |  | Qualcomm |  | 21/3/17: Compl:0%->20%19/6/17: Compl:20%->50%;19/9/17: Compl:50%->100% |  | 74 | 38 |  |  | 2016-12-20 | 2017-09-19
841 | 740276 | Perf. part: LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20 | LTE_SDL_1500ext-Perf | 2 | Rel-15 | R4 | 2017-03-17 | 2017-09-15 | 100% | RP-171389 |  | Qualcomm |  | ; 19/6/17: CD:Thu 15/06/17->Fri 15/09/17 19/9/17: Compl:0%->100% |  | 74 | 38 |  |  | 2016-12-20 | 2017-09-19
842 | 740077 | Add UE Power Class 2 to band 41 intra-band contiguous LTE CA | LTE_CA_C_B41_PC2 | 1 | Rel-15 |  | 2016-12-15 | 2018-12-14 | 53% | RP-162571 |  | Sprint |  |  |  | 74 | 38 |  |  | 2016-12-20 | 2016-12-20
843 | 740177 | Core part: Add UE Power Class 2 to band 41 intra-band contiguous LTE CA | LTE_CA_C_B41_PC2-Core | 2 | Rel-15 | R4 | 2016-12-15 | 2017-12-15 | 100% | RP-172295 |  | Sprint |  | 21/3/17: Compl:0%->5%; 19/6/17: Compl:5%->50%; 19/9/17: Compl:50%->90%; 8/1/18: Compl:90%->100%; |  | 74 | 38 |  |  | 2016-12-20 | 2018-01-08
844 | 780065 | UE Conformance Test Aspects - Add UE Power Class 2 to band 41 intra-band contiguous LTE CA | LTE_CA_C_B41_PC2-UEConTest | 2 | Rel-15 | R5 | 2017-12-15 | 2018-12-14 | 5% | RP-172698 |  | Sprint |  | tested: REL-15 WI LTE_CA_C_B41_PC2-Core; 27/3/18: Co ; |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
845 | 730081 | Addition of Power Class 1 UE to bands B3/B20/B28 for LTE | LTE_HPUE_B3_B20_B28 | 1 | Rel-15 |  | 2016-09-15 | 2017-09-15 | 100% | RP-161871 |  | Motorola Solutions |  |  |  | 73 | 37 |  |  | 2016-09-26 | 2016-09-26
846 | 730181 | Core part: Addition of Power Class 1 UE to bands B3/B20/B28 for LTE | LTE_HPUE_B3_B20_B28-Core | 2 | Rel-15 | R4 | 2016-09-15 | 2017-09-15 | 100% | RP-171757 |  | Motorola Solutions |  | ; 20/12/16: Compl:0%->15%; 20/12/16: CD:Wed 15/03/17->Thu 15/06/1721/3/17: Compl:15%->70%19/6/17: Compl:70%->99%19/9/17: Compl:99%->100%; |  | 73 | 37 |  |  | 2016-09-26 | 2017-09-19
847 | 740080 | TDD operating band in the L-band for LTE | LTE_TDD_L_Band | 1 | Rel-15 |  | 2016-12-15 | 2017-09-15 | 100% | RP-170304 |  | Huawei |  | 21/3/17: 36.753 added;; 14/9/17: WID:RP-162557->RP-170304 | 36.753 | 74 | 38 |  |  | 2016-12-20 | 2017-09-14
848 | 740180 | Core part: TDD operating band in the L-band for LTE | LTE_TDD_L_Band-Core | 2 | Rel-15 | R4 | 2016-12-15 | 2017-09-15 | 100% | RP-170304 |  | Huawei |  | 21/3/17: Compl:0%->15%; 19/6/17: Compl:15%->70%; 19/9/17: Compl:70%->100% |  | 74 | 38 |  |  | 2016-12-20 | 2017-09-19
849 | 740280 | Perf. part: TDD operating band in the L-band for LTE | LTE_TDD_L_Band-Perf | 2 | Rel-15 | R4 | 2017-03-17 | 2017-09-15 | 100% | RP-170304 |  | Huawei |  | 21/3/17: WID: RP-162557->RP-170304; 19/6/17: CD:Thu 15/06/17->Fri 15/09/17; 19/9/17: Compl:0%->100% |  | 74 | 38 |  |  | 2016-12-20 | 2017-09-19
850 | 750060 | Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE | feCOMP_LTE | 1 | Rel-15 | R1 | 2017-03-15 | 2018-09-14 | 99% | RP-171031 |  | Intel |  | follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #75; 14/9/17: WID:RP-170750->RP-171031 |  | 75 | 38 |  |  | 2017-03-21 | 2017-09-14
851 | 750160 | Core part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE | feCOMP_LTE-Core | 2 | Rel-15 | R1 | 2017-03-15 | 2018-09-14 | 99% | RP-180584 | RP-180318 | Intel |  | follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #75; 19/6/17: Compl:0%->70%; 19/6/17: CD:Fri 15/09/ 19/9/17: Compl:70%->90%; 27/3/18: Compl:90%->99%; 27/3/18: CD:Thu 15/03/18->Fri ; 27/6/18: CD:Fri |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
852 | 750260 | Perf. part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE | feCOMP_LTE-Perf | 2 | Rel-15 | R4 | 2017-03-15 | 2018-06-15 | 100% | RP-180584 |  | Intel |  | follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #7519/6/17: WID: RP-170750->RP-171031; 8/1/18: Compl:0%->65%; 8/1/18: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:65%->80%27/3/ ; 27/6/18: Compl:80%->100% |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
853 | 750063 | UE Positioning Accuracy Enhancements for LTE | LCS_LTE_acc_enh | 1 | Rel-15 | R2 | 2017-03-15 | 2018-09-14 | 99% | RP-171508 |  | Nokia |  | 14/9/17: WID:RP-170813->RP-171508 |  | 75 | 38 |  |  | 2017-03-21 | 2017-09-14
854 | 750163 | Core part: UE Positioning Accuracy Enhancements for LTE | LCS_LTE_acc_enh-Core | 2 | Rel-15 | R2 | 2017-03-15 | 2018-09-14 | 99% | RP-181298 | RP-180947 | Nokia |  | ; 19/6/17: Compl:0%->10%; 19/6/17: CD:Fri 15/12/17->Fri 15/06/18 19/9/17: Compl:10%->20%; 8/1/18: Compl:20%->40%; 8/1/18: WID: RP-171508->RP-17231327/3/18: Compl:40%->50%; 27/6/18: Compl:50%->99%; |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
855 | 750263 | Perf. part: UE Positioning Accuracy Enhancements for LTE | LCS_LTE_acc_enh-Perf | 2 | Rel-15 | R4 | 2017-03-15 | 2018-06-15 | 100% | RP-181298 |  | Nokia |  | ; 19/6/17: WID: RP-170813->RP-171508; 8/1/18: Compl:0%->30%; 8/1/18: WID: RP-171508->RP-172313; 27/6/18: Compl:30%->100%; 27/6/18: WID: RP-17231 |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
856 | 750064 | Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL | LTE_1024QAM_DL | 1 | Rel-15 | R1 | 2016-09-14 | 2018-12-14 | 99% | RP-171067 |  | Huawei |  | 14/9/17: WID:RP-170838->RP-171067 |  | 75 | 38 |  |  | 2017-03-21 | 2017-09-14
857 | 750164 | Core part: Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL | LTE_1024QAM_DL-Core | 2 | Rel-15 | R1 | 2017-03-15 | 2018-09-14 | 99% | RP-171740 | RP-180854 | Huawei |  | ; 19/6/17: Compl:0%->20%; 19/6/17: CD:Sat 15/12/18->Thu 15/03/18 19/6/17: FCD:03/18->06/18; 12/7/17: 36.783 added;19/9/17: Compl:20%->40%; 8/1/18: Compl:40%->85%27/3/18: Compl:85%->99% | 36.783 | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
858 | 750264 | Perf. part: Enhancements for high capacity stationary wireless link and introduction of 1024 QAM for LTE DL | LTE_1024QAM_DL-Perf | 2 | Rel-15 | R4 | 2016-09-14 | 2018-12-14 | 100% | RP-171740 |  | Huawei |  | ; 19/6/17: CD:Sat 15/12/18->Fri 15/06/18; 19/6/17: WID: RP-170838->RP-171067 19/9/17: WID: RP-171067->RP-17173827/3/18: Compl:0%->25%; 27/6/18: Compl:25%->50%; 16/1/19: 50%->100 |  | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
859 | 750065 | Enhancements to LTE operation in unlicensed spectrum | LTE_unlic | 1 | Rel-15 | R1 | 2017-03-15 | 2018-12-15 | 99% | RP-180402 |  | Nokia |  | note: The is actually a further LAA enhancement |  | 75 | 38 |  |  | 2017-03-21 | 2017-03-21
860 | 750165 | Core part: Enhancements to LTE operation in unlicensed spectrum | LTE_unlic-Core | 2 | Rel-15 | R1 | 2017-03-15 | 2018-09-14 | 99% | RP-180402 | RP-180948 | Nokia |  | note: The is actually a further LAA enhancement; 19/6/17: Compl:0%->15%; 19/6/17: CD:Fri 15 19/9/17: Compl:15%->30%; 8/1/18: Compl:30%->65%; 27/3/18: Compl:65%->85% 27/3/18: 37.107 added;; | 37.107; 37.106 | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
861 | 750265 | Perf. part: Enhancements to LTE operation in unlicensed spectrum | LTE_unlic-Perf | 2 | Rel-15 | R4 | 2017-12-14 | 2018-12-15 | 100% | RP-180402 |  | Nokia |  | 19/6/17: CD:Thu 15/03/18->Sat 15/12/18; 8/1/18: WID: RP-170848->RP-17284127/3/18: WID: RP-172841->RP-180402; 16/1/19: 0%->100 |  | 75 | 38 |  |  | 2017-03-21 | 2019-01-16
862 | 750069 | Further video enhancements for LTE | LTE_ViLTE_enh2 | 1 | Rel-15 | R2 | 2017-03-15 | 2018-09-14 | 99% | RP-170781 |  | CMCC |  | no Perf. part; compare REL-14 WI LTE_VoLTE_ViLTE_enh |  | 75 | 38 |  |  | 2017-03-21 | 2017-03-21
863 | 750169 | Core part: Further video enhancements for LTE | LTE_ViLTE_enh2-Core | 2 | Rel-15 | R2 | 2017-03-15 | 2018-09-14 | 99% | RP-172726 | RP-172381 | CMCC |  | no Perf. part; compare REL-14 WI LTE_VoLTE_ViLTE_enh19/6/17: Compl:0%->15%19/6/17: W 19/9/17: Compl:15%->35%; 8/1/18: Compl:35%->99%; ; 27/6/18: CD:Fri 15/06/18->Sat 15/09/18 |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
864 | 750070 | Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN | LTE_QMC_Streaming | 1 | Rel-15 | R2 | 2017-03-15 | 2018-12-14 | 68% | RP-170786 |  | China Unicom |  | compare REL-14 WI UMTS_QMC_Streaming-Core |  | 75 | 38 |  |  | 2017-03-21 | 2017-03-21
865 | 750170 | Core part:Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN | LTE_QMC_Streaming-Core | 2 | Rel-15 | R2 | 2017-03-15 | 2018-09-14 | 99% | RP-170956 | RP-172192 | China Unicom |  | compare REL-14 WI UMTS_QMC_Streaming-Core; 19/6/17: Compl:0%->25%; 19/6/17: WID: RP- 19/9/17: Compl:25%->45%; 8/1/18: Compl:45%->99%; ; 27/6/18: CD:Fri 15/06/18->Sat 15/09/18 |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
866 | 790051 | UE Conformance Test Aspects - Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN | LTE_QMC_Streaming-UEConTest | 2 | Rel-15 | R5 | 2018-03-15 | 2018-12-14 | 5% | RP-180215 |  | China Unicom |  | tested: REL-15 WI LTE_QMC_Streaming-Core; WI code to be used: LTE_QMC_Streaming-UEConTest; |  | 79 | 40 |  |  | 2018-03-27 | 2018-06-27
867 | 750071 | Enhancing LTE CA Utilization | LTE_euCA | 1 | Rel-15 | R2 | 2017-03-15 | 2019-12-15 | 69% | RP-170805 |  | Nokia |  |  |  | 75 | 38 |  |  | 2017-03-21 | 2017-03-21
868 | 750171 | Core part: Enhancing LTE CA Utilization | LTE_euCA-Core | 2 | Rel-15 | R2 | 2017-03-15 | 2018-09-14 | 90% | RP-180561 | RP-181069 | Nokia |  | 19/9/17: Compl:0%->22%; 8/1/18: Compl:22%->40%; 16/3/18: FCD:12/17->06/1827/3/18: Compl:40%->60%27/3/18: WID: RP-170805->RP-180561; 27/6/18: Compl:60%->90%; |  | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
869 | 750271 | Perf. part: Enhancing LTE CA Utilization | LTE_euCA-Perf | 2 | Rel-15 | R4 | 2017-09-13 | 2018-12-14 | 100% | RP-180561 |  | Nokia |  | 16/3/18: FCD:12/17->12/18; 27/3/18: WID: RP-170805->RP-180561; 27/6/18: Compl:0%->20%; 26/3/19: 20%->100 |  | 75 | 38 |  |  | 2017-03-21 | 2019-03-26
870 | 820066 | UE Conformance Test Aspects - Enhancing LTE CA Utilization | LTE_euCA-UEConTest | 2 | Rel-15 | R5 | 2018-12-15 | 2019-12-15 | 0% | RP-182619 |  | Nokia |  | tested: REL-15 WI LTE_euCA-Core | [5 empty] | 2019-01-16 | NA
871 | 750073 | 450 MHz Band for LTE in Region 3 | LTE450_Reg3 | 1 | Rel-15 | R4 | 2017-03-15 | 2019-03-15 | 62% | RP-170952 |  | China Unicom |  | 14/9/17: WID:RP-170159->RP-170952 |  | 75 | 38 |  |  | 2017-03-21 | 2017-09-14
872 | 750173 | Core part: 450 MHz Band for LTE in Region 3 | LTE450_Reg3-Core | 2 | Rel-15 | R4 | 2017-03-15 | 2017-12-15 | 100% | RP-170952 |  | China Unicom |  | ; 19/6/17: Compl:0%->30%; 19 12/7/17: 36.759 added;; 19/9/17: Compl:30%->80%; 8/1/18: Compl:80%->100% | 36.759 | 75 | 38 |  |  | 2017-03-21 | 2018-01-08
873 | 750273 | Perf. part: 450 MHz Band for LTE in Region 3 | LTE450_Reg3-Perf | 2 | Rel-15 | R4 | 2017-03-15 | 2017-12-15 | 100% | RP-170952 |  | China Unicom |  | ; 19/6/17: WID: RP-170159->RP-170952; 8/1/18: Compl:0%->100% |  | 75 | 38 |  |  | 2017-03-21 | 2018-01-08
874 | 790058 | UE Conformance Test Aspects - 450 MHz Band for LTE in Region 3 | LTE450_Reg3-UEConTest | 2 | Rel-15 | R5 | 2018-03-15 | 2019-03-15 | 5% | RP-181040 |  | China Unicom, Shi Yu |  | ; 27/6/18: Compl:0%->5%; | 34.121-1; 36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-2; 36.523-3; 37.571-1; 36.905 | 79 | 40 |  |  | 2018-04-19 | 2018-06-27
875 | 750074 | US 600 MHz Band for LTE | LTE600_US | 1 | Rel-15 | R4 | 2017-03-15 | 2017-12-15 | 100% | RP-170740 |  | Ericsson |  |  |  | 75 | 38 |  |  | 2017-03-21 | 2017-03-21
876 | 750174 | Core part: US 600 MHz Band for LTE | LTE600_US-Core | 2 | Rel-15 | R4 | 2017-03-15 | 2017-09-15 | 100% | RP-171142 |  | Ericsson |  | ; 19/6/17: Compl:0%->95%; 19 12/7/17: 36.755 added;19/9/17: Compl:95%->100% | 36.755 | 75 | 38 |  |  | 2017-03-21 | 2017-09-19
877 | 750274 | Perf. part: US 600 MHz Band for LTE | LTE600_US-Perf | 2 | Rel-15 | R4 | 2017-03-15 | 2017-09-15 | 100% | RP-171142 |  | Ericsson |  | ; 19/6/17: Compl:0%->95%; 19 19/9/17: Compl:95%->100% |  | 75 | 38 |  |  | 2017-03-21 | 2017-09-19
878 | 770060 | UE Conformance Test Aspects - US 600 MHz Band for LTE (Band 71) | LTE600_US-UEConTest | 2 | Rel-15 | R5 | 2017-09-15 | 2017-12-15 | 100% | RP-172195 |  | Dish Network |  | ; 8/1/18: Compl:0%->100%; |  | 77 | 39 |  |  | 2017-09-19 | 2018-01-08
879 | 750076 | LAA/eLAA for the CBRS 3.5GHz band in the United States | LTE_3550_CBRS_US_LAA | 1 | Rel-15 | R4 | 2017-03-15 | 2017-12-15 | 100% | RP-170804 |  | AT&T |  | compare REL-14 WI LTE_TDD_3550_CBRS_US; related to LTE band 48, intending a new band definition; includes 2DL/2UL CA with B2 Acronym changed, was "LTE_TDD_3550_CBRS_US_LAA" |  | 75 | 38 |  |  | 2017-03-21 | 2017-06-19
880 | 750176 | Core part: LAA/eLAA for the CBRS 3.5GHz band in the United States | LTE_3550_CBRS_US_LAA-Core | 2 | Rel-15 | R4 | 2017-03-15 | 2017-12-15 | 100% | RP-172626 |  | AT&T |  | compare REL-14 WI LTE_TDD_3550_CBRS_US; related to LTE band 48, intending a new band definition; includes 2DL/2UL CA with B2;19/6/17: Com; Acronym changed, was "LTE_TDD_3550_CBRS_US_LAA-Core"; 12/7/17: 36.790 added;; | 36.79 | 75 | 38 |  |  | 2017-03-21 | 2018-01-08
881 | 750276 | Perf. part: LAA/eLAA for the CBRS 3.5GHz band in the United States | LTE_3550_CBRS_US_LAA-Perf | 2 | Rel-15 | R4 | 2017-03-15 | 2017-12-15 | 100% | RP-172626 |  | AT&T |  | compare REL-14 WI LTE_TDD_3550_CBRS_US; related to LTE band 48, intending a new band definition; includes 2DL/2UL CA with B2; 19/6/17: C Acronym changed, was "LTE_TDD_3550_CBRS_US_LAA-Perf"; |  | 75 | 38 |  |  | 2017-03-21 | 2018-01-08
882 | 760097 | Introduction new band support for 4Rx antenna ports for LTE for REL-15 | LTE_4Rx_AP_DL_bands_R15 | 1 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-171131 |  | Huawei |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
883 | 760197 | Core part: Introduction new band support for 4Rx antenna ports for LTE for REL-15 | LTE_4Rx_AP_DL_bands_R15-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180073 |  | Huawei |  | 19/9/17: Compl:0%->99%; 8/1/18: WID: RP-171131->RP-17234727/3/18: Compl:99%->90% ; 27/6/18: Compl:90%->100% |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
884 | 760297 | Perf. part: Introduction new band support for 4Rx antenna ports for LTE for REL-15 | LTE_4Rx_AP_DL_bands_R15-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180073 |  | Huawei |  | ; 8/1/18: WID: RP-171131->RP-172347; 27/3/18: WID: RP-172347->RP-180073; 27/6/18: Compl:0%->100% |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
885 | 760098 | Addition of band 28 and 40 to LTE MTC cat.0 | LC_MTC_LTE_cat0_B28_B40 | 1 | Rel-15 | R4 | 2017-06-15 | 2017-09-15 | 100% | RP-171132 |  | Huawei |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
886 | 760198 | Core part: Addition of band 28 and 40 to LTE MTC cat.0 | LC_MTC_LTE_cat0_B28_B40-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2017-09-15 | 100% | RP-171132 |  | Huawei |  | 19/9/17: Compl:0%->100% |  | 76 | 39 |  |  | 2017-06-16 | 2017-09-19
887 | 760099 | LTE Advanced high power TDD UE (power class 2) for Rel-15 | LTE_TDD_HPUE_R15 | 1 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-171492 |  | Huawei |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
888 | 760199 | Core part: LTE Advanced high power TDD UE (power class 2) for Rel-15 | LTE_TDD_HPUE_R15-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-171755 |  | Huawei |  | 19/9/17: Compl:0%->10%; 15/12/17: 36.760 added;; 8/1/18: Compl:10%->40%27/3/18: Compl:40%->99%; 27/6/18: Comp | 36.76 | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
889 | 761000 | New LTE band for 3.3-3.4 GHz for Africa | LTE_TDD_3300_Africa | 1 | Rel-15 | R4 | 2017-06-15 | 2018-03-15 | 100% | RP-171506 |  | Huawei |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
890 | 761100 | Core part: New LTE band for 3.3-3.4 GHz for Africa | LTE_TDD_3300_Africa-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-03-15 | 100% | RP-180247 |  | Huawei |  | 12/7/17: 36.758 added;19/9/17: Compl:0%->10%; 8/1/18: Compl:10%->70%27/3/18: Compl:70%->100%; | 36.758 | 76 | 39 |  |  | 2017-06-16 | 2018-03-27
891 | 761200 | Perf. part: New LTE band for 3.3-3.4 GHz for Africa | LTE_TDD_3300_Africa-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-03-15 | 100% | RP-180247 |  | Huawei |  | ; 19/9/17: WID: RP-171506->RP-171759; 27/3/18: Compl:0%->100%; |  | 76 | 39 |  |  | 2017-06-16 | 2018-03-27
892 | 761001 | UE requirements for network-based CRS interference mitigation for LTE | LTE_NW_CRS_IM | 1 | Rel-15 | R4 | 2017-06-15 | 2018-12-15 | 93% | RP-171408 |  | Ericsson |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
893 | 761101 | Core part: UE requirements for network-based CRS interference mitigation for LTE | LTE_NW_CRS_IM-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-09-14 | 85% | RP-181315 |  | Ericsson |  | ; 19/9/17: Compl:0%->15%; 8/1/18: Compl:15%->50%27/3/18: Compl:50%->70%; 27/6/18: Compl:70%->85% |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
894 | 761201 | Perf. part: UE requirements for network-based CRS interference mitigation for LTE | LTE_NW_CRS_IM-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-12-15 | 100% | RP-181315 |  | Ericsson |  | ; 27/6/18: WID: RP-171408->RP-181315; 16/1/19: 0%->100 |  | 76 | 39 |  |  | 2017-06-16 | 2019-01-16
895 | 780068 | Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT) | LTE_MDT_BT_WLAN | 1 | Rel-15 | R2 | 2017-12-15 | 2019-12-15 | 41% | RP-172820 |  | CMCC |  | MDT = Minimization of Drive Tests; no Perf. part; may have SA5 impact |  | 78 | 40 |  |  | 2018-01-08 | 2018-01-08
896 | 780168 | Core part: Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT) | LTE_MDT_BT_WLAN-Core | 2 | Rel-15 | R2 | 2017-12-15 | 2018-09-14 | 95% | RP-180306 | RP-180867 | CMCC |  | MDT = Minimization of Drive Tests; no Perf. part; may have SA5 impact27/3/18: Compl:0%->30%2 ; 27/6/18: Compl:30%->95% |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
897 | 820065 | UE Conformance Test Aspects - Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT) | LTE_MDT_BT_WLAN-UEConTest | 2 | Rel-15 | R5 | 2018-12-15 | 2019-12-15 | 0% | RP-182509 |  | CMCC |  | tested: REL-15 WI LTE_MDT_BT_WLAN-Core | [5 empty] | 2019-01-16 | NA
898 | 780069 | Enhanced LTE Support for Aerial Vehicles | LTE_Aerial | 1 | Rel-15 | R2 | 2017-03-15 | 2019-06-19 | 74% | RP-172826 |  | Ericsson |  | follow-up WI of REL-15 SI FS_LTE_Aerial; no Perf. part |  | 78 | 40 |  |  | 2018-01-08 | 2018-01-08
899 | 750042 | Study on enhanced LTE Support for Aerial Vehicles | FS_LTE_Aerial | 2 | Rel-15 | R2 | 2017-03-15 | 2017-12-15 | 100% | RP-171050 |  | NTT DOCOMO |  | TR 36.7XX19/6/17: Compl:0%->15%; 30/6/17: 36.777 added;; 19/9/17: Compl:15%->30%; 8/1/18: Compl:30%->100% | 36.777 | 75 | 38 |  |  | 2017-03-21 | 2018-01-08
900 | 780169 | Core part: Enhanced LTE Support for Aerial Vehicles | LTE_Aerial-Core | 2 | Rel-15 | R2 | 2017-12-15 | 2018-09-14 | 99% | RP-181310 | RP-181045 | Ericsson |  | follow-up WI of REL-15 SI FS_LTE_Aerial; no Perf. part; 27/3/18: Compl:0%->15%; 27/6/18: Compl:15%->99%; |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
901 | 820062 | UE Conformance Test Aspects - Enhanced LTE Support for Aerial Vehicles | LTE_Aerial-UEConTest | 2 | Rel-15 | R5 | 2018-12-15 | 2019-06-19 | 0% | RP-182324 |  | NTT DOCOMO |  | tested: REL-15 WI LTE_Aerial-Core | [5 empty] | 2019-01-16 | NA
902 | 780071 | Separation of CP and UP for Split Option 2 of NR | NR_CPUP_Split | 1 | Rel-15 | R3 | 2017-12-15 | 2018-06-15 | 100% | RP-172831 |  | Ericsson |  | follow-up WI of REL-15 SI FS_NR_CPUP_Split; introduction of E1 interface |  | 78 | 40 |  |  | 2018-01-08 | 2018-01-08
903 | 780171 | Core part: Separation of CP and UP for Split Option 2 of NR | NR_CPUP_Split-Core | 2 | Rel-15 | R3 | 2017-12-15 | 2018-06-15 | 100% | RP-180326 | RP-181149 | Ericsson |  | follow-up WI of REL-15 SI FS_NR_CPUP_Split; introduction of E1 interface. 30/1/18: acronym updated27/3/18: Compl:0%->30%27/3/18: WID: RP-172831->RP-180326; 27/6/18: Compl:30%->100%; 27/6/18: Stat Rep: ->RP-181149 |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
904 | 780072 | UE requirements for LTE DL 8Rx antenna ports | LTE_8Rx_AP_DL | 1 | Rel-15 | R4 | 2017-12-15 | 2018-12-14 | 100% | RP-172842 |  | Huawei |  | follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL |  | 78 | 40 |  |  | 2018-01-08 | 2018-01-08
905 | 780172 | Core part: UE requirements for LTE DL 8Rx antenna ports | LTE_8Rx_AP_DL-Core | 2 | Rel-15 | R4 | 2017-12-15 | 2018-06-15 | 100% | RP-180960 | RP-180959 | Huawei |  | follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL27/3/18: Compl:0%->40%; 27/6/18: Compl:40%->100% |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
906 | 780272 | Perf. part: UE requirements for LTE DL 8Rx antenna ports | LTE_8Rx_AP_DL-Perf | 2 | Rel-15 | R4 | 2017-12-15 | 2018-12-14 | 100% | RP-180960 |  | Huawei |  | follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL; 27/6/18: Compl:0%->30%; 26/3/19: 30%->100 |  | 78 | 40 |  |  | 2018-01-08 | 2019-03-26
907 | 780073 | ProSe Support for Band 72 in LTE | LTE450_B72_Europe_ProSe | 1 | Rel-15 | R4 | 2017-12-15 | 2018-12-14 | 100% | RP-182441 |  | Airbus |  | This WI was opened, a RAN4 CR RP-172572 was approved and the WI was completed all at RAN #78; compare REL-15 WI LTE450_Europe_PPDR-Core; 16/1/19: WID:RP-172568->RP-182441 |  | 78 | 40 |  |  | 2018-01-08 | 2019-01-16
908 | 780173 | Core part: ProSe Support for Band 72 in LTE | LTE450_B72_Europe_ProSe-Core | 2 | Rel-15 | R4 | 2017-12-15 | 2017-12-15 | 100% | RP-182441 |  | Airbus |  | This WI was opened, a RAN4 CR RP-172572 was approved and the WI was completed all at RAN #78; compare REL-15 WI LTE450_Europe_PPDR-Core; |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
909 | 810063 | UE Conformance Test Aspects - ProSe Support for Band 72 in LTE | LTE450_B72_Europe_ProSe-UEConTest | 2 | Rel-15 | R5 | 2018-09-14 | 2018-12-14 | 100% | RP-181630 |  | Airbus |  | 16/1/19: 0%->100 |  | 81 | 41 |  |  | 2018-09-25 | 2019-01-16
910 | 780074 | LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5 | LTE_CA_R15_xDL1UL | 1 | Rel-15 | R4 | 2017-12-15 | 2018-12-14 | 100% | RP-172839 |  | Qualcomm |  | basket CA WI; TR 36.715-00-01 |  | 78 | 40 |  |  | 2018-01-08 | 2018-01-08
911 | 780174 | Core part:LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5 | LTE_CA_R15_xDL1UL-Core | 2 | Rel-15 | R4 | 2017-12-15 | 2018-06-15 | 100% | RP-181442 |  | Qualcomm |  | basket CA WI; TR 36.715-00-01; 27/3/18: Compl:0%->10%; 27/3/18: 36.715-00-01 added;; 27/6/18: Compl:10%->100%; | 36.715-00-01 | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
912 | 780274 | Perf. part:LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5 | LTE_CA_R15_xDL1UL-Perf | 2 | Rel-15 | R4 | 2017-12-15 | 2018-12-14 | 100% | RP-181442 |  | Qualcomm |  | basket CA WI27/3/18: CD:Sat 15/12/18->Fri 15/06/18 ; 27/6/18: Compl:0%->50%;; 16/1/19: 50%->100 |  | 78 | 40 |  |  | 2018-01-08 | 2019-01-16
913 | 761002 | Performance requirements of interference cancellation receiver for LTE BS | LTE_IC_BS | 1 | Rel-15 | R4 | 2017-06-15 | 2017-09-15 | 100% | RP-171411 |  | China Telecom |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
914 | 761202 | Perf. part: Performance requirements of interference cancellation receiver for LTE BS | LTE_IC_BS-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2017-09-15 | 100% | RP-171411 |  | China Telecom |  | ; 19/9/17: Compl:0%->100% |  | 76 | 39 |  |  | 2017-06-16 | 2017-09-19
915 | 761003 | LTE CRS-Interference Mitigation performance requirements for single RX chain UEs | LTE_1RX_CRS_IM | 1 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-171465 |  | Intel |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
916 | 761203 | Perf. part: LTE CRS-Interference Mitigation performance requirements for single RX chain UEs | LTE_1RX_CRS_IM-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-N1122 |  | Intel |  | ; 19/9/17: Compl:0%->20%; 19/9/17: WID: RP-171465->RP-171831; 8/1/18: Compl:20%->60%; 27/3/18: Compl:60%->85%; 27/6/18: Compl:85%->100% |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
917 | 760090 | LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R15_intra | 1 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-170962 |  | Ericsson |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
918 | 760190 | Core part: LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R15_intra-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180800 |  | Ericsson |  | 12/7/17: 36.715-00-00 added;; 19/9/17: Compl:0%->25% 8/1/18: Compl:25%->70%;27/3/18: Compl:70%->67%; ; 27/6/18: Compl:67%->100%; | 36.715-00-00 | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
919 | 760290 | Perf. part: LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R15_intra-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180800 |  | Ericsson |  | 19/9/17: Compl:0%->25%; 8/1/18: Compl:25%->70%; 8/1/18:27/3/18: Compl:70%->67%; ; 27/6/18: Compl:67%->100%; |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
920 | 760091 | LTE Advanced inter-band CA Rel-15 for 2DL/1UL | LTE_CA_R15_2DL1UL | 1 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-171026 |  | Qualcomm |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
921 | 760191 | Core part:LTE Advanced inter-band CA Rel-15 for 2DL/1UL | LTE_CA_R15_2DL1UL-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-181013 |  | Qualcomm |  | 12/7/17: 36.715-02-01 added;19/9/17: Compl:0%->20%; 8/1/18: Compl:20%->30%; 27/3/18: Compl:30%->40%; ; 27/6/18: Compl:40%->100%; | 36.715-02-01 | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
922 | 760291 | Perf. part:LTE Advanced inter-band CA Rel-15 for 2DL/1UL | LTE_CA_R15_2DL1UL-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-181013 |  | Qualcomm |  | ; 19/9/17: Compl:0%->20% 8/1/18: Compl:20%->30%;27/3/18: Compl:30%->40% ; 27/6/18: Compl:40%->100%; |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
923 | 760092 | LTE Advanced inter-band CA Rel-15 for 3DL/1UL | LTE_CA_R15_3DL1UL | 1 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-171126 |  | Huawei |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
924 | 760192 | Core part:LTE Advanced inter-band CA Rel-15 for 3DL/1UL | LTE_CA_R15_3DL1UL-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180955 |  | Huawei |  | 12/7/17: 36.715-03-01 added;; 19/9/17: Compl:0%->20%; 8/1/18: Compl:20%->40%; 27/3/18: Compl:40%->65%; ; 27/6/18: Compl:65%->100%; | 36.715-03-01 | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
925 | 760292 | Perf. part:LTE Advanced inter-band CA Rel-15 for 3DL/1UL | LTE_CA_R15_3DL1UL-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180955 |  | Huawei |  | ; 19/9/17: Compl:0%->20%; 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->65%; ; 27/6/18: Compl:65%->100%; |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
926 | 760093 | LTE Advanced inter-band CA Rel-15 for 4DL/1UL | LTE_CA_R15_4DL1UL | 1 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-170963 |  | Ericsson |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
927 | 760193 | Core part:LTE Advanced inter-band CA Rel-15 for 4DL/1UL | LTE_CA_R15_4DL1UL-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180801 |  | Ericsson |  | 12/7/17: 36.715-04-01 added;; 19/9/17: Compl:0%->54% 8/1/18: Compl:54%->65%;27/3/18: Compl:65%->63% ; 27/6/18: Compl:63%->100%; | 36.715-04-01 | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
928 | 760293 | Perf. part:LTE Advanced inter-band CA Rel-15 for 4DL/1UL | LTE_CA_R15_4DL1UL-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180801 |  | Ericsson |  | 19/9/17: Compl:0%->54%; 8/1/18: Compl:54%->65%; 27/3/18: Compl:65%->63% ; 27/6/18: Compl:63%->100%; |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
929 | 760094 | LTE Advanced inter-band CA Rel-15 for 5DL/1UL | LTE_CA_R15_5DL1UL | 1 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-171466 |  | Nokia |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
930 | 760194 | Core part:LTE Advanced inter-band CA Rel-15 for 5DL/1UL | LTE_CA_R15_5DL1UL-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180743 |  | Nokia |  | 12/7/17: 36.715-05-01 added;19/9/17: Compl:0%->20%; 8/1/18: Compl:20%->50%;27/3/18: Compl:50%->75% ; 27/6/18: Compl:75%->100%; | 36.715-05-01 | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
931 | 760294 | Perf. part:LTE Advanced inter-band CA Rel-15 for 5DL/1UL | LTE_CA_R15_5DL1UL-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180743 |  | Nokia |  | ; 19/9/17: Compl:0%->20% 8/1/18: Compl:20%->50%; 27/3/18: Compl:50%->75%; ; 27/6/18: Compl:75%->100%; |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
932 | 760095 | LTE Advanced inter-band CA Rel-15 for 2DL/2UL | LTE_CA_R15_2DL2UL | 1 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-171127 |  | Huawei |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
933 | 760195 | Core part:LTE Advanced inter-band CA Rel-15 for 2DL/2UL | LTE_CA_R15_2DL2UL-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180957 |  | Huawei |  | 12/7/17: 36.715-02-02 added;; 19/9/17: Compl:0%->20%; 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->60%; 27/6/18: Compl:60% | 36.715-02-02 | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
934 | 760295 | Perf. part:LTE Advanced inter-band CA Rel-15 for 2DL/2UL | LTE_CA_R15_2DL2UL-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180957 |  | Huawei |  | ; 19/9/17: Compl:0%->20%; 8/1/18: Compl:20%->40%;27/3/18: Compl:40%->60%; 27/6/18: Compl:60%->100% |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
935 | 760096 | LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5 | LTE_CA_R15_xDL2UL | 1 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-170946 |  | LG Electronics |  |  |  | 76 | 39 |  |  | 2017-06-19 | NA
936 | 760196 | Core part:LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5 | LTE_CA_R15_xDL2UL-Core | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180770 |  | LG Electronics |  | 12/7/17: 36.715-00-02 added;; 19/9/17: Compl:0%->20% 8/1/18: Compl:20%->50%; 27/3/18: Compl:50%->80%; ; 27/6/18: | 36.715-00-02 | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
937 | 760296 | Perf. part:LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5 | LTE_CA_R15_xDL2UL-Perf | 2 | Rel-15 | R4 | 2017-06-15 | 2018-06-15 | 100% | RP-180770 |  | LG Electronics |  | 19/9/17: CD:Sat 15/09/18->Fri 15/06/18; 8/1/18: Compl:0%->50%; 27/3/18: Compl:50%->80% ; 27/6/18: Compl:80%->100%; |  | 76 | 39 |  |  | 2017-06-16 | 2018-06-27
938 | 770064 | UE Conformance Test Aspects – Rel-15 CA configurations | LTE_CA_R15-UEConTest | 1 | Rel-15 | R5 | 2017-09-15 | 2019-06-14 | 9% | RP-181202 |  | Ericsson |  | ; 8/1/18: Compl:0%->7%; 27/3/18: Compl:7%->8% ; |  | 77 | 39 |  |  | 2017-09-19 | 2018-06-27
939 | 580037 | LTE UE Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) and UTRA Hand Phantom related UE TRP and TRS Requirements | LTE_UTRA_TRP_TRS | 1 | Rel-15 |  | 2012-12-15 | 2017-12-15 | 82% | RP-130703 | - | Nokia | petri.j.vasenkari@nokia.com | Triggered by Rel-11 TR 37.902 Study on Measurements of radio performances for LTE terminals - TRP and TRS test methodology (FS_LTE_OTA) UID_550022 | UTRA, LTE | 58 | 30 |  |  | 2012-12-10 | 2014-09-15
940 | 580137 | Core part: LTE UE TRP and TRS and UTRA Hand Phantom related UE TRP and TRS Requirements | LTE_UTRA_TRP_TRS-Core | 2 | Rel-15 | R4 | 2012-12-15 | 2017-12-15 | 85% | RP-172035 |  | Nokia | petri.j.vasenkari@nokia.com | ; CD:Wed 18/03/15->Sun 15/03/15; Rel-12->Rel-13; Stat Rep: RP-141158->RP-141973 1st Apr 15: Compl:35%->40% 1st Apr 15: Stat Rep: RP-141973->RP-150104 03/07/15: Stat Rep: RP-150104->RP-150615 29/09/15: Compl:40%->50% 29/09/15: Stat Rep: RP-150615->RP-15 | 25.144, New TS 37.144 | 58 | 30 |  |  | 2012-12-10 | 2018-01-08
941 | 630011 | Test part: LTE UE TRP and TRS and UTRA Hand Phantom | LTE_UTRA_TRP_TRS-UEConTest | 2 | Rel-15 | R5 | 2014-03-15 | 2017-12-15 | 78% | RP-150070 |  | ZTE | TAYLOR Carolyn (carolyn.tayl@zte.com.cn) | Stat Rep: RP-141132->RP-141848; Rel 12->Rel13 1st Apr 15: Compl:15%->20% 1st Apr 15: CD:Mon 15/06/15->Wed 15/06/16 1st Apr 15: WID: RP-140090->RP-150070 1st Apr 15: Stat Rep: RP-141848->RP-150069 03/07/15: Compl:20%->25% 03/07/15: Stat Rep: RP-150069-> | New TS 37.544 | 63 | 32 |  |  | 2014-03-04 | 2018-01-08
942 | 790053 | Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_fenh | 1 | Rel-15 | R6 | 2018-03-15 | 2018-09-15 | 90% | RP-180541 |  | Nokia |  | follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh |  | 79 | 40 |  |  | 2018-03-27 | NA
943 | 790153 | Core part: Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_fenh-Core | 2 | Rel-15 | R6 | 2018-03-15 | 2018-09-14 | 80% | RP-180541 |  | Nokia |  | follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh; 27/6/18: Compl:0%->80%; |  | 79 | 40 |  |  | 2018-03-27 | 2018-06-27
944 | 790253 | Perf. part: Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_fenh-Perf | 2 | Rel-15 | R6 | 2018-03-15 | 2018-09-15 | 100% | RP-180541 |  | Nokia |  | follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh; 27/6/18: Compl:0%->80%;; 10/9/18: 80%->100 |  | 79 | 40 |  |  | 2018-03-27 | 2018-09-10
945 | 790056 | LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5 | LTE_CA_R15_xDL3UL | 1 | Rel-15 | R4 | 2018-03-15 | 2018-06-15 | 100% | RP-180573 |  | KDDI |  | basket CA WI; no Perf. part |  | 79 | 40 |  |  | 2018-03-27 | NA
946 | 790156 | Core part: LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5 | LTE_CA_R15_xDL3UL-Core | 2 | Rel-15 | R4 | 2018-03-15 | 2018-06-15 | 100% | RP-181311 |  | KDDI |  | basket CA WI; no Perf. part; 27/6/18: Compl:0%->100%; … |  | 79 | 40 |  |  | 2018-03-27 | 2018-06-27
947 | 801203 | Perf. Part: LTE Advanced inter-band CA Rel-15 for xDL/3UL with x=3,4,5 | LTE_CA_R15_xDL3UL-Perf | 2 | Rel-15 | R4 | 2018-05-15 | 2018-06-15 | 100% | RP-181311 |  | KDDI |  | Perf. Part was introduced and completed at RAN #80 |  | 80 | 41 |  |  | 2018-06-27 | NA
948 | 790055 | Addition of Power Class 1 UE to bands B31/B72 for LTE | LTE_PC1_B31_B72 | 1 | Rel-15 | R4 | 2018-03-15 | 2018-12-14 | 99% | RP-180178 |  | Airbus |  | to add Power Class 1 (+31dBm) for UE operating in Europe @ 450MHz in frequency bands that are suitable for BB-PPDR operation, i.e. band 31 and band 72; |  | 79 | 40 |  |  | 2018-03-27 | NA
949 | 790155 | Core part: Addition of Power Class 1 UE to bands B31/B72 for LTE | LTE_PC1_B31_B72-Core | 2 | Rel-15 | R4 | 2018-03-15 | 2018-06-15 | 100% | RP-180688 |  | Airbus |  | to add Power Class 1 (+31dBm) for UE operating in Europe @ 450MHz in frequency bands that are suitable for BB-PPDR operation, i.e. band 31 and band 72;27/6/18: moved from Rel-16 |  | 79 | 40 |  |  | 2018-03-27 | 2018-06-27
950 | 810062 | UE Conformance Test Aspects - Addition of Power Class 1 UE to bands B31/B72 for LTE | LTE_PC1_B31_B72-UEConTest | 2 | Rel-15 | R5 | 2018-09-14 | 2018-12-14 | 100% | RP-181629 |  | Airbus |  | 16/1/19: 0%->100 | [5 empty] | 2018-09-25 | 2019-01-16
951 | 0 | Release 15 Studies | - | 1 | Rel-15 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
952 | 0 | Release 15 Studies on 5G | - | 1 | Rel-15 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
953 | 730056 | Study on management aspects of virtualized network functions that are part of the NR | FS_MA_RNVNF | 1 | Rel-15 | S5 | 2016-09-19 | 2017-12-15 | 100% | SP-160703 |  | Intel (Joey Chou | joey.chou@intel.com | 6/10/16: Acronym FS_MA_RVNF ->FS_MA_RNVNF ; 6/10/16: 32.864 added; 1/12/16: 0%->5; 6/3/17: 5%->10; 7/6/17: 10%->40; 11/9/17: 40%->70; 15/12/17: 70%->100; 15/12/17: FCD:09/17->12/17 | TR 32.864 | 73 | 37 |  |  | 2016-09-19 | 2017-12-15
954 | 750043 | Study on CU-DU lower layer split for New Radio | FS_NR_CU_DU_LLS | 1 | Rel-15 | R3 | 2017-03-15 | 2018-06-15 | 100% | RP-180684 |  | NTT DOCOMO |  | CU = central unit, DU = distributed unit; results will be captured in existing TR 38.801; 19/9/17: Compl:0%->30%; 19/9/17: WID: RP-170818->RP-171717; 15/12/17: 38.816 added;; 8/1/18: Compl:30%->95%; 8/1/18: CD:Fr ; 27/6/18 | 38.816 | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
955 | 750040 | Study on NR to support non-terrestrial networks | FS_NR_nonterr_nw | 1 | Rel-15 | R1 | 2017-03-15 | 2018-06-15 | 100% | RP-171450 |  | Thales |  | TR 38.8XX19/6/17: Compl:0%->25%19/6/17: CD:Fri 15/12/17->Thu 15/03/1819/6/17: WID: RP-170717->RP-171450; 30/6/17: 38.811 added;; 19/9/17: Compl:25%->40%; 8/1/18: CD:Thu 15/03/18->Fri 15/06/18; 27/3/18: Compl:40%->45%; 27/6/18: Compl:4 | 38.811 | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
956 | 710045 | STOPPED AT SA#77 - SA3 aspects on Study on Architecture and Security for Next Generation System | FS_NSA | 1 | Rel-15 | S3 | 2016-03-01 | 2017-12-12 | 100% | SP-160727 |  | Vesa Torvinen, Ericsson | vesa.torvinen@ericsson.com | 19/9/16: 0%->25; 22/9/16: WID:SP-160227->SP-160727; 22/9/16: FCD:12/16->03/17; 1/12/16: 25%->45; 6/3/17: 45%->60; 7/6/17: FCD:03/17->12/17 so Rel-14->Rel-15; 7/6/17: 60%->65; 11/9/17: 65%->100 | TR 33.899 | 71 | 36 |  |  | 2016-03-01 | 2017-09-11
957 | 760080 | Study on separation of CP and UP for split option 2 of NR | FS_NR_CPUP_Split | 1 | Rel-15 | R3 | 2017-06-15 | 2017-12-15 | 100% | RP-171905 |  | Ericsson |  | 19/9/17: Compl:0%->45%19/9/17: WID: RP-171421->RP-171905; 15/12/17: 38.806 added;; 8/1/18: Compl:45%->100% | 38.806 | 76 | 39 |  |  | 2017-06-16 | 2018-01-08
958 | 0 | Release 15 Studies on 4G/LTE | - | 1 | Rel-15 |  | 2016-06-09 | 2016-06-09 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
959 | 710064 | Stopped - Study on LTE bandwidth flexibility enhancements | FS_LTE_BW_flex | 1 | Rel-15 | R4 | 2016-03-15 | 2017-03-15 | 100% | RP-161670 |  | Huawei |  | 1/7/16: Compl:0%->50%; 28/7/16: 36.740 added; 26/9/16: WID: RP-161328->RP-161670; 20/12/16: CD:Thu 15/0;21/3/17: CD:Fri 15 12/7/17: 50%->100 since declared as stopped | 36.74 | 71 | 36 |  |  | 2016-03-22 | 2017-07-12
960 | 730070 | Study on interference cancellation receiver for LTE BS | FS_LTE_IC_BS | 1 | Rel-15 | R4 | 2016-09-15 | 2017-06-15 | 100% | RP-161485 |  | China Telecom |  | 6/10/16: 36.766 added; 20/12/16: Compl:0%->35% 21/3/17: Compl:35%->65%; 19/6/17: Compl:65%->100% | 36.766 | 73 | 37 |  |  | 2016-09-26 | 2017-06-19
961 | 740066 | Study on uplink data compression in LTE | FS_LTE_UDC | 1 | Rel-15 | R2 | 2016-12-15 | 2017-09-15 | 100% | RP-170403 |  | CATT |  | ; 21/3/17: WID: RP-162541->RP-170403; 21/3/17: 36.754 added;19/6/17: Compl:0%->90%; 19/9/17: Compl:90%->100 | 36.754 | 74 | 38 |  |  | 2016-12-20 | 2017-09-19
962 | 760081 | Study on LTE DL 8Rx antenna ports | FS_LTE_8Rx_AP_DL | 1 | Rel-15 | R4 | 2017-06-15 | 2017-12-15 | 100% | RP-171753 |  | Huawei |  | 12/7/17: 36.757 added;; 19/9/17: Compl:0%->35%; 8/1/18: Compl:35%->100% | 36.757 | 76 | 39 |  |  | 2017-06-16 | 2018-01-08
963 | 0 | Other Release 15 Studies | - | 1 | Rel-15 |  | 2017-09-08 | 2018-03-16 | 100% | - | - | - | - | - | - |  |  |  |  | 2014-08-29 | 2014-08-29
964 | 770026 | Study on Update to fixed-point basic operators | FS_BASOP | 1 | Rel-15 | S4 | 2017-09-08 | 2018-03-15 | 100% | SP-170613 |  | Jelinek, Milan, VoiceAge Corporation | Milan.Jelinek@USherbrooke.ca | 15/12/17: 26.973 added;; 15/12/17: 0%->80; 16/3/18: 80%->100 | New; 26.973 | 77 | 39 |  |  | 2017-09-08 | 2018-03-16
965 | 710063 | Study on further enhancements to LTE Device to Device (D2D), UE to network relays for IoT (Internet of Things) and wearables | FS_feD2D_IoT_relay_wearable | 1 | Rel-15 | R2 | 2016-03-15 | 2017-12-15 | 100% | RP-170295 |  | Qualcomm |  | 1/7/16: Compl:0%->2%;26/9/16: Compl:2%->5%; 6/10/16: 36.746 added; 20/12/16: Compl:5%->15%;21/3/17: Compl:15%->35%…19/6/17: ; | 36.746 | 71 | 36 |  |  | 2016-03-22 | 2018-01-08
966 | 710049 | Study on Energy Efficiency Aspects of 3GPP Standards | FS_ENEFF | 1 | Rel-15 | SP | 2016-03-11 | 2017-06-09 | 100% | SP-160224 | _SP-170533 | Orange, Xiaobao Chen | xiaobao.chen@orange.com | 28/7/16: 21.866 added;; 9/6/17: FCD:12/16->9/6/17 (Rel-14->Rel-15); 0%->100 | TR 21.866 | 71 | 36 |  |  | 2016-03-11 | 2017-06-09
967 | 700047 | Study on OAM support for assessment of energy efficiency in mobile access networks | FS_OAM_EE | 1 | Rel-15 | S5 | 2015-11-02 | 2017-06-09 | 100% | SP-160430 |  | Cornily,Jean-Michel, ORANGE | jeanmichel.cornily@orange.com | 13/6/16: WID:SP-150674->SP-160430; 13/6/16: 0%->55; 1/12/16: 55%->80; 6/3/17: FCD:03/17->06/17; 6/3/17: 80%->90; 21/3/17: moved from rel-14; 7/6/17: 90%->100 | TR 32.856 | 70 | 36 |  |  | 2015-12-07 | 2017-06-07
968 | 750049 | Study on evaluation methodology of new V2X use cases for LTE and NR | FS_LTE_NR_V2X_eval | 1 | Rel-15 | R1 | 2017-03-15 | 2018-06-15 | 100% | RP-171093 |  | LG Electronics |  | TR 38.8XX19/6/17: WID: RP-170837->RP-171093; 12/7/17: 37.885 added;19/9/17: Compl:0%->5%; 8/1/18: Compl:5%->10%; 8/1/18: CD:Fri 15/12/17->Thu 15/03/18; 27/3/18: Compl:10%->30%; 27/3/18: CD:Thu 15/03/18->Fri 15/06/18; 27/ | 37.885 | 75 | 38 |  |  | 2017-03-21 | 2018-06-27
969 | 760042 | Study on FEC for MC Services | FS_FEC_MCS | 1 | Rel-15 | S4 | 2017-06-05 | 2018-03-15 | 100% | SP-170337 |  | Lambrou, John - Motorola Solutions | john (dot) lambrou (at) motorolasolutions (dot) com | 11/9/17: 0%->15; 15/12/17: 15%->60; 15/12/17: FCD:12/17->03/18; 16/3/18: 60%->100 | 26.881 | 76 | 39 |  |  | 2017-06-03 | 2018-03-16
970 | 710032 | Study on Enhanced Isolated E-UTRAN Operation for Public Safety | FS_IOPS_LB | 1 | Rel-15 | S2 | 2016-03-07 | 2016-12-15 | 100% | SP-160171 |  | Antoine Mouquet, Orange | antoine.mouquet@orange.com | 9/6/16: 0%->6; 28/7/16: 23.798 added; 1/12/16: FCD:09/16->12/16; 1/12/16: 6%->15. 7/12/16: Moved from Rel-14 according to SP-160806.; 6/3/17: 15%->50; 7/6/17: 50%->100 | 23.798 | 71 | 36 |  |  | 2016-03-07 | 2017-06-07
971 | 740016 | Study on Management Enhancement of CUPS of EPC Nodes | FS_MECUPS | 1 | Rel-15 | S5 | 2016-12-01 | 2017-12-12 | 100% | SP-160925 |  | Huawei; Jiang, Junyi | jiangjunyi@huawei.com | 6/3/17: 0%->5; 7/6/17: 5%->40; 7/6/17: FCD:09/17->12/17; 11/9/17: 40%->50; 15/12/17: 50%->100 | 32.867 | 74 | 38 |  |  | 2016-12-01 | 2017-12-15
972 | 720041 | Study on Technical Requirements for a new secure platform for 3GPP applications | FS_NG_SP | 1 | Rel-15 | C6 | 2016-06-13 | 2017-09-12 | 100% | CP-160371 |  | Heiko Kruse | heiko.kruse@safrangroup.com | 16/9/16: 0%->15. ; 5/6/17: 15%->70. 5/6/17: moved to Rel-15 (talks with P. Jolivet); 5/6/17: FCD:12/16->09/20; 15/12/17: 70%->100 | TR 31.801 | 72 | 37 |  |  | 2016-06-13 | 2017-12-15
973 | 750030 | Study on technical requirements for a new secure platform for 3GPP applications | FS_NG_SP2 | 1 | Rel-15 | C6 | 2017-03-03 | 2017-09-14 | 100% | CP-170183 |  | Heiko Kruse | heiko.kruse@safrangroup.com | 21/3/17: 31.801 added;; 11/9/17: 0%->70; 15/12/17: 70%->100 | 31.801 | 75 | 38 |  |  | 2017-03-03 | 2017-12-15
974 | 750041 | Study on scheduling enhancements with CA for UMTS | FS_UTRA_CA_sched_enh | 1 | Rel-15 | R1 | 2017-03-15 | 2017-06-15 | 100% | RP-171065 |  | Huawei |  | TR 25.7XX; 19/6/17: Compl:0%->100%; 12/7/17: 25.708 added; | 25.708 | 75 | 38 |  |  | 2017-03-21 | 2017-07-12
975 | 750050 | Study on Architecture Evolution for E-UTRAN | FS_LTE_arch_evo | 1 | Rel-15 | R3 | 2017-03-15 | 2018-03-15 | 100% | RP-172707 |  | China Unicom |  | TR 36.8XX; 12/7/17: 36.756 added;19/9/17: Compl:0%->40%; 15/12/17: 37.876 added;; 8/1/18: Compl:40%->827/3/18: Compl:85%->100% | 36.756; 37.876 | 75 | 38 |  |  | 2017-03-21 | 2018-03-27
976 | 590045 | Study on Enhanced Acoustic Test Specifications | FS_SEATS | 1 | Rel-15 | S4 | 2013-03-18 | 2017-12-12 | 100% | SP-130028 | - | Knowles, Intel | Scott Isabelle (Knowles), David Isherwood (Intel) | SP#65 completion 09/14=>12/14. Moved to Rel-13. Dec.14: 30->35%, CD 12/14->03/15. Mar.15: CD: 06/16. 40%; June2015: Compl:40%->45. . 15/4/16: moved from R 21/3/17: Moved from Rel-14 (not completed on time); 7/6/17: FCD:06/17->12/17; 11/9/17: 80%->8 | 26.931 | 59 | 30 |  |  | 2013-02-20 | 2017-12-15
977 | 720025 | Study on User Services Enhancements in 3GPP for TV Services | FS_USE_3GPP_4_TV | 1 | Rel-15 | S4 | 2016-06-13 | 2017-09-12 | 100% | SP-160273 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 19/9/16: 0%->30; 6/10/16: 26.917 added; 1/12/16: 30%->60; 1/12/16: FCD:12/16->03/17; 6/3/17: 60%->75; 6/3/17: FCD:03/17->06/17; 21/3/17: Moved from Rel-14 (not completed on time); 7/6/17: 75%->80; 7/6/17: FCD:06/17->09/17; 11/9/17: 80%->100 | TR 26.9xx; 26.917 | 72 | 37 |  |  | 2016-06-11 | 2017-09-11
978 | 730055 | Study on Management aspects of selected IoT-related features | FS_OAM_IOT | 1 | Rel-15 | S5 | 2016-09-19 | 2017-12-12 | 100% | SP-160611 |  | Cisco Systems / Yanover, Vladimir |  | 6/10/16: 32.857 added; 1/12/16: 0%->5; 21/3/17: moved from Rel-14; 7/6/17: FCD:06/17->12/17; 7/6/17: 5%->20; 11/9/17: 20%->30; 15/12/17: 30%->45; 16/3/18: 45%->100 | 32.857 | 73 | 37 |  |  | 2016-09-19 | 2018-03-16
979 | 680054 | Study on Overload Control for Diameter Charging Applications | FS_DOCME_CH | 1 | Rel-15 | S5 | 2015-06-18 | 2017-12-15 | 100% | SP-170481 |  | GUO Wenjie, ZTE | guo.wenjie1@zte.com.cn | Aug2015: moved to Rel-14 (email CT and EG); 07/09/15: 0%->5; 7/3/16: 5%->10; 13/6/16: FCD:03/16->09/16; 19/9/16: FCD: 09/16->06/17; 6/3/17: FCD:03/17->12/17; 21/3/17: moved from rel-14; 7/6/17: 10%->25; 8/6/17: WID:SP-150310->SP-170481; 11/9/17: 25%->3 | New TR 32.869 | 68 | 35 |  |  | 2015-06-26 | 2017-12-15
980 | 730053 | Study on forward compatibility for 3GPP Diameter Charging Applications | FS_FWDCA | 1 | Rel-15 | S5 | 2016-09-19 | 2017-06-15 | 100% | SP-160608 |  | Nokia, Maryse <dot> Gardella <at> Nokia <dot> com | Nokia, Maryse <dot> Gardella <at> Nokia <dot> com | 6/10/16: 32.870 added; 1/12/16: 0%->10; 21/3/17: moved from rel-14; 11/9/17: 10%->40; 15/12/17: 40%->100 | 32.87 | 73 | 37 |  |  | 2016-09-19 | 2017-12-15
981 | 700048 | Study on OAM aspects of SON for AAS-based deployments | FS_OAM_SON_AAS | 1 | Rel-15 | S5 | 2015-11-02 | 2017-06-09 | 100% | SP-150677 |  | Nokia Networks (Yizhi Yao) | Yizhi.yao@nokia.com | 13/6/16: 0%->40; 19/9/16: FCD:09/16->12/16; 19/9/16: 40%->60; 1/12/16: FCD:12/16->03/17; 1/12/16: 60%->70; 6/3/17: FCD:03/17->06/17; 21/3/17: moved from rel-14; 7/6/17: 70%->100 | TR (new) | 70 | 36 |  |  | 2015-12-07 | 2017-06-07
982 | 710007 | Study on Implementation for the Partitioning of Itf-N | FS_IMP_ITFN | 1 | Rel-15 | S5 | 2016-03-01 | 2018-03-15 | 100% | SP-160020 |  | Hu, Yaxi, China Mobile | huyaxi@cmdi.chinamobile.com | 13/6/16: 0%->10; 19/9/16: 10%->35; 1/12/16: 35%->40; 6/3/17: FCD:03/17->03/18; 21/3/17: moved from rel-14; 7/6/17: 40%->60; 11/9/17: 60%->80; 15/12/17: 80%->100 | New TR 32.880 | 71 | 36 |  |  | 2016-03-01 | 2017-12-15
983 | 720046 | Study on Management Aspects of Next Generation Network architecture and features | FS_MAN_NGNAF | 1 | Rel-15 | S5 | 2016-06-13 | 2017-12-12 | 100% | SP-160399 |  | Nokia Networks, Yizhi Yao | Yizhi.yao@nokia.com | 28/7/16: 28.802 added; 19/9/16: 0%->5; 1/12/16: 5%->10; 6/3/17: FCD:03/17->06/17; 6/3/17: 10%->40; 21/3/17: moved from rel-14; 7/6/17: FCD:06/17->12/17; 7/6/17: 40%->60; 11/9/17: 60%->70; 15/12/17: 70%->100 | TR (new); 28.802 | 72 | 37 |  |  | 2016-06-13 | 2017-12-15
984 | 720047 | Study on Management and Orchestration Architecture of Next Generation Network and Service | FS_NGNS_MOA | 1 | Rel-15 | S5 | 2016-06-13 | 2017-12-12 | 100% | SP-160400 |  | Huawei Technologies, Zou Lan | zoulan@huawei.com | 28/7/16: 28.800 added; 19/9/16: 0%->10; 6/3/17: FCD:03/17->06/17; 21/3/17: moved from rel-14; 7/6/17: FCD:06/17->12/17; 7/6/17: 10%->25; 11/9/17: 25%->30; 15/12/17: 30%->100 | TR xy.abc; 28.800 | 72 | 37 |  |  | 2016-06-13 | 2017-12-15
985 | 720063 | Study on SON for eCoMP for LTE | FS_LTE_SON_eCOMP | 1 | Rel-15 | R3 | 2016-06-15 | 2017-06-15 | 100% | RP-161181 |  | Nokia |  | 26/9/16: Compl:0%->10%. ; 20/12/16: Compl:10%->40%21/3/17: Compl:40%->60%; 19/6/17: Compl:60%->100% |  | 72 | 37 |  |  | 2016-07-01 | 2017-06-19
986 | 650036 | Stopped - Study on IMS Enhanced Spoofed Call Prevention and Detection | FS_ESCAPADES | 1 | Rel-15 | S3 | 2014-09-19 | 2017-12-15 | 100% | SP-140611 | - | Sprint | Gregory.schumacher@sprint.com | Dec.14: TR number added. 3/3/15: 0->5%; June2015: Compl:5%->25; 9/12/15: 25%->30; 21/3/17: moved from Rel-13; 21/3/17: FCD:09/15->12/17; 7/6/17: Stopped (30%->100%) | 33.832 | 64 | 33 |  |  | 2014-09-04 | 2017-06-07
987 | 760056 | Study on OAM aspects of LTE and WLAN integration | FS_OAM_LWI | 1 | Rel-15 | S5 | 2017-06-05 | 2018-03-15 | 100% | SP-170480 |  | Yizhi Yao, Intel Corporation | yizhi.yao@intel.com | 30/6/17: 32.868 added;; 11/9/17: 0%->10; 15/12/17: 10%->50; 16/3/18: 50%->90; 7/6/18: 90%->100 | new; 32.868 | 76 | 39 |  |  | 2017-06-03 | 2018-06-07
988 | 760060 | Study on Volume Based Charging Aspects for VoLTE | FS_VBCLTE | 1 | Rel-15 | S5 | 2017-06-05 | 2018-06-14 | 100% | SP-170594 |  | Chen, Ai, China Mobile | chenai@chinamobile.com | 30/6/17: 32.848 added;; 11/9/17: 0%->5; 15/12/17: 5%->35; 16/3/18: 35%->45; 7/6/18: 45%->100 | new; 32.848 | 76 | 39 |  |  | 2017-06-05 | 2018-06-07
989 | 710015 | STOPPED - Study on UE characteristics and performance for Video | FS_UE_VTPerf | 1 | Rel-15 | S4 | 2016-03-01 | 2017-06-15 | 100% | SP-160085 |  | Stéphane PROUST, Orange | stephane.proust@orange.com | 11/6/16: 0%->10; 19/9/16: 10%->30, FCD: 12/16->06/17; 21/3/17: Moved from Rel-14 (not completed on time); 7/6/17: Stopped, so 30%->100 | TR 26.932 | 71 | 36 |  |  | 2016-03-01 | 2017-06-07
990 | 780061 | Study on UE Application Layer Data Throughput Performance Expansion for CA | FS_UE_App_Data_Perf_CA | 1 | Rel-15 | R5 | 2017-12-15 | 2018-06-15 | 100% | RP-180203 |  | PCTEST Engineering Lab |  | compare REL-11 SI FS_UE_App_Data_Perf; note: SI FS_UE_App_Data_Perf_CA is addressing 2DL/1UL involving also an unlicensed carrier of REL-13 LTE_LAA; instead of a new TR, the TR 37.901 will be updated for REL-15; ; |  | 78 | 40 |  |  | 2018-01-08 | 2018-06-27
991 | 760064 | Study on system and functional aspects of Energy Efficiency in 5G networks | FS_EE_5G | 1 | Rel-15 | S5 | 2017-06-05 | 2018-12-14 | 100% | SP-170489 |  | CORNILY, Jean-Michel, ORANGE | jeanmichel.cornily@orange.com | 30/6/17: 32.872 added;; 11/9/17: 0%->5; 15/12/17: 32.972 added;; 15/12/17: 5%->40; 16/3/18: 40%->60; 7/6/18: 60%->65; 7/6/18: FCD:06/18->12/18; 10/9/18: 65%->85; 7/12/18: 85%->100 | new; 32.872; 32.972 | 76 | 39 |  |  | 2017-06-05 | 2018-12-07
841 | 0 | Release 14 Features | - | 1 | Rel-14 |  | 2014-12-12 08:00 | 2014-12-12 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
842 | 0 | Release 14 on Mission Critical | - | 1 | Rel-14 |  | 2016-06-09 08:00 | 2016-06-09 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
843 | 700027 | Mission Critical Improvements | MCImp | 1 | Rel-14 |  | 2015-04-14 08:00 | 2019-12-13 17:00 | 87% |  |  |  |  | Umbrella Feature |  | 70 | 36 |  |  | Mon 07/12/15 | Fri 11/12/15
844 | 700029 | Mission Critical Push to Talk over LTE Realignment | MCImp-MCPTTR | 2 | Rel-14 | S1 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | SP-150821 | SP-170406 | Andrew Thiessen | andrew (at) its (dot) bldrdoc (dot) gov | 2/3/16: FCD: 03/16->06/16. ES in SP-160102; 0->75%; 9/6/16: 75%->100 | 22.179 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
845 | 740022 | Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT | 2 | Rel-14 |  | 2016-06-13 08:00 | 2017-06-14 17:00 | 100% | SP-160490 |  | Lazara, Dom | dom.lazara@motorolasolutions.com | 28/7/16: 23.379 added; 19/9/16: 0%->35; 1/12/16: 35%->100 | TS 23.379, TS 23.280, TS 23.281, TS 23.282; 23.379 | 72 | 37 |  |  | Mon 13/06/16 | Thu 01/12/16
846 | 720056 | Stage 2 of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT | 3 | Rel-14 | S6 | 2016-06-13 08:00 | 2016-12-15 17:00 | 100% | SP-160490 |  | Lazara, Dom | dom.lazara@motorolasolutions.com | 28/7/16: 23.379 added; 19/9/16: 0%->35; 1/12/16: 35%->100 | TS 23.379, TS 23.280, TS 23.281, TS 23.282; 23.379 | 72 | 37 |  |  | Mon 13/06/16 | Thu 01/12/16
847 | 740023 | Stage 3 of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT-CT | 3 | Rel-14 | ct | 2016-12-01 08:00 | 2017-06-14 17:00 | 100% | CP-160824 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com |  |  | 74 | 38 |  |  | Thu 01/12/16 | NA
848 | 740024 | CT1 aspects of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT-CT | 4 | Rel-14 | C1 | 2016-12-01 08:00 | 2017-06-14 17:00 | 100% | CP-160824 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com | 6/3/17: 0%->20; 5/6/17: 20%->95; 14/9/17: 95%->97; 15/12/17: 97%->100 | 24.379, 24.380, 24.381, 24.382, 24.383, 24.384 | 74 | 38 |  |  | Thu 01/12/16 | Fri 15/12/17
849 | 740025 | CT3 aspects of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT-CT | 4 | Rel-14 | C3 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160824 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com | 5/6/17: 0%->100 | 29.165, 29.213, 29.214 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
850 | 740026 | CT4 aspects of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT-CT | 4 | Rel-14 | C4 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160824 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com | 6/3/17: 0%->100 | 23.003, 29.228, 23.335, 29.283 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
851 | 740027 | CT6 aspects of Enhancements for Mission Critical Push To Talk | MCImp-eMCPTT-CT | 4 | Rel-14 | C6 | 2016-12-01 08:00 | 2017-06-14 17:00 | 100% | CP-160824 |  | FREDERICKS, Bob | bobfredericks@motorolasolutions.com | 5/6/17: 0%->100. No work identified for CT6. | 31.102, 31.103 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
852 | 700028 | Mission Critical Services Common Requirements | MCImp-MCCoRe | 2 | Rel-14 | S1 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | SP-150822 | SP-170407 | Andrew Thiessen | andrew (at) its (dot) bldrdoc (dot) gov | 2/3/16: FCD: 03/16->06/16. ES in SP-160104; 0->75%; 9/6/16: 75%->100 | New TS 22.280 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
853 | 720055 | Common functional architecture to support mission critical services | MCImp-MC_ARCH | 2 | Rel-14 | S6 | 2016-06-13 08:00 | 2016-12-15 17:00 | 100% | SP-160489 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 28/7/16: 23.280 added; 19/9/16: 0%->40; 1/12/16: 40%->95; 3/3/17: 95%->100 | TS 23.280, TS 23.379, TS 23.281, TS 23.282; 23.280 | 72 | 37 |  |  | Mon 13/06/16 | Fri 03/03/17
854 | 720053 | Mission Critical Video over LTE | MCImp-MCVideo | 2 | Rel-14 |  | 2015-04-14 08:00 | 2017-06-14 17:00 | 100% | SP-150849 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160106; 0->80%; 9/6/16: 80%->100 |  | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
855 | 670006 | Study on Mission Critical Video over LTE | FS_MCVideo | 3 | Rel-14 | S1 | 2015-04-14 08:00 | 2015-12-15 17:00 | 100% | SP-150048 |  | Villebrun, Emmanuelle (French MoI) | emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 1/4/15:TR number added; June2015: Compl:0%->50; 07/09/15: 50%->70; 7/12/15: 70%->100 | New TR 22.879 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
856 | 700030 | Stage 1 of MCVideo | MCImp-MCVideo | 3 | Rel-14 | S1 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | SP-150849 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160106; 0->80%; 9/6/16: 80%->100 | New TR 22.281 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
857 | 720051 | Stage 2 for MCVideo | MCImp-MCVideo | 3 | Rel-14 | S6 | 2016-06-13 08:00 | 2016-12-15 17:00 | 100% | SP-160491 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 28/7/16: 23.281 added; 19/9/16: 0%->25; 1/12/16: 25%->95; 3/3/17: 95%->100 | TS 23.281, TS 23.280, TS 23.379, TS 23.282; 23.281 | 72 | 37 |  |  | Mon 13/06/16 | Fri 03/03/17
858 | 750018 | MCVideo codecs and media handling | MCImp-MCVideo | 3 | Rel-14 | S4 | 2017-01-11 08:00 | 2017-03-16 17:00 | 100% | SP-170244 |  | John Lambrou (Motorola Solutions) | john (dot) lambrou (at) motorolasolutions (dot) com | 6/3/17: 0%->100 | 26.281 | 75 | 38 |  |  | Fri 03/03/17 | Mon 06/03/17
859 | 740033 | Stage 3 of MCVideo | MCImp-MCVIDEO-CT | 3 | Rel-14 | ct | 2016-12-01 08:00 | 2017-06-14 17:00 | 100% | CP-160827 |  | PATEL, Milan | milan.patel@huawei.com |  | 24.581, 24.281 | 74 | 38 |  |  | Thu 01/12/16 | NA
860 | 740034 | CT1 aspects 3 of MCVideo | MCImp-MCVIDEO-CT | 4 | Rel-14 | C1 | 2016-12-01 08:00 | 2017-06-14 17:00 | 100% | CP-160827 |  | PATEL, Milan | milan.patel@huawei.com | 6/3/17: 0%->25; 5/6/17: 25%->90; 14/9/17: 90%->100 | 24.381, 24.382, 24.383, 24.384 | 74 | 38 |  |  | Thu 01/12/16 | Thu 14/09/17
861 | 740035 | CT3 aspects 3 of MCVideo | MCImp-MCVIDEO-CT | 4 | Rel-14 | C3 | 2016-12-01 08:00 | 2017-03-15 17:00 | 100% | CP-160827 |  | PATEL, Milan | milan.patel@huawei.com | 5/6/17: 0%->100 | 29.165, 29.213, 29.214 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
862 | 740036 | CT4 aspects 3 of MCVideo | MCImp-MCVIDEO-CT | 4 | Rel-14 | C4 | 2016-12-01 08:00 | 2017-03-15 17:00 | 100% | CP-160827 |  | PATEL, Milan | milan.patel@huawei.com | 6/3/17: 0%->100 | 23.003, 23.335, 29.283 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
863 | 740037 | CT6 aspects 3 of MCVideo | MCImp-MCVIDEO-CT | 4 | Rel-14 | C6 | 2016-12-01 08:00 | 2017-06-14 17:00 | 100% | CP-160827 |  | PATEL, Milan | milan.patel@huawei.com | 5/6/17: 0%->100. No work identified for CT6. | 31.102, 31.103 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
864 | 720054 | Mission Critical Data over LTE | MCImp-MCData | 2 | Rel-14 |  | 2015-04-14 08:00 | 2017-06-14 17:00 | 100% | SP-150850 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160109; 0->80%; 9/6/16: 80%->100 |  | 70 | 36 |  |  | Mon 07/12/15 | Thu 28/07/16
865 | 670007 | Study on Mission Critical Data Communications | FS_MCDATA | 3 | Rel-14 | S1 | 2015-04-14 08:00 | 2015-12-15 17:00 | 100% | SP-150049 |  | Villebrun, Emmanuelle (French MoI) | emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 1/4/15:TR number added; June2015: Compl:0%->20; 07/09/15: 20%->90; 7/12/15: 90%->100 | New TR 22.880 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
866 | 700031 | Stage 1 of MCData | MCImp-MCData | 3 | Rel-14 | S1 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | SP-150850 |  | Emmanuelle Villebrun | Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr | 2/3/16: FCD: 03/16->06/16. ES in SP-160109; 0->80%; 9/6/16: 80%->100 | New TR 22.282 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
867 | 720052 | Stage 2 for MCData | MCImp-MCData | 3 | Rel-14 | S6 | 2016-06-13 08:00 | 2016-12-15 17:00 | 100% | SP-160492 |  | David Freeman (UK Home Office) | david@dnf-consulting.co.uk | 28/7/16: 23.282 added; 19/9/16: 0%->10; 1/12/16: 10%->95; 3/3/17: 95%->100 | 23.282 | 72 | 37 |  |  | Mon 13/06/16 | Fri 03/03/17
868 | 740028 | Stage 3 of MCData | MCImp-MCDATA-CT | 3 | Rel-14 | ct | 2016-12-01 08:00 | 2017-06-14 17:00 | 100% | CP-160826 |  | HASON, Baruh | baruh.hason@motorolasolutions.com |  | 24.582, 24.282 | 74 | 38 |  |  | Thu 01/12/16 | Wed 14/06/17
869 | 740029 | CT1 aspects of MCData | MCImp-MCDATA-CT | 4 | Rel-14 | C1 | 2016-12-01 08:00 | 2017-06-14 17:00 | 100% | CP-160826 |  | HASON, Baruh | baruh.hason@motorolasolutions.com | 6/3/17: 0%->10; 5/6/17: 10%->65; 5/6/17: 65%->90; 14/9/17: 90%->96; 15/12/17: 96%->100 | 24.381, 24.382, 24.383, 24.384 | 74 | 38 |  |  | Thu 01/12/16 | Fri 15/12/17
870 | 740030 | CT3 aspects of MCData | MCImp-MCDATA-CT | 4 | Rel-14 | C3 | 2016-12-01 08:00 | 2017-03-15 17:00 | 100% | CP-160826 |  | HASON, Baruh | baruh.hason@motorolasolutions.com | 5/6/17: 0%->100 | 29.165, 29.213, 29.214 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
871 | 740031 | CT4 aspects of MCData | MCImp-MCDATA-CT | 4 | Rel-14 | C4 | 2016-12-01 08:00 | 2017-03-15 17:00 | 100% | CP-160826 |  | HASON, Baruh | baruh.hason@motorolasolutions.com | 6/3/17: 0%->100 | 23.003, 23.335, 29.283 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
872 | 740032 | CT6 aspects of MCData | MCImp-MCDATA-CT | 4 | Rel-14 | C6 | 2016-12-01 08:00 | 2017-06-14 17:00 | 100% | CP-160826 |  | HASON, Baruh | baruh.hason@motorolasolutions.com | No work identified. | 31.102, 31.103 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
873 | 730047 | Security of the Mission Critical Service | MCSec | 2 | Rel-14 | S3 | 2016-09-19 08:00 | 2017-06-15 17:00 | 100% | SP-160566 |  | Haigh, Peter, CESG | peter.haigh@cesg.gsi.gov.uk | 6/10/16: 33.180 added; 1/12/16: 0%->25; 6/3/17: 25%->60; 7/6/17: 60%->85; 11/9/17: 85%->100 | 33.180 | 73 | 37 |  |  | Mon 19/09/16 | Mon 11/09/17
874 | 790052 | UE Conformance Test Aspects - Mission Critical Improvements | MCImp-UEConTest | 2 | Rel-14 | R5 | 2018-03-15 08:00 | 2019-12-13 17:00 | 5% | RP-180527 |  | NIST |  | tested: REL-14 WI MCImp (SA/CT WI: Mission Critical Improvements); to provide conformance test specifications for the Rel-14 core requirements for improvements to Mission Critical Services (MCPTT, MCVideo and MCData).; |  | 79 | 40 |  |  | Tue 27/03/18 | Wed 27/06/18
875 | 730008 | Protocol enhancements for MCPTT over LTE | MCPTTProtoc1 | 1 | Rel-14 | ct | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160581 |  | Ricky Kaura | ricky.kaura@samsung.com | This Feature is a stage-3 only feature that fixes/enhances MCPTT protocol level (not visible from stage2). Not to be confused with Rel-14 MCPTT Stage 3. |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
876 | 730009 | CT1 aspects of MCPTTProtoc1 | MCPTTProtoc1 | 2 | Rel-14 | C1 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160581 |  | Ricky Kaura | ricky.kaura@samsung.com | 6/3/17: 5%->100 | 24.229, 24.379, 24.380, 24.381, 24.382, 24.383, 24.384, 24.980 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
877 | 730010 | CT3 aspects of MCPTTProtoc1 | MCPTTProtoc1 | 2 | Rel-14 | C3 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160581 |  | Ricky Kaura | ricky.kaura@samsung.com | 2/12/16: 0%->20; 6/3/17: 20%->100 | 29.165, 29.212, 29.213, 29.214 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
878 | 730011 | CT4 aspects of MCPTTProtoc1 | MCPTTProtoc1 | 2 | Rel-14 | C4 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160581 |  | Ricky Kaura | ricky.kaura@samsung.com | 6/3/17: 0%->100 | 23.003, 23.008, 29.283 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
879 | 730012 | CT6 aspects of MCPTTProtoc1 | MCPTTProtoc1 | 2 | Rel-14 | C6 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160581 |  | Ricky Kaura | ricky.kaura@samsung.com | 5/6/17: 0%->100. No more work identified. | 31.102 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
880 | 0 | Release 14 on V2X | - | 1 | Rel-14 |  | 2016-06-09 08:00 | 2016-06-09 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
881 | 720030 | LTE support for V2X services | V2XLTE | 1 | Rel-14 |  | 2015-02-09 08:00 | 2018-12-14 17:00 | 95% | SP-150573 |  |  |  | 7/12/15: 0%->5; 28/1/16: 22.185 added; 2/3/16: 5%->90; 9/6/16: 90%->100 | 22.278; 22.185 | 68 | 35 |  |  | Wed 09/09/15 | Thu 09/06/16
882 | 690035 | Stage 1 for LTE support for V2X services | V2XLTE | 2 | Rel-14 | S1 | 2015-09-09 08:00 | 2016-03-17 17:00 | 100% | SP-150573 |  |  |  | 7/12/15: 0%->5; 28/1/16: 22.185 added; 2/3/16: 5%->90; 9/6/16: 90%->100 | 22.278; 22.185 | 68 | 35 |  |  | Wed 09/09/15 | Thu 09/06/16
883 | 720011 | Architecture enhancements for LTE support of V2X services | V2XARC | 2 | Rel-14 | S2 | 2016-06-09 08:00 | 2016-12-15 17:00 | 100% | SP-160317 |  | LG Electronics, LaeYoung Kim | laeyoung.kim@lge.com | 28/7/16: 23.285 added; 19/9/16: 0%->85; 1/12/16: FCD:09/16->12/16; 1/12/16: 85%->100 | 23.285 | 72 | 37 |  |  | Thu 09/06/16 | Thu 01/12/16
884 | 740009 | Security aspect of LTE support of V2X services | V2XLTE-Sec | 2 | Rel-14 | S3 | 2016-12-01 08:00 | 2017-06-15 17:00 | 100% | SP-160955 |  | Huawei, Marcus Wong | mwong@huawei.com | 6/3/17: 0%->75; 7/6/17: 75%->100 | 33.185 | 74 | 38 |  |  | Thu 01/12/16 | Wed 07/06/17
885 | 720090 | RAN aspects of LTE-based V2X Services | LTE_V2X | 2 | Rel-14 |  | 2016-06-15 08:00 | 2018-12-14 17:00 | 85% | RP-161298 |  | LG Electronics |  | follow-up WI of REL-14 SI FS_LTE_V2X |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
886 | 720190 | Core part: LTE-based V2X Services | LTE_V2X-Core | 3 | Rel-14 | R1 | 2016-06-15 08:00 | 2017-03-15 17:00 | 100% | RP-162519 | RP-170237 | LG Electronics |  | follow-up WI of REL-14 SI FS_LTE_V2X26/9/16: Compl:0%->15%26/9/16: WID: RP-161298->RP-161894; 6/10/16: 36.786 added; 6/10/16: added; 20/12/16: Compl:15%->75% 21/3/17: Compl:75%->100% | 36.786; | 72 | 37 |  |  | Fri 01/07/16 | Tue 21/03/17
887 | 720290 | Perf. part: LTE-based V2X Services | LTE_V2X-Perf | 3 | Rel-14 | R4 | 2016-06-15 08:00 | 2017-09-15 17:00 | 100% | RP-162519 |  | LG Electronics |  | ; 26/9/16: WID: RP-161298->RP-161894; 20/12/16: WID: RP-161894->RP-162519; 20/12/16: Stat Rep: ->RP-162519; 19/6/17: Compl:0%->75%; 19/9/17: Compl:75%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 19/09/17
888 | 760086 | UE Conformance Test Aspects - Support for LTE-based V2X Services | LTE_V2X-UEConTest | 3 | Rel-14 | R5 | 2017-06-15 08:00 | 2018-12-14 17:00 | 65% | RP-172356 |  | Huawei |  | ; 19/9/17: Compl:0%->20%; 8/1/18: Compl:20%->40%; 27/3/18: Compl:40%->55% |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
889 | 730026 | CT aspects of V2X Services | V2X-CT | 2 | Rel-14 | ct | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160584 |  | Taehun Kim | taehun78.kim@lge.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
890 | 730027 | CT1 aspects of V2X Services | V2X-CT | 3 | Rel-14 | C1 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160584 |  | Taehun Kim | taehun78.kim@lge.com | 6/10/16: 24.385 added; 6/10/16: 24.386 added; 2/12/16: 0%->65; 6/3/17: 65%->100 | 23.122, 24.301, 24.334; 24.385; 24.386 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
891 | 730028 | CT3 aspects of V2X Services | V2X-CT | 3 | Rel-14 | C3 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160584 |  | Taehun Kim | taehun78.kim@lge.com | 6/10/16: 29.387 added; 2/12/16: 0%->40; 6/3/17: 40%->60; 5/6/17: 60%->100 | 29.212, 29.468; 29.387 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
892 | 730029 | CT4 aspects of V2X Services | V2X-CT | 3 | Rel-14 | C4 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160584 |  | Taehun Kim | taehun78.kim@lge.com | 6/10/16: 29.388 added; 6/10/16: 29.389 added; 2/12/16: 0%->80; 6/3/17: 80%->100 | 23.003, 23.007, 23.008, 29.272; 29.388; 29.389 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
893 | 730030 | CT6 aspects of V2X Services | V2X-CT | 3 | Rel-14 | C6 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160584 |  | Taehun Kim | taehun78.kim@lge.com | 7/3/17: 0%->100 | 31.102, 31.111 | 73 | 37 |  |  | Fri 16/09/16 | Tue 07/03/17
894 | 700019 | Study on LTE support for V2X services | FS_V2XLTE | 2 | Rel-14 |  | 2015-02-09 08:00 | 2016-06-17 17:00 | 100% | SP-150051 |  | Ki-Dong Lee (LG electronics) | kidong.lee@lge.com | 1/4/15:TR number added; June2015: Compl:25%->50; 07/09/15: 50%->75 | New TR 22.885 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/09/15
895 | 670009 | Study on Stage 1 of LTE support for V2X services | FS_V2XLTE_S1 | 3 | Rel-14 | S1 | 2015-02-09 08:00 | 2015-02-09 17:00 | 100% | SP-150051 |  | Ki-Dong Lee (LG electronics) | kidong.lee@lge.com | 1/4/15:TR number added; June2015: Compl:25%->50; 07/09/15: 50%->75; 7/12/15: 75%->100 | New TR 22.885 | 67 | 34 |  |  | Mon 07/12/15 | Mon 07/12/15
896 | 700050 | Study on Stage 2 of LTE support for V2X services | FS_V2XARC | 3 | Rel-14 | S2 | 2015-09-07 08:00 | 2016-06-17 17:00 | 100% | SP-150852 |  | LG Electronics, LaeYoung Kim | laeyoung.kim@lge.com | 11/12/15: WID:SP-150625->SP-150743; 7/3/16: 10%->22; 7/3/16: WID:SP-150743->SP-150852; 9/6/16: 22%->80; 19/9/16: 80%->100 | TR 23.785 | 70 | 36 |  |  | Mon 07/12/15 | Mon 19/09/16
897 | 760072 | Study on Security of LTE support for V2X services | FS_V2XARC_S3 | 3 | Rel-14 | S3 | 2015-09-07 08:00 | 2016-06-17 17:00 | 100% | SP-150852 |  |  |  | Introduced at 100% completion, as per SA3 report to SA#76 | TR 33.885 | 70 | 36 |  |  | Mon 07/12/15 | Mon 19/09/16
898 | 680058 | RAN1 Study on LTE-based V2X Services | FS_LTE_V2X | 3 | Rel-14 | R1 | 2015-06-15 08:00 | 2016-06-15 17:00 | 100% | RP-161263 |  | LG Electronics |  | 29/09/15: Compl:0%->5% 29/09/15: Stat Rep: -->RP-151311 ; 28/1/16: 33.885 added;22/3/16: Compl:35%->50%22/3/16: CD:Wed 15/06/16->Thu 15/09/1622/3/16: WID: RP-15; | 33.885 | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/07/16
899 | 700061 | Support for V2V services based on LTE sidelink | LTE_SL_V2V | 1 | Rel-14 |  | 2015-12-15 08:00 | 2018-09-14 17:00 | 99% | RP-152293 |  | LG Electronics |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
900 | 700161 | Core part: Support for V2V services based on LTE sidelink | LTE_SL_V2V-Core | 2 | Rel-14 | R1 | 2015-12-15 08:00 | 2016-09-15 17:00 | 100% | RP-161603 |  | LG Electronics |  | 22/3/16: Compl:0%->15%22/3/16: WID: RP-152293->RP-1606491/7/16: Compl:15%->60%1/7/16: WID: RP-160649->RP-161272; 28/7/16: 36.785 added; 26/9/16: Compl:60%->100%; 26/9/16: WID: RP-161272->RP-161603 | 36.785 | 70 | 36 |  |  | Fri 01/01/16 | Mon 26/09/16
901 | 700261 | Perf. part: Support for V2V services based on LTE sidelink | LTE_SL_V2V-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 100% | RP-161603 |  | LG Electronics |  | 22/3/16: WID: RP-152293->RP-1606491/7/16: WID: RP-160649->RP-16127226/9/16: WID: RP-161272->RP-161603; 20/12/16: Compl:0%->50% 21/3/17: Compl:50%->80% 21/3/17: CD:Wed 15/03/17->Thu 15/06/1719/6/17: Compl:80%->100% |  | 70 | 36 |  |  | Fri 01/01/16 | Mon 19/06/17
902 | 730073 | UE Conformance Test Aspects - Support for V2V services based on LTE sidelink | LTE_SL_V2V-UEConTest | 2 | Rel-14 | R5 | 2016-09-15 08:00 | 2018-09-14 17:00 | 98% | RP-172358 |  | Huawei |  | ; 20/12/16: Compl:0%->5% 21/3/17: Compl:5%->15%19/9/17: Compl:15%- 8/1/18: Com27/ ; |  | 73 | 37 |  |  | Mon 26/09/16 | Wed 27/06/18
903 | 0 | Release 14 on CIoT | - | 1 | Rel-14 |  | 2016-06-09 08:00 | 2016-06-09 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
904 | 710023 | Non-IP for Cellular Internet of Things (CIoT) for 2G/3G-GPRS(EC-EGPRS) | NonIP_GPRS | 1 | Rel-14 |  | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | SP-160196 | [5 empty] | 71 | 36 |  |  | Wed 02/03/16 | Wed 02/03/16
905 | 710024 | Non-IP for Cellular IoT for EC-EGPRS | NonIP_GPRS | 2 | Rel-14 | S2 | 2016-03-02 08:00 | 2016-06-15 17:00 | 100% | SP-160196 |  | Hans Ronneke, Ericsson | hans . Ronneke (a) ericsson . Com | 9/6/16: 0%->50; 19/9/16: 50%->100 | 23.060, 23.682, 23.401? | 71 | 36 |  |  | Wed 02/03/16 | Mon 19/09/16
906 | 710025 | CT aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 2 | Rel-14 |  | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: WID:CP-160161->CP-160293 |  | 71 | 36 |  |  | Wed 02/03/16 | Sat 11/06/16
907 | 710026 | CT1 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 3 | Rel-14 | C1 | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: 0%->50; 11/6/16: WID:CP-160161->CP-160293; 16/9/16: 50%->65; 2/12/16: 65%->100 | 24.008 | 71 | 36 |  |  | Wed 02/03/16 | Fri 02/12/16
908 | 720069 | CT3 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 3 | Rel-14 | C3 | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: WID:CP-160161->CP-160293; 13/6/16: 0%->65; 20/9/16: 0%->100 | 29.060, 29.274, 29.002, 29.303, 23.008, 29.128, 29.272, 23.007 | 72 | 37 |  |  | Wed 02/03/16 | Tue 20/09/16
909 | 710027 | CT4 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS | NonIP_GPRS-CT | 3 | Rel-14 | C4 | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160293 |  | Orange, Youssef CHADLI | youssef.chadli@orange.com | 11/6/16: WID:CP-160161->CP-160293; 13/6/16: 0%->65; 2/12/16: 65%->100 | 29.060, 29.274, 29.002, 29.303, 23.008, 29.128, 29.272, 23.007 | 71 | 36 |  |  | Wed 02/03/16 | Fri 02/12/16
910 | 720092 | Further enhanced MTC for LTE | LTE_feMTC | 1 | Rel-14 |  | 2016-06-15 08:00 | 2018-09-14 17:00 | 79% | RP-161321 |  | Ericsson |  |  |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
911 | 720192 | Core part: Further enhanced MTC for LTE | LTE_feMTC-Core | 2 | Rel-14 | R1 | 2016-06-15 08:00 | 2017-06-15 17:00 | 100% | RP-170532 | RP-171441 | Ericsson |  | 26/9/16: Compl:0%->12%26/9/16: WID: RP-161321->RP-161464; 20/12/16: Compl:12%->70%; 20/12/16: WID: RP-161464->RP-16252021/3/17: Compl:70%->95% ; 21/3/17: CD19/6/17: Compl:95%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
912 | 720292 | Perf. part: Further enhanced MTC for LTE | LTE_feMTC-Perf | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2017-12-15 17:00 | 100% | RP-170532 |  | Ericsson |  | ; 26/9/16: WID: RP-161321->RP-161464; 20/12/16: WID: RP-161464->RP-162520; 20/12/16: Stat Rep: ->RP-16252021/3/17: CD:Fri 15/09/17->Fri 15/12/1721/3/17 19/6/17: Compl:0%->35%19/9/17: Compl:35%->60%; 8/1/18: Compl:60%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 08/01/18
913 | 770063 | UE Conformance Test Aspects - Further enhanced MTC for LTE | LTE_feMTC-UEConTest | 2 | Rel-14 | R5 | 2017-09-15 08:00 | 2018-09-14 17:00 | 26% | RP-180414 |  | Ericsson |  | ; 8/1/18: Compl:0%->6%; 27/3/18: Compl:6%->21%; ; 2 |  | 77 | 39 |  |  | Tue 19/09/17 | Wed 27/06/18
914 | 720093 | Enhancements of NB-IoT | NB_IOTenh | 1 | Rel-14 |  | 2016-06-15 08:00 | 2018-12-14 17:00 | 100% | RP-161324 |  | Huawei |  |  |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
915 | 720193 | Core part: Enhancements of NB-IoT | NB_IOTenh-Core | 2 | Rel-14 | R1 | 2016-06-15 08:00 | 2017-06-15 17:00 | 100% | RP-171060 | RP-171061 | Huawei |  | 26/9/16: Compl:0%->13%26/9/16: WID: RP-161324->RP-161901; 20/12/16: Compl:13%->70%; 21/3/17: Compl:70%->95%; 21/3/17: CD:Wed 15/03/17->Thu 15/06/1719/6/17: Compl:95%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
916 | 720293 | Perf. part: Enhancements of NB-IoT | NB_IOTenh-Perf | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2017-12-15 17:00 | 100% | RP-171060 |  | Huawei |  | 26/9/16: WID: RP-161324->RP-16190121/3/17: CD:Fri 15/09/17->Fri 15/12/17; 19/6/17: Compl:0%->50%; 19/6/17: WID: RP-161901->RP-171060; 19/9/17: Compl:50%->60%; 8/1/18: Compl:60%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 08/01/18
917 | 770061 | UE Conformance Test Aspects - Enhancements of NB-IoT | NB_IOTenh-UEConTest | 2 | Rel-14 | R5 | 2017-09-15 08:00 | 2018-12-14 17:00 | 100% | RP-182428 |  | Huawei |  | ; 8/1/18: Compl:0%->5%27/3/18: Compl:5%->30%; 27/6/18: C; 16/1/19: 60%->100; 16/1/19: WID:RP-171781->RP-182428 |  | 77 | 39 |  |  | Tue 19/09/17 | Wed 16/01/19
918 | 730021 | AT Commands for CIoT | AT_CIoT | 1 | Rel-14 | C1 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160477 |  | John-Luc Bakker |  | 2/12/16: 10%->95; 6/3/17: 95%->100 |  | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
919 | 730359 | Extended architecture support for Cellular Internet of Things | CIoT_Ext | 1 | Rel-14 |  | 2016-06-17 08:00 | 2017-03-14 17:00 | 100% | SP-160732 |  | Intel : Puneet Jain | puneet.jain@intel.com |  | 23.401, 23.682, 23.060 | 73 | 37 |  |  | Mon 19/09/16 | Mon 19/09/16
920 | 720081 | Study on extended architecture support for Cellular Internet of Things | FS_CIoT_Ext | 2 | Rel-14 | S2 | 2016-06-17 08:00 | 2016-12-15 17:00 | 100% | SP-160505 |  | Intel : Puneet Jain | puneet.jain@intel.com | 28/7/16: 23.730 added; 19/9/16: 0%->70; 1/12/16: FCD:03/17->12/16; 1/12/16: 70%->100 | 23.730 | 72 | 37 |  |  | Fri 17/06/16 | Thu 01/12/16
921 | 730059 | Stage 2 of Extended architecture support for Cellular Internet of Things | CIoT_Ext | 2 | Rel-14 | S2 | 2016-09-15 08:00 | 2016-12-16 17:00 | 100% | SP-160830 |  | Intel : Puneet Jain | puneet.jain@intel.com | 1/12/16: 0%->100; 1/12/16: WID:SP-160732->SP-160830 | 23.401, 23.682, 23.060, 23.271 | 73 | 37 |  |  | Mon 19/09/16 | Thu 01/12/16
922 | 740038 | Stage 3 of extended architecture enhancements for Cellular Internet of Things | CIoT_Ext-CT | 2 | Rel-14 | ct | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160701 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 21/3/17: 24.250 added; | 24.250 | 74 | 38 |  |  | Thu 01/12/16 | Tue 21/03/17
923 | 740039 | CT1 aspects of extended architecture enhancements for Cellular Internet of Things | CIoT_Ext-CT | 3 | Rel-14 | C1 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160701 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 6/3/17: 0%->50; 5/6/17: 50%->100 | 24.301, 24.008 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
924 | 740040 | CT4 aspects of extended architecture enhancements for Cellular Internet of Things | CIoT_Ext-CT | 3 | Rel-14 | C4 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160701 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 6/3/17: 0%->90; 5/6/17: 90%->100 | 23.008, 29.272, 29.002, 29.336, 29.128, 29.171, 29.172, 29.173 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
925 | 730077 | Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_radio_enh | 1 | Rel-14 | R6 | 2016-09-15 08:00 | 2018-06-15 17:00 | 99% | RP-161806 |  | Nokia |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
926 | 730177 | Core part: Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_radio_enh-Core | 2 | Rel-14 | R6 | 2016-09-15 08:00 | 2017-06-15 17:00 | 100% | RP-161806 | RP-171321 | Nokia |  | ; 20/12/16: Compl:0%->50% 21/3/17: Compl:50%->80%19/6/17: Compl:80%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
927 | 730277 | Perf. part: Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things | CIoT_EC_GSM_radio_enh-Perf | 2 | Rel-14 | R6 | 2018-03-15 08:00 | 2018-06-15 17:00 | 100% | RP-161806 |  | Nokia |  | ; 20/12/16: Compl:0%->20% ; 21/3/17: Compl:20%->80%; 19/6/17: Compl:80%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
928 | 730083 | New band support for Rel-14 Narrowband Internet of Things (NB-IOT) | NB_IOT_R14_bands | 1 | Rel-14 | R4 | 2016-09-15 08:00 | 2017-09-15 17:00 | 99% | RP-161890 |  | Ericsson |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
929 | 730183 | Core part: New band support for Rel-14 Narrowband Internet of Things (NB-IOT) | NB_IOT_R14_bands-Core | 2 | Rel-14 | R4 | 2016-09-15 08:00 | 2017-06-15 17:00 | 100% | RP-170139 | RP-170970 | Ericsson |  | ; 20/12/16: Compl:0%->99% 21/3/17: CD:Wed 15/03/17->Thu 15/06/17;19/6/17: Compl:99%->100%19/6/17: Stat Rep: ->RP-170970 |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
930 | 730283 | Perf. part: New band support for Rel-14 Narrowband Internet of Things (NB-IOT) | NB_IOT_R14_bands-Perf | 2 | Rel-14 | R4 | 2016-09-15 08:00 | 2017-06-15 17:00 | 100% | RP-170139 |  | Ericsson |  | ; 20/12/16: Compl:0%->99% 21/3/17: Compl:99%->70% 19/6/17: Compl:70%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
931 | 750057 | UE Conformance Test Aspects - New band support for Rel-14 NB-IoT | NB_IOT_R14_bands-UEConTest | 2 | Rel-14 | R5 | 2017-03-15 08:00 | 2017-09-15 17:00 | 100% | RP-170495 |  | Ericsson |  | tested: REL-14 NB_IOT_R14_bands-Core (which got an exception at RAN #75 to still complete in REL-14 by RAN #76); |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 19/09/17
932 | 720006 | Enhancements of Dedicated Core Networks selection mechanism | eDecor | 1 | Rel-14 |  | 2015-09-17 08:00 | 2017-12-15 17:00 | 99% | SP-160310 | SP-170537 | Roland Gustafsson | Roland.Gustafsson@ericsson.com | 7/12/15: 0%->70; 7/3/16: 70%->80; 9/6/16: 80%->95 | 23.711 | 69 | 35 |  |  | Thu 17/09/15 | Thu 09/06/16
933 | 690051 | Study on Enhancements of Dedicated Core Networks selection mechanism | FS_eDecor | 2 | Rel-14 | S2 | 2015-09-17 08:00 | 2016-03-18 17:00 | 100% | SP-150518 |  | Roland Gustafsson | Roland.Gustafsson@ericsson.com | 7/12/15: 0%->70; 7/3/16: 70%->80; 9/6/16: 80%->95; 19/9/16: 95%->100 | 23.711 | 69 | 35 |  |  | Thu 17/09/15 | Mon 19/09/16
934 | 720007 | Enhancements of Dedicated Core Networks selection mechanism | eDecor | 2 | Rel-14 | S2 | 2016-06-09 08:00 | 2016-09-15 17:00 | 100% | SP-160310 |  | Roland Gustafsson | Roland.Gustafsson@ericsson.com | 19/9/16: 70%->100 | 23.401, 23.060, 23.251 | 72 | 37 |  |  | Thu 17/09/15 | Mon 19/09/16
935 | 730013 | CT aspects of eDecor | eDecor-CT | 2 | Rel-14 | ct | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160475 |  | Mikael Wass | Mikael.wass@ericsson.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
936 | 730014 | CT1 aspects of eDecor | eDecor-CT | 3 | Rel-14 | C1 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160475 |  | Mikael Wass | Mikael.wass@ericsson.com | 2/12/16: 0%->80; 6/3/17: 80%->95; 5/6/17: 95%->100 | 24.301, 24.008, 24.368 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
937 | 730015 | CT4 aspects of eDecor | eDecor-CT | 3 | Rel-14 | C4 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160475 |  | Mikael Wass | Mikael.wass@ericsson.com | 2/12/16: 0%->10; 6/3/17: 10%->100 | 29.303, 23.003, 23.008 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
938 | 730016 | CT6 aspects of eDecor | eDecor-CT | 3 | Rel-14 | C6 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160475 |  | Mikael Wass | Mikael.wass@ericsson.com | 14/12/16: 0%->15; 7/3/17: 15%->85; 5/6/17: 85%->100 | 31.102, 31.111 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
939 | 740067 | RAN aspects of eDECOR for UMTS and LTE | eDECOR-UTRA_LTE | 2 | Rel-14 | R3 | 2016-12-15 08:00 | 2017-12-15 17:00 | 99% | RP-162543 |  | Ericsson |  |  |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 20/12/16
940 | 740167 | Core part: RAN aspects of eDECOR for UMTS and LTE | eDECOR-UTRA_LTE-Core | 3 | Rel-14 | R3 | 2016-12-15 08:00 | 2017-03-15 17:00 | 100% | RP-162543 | RP-170547 | Ericsson |  | 21/3/17: Compl:0%->100%21/3/17: Stat Rep: ->RP-170547 |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
941 | 760088 | UE Conformance Test Aspects - Enhancements of Dedicated Core Networks for UTRA and LTE | eDECOR-UTRA_LTE-UEConTest | 3 | Rel-14 | R5 | 2017-06-15 08:00 | 2017-12-15 17:00 | 100% | RP-171899 |  | Ericsson |  | ; 19/9/17: Compl:0%->50%; 8/1/18: Compl:50%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Mon 08/01/18
942 | 760002 | Deleted - GSM aspects of eDECOR | eDecor | 2 | Rel-14 | R6 | 2017-04-04 08:00 | 2017-06-15 17:00 | 100% | SP-160310 |  | Ericsson |  | Verbal addition by Paolo U. 21/09/17: verbal deletion by Paolo | 44.060, 44.018, 48.018 | 76 | 39 |  |  | Mon 29/05/17 | NA
943 | 740078 | Addition of band 25 and 26 to LTE MTC cat.0 | LC_MTC_LTE_cat0_B25_B26 | 1 | Rel-14 | R4 | 2016-12-15 08:00 | 2017-03-15 17:00 | 100% | RP-162572 |  | Sprint |  |  |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 20/12/16
944 | 740178 | Core part: Addition of band 25 and 26 to LTE MTC cat.0 | LC_MTC_LTE_cat0_B25_B26-Core | 2 | Rel-14 | R4 | 2016-12-15 08:00 | 2017-03-15 17:00 | 100% | RP-162572 |  | Sprint |  | ; 21/3/17: Compl:0%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
945 | 740179 | Addition of bands 25 and 40 to LTE MTC cat.1 | LTE_MTCe2_L1_cat1_B25_B40-Core | 1 | Rel-14 | R4 | 2016-12-15 08:00 | 2017-03-15 17:00 | 100% | RP-162573 |  | Sprint |  | ; 21/3/17: Compl:0%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
946 | 0 | Release 14 on WLAN | - | 1 | Rel-14 |  | 2016-06-09 08:00 | 2016-06-09 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
947 | 720031 | EIR check for WLAN access to EPC | EWE | 1 | Rel-14 |  | 2015-11-02 08:00 | 2016-09-15 17:00 | 100% | SP-150624 |  | Alcatel-Lucent, Nicolas Drevon | Nicolas.Drevon@alcatel-lucent.com | 7/3/16: 45%->60; 9/6/16: 60%->100 | 23.002, 23.402 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
948 | 700039 | Stage 2 of EWE | EWE | 2 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-06-17 17:00 | 100% | SP-150624 |  | Alcatel-Lucent, Nicolas Drevon | Nicolas.Drevon@alcatel-lucent.com | 7/3/16: 45%->60; 9/6/16: 60%->100 | 23.002, 23.402 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
949 | 720002 | CT aspects of EWE | EWE-CT | 2 | Rel-14 | ct | 2016-06-13 08:00 | 2016-09-15 17:00 | 100% | CP-160244 |  | Nokia, Bruno Landais | bruno.landais@nokia.com |  |  | 72 | 37 |  |  | Mon 13/06/16 | NA
950 | 720032 | CT1 aspects of EWE | EWE-CT | 3 | Rel-14 | C1 | 2016-06-13 08:00 | 2016-09-15 17:00 | 100% | CP-160244 |  | Nokia, Bruno Landais | bruno.landais@nokia.com | 16/9/16: 0%->100 | 24.302 | 72 | 37 |  |  | Mon 13/06/16 | Fri 16/09/16
951 | 720033 | CT4 aspects of EWE | EWE-CT | 3 | Rel-14 | C4 | 2016-06-13 08:00 | 2016-09-15 17:00 | 100% | CP-160244 |  | Nokia, Bruno Landais | bruno.landais@nokia.com | 2/12/16: 0%->100 | 29.273 | 72 | 37 |  |  | Mon 13/06/16 | Fri 02/12/16
952 | 730048 | Support of EAP Re-authentication Protocol for WLAN Interworking | ERP | 1 | Rel-14 |  | 2016-09-16 08:00 | 2017-03-16 17:00 | 100% | SP-160568 |  | ORANGE, Todor Gamishev | Todor dot Gamishev at Orange dot com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
953 | 730049 | Support of EAP Re-authentication Protocol for WLAN Interworking | ERP | 2 | Rel-14 | S3 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | SP-160568 |  | ORANGE, Todor Gamishev | Todor dot Gamishev at Orange dot com | 1/12/16: 0%->90; 6/3/17: 90%->100 | 33.402 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
954 | 730003 | CT aspects of ERP | ERP-CT | 2 | Rel-14 | ct | 2016-09-16 08:00 | 2017-03-16 17:00 | 100% | CP-160413 |  | Orange, Julien Bournelle | Julien.bournelle@orange.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
955 | 730045 | CT1 aspects of ERP | ERP-CT | 3 | Rel-14 | C1 | 2016-09-16 08:00 | 2017-03-16 17:00 | 100% | CP-160413 |  | Orange, Julien Bournelle | Julien.bournelle@orange.com | 2/12/16: 0%->80; 6/3/17: 80%->95; 5/6/17: 95%->100 | 24.302 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
956 | 730046 | CT4 aspects of ERP | ERP-CT | 3 | Rel-14 | C4 | 2016-09-16 08:00 | 2017-03-16 17:00 | 100% | CP-160413 |  | Orange, Julien Bournelle | Julien.bournelle@orange.com | 2/12/16: 0%->50; 6/3/17: 50%->95; 5/6/17: 95%->100 | 29.273, 23.008, 23.003 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
957 | 720019 | Phase 2 of the Support of Emergency services over WLAN | SEW2 | 1 | Rel-14 |  | 2015-09-01 08:00 | 2017-03-15 17:00 | 100% | SP-160307 |  | Nicolas Drevon | nicolas.drevon@nokia.com |  | new 23.771, TS 23.402, TS 23.167 | 72 | 37 |  |  | Wed 01/04/15 | Thu 09/06/16
958 | 690033 | Study on Phase 2 of the Support of Emergency services over WLAN | FS_SEW2 | 2 | Rel-14 | S2 | 2015-09-01 08:00 | 2016-06-16 17:00 | 100% | SP-160173 |  | Laurent Thiebaut, Alcatel Lucent | Laurent.thiebaut@alcatel-lucent.com | June2015: Compl:0%->100, SP-150151->SP-150251; 7/12/15: 0%->30, FCD: 12/15->06/16; 7/3/16: 30%->75; 7/3/16: WID:SP-150251->SP-160173; 9/6/16: 75%->100 | new 23.771 | 67 | 34 |  |  | Wed 01/04/15 | Thu 09/06/16
959 | 720018 | Support of Emergency services over WLAN - phase 2 | SEW2 | 2 | Rel-14 | S2 | 2016-06-13 08:00 | 2016-09-15 17:00 | 100% | SP-160307 |  | Nicolas Drevon | nicolas.drevon@nokia.com | 11/6/16: 0%->45; 19/9/16: 45%->100 | TS 23.402, TS 23.167 | 72 | 37 |  |  | Wed 01/04/15 | Mon 19/09/16
960 | 730017 | CT aspects of SEW2 | SEW2-CT | 2 | Rel-14 | ct | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160694 |  | Jennifer Liu | jennifer.liu@nokia.com | 5/12/16: WID:CP-160476->CP-160694 |  | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/12/16
961 | 730018 | CT1 aspects of SEW2 | SEW2-CT | 3 | Rel-14 | C1 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160694 |  | Jennifer Liu | jennifer.liu@nokia.com | 2/12/16: 20%->95; 5/6/17: 95%->100 | 24.302, 24.312, 24.301, 24.244, 24.229, 24.237 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
962 | 730019 | CT4 aspects of SEW2 | SEW2-CT | 3 | Rel-14 | C4 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160694 |  | Jennifer Liu | jennifer.liu@nokia.com | 2/12/16: 0%->100 | 23.003, 29.272, 29.273, 29.274, 29.328 | 73 | 37 |  |  | Fri 16/09/16 | Fri 02/12/16
963 | 730020 | Deleted - CT6 aspects of SEW2 | SEW2-CT | 3 | Rel-14 | C6 | 2016-12-14 08:00 | 2016-12-14 17:00 | 100% | CP-160694 |  | Jennifer Liu | jennifer.liu@nokia.com | Deleted at CT6#82 | 31.102 | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
964 | 720076 | T-ADS supporting WLAN Access | TADS_WLAN | 1 | Rel-14 | S2 | 2016-03-15 08:00 | 2016-09-15 17:00 | 100% | SP-160488 | SP-170519 | Jiang Yi | jiangyi (at) chinamobile (dot) com | 19/9/16: 0%->100 | TS 23.292, TS 23.221, TS 23.402 | 72 | 37 |  |  | Fri 17/06/16 | Mon 19/09/16
965 | 710075 | Enhanced LTE-WLAN Aggregation (LWA) | LTE_WLAN_aggr | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-03-15 17:00 | 100% | RP-160600 |  | Intel |  | follow-up WI of REL-13 WI LTE_WLAN_radio; no Perf. part |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
966 | 710175 | Core part: Enhanced LTE-WLAN Aggregation (LWA) | LTE_WLAN_aggr-Core | 2 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-03-15 17:00 | 100% | RP-160923 | RP-170330 | Intel |  | follow-up WI of REL-13 WI LTE_WLAN_radio; no Perf. part1/7/16: Compl:0%->25%1/7/16: WID: RP-160600->RP-160923; 26/9/16: Compl:25%->45%; 20/12/16: Compl:45%->75%; 20/12/16: Stat Rep: --> ; 21/3/17: Compl:75%->100% ; 21/3/17 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
967 | 0 | Release 14 on IMS | - | 1 | Rel-14 |  | 2016-06-09 08:00 | 2016-06-09 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
968 | 700020 | Evolution to and Interworking with eCall in IMS | EIEI | 1 | Rel-14 |  | 2015-05-11 08:00 | 2018-03-15 17:00 | 100% | SP-150275 | SP-170538 | Kurt Bischinger |  | 12/15: created by MCC to distinguish Stage 1 from Stage 2 | 22.101 | 68 | 35 |  |  | Mon 07/12/15 | Tue 09/06/15
969 | 680004 | Stage 1 of Evolution to and Interworking with eCall in IMS | EIEI | 2 | Rel-14 | S1 | 2015-05-11 08:00 | 2015-06-19 17:00 | 100% | SP-150275 |  | Kurt Bischinger |  |  | 22.101 | 68 | 35 |  |  | Tue 09/06/15 | Tue 09/06/15
970 | 700021 | Stage 2 of Evolution to and Interworking with eCall in IMS | EIEI | 2 | Rel-14 | S2 | 2015-12-11 08:00 | 2016-06-10 17:00 | 100% | SP-150623 |  | Haris Zisimopoulos, Qualcomm Incorporated | harisz@qti.qualcomm.com | 7/3/16: 0%->20; 9/6/16: 20%->100. FCD: 03/16->06/16 | 23.167, 23.401 | 68 | 35 |  |  | Mon 07/12/15 | Thu 09/06/16
971 | 710020 | CT aspects of evolution to and interworking with eCall in IMS | EIEI-CT | 2 | Rel-14 |  | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160053 |  | Lena Chaponniere | lguellec@qti.qualcomm.com |  |  | 71 | 36 |  |  | Wed 02/03/16 | Wed 02/03/16
972 | 710021 | CT1 aspects of evolution to and interworking with eCall in IMS | EIEI-CT | 3 | Rel-14 | C1 | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160053 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 11/6/16: 0%->35; 16/9/16: 35%->85; 2/12/16: 85%->100 | 24.229, 24.301 | 71 | 36 |  |  | Wed 02/03/16 | Fri 02/12/16
973 | 720068 | (IETF) Next-Generation Pan-European eCall (draft-ietf-ecrit-ecall) | EIEI-CT | 3 | Rel-14 | C1-IETF | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160053 |  |  |  | 18/12/17: 30%->100 | draft-ietf-ecrit-ecall | 72 | 37 |  |  | Wed 02/03/16 | Mon 18/12/17
974 | 710022 | CT6 aspects of evolution to and interworking with eCall in IMS | EIEI-CT | 3 | Rel-14 | C6 | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160053 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 16/9/16: 0%->100 | 31.102 | 71 | 36 |  |  | Wed 02/03/16 | Fri 16/09/16
975 | 760084 | UE Conformance Test Aspects - Evolution to and Interworking with eCall in IMS (EIEI) | EIEI-UEConTest | 2 | Rel-14 | R5 | 2017-06-15 08:00 | 2018-03-15 17:00 | 100% | RP-171057 |  | Qualcomm |  | ; 19/9/17: Compl:0%->45%; 8/1/18: Compl:45%->80%; 27/3/18: Compl:80%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Tue 27/03/18
976 | 720074 | Password based service activation for IMS Multimedia Telephony service | PWDIMS | 1 | Rel-14 |  | 2015-03-11 08:00 | 2016-12-15 17:00 | 100% | SP-150041 | SP-170536 | Peter Bleckert (Ericsson) |  | 1/4/15: rapporteur added, Impacted TS added. 31/07/15: 100% | 22.173 | 67 | 34 |  |  | Wed 04/03/15 | Fri 31/07/15
977 | 670012 | Stage 1 for PWDIMS | PWDIMS | 2 | Rel-14 | S1 | 2015-03-11 08:00 | 2015-03-13 17:00 | 100% | SP-150041 |  | Peter Bleckert (Ericsson) |  | 1/4/15: rapporteur added, Impacted TS added. 31/07/15: 100% | 22.173 | 67 | 34 |  |  | Wed 04/03/15 | Fri 31/07/15
978 | 720034 | CT aspects for PWDIMS | PWDIMS-CT | 2 | Rel-14 | ct | 2016-06-13 08:00 | 2016-12-15 17:00 | 100% | CP-160295 |  | Axell, Jörgen |  |  |  | 72 | 37 |  |  | Sat 11/06/16 | NA
979 | 720035 | CT1 aspects for PWDIMS | PWDIMS-CT | 3 | Rel-14 | C1 | 2016-06-13 08:00 | 2016-12-15 17:00 | 100% | CP-160295 |  | Axell, Jörgen |  | 2/12/16: 0%->15; 6/3/17: 15%->100 | 24.623, 24.611 | 72 | 37 |  |  | Sat 11/06/16 | Mon 06/03/17
980 | 720036 | CT3 aspects for PWDIMS | PWDIMS-CT | 3 | Rel-14 | C3 | 2016-06-13 08:00 | 2016-12-15 17:00 | 100% | CP-160295 |  | Axell, Jörgen |  | 5/6/17: 0%->100 | 29.292 | 72 | 37 |  |  | Sat 11/06/16 | Mon 05/06/17
981 | 630007 | IMS Signalling Activated Trace | ISAT | 1 | Rel-14 |  | 2014-03-05 08:00 | 2016-03-11 17:00 | 75% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | Mar 15: WID: CP-140195->CP-150091. ES in CP-150637. 8/3/16: Moved from Rel-13 at CT#71 | - | 63 | 32 |  |  | Wed 29/01/14 | Tue 08/03/16
982 | 630107 | CT1 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-14 | C1 | 2014-03-10 08:00 | 2016-03-11 17:00 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150728; 5/6/17: 0%->100 | 24.229, 24.323 | 63 | 32 |  |  | Wed 29/01/14 | Mon 05/06/17
983 | 651003 | (IETF) IMS Signalling Activated Trace (RFC8497) | ISAT | 2 | Rel-14 | C1-IETF | 2014-09-12 08:00 | 2016-03-11 17:00 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637; 13/6/16: 25%->28 | draft-dawes-sipping-debug | 65 | 33 |  |  | Tue 02/09/14 | Mon 13/06/16
984 | 651103 | (IETF) IMS Signalling Activated Trace (RFC8497) | ISAT | 2 | Rel-14 | C3-IETF | 2014-09-12 08:00 | 2016-03-11 17:00 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637 | draft-dawes-sipping-debug | 65 | 33 |  |  | Tue 02/09/14 | Tue 09/12/14
985 | 651203 | (IETF) IMS Signalling Activated Trace (RFC8497) | ISAT | 2 | Rel-14 | C4-IETF | 2014-09-12 08:00 | 2016-03-11 17:00 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637; 5/6/17: 25%->70 | draft-dawes-sipping-debug | 65 | 33 |  |  | Tue 02/09/14 | Mon 05/06/17
986 | 630207 | CT3 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-14 | C3 | 2014-03-10 08:00 | 2016-03-11 17:00 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637; 5/6/17: 0%->100 | 29.165 | 63 | 32 |  |  | Wed 29/01/14 | Mon 05/06/17
987 | 630307 | CT4 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-14 | C4 | 2014-03-05 08:00 | 2016-03-11 17:00 | 100% | CP-150091 |  | Vodafone | peter.dawes @vodafone.com | CP66: moved to Rel-13. Mar.15: 90%. ES in CP-150615. 7/3/16: Rel-13->Rel-14; 5/6/17: 90%->100 | 23.008, 29.228, 29.229, 29.328, 29.329 | 63 | 32 |  |  | Wed 29/01/14 | Mon 05/06/17
988 | 0 | Other Release 14 | - | 1 | Rel-14 |  | 2016-06-09 08:00 | 2016-06-09 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
989 | 740017 | User Controlled Spoofed Call Treatment | SPECTRE | 1 | Rel-14 |  | 2016-08-23 08:00 | 2018-06-15 17:00 | 100% | SP-160898 |  | Greg Schumacher, Sprint |  | 1/12/16: moved from Rel-15 to Rel-14; 1/12/16: WID:SP-160729->SP-160898 |  | 73 | 37 |  |  | Mon 19/09/16 | Thu 01/12/16
990 | 730004 | Stage 1 of User Controlled Spoofed Call Treatment | SPECTRE | 2 | Rel-14 | S1 | 2016-08-23 08:00 | 2016-09-19 17:00 | 100% | SP-160898 |  | Greg Schumacher, Sprint |  | 1/12/16: moved from Rel-15 to Rel-14; 1/12/16: WID:SP-160729->SP-160898 | 22.228, 22.173 | 73 | 37 |  |  | Mon 19/09/16 | Thu 01/12/16
991 | 740018 | Stage 3 of User Controlled Spoofed Call Treatment | SPECTRE-CT | 2 | Rel-14 | C1 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160696 |  | Dolly, Martin | md3135@att.com | 2/12/16: 0%->25; 6/3/17: 25%->100 | 24.229, 29.165 | 74 | 38 |  |  | Mon 19/09/16 | Mon 06/03/17
992 | 750037 | (IETF) A SIP Response Code for Unwanted Calls (draft-ietf-sipcore-status-unwanted) | SPECTRE-CT_IETF | 2 | Rel-14 | C1-IETF | 2017-03-14 08:00 | 2017-03-14 17:00 | 100% |  |  | Ericsson |  | 18/12/17: 20%->100 |  | 75 | 38 |  |  | Tue 21/03/17 | Mon 18/12/17
993 | 780049 | (IETF) Authenticated Identity Management in SIP (draft-ietf-stir-rfc4474bis) | SPECTRE-CT_IETF2 | 2 | Rel-14 | C1-IETF | 2017-06-15 08:00 | 2018-06-15 17:00 | 100% |  |  | Christer Holmberg | christer.holmberg@ericsson.com | 22/3/18: 0%->100 |  | 78 | 40 |  |  | Mon 18/12/17 | Thu 22/03/18
994 | 700032 | Enhancement for TV service | EnTV | 1 | Rel-14 |  | 2015-04-14 08:00 | 2017-06-09 17:00 | 100% | SP-150756 | SP-170532 | Zhiming Li | Lizhiming@huawei.com | 2/3/16: 0%->100 | 22.101 | 70 | 36 |  |  | Mon 07/12/15 | Wed 02/03/16
995 | 670010 | Study on 3GPP Enhancement for TV Video service | FS_EnTV | 2 | Rel-14 | S1 | 2015-04-14 08:00 | 2015-12-15 17:00 | 100% | SP-150052 |  | Zhiming Li (Huawei) | lizhiming@huawei.com | 1/4/15:TR number added; June2015: Compl:0%->20; 07/09/15: 20%->75; 7/12/15: 75%->100 | TR 22.816 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
996 | 720015 | System Architecture Enhancements to eMBMS for TV Video Service | AE_enTV | 2 | Rel-14 |  | 2016-03-11 08:00 | 2016-12-15 17:00 | 100% | SP-160730 | [5 empty] | 71 | 36 |  |  | Fri 11/03/16 | Thu 09/06/16
997 | 710046 | Study on System Architecture Enhancements to eMBMS for TV Video Service | FS_AE_enTV | 3 | Rel-14 | S2 | 2016-03-11 08:00 | 2016-09-15 17:00 | 100% | SP-160225 |  | Miguel Griot, Qualcomm | mgriot@qti.qualcomm.com | 9/6/16: 0%->70; 28/7/16: 23.746 added; 19/9/16: 70%->100 | TR 23.746 | 71 | 36 |  |  | Fri 11/03/16 | Mon 19/09/16
998 | 730058 | System Architecture Enhancements for TV service | AE_enTV | 3 | Rel-14 | S2 | 2016-08-25 08:00 | 2016-12-15 17:00 | 100% | SP-160730 |  | Miguel Griot, Qualcomm | mgriot@qti.qualcomm.com | 19/9/16: 0%->85; 1/12/16: FCD:09/16->12/16; 1/12/16: 85%->100 | TS 23.246 | 73 | 37 |  |  | Mon 19/09/16 | Thu 01/12/16
999 | 730052 | Mobile Network Interface for MBMS Delivery of Media and TV services | AE_enTV-MI_MTV | 2 | Rel-14 | S4 | 2016-08-22 08:00 | 2016-12-09 17:00 | 100% | SP-160731 |  | Thorsten Lohmar | Thorsten.lohmar@ericsson.com | 06/10/16: Acronym: SA_enTV-MI_MTV -> AE_enTV-MI_MTV; 1/12/16: FCD:09/16->2/16; 1/12/16: 0%->50; 8/12/16: 50%->100 | 26.346 | 73 | 37 |  |  | Mon 19/09/16 | Thu 08/12/16
1000 | 740060 | Codec aspects for eMBMS Delivery of Media and TV Services | AE_enTV-S4 | 2 | Rel-14 | S4 | 2016-12-08 08:00 | 2017-06-09 17:00 | 100% | SP-160956 |  | Imed Bouazizi | i.bouazizi@samsung.com | 6/3/17: 0%->20; 6/3/17: FCD:03/17->06/17; 7/6/17: 20%->100 | 26.347, 26.346 | 74 | 38 |  |  | Thu 08/12/16 | Wed 07/06/17
1001 | 740049 | Stage 3 of system architecture enhancements for TV service | AE_enTV-CT | 2 | Rel-14 | ct | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160816 |  | Catovic, Amer | amerc@qti.qualcomm.com | 21/3/17: 29.116 added; | 24.116, 24.117; 29.116 | 74 | 38 |  |  | Thu 01/12/16 | Tue 21/03/17
1002 | 740050 | CT1 aspects of system architecture enhancements for TV service | AE_enTV-CT | 3 | Rel-14 | C1 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160816 |  | Catovic, Amer | amerc@qti.qualcomm.com | 2/12/16: 0%->40; 6/3/17: 40%->75; 5/6/17: 75%->100 | 24.008 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1003 | 740051 | CT3 aspects of system architecture enhancements for TV service | AE_enTV-CT | 3 | Rel-14 | C3 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160816 |  | Catovic, Amer | amerc@qti.qualcomm.com | 6/3/17: 0%->80; 6/3/17: 80%->100 | 29.061 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
1004 | 740052 | CT4 aspects of system architecture enhancements for TV service | AE_enTV-CT | 3 | Rel-14 | C4 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160816 |  | Catovic, Amer | amerc@qti.qualcomm.com | 5/6/17: 0%->100 | 29.274, 23.003 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1005 | 740053 | CT6 aspects of system architecture enhancements for TV service | AE_enTV-CT | 3 | Rel-14 | C6 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160816 |  | Catovic, Amer | amerc@qti.qualcomm.com | 7/3/17: 0%->100 | 31.102 | 74 | 38 |  |  | Thu 01/12/16 | Tue 07/03/17
1006 | 700054 | MBMS Transport Protocol and APIs | TRAPI | 1 | Rel-14 | S4 | 2015-12-11 08:00 | 2017-03-15 17:00 | 100% | SP-150851 |  | Samsung, Imed Bouazizi | i.bouazizi@samsung.com | 28/1/16: 26.347 added; 7/3/16: 0%->20; 11/6/16: 20%->35; 19/9/16: 35%->60. FCD: 09/16->03/17; 1/12/16: 60%->70; 6/3/17: 70%->100 | 26.346, 26.852, New TS; 26.347 | 70 | 36 |  |  | Fri 11/12/15 | Mon 06/03/17
1007 | 670003 | Multimedia Priority Service Modifications | MPS_Mods | 1 | Rel-14 | S1 | 2015-03-11 08:00 | 2016-06-15 17:00 | 100% | SP-150043 |  | Ray P. Singh (Applied Communications Science) | rsingh@appcomsci.com | 1/4/15: rapporteur added, Impacted TS added. 6/15: 0->25%; 07/09/15: 25%->40; 7/12/15: 40%->70; 2/3/16: 70%->80; 9/6/16: 80%->100 | 22.153 | 67 | 34 |  |  | Wed 04/03/15 | Thu 09/06/16
1008 | 721004 | Lawful Interception Rel-14 | LI14 | 1 | Rel-14 | S3LI | 2016-06-15 08:00 | 2017-12-15 17:00 | 100% | SP-170038 |  | Koen JASPERS, PIDS |  | 1/12/16: 0%->10; 2/3/17: WID:SP-160375->SP-1570038; 3/3/17: 8%->15; 6/3/17: 15%->20; 9/3/17: WID:SP-1570038->SP-170038; 7/6/17: 20%->50; 11/9/17: 50%->80; 15/12/17: 80%->100 |  | 72 | 37 |  |  | Wed 27/07/16 | Fri 15/12/17
1009 | 730031 | SIP Reason header extension | REAS_EXT | 1 | Rel-14 | ct | 2016-09-16 08:00 | 2018-06-14 17:00 | 75% | CP-160481 | CP-171175 | Mohali, Marianne | marianne.mohali@orange.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
1010 | 730032 | CT1 aspects of SIP Reason header extension | REAS_EXT | 2 | Rel-14 | C1 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160481 |  | Mohali, Marianne | marianne.mohali@orange.com | 2/12/16: 0%->50; 6/3/17: 50%->85; 5/6/17: 85%->100 | 24.229 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
1011 | 780050 | (IETF) ISUP Cause Location Parameter for the SIP Reason Header Field (draft-ietf-sipcore-reason-q850-loc) | REAS_EXT | 2 | Rel-14 | C1-IETF | 2017-06-15 08:00 | 2018-06-14 17:00 | 50% |  |  | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de |  |  | 78 | 40 |  |  | Mon 18/12/17 | NA
1012 | 730033 | CT3 aspects of SIP Reason header extension | REAS_EXT | 2 | Rel-14 | C3 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160481 |  | Mohali, Marianne | marianne.mohali@orange.com | 5/6/17: 0%->100 | 29.163, 29.292 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
1013 | 690034 | Enhancements to User Location Reporting Support | eULRS | 1 | Rel-14 | S1 | 2015-09-09 08:00 | 2015-12-18 17:00 | 100% | SP-150540 |  |  |  | 2/3/16: 0%->100 |  | 68 | 35 |  |  | Wed 09/09/15 | Wed 02/03/16
1014 | 730002 | Diameter Load Control Mechanism | DLoCMe | 1 | Rel-14 | ct | 2014-12-03 08:00 | 2017-03-15 17:00 | 98% | CP-160645 | CP-171049 | Nokia, Ulrich Wiehe | ulrich.wiehe@nokia.com | 5/12/16: WID:CP-160412->CP-160645 |  | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/12/16
1015 | 730041 | CT3 aspects of Diameter Load Control Mechanism | DLoCMe | 2 | Rel-14 | C3 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160645 |  | Nokia, Ulrich Wiehe | ulrich.wiehe@nokia.com | 2/12/16: 0%->100 | 29.272, 29.273, 29.228, 29.229, 29.328, 29.329, 29.336, 29.344, 29.345, 29.128, 29.283 | 73 | 37 |  |  | Fri 16/09/16 | Fri 02/12/16
1016 | 730042 | CT4 aspects of Diameter Load Control Mechanism | DLoCMe | 2 | Rel-14 | C4 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160645 |  | Nokia, Ulrich Wiehe | ulrich.wiehe@nokia.com | 2/12/16: 0%->100 | 29.153, 29.154, 29.212, 29.214, 29.215, 29.217, 29.219, 29.213 | 73 | 37 |  |  | Fri 16/09/16 | Fri 02/12/16
1017 | 740058 | (IETF) Diameter Load Information Conveyance (draft-ietf-dime-load) | DLoCMe | 2 | Rel-14 | C4-IETF | 2016-12-02 08:00 | 2017-03-15 17:00 | 90% | CP-160645 |  |  |  | 2/12/16: 0%->90 |  | 74 | 38 |  |  | Fri 02/12/16 | Fri 02/12/16
1018 | 660025 | Study on Diameter Load Control Mechanisms | FS_DLoCME | 2 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-09-11 17:00 | 100% | CP-140996 |  | Alcatel-Lucent |  | 0->5%. Mar. 15: 10%; 7/12/15: 10%->40; 13/6/16: 40%->100 | New 29.810 | 66 | 34 |  |  | Thu 04/12/14 | Mon 13/06/16
1019 | 740012 | Diameter Base Protocol Specification Update | DBPU | 1 | Rel-14 |  | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160823 |  | Huawei, Peter Schmitt | Peter.Schmitt@huawei.com |  |  | 74 | 38 |  |  | Thu 01/12/16 | NA
1020 | 740054 | CT aspects of Diameter Base Protocol Specification Update | DBPU | 2 | Rel-14 | ct | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160823 |  | Huawei, Peter Schmitt | Peter.Schmitt@huawei.com |  |  | 74 | 38 |  |  | Thu 01/12/16 | NA
1021 | 740055 | CT3 aspects of Diameter Base Protocol Specification Update | DBPU | 3 | Rel-14 | C3 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160823 |  | Huawei, Peter Schmitt | Peter.Schmitt@huawei.com | 6/3/17: 0%->100 | 29.061, 29.153, 29.154, 29.212, 29.214, 29.215, 29.217, 29.219, 29.368, 29.468, 29.213, 29.155, 29.201 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
1022 | 740056 | CT4 aspects of Diameter Base Protocol Specification Update | DBPU | 3 | Rel-14 | C4 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160823 |  | Huawei, Peter Schmitt | Peter.Schmitt@huawei.com | 2/12/16: 0%->10; 6/3/17: 10%->100 | 29.109, 29.128, 29.172, 29.173, 29.228, 29.229, 29.272, 29.273, 29.283, 29.328, 29.329, 29.336, 29.337, 29.338, 29.343, 29.344, 29.345 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
1023 | 740013 | Charging aspects for Diameter Base Protocol Specification Update | DBPU-CH | 2 | Rel-14 | S5 | 2016-12-01 08:00 | 2017-03-10 17:00 | 100% | SP-160837 |  | Nokia | Nokia, Maryse <dot> Gardella <at> Nokia <dot> com | 6/3/17: 0%->100 | 32.240, 32.251, 32.260, 32.270, 32.271, 32.272, 32.273, 32.274, 32.275, 32.278, 32.280, 32.295, 32.296, 32.297, 32.299 | 74 | 38 |  |  | Thu 01/12/16 | Mon 06/03/17
1024 | 720060 | Enhancements to Multi-stream Multiparty Conferencing Media Handling | MMCMH_Enh | 1 | Rel-14 |  | 2016-03-02 08:00 | 2017-03-21 17:00 | 99% | SP-160272 | SP-170528 | Nikolai Leung | nleung@qti.qualcomm.com |  | TS 26.114 | 72 | 37 |  |  | Sat 11/06/16 | NA
1025 | 720029 | Overall aspects of MMCMH_Enh | MMCMH_Enh | 2 | Rel-14 | S4 | 2016-06-13 08:00 | 2017-03-10 17:00 | 100% | SP-160596 |  | Nikolai Leung | nleung@qti.qualcomm.com | 19/9/16: WID:SP-160272->SP-160785; 19/9/16: 0%->50; 1/12/16: 50%->80; 1/12/16: FCD:12/16->03/17; 6/3/17: 80%->100 | TS 26.114, TR 26.980 | 72 | 37 |  |  | Sat 11/06/16 | Mon 06/03/17
1026 | 720064 | CT aspects of MMCMH_Enh | MMCMH_Enh-CT | 2 | Rel-14 | ct | 2016-03-02 08:00 | 2017-03-21 17:00 | 99% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | To be checked at SA4 if a part can stay in Rel-13 (now Stages 1 and 2 by SA4 in UID660050), while the CT aspects are in Rel-14. 06/16: Name changed from "CT aspects of (or "Enhancements of") MTSI Extension on Multi-stream". Acronym changed from "MMCMH- |  | 72 | 37 |  |  | Wed 02/03/16 | Mon 13/06/16
1027 | 720065 | CT1 aspects of MMCMH_Enh | MMCMH_Enh-CT | 3 | Rel-14 | C1 | 2016-03-02 08:00 | 2017-03-15 17:00 | 100% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Name changed from "CT1 aspects of MTSI Extension on Multi-stream". Acronym changed from "MMCMH-CT"; 13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17; 13/6/16: WID:CP-160250->CP-160369; 2/12/16: 0%->95; 6/3/17: 95%->100 | 24.229 | 72 | 37 |  |  | Wed 02/03/16 | Mon 06/03/17
1028 | 720066 | CT3 aspects of MMCMH_Enh | MMCMH_Enh-CT | 3 | Rel-14 | C3 | 2016-03-02 08:00 | 2017-03-15 17:00 | 100% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Acronym changed from "MMCMH-CT"; 13/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17; 13/6/16: WID:CP-160250->CP-160369; 6/3/17: 0%->100 | 29.162, 29.213, 29.214, 29.165 | 72 | 37 |  |  | Wed 02/03/16 | Mon 06/03/17
1029 | 720067 | CT4 aspects of MMCMH_Enh | MMCMH_Enh-CT | 3 | Rel-14 | C4 | 2016-03-02 08:00 | 2017-03-15 17:00 | 100% | CP-160369 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | 3/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17; 13/6/16: WID:CP-160250->CP-160369; 2/12/16: 0%->35; 6/3/17: 35%->75; 5/6/17: 75%->100 | 23.333, 29.333, 23.334, 29.334, 29.238 | 72 | 37 |  |  | Wed 02/03/16 | Mon 05/06/17
1030 | 750038 | (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast) | MMCMH_Enh-CT | 3 | Rel-14 | C1-IETF | 2017-03-21 08:00 | 2017-03-21 17:00 | 50% |  |  | Ericsson | tomas.frankkila@ericsson.com |  |  | 75 | 38 |  |  | Tue 21/03/17 | NA
1031 | 750039 | (IETF) RTP Payload Format Restrictions (draft-ietf-mmusic-rid) | MMCMH_Enh-CT | 3 | Rel-14 | C1-IETF | 2017-03-21 08:00 | 2017-03-21 17:00 | 20% |  |  | Ericsson |  |  |  | 75 | 38 |  |  | Tue 21/03/17 | NA
1032 | 710002 | Deleted - CT aspects of (or "Enhancements of") MTSI Extension on Multi-stream | MMCMH-CT | 1 | Rel-14 | ct | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT |  | 71 | 36 | CP-72 |  | Wed 02/03/16 | Mon 13/06/16
1033 | 710028 | deleted -CT1 aspects of MTSI Extension on Multi-stream | MMCMH-CT | 2 | Rel-14 | C1 | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT | 24.229 | 71 | 36 | CP-72 |  | Wed 02/03/16 | Mon 13/06/16
1034 | 710029 | deleted -CT3 aspects of MTSI Extension on Multi-stream | MMCMH-CT | 2 | Rel-14 | C3 | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT | 29.162, 29.213, 29.214, 29.165 | 71 | 36 | CP-72 |  | Wed 02/03/16 | Mon 13/06/16
1035 | 710030 | deleted -CT4 aspects of MTSI Extension on Multi-stream | MMCMH-CT | 2 | Rel-14 | C4 | 2016-03-02 08:00 | 2016-09-15 17:00 | 100% | CP-160117 |  | Ericsson, Nevenka Biondic | nevenka.biondic@ericsson.com | Deleted, "replaced" by MMCMH_Enh-CT | 23.333, 29.333, 23.334, 29.334, 29.238 | 71 | 36 | CP-72 |  | Wed 02/03/16 | Mon 13/06/16
1036 | 720008 | Control and User Plane Separation of EPC nodes | CUPS | 1 | Rel-14 |  | 2015-09-17 08:00 | 2017-03-15 17:00 | 100% | SP-160316 | SP-170520 | Huawei, Mirko Schramm | mirko.schramm@huawei.com | 7/12/15: 0%->20; 7/3/16: 20%->40; 9/6/16: 40%->100; 28/7/16: 23.214 added; | 23.714; 23.214 | 69 | 35 |  |  | Thu 17/09/15 | Thu 28/07/16
1037 | 690052 | Study on Control and User Plane Separation of EPC nodes | FS_CUPS | 2 | Rel-14 | S2 | 2015-09-17 08:00 | 2016-06-17 17:00 | 100% | SP-150519 |  | Huawei, Mirko Schramm | mirko.schramm@huawei.com | 7/12/15: 0%->20; 7/3/16: 20%->40; 9/6/16: 40%->100 | 23.714 | 69 | 35 |  |  | Thu 17/09/15 | Thu 09/06/16
1038 | 720009 | Control and User Plane Separation of EPC nodes | CUPS | 2 | Rel-14 | S2 | 2016-06-09 08:00 | 2016-09-15 17:00 | 100% | SP-160316 |  | Huawei, Mirko Schramm | mirko.schramm@huawei.com | 19/9/16: 0%->80; 1/12/16: 80%->100 | 23.214, 23.002, 23.203, 23.401, 23.402 | 72 | 37 |  |  | Thu 17/09/15 | Thu 01/12/16
1039 | 730001 | CT aspects for CUPS | CUPS-CT | 2 | Rel-14 | ct | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160579 |  | Huawei, Peter Schmitt | peter.schmitt@huawei.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
1040 | 730039 | CT3 aspects for CUPS | CUPS-CT | 3 | Rel-14 | C3 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160579 |  | Huawei, Peter Schmitt | peter.schmitt@huawei.com | 8/6/17: 0%->100 | 29.212, 29.213 | 73 | 37 |  |  | Fri 16/09/16 | Thu 08/06/17
1041 | 730040 | CT4 aspects for CUPS | CUPS-CT | 3 | Rel-14 | C4 | 2016-09-16 08:00 | 2017-03-15 17:00 | 100% | CP-160579 |  | Huawei, Peter Schmitt | peter.schmitt@huawei.com | 2/12/16: 0%->40; 6/3/17: 40%->75; 5/6/17: 75%->100 | 23.007, 29.274, 29.281, 29.303, 23.008 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
1042 | 690048 | OAM14 Rel-14 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM14 | 1 | Rel-14 | S5 | 2015-03-12 08:00 | 2017-12-12 17:00 | 100% | [6 empty] | 68 | 35 |  |  | Wed 16/09/15 | Wed 16/09/15
1043 | 680035 | Management of mobile networks that include virtualized network functions | OAM14-MAMO_VNF | 2 | Rel-14 | S5 | 2015-06-15 08:00 | 2017-12-12 17:00 | 100% | SP-150362 |  | Jinglei Liu, China Mobile | liujinglei@chinamobile.com | June2015: WID:SP-150308->SP-150362 |  | 68 | 35 |  |  | Mon 15/06/15 | Thu 18/06/15
1044 | 680036 | Management concept, architecture and requirements for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-MCAR | 3 | Rel-14 | S5 | 2015-06-15 08:00 | 2016-12-15 17:00 | 100% | SP-160023 |  | Jinglei Liu, China Mobile (liujinglei@chinamobile.com) | liujinglei@chinamobile.com | June2015: WID:SP-150309->SP-150363. Aug2015: FCD: Mar 2016; 07/09/15: 0%->20. 15/09/15: FCD: Mar 16->Dec 16, moved to Rel-14; 7/12/15: 20%->40; 7/3/16: 40%->50; 7/3/16: WID:SP-150363->SP-160023 ( FCD: Dec16->Sep16); 13/6/16: 50%->70; 19/9/16: FCD:09/16 | 28.xyz, 32.101 | 68 | 35 |  |  | Mon 15/06/15 | Wed 22/03/17
1045 | 690039 | Configuration Management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-CM | 3 | Rel-14 | S5 | 2015-09-16 08:00 | 2017-06-09 17:00 | 100% | SP-160401 |  | ZTE Corporation (Zhu Weihong, zhu.weihong@zte.com.cn) | zhu.weihong@zte.com.cn | 5/10/15: 28.513; 28.512; 28.511; 28.510 added; 7/12/15: 0%->15; 7/3/16: 15%->20; 13/6/16: 20%->30; 19/9/16: 30%->50; 1/12/16: 50%->60; 1/12/16: FCD:12/16->03/17; 6/3/17: FCD:03/17->06/17; 6/3/17: 60%->80; 7/6/17: 80%->100 | 28.513; 28.512; 28.511; 28.510; 28.621, 28.622, 28.623, 28.704, 28.707 | 69 | 35 |  |  | Mon 15/06/15 | Wed 07/06/17
1046 | 690040 | Fault Management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-FM | 3 | Rel-14 | S5 | 2015-09-16 08:00 | 2017-06-09 17:00 | 100% | SP-160403 |  | Huawei (Kai ZHANG, kai.zhangkai@huawei.com) | kai.zhangkai@huawei.com | 5/10/15: 28.518; 28.517; 28.516; 28.515 added; 7/12/15: 0%->10; 7/3/16: 10%->15; 13/6/16: 15%->50; 13/6/16: WID:SP-150404->SP-160403; 19/9/16: 50%->75; 1/12/16: 75%->80; 1/12/16: 80%->; 1/12/16: FCD:12/16->03/17; 6/3/17: FCD:03/17->06/17; 6/3/17: 80%-> | 28.515, 28.516, 28.517, 28.518, 32.111-1, 32.111-2, 32.111-6 | 69 | 35 |  |  | Mon 15/06/15 | Wed 07/06/17
1047 | 690041 | Performance management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-PM | 3 | Rel-14 | S5 | 2015-09-16 08:00 | 2017-12-12 17:00 | 100% | SP-160402 |  | Intel (Joey Chou, joey.chou@intel.com) | joey.chou@intel.com | 5/10/15: 28.523; 28.522; 28.521; 28.520 added; 7/12/15: 0%->10; 7/3/16: 10%->15; 13/6/16: 15%->30; 13/6/16: WID:SP-150401->SP-160402; 19/9/16: 30%->60; 1/12/16: FCD:12/16->03/17; 6/3/17: FCD:03/17->06/17; 6/3/17: 60%->75; 7/6/17: 75%->90; 7/6/17: FCD:0 | 28.523; 28.522; 28.521; 28.520; 32.426, 32.409, 32.401 | 69 | 35 |  |  | Mon 15/06/15 | Mon 11/09/17
1048 | 690042 | Lifecycle management for mobile networks that include virtualized network functions | OAM14-MAMO_VNF-LCM | 3 | Rel-14 | S5 | 2015-09-16 08:00 | 2017-06-09 17:00 | 100% | SP-160427 |  | Anatoly Andrianov (anatoly.andrianov@nokia.com), Nokia Networks | anatoly.andrianov@nokia.com | 5/10/15: 28.528; 28.527; 28.526; 28.525 added; 7/12/15: 0%->10; 7/3/16: 10%->15; 13/6/16: 15%->25; 13/6/16: WID:SP-150403->SP-160427; 19/9/16: 25%->40; 1/12/16: 40%->60; 1/12/16: FCD:12/16->03/17; 6/3/17: FCD:03/17->06/17; 6/3/17: 60%->80; 7/6/17: 80%- | 28.525, 28.526, 28.527, 28.528, 28.704, 28.705, 28.706, 28.707, 28.708, 28.709 | 69 | 35 |  |  | Mon 15/06/15 | Wed 07/06/17
1049 | 710009 | Filtering of PM measurements and data volume | OAM14-FILMEAS | 2 | Rel-14 | S5 | 2016-03-01 08:00 | 2016-12-01 17:00 | 100% | SP-160610 |  | Ericsson: Robert Petersen | robert.petersen@ericsson.com | 13/6/16: 0%->15; 19/9/16: WID:SP-160022->SP-160610; 19/9/16: 15%->60; 1/12/16: 60%->95; 6/3/17: 95%->100 | New 32.817, 32.425, 32.412, 32.416, 32.130 | 71 | 36 |  |  | Tue 01/03/16 | Mon 06/03/17
1050 | 670028 | Study on OAM support for Licensed Shared Access (LSA) | FS_OAM_LSA | 2 | Rel-14 | S5 | 2015-03-12 08:00 | 2016-03-11 17:00 | 100% | SP-150056 |  | Nokia Networks, Anatoly Andrianov | anatoly<dot>andrianov<at>nokia<dot>com | June2015: Compl:0%->15; 07/09/15: 15%->70; 7/12/15: 70%->75; 7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14; 28/7/16: 28.303 added; 28/7/16: 28.302 added; 28/7/16: 28.301 added; 28/7/16: 33.250 added; 28/7/16: added; | 28.303; 28.302; 28.301; | 67 | 34 |  |  | Thu 12/03/15 | Thu 28/07/16
1051 | 720044 | OAM support for Licensed Shared Access (LSA) | OAM14-LSA | 2 | Rel-14 | S5 | 2016-06-13 08:00 | 2017-06-12 17:00 | 100% | SP-160397 |  | Nokia: Olaf Pollakowski |  | 28/7/16: 28.303 added; 28/7/16: 28.302 added; 28/7/16: 28.301 added; 19/9/16: 0%->20; 1/12/16: 20%->30; 6/3/17: 30%->40; 7/6/17: 40%->100 | 32.101; 28.303; 28.302; 28.301 | 72 | 37 |  |  | Thu 12/03/15 | Wed 07/06/17
1052 | 680050 | Development of super-wideband and fullband P.835 | DESUDAPS | 1 | Rel-14 | S4 | 2015-06-16 08:00 | 2017-06-15 17:00 | 100% | SP-150215 | SP-170346 | Scott Isabelle (Knowles, Inc.) | sisabelle@audience.com | 06/15: FCD corrected to Dec.15; Aug2015: 0%->5; 07/09/15: 5%->20, FCD: 12/15->06.16; 7/12/15: 20%->40, MOVED TO REL-14; 7/3/16: 40%->50. 15/4/16: 6/16->12/16; 11/6/16: 50%->60; 19/9/16: 60%->70, fcd: 12/16->06/17; 1/12/16: 70%->75; 6/3/17: 75%->80; 7/6 | 26.131, 26.132 | 68 | 35 |  |  | Thu 18/06/15 | Wed 07/06/17
1053 | 670004 | Enhancing Location Capabilities for Indoor and Outdoor Emergency Communications | ELIOT | 1 | Rel-14 | S1 | 2015-03-11 08:00 | 2015-12-15 17:00 | 100% | SP-150044 | SP-170553 | Greg Schumacher | Gregory.schumacher@sprint.com | 1/4/15: rapporteur added, Impacted TS added; June2015: Compl:0%->25; 07/09/15: 25%->80; 2/3/16: 80%->100 | 22.101, 22.071 | 67 | 34 |  |  | Wed 04/03/15 | Wed 02/03/16
1054 | 670005 | Enhancements to Domain Selection between VoLTE and CDMA CS | eDSVCC | 1 | Rel-14 | S1 | 2015-03-11 08:00 | 2015-06-15 17:00 | 100% | SP-150045 |  | China Telecom, Hongmei Zhu | zhuhongmei@gsta.com | 1/4/15: rapporteur added, Impacted TS added; June2015: Compl:0%->100 | 22.101 | 67 | 34 |  |  | Wed 04/03/15 | Mon 15/06/15
1055 | 680002 | Control of Applications when Third party Servers encounter difficulties | CATS | 1 | Rel-14 | S1 | 2015-05-11 08:00 | 2015-09-16 17:00 | 100% | SP-150273 | SP-170338 | Eriko Yoshida, KDDI | er-yoshida (at) kddi (dot) com | 07/09/15: 0%->100 | 22.011 | 68 | 35 |  |  | Tue 09/06/15 | Mon 07/09/15
1056 | 720080 | PS Data Off Services | PS_Data_Off | 1 | Rel-14 |  | 2015-11-09 08:00 | 2017-06-09 17:00 | 100% | SP-150823 | SP-170708 | Orange, Bruno Tossou | bruno.tossou@orange.com | 2/3/16: 0%->100 | 22.030 | 70 | 36 |  |  | Mon 07/12/15 | Wed 02/03/16
1057 | 700033 | PS Data Off Services | PS_Data_Off | 2 | Rel-14 | S1 | 2015-11-09 08:00 | 2016-03-15 17:00 | 100% | SP-150823 |  | Orange, Bruno Tossou | bruno.tossou@orange.com | 2/3/16: 0%->100 | 22.030 | 70 | 36 |  |  | Mon 07/12/15 | Wed 02/03/16
1058 | 720079 | Study on Stage 2 of PS Data off function | FS_PS_DATA_OFF | 2 | Rel-14 | S2 | 2016-06-17 08:00 | 2016-12-15 17:00 | 100% | SP-160318 |  | Orange, david <dot> cailliere <at> orange <dot> com | david <dot> cailliere <at> orange <dot> com | 28/7/16: 23.702 added; 19/9/16: 0%->60; 1/12/16: FCD:09/16->12/16; 1/12/16: 60%->100 | TR 23.702 | 72 | 37 |  |  | Fri 17/06/16 | Thu 01/12/16
1059 | 740004 | Stage 2 of PS Data Off | PS_DATA_OFF | 2 | Rel-14 | S2 | 2016-11-17 08:00 | 2016-12-15 17:00 | 100% | SP-160831 |  | Christophe Petit (Orange) | kris (dot) petit (at) orange (dot) com | 1/12/16: 0%->100 | 23.401, 23.203, 23.060, 23.228, 23.292, 23.221 | 74 | 38 |  |  | Thu 01/12/16 | Thu 01/12/16
1060 | 740041 | Stage 3 of PS Data Off | PS_DATA_OFF-CT | 2 | Rel-14 | ct | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160702 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  |  | 74 | 38 |  |  | Thu 01/12/16 | NA
1061 | 740042 | CT1 aspects of PS Data Off | PS_DATA_OFF-CT | 3 | Rel-14 | C1 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160702 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 6/3/17: 0%->95; 5/6/17: 95%->100 | 24.008, 24.301, 27.007, 24.229, 24.368, 24.167 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1062 | 740043 | CT3 aspects of PS Data Off | PS_DATA_OFF-CT | 3 | Rel-14 | C3 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160702 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 6/3/17: 0%->60; 8/6/17: 60%->100 | 29.212, 29.213 | 74 | 38 |  |  | Thu 01/12/16 | Thu 08/06/17
1063 | 740044 | CT6 aspects of PS Data Off | PS_DATA_OFF-CT | 3 | Rel-14 | C6 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160702 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 7/3/17: 0%->100 | 31.102, 31.103, 31.111 | 74 | 38 |  |  | Thu 01/12/16 | Tue 07/03/17
1064 | 740014 | Charging Aspect for 3GPP PS Data off Function | PS_DATA_OFF-CH | 2 | Rel-14 | S5 | 2016-12-01 08:00 | 2017-06-09 17:00 | 100% | SP-160839 |  | Huawei， Chen, Shan | chenshan@huawei.com | 6/3/17: 0%->70; 6/3/17: FCD:03/17->06/17; 7/6/17: 70%->100 | TS 32.251, TS 32.298, TS 32.299 | 74 | 38 |  |  | Thu 01/12/16 | Wed 07/06/17
1065 | 710003 | SCC AS Restoration | SCCAS_RES | 1 | Rel-14 | C4 | 2016-03-02 08:00 | 2016-12-15 17:00 | 100% | CP-160118 |  | China Mobile, Hao Zhang, | zhanghao@chinamobile.com | 13/6/16: 0%->100 | 23.380 | 71 | 36 |  |  | Wed 02/03/16 | Mon 13/06/16
1066 | 710004 | Paging Policy Enhancements and Procedure | PPEPO_LTE | 1 | Rel-14 | S1 | 2016-02-01 08:00 | 2016-03-01 17:00 | 100% | SP-160113 | SP-170549 | China Unicom, Zhuoyun Zhang | zhangzy910@chinaunicom.cn |  | 22.101 | 71 | 36 |  |  | Tue 01/03/16 | Tue 01/03/16
1067 | 720077 | Enhancement to Flexible Mobile Service Steering | eFMSS | 1 | Rel-14 |  | 2015-05-11 08:00 | 2016-09-15 17:00 | 100% | SP-160115 |  | China Mobile, Lu Lu | lulu@chinamobile.com |  | 22.115, 22.101 | 72 | 37 |  |  | Tue 01/03/16 | Tue 01/03/16
1068 | 680003 | Study on enhancement to FMSS for Rel 14 | FS_eFMSS | 2 | Rel-14 | S1 | 2015-05-11 08:00 | 2015-12-16 17:00 | 100% | SP-150280 |  | Lu Lu, China Mobile | lulu@chinamobile.com | 7/12/15: 70%->100 | 22.808 | 68 | 35 |  |  | Tue 09/06/15 | Mon 07/12/15
1069 | 710005 | Stage 1 of Enhancement to Flexible Mobile Service Steering | eFMSS | 2 | Rel-14 | S1 | 2016-02-01 08:00 | 2016-03-01 17:00 | 100% | SP-160115 |  | China Mobile, Lu Lu | lulu@chinamobile.com |  | 22.115, 22.101 | 71 | 36 |  |  | Tue 01/03/16 | Tue 01/03/16
1070 | 720078 | Stage 2 of Enhancement to Flexible Mobile Service Steering | eFMSS | 2 | Rel-14 | S2 | 2016-06-17 08:00 | 2016-09-15 17:00 | 100% | SP-160314 |  | ZTE, Tricci So |  | 19/9/16: 0%->100 | 23.203 | 72 | 37 |  |  | Tue 01/03/16 | Mon 19/09/16
1071 | 710010 | Media Handling Extensions of IMS-based Telepresence | IMS_TELEP_EXT | 1 | Rel-14 |  | 2016-03-01 08:00 | 2016-12-01 17:00 | 33% | SP-160081 | SP-170515 | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 11/6/16: 0%->10 | 26.223 | 71 | 36 |  |  | Tue 01/03/16 | Sat 11/06/16
1072 | 721005 | S4 aspects of Media Handling Extensions of IMS-based Telepresence | IMS_TELEP_EXT | 2 | Rel-14 | S4 | 2016-03-01 08:00 | 2016-12-01 17:00 | 100% | SP-160081 |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 11/6/16: 0%->10; 19/9/16: 10%->60; 1/12/16: 60%->100 | 26.223 | 72 | 37 |  |  | Tue 01/03/16 | Thu 01/12/16
1073 | 720061 | (IETF) Other IETF aspects of IMS_TELEP_EXT | IMS_TELEP_EXT | 2 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 25% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  | draft-ietf-payload-rtp-h265, -flexible-fec-scheme , draft-ietf-clue-framework , -datachannel, -signalling, -data-model-schema, -protocol, -rtp-mapping, draft-ietf-mmusic-sctp-sdp, -data-channel-sdpneg, draft-ietf-tsvwg-sctp-dtls-encaps | 72 | 37 |  |  | Tue 01/03/16 | NA
1074 | 800103 | (IETF) RTP Payload Format for Flexible Forward Error Correction (FEC) (draft-ietf-payload-flexible-fec-scheme) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 25% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1075 | 800104 | (IETF) Framework for Telepresence Multi-Streams (draft-ietf-clue-framework) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 25% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1076 | 800105 | (IETF) CLUE Protocol data channel (draft-ietf-clue-datachannel) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 25% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1077 | 800106 | (IETF) Session Signaling for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-signaling) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 25% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1078 | 800107 | (IETF) An XML Schema for the CLUE data model (draft-ietf-clue-data-model-schema) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 25% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1079 | 800108 | (IETF) Protocol for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-protocol) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 25% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1080 | 800109 | (IETF) Mapping RTP streams to CLUE Media Captures (draft-ietf-clue-rtp-mapping) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 25% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1081 | 800110 | (IETF) Session Description Protocol (SDP) Offer/Answer Procedures For Stream Control Transmission Protocol (SCTP) over Datagram Transport Layer Security (DTLS) Transport. (draft-ietf-mmusic-sctp-sdp) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 25% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1082 | 800111 | (IETF) SDP-based Data Channel Negotiation (draft-ietf-mmusic-data-channel-sdpneg) | IMS_TELEP_EXT | 3 | Rel-14 | S4-IETF | 2016-03-01 08:00 | 2016-12-01 17:00 | 25% |  |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1083 | 710011 | Improved Streaming QoE Reporting in 3GPP | IQoE | 1 | Rel-14 | S4 | 2016-03-01 08:00 | 2017-03-15 17:00 | 100% | SP-160082 | SP-170521 | Zhiming Li, Huawei | Lizhiming@huawei.com | 11/6/16: 0%->10; 19/9/16: 10%->55. FDC: 12/16->03/17; 1/12/16: 55%->65; 6/3/17: 65%->100 | New 26.909, 26.247, 26.346 | 71 | 36 |  |  | Tue 01/03/16 | Mon 06/03/17
1084 | 710085 | New GPRS algorithms for EASE | EASE_ALGOs_SA3 | 1 | Rel-14 | S3 | 2016-03-15 08:00 | 2016-06-15 17:00 | 100% | SP-160203 |  | Tim Evans, Vodafone |  | Discussion whether it should be Rel-13. To be concluded at SA#72.; 13/6/16: 0%->60; 1/12/16: 60%->70; 6/3/17: 70%->100 | 55.241, 55.242, 55.243, 55.251, 55.252, 55.253 | 71 | 36 |  |  | Tue 22/03/16 | Mon 06/03/17
1085 | 710048 | S8 Home Routing Architecture for VoLTE | V8 | 1 | Rel-14 |  | 2015-06-18 08:00 | 2017-06-09 17:00 | 100% | SP-160315 | SP-170522 |  |  | Umbrella, created by MCC to group SA2 and SA3 activities |  | 71 | 36 |  |  | Fri 11/03/16 | Fri 11/03/16
1086 | 680053 | Study on S8 Home Routing Architecture | FS_V8 | 2 | Rel-14 | S2 | 2015-06-18 08:00 | 2016-03-10 17:00 | 100% | SP-150255 |  | Motohiro ABE | motohiro(dot)abe(dot)cu(at) nttdocomo (dot) com | 07/09/15: 0%->10; 07/09/15: 10%->100; 7/12/15: 100%->10% (mistake?) then 10%->70, FCD: 12/15-?03/16; 7/3/16: 70%->80; 9/6/16: 80%->100 | New TR 23.xxx | 68 | 35 |  |  | Thu 18/06/15 | Thu 09/06/16
1087 | 690049 | Study on LI in S8 Home Routing Architecture for VoLTE | FS_LIV8 | 2 | Rel-14 | S3 | 2015-09-17 08:00 | 2016-06-17 17:00 | 100% | SP-150461 |  | Greg Schumacher (SPRINT) Gregory | Schumacher@sprint.com | 7/12/15: 0%->45; 28/1/16: 33.827 added; 7/3/16: 45%->55; 19/9/16: 55%->65; 15/12/17: 65%->100 | TR 33.827 | 69 | 35 |  |  | Thu 17/09/15 | Fri 15/12/17
1088 | 720017 | S8 Home Routing Architecture for VoLTE | V8 | 2 | Rel-14 | S2 | 2016-06-13 08:00 | 2016-12-15 17:00 | 100% | SP-160315 |  | Motohiro ABE | motohiro(dot)abe(dot)cu(at) nttdocomo (dot) com | 11/6/16: 0%->60; 19/9/16: 60%->95; 1/12/16: FCD:09/16->12/16; 1/12/16: 95%->100 | TS 23.228, TS 23.167, TS 23.203 | 72 | 37 |  |  | Thu 18/06/15 | Thu 01/12/16
1089 | 730023 | CT Aspects of V8 | V8-CT | 2 | Rel-14 | ct | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160479 |  | Tsuyoshi Takakura (NTT DOCOMO) | tsuyoshi.takakura.ey@s1.nttdocomo.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
1090 | 730024 | CT1 Aspects of V8 | V8-CT | 3 | Rel-14 | C1 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160479 |  | Tsuyoshi Takakura (NTT DOCOMO) | tsuyoshi.takakura.ey@s1.nttdocomo.com | 2/12/16: 40%->100 | 24.229 | 73 | 37 |  |  | Fri 16/09/16 | Fri 02/12/16
1091 | 730025 | CT3 Aspects of V8 | V8-CT | 3 | Rel-14 | C3 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160479 |  | Tsuyoshi Takakura (NTT DOCOMO) | tsuyoshi.takakura.ey@s1.nttdocomo.com | 2/12/16: 40%->100 | 29.212, 29.213, 29.214 | 73 | 37 |  |  | Fri 16/09/16 | Fri 02/12/16
1092 | 720050 | Charging Aspects of S8 Home Routing Architecture for VoLTE | CH14-V8 | 2 | Rel-14 | S5 | 2016-06-13 08:00 | 2017-06-09 17:00 | 100% | SP-160838 |  | Chen, Ai (China Mobile) | chenai(at) chinamobile (dot) com | 19/9/16: 0%->15; 1/12/16: FCD:12/16->03/17; 1/12/16: 15%->60; 1/12/16: WID:SP-160429->SP-160838; 6/3/17: FCD:03/17->06/17; 7/6/17: 60%->100 | 32.240, 32.251, 32.260 | 72 | 37 |  |  | Mon 13/06/16 | Wed 07/06/17
1093 | 720020 | Improvements of awareness of user location change | AULC | 1 | Rel-14 |  | 2015-09-17 08:00 | 2017-06-09 17:00 | 100% | SP-160308 | SP-170524 | Yang Xu | xuyang49@chinaunicom.cn |  |  | 72 | 37 |  |  | Thu 17/09/15 | Thu 09/06/16
1094 | 690050 | Study on improvement of awareness of user location change | FS_AULC | 2 | Rel-14 | S2 | 2015-09-17 08:00 | 2016-06-17 17:00 | 100% | SP-150517 |  | Yang Xu | xuyang49@chinaunicom.cn | 7/12/15: 0%->40; 7/3/16: 40%->70; 9/6/16: 70%->100 | 23.710 | 69 | 35 |  |  | Thu 17/09/15 | Thu 09/06/16
1095 | 720021 | Improvements of awareness of user location change | AULC | 2 | Rel-14 | S2 | 2016-06-06 08:00 | 2016-09-15 17:00 | 100% | SP-160308 |  | Yang Xu | xuyang49@chinaunicom.cn | 11/6/16: 0%->10; 19/9/16: 10%->100 | 23.401, 23.203, 23.060 | 72 | 37 |  |  | Thu 17/09/15 | Mon 19/09/16
1096 | 730034 | CT Aspect of AULC | AULC-CT | 2 | Rel-14 | ct | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160466 |  | Huawei, Wu Yizhuang | wuyizhuang@huawei.com |  |  | 73 | 37 |  |  | Fri 16/09/16 | Fri 16/09/16
1097 | 730035 | CT3 Aspect of AULC | AULC-CT | 3 | Rel-14 | C3 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160466 |  | Huawei, Wu Yizhuang | wuyizhuang@huawei.com | 2/12/16: 0%->10; 6/3/17: 10%->100 | 29.212, 29.213 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
1098 | 730036 | CT4 Aspect of AULC | AULC-CT | 3 | Rel-14 | C4 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160466 |  | Huawei, Wu Yizhuang | wuyizhuang@huawei.com | 2/12/16: 0%->95; 6/3/17: 95%->100 | 29.274 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
1099 | 730054 | Charging Aspects of Improvements of AULC | AULC-CH | 2 | Rel-14 | S5 | 2016-09-19 08:00 | 2017-06-09 17:00 | 100% | SP-160609 |  | Huawei， Chen, Shan | chenshan@huawei.com | 1/12/16: 0%->40; 6/3/17: 40%->80; 6/3/17: FCD:03/17->06/17; 7/6/17: 80%->100 | TS32.251, TS32.298, TS32.299 | 73 | 37 |  |  | Mon 19/09/16 | Wed 07/06/17
1100 | 720022 | Service Domain Centralization | SeDoC | 1 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-09-19 17:00 | 100% | SP-160675 |  | Chris Joul (T-Mobile USA) | chris (dot) joul (at) t (dash) mobile (dot) com |  |  | 72 | 37 |  |  | Mon 07/12/15 | Thu 09/06/16
1101 | 700040 | Study on Service Domain Centralization | FS_SeDoC | 2 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-09-15 17:00 | 100% | SP-160306 |  | Chris Joul (T-Mobile USA) | chris (dot) joul (at) t (dash) mobile (dot) com | Comes back from previous release; 28/1/16: 23.719 added; 7/3/16: 0%->30; 7/3/16: WID:SP-150626->SP-1601679/6/16: 30%->70; 11/6/16: WID:SP-160167->SP-160306. FCD: 06/16->09/16; 1/12/16: 70%->100 | 23.719 | 70 | 36 |  |  | Mon 07/12/15 | Thu 01/12/16
1102 | 730044 | Service Domain Centralization | SeDoC | 2 | Rel-14 | S2 | 2016-08-16 08:00 | 2016-09-19 17:00 | 100% | SP-160675 |  | Chris Joul (T-Mobile USA) | chris (dot) joul (at) t (dash) mobile (dot) com | 19/9/16: 0%->100 | 23.292, 23.167 | 73 | 37 |  |  | Mon 19/09/16 | Mon 19/09/16
1103 | 720014 | Sponsored data connectivity improvements | SDCI | 1 | Rel-14 |  | 2015-11-02 08:00 | 2016-12-15 17:00 | 100% | SP-160309 | SP-170523 | Yang Xu | xuyang49@chinaunicom.cn |  |  | 72 | 37 |  |  | Mon 07/12/15 | Thu 09/06/16
1104 | 700041 | Study on sponsored data connectivity improvements | FS_SDCI | 2 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150627 |  | Yang Xu | xuyang49@chinaunicom.cn | 28/1/16: 23.721 added; 7/3/16: 10%->40; 9/6/16: 40%->100 | 23.721 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1105 | 720024 | Sponsored data connectivity improvements | SDCI | 2 | Rel-14 | S2 | 2016-06-13 08:00 | 2016-09-15 17:00 | 100% | SP-160309 |  | Yang Xu | xuyang49@chinaunicom.cn | 19/9/16: 0%->100 | 23.203, 23.682 | 72 | 37 |  |  | Mon 07/12/15 | Mon 19/09/16
1106 | 730037 | CT Aspects of SDCI | SDCI-CT | 2 | Rel-14 | ct | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160580 |  | China Unicom, Xu, Yang | xuyang49@chinaunicom.cn | 6/10/16: 29.251 added; | 29.251 | 73 | 37 |  |  | Fri 16/09/16 | Thu 06/10/16
1107 | 730038 | CT3 Aspects of SDCI | SDCI-CT | 3 | Rel-14 | C3 | 2016-09-16 08:00 | 2016-12-15 17:00 | 100% | CP-160580 |  | China Unicom, Xu, Yang | xuyang49@chinaunicom.cn | 6/10/16: 29.250 added; 2/12/16: 10%->30; 6/3/17: 30%->80; 5/6/17: 80%->100 | 29.212, 29.213, 29.214, 29.201, 29.250 | 73 | 37 |  |  | Fri 16/09/16 | Mon 05/06/17
1108 | 710017 | Stage-3 SAE Protocol Development - Phase 5 | SAES5 | 1 | Rel-14 | C1 | 2016-03-02 08:00 | 2017-03-15 17:00 | 100% | CP-160052 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com |  | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 71 | 36 |  |  | Wed 02/03/16 | Wed 02/03/16
1109 | 710018 | SAES5 CS Fallback in EPS | SAES5-CSFB | 2 | Rel-14 | C1 | 2016-03-02 08:00 | 2017-03-15 17:00 | 100% | CP-160052 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com | 11/6/16: 0%->5; 16/9/16: 5%->20; 2/12/16: 20%->70; 6/3/17: 70%->100 | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 71 | 36 |  |  | Wed 02/03/16 | Mon 06/03/17
1110 | 710019 | SAES5 for support for non-3GPP accesses | SAES5-non3GPP | 2 | Rel-14 | C1 | 2016-03-02 08:00 | 2017-03-15 17:00 | 100% | CP-160052 |  | Interdigital, Aghili, Behrouz | Behrouz.aghili@interdigital.com | 11/6/16: 0%->15; 16/9/16: 15%->20; 2/12/16: 20%->85; 6/3/17: 85%->100 | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 71 | 36 |  |  | Wed 02/03/16 | Mon 06/03/17
1111 | 720073 | SAE Protocol Development (Stage 3) - Phase 5 | SAES5 | 2 | Rel-14 | C1 | 2016-03-02 08:00 | 2017-03-15 17:00 | 100% | CP-160052 |  |  |  | Added following CT1's chair e-mail 14/06/16; 16/9/16: 0%->20; 2/12/16: 20%->85; 6/3/17: 85%->100 |  | 72 | 37 |  |  | Tue 24/03/15 | Mon 06/03/17
1112 | 720012 | Group based enhancements in the network capability exposure functions | GENCEF | 1 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-12-16 17:00 | 100% | SP-160311 | SP-170517 | Samsung, Sung Hwan Won | sunghwan.won@samsung.com |  |  | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1113 | 700043 | Study on group based enhancements in the network capability exposure functions | FS_GENCEF | 2 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-160311 |  | Samsung, Sung Hwan Won | sunghwan.won@samsung.com | 28/1/16: 23.773 added; 28/1/16: 23.742 added; 7/3/16: 0%->10; 9/6/16: 10%->100 | 23.xyz; 23.773; 23.742 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1114 | 720013 | Group based enhancements in the network capability exposure functions | GENCEF | 2 | Rel-14 | S2 | 2016-06-09 08:00 | 2016-12-16 17:00 | 100% | SP-160311 |  | Samsung, Sunghoon Kim | s.hun.kim@samsung.com | 19/9/16: 0%->90; 1/12/16: FCD:09/16->12/16; 1/12/16: 90%->100 | 23.682 | 72 | 37 |  |  | Mon 07/12/15 | Thu 01/12/16
1115 | 720084 | Robust Call Setup for VoLTE subscriber in LTE | RobVoLTE | 1 | Rel-14 |  | 2015-11-02 08:00 | 2018-09-14 17:00 | 99% | SP-160312 | [5 empty] | 72 | 37 |  |  | Mon 07/12/15 | NA
1116 | 700044 | Study on Robust Call Setup for VoLTE subscriber in LTE | FS_RobVoLTE | 2 | Rel-14 | S2 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150632 |  | Xiaobo Wu, Huawei | wuxiaobo@ huawei.com | 28/1/16: 23.750 added; 7/3/16: 0%->20; 9/6/16: 20%->100 | 23.8xx; 23.750 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1117 | 720301 | Robust Call Setup for VoLTE subscriber in LTE | RobVoLTE | 2 | Rel-14 | S2 | 2016-06-17 08:00 | 2016-09-15 17:00 | 100% | SP-160312 |  | Xiaobo Wu, Huawei | wuxiaobo@ huawei.com | 19/9/16: 0%->100. 1/12/16: UID changed: 720085 -> 720301 (720085 was also used for RP-161181) | 23.228, 23.237 | 72 |  |  |  | Mon 07/12/15 | Thu 01/12/16
1118 | 730022 | CT Aspects of RobVoLTE | RobVoLTE-CT | 2 | Rel-14 | C1 | 2016-09-16 08:00 | 2017-03-16 17:00 | 100% | CP-160478 |  | PATEL, Milan | Milan.Patel@huawei.com | 2/12/16: 0%->80; 6/3/17: 80%->100 | 24.229, 24.292 | 73 | 37 |  |  | Fri 16/09/16 | Mon 06/03/17
1119 | 730078 | Voice and Video Enhancement for LTE | LTE_VoLTE_ViLTE_enh | 2 | Rel-14 | R2 | 2016-09-15 08:00 | 2018-09-14 17:00 | 99% | RP-161856 |  | CMCC |  |  |  | 73 | 37 |  |  | Wed 14/12/16 | Mon 26/09/16
1120 | 730178 | Core part: Voice and Video Enhancement for LTE | LTE_VoLTE_ViLTE_enh-Core | 3 | Rel-14 | R2 | 2016-09-15 08:00 | 2017-03-15 17:00 | 100% | RP-161856 | RP-170323 | CMCC |  | ; 20/12/16: Compl:0%->80%; 21/3/17: Compl:80%->100%; 21/3/17: Stat Rep: ->RP-170323 |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 21/03/17
1121 | 760089 | UE Conformance Test Aspects –Voice and Video Enhancement for LTE | LTE_VoLTE_ViLTE_enh-UEConTest | 3 | Rel-14 | R5 | 2017-06-15 08:00 | 2018-09-14 17:00 | 100% | RP-182849 |  | CATT |  | ; 19/9/17: Compl:0%->20%; 8/1/18: Compl:20%->60%; 27/3/18: Compl:60 ;; 16/1/19: 95%->100; 16/1/19: WID:RP-171385->RP-182849 |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 16/01/19
1122 | 740010 | RAN-Assisted Codec Adaptation in MTSI | LTE_VoLTE_ViLTE_enh-S4 | 2 | Rel-14 | S4 | 2016-12-01 08:00 | 2017-06-09 17:00 | 100% | SP-160778 | SP-170516 | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 6/3/17: 0%->65; 6/3/17: FCD:03/17->06/17; 7/6/17: 65%->100 |  | 74 | 38 |  |  | Thu 01/12/16 | Wed 07/06/17
1123 | 720028 | Extension of UE Delay test methods and requirements | EXT_UED | 1 | Rel-14 | S4 | 2016-06-13 08:00 | 2017-06-09 17:00 | 100% | SP-160600 | SP-170345 | Stéphane Ragot, ORANGE | stephane.ragot@orange.com | 19/9/16: WID:SP-160271->SP-160600; 19/9/16: 0%->20; 1/12/16: 20%->30; 14/12/16: 30%->50; 6/3/17: 50%->60; 6/3/17: FCD:03/17->06/17; 7/6/17: 60%->100 | TR 26.954, 26.131, 26.132 | 72 | 37 |  |  | Sat 11/06/16 | Wed 07/06/17
1124 | 720037 | Improved operator control using new UE configuration parameters | IOC_UE_conf | 1 | Rel-14 |  | 2016-06-13 08:00 | 2017-03-15 17:00 | 100% | CP-160828 | CP-171176 | Sedlacek, Ivo | ivo.sedlacek@ericsson.com | 11/6/16: 0%->10; 17/10/16: WID:CP-160296->CP-160374; 5/12/16: WID:CP-160374->CP-160828 | 24.167, 24.229, 24.301, 24.302, 24.312, 24.341, 24.368, 24.607, 24.623, TS 24.XXX, TS 24.YYY | 72 | 37 |  |  | Sat 11/06/16 | Mon 05/12/16
1125 | 720038 | CT1 aspects of IOC_UE_conf | IOC_UE_conf | 2 | Rel-14 | C1 | 2016-06-13 08:00 | 2017-03-15 17:00 | 100% | CP-160828 |  | Sedlacek, Ivo | ivo.sedlacek@ericsson.com | 11/6/16: 0%->10; 16/9/16: 10%->20; 17/10/16: WID:CP-160296->CP-160374; 2/12/16: 20%->75; 6/3/17: 75%->100 | 24.167, 24.229, 24.301, 24.302, 24.312, 24.341, 24.368, 24.607, 24.623, 24.275 | 72 | 37 |  |  | Sat 11/06/16 | Mon 06/03/17
1126 | 720039 | CT6 aspects of IOC_UE_conf | IOC_UE_conf | 2 | Rel-14 | C6 | 2016-06-13 08:00 | 2017-03-15 17:00 | 100% | CP-160828 |  | Adrian Buckley | abuckley@blackberry.com | 11/6/16: 0%->10; 14/12/16: 0%->15; 7/3/17: 15%->85; 5/6/17: 85%->100 | 31.102, 31.103 | 72 | 37 |  |  | Sat 11/06/16 | Mon 05/06/17
1127 | 720001 | Shared Subscription Data Update | eSDU | 1 | Rel-14 | C4 | 2016-06-13 08:00 | 2016-12-15 17:00 | 100% | CP-160644 | CP-171050 | Nokia, Ulrich Wiehe | ulrich.wiehe@nokia.com | 13/6/16: 0%->25; 2/12/16: 25%->100; 5/12/16: WID:CP-160243->CP-160644 | 29.272, 29.002, 29.305, 29.230 | 72 | 37 |  |  | Mon 13/06/16 | Mon 05/12/16
1128 | 710012 | Rel-14 Charging | CH14 | 1 | Rel-14 | S5 | 2016-03-01 08:00 | 2017-06-09 17:00 | 100% | SP-160021 |  |  |  | Umbrella Feature |  | 71 | 36 |  |  | Tue 01/03/16 | Tue 01/03/16
1129 | 710008 | Resource Optimization for PS Domain Online | CH14-ROPOCH | 2 | Rel-14 | S5 | 2016-03-01 08:00 | 2017-06-09 17:00 | 100% | SP-160021 |  | Shrader, David(Ericsson) | david.shrader@ericsson.com | 13/6/16: 0%->10. FCD:09/16->03/17; 19/9/16: FCD: 09/16->03/17; 19/9/16: 10%->20; 1/12/16: 20%->50; 6/3/17: 50%->80; 6/3/17: FCD:03/17->06/20; 7/6/17: 80%->100 | 32.251, 32.299 | 71 | 36 |  |  | Tue 01/03/16 | Wed 07/06/17
1130 | 740015 | Charging for SMS via T4 | CH14-SMST4 | 2 | Rel-14 | S5 | 2016-12-01 08:00 | 2017-06-09 17:00 | 100% | SP-160840 |  | Nokia | Maryse <dot> Gardella <at> Nokia <dot> com | 6/3/17: 0%->20; 6/3/17: FCD:03/17->06/17; 7/6/17: 20%->100 | TS 32.274, TS 32.250 , TS 32.298, TS 32.299 | 74 | 38 |  |  | Thu 01/12/16 | Wed 07/06/17
1131 | 720049 | Charging Aspects of Enhanced Proximity-based Services | CH14-ProSe | 2 | Rel-14 | S5 | 2016-06-13 08:00 | 2017-06-09 17:00 | 100% | SP-160428 | SP-170408 | Chen, Shan | chenshan@huawei.com | 19/9/16: 0%->40; 1/12/16: 40%->60; 6/3/17: FCD:03/17->06/17; 6/3/17: 60%->80; 7/6/17: 80%->100 | 32.240, 32.251, 32.277, 32.298, 32.299 | 72 | 37 |  |  | Mon 13/06/16 | Wed 07/06/17
1132 | 740019 | Determination of Completeness of Charging Information in IMS | CH14-DCCII | 1 | Rel-14 | S5 | 2016-06-13 08:00 | 2017-06-09 17:00 | 100% | SP-160398 |  | Jesske, Roland (Deutsche Telekom) |  | 19/9/16: 0%->10 | 32.240, 32.260, 32.298, 32.299 | 72 | 37 |  |  | Mon 13/06/16 | Mon 19/09/16
1133 | 720045 | Determination of Completeness of Charging Information in IMS | CH14-DCCII | 2 | Rel-14 | S5 | 2016-06-13 08:00 | 2017-06-09 17:00 | 100% | SP-160398 | SP-170344 | Jesske, Roland (Deutsche Telekom) |  | 19/9/16: 0%->10; 6/3/17: FCD:03/17->06/17; 7/6/17: 10%->100 | 32.240, 32.260, 32.298, 32.299 | 72 | 37 |  |  | Mon 13/06/16 | Wed 07/06/17
1134 | 740059 | CT Aspects of Determination of Completeness of Charging Information in IMS | CH14-DCCII-CT | 2 | Rel-14 | ct | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160697 | CP-171048 | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de |  |  | 74 | 38 |  |  | Thu 01/12/16 | Tue 21/03/17
1135 | 740020 | CT1 Aspects of Determination of Completeness of Charging Information in IMS | CH14-DCCII-CT | 3 | Rel-14 | C1 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160697 |  | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de | 2/12/16: 0%->10; 6/3/17: 10%->35; 5/6/17: 35%->100 | 24.229 | 74 | 38 |  |  | Thu 01/12/16 | Mon 05/06/17
1136 | 740021 | CT3 Aspects of Determination of Completeness of Charging Information in IMS | CH14-DCCII-CT | 3 | Rel-14 | C3 | 2016-12-01 08:00 | 2017-03-14 17:00 | 100% | CP-160697 |  | Michael KREIPL, Deutsche Telekom | michael(dot)kreipl(at)telekom(dot)de | 8/6/17: 0%->100 | 29.165 | 74 | 38 |  |  | Thu 01/12/16 | Thu 08/06/17
1137 | 700060 | Enhanced LAA for LTE | LTE_eLAA | 1 | Rel-14 |  | 2015-12-15 08:00 | 2018-09-14 17:00 | 94% | RP-152272 |  | Ericsson |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
1138 | 700160 | Core part: Enhanced LAA for LTE | LTE_eLAA-Core | 2 | Rel-14 | R1 | 2015-12-15 08:00 | 2017-03-15 17:00 | 100% | RP-162235 | RP-170269 | Ericsson |  | 22/3/16: Compl:0%->20%22/3/16: WID: RP-152272->RP-1604071/7/16: Compl:20%->60%1/7/16: WID: RP-160407->RP-160881; 26/9/16: Compl:60%->92%; 26/9/16: CD:Thu 15/09/16->Thu 15/12/16; 26/9/16: WID: ; 20/12/16: Compl:92%->97%; 20/12/16:21/3/17: Compl: |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 21/03/17
1139 | 700260 | Perf. part: Enhanced LAA for LTE | LTE_eLAA-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-09-15 17:00 | 100% | RP-162235 |  | Ericsson |  | 22/3/16: WID: RP-152272->RP-160407; 1/7/16: WID: RP-160407->RP-16088126/9/16: CD:Wed 15/03/17->Thu 15/06/1726/9/16: WID: RP-160881->RP-161832; 20/12/16: WID: RP-161832->RP-162235;21/3/17: Compl:0%->33%; 19/6/17: Compl:33%->50%; ; |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 19/09/17
1140 | 730075 | UE Conformance Test Aspects - Enhanced LAA for LTE | LTE_eLAA-UEConTest | 2 | Rel-14 | R5 | 2016-09-15 08:00 | 2018-09-14 17:00 | 85% | RP-171577 |  | Intel |  | ; 21/3/17: Compl:0%->5% ;19/6/17: Compl:5%->6%; 19/9/17: Compl 8/1/18: C2 ; |  | 73 | 37 |  |  | Mon 26/09/16 | Wed 27/06/18
1141 | 700062 | RRC optimization for UMTS | UTRA_RRCopt | 1 | Rel-14 | R2 | 2015-12-15 08:00 | 2016-09-15 17:00 | 100% | RP-152267 |  | Ericsson |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
1142 | 700162 | Core part: RRC optimization for UMTS | UTRA_RRCopt-Core | 2 | Rel-14 | R2 | 2015-12-15 08:00 | 2016-09-15 17:00 | 100% | RP-160287 | RP-172758 | Ericsson |  | 22/3/16: Compl:0%->8%; 1/7/16: Compl:8%->70%26/9/16: Compl:70%->100%; 8/1/18: Stat Rep: ->RP-172758 |  | 70 | 36 |  |  | Fri 01/01/16 | Mon 08/01/18
1143 | 700063 | DTX/DRX enhancements in CELL_FACH | FACH_DTXDRX | 1 | Rel-14 | R2 | 2015-12-15 08:00 | 2016-12-15 17:00 | 100% | RP-152286 |  | Huawei |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
1144 | 700163 | Core part: DTX/DRX enhancements in CELL_FACH | FACH_DTXDRX-Core | 2 | Rel-14 | R2 | 2015-12-15 08:00 | 2016-12-15 17:00 | 100% | RP-162513 | RP-162132 | Huawei |  | 22/3/16: Compl:0%->20%; 1/7/16: Compl:20%->50%26/9/16: Compl:50%->65%; 20/12/16: Compl:65%->100%; |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
1145 | 700077 | AWS-3/4 Band for LTE | LTE_AWS_3_4 | 1 | Rel-14 |  | 2015-12-15 08:00 | 2016-12-15 17:00 | 100% | RP-151731 |  | Dish Network |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
1146 | 700177 | Core part: AWS-3/4 Band for LTE | LTE_AWS_3_4-Core | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-160783 |  | Dish Network |  | ; 22/3/16: Compl:0%->60%; 1/7/16: Compl:60%->100%; 1/7/16: CD:Th | 36.749 | 70 | 36 |  |  | Fri 01/01/16 | Fri 01/07/16
1147 | 700277 | Perf. part: AWS-3/4 Band for LTE | LTE_AWS_3_4-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-160783 |  | Dish Network |  | 1/7/16: Compl:0%->100%1/7/16: CD:Thu 15/09/16->Wed 15/06 |  | 70 | 36 |  |  | Fri 01/01/16 | Fri 01/07/16
1148 | 730072 | UE Conformance Test Aspects – AWS-3/4 Band for LTE (Band 70) | LTE_AWS_3_4-UEConTest | 2 | Rel-14 | R5 | 2016-09-15 08:00 | 2016-12-15 17:00 | 100% | RP-162009 |  | Dish Network |  | ; 20/12/16: Compl:0%->100%; |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 20/12/16
1149 | 700078 | LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3 | LTE_1980_2170_REG3 | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2015-12-15 17:00 | 0% | RP-152238 |  | KT Corp. |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
1150 | 700178 | Core part: LTE FDD in the Bands 1980-2010 MHz and 2170-2200MHz for Region 3 | LTE_1980_2170_REG3-Core | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2015-12-15 17:00 | 0% | RP-152238 |  | KT Corp. |  |  |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 22/12/15
1151 | 740073 | Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1 | LTE_1980_2170_REG1_addBWs | 1 | Rel-14 | R4 | 2016-12-15 08:00 | 2017-09-15 17:00 | 99% | RP-162515 |  | Hughes Network Systems |  |  |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 20/12/16
1152 | 740173 | Core part: Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1 | LTE_1980_2170_REG1_addBWs-Core | 2 | Rel-14 | R4 | 2016-12-15 08:00 | 2017-03-15 17:00 | 100% | RP-170235 |  | Hughes Network Systems |  | ; 21/3/17: Compl:0%->100% ; 2 |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 21/03/17
1153 | 760083 | UE Conformance Test Aspects – Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1 | LTE_1980_2170_REG1_addBWs-UEConTest | 2 | Rel-14 | R5 | 2017-06-15 08:00 | 2017-09-15 17:00 | 100% | RP-170931 |  | Dish Network |  | ; 19/9/17: Compl:0%->100% |  | 76 | 39 |  |  | Fri 16/06/17 | Tue 19/09/17
1154 | 700079 | LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE CA (2DL/1UL) with Band 3 for region 1 | LTE_FDD_2600_CA_B3 | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-12-15 17:00 | 99% | RP-152253 |  | Orange |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
1155 | 700179 | Core part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE CA (2DL/1UL) with Band 3 for region 1 | LTE_FDD_2600_CA_B3-Core | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-161200 |  | Orange |  | 28/1/16: 36.858 added;22/3/16: Compl:0%->40%22/3/16: WID: RP-152253->RP-160378; 1/7/16: Compl:40%->100%; | 36.858 | 70 | 36 |  |  | Fri 01/01/16 | Fri 01/07/16
1156 | 700279 | Perf. part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE CA (2DL/1UL) with Band 3 for region 1 | LTE_FDD_2600_CA_B3-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-161200 |  | Orange |  | ; 22/3/16: WID: RP-152253->RP-1603781/7/16: Compl:0%->100%1/7/16 |  | 70 | 36 |  |  | Fri 01/01/16 | Fri 01/07/16
1157 | 750052 | UE Conformance Test Aspects - LTE 2.6 GHz FDD SDL band (2570-2620 MHz) and LTE CA (2DL/1UL) with Band 3 for Region 1 (Band 69) | LTE_FDD_2600_CA_B3-UEConTest | 2 | Rel-14 | R5 | 2017-03-15 08:00 | 2017-12-15 17:00 | 100% | RP-172257 |  | Bureau Veritas |  | ; 19/9/17: Compl:43%->96%; 8/1/18: Compl:96%->100%; | [5 empty] | Mon 19/06/17 | Mon 08/01/18
1158 | 700080 | Multi-Band Base Station testing with three or more bands | MB_BS_test_3B | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-12-15 17:00 | 100% | RP-152205 |  | Alcatel-Lucent |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
1159 | 700180 | Core part: Multi-Band Base Station testing with three or more bands | MB_BS_test_3B-Core | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-12-15 17:00 | 100% | RP-162442 | RP-162032 | Alcatel-Lucent |  | 22/3/16: Compl:0%->50%22/3/16: WID: RP-152205->RP-1600631/7/16: Compl:50%->90%; 26/9/16: Compl:90%->95%; 26/9/16; 20/12/16: Compl:95%->100%; | 37.871 | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
1160 | 700280 | Perf. part: Multi-Band Base Station testing with three or more bands | MB_BS_test_3B-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-12-15 17:00 | 100% | RP-162442 |  | Alcatel-Lucent |  | 22/3/16: Compl:0%->5%22/3/16: WID: RP-152205->RP-160063; 1/7/16: Compl:5%->30%26/9/16: Compl:30%->60%26/; 20/12/16: Compl:60%->100%; |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
1161 | 700081 | Performance enhancements for high speed scenario in LTE | LTE_high_speed | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2018-09-14 17:00 | 98% | RP-152263 |  | NTT DOCOMO |  |  |  | 70 | 36 |  |  | Thu 07/01/16 | Tue 22/12/15
1162 | 700181 | Core part: Performance enhancements for high speed scenario in LTE | LTE_high_speed-Core | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2016-12-15 17:00 | 100% | RP-160172 | RP-162222 | NTT DOCOMO |  | 22/3/16: Compl:0%->5%22/3/16: WID: RP-152263->RP-160172; 1/7/16: Compl:5%->25%26/9/16: Compl:25%->45%20/12/16: Compl:45%->100%20/12/16: Stat Rep: ->RP-162222 |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
1163 | 700282 | Perf. part: Performance enhancements for high speed scenario in LTE | LTE_high_speed-Perf | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 100% | RP-171039 |  | NTT DOCOMO |  | 22/3/16: WID: RP-152263->RP-1601721/7/16: Compl:0%->20%; 26/9/16: Compl:20%->25%; 20/12/16: Compl:25%->35% ; 21/3/17: Compl:35%->70%; 19/6/17: Compl:70%->100%; 19/6/17: WID: RP-160172->RP-171039 |  | 70 | 36 |  |  | Fri 01/01/16 | Mon 19/06/17
1164 | 750056 | UE Conformance Test Aspects - Performance enhancements for high speed scenario in LTE | LTE_high_speed-UEConTest | 2 | Rel-14 | R5 | 2017-03-15 08:00 | 2018-09-14 17:00 | 95% | RP-170367 |  | CMCC |  | tested: REL-14 LTE_high_speed-Core;; 19/6/17: Compl: 1 8/1/18:27/3/ ; |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1165 | 710072 | Further Indoor Positioning Enhancements for UTRA and LTE | UTRA_LTE_iPos_enh2 | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-12-15 17:00 | 99% | RP-160538 |  | Huawei |  | follow-up WI of REL-13 WI UTRA_LTE_iPos_enh |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
1166 | 710172 | Core part: Further Indoor Positioning Enhancements for UTRA and LTE | UTRA_LTE_iPos_enh2-Core | 2 | Rel-14 | R2 | 2016-03-15 08:00 | 2016-12-15 17:00 | 100% | RP-162026 | RP-162506 | Huawei |  | follow-up WI of REL-13 WI UTRA_LTE_iPos_enh1/7/16: Compl:0%->30%; 26/9/16: Compl:30%->60%; 26/9/16: WID:; 20/12/16: Compl:60%->100%; |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 20/12/16
1167 | 710272 | Perf. part: Further Indoor Positioning Enhancements for UTRA and LTE | UTRA_LTE_iPos_enh2-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-06-15 17:00 | 100% | RP-162026 |  | Huawei |  | 26/9/16: CD:Wed 15/03/17->Thu 15/06/1726/9/16: WID: RP-160538->RP-161850; 20/12/16: Compl:0%->30%; 20/12/16: WI21/3/17: Compl:30%->50%19/6/17: Compl:50%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 19/06/17
1168 | 750053 | UE Conformance Test Aspects - RAT Independent Further Indoor Positioning Enhancements for LTE | LTE_iPos_enh2_RI-UEConTest | 2 | Rel-14 | R5 | 2017-03-15 08:00 | 2017-12-15 17:00 | 100% | RP-172317 |  | NextNav |  | tested: REL-14 UTRA_LTE_iPos_enh2-Core (but only RAT independent aspects for LTE);; ; |  | 75 | 38 |  |  | Tue 21/03/17 | Mon 08/01/18
1169 | 710076 | Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE | LTE_MIMO_OTA | 1 | Rel-14 | R4 | 2016-03-15 08:00 | 2018-03-15 17:00 | 99% | RP-160603 |  | Intel |  | follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core; no Perf. part |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
1170 | 710176 | Core part: Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE | LTE_MIMO_OTA-Core | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-09-15 17:00 | 100% | RP-170278 |  | Intel |  | follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core; no Perf. part1/7/16: Compl:0%->10%1/7/16: WID: RP-160603->RP-16091426/9/16: Compl:10%->15%; 20/12/16: Compl:15%->25%; 20/12/16: WID: RP-160914->RP-162306;21/3/17: Compl:25%->33%;1 ; |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 19/09/17
1171 | 730071 | UE Conformance Test Aspects - Radiated Performance of Multiple-antenna Receivers in the LTE UE | LTE_MIMO_OTA-UEConTest | 2 | Rel-14 | R5 | 2016-09-15 08:00 | 2018-03-15 17:00 | 100% | RP-171615 |  | Intel |  | ; 20/12/16: Compl:0%->5%21/3/17: Compl:5%->20%19/6/17: Compl:20% 1 8/1/18: C27/3/ |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 27/03/18
1172 | 710077 | Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-12-15 17:00 | 99% | RP-160623 |  | Samsung |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
1173 | 710177 | Core part: Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO-Core | 2 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-03-15 17:00 | 100% | RP-160623 | RP-170173 | Samsung |  | ; 1/7/16: Compl:0%->25%26/9/16: Compl:25%->40%; 20/12/16: Compl:40%->80%; 20/12/16: Stat Rep: -->; 21/3/17: Compl:80%->100%; 21/3/17: Stat Rep: ->RP-170173 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
1174 | 710277 | Perf. part: Enhancements on Full-Dimension (FD) MIMO for LTE | LTE_eFDMIMO-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-12-15 17:00 | 100% | RP-160623 |  | Samsung |  | ; 20/12/16: Stat Rep: -->; 19/6/17: Compl:0%->50%19/9/17: Compl:50%->70%19/9/17: CD:Fri 15/09/17->Fri 15/12/17; 8/1/18: Compl:70%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 08/01/18
1175 | 710078 | Further mobility enhancements in LTE | LTE_eMob | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-06-15 17:00 | 100% | RP-160636 |  | ZTE |  | no Perf. part |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
1176 | 710178 | Core part: Further mobility enhancements in LTE | LTE_eMob-Core | 2 | Rel-14 | R2 | 2016-03-15 08:00 | 2017-03-15 17:00 | 100% | RP-162503 | RP-170369 | ZTE |  | no Perf. part; 1/7/16: Compl:0%->25%; 1/7/16: WID: RP-160636->RP-160921; 26/9/16: Compl:25%->50%; 20/12/16: Compl:50%->90%; 20/12/16: CD:Thu 15/12/16->Wed 15/03/1721/3/17: Compl:90%->100%; 21/3/17: St |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
1177 | 740265 | Perf. Part: Further mobility enhancements in LTE | LTE_eMob-Perf | 2 | Rel-14 | R4 | 2016-12-15 08:00 | 2017-06-15 17:00 | 100% | RP-162503 |  | ZTE | [7 empty] | Mon 19/06/17 | NA
1178 | 710079 | Uplink Capacity Enhancements for LTE | LTE_UL_CAP_enh | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2018-12-14 17:00 | 82% | RP-160664 |  | Ericsson |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
1179 | 710179 | Core part: Uplink Capacity Enhancements for LTE | LTE_UL_CAP_enh-Core | 2 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-03-15 17:00 | 100% | RP-162488 | RP-170115 | Ericsson |  | 1/7/16: Compl:0%->25%26/9/16: Compl:25%->40%; 20/12/16: Compl:40%->85%; 20/12/16: WID: RP-160664->RP-162488; 20/12/16: Stat Rep: -->21/3/17: Compl:85%->100%21/3/17: Stat Rep: ->RP-170115 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
1180 | 710279 | Perf. part: Uplink Capacity Enhancements for LTE | LTE_UL_CAP_enh-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-09-15 17:00 | 100% | RP-162488 |  | Ericsson |  | ; 20/12/16: WID: RP-160664->RP-162488; 20/12/16: Stat Rep: -->;21/3/17: Compl:0%->20%19/6/17: Compl:20%->75%; 19/9/17: Compl:75%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 19/09/17
1181 | 780063 | UE Conformance Test Aspects - Uplink capacity enhancements for LTE | LTE_UL_CAP_enh-UEConTest | 2 | Rel-14 | R5 | 2017-12-15 08:00 | 2018-12-14 17:00 | 35% | RP-172639 |  | Ericsson |  | tested: REL-14 WI LTE_UL_CAP_enh-Core; related to UL 256 QAM27/3 ; |  | 78 | 40 |  |  | Mon 08/01/18 | Wed 27/06/18
1182 | 710080 | L2 latency reduction techniques for LTE | LTE_LATRED_L2 | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2018-03-15 17:00 | 99% | RP-160667 |  | Ericsson |  | no Perf. part; follow-up WI of SI FS_LTE_LATRED |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
1183 | 710180 | Core part: L2 latency reduction techniques for LTE | LTE_LATRED_L2-Core | 2 | Rel-14 | R2 | 2016-03-15 08:00 | 2016-09-15 17:00 | 100% | RP-160667 | RP-172559 | Ericsson |  | no Perf. part; follow-up WI of SI FS_LTE_LATRED; 1/7/16: Compl:0%->80%; 26/9/16: Compl:80%->100%8/1/18: Stat Rep: -->RP-172559 |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 08/01/18
1184 | 780064 | UE Conformance Test Aspects - L2 latency reduction techniques for LTE | LTE_LATRED_L2-UEConTest | 2 | Rel-14 | R5 | 2017-12-15 08:00 | 2018-03-15 17:00 | 100% | RP-180530 |  | Ericsson |  | tested: REL-14 WI LTE_LATRED_L2-Core27/3/18: Compl:0%->100%; |  | 78 | 40 |  |  | Mon 08/01/18 | Tue 27/03/18
1185 | 710081 | eMBMS enhancements for LTE | MBMS_LTE_enh2 | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-09-15 17:00 | 99% | RP-160675 | RP-171628 | Ericsson |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
1186 | 710181 | Core part: eMBMS enhancements for LTE | MBMS_LTE_enh2-Core | 2 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-09-15 17:00 | 100% | RP-170199 |  | Ericsson |  | 1/7/16: Compl:0%->10%1/7/16: CD:Tue 15/03/16->Wed 15/03/171/7/16: WID: RP-160675->RP-16129726/9/16: Compl:10%->55%; 20/12/16: Compl:55%->80%; 20/12/16: WID: RP-161297->RP-162231 ; 21/3/17: Compl:80%->90% ; 19/6/17: Compl:90 ; |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 19/09/17
1187 | 710281 | Perf. part: eMBMS enhancements for LTE | MBMS_LTE_enh2-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-09-15 17:00 | 100% | RP-170199 |  | Ericsson |  | ; 1/7/16: CD:Wed 15/06/16->Fri 15/09/17; 1/7/16: WID: RP-160675->RP-161297; 20/12/16: WID: RP-161297->RP-162231; 20/12/16: Stat Rep: --> ; 21/3/17: WID: RP-162231->RP-17019919/6/17: Compl:0%->70%; 19/9/17: Compl:70%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 19/09/17
1188 | 710082 | SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2018-06-15 17:00 | 99% | RP-160676 |  | Huawei |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
1189 | 710182 | Core part: SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch-Core | 2 | Rel-14 | R1 | 2016-03-15 08:00 | 2016-12-15 17:00 | 100% | RP-160935 | RP-162137 | Huawei |  | 1/7/16: Compl:0%->35%1/7/16: WID: RP-160676->RP-160935; 26/9/16: Compl:35%->55%; 20/12/16: Compl:55%->100%; 20/12/16: Stat Rep: -->RP-162137 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 20/12/16
1190 | 710282 | Perf. part: SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-06-15 17:00 | 100% | RP-160935 |  | Huawei |  | 1/7/16: WID: RP-160676->RP-160935; 20/12/16: Stat Rep: --> 21/3/17: Compl:0%->25% 21/3/17: CD:Wed 15/03/17->Thu 15/06/17; 19/6/17: Compl:25%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 19/06/17
1191 | 750054 | UE Conformance Test Aspects - SRS (sounding reference signal) switching between LTE component carriers | LTE_SRS_switch-UEConTest | 2 | Rel-14 | R5 | 2017-03-15 08:00 | 2018-06-15 17:00 | 100% | RP-180848 |  | Huawei |  | tested: REL-14 LTE_SRS_switch-Core;; 19/6/17: Compl:0%->5%; 8/1/18: Compl:27/3/ ; |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1192 | 710084 | Downlink Multiuser Superposition Transmission for LTE | LTE_MUST | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-06-15 17:00 | 100% | RP-160680 |  | MediaTek |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 22/03/16
1193 | 710184 | Core part: Downlink Multiuser Superposition Transmission for LTE | LTE_MUST-Core | 2 | Rel-14 | R1 | 2016-03-15 08:00 | 2016-12-15 17:00 | 100% | RP-161019 | RP-162504 | MediaTek |  | ; 1/7/16: Compl:0%->40%; 1/7/16: WID: RP-160680->RP-16101926/9/16: Compl:40%->60%; 20/12/16: Compl:60%->100%; 20/12/16: Stat Rep: -->RP-162504 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 20/12/16
1194 | 710284 | Perf. part: Downlink Multiuser Superposition Transmission for LTE | LTE_MUST-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-06-15 17:00 | 100% | RP-161019 |  | MediaTek |  | 1/7/16: WID: RP-160680->RP-161019; 26/9/16: CD:Fri 15/09/17->Thu 15/06/17; 20/12/16: Stat Rep: --> ; 21/3/17: Compl:0%->25%19/6/17: Compl:25%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 19/06/17
1195 | 720040 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 1 | Rel-14 | C1 | 2016-06-14 08:00 | 2017-03-15 17:00 | 81% | CP-160294 |  |  |  | 11/6/16: 0%->15; 5/6/17: 67%->100 |  | 72 | 37 |  |  | Sat 11/06/16 | Mon 05/06/17
1196 | 720070 | CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 2 | Rel-14 | C1 | 2016-06-14 08:00 | 2017-03-15 17:00 | 100% | CP-160294 |  | Alcatel-Lucent | Keith Drage | Mar.15: 0->10%; June2015: Compl:10%->30; 07/09/15: 30%->70; 7/12/15: 70%->100; 16/9/16: 0%->30; 2/12/16: 30%->75; 6/3/17: 75%->100 |  | 72 | 37 |  |  | Thu 04/12/14 | Mon 06/03/17
1197 | 720071 | (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 2 | Rel-14 | C1-IETF | 2016-06-14 08:00 | 2017-03-15 17:00 | 100% | CP-160294 |  | Alcatel-Lucent | Keith Drage |  | draft-ietf-mmusic-dtls-sdp, draft-ietf-mmusic-4572-update (became RFC 8122) | 72 | 37 |  |  | Thu 04/12/14 | Mon 07/12/15
1198 | 800112 | (IETF) Session Description Protocol (SDP) Offer/Answer Considerations for Datagram Transport Layer Security (DTLS) and Transport Layer Security (TLS) (draft-ietf-mmusic-dtls-sdp) | IMSProtoc8 | 2 | Rel-14 | C1-IETF | 2016-06-14 08:00 | 2017-03-15 17:00 | 25% | CP-160294 |  | Alcatel-Lucent | Keith Drage |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
1199 | 720072 | CT3 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc8 | 2 | Rel-14 | C3 | 2016-06-14 08:00 | 2017-03-15 17:00 | 100% | CP-160294 |  | Alcatel-Lucent | Keith Drage | 2/4/15: added, following CT3 chair's info that the WID also has a CT3 part; June2015: Compl:0%->20; 07/09/15: 20%->40; 7/12/15: 40%->100; 20/9/16: 0%->10; 2/12/16: 10%->30; 6/3/17: 30%->100 |  | 72 | 37 |  |  | Thu 02/04/15 | Mon 06/03/17
1200 | 720094 | Multi-Carrier Enhancements for UMTS | UTRA_MCe | 1 | Rel-14 | R2 | 2015-12-15 08:00 | 2016-12-15 17:00 | 100% | RP-161259 |  | Huawei, HiSilicon |  | no Perf. part; follow-up WI of REL-14 SI FS_UTRA_MCe |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
1201 | 700059 | Study on Multi-Carrier Enhancements for UMTS | FS_UTRA_MCe | 2 | Rel-14 | R1 | 2015-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-152290 |  | Huawei |  | 22/3/16: Compl:0%->20%; 1/7/16: Compl:20%->100%; 28/7/16: 25.707 added; | 25.707 | 70 | 36 |  |  | Fri 01/01/16 | Thu 28/07/16
1202 | 720194 | Core part: Multi-Carrier Enhancements for UMTS | UTRA_MCe-Core | 2 | Rel-14 | R2 | 2016-06-15 08:00 | 2016-12-15 17:00 | 100% | RP-162453 | RP-162129 | Huawei, HiSilicon |  | no Perf. part; follow-up WI of REL-14 SI FS_UTRA_MCe; 26/9/16: Compl:0%->35%; 20/12/16: Compl:35%->100%; |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
1203 | 720095 | Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States | LTE_TDD_3550_CBRS_US | 1 | Rel-14 | R4 | 2016-06-15 08:00 | 2017-06-15 17:00 | 100% | RP-161219 |  | Nokia |  |  |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
1204 | 720195 | Core part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States | LTE_TDD_3550_CBRS_US-Core | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 100% | RP-162007 |  | Nokia |  | 26/9/16: Compl:0%->70%; 6/10/16: 36.744 added; 20/12/16: Compl:70%->100%; | 36.744 | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
1205 | 720295 | Perf. part: Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States | LTE_TDD_3550_CBRS_US-Perf | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 100% | RP-162007 |  | Nokia |  | ; 20/12/16: Compl:0%->100%; |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
1206 | 740069 | UE Conformance Test Aspects – Citizens Broadband Radio Service (CBRS) 3.5GHz Band for LTE in the United States (Band 48) | LTE_TDD_3550_CBRS_US-UEConTest | 2 | Rel-14 | R5 | 2016-12-15 08:00 | 2017-06-15 17:00 | 100% | RP-162254 |  | Nokia |  | 21/3/17: Compl:0%->60% ; 19/6/17: Compl:60%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Mon 19/06/17
1207 | 720096 | LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2 | 1 | Rel-14 | R4 | 2016-06-15 08:00 | 2017-03-15 17:00 | 100% | RP-161221 |  | Sprint |  | follow-up WI of SI FS_LTE_B41_HPUE |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
1208 | 720196 | Core part: LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2-Core | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 100% | RP-161221 |  | Sprint |  | follow-up WI of SI FS_LTE_B41_HPUE; 26/9/16: Compl:0%->80%; 20/12/16: Compl:80%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
1209 | 720296 | Perf. part: LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2-Perf | 2 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 100% | RP-161221 |  | Sprint |  | 26/9/16: Compl:0%->80%; 20/12/16: Compl:80%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
1210 | 730076 | UE Conformance Test Aspects – LTE Band 41 UE power class 2 operation | LTE_B41_UE_PC2-UEConTest | 2 | Rel-14 | R5 | 2016-09-15 08:00 | 2017-03-15 17:00 | 100% | RP-161789 |  | Sprint |  | ; 20/12/16: Compl:0%->65% 21/3/17: Compl:65%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 21/03/17
1211 | 721002 | Dedicated Core Networks for GERAN | DECOR_GERAN | 1 | Rel-14 | R6 | 2016-06-15 08:00 | 2016-09-15 17:00 | 100% | RP-161029 |  | Ericsson |  | no Perf. part; DECOR was a REL-13 SA2 feature |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
1212 | 721102 | Core part: Dedicated Core Networks for GERAN | DECOR_GERAN-Core | 2 | Rel-14 | R6 | 2016-06-15 08:00 | 2016-09-15 17:00 | 100% | RP-161029 | RP-170194 | Ericsson |  | no Perf. part; DECOR was a REL-13 SA2 feature; 26/9/16: Compl:0%->100%21/3/17: Stat Rep: ->RP-170194 |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 21/03/17
1213 | 721003 | Positioning Enhancements for GERAN | ePOS_GERAN | 1 | Rel-14 | R6 | 2016-06-15 08:00 | 2017-06-15 17:00 | 100% | RP-161260 |  | Ericsson |  |  |  | 72 | 37 |  |  | Fri 08/07/16 | Wed 22/06/16
1214 | 721103 | Core part: Positioning Enhancements for GERAN | ePOS_GERAN-Core | 2 | Rel-14 | R6 | 2016-06-15 08:00 | 2017-06-15 17:00 | 100% | RP-171052 | RP-170920 | Ericsson |  | 26/9/16: Compl:0%->30%; 20/12/16: Compl:30%->50% 21/3/17: Compl:50%->80% ; 19/6/17: Compl:80%->100%; |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
1215 | 721203 | Perf. part: Positioning Enhancements for GERAN | ePOS_GERAN-Perf | 2 | Rel-14 | R6 | 2016-06-15 08:00 | 2017-06-15 17:00 | 100% | RP-171052 |  | Ericsson |  | ; 20/12/16: Compl:0%->50% ; 21/3/17: Compl:50%->80%; 19/6/17: Compl:80%->100%; |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
1216 | 730079 | Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN | UMTS_QMC_Streaming | 1 | Rel-14 | R2 | 2014-12-03 08:00 | 2018-03-15 17:00 | 99% | RP-161917 |  | China Unicom |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
1217 | 660037 | Study on KQIs for Service Experience | FS_KQISE | 2 | Rel-14 | S5 | 2014-12-03 08:00 | 2016-03-11 17:00 | 100% | SP-150676 |  | Li, Hui (hui.li(at)huawei.com) | hui.li(at)huawei.com | Mar 15: 0->5%; June2015: Compl:0%->40; 07/09/15: 40%->50; 14/09/15: WID:SP-140784->SP-150405; 7/12/15: 50%->75; 7/12/15: WID:SP-150405->SP-150676 ; 7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14 | TR 32.8xy | 66 | 34 |  |  | Thu 04/12/14 | Tue 22/03/16
1218 | 730179 | Core part:Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN | UMTS_QMC_Streaming-Core | 2 | Rel-14 | R2 | 2016-09-15 08:00 | 2017-03-15 17:00 | 100% | RP-161917 | RP-170259 | China Unicom |  | ; 20/12/16: Compl:0%->60% ; 21/3/17: Compl:60%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 21/03/17
1219 | 750055 | UE Conformance Test Aspects -Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN | UMTS_QMC_Streaming-UEConTest | 2 | Rel-14 | R5 | 2017-03-15 08:00 | 2018-03-15 17:00 | 100% | RP-180559 |  | Huawei |  | tested: REL-14 UMTS_QMC_Streaming-Core;19/6/17: Comp 19/ 8/1/18: 27/3/ |  | 75 | 38 |  |  | Tue 21/03/17 | Tue 27/03/18
1220 | 730080 | Flexible eNB-ID and Cell-ID in E-UTRAN | LTE_FNBID | 1 | Rel-14 | R3 | 2016-03-15 08:00 | 2017-03-15 17:00 | 100% | RP-161896 |  | China Telecom |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
1221 | 710056 | Study on flexible eNB-ID and Cell-ID in E-UTRAN | FS_LTE_FNBID | 2 | Rel-14 | R3 | 2016-03-15 08:00 | 2016-09-15 17:00 | 100% | RP-160534 | - | China Telecom |  | 1/7/16: Compl:0%->60%26/9/16: Compl:60%->100% | New TR 36.896 | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
1222 | 730180 | Core part: Flexible eNB-ID and Cell-ID in E-UTRAN | LTE_FNBID-Core | 2 | Rel-14 | R3 | 2016-09-15 08:00 | 2017-03-15 17:00 | 100% | RP-161896 | RP-170478 | China Telecom |  | ; 20/12/16: Compl:0%->80%21/3/17: Compl:80%->100%21/3/17: Stat Rep: ->RP-170478 |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 21/03/17
1223 | 730084 | 4 receiver (4Rx) antenna ports with Carrier Aggregation (CA) for LTE downlink (DL) | LTE_4Rx_AP_DL_CA | 1 | Rel-14 | R4 | 2016-09-15 08:00 | 2018-09-14 17:00 | 95% | RP-161897 |  | Ericsson |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
1224 | 730184 | Core part: 4 receiver (RX) antenna ports with CA for LTE downlink (DL) | LTE_4Rx_AP_DL_CA-Core | 2 | Rel-14 | R4 | 2016-09-15 08:00 | 2016-12-15 17:00 | 100% | RP-161897 | RP-162059 | Ericsson |  | ; 20/12/16: Compl:0%->100%; 20/12/16: Stat Rep: ->RP-162059 |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 20/12/16
1225 | 730284 | Perf. part: 4 receiver (RX) antenna ports with CA for LTE downlink (DL) | LTE_4Rx_AP_DL_CA-Perf | 2 | Rel-14 | R4 | 2016-09-15 08:00 | 2017-09-15 17:00 | 100% | RP-161897 |  | Ericsson |  | ; 20/12/16: Compl:0%->30%;21/3/17: Compl:30%->50%19/6/17: Compl:50%->90%; 19/9/17: Compl:90%->100% |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 19/09/17
1226 | 740071 | Introduction of new band support for 4Rx antenna ports for LTE | LTE_4Rx_AP_DL_bands | 2 | Rel-14 | R4 | 2016-12-15 08:00 | 2018-09-14 17:00 | 93% | RP-162496 |  | Huawei |  | Pending acronym |  | 74 | 38 |  |  | Tue 20/12/16 | Tue 20/12/16
1227 | 740171 | Core part: Introduction of new band support for 4Rx antenna ports for LTE | LTE_4Rx_AP_DL_bands-Core | 3 | Rel-14 | R4 | 2016-12-15 08:00 | 2017-06-15 17:00 | 100% | RP-170307 |  | Huawei |  | ; 21/3/17: Compl:0%->80% ; 2119/6/17: Compl:80%->100% |  | 74 | 38 |  |  | Tue 20/12/16 | Mon 19/06/17
1228 | 750058 | UE Conformance Test Aspects - 4 Rx antenna ports with CA for LTE DL | LTE_4Rx_AP_DL_CA-UEConTest | 3 | Rel-14 | R5 | 2017-03-15 08:00 | 2018-09-14 17:00 | 90% | RP-170704 |  | Ericsson |  | tested: REL-14 LTE_4Rx_AP_DL_CA-Core; 19/6/17: C 1 8/1/18: C 27/3/ ; |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1229 | 730085 | Requirements for a new UE category with single receiver based on Category 1 for LTE | LTE_UE_cat_1RX | 1 | Rel-14 | R4 | 2016-09-15 08:00 | 2018-09-14 17:00 | 92% | RP-161898 |  | Qualcomm |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
1230 | 730185 | Core part: Requirements for a new UE category with single receiver based on Category 1 for LTE | LTE_UE_cat_1RX-Core | 2 | Rel-14 | R4 | 2016-09-15 08:00 | 2017-06-15 17:00 | 100% | RP-171149 | RP-171317 | Qualcomm |  | ; 20/12/16: Compl:0%->70%; 20/12/16: CD:Thu 15/12/16->Wed 15/03/17 ; 21/3/17: Compl:70%->95% 21/3/17: CD:Wed 15/03/17->Thu 15/06/1 19/6/17: Compl:95%->100%; |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
1231 | 730285 | Perf. part: Requirements for a new UE category with single receiver based on Category 1 for LTE | LTE_UE_cat_1RX-Perf | 2 | Rel-14 | R4 | 2016-09-15 08:00 | 2017-09-15 17:00 | 100% | RP-171149 |  | Qualcomm |  | ; 20/12/16: Compl:0%->20%; 20/12/16: CD:Thu 15/06/17->Fri 15/09/17 21/3/17: Compl:20%->70% ; 21/3/17: WID: RP-162570->RP-17079119/6/17: Compl:70%->100%; |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 19/06/17
1232 | 760085 | UE Conformance Test Aspects – Requirements for a new UE category 1bis with single receiver based on category 1 for LTE | LTE_UE_cat_1RX-UEConTest | 2 | Rel-14 | R5 | 2017-06-15 08:00 | 2018-09-14 17:00 | 80% | RP-180263 |  | Qualcomm |  | ; 19/9/17: Compl:0%->5%; 8/1/18: Compl:5%->45%27/3/18: Compl:45%->70%; |  | 76 | 39 |  |  | Fri 16/06/17 | Wed 27/06/18
1233 | 730086 | Enhanced LTE WLAN Radio Level Integration with IPsec Tunnel (eLWIP) | LTE_WLAN_eLWIP | 1 | Rel-14 | R3 | 2016-09-15 08:00 | 2017-03-15 17:00 | 100% | RP-161929 |  | Nokia |  |  |  | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
1234 | 730186 | Core part: Enhanced LTE WLAN Radio Level Integration with IPsec Tunnel (eLWIP) | LTE_WLAN_eLWIP-Core | 2 | Rel-14 | R3 | 2016-09-15 08:00 | 2017-03-15 17:00 | 100% | RP-161929 | RP-170706 | Nokia |  | ; 20/12/16: Compl:0%->60% 21/3/17: Compl:60%->100% 21/3/17: Stat Rep: ->RP-170706 |  | 73 | 37 |  |  | Mon 26/09/16 | Tue 21/03/17
1235 | 710083 | LTE Measurement Gap Enhancement | LTE_meas_gap_enh | 1 | Rel-14 |  | 2016-03-15 08:00 | 2017-06-15 17:00 | 100% | RP-160678 |  | Intel |  |  |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
1236 | 710183 | Core part: LTE Measurement Gap Enhancement | LTE_meas_gap_enh-Core | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-06-15 17:00 | 100% | RP-160912 | RP-171330 | Intel |  | ; 1/7/16: Compl:0%->10%; 1/7/16: CD:Thu 15/06/17->Wed 15/03/17; 1/7/16: WID: RP-160678->RP-160912; 26/9/16: Compl:10%->25%26/9/16: R; 20/12/16: Compl:25%->60% 21/3/17: Compl:60%->95% 19/6/17: Compl:95%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 19/06/17
1237 | 710283 | Perf. part: LTE Measurement Gap Enhancement | LTE_meas_gap_enh-Perf | 2 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-06-15 17:00 | 100% | RP-160912 |  | Intel |  | 1/7/16: WID: RP-160678->RP-1609121/7/16: Release: Rel-15->Rel-14; 20/12/16: Stat Rep: -->; 20/12/16: Release: Rel-15->Rel-14 21/3/17: Compl:0%->20% 21/3/17: Release: Rel19/6/17: Compl:20%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 19/06/17
1238 | 730082 | Enhanced CRS and SU-MIMO Interference Mitigation Performance Requirements for LTE | LTE_eCRSIM_eSUMIMO | 1 | Rel-14 |  | 2016-09-15 08:00 | 2017-09-15 17:00 | 100% | RP-161877 |  | Intel |  |  | 39.747 | 73 | 37 |  |  | Mon 26/09/16 | Mon 26/09/16
1239 | 730282 | Perf. part: Enhanced CRS and SU-MIMO Interference Mitigation Performance Requirements for LTE | LTE_eCRSIM_eSUMIMO-Perf | 2 | Rel-14 | R4 | 2016-09-15 08:00 | 2017-09-15 17:00 | 100% | RP-162303 |  | Intel |  | 6/10/16: 36.176 added; 20/12/16: Compl:0%->30%21/3/17: Compl:30%->50% ; 21/3/17: Release: Rel-15->Rel-14; 19/6/17: Compl:50%->85%19/9/17: Compl:85%->100% | 36.176 | 73 | 37 |  |  | Mon 26/09/16 | Tue 19/09/17
1240 | 780051 | Miscellaneous IETF dependencies | TEI14_IETF | 1 | Rel-14 |  | 2017-03-15 08:00 | 2017-12-14 17:00 | 72% |  |  |  |  | Created upon demand of RAN5 |  | 78 | 40 |  |  | Mon 18/12/17 | NA
1241 | 780052 | (IETF) SDP Offer/Answer Clarifications for RTP/RTCP Multiplexing [RFC 5761 (was draft-ietf-avtcore-5761-update)] | TEI14_IETF | 2 | Rel-14 | CT1-IETF | 2017-03-15 08:00 | 2017-09-15 17:00 | 100% | [6 empty] | 78 | 40 |  |  | Mon 18/12/17 | NA
1242 | 780053 | (IETF) T.140 Text Conversation over Data Channels (draft-schwarz-mmusic-t140-usage-data-channel) | TEI14_IETF | 2 | Rel-14 | CT1-IETF | 2017-03-15 08:00 | 2017-12-14 17:00 | 25% | [6 empty] | 78 | 40 |  |  | Mon 18/12/17 | NA
1243 | 780054 | (IETF) BFCP floor control signalling over Data Channels (draft-schwarz-mmusic-bfcp-usage-data-channel) | TEI14_IETF | 2 | Rel-14 | CT1-IETF | 2017-03-15 08:00 | 2017-12-14 17:00 | 100% |  |  |  |  | 22/3/18: 25%->100 |  | 78 | 40 |  |  | Mon 18/12/17 | Thu 22/03/18
1244 | 620062 | Security Assurance Specification for 3GPP network products | SCAS | 1 | Rel-14 | S3 | 2013-12-09 08:00 | 2017-06-15 17:00 | 100% | SP-150292 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | Triggered by Rel-12 TR 33.805 Study on Security Assurance Methodology for 3GPP Network Elements (FS_SECAM); June2015: WID:SP-130718->SP-150292. Aug 15: TR numb added; 28/1/16: 33.926 added; 28/7/16: 33.250 added;06/10/16: moved to Rel-14 as per John/Mir; | 33.199; 33.926, 33.117; 33.250; 33.515 | 62 | 32 |  |  | Fri 22/11/13 | Mon 06/08/18
1245 | 620162 | STOPPED - TR on Pilot development of Security Assurance Specification for MME network product class | SCAS-SA3Pil_TR | 2 | Rel-14 | S3 | 2013-12-09 08:00 | 2014-12-12 17:00 | 100% | SP-130718 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | This TR collects input for the new TS 33.116. Dec.14: 55->70%. 3/3/15: 70->55%. 10/03/15: 55->75%; June2015: Compl:75%->80; 7/12/15: STOPPED AT 80% (marked as 100% here since no more work expected) | New TR 33.806 | 62 | 32 |  |  | Fri 22/11/13 | Mon 07/12/15
1246 | 620362 | TR on Security Assurance scheme for 3GPP network products | SCAS-SA3TR | 2 | Rel-14 | S3 | 2013-12-09 08:00 | 2016-12-15 17:00 | 100% | SP-150716 | - | NTT DOCOMO | Alf Zugenmaier (alf.zugenmaier@hm.edu) | This TR contains results of the second WID objective. Dec.14: 75->85%; June2015: Compl:85%->90; 7/12/15: 90%->92; 10/12/15: WID:SP-130718->SP-150716; 19/9/16: 92%->98. FCD set to 12.16 (was 03/16); 6/10/16: 33.216 added; 1/12/16: 81%->100 | New TR 33.916; 33.216 | 62 | 32 |  |  | Fri 22/11/13 | Thu 01/12/16
1247 | 620262 | Security Assurance Specification for 3GPP network product classes | SCAS-SA3 | 2 | Rel-14 | S3 | 2013-12-13 08:00 | 2017-06-15 17:00 | 100% | SP-150716 | - | China Mobile | Judy Zhu (zhuhongru@chinamobile.com) | June2015: 0%->5; 7/12/15: 5%->72.; 10/12/15: WID:SP-130718->SP-150716; 7/3/16: 72%->75; 28/7/16: 33.250 added; 19/9/16: 75%->90. FCD set to 12.16 (was 03/16). 6/3/17: moved from Rel-14.; 15/2/18: moved back to Rel-14; 6/8/18: 33.515 added; | New TS 33.116, 33.117; 33.250; 22.511; 22.512; 22.513; 22.514; 33.515 | 62 | 32 |  |  | Fri 22/11/13 | Mon 06/08/18
1248 | 680099 | (Small) Technical Enhancements and Improvements for Rel-14 | TEI14 | 1 | Rel-14 | SP,CP,RP,R4 | 2015-05-11 08:00 | 2015-06-18 17:00 | 100% | [6 empty] | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
1249 | 689999 | (Small) Test Technical Enhancements and Improvements for Rel-14 | TEI14_Test | 1 | Rel-14 | SP,CP,RP,GP | 2016-09-13 08:00 | 2018-12-20 17:00 | 100% | - |  | - | - | Created upon demand of RAN5 | - |  |  |  |  | Mon 12/01/15 | Wed 24/02/16
1250 | 709998 | Rel-14 LTE Carrier Aggregation (CA) | LTE_CA_Rel14 | 1 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | - | - | - | - | Acronym changed from "LTE_CA_Rel-13" to "LTE_CA_Rel13" |  | 58 | 30 |  |  | Fri 14/12/12 | Thu 15/01/15
1251 | 690086 | LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12 | LTE_CA_B4_B5_B12_B12 | 2 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151521 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | NA
1252 | 690186 | Core part: LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12 | LTE_CA_B4_B5_B12_B12-Core | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151521 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
1253 | 690286 | Perf. part: LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12 | LTE_CA_B4_B5_B12_B12-Perf | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151521 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
1254 | 690087 | LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12 | LTE_CA_B4_B4_B12_B12 | 2 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151522 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | NA
1255 | 690187 | Core part: LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12 | LTE_CA_B4_B4_B12_B12-Core | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151522 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
1256 | 690287 | Perf. part: LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12 | LTE_CA_B4_B4_B12_B12-Perf | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151522 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
1257 | 690088 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12 | LTE_CA_B2_B4_B12_B12 | 2 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151523 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | NA
1258 | 690188 | Core part: LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12 | LTE_CA_B2_B4_B12_B12-Core | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151523 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
1259 | 690288 | Perf. part: LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12 | LTE_CA_B2_B4_B12_B12-Perf | 3 | Rel-14 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 90% | RP-151523 | - | US Cellular |  |  |  | RP-69 | PCG-35 |  |  | Tue 29/09/15 | Fri 01/01/16
1260 | 709999 | Rel-14LTE Advanced inter-band CA | LTE_AIBCA_Rel14 | 1 | Rel-14 | R4 | 2015-12-15 08:00 | 2018-12-14 17:00 | 78% | - | - | - | - | Acronym changed from "LTE_CA_Rel-13" to "LTE_CA_Rel13" |  | 58 | 30 |  |  | Fri 14/12/12 | Thu 15/01/15
1261 | 700069 | LTE Advanced inter-band CA Rel-14 for 5DL/1UL | LTE_CA_R14_5DL1UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 95% | RP-151671 |  | Nokia Networks |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
1262 | 700169 | Core part: LTE Advanced inter-band CA Rel-14 for 5DL/1UL | LTE_CA_R14_5DL1UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 95% | RP-170143 |  | Nokia Networks |  | 28/1/16: 36.714-05-01 added; 22/3/16: Compl:0%->15%; 22/3/16: WID: RP-151671->RP-1606151/7/16: Compl:15%->40%; 26/9/16: Compl:40%->60%; 20/12/16: Compl ; 21/3/17 | 36.714-05-01 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1263 | 700269 | Perf. part: LTE Advanced inter-band CA Rel-14 for 5DL/1UL | LTE_CA_R14_5DL1UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 95% | RP-170143 |  | Nokia Networks |  | 22/3/16: WID: RP-151671->RP-1606151/7/16: WID: RP-160615->RP-16105226/9/16: WID: RP-161052->RP-161496; 20/12/16: Compl:0%->90% ; 21/3/17: Compl:90%->95%; |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1264 | 700070 | LTE Advanced inter-band CA Rel-14 for 2DL/1UL | LTE_CA_R14_2DL1UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 80% | RP-152196 |  | Qualcomm |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
1265 | 700170 | Core part: LTE Advanced inter-band CA Rel-14 for 2DL/1UL | LTE_CA_R14_2DL1UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 80% | RP-170123 |  | Qualcomm |  | 28/1/16: 36.714-02-01 added; 22/3/16: Compl:0%->20%; 22/3/16: WID: RP-152196->RP-160616; 1/7/16: Compl:20%->30%; 1/7/16: WI26/9/16: Compl:30%->50%; 20/12/16: Com 21/3/17: | 36.714-02-01 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1266 | 700270 | Perf. part: LTE Advanced inter-band CA Rel-14 for 2DL/1UL | LTE_CA_R14_2DL1UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 80% | RP-170123 |  | Qualcomm |  | 22/3/16: WID: RP-152196->RP-1606161/7/16: Compl:0%->30%1/7/16: WID: RP-160616->RP-161202; 26/9/16: Compl:30%->50% 20/12/16: Compl:50%->75% 21/3/17: Compl:75%->80%; |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1267 | 700071 | LTE Advanced inter-band CA Rel-14 for 2DL/2UL | LTE_CA_R14_2DL2UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 90% | RP-152237 |  | Huawei |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
1268 | 700171 | Core part: LTE Advanced inter-band CA Rel-14 for 2DL/2UL | LTE_CA_R14_2DL2UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 90% | RP-170312 |  | Huawei |  | 28/1/16: 36.714-02-02 added;22/3/16: Compl:0%->20%22/3/16: WID: RP-152237->RP-160192; 1/7/16: Compl:20%->40%; 26/9/16: Compl:40%->60%; 20/12/16: C ; 21/3/17: | 36.714-02-02 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1269 | 700271 | Perf. part: LTE Advanced inter-band CA Rel-14 for 2DL/2UL | LTE_CA_R14_2DL2UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 90% | RP-170312 |  | Huawei |  | ; 22/3/16: WID: RP-152237->RP-1601921/7/16: WID: RP-160192->RP-16094726/9/16: WID: RP-160947->RP-161676; 20/12/16: Compl:0%->80%; 21/3/17: Compl:80%->90 |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1270 | 700072 | LTE Advanced inter-band CA Rel-14 for 3DL/3UL | LTE_CA_R14_3DL3UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 100% | RP-152241 |  | Nokia Networks |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
1271 | 700172 | Core part: LTE Advanced inter-band CA Rel-14 for 3DL/3UL | LTE_CA_R14_3DL3UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 100% | RP-152241 |  | Nokia Networks |  | 28/1/16: 36.714-03-03 added;22/3/16: Compl:0%->1%1/7/16: Compl:1%->15%; 21/3/17: Compl:15%->100% | 36.714-03-03 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1272 | 700272 | Perf. part: LTE Advanced inter-band CA Rel-14 for 3DL/3UL | LTE_CA_R14_3DL3UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-03-15 17:00 | 100% | RP-152241 |  | Nokia Networks |  | ; 1/7/16: Compl:0%->15%21/3/17: Compl:15%->100% |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1273 | 700073 | LTE Advanced inter-band CA Rel-14 for xDL/2UL with x=3,4,5 | LTE_CA_R14_xDL2UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 48% | RP-152246 |  | LG Electronics |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
1274 | 700173 | Core part: LTE Advanced inter-band CA Rel-14 for xDL/2UL with x=3,4,5 | LTE_CA_R14_xDL2UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 95% | RP-170128 |  | LG Electronics |  | 28/1/16: 36.714-00-02 added; 22/3/16: Compl:0%->10%; 22/3/16: WID: RP-152246->RP-160148; 1/7/16: Compl:10%->40%; 26/9/16: Compl:40%->70%; 20/; 21/3/17: | 36.714-00-02 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1275 | 700273 | Perf. part: LTE Advanced inter-band CA Rel-14 for xDL/2UL with x=3,4,5 | LTE_CA_R14_xDL2UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 0% | RP-170128 |  | LG Electronics |  | 22/3/16: WID: RP-152246->RP-1601481/7/16: WID: RP-160148->RP-160748; 26/9/16: WID: RP-160748->RP-161487; 20/12/16: WID: RP-161487->RP-16203621/3/17: |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1276 | 700074 | LTE Advanced inter-band CA Rel-14 for 4DL/1UL | LTE_CA_R14_4DL1UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 95% | RP-152249 |  | Ericsson |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
1277 | 700174 | Core part: LTE Advanced inter-band CA Rel-14 for 4DL/1UL | LTE_CA_R14_4DL1UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 95% | RP-170189 |  | Ericsson |  | 28/1/16: 36.714-04-01 added;22/3/16: Compl:0%->30%22/3/16: WID: RP-152249->RP-1606141/7/16: Compl:30%->38%; 26/9/16: Compl:38%->74%; 20/12/16: Compl:74%->9521/3/1 | 36.714-04-01 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1278 | 700274 | Perf. part: LTE Advanced inter-band CA Rel-14 for 4DL/1UL | LTE_CA_R14_4DL1UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 95% | RP-170189 |  | Ericsson |  | ; 22/3/16: WID: RP-152249->RP-160614; 1/7/16: Compl:0%->38%; 1/7/16: WID: RP-160614->RP-16082126/9/16: Compl:38%->0%; 20/12/16: Compl:0%->95% ; 21/3/17: CD:Wed 1 |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1279 | 700075 | LTE Advanced intra-band CA for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R14_intra | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 82% | RP-152250 |  | Ericsson |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
1280 | 700175 | Core part: LTE Advanced intra-band CA for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R14_intra-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 82% | RP-170188 |  | Ericsson |  | 28/1/16: 36.714-00-00 added;22/3/16: Compl:0%->60%22/3/16: WID: RP-152250->RP-160613; 1/7/16: Compl:60%->50%; 1/7/16: WID: RP-160613; 26/9/16: Compl:50%->44%; 20/12/16:21/3/1 | 36.714-00-00 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1281 | 700275 | Perf. part: LTE Advanced intra-band CA for xDL/yUL including contiguous and non-contiguous spectrum | LTE_CA_R14_intra-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 82% | RP-170188 |  | Ericsson |  | ; 22/3/16: WID: RP-152250->RP-1606131/7/16: Compl:0%->50%1/7/16: WID: RP-160613->RP-16082226/9/16: WID: RP-160822->RP-161473; 20/12/16: Compl:50%->64% 21/3/17: Compl:64%-> |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1282 | 700076 | LTE Advanced inter-band CA Rel-14 for 3DL/1UL | LTE_CA_R14_3DL1UL | 2 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 90% | RP-152278 |  | Huawei |  |  |  | RP-70 | PCG-36 |  |  | Thu 07/01/16 | Tue 22/12/15
1283 | 700176 | Core part: LTE Advanced inter-band CA Rel-14 for 3DL/1UL | LTE_CA_R14_3DL1UL-Core | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 90% | RP-170309 |  | Huawei |  | 28/1/16: 36.714-03-01 added;22/3/16: Compl:0%->15%22/3/16: WID: RP-152278->RP-1605821/7/16: Compl:15%->40%1/7/1626/9/16: Compl:40%->60%; 20/12/16: Compl:60%->80 21/3/1 | 36.714-03-01 | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1284 | 700276 | Perf. part: LTE Advanced inter-band CA Rel-14 for 3DL/1UL | LTE_CA_R14_3DL1UL-Perf | 3 | Rel-14 | R4 | 2015-12-15 08:00 | 2017-06-15 17:00 | 90% | RP-170309 |  | Huawei |  | 22/3/16: WID: RP-152278->RP-160582; 1/7/16: WID: RP-160582->RP-160945; 26/9/16: WID: RP-160945->RP-161674; 20/12/16: Compl:0%->80%21/3/17: Compl:80%->90%; |  | RP-70 | PCG-36 |  |  | Fri 01/01/16 | Tue 21/03/17
1285 | 720098 | UE Conformance Test Aspects – Rel-14 CA configurations | LTE_CA_R14-UEConTest | 2 | Rel-14 | R5 | 2016-06-15 08:00 | 2018-12-14 17:00 | 20% | RP-161528 |  | Ericsson |  | testing REL-14 CA basket WIs: LTE_CA_R14_intra-Core, LTE_CA_R14_2DL1UL-Core, LTE_CA_R14_3DL1UL-Core, LTE_CA_R14_4DL1UL-Core, LTE_CA_R14_5DL1UL-Core, LTE_CA_R14_2DL2UL-Core, LTE_CA_R14_xDL2UL-Core, LTE_CA_R14_3DL3UL-Core ; |  | TSG#72 | PCG-37 |  |  | Fri 01/07/16 | Wed 27/06/18
1286 | 0 | Release 14 Studies | - | 1 | Rel-14 | SP,RP,CP,GP | 2014-09-17 08:00 | 2015-12-11 17:00 | 100% | - | - |  | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1287 | 690060 | Study on channel model for frequency spectrum above 6 GHz | FS_6GHz_CH_model | 1 | Rel-14 | R1 | 2015-09-15 08:00 | 2016-06-15 17:00 | 100% | RP-160210 |  | Samsung |  | will start only in RAN in Q4/15; 28/1/16: 38.900 added; 22/3/16: Compl:10%->20%; 22/3/16: WID: RP-151606->RP-160210; 1/7/16: Compl:20%->100%. 2/12/16: Moved to Rel-15 according JMM email to move all 38.xxx related WIDs to Rel-15; 21/3/17: Stat Rep: --> | 38.900 | 69 | 35 |  |  | Tue 29/09/15 | Tue 21/03/17
1288 | 700058 | Study on Scenarios and Requirements for Next Generation Access Technologies | FS_NG_SReq | 1 | Rel-14 | RP | 2015-12-15 08:00 | 2016-12-15 17:00 | 100% | RP-160811 |  | CMCC |  | 22/3/16: Compl:0%->80%1/7/16: WID: RP-152257->RP-160811. 18/9/16: FCD: Sept 16, 80->95%26/9/16: Compl:95%->100%; 14/12/16: FCD:09/16->12/16; 14/12/16: 100%->9820/12/16: Compl:98%->100%20/12/16: CD:Mon 12/12/16->Thu 15/12/1620/12/16: Release: Rel-15->Re | 38.xxx | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
1289 | 720086 | Study on NB-IoT RF requirement for coexistence with CDMA | FS_NB_IOT_CDMA_coex | 1 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 100% | RP-161187 |  | China Telecom |  | ; 26/9/16: Compl:0%->35%; 6/10/16: 36.752 added; 20/12/16: Compl:35%->100% | 36.752 | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
1290 | 610032 | Study on need for Multiple Access Point Names | FS_MAPN | 1 | Rel-14 | S1 | 2013-09-12 08:00 | 2015-06-19 17:00 | 100% | SP-130416 |  | Giesecke & Devrient | Ilario.macchi@gi-de.com | SP#65 moved to Rel-14. Completion 12/14=>03/15. Triggered by S1-133134 LS on GSMA Connected Living Programme Request for APN Storage in the SIM. Dec.14: 50->70%, CD: 03/15->06/15. Mar.15: 90%; June2015: Compl:90%->100 | 22.802 | 61 | 31 |  |  | Mon 26/08/13 | Mon 15/06/15
1291 | 620071 | Study on Multimedia Broadcast Supplement for Public Warning System | FS_MBSP | 1 | Rel-14 | S1 | 2013-12-11 08:00 | 2014-12-12 17:00 | 100% | SP-130599 |  | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Moved to Rel-14. TR 22.815v100 for Information. Linked to Rel-9 Feature PWS. Dec.14:70->100% | 22.815 | 62 | 32 |  |  | Tue 26/11/13 | Wed 03/12/14
1292 | 630018 | Study on service aspects for dealing with User Control over spoofed calls | FS_UC_SPOOF | 1 | Rel-14 | S1 | 2014-03-07 08:00 | 2015-03-20 17:00 | 100% | SP-140074 |  | Sprint | Gregory.schumacher@sprint.com | SP#65 moved to Rel-14. Linked to SA3 Rel-11 TR 33.838 PUCI and Rel-12 ongoing study TR 33.831 (FS_SPOOF). Dec.14: 70->90, CD: 12/14->03/15. Mar.15: 100% | 22.898 | 63 | 32 |  |  | Wed 05/02/14 | Wed 04/03/15
1293 | 640060 | Study on User Location Reporting Support enhancements | FS_eULRS | 1 | Rel-14 | S1 | 2014-06-19 08:00 | 2015-06-17 17:00 | 100% | SP-140402 |  | China Unicom | Zhuoyun Zhang ( zhangzy910@chinaunicom.cn) | SP#65 moved to Rel-14. Linked to Rel-12 SA2 TR 23.843 Study on Core Network Overload solutions (FS_CNO) and Rel-13 Feature Service Exposure and Enablement Support (SEES). Dec.14: 30->70%. Mar.15: 90%; June2015: Compl:90%->100 | 22.899 | 64 | 33 |  |  | Thu 29/05/14 | Mon 15/06/15
1294 | 640061 | Study on Control of Applications when Third party Servers encounter difficulties | FS_CATS | 1 | Rel-14 | S1 | 2014-06-19 08:00 | 2015-06-15 17:00 | 100% | SP-140758 |  | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | SP#65 completion 12/14=>03/15. Moved to Rel-14. Linked to Rel-13 Feature SEES and Rel-13 TR 22.806 (FS_ACDC). Dec.14: 30->60%, WID SP-140246->SP-140758, CD: 12/14->03/15. Mar.15: CD: 03/13->06/15. 60->90%; June2015: Compl:90%->100 | 22.818 | 64 | 33 |  |  | Thu 29/05/14 | Mon 15/06/15
1295 | 670011 | Study on Paging Policy Enhancements and Procedure Optimizations in LTE | FS_PPEPO_LTE | 1 | Rel-14 | S1 | 2015-04-14 08:00 | 2015-12-15 17:00 | 100% | SP-150053 |  | Zhuoyun Zhang (China Unicom) | zhangzy910@chinaunicom.cn | 1/4/15:TR number added; June2015: Compl:0%->40; 07/09/15: 40%->60; 7/12/15: 60%->100 | New TR 22.838 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
1296 | 670041 | Study on Latency reduction techniques for LTE | FS_LTE_LATRED | 1 | Rel-14 | R2 | 2015-03-16 08:00 | 2016-06-15 17:00 | 100% | RP-150465 |  | Ericsson |  | 03/07/15: Compl:0%->10% 03/07/15: Stat Rep: -->RP-150780 03/07/15: Release: Rel-13->Rel-14 29/09/15: Compl:10%->25% 29/09/15: Stat Rep: RP-150780->RP-151286 22/3/16: Compl:50%->60%; | 36.881 | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/07/16
1297 | 680057 | Study on High Power LTE UE for Band 41 | FS_LTE_B41_HPUE | 1 | Rel-14 | R4 | 2015-06-15 08:00 | 2016-06-15 17:00 | 100% | RP-160092 |  | Sprint |  | 7/9/15: TR added 29/09/15: Compl:0%->1% 29/09/15: Stat Rep: -->RP-151436 ; 22/3/16: Compl:10%->40%; 22/3/16: WID: RP-151104->RP-1600921/7/16: Compl | 36.886 | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/07/16
1298 | 680049 | Study on Media and Quality Aspects of SRVCC Enhancements | FS_SETA_S4 | 1 | Rel-14 | S4 | 2015-06-18 08:00 | 2016-03-11 17:00 | 100% | SP-150361 |  | Frédéric Gabin, Ericsson LM | frederic . gabin @ ericsson . com | Aug2015: 0%->25; 07/09/15: 25%->30; 7/12/15: 30%->80, FCD: 12/15->03/16, MOVED TO REL-14; 7/3/16: 80%->100 | New TR 26.916, TS 26.114 | 68 | 35 |  |  | Thu 18/06/15 | Mon 07/03/16
1299 | 720085 | Deleted - Study on SON for eCoMP for LTE | delFS_LTE_SON_eCOMP | 1 | Rel-14 | R3 | 2016-06-14 08:00 | 2016-06-16 17:00 | 100% | RP-161181 |  | Nokia |  | 26/9/16: Compl:0%->10%. 1/12/16: Deleted: 720085 was allocated twice: to FS_LTE_SON-ECOMP (now in 720063) and to ROBVOLTE (now in 720301) | 23.228, 23.237 | 72 | 37 |  |  | Mon 07/12/15 | Mon 26/09/16
1300 | 700036 | Study on UICC power optimization for MTC | FS_UICC_MTC_OPT | 1 | Rel-14 | C6 | 2016-06-15 08:00 | 2016-12-15 17:00 | 100% | CP-150875 |  | Berionne, Michele | micheleb [at] qti [dot] qualcomm [dot] com | 7/3/16: 0%->100; 5/6/17: 71%->100 | 31.970 | 70 | 36 |  |  | Mon 07/12/15 | Mon 05/06/17
1301 | 710013 | Study on Server and Network Assisted DASH for 3GPP | FS_SAND | 1 | Rel-14 | S4 | 2016-03-01 08:00 | 2016-12-15 17:00 | 100% | SP-160083 |  | Ozgur Oyman, Intel | ozgur.oyman@intel.com | 11/6/16: 0%->10; 19/9/16: 10%->60; 1/12/16: 60%->100 | TR26.957 | 71 | 36 |  |  | Tue 01/03/16 | Thu 01/12/16
1302 | 710016 | Study on MBMS usage for mission critical communication services | FS_MBMS_MCservices | 1 | Rel-14 | C1 | 2016-03-01 08:00 | 2016-03-01 08:00 | 99% | SP-160728 |  | Magnus Tränk, Ericsson LM | magnus.trank@ericsson.com | 11/6/16: 0%->35. Name corrected; 19/9/16: WID:SP-160201->SP-160525; FCD: 09/16->12/16; 19/9/16: 35%->60; 23/9/16: WID:SP-160525->SP-160728; 1/12/16: 60%->95; 3/3/17: 95%->100 | TR 23.780 | 71 | 36 |  |  | Tue 01/03/16 | Fri 03/03/17
1303 | 710057 | Study on enhancement of VoLTE | FS_LTE_eVoLTE | 1 | Rel-14 | R2 | 2016-03-15 08:00 | 2016-09-15 17:00 | 100% | RP-160902 | - | CMCC |  | 1/7/16: Compl:0%->75%1/7/16: WI; 28/7/16: 36.750 added; 26/9/16: Compl:75%->100% | 36.750 | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
1304 | 710058 | Study on HSPA and LTE Joint Operation | FS_UTRA_LTE_JOP | 1 | Rel-14 | R3 | 2016-03-15 08:00 | 2016-12-15 17:00 | 100% | RP-160571 |  | China Unicom |  | ; 1/7/16: Compl:0%->30%; 26/9/16: Compl:30%->80%; 20/12/16: Compl:80%->100%; | New 37.805 | 71 | 36 |  |  | Tue 22/03/16 | Tue 20/12/16
1305 | 710059 | Study on LTE Advanced CA of Band 3 and Band 39 | FS_LTE_CA_B3_B39 | 1 | Rel-14 | R4 | 2016-03-15 08:00 | 2017-03-15 17:00 | 100% | RP-161704 |  | ZTE |  | intention to capture results in existing TR 36.714-02-01 ; 1/7/16: Compl:0%->30%; 26/9/16: Compl:30%->50%; 20/12/16: Compl ; 21/3/17: Compl:8 |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
1306 | 710060 | Study on Context Aware Service Delivery in RAN for LTE | FS_LTE_context | 1 | Rel-14 | R3 | 2016-03-15 08:00 | 2017-03-15 17:00 | 100% | RP-160906 |  | CMCC |  | 1/7/16: Compl:0%->25%1/26/9/16: Compl:25%->40%; 20/12/16: Compl:40%->70% ; 21/3/17: Compl:70%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
1307 | 710061 | Study on further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE | FS_feCOMP_LTE | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-03-15 17:00 | 100% | RP-160954 |  | Intel |  | ; 1/7/16: Compl:0%->15%; 26/9/16: Compl:15%->30%; 20/12/16: Compl:30%->80%21/3/17: Compl:80%->100% |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
1308 | 670015 | Study on Determination of Completeness of Charging Information in IMS | FS_DCCHII | 1 | Rel-14 | S5 | 2015-03-05 08:00 | 2016-03-11 17:00 | 100% | SP-150106 |  | Jesske, Roland | r.jesske@telekom.de | 11/03/15: WID changed from FS_DCCII to FS_DCCHII as per SA5 chair request; June2015: Compl:0%->7; 07/09/15: 7%->15; 7/12/15: 15%->60, FCD: 09/15->03/16; 7/3/16: 60%->100. 22/3/16: Rel-13->Rel-14 | 32.xyz | 67 | 34 |  |  | Thu 05/03/15 | Tue 22/03/16
1309 | 660058 | Study on Interactivity Support for 3GPP-based Streaming and Download Services | FS_IS3 | 1 | Rel-14 | S4 | 2014-12-12 08:00 | 2017-03-10 17:00 | 100% | SP-140742 |  | Lo, Charles, Qualcomm | clo@qti.qualcomm.com | TR number added. Mar. 15: 0->5%; June2015: Compl:5%->10; Aug2015: 10%->15; 07/09/15: 15%->30, FCD: 12/15->03/16; 7/3/16: 30%->40. 15/4/16: moved from Rel-13. FCD: 11/3/16->23/9/16; 11/6/16: 40%->50; 19/9/16: 50%->70, FCD:09/16->12/16; 1/12/16: 70%->80; | 26.953 | 66 | 34 |  |  | Fri 12/12/14 | Mon 06/03/17
1310 | 720026 | Study on MBMS usage and codecs for MCPTT call and MC Video Service | FS_MCP_V | 1 | Rel-14 | S4 | 2016-06-13 08:00 | 2017-03-15 17:00 | 100% | SP-160274 |  | Zhiming Li, Huawei | lizhiming@huawei.com | 28/7/16: 26.880 added; 19/9/16: 0%->30, FCD: 12/16->03/17; 1/12/16: 30%->60; 6/3/17: 60%->100 | 26.880 | 72 | 37 |  |  | Sat 11/06/16 | Mon 06/03/17
1311 | 720027 | Study on MBMS Extensions for Provisioning and Content Ingestion | FS_xMBMS | 1 | Rel-14 | S4 | 2016-06-13 08:00 | 2017-03-10 17:00 | 100% | SP-160275 |  | Kyungmo Park, sk telecom | kyungmo.park@sk.com | 28/7/16: 26.981 added; 19/9/16: 0%->30; 1/12/16: 30%->50; 1/12/16: FCD:12/16->03/17; 6/3/17: 50%->100 | TR 26.981 | 72 | 37 |  |  | Sat 11/06/16 | Mon 06/03/17
1312 | 720088 | Study on global application of LTE Band 11 and of LTE Band 21 UEs | FS_LTE_B11_B21_global | 1 | Rel-14 | R4 | 2016-06-15 08:00 | 2016-12-15 17:00 | 100% | RP-161220 |  | SoftBank |  | 26/9/16: Compl:0%->30%; 6/10/16: 36.745 added; 20/12/16: Compl:30%->100% | 36.745 | 72 | 37 |  |  | Fri 01/07/16 | Tue 20/12/16
1313 | 720089 | Study on Downlink MIMO for GERAN | FS_DOMIMO_RAN6 | 1 | Rel-14 | R6 | 2016-06-15 08:00 | 2016-09-15 17:00 | 100% | RP-161261 |  | Nokia, Alcatel-Lucent Shanghai Bell |  | continuation of GERAN SI UID 590034, DOMIMO under RAN626/9/16: Compl:0%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 26/09/16
1314 | 700018 | Release 14 studies on 5G MObile Network for Advanced communications |  | 1 | Rel-14 | S1 | 2015-02-02 08:00 | 2016-12-15 17:00 | 100% | SP-150142 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com | 11/3: WID: SP-150050->150142; June2015: Compl:0%->20; 07/09/15: 20%->60. 07/12/15: Created by MCC as BB to dissociate SA1 versus SA2 aspects | New TR 22.891 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/09/15
1315 | 700022 | Study on Stage 1 for New Services and Markets Technology Enablers | FS_SMARTER | 1 | Rel-14 | S1 | 2015-02-02 08:00 | 2016-06-10 17:00 | 100% | SP-150142 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com |  | New TR 22.891 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/09/15
1316 | 670008 | General aspects of FS_SMARTER SA1 | FS_SMARTER | 2 | Rel-14 | S1 | 2015-02-02 08:00 | 2016-02-12 17:00 | 100% | SP-150142 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com | 7/12/15: 60%->85; 2/3/16: 85%->95; 7/6/17: 95%->100 | New TR 22.891 | 67 | 34 |  |  | Wed 04/03/15 | Wed 07/06/17
1317 | 700023 | FS_SMARTER – massive Internet of Things | FS_SMARTER-mIoT | 2 | Rel-14 | S1 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150817 |  | Adrian Neal (Vodafone) | adrian.neal@vodafone.com | 2/3/16: 35%->65; 9/6/16: 65%->100 | New TR 22.861 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1318 | 700024 | FS_SMARTER – Critical Communications | FS_SMARTER-CRIC | 2 | Rel-14 | S1 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150818 |  | Kanerva, Mikko | mikko.kanerva@nokia.com | 2/3/16: 15%->60; 9/6/16: 60%->95; 7/6/17: 95%->100 | New TR 22.862 | 70 | 36 |  |  | Mon 07/12/15 | Wed 07/06/17
1319 | 700025 | FS_SMARTER – enhanced Mobile Broadband | FS_SMARTER-eMBB | 2 | Rel-14 | S1 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150819 |  | Laurence Meriau | laurence.meriau@huawei.com | 2/3/16: 40%->75; 9/6/16: 75%->100 | New TR 22.863 | 70 | 36 |  |  | Mon 07/12/15 | Thu 09/06/16
1320 | 700026 | FS_SMARTER – Network Operation | FS_SMARTER-NEO | 2 | Rel-14 | S1 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150820 |  | Lu Lu | lulu@chinamobile.com | 2/3/16: 30%->60; 19/9/16: 60%->100 | New TR 22.864 | 70 | 36 |  |  | Mon 07/12/15 | Mon 19/09/16
1321 | 700017 | SA2 aspects on Study on Architecture and Security for next Generation System | FS_NextGen | 1 | Rel-14 | S2 | 2015-12-07 08:00 | 2016-12-15 17:00 | 100% | SP-160727 |  | suntao@chinamobile.com, devaki.chandramouli@nokia.com | suntao@chinamobile.com, devaki.chandramouli@nokia.com | 28/1/16: 23.799 added; Acronym corrected ("NexGen"->"NextGen"); 7/3/16: 5%->15; 10/3/16: WID:SP-150853->SP-160200. Name changed from "Study on Architecture for next Generation System"; 9/6/16: 15%->35; 19/9/16: 35%->64; 22/9/16: WID:SP-160227->SP-16072 | TR 23.799 | 70 | 36 |  |  | Mon 07/12/15 | Thu 01/12/16
1322 | 710062 | Study on New Radio (NR) Access Technology | FS_NR_newRAT | 1 | Rel-14 | R1 | 2016-03-15 08:00 | 2017-03-15 17:00 | 100% | RP-170379 |  | NTT DOCOMO |  | includes RAN TR 38.801; 1/7/16: Compl:0%->10%; 1/7/16: CD:Thu 15/06/17->Wed 15/03/17; 1/7/16: WID: RP-160671->RP-161214; 1/7/16: Release: Rel-15->Rel-14; 28/7/16: 38.802 added; 26/9/16: Compl:10%->20%; 26/9/16: WID: RP-161214->RP-161596. 2/12/16: Moved | TR 38.801, TR 38.912; 38.802; 38.901; 38.805 | 71 | 36 |  |  | Tue 22/03/16 | Tue 21/03/17
1323 | 0 | Release 13 Features | - | 1 | Rel-13 | SP,RP,CP,GP | 2013-12-11 08:00 | 2014-11-25 10:00 | 100% | - | - |  |  | - | - |  |  |  |  | Mon 04/03/13 | Mon 04/03/13
1324 | 620064 | Mission Critical Push To Talk over LTE (MCPTT) | MCPTT | 1 | Rel-13 |  | 2013-12-11 08:00 | 2018-06-15 17:00 | 96% | SP-150356 | - | NIST | david.cypher@nist.gov | SP#65 updated WID SP-140276=>SP-140435. Mar 15: WID: SP-140879->SP-150164. 4/15: S4 added. 6/15: WID updated | Stage 1/2; | 62 | 32 |  |  | Tue 26/11/13 | Thu 28/07/16
1325 | 640142 | Study on Application Architecture to support MCPTT | MCPTT | 2 | Rel-13 | S6 | 2014-06-23 08:00 | 2015-09-16 17:00 | 100% | SP-150356 | - | Yannick Lair | yannick.lair@lge.com | SP#65 completion 12/14=>06/15. Updated WID SP-140276=>SP-140435. Dec.14: 2->20%. Mar 15: WID: SP-140879->SP-150095. Mar15: 30%. Transferred to SA6. June 15: FCD shifted to Sept,WID updated; June2015: Compl:24%->50; June2015: Compl:50%->70. 3/8/15: Rapp | New TR 23.779 | 64 | 33 |  |  | Wed 04/06/14 | Mon 07/09/15
1326 | 670030 | SA2 Study on Architecture Enhancements at the EPS and IMS Level to Support MCPTT | MCPTT | 2 | Rel-13 | S2 | 2015-03-13 08:00 | 2015-06-17 17:00 | 100% | SP-150356 |  | Randy Bloomfield (randy@its.bldrdoc.gov) | Randy Bloomfield (randy@its.bldrdoc.gov) | Mar 2015: WID: SP-140879->SP-150164.; June2015: Compl:0%->30, WID updated; 07/09/15: 30%->100, "To be confirmed" deleted, since SA2 has completed it. |  | 67 | 34 |  |  | Fri 13/03/15 | Mon 07/09/15
1327 | 670032 | Study on Security Enhancements for MCPTT | MCPTT | 2 | Rel-13 | S3 | 2015-03-13 08:00 | 2016-03-11 17:00 | 100% | SP-150356 |  | Peter Haigh (peter.haigh at cesg.gsi.gov.uk) | Peter Haigh (peter.haigh at cesg.gsi.gov.uk) | Mar 2015: WID: SP-140879->SP-150164. Name clarified.6/15: WID updated; 7/12/15: 0%->75; 10/12/15: FCD->March, ES in SP-150729; 7/3/16: 75%->80; 28/7/16: 33.280 added; 28/7/16: 39.880 added; 1/12/16: 80%->100 | 33.879; 33.280; 39.880 | 67 | 34 |  |  | Fri 13/03/15 | Thu 01/12/16
1328 | 670022 | Study on media, codecs and MBMS enhancements for MCPTT | MCPTT | 2 | Rel-13 | S4 | 2014-12-12 08:00 | 2016-03-11 17:00 | 85% | SP-150356 |  | Zhiming Li (lizhiming@huawei.com) | Zhiming Li (lizhiming@huawei.com) | Mar 2015: WID: SP-140879->SP-150164. Name clarified. 5/5/15: TR number added; June2015: Compl:0%->5, WID updated; Aug2015: 5%->15; 07/09/15: 15%->40; 7/12/15: 40%->80, FCD: 12/15->03/16; 7/3/16: 80%->85 | New TR 26.879 | 67 | 34 |  |  | Thu 05/03/15 | Mon 07/03/16
1329 | 620164 | Stage 1 for MCPTT | MCPTT | 2 | Rel-13 | S1 | 2013-12-11 08:00 | 2014-12-12 17:00 | 100% | SP-150356 | SP-140502 | NIST | david.cypher@nist.gov | SP#65 completion 09/14=>12/14. Exception in SP-140502. TS 22.179v100 for Information. Completed. Mar 15: WID: SP-140879->SP-150164. 6/15: WID updated | New TS 22.179 | 62 | 32 |  |  | Tue 26/11/13 | Thu 18/06/15
1330 | 640143 | Functional architecture and information flows to support MCPTT | MCPTT | 2 | Rel-13 | S6 | 2015-06-18 08:00 | 2015-12-11 17:00 | 100% | SP-150356 | - | Yannick Lair | yannick.lair@lge.com | June2015: added as per SP-150356; June2015: Compl:0%->15. 31 July: Rapporteur corrected. 3/8/15: name aligned to the WID; 07/09/15: 15%->50; 07/09/15: 50%->85. 15/09/15: FCD: 09/15->12/15; 7/3/16: 85%->100 | New TS 23.179 | 64 | 33 |  |  | Wed 04/06/14 | Mon 07/03/16
1331 | 660053 | Security of MCPTT | MCPTT | 2 | Rel-13 | S3 | 2014-12-12 08:00 | 2016-03-11 17:00 | 100% | SP-150356 |  | Peter Haigh (peter.haigh at cesg.gsi.gov.uk) | Peter Haigh (peter.haigh at cesg.gsi.gov.uk) | Mar 2015: WID: SP-140879->SP-150164. Name clarified. FCD: 03/2016->12/2015; June2015: Compl:5%->15, WID updated. 7/9/15: TS number added; 7/12/15: 15%->60. FCD -> 03/16, ES in SP-150729; 7/3/16: 60%->85; 1/12/16: 85%->98; 6/3/17: 98%->100 | TS 33.179 | 66 | 34 |  |  | Fri 12/12/14 | Mon 06/03/17
1332 | 670023 | MCPTT Codecs and media handling | MCPTT | 2 | Rel-13 | S4 | 2015-03-05 08:00 | 2016-03-11 17:00 | 85% | SP-150356 |  | Zhiming Li (lizhiming@huawei.com) | Zhiming Li (lizhiming@huawei.com) | Mar 2015: WID: SP-140879->SP-150164. Name clarified. FCD: 03/2016->12/2015; June2015: Compl:0%->5, WID updated; Aug2015: 5%->15; 07/09/15: 15%->40. ES in SP-150663; 7/3/16: 40%->85 | 26.346, new TS 26.179 | 67 | 34 |  |  | Thu 05/03/15 | Mon 07/03/16
1333 | 690011 | MCPTT protocol aspects | MCPTT-CT | 2 | Rel-13 | ct | 2015-09-07 08:00 | 2016-06-30 17:00 | 96% | CP-150793 |  | Keith Drage, Alcatel-Lucent |  | 7/12/15: WID:CP-150587->CP-150793; 28/1/16: 24.384 added; |  | 69 | 35 |  |  | Mon 07/09/15 | Thu 28/01/16
1334 | 690017 | CT1 aspects for MCPTT protocol aspects | MCPTT-CT | 3 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | 7/12/15: WID:CP-150587->CP-150793; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 24.379, 24.380 24.38, 24.382, 24.383, 24.384, 24.229 | 69 | 35 |  |  | Mon 07/09/15 | Mon 05/12/16
1335 | 690096 | Call Control – On Network | MCPTT-CT | 4 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties; 7/12/15: 0%->50; 7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721; 7/3/16: 50%->100; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 24.379 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
1336 | 690097 | Call Control – Off Network | MCPTT-CT | 4 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties; 7/12/15: 0%->75; 7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721; 7/3/16: 75%->100; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 24.379 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
1337 | 690098 | Floor Control – On Network | MCPTT-CT | 4 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties; 7/12/15: 0%->80; 7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721; 7/3/16: 80%->100; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 24.380 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
1338 | 690099 | Floor Control – Off Network | MCPTT-CT | 4 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties; 7/12/15: 0%->85; 7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721; 7/3/16: 85%->100; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 24.380 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
1339 | 691000 | Broadcast – Call Control and Floor Control | MCPTT-CT | 4 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties; 7/12/15: 0%->50; 7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721; 7/3/16: 50%->100; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 24.379, 24.380 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
1340 | 691001 | Group management | MCPTT-CT | 4 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties; 7/12/15: 0%->75; 7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721; 7/3/16: 75%->100; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 24.381 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
1341 | 691002 | Identity management | MCPTT-CT | 4 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties; 7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721; 7/3/16: 0%->100; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 24.382 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
1342 | 691003 | Management Object | MCPTT-CT | 4 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Proposed by Atle after some talks with several interested parties; 7/12/15: 0%->10; 7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721; 7/3/16: 10%->100. Name changed from "Configuration management"; 7/3/16: WID:CP-150863->CP-160160; 5/12/1 | 24.383 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/12/16
1343 | 710033 | Configuration management | MCPTT-CT | 4 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Samsung, Ricky Kaura | ricky.kaura@samsung.com | Introduced from CT1 WP update in 03/16; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 24.384 | 71 | 36 |  |  | Mon 07/03/16 | Mon 05/12/16
1344 | 690028 | CT3 aspects for MCPTT protocol aspects | MCPTT-CT | 3 | Rel-13 | C3 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Alcatel-Lucent, Keith Drage | keith.drage@alcatel-lucent.com | 7/12/15: 0%->70; 7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150643; 7/3/16: 70%->100; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 29.165 | 69 | 35 |  |  | Mon 07/09/15 | Mon 05/12/16
1345 | 690018 | CT4 aspects for MCPTT protocol aspects | MCPTT-CT | 3 | Rel-13 | C4 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Alcatel-Lucent, Keith Drage | keith.drage@alcatel-lucent.com | 7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150864; 7/3/16: 0%->100; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 23.003, 23.008, 29.283 | 69 | 35 |  |  | Mon 07/09/15 | Mon 05/12/16
1346 | 700049 | CT6 aspects for MCPTT protocol aspects | MCPTT-CT | 3 | Rel-13 | C6 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-160817 |  | Alcatel-Lucent, Keith Drage | keith.drage@alcatel-lucent.com | 7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150866; 7/3/16: 0%->100; 7/3/16: WID:CP-150863->CP-160160; 5/12/16: WID:CP-160160->CP-160817 | 31.102, 31.103 | 70 | 36 |  |  | Mon 07/09/15 | Mon 05/12/16
1347 | 710034 | (IETF) IANA Registration of New SIP Resource- Priority Namespace for MCPTT | MCPTT-CT | 3 | Rel-13 | C1-IETF | 2016-02-10 08:00 | 2016-06-30 17:00 | 25% | CP-160817 |  | Ericsson | christer.holmberg@ericsson.com | 5/12/16: WID:CP-160160->CP-160817 | draft-holmberg-dispatch-mcptt-rp-namespace | 71 | 36 |  |  | Mon 07/03/16 | Mon 05/12/16
1348 | 690019 | IMS Profile to support MCPTT | MCPTT-Prof | 2 | Rel-13 | C1 | 2015-09-14 08:00 | 2016-03-11 17:00 | 100% | CP-150794 |  | Huawei, PATEL Milan | Milan.Patel@huawei.com | 12/15: TR # added; 7/12/15: 0%->60; 7/12/15: WID:CP-150500->CP-150794. FCD -> 03/16, ES in CP-150722; 7/3/16: 60%->100 | 24.980 | 69 | 35 |  |  | Wed 09/09/15 | Mon 07/03/16
1349 | 740070 | UE Conformance Test Aspects - Support for Mission Critical Push To Talk over LTE (MCPTT) | MCPTT-ConTest | 2 | Rel-13 | R5 | 2016-12-15 08:00 | 2018-06-15 17:00 | 100% | RP-180132 |  | US Department of Commerce |  | 6/1/17: acronym changed from "MCPTT-UEConTest" ; 21/3/17: Compl:0%->5%; 21/3/17: 36.579-5 added; | 36.579-5 | 74 | 38 |  |  | Tue 20/12/16 | Wed 27/06/18
1350 | 640062 | Deleted: SA2 aspects for MCPTT | MCPTT | 2 | Rel-13 | S2 | 2015-03-13 08:00 | 2015-03-13 17:00 | 100% | SP-150356 | - | Randy Bloomfield (randy@its.bldrdoc.gov) | Randy Bloomfield (randy@its.bldrdoc.gov) | Mar 2015: transferred to SA6. Was 06/14 to 06/15. 6/15: WID updated | New TS 23.179 | 64 | 33 | SP-69 |  | Wed 04/06/14 | Thu 18/06/15
1351 | 670031 | Deleted (duplicated): Application Architecture to support MCPTT | MCPTT | 2 | Rel-13 | S6 | 2015-03-13 08:00 | 2015-03-13 08:00 | 100% | SP-150356 |  | U.S. Department of Commerce | Randy Bloomfield (randy@its.bldrdoc.gov) | Mar 2015: WID: SP-140879->SP-150164. Name clarified.6/15: WID updated. 7/15: removed since duplicates 640143 and 660054 (only 640143 is kept) |  | 67 | 34 | SP-69 |  | Fri 13/03/15 | Fri 31/07/15
1352 | 660054 | Deleted (duplicated): SA6 aspects for MCPTT | MCPTT | 2 | Rel-13 | S6 | 2014-12-12 08:00 | 2015-12-11 17:00 | 100% | SP-150356 |  | David Cypher (david.cypher at nist.gov) | David Cypher (david.cypher at nist.gov) | Mar 2015: WID: SP-140879->SP-150164. Name clarified. 6/15: WID updated. 31 July: deleted since duplicates 640143 and 670031 (only 640143 is kept) |  | 66 | 34 | SP-69 |  | Fri 12/12/14 | Thu 18/06/15
1353 | 670024 | MBMS Extensions and Profiling | MEPRO | 1 | Rel-13 | S4 | 2015-03-05 08:00 | 2015-12-11 17:00 | 100% | SP-150439 |  | Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson | i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com | 1/4/15: TS number added; 14/09/15: WID:SP-150099->SP-150439 | 26.346, new TR 26.852 | 67 | 34 |  |  | Thu 05/03/15 | Mon 14/09/15
1354 | 670090 | TR on Profiling and Extensions of MBMS | MEPRO | 2 | Rel-13 | S4 | 2015-03-05 08:00 | 2015-12-11 17:00 | 100% | SP-150439 |  | Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson | i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com | 8/4/15: line added; June2015: Compl:0%->10; Aug2015: 10%->15; 07/09/15: 15%->40; 14/09/15: WID:SP-150099->SP-150439; 7/12/15: 40%->100 | new TR 26.852 | 67 | 34 |  |  | Wed 08/04/15 | Mon 07/12/15
1355 | 670091 | Specification of MBMS Extensions and Profiling | MEPRO | 2 | Rel-13 | S4 | 2015-03-05 08:00 | 2015-12-11 17:00 | 100% | SP-150439 |  | Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson | i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com | 8/4/15: line added; June2015: Compl:0%->10; Aug2015: 10%->15; 07/09/15: 15%->40; 14/09/15: WID:SP-150099->SP-150439; 7/12/15: 40%->100 | 26.346 | 67 | 34 |  |  | Wed 08/04/15 | Mon 07/12/15
1356 | 630015 | Isolated E-UTRAN Operation for Public Safety | IOPS | 1 | Rel-13 | S1 | 2014-03-07 08:00 | 2016-03-11 17:00 | 100% | SP-150463 | S1-143304 | General Dynamics | paul.piggin@gd-broadband.com | SP#65 completed. TS 22.346v100 for 1-step Approval. Triggered by Rel-13 TR 22.897 (FS_IOPS); 14/09/15: WID:SP 150358->SP-150463 | New TS 22.346 | 63 | 32 |  |  | Wed 05/02/14 | Mon 14/09/15
1357 | 680047 | Stage 1 fo Isolated E-UTRAN Operation for Public Safety | IOPS | 2 | Rel-13 | S1 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-150463 | S1-143304 | General Dynamics | paul.piggin@gd-broadband.com | SP#65 completed. TS 22.346v100 for 1-step Approval. Triggered by Rel-13 TR 22.897 (FS_IOPS); 14/09/15: WID:SP 150358->SP-150463 | New TS 22.346 | 63 | 32 |  |  | Wed 05/02/14 | Mon 14/09/15
1358 | 680048 | Stage 2 for Isolated E-UTRAN Operation for Public Safety | IOPS | 2 | Rel-13 | S2 | 2015-06-18 08:00 | 2015-12-30 17:00 | 100% | SP-150463 |  | Phil Young | phil.young@gd-broadband.com | 07/09/15: 0%->100; 14/09/15: WID:SP 150358->SP-150463 | 23.401 | 63 | 32 |  |  | Wed 05/02/14 | Mon 14/09/15
1359 | 690047 | Security aspects for Isolated E-UTRAN Operation for Public Safety | IOPS | 2 | Rel-13 | S3 | 2015-09-16 08:00 | 2015-12-30 17:00 | 100% | SP-150463 |  | General Dynamics | paul.piggin@gd-ms.uk | 07/09/15: 0%->100; 11/12/15: 0%->100 | TS 33.401 | 63 | 32 |  |  | Wed 05/02/14 | Fri 11/12/15
1360 | 700037 | CT aspects for IOPS | IOPS-CT | 2 | Rel-13 | C6 | 2015-11-02 08:00 | 2016-03-11 17:00 | 100% | CP-150876 |  | Heiko Kruse, Morpho Cards GmbH | heiko.kruse@mrpho.com |  |  | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/12/15
1361 | 700038 | CT6 aspects for IOPS | IOPS-CT | 3 | Rel-13 | C6 | 2015-11-02 08:00 | 2016-03-11 17:00 | 100% | CP-150876 |  | Heiko Kruse, Morpho Cards GmbH | heiko.kruse@mrpho.com | ES in CP-150837; 7/3/16: 0%->100 | 31.102 | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/03/16
1362 | 640042 | Service Requirements Maintenance for Group Communication System Enablers for LTE | SRM_GCSE_LTE | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-17 17:00 | 100% | SP-140228 | S1-143307 | Nokia Networks | Juergen.Merkel@nsn.com | SP#65 completed. Some Rel-12 service reqs have no Stage 2/3 implementation | 22.468 | 64 | 33 |  |  | Tue 27/05/14 | Wed 03/09/14
1363 | 650018 | Enhanced Calling Information Presentation | ECIP | 1 | Rel-13 | S1 | 2014-09-15 08:00 | 2015-12-16 17:00 | 100% | SP-140513 | S1-143311 | China Mobile | LI Xiaofan (lixiaofan@chinamobile.com | SP#65 approved WID & completed. Triggered by Rel-13 TR 22.810. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067. 31/07/15: 100% | 22.182 (CAT), 22.183 (CRS) | 62 | 32 |  |  | Tue 26/11/13 | Fri 31/07/15
1364 | 650019 | Flexible Mobile Service Steering | FMSS | 1 | Rel-13 | S1,S2 | 2014-09-15 08:00 | 2016-03-11 17:00 | 100% | SP-140638 | S1-143310 | China Mobile | Lu Lu (lulu@chinamobile.com) | SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS) | 22.101 | 65 | 33 |  |  | Tue 26/11/13 | Thu 28/08/14
1365 | 650055 | Stage 1 for Flexible Mobile Service Steering | FMSS-ST1 | 2 | Rel-13 | S1 | 2014-09-15 08:00 | 2014-09-17 17:00 | 100% | SP-140638 | S1-143310 | China Mobile | Lu Lu (lulu@chinamobile.com) | SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS). Dec.14: moved from Feature to S1 BB | 22.101 | 65 | 33 |  |  | Tue 26/11/13 | Wed 03/12/14
1366 | 660002 | Flexible Mobile Service Steering TR Phase | FMSS-SA2TR | 2 | Rel-13 | S2 | 2014-12-12 08:00 | 2015-06-17 17:00 | 100% | SP-140703 |  | Lu Lu, China Mobile | lulu@chinamobile.com | 3/3: TR number added.Mar15: 15->20%; June2015: Compl:20%->85; 07/09/15: 85%->100 | 23.718 | 66 | 34 |  |  | Wed 03/12/14 | Mon 07/09/15
1367 | 660003 | Flexible Mobile Service Steering - Stage 2 | FMSS-SA2 | 2 | Rel-13 | S2 | 2014-12-12 08:00 | 2015-06-17 17:00 | 100% | SP-140703 |  | Lu Lu, China Mobile | lulu@chinamobile.com | 07/09/15: 0%->90; 07/09/15: 90%->100 |  | 66 | 34 |  |  | Wed 03/12/14 | Mon 07/09/15
1368 | 690024 | CT3 Aspect of Flexible Mobile Service Steering | FMSS-CT | 2 | Rel-13 | C3 | 2015-09-09 08:00 | 2016-03-11 17:00 | 100% | CP-150799 |  | ZTE,Zhou Xiaoyun | zhou.xiaoyun@zte.com.cn | 07/09/15: 0%->20; 14/09/15: WID:CP-150488->CP-150577; 7/12/15: 20%->90; 7/12/15: WID:CP-150577->CP-150799. FCD -> 03/16. ES in CP-150646; 7/3/16: 90%->100 | 29.abc, 29.212, 29.213 | 69 | 35 |  |  | Wed 09/09/15 | Mon 07/03/16
1369 | 650020 | GERAN UTRAN Sharing Enhancements | GUSH | 1 | Rel-13 | S1 | 2014-09-19 08:00 | 2014-12-12 17:00 | 100% | SP-140637 | SP-140515 | Telefónica | chris.friel@telefonica.com | SP#65 exception in SP-140515. Triggered by TR 22.852 (FS_RSE and FS_GUSH). Completed. | 22.101 | 65 | 33 |  |  | Wed 13/08/14 | Wed 03/12/14
1370 | 640052 | Application specific Congestion control for Data Communication | ACDC | 1 | Rel-13 | S1,C1 | 2014-06-18 08:00 | 2016-03-11 17:00 | 100% | SP-140234 | S1-143305 | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#65 completed. Triggered by Rel-13 Study TR 22.806 | 22.011 | 64 | 33 |  |  | Tue 27/05/14 | Fri 29/08/14
1371 | 660013 | Stage 1 for Application specific Congestion control for Data Communication | ACDC-ST1 | 2 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-17 17:00 | 100% | SP-140234 | S1-143305 | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | Results from MCC Split of the SA1 feature into F+BB for stage 1 | 22.011 | 64 | 33 |  |  | Tue 27/05/14 | Fri 29/08/14
1372 | 660039 | Stage 3 for Application specific Congestion control for Data Communication | ACDC-CT | 2 | Rel-13 | C1 | 2014-12-04 08:00 | 2016-03-11 17:00 | 100% | CP-150282 |  | Kim, Jaehyun, LGE | jaehyun7.kim@lge.com | Presented at CT#66. June 2015: FCD: June->Dec 2015, WID: CP-140999-> CP-150282 | TS 24.105, 24.301, 24.008, 27.007, 31.102 | 66 | 34 |  |  | Thu 04/12/14 | Tue 09/12/14
1373 | 660139 | CT1 part of Stage 3 for Application specific Congestion control for Data Communication | ACDC-CT | 3 | Rel-13 | C1 | 2014-12-04 08:00 | 2015-12-16 17:00 | 100% | CP-150282 |  | Kim, Jaehyun, LGE | jaehyun7.kim@lge.com | Presented at CT#66; June2015: Compl:0%->10. June 2015: FCD: June->Dec 2015, WID: CP-140999-> CP-150282; 07/09/15: 5%->70; 7/12/15: 70%->100 | 24.105, 24.301, 24.008, 27.007, 23.122 | 66 | 34 |  |  | Tue 05/05/15 | Mon 07/12/15
1374 | 660239 | CT6 part of Stage 3 for Application specific Congestion control for Data Communication | ACDC-CT | 3 | Rel-13 | C6 | 2014-12-04 08:00 | 2016-03-11 17:00 | 100% | CP-150282 |  | Kim, Jaehyun, LGE | jaehyun7.kim@lge.com | Presented at CT#66. June 2015: FCD: June->Dec 2015, WID: CP-140999-> CP-150282. 12/15: FCD -> 03/16, ES in CP-150838; 7/3/16: 0%->100 | 31.102 | 66 | 34 |  |  | Tue 05/05/15 | Mon 07/03/16
1375 | 670059 | RAN aspects of Application specific Congestion control for Data Communication | ACDC-RAN | 2 | Rel-13 | R2 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150512 |  | LG Electronics |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1376 | 670159 | Core part: RAN aspects of Application specific Congestion control for Data Communication | ACDC-RAN-Core | 3 | Rel-13 | R2 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150662 | RP-151275 | LG Electronics |  | 03/07/15: Compl:0%->25% 03/07/15: WID: RP-150512->RP-150662 03/07/15: Stat Rep: ->RP-150661 29/09/15: Compl:25%->70% 29/09/15: Stat Rep: RP-150661->RP-151275; 1/1/16: Compl:70%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1377 | 570029 | User Plane Congestion management | UPCON | 1 | Rel-13 | S1,S2,C3,C4 | 2012-09-12 08:00 | 2015-03-18 17:00 | 100% | SP-140631 | - | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). Triggered by Rel-12 TR 22.805 Study on User Plane Congestion management (FS_UPCON) | Stage 1/2/3 | 57 | 29 |  |  | Mon 06/08/12 | Tue 16/09/14
1378 | 570129 | Stage 1 for User Plane Congestion management | UPCON-ST1 | 2 | Rel-13 | S1 | 2012-09-12 08:00 | 2013-03-06 17:00 | 100% | SP-140631 | - | KDDI | Eriko Yoshida (er-yoshida@kddi.com) | SP#63 moved to Rel-13 updated WID SP-120890=>SP-140153. SP#59 completed. Convert TR 22.805 clause 6 consolidated requirements to normative requirements in 22.101. 3/3/15: start date corrected (was Mar 12) | 22.101 | 57 | 29 |  |  | Mon 06/08/12 | Tue 03/03/15
1379 | 580057 | TR on Stage 2 for User Plane Congestion management | UPCON-SA2TR | 2 | Rel-13 | S2 | 2012-12-12 08:00 | 2015-03-18 17:00 | 100% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631. TR 23.705v100 for Information. Dec.14: 87->98%. Mar15: 100% | new TR 23.705 | 58 | 30 |  |  | Tue 13/11/12 | Thu 05/03/15
1380 | 580058 | Deleted - Stage 2 for User Plane Congestion management | UPCON-SA2Del | 2 | Rel-13 | S2 | 2012-12-19 08:00 | 2013-12-11 17:00 | 100% | SP-140631 | - | NEC | andreas.maeder@neclab.eu | SP#62 stopped at 0% completion | TBD | 58 | 30 | SP-62 | PCG-32 | Tue 13/11/12 | Tue 16/09/14
1381 | 630019 | BB1: RAN Downlink Traffic Differentiation, Congestion Detection and Reporting | UPCON-DOTCON | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2015-03-13 17:00 | 100% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631. IncludES in CP-150RAN Congestion Detection: , RAN Traffic Differentiation, RAN Congestion Reporting, CN Congestion Mitigation mechanisms, Dynamic Policy Control | - | 63 | 32 |  |  | Tue 04/03/14 | Tue 16/09/14
1382 | 630119 | Stage 2 for RAN Downlink Traffic Differentiation, Congestion Detection and Reporting | UPCON-DOTCON-SA2 | 3 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-12-12 17:00 | 100% | SP-140434 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>S2-142850 (added impacted specs). Dec.14: 70->100% only if RAN agrees to standardize the FPI | 23.060, 23.203, 23.401 | 63 | 32 |  |  | Tue 04/03/14 | Wed 03/12/14
1383 | 650007 | CT aspects of User Plane Congestion Management for BB1 | UPCON-DOTCON-CT | 3 | Rel-13 | C3 | 2014-03-18 08:00 | 2015-03-13 17:00 | 100% | CP-150365 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | Stage 3; WID: CP-140734->CP-140929. June 2015: WID: CP-140929-> CP-150365. | Stage 3 | 65 | 33 |  |  | Tue 29/07/14 | Tue 09/12/14
1384 | 650107 | CT3 part of CT aspects of User Plane Congestion Management for BB1 | UPCON-DOTCON-CT | 4 | Rel-13 | C3 | 2014-03-18 08:00 | 2015-03-13 17:00 | 100% | CP-150365 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | Dec.14: 0->60; WID: CP-140734->CP-140929. Mar.15: 60->95%; June2015: Compl:95%->100. WID: CP-140929-> CP-150365. | 29.201, 29.212, 29.213, 29.214, 29.215, 29.219, New TS 29.217 (PCC over Np) | 65 | 33 |  |  | Tue 29/07/14 | Mon 15/06/15
1385 | 650207 | CT4 part of CT aspects of User Plane Congestion Management for BB1 | UPCON-DOTCON-CT | 4 | Rel-13 | C4 | 2014-03-18 08:00 | 2015-03-13 17:00 | 100% | CP-150365 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | Dec.14: 0->20; WID: CP-140734->CP-140929. Mar. 15: 50%; June2015: Compl:50%->90. WID: CP-140929-> CP-150365.; 07/09/15: 90%->100 | 23.003, 29.303, New TS 29.405 (UPCON over Nq) | 65 | 33 |  |  | Tue 29/07/14 | Mon 07/09/15
1386 | 630020 | Deleted - BB2: Application and Content Prioritization | UPCON-CONDEL | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). IncludES in CP-150Content specific UP prioritization (Video), Application specific UP prioritization | TBD | 63 | 32 | SP-65 | PCG-33 | Tue 04/03/14 | Tue 16/09/14
1387 | 630021 | Deleted - BB3: Uplink traffic and attended/unattended traffic | UPCON-TRAFDEL | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140631 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). IncludES in CP-150Uplink Congestion Management, Un/Attended UE Information | TBD | 63 | 32 | SP-65 | PCG-33 | Tue 04/03/14 | Tue 16/09/14
1388 | 650028 | Media Handling Aspects of IMS-based Telepresence | IMS_TELEP_S4 | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2017-03-15 17:00 | 79% | SP-140483 | - | Intel | ozgur.oyman@intel.com | Can be seen as an "enhancement" of Rel-12 IMS-based Telepresence (IMS_TELEP) UID_530042. Mar. 15: 20% | - | 65 | 33 |  |  | Fri 05/09/14 | Thu 05/03/15
1389 | 650128 | TR on Media Handling Aspects of IMS-based Telepresence | IMS_TELEP_S4 | 2 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-09-16 17:00 | 100% | SP-140483 | - | Intel | ozgur.oyman@intel.com | Dec.14: 0->10%. 8/4/15: 20%; June2015: Compl:20%->30; Aug2015: 30%->35; 07/09/15: 35%->60; 7/12/15: 60%->100 | New TR 26.9xy | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/12/15
1390 | 650228 | Specification on Media Handling Aspects of IMS-based Telepresence | IMS_TELEP_S4 | 2 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 100% | SP-140483 | - | Intel | ozgur.oyman@intel.com | Dec.14: 0->10%. 8/4/15: 20%; June2015: Compl:20%->30; 07/09/15: 30%->60; 7/12/15: 60%->100 | New TS 26.1xy | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/12/15
1391 | 710035 | (IETF) CLUE Protocol (draft-ietf-clue-protocol) | IMS_TELEP_S4 | 2 | Rel-13 | S4-IETF | 2015-12-10 08:00 | 2017-03-15 17:00 | 60% |  |  | Intel | ozgur.oyman@intel.com |  | 26.22 | 71 | 36 |  |  | Mon 07/03/16 | NA
1392 | 710036 | (IETF) Mapping RTP streams to CLUE media captures (draft-ietf-clue-rtp-mapping) | IMS_TELEP_S4 | 2 | Rel-13 | S4-IETF | 2015-12-10 08:00 | 2017-03-15 17:00 | 60% |  |  | Intel | ozgur.oyman@intel.com |  | 26.22 | 71 | 36 |  |  | Mon 07/03/16 | NA
1393 | 710037 | Deleted - (IETF) DTLS Encapsulation of SCTP Packets (draft-ietf-tsvwg-sctp-dtls-encaps) | IMS_TELEP_S4 | 2 | Rel-13 | S4-IETF | 2015-12-10 08:00 | 2017-03-15 17:00 | 100% |  |  | Intel | ozgur.oyman@intel.com | 22/3/18: 95%->100. 07/06/18: deleted as per SP-180260 | 26.22 | 71 | 36 |  |  | Mon 07/03/16 | Thu 07/06/18
1394 | 710038 | (IETF) Using Simulcast in SDP and RTP Sessions (draft-ietf-mmusic-sdp-simulcast) | IMS_TELEP_S4 | 2 | Rel-13 | S4-IETF | 2015-12-10 08:00 | 2017-03-15 17:00 | 60% |  |  | Ericsson | tomas.frankkila@ericsson.com |  | 26.114, 26.223 | 71 | 36 |  |  | Mon 07/03/16 | NA
1395 | 600045 | RAN Sharing Enhancements | RSE | 1 | Rel-13 | S1,R3 | 2013-06-19 08:00 | 2015-12-15 17:00 | 100% | SP-130330 | - | NEC | joerg.swetina@neclab.eu | Triggered by Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) | - | 60 | 31 |  |  | Mon 03/06/13 | Tue 26/11/13
1396 | 600145 | Stage 1 for RAN Sharing Enhancements | RSE-SA1 | 2 | Rel-13 | S1 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | SP-130330 | - | NEC | joerg.swetina@neclab.eu | SP#62 completed | 22.101 | 60 | 31 |  |  | Mon 03/06/13 | Tue 26/11/13
1397 | 650021 | RAN aspects of RAN Sharing Enhancements for LTE | RSE-RAN_LTE | 2 | Rel-13 | R3 | 2014-09-12 08:00 | 2015-12-15 17:00 | 100% | RP-141671 | - | NEC | Siva.Vakeesar@emea.nec.com | Triggered by TR 36.856 Study on RAN aspects of RAN Sharing Enhancements for LTE (FS_RSE-RAN_LTE) & SA1 22.101 Stage 1 | LTE | 65 | 33 |  |  | Mon 16/06/14 | Sun 05/10/14
1398 | 650121 | Core part: RAN aspects of RAN Sharing Enhancements for LTE | RSE-RAN_LTE-Core | 3 | Rel-13 | R3 | 2014-09-12 08:00 | 2015-12-15 17:00 | 100% | RP-151827 | RP-151295 | NEC | Siva.Vakeesar@emea.nec.com | ; CD:Mon 15/06/15->Tue 15/09/15; Stat Rep: -->RP-141891 1st Apr 15: Compl:15%->20% 1st Apr 15: Stat Rep: RP-141891->RP-150289 03/07/15: Compl:20%->75% 03/07/15: Stat Rep: RP-150289->RP-150875 29/09/15: Compl:75%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/1 | 36.300, 36.413, 36.423 | 65 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
1399 | 630014 | Enhancements to WEBRTC interoperability | eWebRTCi | 1 | Rel-13 | S1,S2,S3 | 2014-03-07 08:00 | 2016-03-11 17:00 | 95% | SP-140630 | - | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part, SA1 change). Add enhanced interoperability support for WebRTC to Rel-12 Web Real Time Communication (WebRTC) Access to IMS. | Stage 1/2 | 63 | 32 |  |  | Wed 05/02/14 | Tue 16/09/14
1400 | 630114 | Stage 1 for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S1 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140630 | S1-143303 | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#65 completed. Updated WID SP-140286=>SP-140630 | 22.228 | 63 | 32 |  |  | Wed 05/02/14 | Tue 16/09/14
1401 | 640138 | TR on Stage 2 for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S2 | 2014-06-19 08:00 | 2015-03-18 17:00 | 100% | SP-140630 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 9->55%; June2015: Compl:55%->85; 07/09/15: 85%->100 | New TR 23.706 | 64 | 33 |  |  | Thu 12/06/14 | Mon 07/09/15
1402 | 640038 | Stage 2 for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 100% | SP-140630 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part); June2015: Compl:0%->85; 07/09/15: 85%->100 | 23.228 | 64 | 33 |  |  | Thu 12/06/14 | Mon 07/09/15
1403 | 650122 | TR on Security for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S3 | 2014-09-17 08:00 | 2015-09-30 17:00 | 100% | SP-140630 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 0->20%, TR number added. 3/3/15: 30%.; June2015: Compl:30%->75; 11/12/15: 54%->100; 11/12/15: 100%->100 | New TR 33.872 | 65 | 33 |  |  | Thu 04/09/14 | Fri 11/12/15
1404 | 650022 | Security for Enhancements to WEBRTC interoperability | eWebRTCi | 2 | Rel-13 | S3 | 2014-09-17 08:00 | 2015-09-30 17:00 | 100% | SP-140630 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 0->20%; 11/12/15: 15%->100 | 33.203, 33.328 | 65 | 33 |  |  | Thu 04/09/14 | Fri 11/12/15
1405 | 690037 | (IETF) Session Traversal Utilities for NAT (STUN) Extension for Third Party Authorization (draft-ietf-tram-turn-third-party-authz) | eWebRTCi | 2 | Rel-13 | S3-IET | 2014-09-17 08:00 | 2015-08-12 13:48 | 100% | SP-150474 | - | Alcatel-Lucent |  | TS 33.203 CR0235 draft-ietf-tram-turn-third-party-authz; 7/3/16: 10%->100 | 33.203, RRC 7635 (was draft-ietf-tram-turn-third-party-authz) | 69 | 35 |  |  | Thu 04/09/14 | Mon 07/03/16
1406 | 690012 | Stage 3 for Enhancements to WebRTC interoperability | eWebRTCi-CT | 2 | Rel-13 | ct | 2015-09-07 08:00 | 2016-03-11 17:00 | 84% | CP-150767 |  | China Mobile, Song Yue | songyue@chinamobile.com | 7/12/15: WID:CP-150498->CP-150790->CP-150767 |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
1407 | 690015 | CT1 aspects 3 for Enhancements to WebRTC interoperability | eWebRTCi-CT | 3 | Rel-13 | C1 | 2015-09-07 08:00 | 2015-12-18 17:00 | 100% | CP-150767 |  | China Mobile, Song Yue | songyue@chinamobile.com | 7/12/15: 0%->100; 7/12/15: WID:CP-150498->CP-150790->CP-150767 | 24.371, 24.229 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
1408 | 690029 | CT3 aspects for Enhancements to WebRTC interoperability | eWebRTCi-CT | 3 | Rel-13 | C3 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-150767 |  | China Mobile, Song Yue | songyue@chinamobile.com | 7/12/15: WID:CP-150498->CP-150790->CP-150767. ES in CP-150644; 7/3/16: 0%->100 | 29.214 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
1409 | 690016 | CT4 aspects for Enhancements to WebRTC interoperability | eWebRTCi-CT | 3 | Rel-13 | C4 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-150767 |  | China Mobile, Song Yue | songyue@chinamobile.com | 7/12/15: WID:CP-150498->CP-150790->CP-150767. ES in CP-150623; 7/3/16: 0%->100 | 29.228, 23.334, 29.334, 23.008 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
1410 | 710039 | (IETF) SDP-based Data Channel Negotiation (draft-ietf-mmusic-data-channel-sdpneg) | eWebRTCi-CT | 3 | Rel-13 | C1-IETF,SA4-IETF | 2015-12-08 08:00 | 2016-03-11 17:00 | 75% |  |  | Ericsson | christer.holmberg@ericsson.com | 7/3/16: Introduced by IETF updates | 24.371, 24.229 | 71 | 36 |  |  | Mon 07/03/16 | Mon 07/03/16
1411 | 710040 | (IETF) MSRP over Data Channels (draft-ietf-mmusic-msrp-usage-data-channel) | eWebRTCi-CT | 3 | Rel-13 | C1-IETF | 2015-12-08 08:00 | 2016-03-11 17:00 | 75% |  |  | Ericsson | christer.holmberg@ericsson.com | 7/3/16: Introduced by IETF updates | 24.371, 24.229, 26.223 | 71 | 36 |  |  | Mon 07/03/16 | Mon 07/03/16
1412 | 710041 | (IETF) A Language for Rules Describing JSON Content (draft-newton-json-content-rules) | eWebRTCi-CT | 3 | Rel-13 | C3-IETF | 2015-12-08 08:00 | 2016-03-11 17:00 | 25% |  |  | Ericsson | christer.holmberg@ericsson.com | 7/3/16: Introduced by IETF updates | 24.371, 24.229, 26.223 | 71 | 36 |  |  | Mon 07/03/16 | Mon 07/03/16
1413 | 630016 | Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | CSPS_Coord | 1 | Rel-13 | S2 | 2014-03-07 08:00 | 2016-05-12 17:00 | 100% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | Provide improvements to the solutions for CS/PS coordination in TS 23.251 to ensure that CS/PS coordination can be achieved for all mobility scenarios | Stage 2 | 63 | 32 |  |  | Wed 05/02/14 | Tue 04/03/14
1414 | 630116 | TR on Stage 2 for Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | CSPS_Coord-SA2TR | 2 | Rel-13 | S2 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | SP#65 completed. TR 23.704v200 for Approval | New TR 23.704 | 63 | 32 |  |  | Wed 05/02/14 | Mon 04/08/14
1415 | 630216 | Stage 2 for Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks | CSPS_Coord-SA2 | 2 | Rel-13 | S2 | 2014-03-12 08:00 | 2014-12-12 17:00 | 100% | SP-140168 | - | Ericsson | roland.gustafsson@ericsson.com | Dec.14: 0->100% | 23.216, 23.251, 23.272 | 63 | 32 |  |  | Wed 05/02/14 | Wed 03/12/14
1416 | 650100 | RAN aspects for improvements to CS/PS coordination in GERAN Shared Networks | CSPS_Coord_GERAN | 2 | Rel-13 | G2 | 2015-03-11 08:00 | 2016-05-12 17:00 | 100% | GP-150225 |  | Nicklas Johansson, Ericsson LM | Nicklas.Johansson@Ericsson.com | June2015: Compl:0%->35; 07/09/15: 35%->50, FCD:08/15->11/15; 7/12/15: 50%->95, FCD: 12/15->02/16. 02/03/16: FCD: 02/16->05/16; 13/6/16: 95%->100 | 48.008, 48.018 | 65 |  |  |  | Thu 07/05/15 | Mon 13/06/16
1417 | 640040 | Enhancements to Proximity-based Services | eProSe | 1 | Rel-13 | S1,S2,S3 | 2013-03-18 08:00 | 2016-03-11 17:00 | 100% | SP-140386 | - | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | - | Stage 1/2 | 64 | 33 |  |  | Tue 27/05/14 | Fri 05/09/14
1418 | 640140 | Stage 1 for Enhancements to Proximity-based Services | eProSe-SA1 | 2 | Rel-13 | S1 | 2014-06-19 08:00 | 2014-09-17 17:00 | 100% | SP-140386 | - | Qualcomm | Eddy Hall (edhall@qti.qualcomm.com) | SP#65 completed. Some Rel-12 ProSe service requirements have not been implemented at Stage 2/3 level. These are taken up in Rel-13 Stage 2/3 and need Stage 1 appropriate service requirements. No new service requirements are introduced. | 22.115, 22.278 | 64 | 33 |  |  | Tue 27/05/14 | Wed 03/09/14
1419 | 640041 | Stage 2 for Enhancements to Proximity-based Services - Extensions | eProSe-Ext-SA2 | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-09-16 17:00 | 100% | SP-150028 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Mar15: WID: SP-140573 ->SP-150028; June2015: Compl:0%->30. FCD: June->Sept. 07/09/15: 24->70%; 07/09/15: 70%->90; 7/12/15: 90%->100 | 23.303, TBD | 64 | 33 |  |  | Tue 17/06/14 | Mon 07/12/15
1420 | 640141 | TR on Stage 2 for Enhancements to Proximity-based Services - Extensions | eProSe-Ext-SA2TR | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-13 17:00 | 100% | SP-150028 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Acronym corrected: eProSe-Ex-SA2TRt->eProSe-Ext-SA2TR. Mar15: 60% Mar15: WID: SP-140573 ->SP-150028; June2015: Compl:60%->90; 07/09/15: 90%->95; 07/09/15: 95%->100 | New TR 23.713 | 64 | 33 |  |  | Tue 17/06/14 | Mon 07/09/15
1421 | 650023 | Security for Enhancements to Proximity-based Services - Extensions | eProSe-Ext-SA3 | 2 | Rel-13 | S3 | 2014-09-19 08:00 | 2016-03-11 17:00 | 100% | SP-150028 | - | Qualcomm | Adrian Escott (aescott@qti.qualcomm.com) | SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Acronym corrected: eProSe-Ex-SA3t->eProSe-Ext-SA3. Mar15: WID: SP-140573 ->SP-150028; 7/12/15: 0%->75; 10/12/15: FCD ->03/16, ES in SP-150714; 7/3/16: 75%->100 | 33.303 | 65 | 33 |  |  | Thu 04/09/14 | Mon 07/03/16
1422 | 680006 | CT aspects of enhancements to Proximity-based | eProSe-Ext-CT | 2 | Rel-13 | C1 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150370 |  | Lena Chaponniere | lguellec@qti.qualcomm.com |  | 23.122, 24.301, 24.333, 24.334 | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
1423 | 680007 | CT1 aspects of enhancements to Proximity-based | eProSe-Ext-CT | 3 | Rel-13 | C1 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150370 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 07/09/15: 0%->40; 7/12/15: 40%->90. FCD -> 03/16, ES in CP-150724; 7/3/16: 90%->100 | 29.343 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
1424 | 680008 | CT3 aspects of enhancements to Proximity-based | eProSe-Ext-CT | 3 | Rel-13 | C3 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150370 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 07/09/15: 0%->60; 8/3/16: 60%->100 | 23.003, 23.008, 29.272, 29.344, 29.345 | 68 | 35 |  |  | Mon 15/06/15 | Tue 08/03/16
1425 | 680009 | CT4 aspects of enhancements to Proximity-based | eProSe-Ext-CT | 3 | Rel-13 | C4 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150370 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 07/09/15: 0%->10; 7/12/15: 10%->80. FCD->03/16. ES in CP-150616; 7/3/16: 80%->100 | 31.102, 31.111 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
1426 | 680010 | CT6 aspects of enhancements to Proximity-based | eProSe-Ext-CT | 3 | Rel-13 | C6 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150370 |  | Lena Chaponniere | lguellec@qti.qualcomm.com | 7/12/15: FCD -> 03/16, ES in CP-150839. FCD->03/16. ES in CP-150616; 7/3/16: 0%->95; 8/3/16: 95%->100 | 31.102, 31.111 | 68 | 35 |  |  | Mon 15/06/15 | Tue 08/03/16
1427 | 590035 | Study on Security for Proximity-based Services | FS_ProSe_Sec | 2 | Rel-13 | S3 | 2013-03-18 08:00 | 2015-06-17 17:00 | 100% | SP-140629 | - | Qualcomm | Adrian Escott (aescott@qti.qualcomm.com) | SP#65 updated WID SP-140300=>SP-140629 (Moved the TR phase to Rel-13 as a stand-alone Study). Completion 09/14=>06/15. SP#64 TR 33.833 v100 for Information. 4/3/15: 95%->70% (more topics to be included); June2015: Compl:70%->75; 7/12/15: 75%->95; 7/3/1 | 33.833 | 59 | 30 |  |  | Wed 20/02/13 | Thu 01/12/16
1428 | 729999 | Note: Charging Aspects done in Rel-14 under CH14-Prose (UID 720049) | eProSe | 2 | Rel-13 | S5 | 2015-06-17 17:00 | 2015-06-17 17:00 | 100% | [6 empty] | 72 |  |  |  | Mon 13/06/16 | Thu 01/12/16
1429 | 640045 | voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD | 1 | Rel-13 | S1,S2,C4,C1,C3 | 2014-06-16 08:00 | 2014-12-12 17:00 | 100% | SP-140394 | - | Alcatel-Lucent | (betsy.covell@alcatel-lucent.com) | - | Stage 1/2 | 64 | 33 |  |  | Thu 29/05/14 | Wed 11/06/14
1430 | 640145 | Stage 1 for voice over E-UTRAN Paging Policy Differentiation | voE_UTRA-N_PPD-SA1 | 2 | Rel-13 | S1 | 2014-06-16 08:00 | 2014-06-18 17:00 | 100% | SP-140394 | - | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#64 approved WID & completed | 22.228, 22.278 | 64 | 33 |  |  | Thu 29/05/14 | Wed 11/06/14
1431 | 640245 | Stage 2 for voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-SA2 | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2014-12-12 17:00 | 100% | SP-140394 | - | Alcatel-Lucent | laurent.thiebaut@alcatel-lucent.com | Architectural enhancements allowing a differentiated paging policy for IMS voice calls over E-UTRAN. Dec.14: 25->100% | 23.228, 23.401 | 64 | 33 |  |  | Wed 11/06/14 | Wed 03/12/14
1432 | 650003 | CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 2 | Rel-13 | C4,C1,C3 | 2014-09-16 08:00 | 2014-12-09 17:00 | 100% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | Stage 3 | Stage 3 | 65 | 33 |  |  | Tue 29/07/14 | Tue 29/07/14
1433 | 650103 | CT4 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 3 | Rel-13 | C4 | 2014-09-16 08:00 | 2014-12-09 17:00 | 100% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | Mar.15: 0->100% | 29.274, 29.281 | 65 | 33 |  |  | Tue 29/07/14 | Wed 04/03/15
1434 | 650203 | CT1 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 3 | Rel-13 | C1 | 2014-09-16 08:00 | 2014-12-09 17:00 | 100% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | Dec.14: 0->50%; 07/09/15: 50%->50; 7/12/15: 50%->100 | 24.229 | 65 | 33 |  |  | Tue 29/07/14 | Mon 07/12/15
1435 | 650303 | CT3 part of CT aspects of voice over E-UTRAN Paging Policy Differentiation | voE_UTRAN_PPD-CT | 3 | Rel-13 | C3 | 2014-09-16 08:00 | 2014-12-09 17:00 | 100% | CP-140491 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | Mar.15: 0->100% | 29.061 | 65 | 33 |  |  | Tue 29/07/14 | Wed 04/03/15
1436 | 640047 | IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM | 1 | Rel-13 | S2 | 2014-06-18 08:00 | 2016-06-15 17:00 | 100% | SP-150250 | - | Tricci So, ZTE | tso@zte.com.cn | 06/15: WID: SP-140279->SP-150250 | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Thu 18/06/15
1437 | 640147 | TR for IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-SA2TR | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-13 17:00 | 100% | SP-140279 | - | Tricci So, ZTE | tso@zte.com.cn | Revived the Rel-12 DRAFT TR 23.861 stopped at SP#59 (at 40% completion). Dec.14: 20->60%; June2015: Compl:60%->90, WID: SP-140279->SP-150250 | New TR 23.861 | 64 | 33 |  |  | Fri 30/05/14 | Thu 18/06/15
1438 | 640247 | Stage 2 for IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-SA2 | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-09-16 17:00 | 100% | SP-150250 |  | Tricci So, ZTE | tso@zte.com.cn | June2015: Compl:0%->65, WID: SP-140279->SP-150250; 07/09/15: 52%->100 | 23.402, New TS 23.203 | 64 |  |  |  | Fri 30/05/14 | Mon 07/09/15
1439 | 690043 | Charging Aspects of IP Flow Mobility support for S2a and S2b Interfaces (NBIFOM) | NBIFOM-CH | 2 | Rel-13 | S5 | 2015-09-16 08:00 | 2016-06-15 17:00 | 100% | SP-150406 |  | GUO Wenjie, ZTE | guo.wenjie1@zte.com.cn | 7/12/15: 0%->50. ES in SP-150710 (wrong UID mentioned in the ES); 7/3/16: 50%->85%, FCD:03/16->06/16; 13/6/16: 85%->100 | 32.251, 32.298, 32.299 | 69 | 35 |  |  | Fri 30/05/14 | Mon 13/06/16
1440 | 680019 | CT aspects of IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-CT | 2 | Rel-13 | C1 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150874 |  | Xingyue(Joy) Zhou, ZTECorporation | zhou.xingyue@zte.com.cn | 14/09/15: WID:CP-150285->CP-150497; 7/12/15: WID:CP-150497->CP-150791->874 | 24.161 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1441 | 680020 | CT1 aspects of IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-CT | 3 | Rel-13 | C1 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150874 |  | Xingyue(Joy) Zhou, ZTECorporation. ES in 641 | zhou.xingyue@zte.com.cn | 07/09/15: 0%->25; 14/09/15: WID:CP-150285->CP-150497; 7/12/15: 25%->75; 7/12/15: WID:CP-150497->CP-150791->874. FCD -> 03/16. ES in CP-150725; 7/3/16: 75%->100 | 24.301, 24.302, 24.244, 24.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
1442 | 680021 | CT3 aspects of IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-CT | 3 | Rel-13 | C3 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150874 |  | 680001Xingyue(Joy) Zhou, ZTECorporation. ES in 641 | zhou.xingyue@zte.com.cn | 07/09/15: 0%->40; 14/09/15: WID:CP-150285->CP-150497; 7/12/15: 40%->95; 7/12/15: WID:CP-150497->CP-150791->874. FCD -> 03/16. ES in CP-150725; 7/3/16: 95%->100 | 29.212, 29.213, 29.214, 29.215 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
1443 | 680022 | CT4 aspects of IP Flow Mobility support for S2a and S2b Interfaces | NBIFOM-CT | 3 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150874 |  | Xingyue(Joy) Zhou, ZTECorporation | zhou.xingyue@zte.com.cn | 07/09/15: 0%->20; 14/09/15: WID:CP-150285->CP-150497; 7/12/15: 20%->100; 7/12/15: WID:CP-150497->CP-150791->874 | 29.274, 23.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1444 | 640053 | Double Resource Reuse for Multiple Media Sessions | DRuMS | 1 | Rel-13 | S2 | 2014-03-14 08:00 | 2015-03-13 17:00 | 100% | SP-140393 | - | Ericsson | George.Foti@ericsson.com | - | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Wed 11/06/14
1445 | 640153 | Stage 2 for Double Resource Reuse for Multiple Media Sessions | DRuMS-SA2 | 2 | Rel-13 | S2 | 2014-03-14 08:00 | 2015-03-13 17:00 | 100% | SP-140393 | - | Ericsson | George.Foti@ericsson.com | Dec.14: 49->95%. Mar15: 100% | 23.203, 23.228 | 64 | 33 |  |  | Fri 30/05/14 | Thu 05/03/15
1446 | 660019 | CT aspects of Double Resource Reuse for Multiple Media Sessions | DRuMS-CT | 2 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 100% | CP-140926 |  | Ericsson |  |  | 24.229, 24.615, 24.610, 24.605, 29.212, 29.213, 29.214, 29.215 | 66 | 34 |  |  | Thu 04/12/14 | Thu 04/12/14
1447 | 660047 | CT1 aspects of Double Resource Reuse for Multiple Media Sessions | DRuMS-CT | 3 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-03-13 17:00 | 100% | CP-140926 |  | Ericsson |  | 5/5/15: C3 corrected in C1; June2015: Compl:65%->90; 07/09/15: 90%->100 | 24.229, 24.615, 24.610, 24.605 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/09/15
1448 | 660048 | CT3 aspects of Double Resource Reuse for Multiple Media Sessions | DRuMS-CT | 3 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 100% | CP-140926 |  | Ericsson | Jan Holm | Mar.15: 65->95%; June2015: Compl:95%->100 | 29.212, 29.213, 29.214, 29.215 | 66 | 34 |  |  | Tue 09/12/14 | Mon 15/06/15
1449 | 640056 | Lawful Interception in the 3GPP Rel-13 | LI13 | 1 | Rel-13 | S3 | 2014-06-18 08:00 | 2016-12-15 17:00 | 100% | SP-160043 | - | PIDS, Alcatel-Lucent | Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com | SP#65 updated WID SP-140400=>SP-140578. 2/4/15: WID SP-140815->SP-150111; June2015: Compl:0%->10. WID: SP-150111->SP-150290; 14/09/15: WID:SP-150290->SP-150460; 7/12/15: 10%->15; 7/3/16: 13%->20; 7/3/16: WID:SP-150460->SP-160043; 19/9/16: 20%->60. FCD | 33.106, 33.107, 33.108 | 64 | 33 |  |  | Wed 11/06/14 | Thu 01/12/16
1450 | 640055 | STOPPED - Study on Lawful Interception Service Evolution | FS_LISE | 1 | Rel-13 | S3 | 2014-06-23 08:00 | 2015-12-09 17:00 | 100% | SP-140303 | - | Alcatel-Lucent | terry.jacobson@alcatel-lucent.com | Linked to LI13 which defines existing LI service requirements in TS 33.106 as well as existing HI1, HI2 & HI3 reference points. 3/3/15: 0->5%; 7/12/15: 5%->10. Stoppped at 10% in March 2017.; 6/3/17: 10%->100 | 33.826 | 64 | 33 |  |  | Wed 11/06/14 | Mon 06/03/17
1451 | 640058 | Video enhancements by Region-Of-Interest information signalling | ROI | 1 | Rel-13 | S4 | 2014-06-18 08:00 | 2015-12-16 17:00 | 100% | SP-140219 | - | Intel | ozgur.oyman@intel.com | Dec.14: 5->20%. Mar.15: 40%; 07/09/15: 43%->100 | 26.114 | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/09/15
1452 | 680031 | SA4 aspects of Video enhancements by Region-Of-Interest information signalling | ROI | 2 | Rel-13 | S4 | 2014-06-18 08:00 | 2015-09-16 17:00 | 100% | SP-140219 | - | Intel | ozgur.oyman@intel.com | Created by MCC as the structure of the Feature get expanded to include CT aspects; June2015: Compl:40%->90, FCD: 06/15->09/15; Aug2015: Compl:90%->95 | 26.114 | 64 | 33 |  |  | Mon 15/06/15 | Wed 12/08/15
1453 | 680017 | CT Aspects of Video Enhancements by Region-Of-Interest information signalling | ROI-CT | 2 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150425 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | 14/09/15: WID:CP-150241->CP-150425 |  | 68 | 35 |  |  | Mon 15/06/15 | Mon 14/09/15
1454 | 680032 | CT1 Aspects of Video Enhancements by Region-Of-Interest information signalling | ROI-CT | 3 | Rel-13 | C1 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150425 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | 07/09/15: 100%->50; 14/09/15: WID:CP-150241->CP-150425; 7/12/15: 50%->100 | 24.229 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1455 | 680033 | CT3 Aspects of Video Enhancements by Region-Of-Interest information signalling | ROI-CT | 3 | Rel-13 | C3 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150425 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | 07/09/15: 100%->10; 14/09/15: WID:CP-150241->CP-150425; 7/12/15: 10%->100 | 29.162 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1456 | 680034 | CT4 Aspects of Video Enhancements by Region-Of-Interest information signalling | ROI-CT | 3 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150425 |  | Vivek Gupta, Intel | vivek.g.gupta@intel.com | 07/09/15: 100%->5; 14/09/15: WID:CP-150241->CP-150425; 7/12/15: 5%->100 | 23.334, 29.334, 29.238 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1457 | 650026 | TV video profile | TVProf | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2016-03-11 17:00 | 100% | SP-140481 | - | Orange | gilles.teniou@orange.com | Mar. 15: 5->15% | - | 65 | 33 |  |  | Fri 05/09/14 | Thu 05/03/15
1458 | 650126 | TR on TV video profile | TVProf-SA4TR | 2 | Rel-13 | S4 | 2014-09-09 08:00 | 2016-03-11 17:00 | 100% | SP-140481 | - | Orange | gilles.teniou@orange.com | Dec.14: 0->5%; June2015: Compl:15%->30; Aug2015: 30%->45; 07/09/15: 45%->70; 7/12/15: 70%->85, FCD: 12/15->03/16; 7/3/16: 85%->100 | New TR 26.9xy. ES in SP-150650 | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/03/16
1459 | 650226 | Specification on TV video profile | TVProf-SA4 | 2 | Rel-13 | S4 | 2014-09-09 08:00 | 2016-03-11 17:00 | 100% | SP-140481 | - | Orange | gilles.teniou@orange.com | Dec.14: 0->5%; June2015: Compl:15%->30; Aug2015: 30%->45; 07/09/15: 45%->70; 7/12/15: 70%->85, FCD: 12/15->03/16. ES in SP-150650; 7/3/16: 85%->100 | 26.234, 26.244, 26.346, 26.247, New TS 26.xyz. ES in SP-150650 | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/03/16
1460 | 650027 | Enhanced LTE UE Delay test methods and requirements | E_LTE_UED | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2016-06-15 17:00 | 100% | SP-140482 | - | Orange | stephane.ragot@orange.com | Mar. 15: 0->5%; June2015: Compl:5%->10; Aug2015: 10%->15; 07/09/15: 15%->50; 7/12/15: 50%->80, FCD: 12/15->03/16. ES in SP-150652; 7/3/16: FCD: 03/16->06/16; 11/6/16: 80%->100 | 26.131, 26.132 | 65 | 33 |  |  | Fri 05/09/14 | Sat 11/06/16
1461 | 650029 | HTML5 Presentation Layer | HTML5 | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 100% | SP-140484 | - | Samsung | Imed Bouazizi (i.bouazizi@samsung.com) | Triggered by Rel-12 TR 26.907 (Study of HTML5 and 3GPP User Services). Dec.14: 0->5%. Mar. 15: 10%; June2015: Compl:10%->20; Aug2015: 20%->40; 07/09/15: 40%->70; 7/12/15: 70%->100 | 26.140, 26.234, 26.247, 26.346, New TS 26.xyz | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/12/15
1462 | 650030 | Support of EVS in 3G Circuit-Switched networks | EVSoCS | 1 | Rel-13 | S4,C4,C1,C3,R1,R2,R3 | 2014-09-09 08:00 | 2016-03-11 17:00 | 100% | SP-140485 | - | Qualcomm | Imre Varga (ivarga@qti.qualcomm.com) | Provide CS support of EVS to enhance voice quality in CS services over UTRAN (3G WCDMA). Dec.14: 0->5%; 28/1/16: 26.454 added; 28/1/16: 26.453 added; | 26.103, 28.062, New TS 26.454; New TS 26.453 | 65 | 33 |  |  | Fri 05/09/14 | Thu 28/01/16
1463 | 670016 | SA4 aspects of EVS in 3G Circuit-Switched networks | EVSoCS-S4 | 2 | Rel-13 | S4 | 2014-09-09 08:00 | 2016-03-11 17:00 | 100% | SP-140485 | - | Qualcomm | Imre Varga (ivarga@qti.qualcomm.com) | Created by MCC (duplicated from previously single-line Feature) due to the introduction of the CT BB. Mar. 15: 10%; Aug2015: 10%->20; 07/09/15: 20%->40; 7/12/15: 40%->60, FCD:12/15->03/16. ES in SP-150655; 28/1/16: 26.454 added; 28/1/16: 26.453 added; | 26.103, 28.062, New TS 26.454; New TS 26.453 | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/03/16
1464 | 670002 | CT aspects of EVS in 3G Circuit-Switched Networks | EVSoCS-CT | 2 | Rel-13 | C4,C1,C3 | 2015-03-04 08:00 | 2016-03-11 17:00 | 100% | CP-150200 |  | Qualcomm, Lena Chaponniere | lguellec@qti.qualcomm.com |  |  | 67 | 34 |  |  | Wed 04/03/15 | Mon 09/03/15
1465 | 670017 | CT1 aspects of EVS in 3G Circuit-Switched Networks | EVSoCS-CT | 3 | Rel-13 | C1 | 2015-03-04 08:00 | 2015-12-11 17:00 | 100% | CP-150200 |  | Qualcomm, Lena Chaponniere | lguellec@qti.qualcomm.com | 07/09/15: 0%->90; 7/12/15: 90%->100 | 24.008 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
1466 | 670018 | CT3 aspects of EVS in 3G Circuit-Switched Networks | EVSoCS-CT | 3 | Rel-13 | C3 | 2015-03-04 08:00 | 2016-03-11 17:00 | 100% | CP-150200 |  | Qualcomm, Lena Chaponniere | lguellec@qti.qualcomm.com | June2015: Compl:0%->10; 07/09/15: 10%->15; 7/12/15: 15%->90. FCD -> 03/16, ES in CP-150638; 7/3/16: 90%->100 | 29.163, 29.414, 29.415 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/03/16
1467 | 670019 | CT4 aspects of EVS in 3G Circuit-Switched Networks | EVSoCS-CT | 3 | Rel-13 | C4 | 2015-03-04 08:00 | 2016-03-11 17:00 | 100% | CP-150200 |  | Qualcomm, Lena Chaponniere | lguellec@qti.qualcomm.com | June2015: Compl:0%->95. FCD -> 03/16, ES in CP-150618; 7/3/16: 95%->100 | 23.153, 23.334, 29.002, 29.231, 29.232, 29.332, 29.334 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/03/16
1468 | 660073 | Support of EVS over UTRAN CS | EVSoCS_UTRAN | 2 | Rel-13 | R2,R1,R3 | 2015-06-16 10:40 | 2015-12-15 17:00 | 100% | RP-142282 |  | Qualcomm | Qualcomm |  |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 15/01/15
1469 | 660173 | Core part: Support of EVS over UTRAN CS | EVSoCS_UTRAN-Core | 3 | Rel-13 | R2,R1,R3 | 2015-06-16 10:40 | 2015-12-15 17:00 | 100% | RP-142282 | RP-151282 | Francesco Pica - Qualcomm Incorporated | fpica@qti.qualcomm.com | Rapporteur details and involved WGs updated 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150128. 5/5/15: 0->10% 03/07/15: Compl:10%->25% 03/07/15: Stat Rep: RP-150128->RP-150759 29/09/15: Compl:25%->50% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 2 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1470 | 650031 | Enhanced DASH (Dynamic Adaptive Streaming over HTTP in 3GPP) | eDASH | 1 | Rel-13 | S4 | 2014-09-09 08:00 | 2015-12-16 17:00 | 100% | SP-150448 | - | Qualcomm, Huawei | Thomas Stockhammer (tsto@qti.qualcomm.com), Li Zhiming (lizhiming@huawei.com) | Triggered by Rel-12 Dec.14: 0->10%. Mar. 15: 15%; June2015: Compl:15%->25. WID updated; Aug2015: 25%->30; 07/09/15: 30%->60; 14/09/15: WID:SP-150211->SP-150448; 7/12/15: 60%->100 | 26.233, 26.234, 26.244, 26.247, 26.938, TS 26.346, TR 26.946 | 65 | 33 |  |  | Fri 05/09/14 | Mon 07/12/15
1471 | 650032 | QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3) | QOSE2EMTSI | 1 | Rel-13 | S4,C3,C1,C4 | 2013-03-06 08:00 | 2016-03-11 17:00 | 100% | SP-140601 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel-12 incl. new TR to Rel-13). Co-ordinate with SA2, CT1/3/4, IETF MMUSIC. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040 | - | 59 | 30 |  |  | Wed 20/02/13 | Sat 20/09/14
1472 | 620068 | TR on improved end-to-end QoS handling for MTSI | QOSE2EMTSI | 2 | Rel-13 | S4 | 2013-12-11 08:00 | 2016-03-11 17:00 | 100% | SP-140601 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel12 incl. new TR to Rel-13). Completion 03/15=>06/15. Mar15: 26.924 for info. 8/4/15: 50%; Aug2015: 50%->60; 7/12/15: 75%->90, FCD: 06/15->03/16; 7/3/16: 90%->100 | new TR 26.924 | 62 | 32 |  |  | Fri 29/11/13 | Mon 07/03/16
1473 | 650132 | SA4 part of QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3) | QOSE2EMTSI | 2 | Rel-13 | S4 | 2013-03-06 08:00 | 2016-03-11 17:00 | 100% | SP-140601 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65: WID SP-130670=>SP-140601 (moved from Rel12 incl. new TR to Rel-13). FCD 03/15=>06/15. St1 in TS 22.173. 12/14: 70->40%, CD: 06/15->09/15. 03/15: 50%. June 15: FCD: 09/15->12/15; 08/15: 60%; 09/15: 75%; 7/12. ES in SP-150658; 7/3/16: 90%->100 | 26.114 | 59 | 30 |  |  | Wed 20/02/13 | Mon 07/03/16
1474 | 660043 | CT Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT | 2 | Rel-13 | C3,C1,C4 | 2014-11-05 08:00 | 2016-03-11 17:00 | 100% | CP-140925 |  | Ericsson |  |  |  | 66 | 34 |  |  | Tue 09/12/14 | Tue 09/12/14
1475 | 660044 | CT3 Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT | 3 | Rel-13 | C3 | 2014-11-05 08:00 | 2016-03-11 17:00 | 100% | CP-140925 |  | Ericsson |  | 7/12/15: 0%->70. FCD -> 03/16, ES in CP-150636; 7/3/16: 70%->100 | 29.162, 29.163, 29.213, 29.214 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/03/16
1476 | 660045 | CT1 Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT | 3 | Rel-13 | C1 | 2014-11-05 08:00 | 2016-03-11 17:00 | 100% | CP-140925 |  | Ericsson |  | FCD -> 03/16, ES in CP-150726; 7/3/16: 0%->100 | 24.229 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/03/16
1477 | 660046 | CT4 Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT | 3 | Rel-13 | C4 | 2014-11-05 08:00 | 2016-03-11 17:00 | 100% | CP-140925 |  | Ericsson |  | FCD -> 03/16, ES in CP-150620; 7/3/16: 0%->100 | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/03/16
1478 | 660050 | MTSI Extension on Multi-stream Multiparty | MMCMH | 1 | Rel-13 | S4 | 2014-12-12 08:00 | 2016-03-07 17:00 | 83% | SP-150660 |  | Tomas Frankkila, Ericsson LM | tomas.frankkila@ericsson.com | Mar. 15: 0->10%. WID: SP-140738->SP-150097; June2015: Compl:10%->30; Aug2015: 30%->50, FCD: sep->Dec 2015; 07/09/15: 50%->60; 7/12/15: 60%->100; 10/12/15: WID:SP-150097->SP-150660. Might be moved to Rel-14 (see note in UID710002) | 26.114, New TR 26.980 | 66 | 34 |  |  | Fri 12/12/14 | Thu 10/12/15
1479 | 710042 | Codec aspects for MMCMH | MMCMH | 2 | Rel-13 | S4 | 2014-12-12 08:00 | 2015-12-17 17:00 | 100% | SP-150660 |  | Tomas Frankkila, Ericsson LM | tomas.frankkila@ericsson.com | Introduced by MCC to dissociate S4 from IeTF aspects | 26.114, New TR 26.980 | 66 | 34 |  |  | Fri 12/12/14 | Thu 10/12/15
1480 | 710043 | (IETF) RTP Stream Pause and Resume (RFC 7728) | MMCMH | 2 | Rel-13 | S4-IETF | 2015-12-07 08:00 | 2016-03-07 17:00 | 100% | SP-150660 |  | Ericsson | tomas.frankkila@ericsson.com | 02/2016: published as RFC 7728 | (IETF) RTP Stream Pause and Resume (RFC 7728) | 71 | 36 |  |  | Fri 12/12/14 | Mon 07/03/16
1481 | 720062 | (IETF) (draft-ietf-mmusic-sdp-simulcast) | MMCMH | 2 | Rel-13 | S4-IETF | 2015-12-07 08:00 | 2016-03-07 17:00 | 0% | [6 empty] | 72 | 37 |  |  | Mon 13/06/16 | NA
1482 | 660051 | Video Telephony Robustness Improvements Extensions | VTRI_EXT | 1 | Rel-13 | S4 | 2014-12-12 08:00 | 2015-09-11 17:00 | 70% | SP-140739 |  | Muhammed Coban, Qualcomm Incorporated | mcoban@qti.qualcomm.com | New TR added. 3/3/15: "extensions" added in the title. Mar. 15: 0->10% | 26.922 (new), 26.114 | 66 | 34 |  |  | Fri 12/12/14 | Thu 05/03/15
1483 | 660151 | TR on Video Telephony Robustness Improvements | VTRI_EXT | 2 | Rel-13 | S4 | 2014-12-12 08:00 | 2015-09-11 17:00 | 100% | SP-140739 |  | Muhammed Coban, Qualcomm Incorporated | mcoban@qti.qualcomm.com | 3/3/15: created to distinguish TR and TS tasks; June2015: Compl:10%->40; Aug2015: 40%->95; 07/09/15: 95%->100 | 26.922 (new), 26.114 | 66 | 34 |  |  | Tue 03/03/15 | Mon 07/09/15
1484 | 660251 | Specification on Video Telephony Robustness Improvements | VTRI_EXT | 2 | Rel-13 | S4 | 2014-12-12 08:00 | 2015-09-11 17:00 | 100% | SP-140739 |  | Muhammed Coban, Qualcomm Incorporated | mcoban@qti.qualcomm.com | 3/3/15: created to distinguish TR and TS tasks; June2015: Compl:10%->40; Aug2015: 40%->95; 07/09/15: 95%->100 | 26.922 (new), 26.114 | 66 | 34 |  |  | Tue 03/03/15 | Mon 07/09/15
1485 | 690038 | (IETF) RTP Payload Format for Non-Interleaved and Interleaved Parity Forward Error Correction (FEC) (draft-ietf-payload-flexible-fec-scheme) | VTRI_EXT | 2 | Rel-13 | S4-IETF | 2014-12-12 08:00 | 2015-09-11 17:00 | 10% | SP-15047 |  | Muhammed Coban, Qualcomm Incorporated | mcoban@qti.qualcomm.com | 26.114, draft-ietf-payload-flexible-fec-scheme. 7/10/15: rapporteur added | 26.114, draft-ietf-payload-flexible-fec-scheme | 69 | 35 |  |  | Tue 03/03/15 | Wed 07/10/15
1486 | 660052 | Acoustic Test methods and Performance Objectives for Speakerphone Performance in Noisy Environments | ATeMPO_SPINE | 1 | Rel-13 | S4 | 2014-12-12 08:00 | 2016-03-11 17:00 | 100% | SP-140740 |  | Andre Schevciw, Qualcomm Incorporated; Scott Isabelle, Audience Inc. | aschevci@qti.qualcomm.com; sisabelle@audience.com | June2015: Compl:0%->10. Aug: FCD: Jun->Sep15; 07/09/15: 10%->30, FCD:09/15->12/15; 7/12/15: 40%->80, FCD: 12/15->03/16. ES in SP-150642; 7/3/16: 80%->100 | 26.131, 26.132 | 66 | 34 |  |  | Fri 12/12/14 | Mon 07/03/16
1487 | 630010 | Rel-13 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM13 | 1 | Rel-13 | S5 | 2012-06-20 08:00 | 2016-03-11 17:00 | 100% | SP-150305 | - | - | - | OAM13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI; June2015: WID:-->SP-150305; 5/10/15: 28.683 added; | 28.683 | 63 | 32 |  |  | Thu 27/02/14 | Mon 05/10/15
1488 | 560132 | Enhanced Network Management (NM) centralized Coverage and Capacity Optimization | SON-NM-CCO | 2 | Rel-13 | S5 | 2014-09-19 08:00 | 2015-12-11 17:00 | 100% | SP-140060 | - | Ericsson | robert.petersen@ericsson.com | SP#64 work not started. Dec.14: 0->20, cd: 06/15->12/15. Mar 15: 20->30%; June2015: Compl:30%->50; 07/09/15: 50%->60; 7/12/15: 60%->100 | 28.627, 28.628, 32.103, 32.422, 32.425, 32.442 | 56 | 29 |  |  | Wed 18/04/12 | Mon 07/12/15
1489 | 560034 | Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | OAM-NGMN_OPE | 2 | Rel-13 | S5 | 2012-06-20 08:00 | 2015-03-18 17:00 | 100% | SP-140538 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13. Source of external requirements: NGMN Top OPE Recommendations 1.0 | - | 56 | 29 |  |  | Mon 14/05/12 | Mon 01/09/14
1490 | 560134 | TR on Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | OAM-NGMN_OPE | 3 | Rel-13 | S5 | 2012-06-20 08:00 | 2015-03-18 17:00 | 100% | SP-140538 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13.. Dec.14: 72->78. Mar 15: 80%; June2015: Compl:80%->85; 07/09/15: 85%->90; 7/12/15: 90%->100 | New TR 32.838 | 56 | 29 |  |  | Mon 14/05/12 | Mon 07/12/15
1491 | 560234 | TS work on Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations | OAM-NGMN_OPE | 3 | Rel-13 | S5 | 2012-06-25 08:00 | 2015-03-18 17:00 | 100% | SP-140538 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13; 7/12/15: 50%->100 | 32.101/2/3,32.111-1,32.111-2,32.111-6,32.15x,32.401,32.411,32.412,32.421,32.422,32.423,32.431,32.432,32.436,32.441,32.442,32.446,32.500,32.501,32.502,32.506,32.521,32.522,32.526,32.531,32.532,32.536,32.551,32.691,32.692,32.696,32.762 | 56 | 29 |  |  | Mon 14/05/12 | Mon 07/12/15
1492 | 560235 | Converged management Performance Management Interface Definitions | OAM-PMID | 2 | Rel-13 | S5 | 2012-06-20 08:00 | 2015-12-11 17:00 | 100% | SP-150678 | - | Huawei | christian.toche@huawei.com | SP#65 updated WID SP-130641=>SP-140613. Completion 09/14=>12/15. Moved to Rel-13. Completion 09/14=>12/15. Dec.14: 20->30; June2015: Compl:30%->60; 07/09/15: 60%->80; 7/12/15: 80%->100; 7/12/15: WID:SP-140613->SP-150678 | new TSs 32.863 | 56 | 29 |  |  | Mon 14/05/12 | Mon 07/12/15
1493 | 560036 | WLAN Management | WLAN-OAM | 2 | Rel-13 | S5 | 2012-06-27 08:00 | 2015-06-17 17:00 | 100% | SP-140535 | - | Intel | joey.chou@intel.com | SP#65 moved to Rel-13. Updated WID SP-130042=>SP-140535 (split into Rel-12 Study & Rel-13 normative WI). TR 32.841 was completed as a Rel-12 Study and has triggered this normative work | - | 56 | 29 |  |  | Tue 12/06/12 | Wed 10/09/14
1494 | 560136 | WLAN Network Resource Model for Type-2 interface | WLAN-OAM-SA5 | 3 | Rel-13 | S5 | 2012-06-27 08:00 | 2015-06-17 17:00 | 100% | SP-140535 | - | Intel | joey.chou@intel.com | SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13. Dec.14: 10->20; June2015: Compl:20%->70; 07/09/15: 70%->80; 7/12/15: 80%->100 | new TS (28.680, 28.682), 28.681 | 56 | 29 |  |  | Tue 12/06/12 | Mon 07/12/15
1495 | 560236 | WLAN measurements defined in IEEE and IETF WLAN performance measurements for use on Type-2 interface | WLAN-OAM-SA5ietf | 3 | Rel-13 | S5 | 2012-06-27 08:00 | 2015-06-17 17:00 | 100% | SP-140535 | - | Intel | joey.chou@intel.com | SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13. 22/01:Acronym modified; June2015: Compl:5%->20; 07/09/15: 20%->60; 7/12/15: 60%->100 | new TS 28.403 | 56 | 29 |  |  | Tue 12/06/12 | Mon 07/12/15
1496 | 600044 | Energy Efficiency related Performance Measurements | OAM-PM_EE | 2 | Rel-13 | S5 | 2013-06-21 08:00 | 2016-03-11 17:00 | 100% | SP-140612 | - | Nokia Networks | Yizhi.yao@nsn.com | SP#65 updated WID SP-130263=>SP-140612. Completion 09/14=>06/15. Moved to Rel-13; June2015: Compl:25%->40; 07/09/15: 40%->50. ES in SP-150708; 7/3/16: 50%->100 | 32.425 | 60 | 31 |  |  | Sun 02/06/13 | Mon 07/03/16
1497 | 660055 | Multi-Broadcast Single Frequency Network (MBSFN) Minimization of Drive Tests (MDT) enhancement | MBSFN_MDT | 2 | Rel-13 | S5 | 2014-12-12 08:00 | 2014-12-12 17:00 | 100% | SP-140786 |  | Padma Sudarsan (Alcatel-Lucent) | padma.sudarsan<AT>alcatel-lucent<DOT>com | Mar 15: 0->15%; June2015: Compl:15%->100 | 32.421, 32.422, 32.423, 32.441, 32.442, 32.446 | 66 | 34 |  |  | Fri 12/12/14 | Mon 15/06/15
1498 | 641000 | Rel-13 Charging | CH13 | 1 | Rel-13 | S5 | 2014-06-19 08:00 | 2015-12-16 17:00 | 100% | SP-150307 | - | - | - | CH13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI; June2015: WID:-->SP-150307 | - | 64 | 33 |  |  | Fri 06/06/14 | Thu 18/06/15
1499 | 640059 | Inter-PLMN PS domain online charging | iPLMN-PS-OCH | 2 | Rel-13 | S5 | 2014-06-19 08:00 | 2015-12-16 17:00 | 100% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Study and specify Gy Reference Point “service data flows based online charging” for inter-PLMN situations | Stage 2/3 | 64 | 33 |  |  | Fri 06/06/14 | Fri 06/06/14
1500 | 640159 | TR on Inter-PLMN PS domain online charging | iPLMN-PS-OCH | 3 | Rel-13 | S5 | 2014-06-19 08:00 | 2015-06-17 17:00 | 100% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Dec.14: 10->25%. Mar15: 20->60%. 06/15: 100%; 7/12/15: 100%->100 | New TR 32.843 | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/12/15
1501 | 640259 | Specification of Inter-PLMN PS domain online charging | iPLMN-PS-OCH | 3 | Rel-13 | S5 | 2014-06-23 08:00 | 2015-12-16 17:00 | 100% | SP-140324 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | 07/09/15: 0%->80; 7/12/15: 80%->100 | 32.251, 32.299 | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/12/15
1502 | 660056 | ULI and release causes for charging enhancement for VoLTE | ULRELC-CH | 2 | Rel-13 | S5 | 2014-12-12 08:00 | 2015-12-07 17:00 | 100% | SP-140785 |  | Alcatel-Lucent, Maryse Gardella | Alcatel-Lucent, Maryse <dot> Gardella <at> Alcatel-Lucent <dot> com | Acronym changed to ULRELC-CH. Mar15: 0->5%. CD: 12/14->09/15. 06/15: 20%; 07/09/15: 20%->40; 7/12/15: 40%->100, FCD: 09/15->12/15 | 32.251, 32.260, 32.299, 32.298, | 66 | 34 |  |  | Fri 12/12/14 | Mon 07/12/15
1503 | 670025 | Charging on enhancements for IMS Service Continuity | CHeISC | 2 | Rel-13 | S5 | 2015-03-05 08:00 | 2015-09-09 17:00 | 100% | SP-150055 |  | Gerald Goermer | Gerald <dot> Goermer <at> nsn <dot> com | 06/15: 0->50%; 07/09/15: 50%->100. FCD: 12/15->09/15 | 32.260, 32.299, 32.298 | 67 | 34 |  |  | Thu 05/03/15 | Mon 07/09/15
1504 | 680037 | Announcements for IMS Online Charging | ANIMO | 2 | Rel-13 | S5 | 2015-06-15 08:00 | 2015-12-14 17:00 | 100% | SP-150675 |  | Amdocs, Naceur <dot> Lagha <at> Amdocs <dot> com |  | 07/09/15: 0%->30; 7/12/15: 30%->100; 7/12/15: WID:SP-150307->SP-150675 | 32.260, 32.275, 32.299, 32.240, 32.281 | 68 | 35 |  |  | Sun 14/06/15 | Mon 07/12/15
1505 | 680038 | Enhanced S2a Mobility Over Trusted WLAN access to EPC - Charging | eSaMOG-CH | 2 | Rel-13 | S5 | 2015-06-15 08:00 | 2015-09-17 12:00 | 100% | SP-150344 |  | Alcatel-Lucent, Maryse <dot> Gardella <at> Alcatel-Lucent <dot> com |  | 07/09/15: 0%->30; 7/12/15: 30%->100 | 32.240, 32.251, 32.299, 32.298 | 68 | 35 |  |  | Sun 14/06/15 | Mon 07/12/15
1506 | 610005 | Support of Real-time Transport Protocol (RTP) / Real-time Transport Control Protocol (RTCP) multiplexing (signalling) in IMS | RTCP_MUX | 1 | Rel-13 | C4,C1,C3 | 2013-09-09 08:00 | 2015-12-11 17:00 | 100% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Stage 2/3 | Stage 2/3 | 61 | 31 |  |  | Sat 10/08/13 | Wed 03/09/14
1507 | 610105 | CT4 part of Support of RTP / RTCP multiplexing (signalling) in IMS | RTCP_MUX | 2 | Rel-13 | C4 | 2013-09-09 08:00 | 2015-12-11 17:00 | 100% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Completion 09/14=>12/15. Dec.14: 10->100 | 23.334, 29.334 | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
1508 | 610205 | CT1 part of Support of RTP / RTCP multiplexing (signalling) in IMS | RTCP_MUX | 2 | Rel-13 | C1 | 2013-09-13 08:00 | 2015-12-11 17:00 | 100% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Completion 09/14=>12/15; 7/12/15: 0%->100 | 24.229 | 61 | 31 |  |  | Sat 10/08/13 | Mon 07/12/15
1509 | 610305 | CT3 part of Support of RTP / RTCP multiplexing (signalling) in IMS | RTCP_MUX | 2 | Rel-13 | C3 | 2013-09-13 08:00 | 2015-12-11 17:00 | 100% | CP-130436 | - | Alcatel-Lucent | Albrecht.Schwarz@alcatel-lucent.com | CP#65 moved to Rel-13. Completion 09/14=>12/15; 8/12/15: 0%->100 | 29.213, 29.214 | 61 | 31 |  |  | Sat 10/08/13 | Tue 08/12/15
1510 | 550017 | LTE in the 1670-1675 MHz Band for US (on hold till 12/2014) | LTE_FDD_1670_US | 1 | Rel-13 | R4,R2,R3 | 2012-03-05 08:00 | 2015-06-09 17:00 | 8% | RP-121397 | - | LightSquared | masoud.olfat@lightsquared.com | RP#65 FS_LTE_FDD_1670_US is extended to 12/14 and this WI (LTE_FDD_1670_US) is on hold till 12/14 | LTE | 55 | 28 |  |  | Thu 23/02/12 | Tue 09/09/14
1511 | 550117 | Core part: LTE in the 1670-1675 MHz Band for US (on hold till 12/2014) | LTE_FDD_1670_US-Core | 2 | Rel-13 | R4,R2,R3 | 2013-08-06 14:12 | 2015-03-10 17:00 | 15% | RP-121397 | RP-141452 | LightSquared | masoud.olfat@lightsquared.com | RP#65 completion 03/15=>06/15. On hold till 12/2014 | 25.101, 25.104, 25.113, 25.133, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, new TR 36.832 | 55 | 28 |  |  | Thu 23/02/12 | Tue 09/09/14
1512 | 550217 | Perf. Part: LTE in the 1670-1675 MHz Band for US (on hold till 12/2014) | LTE_FDD_1670_US-Perf | 2 | Rel-13 | R4 | 2012-03-05 08:00 | 2015-06-09 17:00 | 5% | RP-121397 | RP-141452 | LightSquared | masoud.olfat@lightsquared.com | RP#65 completion 06/15=>09/15. . On hold till 12/2014 | 25.133, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.113, 36.124, 36.133, 36.141, 36.307 | 55 | 28 |  |  | Thu 23/02/12 | Tue 09/09/14
1513 | 640019 | Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB_sig | 1 | Rel-13 | R3 | 2014-06-18 08:00 | 2015-09-15 17:00 | 100% | RP-141032 | - | Samsung | sunghwan.won@samsung.com | Triggered by TR 36.874 Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul (UID_600015) | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 23/06/14
1514 | 640119 | Core part: Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB_sig-Core | 2 | Rel-13 | R3 | 2014-06-18 08:00 | 2015-09-15 17:00 | 100% | RP-141032 | RP-151213 | Samsung | sunghwan.won@samsung.com | CD:Thu 11/12/14->Mon 15/06/15; Compl:0%->15%; Stat Rep: -->RP-141805 1st Apr 15: Compl:15%->30% 1st Apr 15: Stat Rep: RP-141805->RP-150162 03/07/15: Compl:30%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150162->RP-150846 29/09/1 | 36.300, 36.423 | 64 | 33 |  |  | Mon 16/06/14 | Tue 29/09/15
1515 | 640036 | 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | LTE_1980_2170_REG1 | 1 | Rel-13 | R4 | 2014-06-17 08:00 | 2016-09-15 17:00 | 100% | RP-141710 | - | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | Triggered by TR 37.846 Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) FS_UTRA_LTE_1980_2170_REG1 | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1516 | 640136 | Core part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | LTE_1980_2170_REG1-Core | 2 | Rel-13 | R4 | 2014-06-17 08:00 | 2015-12-15 17:00 | 100% | RP-151732 | RP-151299 | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | CD:Fri 12/06/15->Mon 15/06/15; Compl:5%->15%; Stat Rep: RP-141627->RP-141795 1st Apr 15: Compl:15%->35% 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: Compl:35%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03 | 36.101, 36.104, 36.133, 36.141, 36.307, generic TR 36.853 (3 Band CA with 1UL), New TR 36.862 (Technical Report for 2 GHz Band in Region 1) | 64 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
1517 | 640236 | Perf. Part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | LTE_1980_2170_REG1-Perf | 2 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-12-15 17:00 | 100% | RP-151732 | RP-151299 | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | CD:Fri 12/06/15->Mon 15/06/15; Compl:0%->0%; Stat Rep: RP-141627->RP-141795 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150106->RP-150705 29/09/15: Stat | 36.101, 36.104, 36.133, 36.141, 36.307, 36.862 | 64 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
1518 | 710066 | UE Conformance Test Aspects - FDD LTE band 1980-2010 MHz and 2170-2200MHz (band 65) in Region1 and Region 3 | LTE_1980_2170_REG1_REG3-UEConTest | 2 | Rel-13 | R5 | 2016-03-15 08:00 | 2016-09-15 17:00 | 100% | RP-160774 | - | Dish Network |  | testing REL-13 LTE_1980_2170_REG1-Core and LTE_1980_2170_REG3-Core; |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
1519 | 650034 | Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments | UTRA_LTE_SON_AAS | 1 | Rel-13 | R3,G2 | 2014-09-12 08:00 | 2015-06-15 17:00 | 100% | RP-141624 | - | Nokia Networks | krzysztof.kordybach@nsn.com | Triggered by TR 37.822 Study on Next-Generation SON for UTRA and LTE (FS_UTRA_LTE_NG_SON) | LTE | 65 | 33 |  |  | Mon 16/06/14 | Tue 16/09/14
1520 | 650134 | Core part: Self Organizing Networks (SON) for Active Antenna System (AAS) based deployments | UTRA_LTE_SON_AAS-Core | 2 | Rel-13 | R3 | 2014-09-12 08:00 | 2015-06-15 17:00 | 100% | RP-141624 | RP-150727 | Nokia Networks | krzysztof.kordybach@nsn.com | CD:Tue 16/06/15->Mon 15/06/15; Compl:0%->15%; Stat Rep: -->RP-141854 1st Apr 15: Compl:15%->25% 1st Apr 15: Stat Rep: RP-141854->RP-150110 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150110->RP-150727 | 36.300, 36.423, 36.413, 25.413 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1521 | 660001 | Usage Monitoring Control PCC Extension | eUMONC | 1 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 100% | SP-140709 |  | CTBRI |  |  |  | 66 | 34 |  |  | Wed 03/12/14 | Wed 03/12/14
1522 | 660022 | Stage 2 of Usage Monitoring Control PCC Extension | eUMONC-SA2 | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 100% | SP-140709 |  | China Telecom, Jinyan Li | lijy@ctbri.com.cn | June2015: Compl:6%->100. Verbal indication from SA2 chair | 23.203 | 66 | 34 |  |  | Wed 03/12/14 | Mon 15/06/15
1523 | 660020 | CT3 Aspect of Usage Monitoring Control extension | eUMONC-CT3 | 2 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 100% | CP-140927 |  | ZTE |  | Mar.15: 10->100% | 29.212, 29.215 | 66 | 34 |  |  | Thu 04/12/14 | Wed 04/03/15
1524 | 660030 | Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLAN | 1 | Rel-13 | C1 | 2014-10-06 08:00 | 2015-03-13 17:00 | 100% | CP-140813 |  | Ericsson |  |  |  | 66 | 34 |  |  | Thu 04/12/14 | Tue 09/12/14
1525 | 660014 | CT1 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLAN | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-03-13 17:00 | 100% | CP-140813 |  | Ericsson |  | . 12/12:0->100%. 5/5/15: acronym changed from ePCSCF_WLAN-CT1 to ePCSCF_WLAN | 24.229, 24.302 | 66 | 34 |  |  | Thu 04/12/14 | Tue 05/05/15
1526 | 660023 | CT4 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLAN | 2 | Rel-13 | C4 | 2014-10-06 08:00 | 2015-03-13 17:00 | 100% | CP-140813 |  | Ericsson |  | Mar.15: 0->100%. 5/5/15: acronym changed from ePCSCF_WLAN-CT1 to ePCSCF_WLAN | 29.274, 29.275 | 66 | 34 |  |  | Thu 04/12/14 | Tue 05/05/15
1527 | 660028 | P-CSCF Restoration Enhancements with WLAN | PCSCF_RES_WLAN | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-12-14 08:24 | 100% | CP-150275 |  | Jean-Jacques Trottin, Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | WID added, acronym. June 2015: WID: CP-140995-> CP-150275 |  | 66 | 34 |  |  | Thu 04/12/14 | Tue 09/12/14
1528 | 660041 | CT1 aspects of P-CSCF Restoration Enhancements with WLAN | PCSCF_RES_WLAN | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-12-14 08:24 | 100% | CP-150275 |  | Jean-Jacques Trottin, Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CT4->CT1. 2/4/15: acronym changed to PCSCF_RES_WLAN; June2015: Compl:0%->10. June 2015: WID: CP-140995-> CP-150275; 07/09/15: 10%->70; 7/12/15: 70%->100 | 24.302, 24.229, 24.244, 24.008 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/12/15
1529 | 660040 | CT4 aspects of P-CSCF Restoration Enhancements with WLAN | PCSCF_RES_WLAN | 2 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-12-11 17:00 | 100% | CP-150275 |  | Jean-Jacques Trottin, Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | Dec.14: 0->5%. Mar.15: 5->100%. 2/4/15: acronym changed to PCSCF_RES_WLAN; June2015: Compl:100%->75. June 2015: WID: CP-140995-> CP-150275; 07/09/15: 75%->85; 7/12/15: 85%->100 | New 29.8xy, 23.380, 29.273, 29.274, 29.275, 23.008 | 66 | 34 |  |  | Tue 09/12/14 | Mon 07/12/15
1530 | 680012 | Mobile Equipment Identity signalling over WLAN | MEI_WLAN | 1 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-09-17 17:00 | 100% | CP-150236 |  | Bruno Landais, Alcatel-Lucent | bruno.landais@alcatel-lucent.com |  | 24.244, 24.302, 29.273, 29.274, 29.275, 23.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
1531 | 680039 | CT1 aspects of Mobile Equipment Identity signalling over WLAN | MEI_WLAN | 2 | Rel-13 | C1 | 2015-06-15 08:00 | 2015-09-17 17:00 | 100% | CP-150236 |  | Bruno Landais, Alcatel-Lucent | bruno.landais@alcatel-lucent.com | 07/09/15: 0%->80; 7/12/15: 80%->100 | 24.244, 24.302 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1532 | 680040 | CT4 aspects of Mobile Equipment Identity signalling over WLAN | MEI_WLAN | 2 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-09-17 17:00 | 100% | CP-150236 |  | Bruno Landais, Alcatel-Lucent | bruno.landais@alcatel-lucent.com | 07/09/15: 0%->90; 7/12/15: 90%->100 | 29.273, 29.274, 29.275, 23.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1533 | 680041 | Authentication Signalling Improvements for WLAN | ASI_WLAN | 1 | Rel-13 | C1 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150330 |  | Youyang Yu | yuyouyang@huawei.com | 07/09/15: 0%->40; 7/12/15: 40%->95. FCD -> 03/16, ES in CP-150727; 7/3/16: 95%->100 | 24.302, 24.244 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
1534 | 660016 | Stage-3 SAE Protocol Development - Phase 4 | SAES4 | 1 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-12-11 17:00 | 100% | CP-140814 |  | interdigital |  | WP Structure created 24/03/15 to avoid confusion in Acronyms | 23.12, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 66 | 34 |  |  | Thu 04/12/14 | Tue 24/03/15
1535 | 670037 | SAE Protocol Development (Stage 3) - Phase 4 | SAES4 | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-12-11 17:00 | 100% | CP-140814 |  | interdigital |  | WP Structure created 24/03/15 to avoid confusion in Acronyms. 5/5/15: acronym changed from "SAES4-CT1"; June2015: Compl:0%->30; 07/09/15: 30%->70; 7/12/15: 70%->100 |  | 66 | 34 |  |  | Tue 24/03/15 | Mon 07/12/15
1536 | 670038 | CS Fallback in EPS - Phase 4 | SAES4-CSFB | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-12-11 17:00 | 100% | CP-140814 |  | interdigital |  | WP Structure created 24/03/15 to avoid confusion in Acronyms; June2015: Compl:0%->30; 07/09/15: 30%->70; 7/12/15: 70%->100 |  | 66 | 34 |  |  | Tue 24/03/15 | Mon 07/12/15
1537 | 670039 | SAE for support for non-3GPP accesses - Phase 4 | SAES4-non3GPP | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-12-11 17:00 | 100% | CP-140814 |  | interdigital |  | WP Structure created 24/03/15 to avoid confusion in Acronyms; June2015: Compl:0%->30; 07/09/15: 30%->50; 7/12/15: 50%->100 |  | 66 | 34 |  |  | Tue 24/03/15 | Mon 07/12/15
1538 | 660034 | Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 1 | Rel-13 | C1,C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 74% | CP-140928 |  | Orange |  |  |  | 66 | 34 |  |  | Thu 04/12/14 | Tue 09/12/14
1539 | 660134 | Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-03-13 17:00 | 100% |  |  | Orange |  | 5/5/15: created; June2015: Compl:0%->70; 07/09/15: 70%->100 | 24.229 | 66 | 34 |  |  | Tue 05/05/15 | Mon 07/09/15
1540 | 660036 | (IETF) CT1 part of Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 2 | Rel-13 | C1-IETF | 2014-12-03 08:00 | 2015-03-10 17:00 | 0% | CP-140928 |  | Orange |  | Mar15: resp WG:C1->C1-IETF. WID changed from INNB_IW-CT1 | draft-mohali-dispatch-cause-for-service-number | 66 | 34 |  |  | Thu 04/12/14 | Wed 18/03/15
1541 | 660021 | CT3 aspects of Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 2 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 100% | CP-140928 |  | Orange |  | Mar.15: 80->90%. WID changed from INNB_IW-CT3; June2015: Compl:0%->98; 07/09/15: 98%->99; 7/12/15: 99%->100 |  | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
1542 | 660042 | Warning Status Report in EPS | WSR_EPS | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-09-14 17:00 | 100% | CP-150792 |  | one2many |  | 5/5/15: acronym changed from "WSR_EP"; 7/12/15: WID:CP-140998->CP-150792 |  | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
1543 | 660015 | CT1 aspects of Warning Status Report in EPS | WSR_EPS | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-09-14 17:00 | 100% | CP-150792 |  | one2many |  | 2/4/15: acronym changed to WSR_EP. 5/5/15: acronym changed from "WSR_EP"; 07/09/15: 0%->25; 7/12/15: 25%->100; 7/12/15: WID:CP-140998->CP-150792 | New TR 23.712 | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
1544 | 660029 | CT4 aspects of Warning Status Report in EPS | WSR_EPS | 2 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-09-14 17:00 | 100% | CP-150792 |  | one2many |  | 2/4/15: acronym changed to WSR_EP. 5/5/15: acronym changed from "WSR_EP"; 7/12/15: 0%->100; 7/12/15: WID:CP-140998->CP-150792 |  | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
1545 | 660026 | Shared Data Update for Multiple Subscriber | SHARED_SubData_UPD | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2014-12-03 17:00 | 100% | CP-150013 |  | Huawei, Susan Shi | susan.shishufeng@huawei.com | Mar.15: 0->50%, WID: CP-140804->CP-150013; June2015: Compl:50%->95; 07/09/15: 95%->100 | 29.328, 29.364 | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/09/15
1546 | 660017 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc7 | 1 | Rel-13 | C1 | 2014-12-03 08:00 | 2017-06-20 17:00 | 70% | CP-140815 |  | Alcatel-Lucent | Keith Drage | Mar.15: 0->10% | 23.218, 24.998, 24.930 | 66 | 34 |  |  | Thu 04/12/14 | Wed 04/03/15
1547 | 670096 | CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc7 | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-12-11 17:00 | 100% | CP-140815 |  | Alcatel-Lucent | Keith Drage | Mar.15: 0->10%; June2015: Compl:10%->30; 07/09/15: 30%->70; 7/12/15: 70%->100 |  | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
1548 | 720059 | (IETF) CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc7 | 2 | Rel-13 | C1 | 2016-06-13 08:00 | 2017-06-20 17:00 | 10% | CP-140815 |  | Alcatel-Lucent | Keith Drage |  | draft-ietf-mmusic-dtls-sdp, draft-ietf-mmusic-4572-update | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
1549 | 670097 | CT3 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc7 | 2 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-12-11 17:00 | 100% | CP-140815 |  | Alcatel-Lucent | Keith Drage | 2/4/15: added, following CT3 chair's info that the WID also has a CT3 part; June2015: Compl:0%->20; 07/09/15: 20%->40; 7/12/15: 40%->100 |  | 67 | 34 |  |  | Thu 02/04/15 | Mon 07/12/15
1550 | 670013 | Retry restriction for Improving System Efficiency | RISE | 1 | Rel-13 | C1 | 2015-03-04 08:00 | 2015-12-15 17:00 | 100% | CP-150495 |  | Huawei, Lin Shu | shulin@huawei.com | Continuation of Rel-12 SINE UID 620006. 5/5/15: acronym changed from "RISE"; June2015: Compl:0%->10; 07/09/15: 10%->70; 14/09/15: WID:CP-150092->CP-150495; 7/12/15: 70%->100 |  | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/12/15
1551 | 670020 | H.248 Aspects of WebRTC Data Channel on IMS Access Gateway | WebRTCH248DC | 1 | Rel-13 | C4 | 2015-03-04 08:00 | 2016-03-11 17:00 | 100% | CP-150185 |  | China Mobile, Xiaoning Du | duxiaoning@chinamobile.com |  | 23.334 | 67 | 34 |  |  | Wed 04/03/15 | Mon 09/03/15
1552 | 670001 | CT4 Aspect of H.248 Aspects of WebRTC Data Channel on IMS Access Gateway | WebRTCH248DC | 2 | Rel-13 | C4 | 2015-03-04 08:00 | 2016-03-11 17:00 | 100% | CP-150185 |  | China Mobile, Xiaoning Du. ES in 639 | duxiaoning@chinamobile.com | June2015: Compl:0%->10; 07/09/15: 10%->20; 7/12/15: 20%->90; 7/3/16: 90%->100 | 23.334 | 67 | 34 |  |  | Wed 04/03/15 | Mon 07/03/16
1553 | 670021 | Continuation of the Overload Control for PCC based Diameter applications | cDOCME_PCC | 1 | Rel-13 | C3 | 2015-03-04 08:00 | 2015-12-11 17:00 | 100% | CP-150194 |  | ZTE, Zhou Xiaoyun | zhou.xiaoyun@zte.com.cn | Relates to UID 580026 (Study on Diameter overload control mechanism); June2015: Compl:0%->100 | 29.212, 29.215, 29.219, 29.217 | 67 | 34 |  |  | Wed 04/03/15 | Mon 15/06/15
1554 | 670026 | Review of dedicated 3GPP UICC features | Red_UCe | 1 | Rel-13 | C6 | 2015-03-09 08:00 | 2015-12-11 17:00 | 100% | CP-150152 |  | Blackberry, Adrian Buckley | abuckley@blackberry.com | Results from the homonymous Study; June2015: Compl:0%->60; 07/09/15: 60%->75; 7/3/16: 75%->100 | 31.102, 31.111, 31.121, 31.124 | 67 | 34 |  |  | Mon 09/03/15 | Mon 07/03/16
1555 | 680014 | Controlling IMS Media Plane with SDP Capability | SDPCN_IMS | 1 | Rel-13 | C4 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150238 |  | Weiwei(Tommy) Yang, Huawei. ES in 640 | tommy@huawei.com |  | 23.334, 29.334, 29.162, 29.238, 23.333, 29.333, 29.163, 29.332, 29.292, 29.232, 29.235 | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
1556 | 680042 | CT3 aspects of Controlling IMS Media Plane with SDP Capability | SDPCN_IMS | 2 | Rel-13 | C3 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150238 |  | Weiwei(Tommy) Yang, Huawei. ES in 640 | tommy@huawei.com | 7/12/15: 0%->90. FCD->03/16. ES in CP-150614; 7/3/16: 90%->100 | 29.162, 29.163, 29.292, 29.235 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
1557 | 680043 | CT4 aspects of Controlling IMS Media Plane with SDP Capability | SDPCN_IMS | 2 | Rel-13 | C4 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150238 |  | Weiwei(Tommy) Yang, Huawei. ES in 640 | tommy@huawei.com | 07/09/15: 0%->5; 7/12/15: 5%->70. FCD->03/16. ES in CP-150614; 7/3/16: 70%->100 | 23.334, 29.334, 29.238, 23.333, 29.333, 29.332, 29.232 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
1558 | 640044 | (SA66: on hold) Co-ordinated packet data network gateway (P-GW) change for SIPTO | CSIPTO | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-16 17:00 | 100% | SP-140509 | S1-143306 | Intel | Eric.siow@intel.com | SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO) | 22.101 | 64 | 33 |  |  | Tue 27/05/14 | Fri 12/12/14
1559 | 660012 | Stage 1 for Co-ordinated packet data network gateway (P-GW) change for SIPTO | CSIPTO-ST1 | 2 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-16 17:00 | 100% | SP-140509 | S1-143306 | Intel | Eric.siow@intel.com | SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO). Dec.14: former S1-only feature split | 22.101 | 64 | 33 |  |  | Tue 27/05/14 | Wed 03/12/14
1560 | 640051 | Enhanced CS Fallback (CSFB) | eCSFB | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2015-03-13 17:00 | 100% | SP-140579 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579 (added SA3 part). Linked to Rel-8 WIs Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC) and CS Fallback in EPS (SAES-CSFB) | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Fri 12/12/14
1561 | 640151 | TR for Enhanced CS Fallback (CSFB) | eCSFB | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2014-12-12 17:00 | 100% | SP-140579 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579 (added SA3 part). Dec.14: 35->85%; 14/09/15: 85%->100. SA#69: decision not to continue the work on this. No normative work. | New TR 23.772 | 64 | 33 |  |  | Wed 11/06/14 | Mon 14/09/15
1562 | 640251 | Deleted - Stage 2 for Enhanced CS Fallback (CSFB) | eCSFB | 2 | Rel-13 | S2 | 2015-03-13 17:00 | 2015-03-13 17:00 | 100% | SP-140579 | - | China Unicom | Yang Xu (xuyang49@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579 (added SA3 part) | 23.272 | 64 | 33 | SP-69 |  | Wed 11/06/14 | Wed 11/06/14
1563 | 650024 | Deleted - Security for Enhanced CS Fallback (CSFB) | eCSFB | 2 | Rel-13 | S3 | 2014-09-18 08:00 | 2014-09-18 17:00 | 100% | SP-140579 | - | China Unicom | Feng Gao (gaofeng149@chinaunicom.cn) | SP#65 updated ID SP-140285=>SP-140579; 14/09/15: 0%->100. SA#69: deleted, since SA2 has stopped the work. |  | 65 | 33 | SP-69 |  | Mon 15/09/14 | Mon 14/09/15
1564 | 650025 | SRVCC Enhancements for Transcoding Avoidance | SETA | 1 | Rel-13 | S2 | 2014-09-19 08:00 | 2015-06-17 17:00 | 100% | SP-140436 | - | Ericsson | George.Foti@ericsson.com | Enhance chances for end-to-end transcoder free operation (TrFo) where possible/ ensure proper CS radio resources are reserved for optimal RAN codec. Address TrFo of EVS codecs during SRVCC that are not covered by Rel-12 | Stage 2 | 65 | 33 |  |  | Tue 05/08/14 | Fri 12/12/14
1565 | 650125 | TR for SRVCC Enhancements for Transcoding Avoidance | SETA-SA2TR | 2 | Rel-13 | S2 | 2014-09-19 08:00 | 2015-03-13 17:00 | 100% | SP-140436 | - | Ericsson | George.Foti@ericsson.com | Dec.14: 0->70%; 14/09/15: 70%->100. Stopped without conclusion, no intention to continue the study nor to do any mormative work. | New TR 23.7xy | 65 | 33 |  |  | Tue 05/08/14 | Mon 14/09/15
1566 | 650225 | Deleted - Stage 2 for SRVCC Enhancements for Transcoding Avoidance | SETA-SA2 | 2 | Rel-13 | S2 | 2015-06-17 17:00 | 2015-06-17 17:00 | 100% | SP-140436 | - | Ericsson | George.Foti@ericsson.com | SA#69: stop the work on this. | 23.216, 23.237 | 65 | 33 | SP-69 |  | Tue 05/08/14 | Wed 16/09/15
1567 | 590030 | Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA | 1 | Rel-13 | R4 | 2013-03-04 08:00 | 2016-09-15 17:00 | 100% | RP-130373 | - | Huawei | ronnie.zhang@huawei.com | Triggered by Rel-12 TR 37.840 Study of RF and EMC Requirements for Active Antenna Array System BS (FS_AAS_BS_LTE_UTRA) | UTRA, LTE, GERAN | 59 | 30 |  |  | Tue 26/02/13 | Mon 15/09/14
1568 | 590130 | Core part: Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA-Core | 2 | Rel-13 | R4 | 2013-03-04 08:00 | 2016-03-15 17:00 | 100% | RP-160188 | RP-151241 | Huawei | ronnie.zhang@huawei.com | ; CD:Thu 11/12/14->Tue 15/12/15; WID: RP-141966->RP-142235; Stat Rep: RP-141249->RP-141908; Release: Rel-12->Rel-13 03/07/15: Stat Rep: RP-141908->RP-150687 29/09/15: Compl:75%->80% 29/09/15: Stat Rep: RP-150687->RP-151241; | New TS 37.142 (AAS BS Tx & Rx), New TR 37.842, 37.114, 37.145-1, 37.145-2 | 59 | 30 |  |  | Tue 26/02/13 | Tue 22/03/16
1569 | 590230 | Perf. part: Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA-Perf | 2 | Rel-13 | R4 | 2013-03-15 | 2016-09-15 17:00 | 100% | RP-160188 | RP-151241 | Huawei | ronnie.zhang@huawei.com | ; CD:Sat 18/06/16->Wed 15/06/16; WID: RP-141966->RP-142235; Stat Rep: RP-141249->RP-141908; Release: Rel-12->Rel-13 03/07/15: Stat Rep: RP-141908->RP-150687 29/09/15: Stat Rep: RP-150687->RP-151241 22/3/16: Compl:2 26/9/16: Compl:95%->100% | New TS 37.1xy (AAS BS conformance testing) | 59 | 30 |  |  | Tue 26/02/13 | Mon 26/09/16
1570 | 660074 | Enhanced LTE Device to Device Proximity Services | LTE_eD2D_Prox | 1 | Rel-13 | R2 | 2014-12-15 08:00 | 2016-09-15 17:00 | 100% | RP-142311 |  | Qualcomm | Qualcomm |  |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 15/01/15
1571 | 660174 | Core part: Enhanced LTE Device to Device Proximity Services | LTE_eD2D_Prox-Core | 2 | Rel-13 | R2,R1,R3 | 2015-08-14 14:20 | 2016-03-15 17:00 | 100% | RP-150441 | RP-151337 | Qualcomm Incorporated, Shailesh Patil | patil@qti.qualcomm.com | Rapporteur details and involved WGs updated 1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Compl:0%->32% 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Compl:32%->55% 29/09/15: Stat Rep: RP-150795->RP-151337; |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
1572 | 660274 | Perf. part: Enhanced LTE Device to Device Proximity Services | LTE_eD2D_Prox-Perf | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-09-15 17:00 | 100% | RP-150441 | RP-151337 | Qualcomm | Qualcomm | 1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Stat Rep: RP-150795->RP-151337; 1/1/16: CD; 22/3/16: Compl:0%->10%;26/9/16: Compl:85%->100% |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 26/09/16
1573 | 660076 | Radiated requirements for the verification of multi-antenna reception performance of UEs | UTRA_LTE_MIMO_OTA | 1 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-142221 | RP-171826 | Intel | Intel |  |  | 66 | 34 |  |  | Thu 15/01/15 | Thu 15/01/15
1574 | 660176 | Core part: Radiated requirements for the verification of multi-antenna reception performance of UEs | UTRA_LTE_MIMO_OTA-Core | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-160344 | RP-151573 | Intel | Intel | 1st Apr 15: Compl:0%->5% 1st Apr 15: WID: RP-142221->RP-150261 1st Apr 15: Stat Rep: ->RP-150260 03/07/15: Compl:5%->15% 03/07/15: Stat Rep: RP-150260->RP-150746 29/09/15: Compl:15%->25% 29/09/15: WID: RP-150261->RP-151574 29/09/15: Stat Rep: RP-15074 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
1575 | 660077 | UE core requirements for uplink 64 QAM | LTE_UL64QAM | 1 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-142222 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Thu 15/01/15 | Thu 15/01/15
1576 | 660177 | Core part: UE core requirements for uplink 64 QAM | LTE_UL64QAM-Core | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-150691 | RP-151244 | Huawei | Huawei | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150232 03/07/15: Compl:10%->90% 03/07/15: WID: RP-142222->RP-150691 03/07/15: Stat Rep: RP-150232->RP-150688 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150688->RP-151244 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
1577 | 680069 | UE Conformance Test Aspects - Core Requirements for Uplink 64QAM for E-UTRA | LTE_UL64QAM-UEConTest | 1 | Rel-13 | R5 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150812 | RP-151174 | CMCC |  | tested Core part: LTE_UL64QAM-Core which is not yet completed 29/09/15: Compl:0%->5% 29/09/15: Stat Rep: -->RP-151174 1/1/16: Compl:5%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1578 | 660078 | Performance requirements of MMSE-IRC receiver for LTE BS | LTE_MMSE_IRC_BS | 1 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-142223 |  | China Telecom | China Telecom |  |  | 66 | 34 |  |  | Thu 15/01/15 | Thu 15/01/15
1579 | 660278 | Perf. part: Performance requirements of MMSE-IRC receiver for LTE BS | LTE_MMSE_IRC_BS-Perf | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-150206 | RP-151215 | China Telecom | China Telecom | 1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142223->RP-150206 1st Apr 15: Stat Rep: ->RP-150204 03/07/15: Compl:10%->35% 03/07/15: Stat Rep: RP-150204->RP-150630 29/09/15: Compl:35%->50% 29/09/15: Stat Rep: RP-150630->RP-151215; |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/07/16
1580 | 660079 | CRS Interference Mitigation for LTE Homogenous Deployments | LTE_CRSIM | 1 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-142263 |  | Ericsson | Ericsson |  |  | 66 | 34 |  |  | Thu 15/01/15 | Thu 15/01/15
1581 | 660279 | Perf. part: CRS Interference Mitigation for LTE Homogenous Deployments | LTE_CRSIM-Perf | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-142263 | RP-151171 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Mon 15/06/15->Tue 15/03/16 1st Apr 15: Stat Rep: ->RP-150061 03/07/15: Compl:10%->20% 03/07/15: Stat Rep: RP-150061->RP-150584 29/09/15: Compl:20%->30% 29/09/15: Stat Rep: RP-150584->RP-151171 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
1582 | 670055 | Dual Connectivity enhancements for LTE | LTE_dualC_enh | 1 | Rel-13 | R2 | 2015-03-16 08:00 | 2016-06-15 17:00 | 100% | RP-150490 |  | NTT DOCOMO |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1583 | 670155 | Core part: Dual Connectivity enhancements for LTE | LTE_dualC_enh-Core | 2 | Rel-13 | R2 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-151739 | RP-151330 | NTT DOCOMO |  | 03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150744 29/09/15: Compl:25%->55% 29/09/15: Stat Rep: RP-150744->RP-151330 1/1/16: Compl:55%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1584 | 670255 | Perf. part: Dual Connectivity enhancements for LTE | LTE_dualC_enh-Perf | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2016-06-15 17:00 | 100% | RP-151739 | RP-151330 | NTT DOCOMO |  | 03/07/15: Stat Rep: ->RP-150744 29/09/15: Stat Rep: RP-150744->RP-151330 ; 1/1/16: WID: RP-150490->RP-15173922/3/16: Compl:0%->50%; |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/07/16
1585 | 670056 | Multicarrier Load Distribution of UEs in LTE | LTE_MC_load | 1 | Rel-13 | R2 | 2015-03-16 08:00 | 2016-09-15 17:00 | 100% | RP-150491 |  | ZTE |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1586 | 670156 | Core part: Multicarrier Load Distribution of UEs in LTE | LTE_MC_load-Core | 2 | Rel-13 | R2 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-152181 | RP-151190 | ZTE |  | 03/07/15: Compl:0%->40% 03/07/15: WID: RP-150491->RP-150611 03/07/15: Stat Rep: ->RP-150610 29/09/15: Compl:40%->55% 29/09/15: WID: RP-150611->RP-151206 29/09/15: Stat Rep: RP-150610->RP-151190 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1587 | 670256 | Perf. part: Multicarrier Load Distribution of UEs in LTE | LTE_MC_load-Perf | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2016-09-15 17:00 | 100% | RP-161699 | RP-151190 | ZTE |  | 03/07/15: WID: RP-150491->RP-150611 03/07/15: Stat Rep: ->RP-150610 29/09/15: WID: RP-150611->RP-151206 29/09/15: Stat Rep: RP-150610->RP-1511901/1/16:22/3/16: Compl:70%->75%; 26/9/16: Compl:90%->100%; 26/9/16: WID: RP-152181 |  | 67 | 34 |  |  | Wed 01/04/15 | Mon 26/09/16
1588 | 670058 | LTE-WLAN Radio Level Integration and Interworking Enhancement | LTE_WLAN_radio | 1 | Rel-13 | R2 | 2015-03-16 08:00 | 2018-09-14 17:00 | 77% | RP-150510 |  | Intel |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1589 | 670158 | Core part: LTE-WLAN Radio Level Integration and Interworking Enhancement | LTE_WLAN_radio-Core | 2 | Rel-13 | R2 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-160521 | RP-151563 | Intel |  | 03/07/15: Compl:0%->30% 03/07/15: WID: RP-150510->RP-151114 03/07/15: Stat Rep: ->RP-151081, 07/08/15: impacted TSs added 29/09/15: Compl:30%->35% 29/09/15: Stat Rep: RP-151081->RP-151563; | 36.461, 36.462, 36.463, 36.464, 36.465, 36.622, 36.623, 36.624, 36.625, 36.360 | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
1590 | 670258 | Perf. part: LTE-WLAN Radio Level Integration and Interworking Enhancement | LTE_WLAN_radio-Perf | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-160521 | RP-151563 | Intel |  | 03/07/15: WID: RP-150510->RP-151114 03/07/15: Stat Rep: ->RP-151081 29/09/15: Stat Rep: RP-151081->RP-1515631/1/16: Compl:0%->10% ; 22/3/16: Compl:10%->100%; |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
1591 | 710070 | UE Conformance Test Aspects - WLAN/3GPP Radio Level Integration and Interworking Enhancement Interworking | LTE_WLAN_radio-UEConTest | 2 | Rel-13 | R5 | 2016-03-15 08:00 | 2018-09-14 17:00 | 58% | RP-180942 |  | Intel |  | testing REL-13 LTE_WLAN_radio-Core; 1/7/16: Compl:0%->5%; 20/21/3/17: Compl:20 ;27/3/18: ; |  | 71 | 36 |  |  | Tue 22/03/16 | Wed 27/06/18
1592 | 670060 | RAN aspects for improvements to CS/PS coordination in UTRAN Shared Network | CSPS_Coord-UTRA | 1 | Rel-13 | R3 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150500 |  | Ericsson |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1593 | 670160 | Core part: RAN aspects for improvements to CS/PS coordination in UTRAN Shared Network | CSPS_Coord-UTRA-Core | 2 | Rel-13 | R3 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150500 | RP-151289 | Ericsson |  | 03/07/15: Compl:0%->45% 03/07/15: Stat Rep: ->RP-150842 29/09/15: Compl:45%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150842->RP-1512891/1/16: Compl:80%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1594 | 670061 | LTE DL 4 Rx antenna ports | LTE_4Rx_AP_DL | 1 | Rel-13 | R4 | 2000-01-03 08:00 | 2017-09-15 17:00 | 99% | RP-150427 |  | Ericsson |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1595 | 670161 | Core part: LTE DL 4 Rx antenna ports | LTE_4Rx_AP_DL-Core | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150427 | RP-151265 | Ericsson |  | 03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150803 29/09/15: Compl:25%->50% 29/09/15: Stat Rep: RP-150803->RP-151265; 1/1/16: Compl:50%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1596 | 670261 | Perf. part: LTE DL 4 Rx antenna ports | LTE_4Rx_AP_DL-Perf | 2 | Rel-13 | R4 | 2000-01-03 08:00 | 2016-09-15 17:00 | 100% | RP-161237 | RP-151265 | Ericsson |  | 03/07/15: Compl:0%->15% 03/07/15: CD:Mon 02/10/00->Wed 15/06/16 03/07/15: Stat Rep: ->RP-150803 29/09/15: Compl:15%->35% 29/09/15: Stat Rep: RP-150803->RP-15126522/3/16: Compl:60%-;26/9/16: Compl:90%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Mon 26/09/16
1597 | 700066 | UE Conformance Test Aspects - LTE DL 4 Rx antenna ports | LTE_4Rx_AP_DL-UEConTest | 2 | Rel-13 | R5 | 2015-12-15 08:00 | 2017-09-15 17:00 | 100% | RP-160078 |  | Ericsson |  | ; 22/3/16: Compl:0%->10%; 1/7/16: Compl:10%->25%; 26/9/16: 21/3/17: Compl:60%->70 ; |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 19/09/17
1598 | 670062 | AWS-Extension Band for LTE | LTE_AWS_EXT | 1 | Rel-13 | R4 | 2015-03-16 08:00 | 2016-09-15 17:00 | 100% | RP-150428 |  | Ericsson |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1599 | 670162 | Core part: AWS-Extension Band for LTE | LTE_AWS_EXT-Core | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150800 | RP-151343 | Ericsson |  | 03/07/15: Compl:0%->20% 03/07/15: WID: RP-150428->RP-150800 03/07/15: Stat Rep: ->RP-150796 29/09/15: Compl:20%->50% 29/09/15: Stat Rep: RP-150796->RP-151343 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1600 | 670262 | Perf. part: AWS-Extension Band for LTE | LTE_AWS_EXT-Perf | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150800 | RP-151343 | Ericsson |  | 03/07/15: WID: RP-150428->RP-150800 03/07/15: Stat Rep: ->RP-150796 29/09/15: Stat Rep: RP-150796->RP-151343; |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1601 | 700068 | UE Conformance Test Aspects - AWS-Extension Band for LTE (Band 66) | LTE_AWS_EXT-UEConTest | 2 | Rel-13 | R5 | 2015-12-15 08:00 | 2016-09-15 17:00 | 100% | RP-161524 |  | Ericsson |  | ; 22/3/16: Compl:0%->10%1/7/16: Compl:10%->65%26/9/16: Comp |  | 70 | 36 |  |  | Fri 01/01/16 | Mon 26/09/16
1602 | 670063 | Additional bandwidth combination set for LTE Advanced inter-band CA of Band 5 and Band 7 | LTE_CA_B5_B7_BWset | 1 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150171 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1603 | 670163 | Core part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 5 and Band 7 | LTE_CA_B5_B7_BWset-Core | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150602 | RP-150536 | Nokia Networks |  | 03/07/15: Compl:0%->100% 03/07/15: WID: RP-150171->RP-150602 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1604 | 670263 | Perf. part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 5 and Band 7 | LTE_CA_B5_B7_BWset-Perf | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150602 | RP-150536 | Nokia Networks |  | 03/07/15: Compl:0%->100% 03/07/15: WID: RP-150171->RP-150602 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1605 | 670064 | Additional bandwidth combination set for LTE Advanced inter-band CA of Band 3 and Band 5 | LTE_CA_B3_B5_BWset | 1 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150425 |  | Samsung |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1606 | 670164 | Core part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 3 and Band 5 | LTE_CA_B3_B5_BWset-Core | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150425 | RP-150536 | Samsung |  | 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1607 | 670264 | Perf. part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 3 and Band 5 | LTE_CA_B3_B5_BWset-Perf | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150425 | RP-150536 | Samsung |  | 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1608 | 670054 | Multiflow Enhancements for UTRA | HSDPA_MFTX_enh | 1 | Rel-13 | R2 | 2015-03-16 08:00 | 2015-09-15 17:00 | 100% | RP-150288 |  | Nokia | alexander.sayenko@nokia.com |  |  | 67 | 34 |  |  | Tue 05/05/15 | Tue 05/05/15
1609 | 670154 | Core part: Multiflow Enhancements for UTRA | HSDPA_MFTX_enh-Core | 2 | Rel-13 | R2 | 2015-03-16 08:00 | 2015-09-15 17:00 | 100% | RP-151021 | RP-151302 | Nokia | alexander.sayenko@nokia.com | 03/07/15: Compl:0%->80% 03/07/15: WID: RP-150288->RP-151021 03/07/15: Stat Rep: ->RP-150827 29/09/15: Compl:80%->100% 29/09/15: Stat Rep: RP-150827->RP-151302 |  | 67 | 34 |  |  | Tue 05/05/15 | Tue 29/09/15
1610 | 680044 | Message interworking during PS to CS SRVCC | mSRVCC | 1 | Rel-13 | C1 | 2015-06-15 08:00 | 2015-09-16 17:00 | 100% | CP-150401 |  | Ivo Sedlacek, Ericsson | ivo.sedlacek@ericsson.com |  |  | 68 | 35 |  |  | Mon 15/06/15 | Mon 15/06/15
1611 | 680045 | CT1 aspects of Message interworking during PS to CS SRVCC | mSRVCC | 2 | Rel-13 | C1 | 2015-06-15 08:00 | 2015-09-16 17:00 | 100% | CP-150401 |  | Ivo Sedlacek, Ericsson | ivo.sedlacek@ericsson.com | 07/09/15: 0%->25; 7/12/15: 25%->100 | 24.237, 24.292 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1612 | 680046 | CT3 aspects of Message interworking during PS to CS SRVCC | mSRVCC | 2 | Rel-13 | C3 | 2015-06-15 08:00 | 2015-09-16 17:00 | 100% | CP-150401 |  | Ivo Sedlacek, Ericsson | ivo.sedlacek@ericsson.com | 07/09/15: 0%->70; 7/12/15: 70%->100 | 29.292 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1613 | 690008 | Support of Emergency services over WLAN – phase 1 | SEW1 | 1 | Rel-13 | S2 | 2015-06-18 08:00 | 2016-03-11 17:00 | 100% | SP-150253 |  | Laurent thiebaut | Laurent.thiebaut@alcatel-lucent.com | 07/09/15: 0%->100 | TS 23.402, TS 23.167, TS 23.271, TS 23.203, TS 23.228 | 68 | 35 |  |  | Thu 18/06/15 | Mon 07/09/15
1614 | 680051 | Stage 2 of Support of Emergency services over WLAN - phase 1 | SEW1 | 2 | Rel-13 | S2 | 2015-06-18 08:00 | 2015-09-16 17:00 | 100% | SP-150253 |  | Laurent thiebaut | Laurent.thiebaut@alcatel-lucent.com | 07/09/15: 0%->100 | TS 23.402, TS 23.167, TS 23.271, TS 23.203, TS 23.228 | 68 | 35 |  |  | Thu 18/06/15 | Mon 07/09/15
1615 | 690009 | CT aspects of Support of Emergency services over WLAN – phase 1 | SEW1-CT | 2 | Rel-13 | ct | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-150571 |  | Alcatel-Lucent, Jennifer Liu (CT1) | jennifer.liu@alcatel-lucent.com |  |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 14/09/15
1616 | 690022 | CT1 aspects of Support of Emergency services over WLAN – phase 1 | SEW1-CT | 3 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-150571 |  | Alcatel-Lucent, Jennifer Liu (CT1) | jennifer.liu@alcatel-lucent.com | 7/12/15: 60%->95. FCD -> 03/16, ES in CP-150729; 7/3/16: 95%->100 | 24.302, 24.229 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
1617 | 690025 | CT3 aspects of Support of Emergency services over WLAN – phase 1 | SEW1-CT | 3 | Rel-13 | C3 | 2015-09-07 08:00 | 2015-12-11 17:00 | 100% | CP-150571 |  | Alcatel-Lucent, Jennifer Liu (CT1) | jennifer.liu@alcatel-lucent.com | 7/12/15: 0%->100 | 29.212, 29.214 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
1618 | 690023 | CT4 aspects of Support of Emergency services over WLAN – phase 1 | SEW1-CT | 3 | Rel-13 | C4 | 2015-09-07 08:00 | 2015-12-11 17:00 | 100% | CP-150571 |  | Alcatel-Lucent, Jennifer Liu (CT1) | jennifer.liu@alcatel-lucent.com | 7/12/15: 0%->100 | 23.003, 23.008, 29.273, 29.274 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
1619 | 690036 | CT6 aspects of Support of Emergency services over WLAN – phase 1 | SEW1-CT | 3 | Rel-13 | C6 | 2015-09-07 08:00 | 2015-12-11 17:00 | 100% | CP-150571 |  | Alcatel-Lucent, Jennifer Liu (CT1) | jennifer.liu@alcatel-lucent.com | 7/3/16: 0%->100 | 31.102 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
1620 | 660009 | MBMS Enhancements | MBMS_enh | 1 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-12-07 17:00 | 100% | SP-150516 |  | Nokia Networks, Curt Wong |  | . 3/3: WID tdoc number updated; 14/09/15: WID:SP-140883->SP-150516 |  | 66 | 34 |  |  | Wed 03/12/14 | Mon 14/09/15
1621 | 660010 | MBMS Enhancements TR Phase | FS_MBMS_enh_TR | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-09-14 17:00 | 100% | SP-150516 |  | Nokia Networks, Curt Wong |  | Acronym changed from "MBMS_enh-SA2TR". Mar15: 0->10%; June2015: Compl:10%->50; 07/09/15: 50%->70. acronym changed from "MBMS_enh" to "MBMS_enh_TR"; 07/09/15: 70%->100; 14/09/15: WID:SP-140883->SP-150516 | TR 23.8xy | 66 | 34 |  |  | Wed 03/12/14 | Mon 14/09/15
1622 | 690046 | MBMS Enhancements | MBMS_enh_St2 | 2 | Rel-13 | S2 | 2015-08-10 08:00 | 2015-09-16 17:00 | 100% | SP-150520 |  | Nokia Networks, Curt Wong |  | SA#69: no normative work, moved as Study only. 14/10/15: corrected: was mentioned as FS_ | TS 23.246, TS 23.468 | 69 | 35 |  |  | Wed 16/09/15 | Wed 14/10/15
1623 | 700006 | CT aspects of MBMS Enhancements | MBMS_enh-CT | 2 | Rel-13 | C3 | 2015-11-09 08:00 | 2015-12-07 17:00 | 100% | CP-150798 |  | Nokia Networks, Thomas Belling |  |  |  | 70 | 36 |  |  | Mon 07/12/15 | NA
1624 | 700035 | CT3 aspects of MBMS enhancements | MBMS_enh-CT | 3 | Rel-13 | C3 | 2015-11-09 08:00 | 2015-12-07 17:00 | 100% | CP-150798 |  | Nokia Networks, Thomas Belling |  | 8/12/15: 0%->100 | 29.061, 29.468 | 70 | 36 |  |  | Mon 07/12/15 | Tue 08/12/15
1625 | 700007 | CT4 aspects of MBMS enhancements | MBMS_enh-CT | 3 | Rel-13 | C4 | 2015-11-09 08:00 | 2015-12-07 17:00 | 100% | CP-150798 |  | Nokia Networks, Thomas Belling |  |  | 29.274, 23.008, 29.230 | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/12/15
1626 | 660011 | Deleted (not approved) - MBMS Enhancements - Stage 2 | MBMS_enh_TS | 2 | Rel-13 | S2 | 2015-03-13 08:00 | 2015-03-13 17:00 | 100% | SP-140883 |  | Rainer Liebhart |  | Commented during RAN#67 that it should have never beeen here. 07/09/15: "undeleted", acronym changed from "MBMS_enh-del" to "MBMS_enh_TS". 14/10/15: SP-140883 was never approved so this line should have never appeared in the WP. | TS 23.246, TS 23.468 | 66 | 34 | SP-69 |  | Wed 03/12/14 | Wed 16/09/15
1627 | 690002 | EPC Signalling Improvements for race scenarios | EPC_SIG_RACE | 1 | Rel-13 | C4 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-150424 |  | Huawei, Peter Schmitt | Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM |  |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 14/09/15
1628 | 690026 | CT3 aspects for EPC Signalling Improvements for race scenarios | EPC_SIG_RACE | 2 | Rel-13 | C3 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-150424 |  | Huawei, Peter Schmitt | Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM | 7/12/15: FCD -> 03/16, ES in CP-150861; 8/12/15: 0%->100 | 29.212, 29.213 | 69 | 35 |  |  | Mon 07/09/15 | Tue 08/12/15
1629 | 690027 | CT4 aspects for EPC Signalling Improvements for race scenarios | EPC_SIG_RACE | 2 | Rel-13 | C4 | 2015-09-07 08:00 | 2015-12-18 17:00 | 100% | CP-150424 |  | Huawei, Peter Schmitt | Huawei, Peter Schmitt, Peter.Schmitt@HUAWEI.COM | 7/12/15: 95%->100 | 29.274, 29.274, 29.275, 29.282, 29.273, 29.230, 23.008, 29.273 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
1630 | 700008 | Diameter Message Priority | DiaPri | 1 | Rel-13 | C4 | 2015-11-02 08:00 | 2016-06-16 17:00 | 100% | CP-150613 |  | Alcatel-Lucent, Jean-Jacques Trottin | jean-jacques.trottin@alcatel-lucent.com |  |  | 70 | 36 |  |  | Mon 07/12/15 | NA
1631 | 700009 | CT3 aspects of DiaPri | DiaPri | 2 | Rel-13 | C3 | 2015-11-02 08:00 | 2016-03-11 17:00 | 100% | CP-150613 |  | Intel, Vivek Gupta |  | ES in CP-150645; 7/3/16: 65%->100 | 29.153, 29.154, 29.201, 29.212, 29.213, 29.214, 29.215, 29.217, 29.219 | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/03/16
1632 | 700010 | CT4 aspects of DiaPri | DiaPri | 2 | Rel-13 | C4 | 2015-11-02 08:00 | 2016-03-11 17:00 | 100% | CP-150613 |  | Alcatel-Lucent, Jean-Jacques Trottin | jean-jacques.trottin@alcatel-lucent.com | ES in CP-150622; 7/3/16: 70%->100 | 29.228, 29.229, 29.272, 29.273, 29.328, 29.329, 29.336, 29.337, 29.338, 29.344, 29.345 | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/03/16
1633 | 710044 | (IETF) Diameter Routing Message Priority (draft-ietf-dime-drmp) | DiaPri | 2 | Rel-13 | C4-IETF | 2015-12-08 08:00 | 2016-06-16 17:00 | 100% | 7/3/16: introduced by IETF inputs |  | Alcatel-Lucent, Jean-Jacques Trottin | jean-jacques.trottin@alcatel-lucent.com | 02/2016: publication requested; 2/12/16: 85%->100 | 29.227, 29.272, 29.273, 29.229 | 71 | 36 |  |  | Mon 07/03/16 | Fri 02/12/16
1634 | 680059 | Downlink TPC Enhancements for UMTS | UTRA_EDL_TPC | 1 | Rel-13 | R1 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151044 | - | Huawei |  | follow-up WI of REL-13 SI FS_UTRA_EDL; TPC = Transmit Power Control |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
1635 | 680159 | Core part: Downlink TPC Enhancements for UMTS | UTRA_EDL_TPC-Core | 2 | Rel-13 | R1,R2,R3 | 2015-10-15 08:00 | 2015-12-15 17:00 | 100% | RP-151880 | RP-151564 | Huawei |  | follow-up WI of REL-13 SI FS_UTRA_EDL; TPC = Transmit Power Control 29/09/15: Compl:0%->35% 29/09/15: Stat Rep: -->RP-1515641/1/16: Compl:35%->100%1/1/16: WID: |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1636 | 680259 | Perf. part: Downlink TPC Enhancements for UMTS | UTRA_EDL_TPC-Perf | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151880 | RP-151564 | Huawei |  | follow-up WI of REL-13 SI FS_UTRA_EDL; TPC = Transmit Power Control 29/09/15: Stat Rep: -->RP-151564; 1/1/16: Compl:0%->80%; 1/1/16: WID: RP-151044->RP-151880 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
1637 | 680060 | Licensed-Assisted Access using LTE | LTE_LAA | 1 | Rel-13 | R1 | 2015-06-15 08:00 | 2017-09-15 17:00 | 99% | RP-151045 | - | Ericsson |  | follow-up WI of REL-13 SI FS_LTE_LAA |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
1638 | 680160 | Core part: Licensed-Assisted Access using LTE | LTE_LAA-Core | 2 | Rel-13 | R1 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151045 | RP-151390 | Ericsson |  | follow-up WI of REL-13 SI FS_LTE_LAA 29/09/15: Compl:0%->25% 29/09/15: Stat Rep: -->RP-1513901/1/16: Compl:25%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1639 | 680260 | Perf. part: Licensed-Assisted Access using LTE | LTE_LAA-Perf | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-12-15 17:00 | 100% | RP-151045 |  | Ericsson |  | follow-up WI of REL-13 SI FS_LTE_LAA 29/09/15: Stat Rep: -->RP-15139022/3/16: Compl:0%->33%; 1/7/16: Compl:3; 26/9/16: Compl:50%->90%; 20/12/16: Compl:90%->100%; 20/12/16: Stat Rep: RP-151390-> |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 20/12/16
1640 | 700067 | UE Conformance Test Aspects - Licensed-Assisted Access using LTE | LTE_LAA-UEConTest | 2 | Rel-13 | R5 | 2015-12-15 08:00 | 2017-09-15 17:00 | 100% | RP-162376 |  | Motorola Mobility |  | ; 22/3/16: Compl:0%->5%1/7/16: Compl:5%->8%26/9/16: Compl:8%->15%; 20/21/3/17: Com ; |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 19/09/17
1641 | 680061 | Elevation Beamforming/Full-Dimension (FD) MIMO for LTE | LTE_EBF_FDMIMO | 1 | Rel-13 | R1 | 2015-06-15 08:00 | 2018-12-14 17:00 | 63% | RP-151085 | - | Samsung |  | follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
1642 | 680161 | Core part: Elevation Beamforming/Full-Dimension (FD) MIMO for LTE | LTE_EBF_FDMIMO-Core | 2 | Rel-13 | R1 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151085 | RP-151565 | Samsung |  | follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO 29/09/15: Compl:0%->25% 29/09/15: Stat Rep: -->RP-151565 1/1/16: Compl:25%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1643 | 680261 | Perf. part: Elevation Beamforming/Full-Dimension (FD) MIMO for LTE | LTE_EBF_FDMIMO-Perf | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-09-15 17:00 | 100% | RP-151085 | RP-151565 | Samsung |  | follow-up WI of REL-13 SI FS_LTE_EBF_FDMIMO 29/09/15: Stat Rep: -->RP-151565 ; 1/1/16: Compl:0%->5%; 22/3/16: Compl:5%->35%;26/9/16: Compl:70%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Mon 26/09/16
1644 | 770062 | UE Conformance Test Aspects - Elevation Beamforming/Full-Dimension MIMO for LTE | LTE_EBF_FDMIMO-UEConTest | 2 | Rel-13 | R5 | 2017-09-15 08:00 | 2018-12-14 17:00 | 10% | RP-172651 |  | Ericsson |  | ; 8/1/18: Compl:0%->5%; 27/3/18: Compl:5%->10%; 27/6/18: CD:Fri 15/06/18- |  | 77 | 39 |  |  | Tue 19/09/17 | Wed 27/06/18
1645 | 680062 | L2/L3 Downlink enhancements for UMTS | UTRA_EDL_L23 | 1 | Rel-13 | R2 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151043 | - | Huawei |  | no Perf. part; follow-up of Rel-13 SI FS_UTRA_EDL |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
1646 | 680162 | Core part: L2/L3 Downlink enhancements for UMTS | UTRA_EDL_L23-Core | 2 | Rel-13 | R2 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-152184 | RP-151238 | Huawei |  | no Perf. part; follow-up of Rel-13 SI FS_UTRA_EDL 29/09/15: Compl:0%->35% 29/09/15: WID: RP-151043->RP-151249 29/09/15: Stat Rep: -->RP-1512381/1/16: Compl:35%->100% ; |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1647 | 680064 | Support of single-cell point-to-multipoint transmission in LTE | LTE_SC_PTM | 1 | Rel-13 | R2 | 2015-06-15 08:00 | 2016-09-15 17:00 | 100% | RP-151110 | - | Huawei |  | follow-up WI of REL-13 SI FS_LTE_SC_PTM |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
1648 | 680164 | Core part: Support of single-cell point-to-multipoint transmission in LTE | LTE_SC_PTM-Core | 2 | Rel-13 | R2 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151110 | RP-151237 | Huawei |  | follow-up WI of REL-13 SI FS_LTE_SC_PTM 29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-151237 1/1/16: Compl:30%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1649 | 680264 | Perf. part: Support of single-cell point-to-multipoint transmission in LTE | LTE_SC_PTM-Perf | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151110 | RP-151237 | Huawei |  | follow-up WI of REL-13 SI FS_LTE_SC_PTM 29/09/15: Stat Rep: -->RP-1512371/1/16: Compl:0%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1650 | 710069 | UE Conformance Test Aspects - Support of single-cell point-to-multipoint transmission in LTE | LTE_SC_PTM-UEConTest | 2 | Rel-13 | R5 | 2016-03-15 08:00 | 2016-09-15 17:00 | 100% | RP-161681 | - | Huawei |  | testing REL-13 LTE_SC_PTM-Core1/7/16: Compl:0%->40%26/9/16 |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
1651 | 680065 | Extension of Dual Connectivity in E-UTRAN | LTE_dualC_ext | 1 | Rel-13 | R3 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151008 | - | Samsung |  | no Perf. part; follow-up WI of REL-13 SI FS_LTE_dualC_ext; |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
1652 | 680165 | Core part: Extension of Dual Connectivity in E-UTRAN | LTE_dualC_ext-Core | 2 | Rel-13 | R3 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151798 | RP-151214 | Samsung |  | no Perf. part; follow-up WI of REL-13 SI FS_LTE_dualC_ext; 29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-151214; 1/1/16: Compl:3 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1653 | 680067 | RAN sharing enhancements for UMTS | RSE_UTRA_GUSH | 1 | Rel-13 | R3 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151086 | - | Huawei |  | no Perf. part; follow-up WI for Rel-13 SI FS_RSE_UTRA_GUSH; note: GUSH was a REL-13 SA1 WI; there is an ongoing REL-13 WI for LTE: RSE-RAN_LTE; |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
1654 | 680167 | Core part: RAN sharing enhancements for UMTS | RSE_UTRA_GUSH-Core | 2 | Rel-13 | R3 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151251 | RP-151239 | Huawei |  | no Perf. part; follow-up WI for Rel-13 SI FS_RSE_UTRA_GUSH; note: GUSH was a REL-13 SA1 WI; there is an ongoing REL-13 WI for LTE: RSE-RAN_LTE; 29/09/15: Compl:0%->30% 29/09/15: WID: RP-151086->RP-151251 29/09/15: Stat Rep: -->RP-151239 ; |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1655 | 680071 | Interference mitigation for downlink control channels of LTE | LTE_IM_DLCCH | 1 | Rel-13 | R4 | 2015-06-15 08:00 | 2018-09-14 17:00 | 90% | RP-151107 | - | Intel |  | only Perf. part, no Core part; |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
1656 | 680271 | Perf. part: Interference mitigation for downlink control channels of LTE | LTE_IM_DLCCH-Perf | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-06-15 17:00 | 100% | RP-160908 | RP-151301 | Intel |  | only Perf. part, no Core part; 29/09/15: CD:Tue 15/03/16->Wed 15/06/16 29/09/15: Stat Rep: -->RP-1513011/1/16: Compl:0%->40%22/3/16: Compl:40%->70% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/07/16
1657 | 750051 | UE Conformance Test Aspects - Interference Mitigation for Downlink Control Channels of LTE | LTE_IM_DLCCH-UEConTest | 2 | Rel-13 | R5 | 2017-03-15 08:00 | 2018-09-14 17:00 | 84% | RP-180176 |  | Intel |  | tested: REL-13 LTE_IM_DLCCH-Perf (note: WI had no Core part);19/6/171 8/1/18: C 27/3/18 ; |  | 75 | 38 |  |  | Tue 21/03/17 | Wed 27/06/18
1658 | 690062 | Network-Assisted Interference Cancellation and Suppression for UMTS | UTRA_NAICS | 1 | Rel-13 | R1 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151577 | - | Huawei |  | no Perf. part; follow-up WI REL-13 RAN1 SI FS_UTRA_NAICS |  | 69 | 35 |  |  | Tue 29/09/15 | NA
1659 | 690162 | Core part: Network-Assisted Interference Cancellation and Suppression for UMTS | UTRA_NAICS-Core | 2 | Rel-13 | R1 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151879 | - | Huawei |  | no Perf. part; follow-up WI REL-13 RAN1 SI FS_UTRA_NAICS ; 1/1/16: Compl:0%->100% ; 1/1/16: WID: RP-151577->RP-151879 |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
1660 | 690064 | Dual Carrier HSUPA Enhancements for UTRAN CS | DC_HSUPA_CS | 1 | Rel-13 | R2 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151607 | - | Nokia Networks |  | no Perf. part; compare REL-13 WI HSUPA_DB_MC |  | 69 | 35 |  |  | Tue 29/09/15 | NA
1661 | 690164 | Core part: Dual Carrier HSUPA Enhancements for UTRAN CS | DC_HSUPA_CS-Core | 2 | Rel-13 | R2 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151780 | - | Nokia Networks |  | no Perf. part; compare REL-13 WI HSUPA_DB_MC 1/1/16: Compl:0%->100% 1/1/16: WID: RP-151607->RP-151780 |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
1662 | 690065 | Further Enhancements of Minimization of Drive Tests for E-UTRAN | LTE_eMDT2 | 1 | Rel-13 | R2 | 2015-03-16 08:00 | 2017-03-15 17:00 | 100% | RP-151611 | - | CMCC |  | no Perf. part; follow-up WI of REL-13 SI FS_LTE_eMDT2 |  | 69 | 35 |  |  | Tue 29/09/15 | NA
1663 | 670042 | Study on further Enhancements of Minimization of Drive Tests for E-UTRAN | FS_LTE_eMDT2 | 2 | Rel-13 | R2 | 2015-03-16 08:00 | 2015-09-15 17:00 | 100% | RP-150472 | RP-151181 | CMCC |  | 03/07/15: Compl:0%->70% 03/07/15: Stat Rep: -->RP-150806 29/09/15: Compl:70%->100% 29/09/15: Stat Rep: RP-150806->RP-151181 | 36.880 | 67 | 34 |  |  | Wed 01/04/15 | Tue 29/09/15
1664 | 690165 | Core part: Further Enhancements of Minimization of Drive Tests for E-UTRAN | LTE_eMDT2-Core | 2 | Rel-13 | R2 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151611 | - | CMCC |  | no Perf. part; follow-up WI of REL-13 SI FS_LTE_eMDT2; 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
1665 | 721000 | UE Conformance Test Aspects – Further Enhancements of Minimization of Drive Tests for E-UTRAN | LTE_eMDT2-UEConTest | 2 | Rel-13 | R5 | 2016-06-15 08:00 | 2017-03-15 17:00 | 100% | RP-161071 |  | Intel |  | tested REL-13 WI: LTE_eMDT2-Core26/9/16: Com;21/3/17: Compl:5%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 21/03/17
1666 | 690066 | LTE-WLAN RAN Level Integration supporting legacy WLAN | LTE_WLAN_radio_legacy | 1 | Rel-13 | R2 | 2015-09-15 08:00 | 2016-03-15 17:00 | 100% | RP-151615 | - | Alcatel-Lucent |  | no Perf. part; compare REL-13 WI LTE_WLAN_radio |  | 69 | 35 |  |  | Tue 29/09/15 | NA
1667 | 690166 | Core part: LTE-WLAN RAN Level Integration supporting legacy WLAN | LTE_WLAN_radio_legacy-Core | 2 | Rel-13 | R2 | 2015-09-15 08:00 | 2016-03-15 17:00 | 100% | RP-160608 | - | Alcatel-Lucent |  | no Perf. part; compare REL-13 WI LTE_WLAN_radio1/1/16: Compl:0%->95% 22/3/16: Compl:95%->100%; 28/7/16: 36.361 added; | 36.361 | 69 | 35 |  |  | Tue 29/09/15 | Thu 28/07/16
1668 | 690067 | Indoor Positioning enhancements for UTRA and LTE | UTRA_LTE_iPos_enh | 1 | Rel-13 | R2 | 2015-09-15 08:00 | 2017-03-15 17:00 | 100% | RP-151624 | - | NextNav |  | follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh |  | 69 | 35 |  |  | Tue 29/09/15 | NA
1669 | 690167 | Core part: Indoor Positioning enhancements for UTRA and LTE | UTRA_LTE_iPos_enh-Core | 2 | Rel-13 | R2 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-160332 | - | NextNav |  | follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh1/1/16: Compl:0%->100%1/1/16: WID: RP-151624->RP-15225122/3/16: WID: RP-152251->RP-160332 |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
1670 | 690267 | Perf. part: Indoor Positioning enhancements for UTRA and LTE | UTRA_LTE_iPos_enh-Perf | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2016-06-15 17:00 | 100% | RP-160332 | - | NextNav |  | follow-up WI of REL-13 SI FS_UTRA_LTE_iPos_enh 1/1/16: Compl:0%->10% 1/1/16: WID: RP-151624->RP-152251; 22/3/16: Compl:10%->20%; 22/3/16: WID: RP-152251->RP-160332 28/7/16: 37.171 added; 28/7/16: 37.958 added; | 37.171; 37.958 | 69 | 35 |  |  | Tue 29/09/15 | Thu 28/07/16
1671 | 700011 | CT aspects of Indoor Positionning | UTRA_LTE_iPos_enh-CT | 2 | Rel-13 | C4 | 2015-10-12 08:00 | 2015-12-07 17:00 | 100% | CP-150612 |  | Ericsson, Jesús de Gregorio | jesus.de.gregorio@ericsson.com |  | 29.171, 29.172, 29.230, 29.002 | 70 | 36 |  |  | Mon 07/12/15 | NA
1672 | 700053 | CT4 aspects of Indoor Positionning | UTRA_LTE_iPos_enh-CT | 3 | Rel-13 | C4 | 2015-10-12 08:00 | 2015-12-07 17:00 | 100% | CP-150612 |  | Ericsson, Jesús de Gregorio | jesus.de.gregorio@ericsson.com | 8/12/15: 0%->100 | 29.171, 29.172, 29.230, 29.002 | 70 | 36 |  |  | Mon 07/12/15 | Tue 08/12/15
1673 | 720099 | UE Conformance Test Aspects – Indoor Positioning Enhancement Support for LTE and UMTS | UTRA_LTE_iPos_enh-UEConTest | 2 | Rel-13 | R5 | 2016-06-15 08:00 | 2017-03-15 17:00 | 100% | RP-170233 |  | NextNav |  | tested REL-13 WI: UTRA_LTE_iPos_enh-Core; 26/9/1; 20/12/16:21/3/17: Compl: |  | 72 | 37 |  |  | Fri 01/07/16 | Tue 21/03/17
1674 | 680063 | Power saving enhancements for UMTS | UTRA_SDATA_POWSAV | 1 | Rel-13 | R2 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151092 | - | Ericsson |  | no Perf. part; follow-up WI of SI FS_UTRA_SDATA |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
1675 | 680163 | Core part: Power saving enhancements for UMTS | UTRA_SDATA_POWSAV-Core | 2 | Rel-13 | R2 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151998 | RP-151291 | Ericsson |  | no Perf. part; follow-up WI of SI FS_UTRA_SDATA 29/09/15: Compl:0%->25% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: WID: RP-151092->RP-151292 29/09/15: Stat Rep: -->RP-151291 29/09/15: Release: Rel-14->Rel-13 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1676 | 700256 | Perf. Part: Power saving enhancements for UMTS | UTRA_SDATA_POWSAV-Perf | 2 | Rel-13 | R4 | 2015-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-151998 |  | Ericsson |  | ; 22/3/16: Compl:0%->100% |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 22/03/16
1677 | 680073 | 700MHz E-UTRA FDD Band for Arab Region | LTE_FDD_700_ARAB | 1 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151042 | - | Etisalat |  | REL-independent from REL-9 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
1678 | 680173 | Core part: 700MHz E-UTRA FDD Band for Arab Region | LTE_FDD_700_ARAB-Core | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151042 | RP-151207 | Etisalat |  | REL-independent from REL-9. Aug 15: TR numb added 29/09/15: Compl:0%->15% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151207 29/09/15: Release: Rel-14->Rel-13; | 36.893 | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
1679 | 680273 | Perf. part: 700MHz E-UTRA FDD Band for Arab Region | LTE_FDD_700_ARAB-Perf | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151042 | RP-151207 | Etisalat |  | REL-independent from REL-9 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151207 29/09/15: Release: Rel-14->Rel-13 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
1680 | 680075 | European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE CA (2DL/1UL) with Band 20 | LTE_CA_700EU_B20 | 1 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150861 | - | TeliaSonera |  | introduction of new DL only band and 2DL/1UL CA with it |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
1681 | 680175 | Core part: European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE CA (2DL/1UL) with Band 20 | LTE_CA_700EU_B20-Core | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151228 | RP-151232 | TeliaSonera |  | introduction of new DL only band and 2DL/1UL CA with it. Aug 15: TR numb added 29/09/15: Compl:0%->80% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: WID: RP-150861->RP-151228 29/09/15: Stat Rep: -->RP-151232 29/09/15: Release: Rel-14->Rel-13 | 36.895 | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1682 | 680275 | Perf. part: European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE CA (2DL/1UL) with Band 20 | LTE_CA_700EU_B20-Perf | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151228 | RP-151232 | TeliaSonera |  | introduction of new DL only band and 2DL/1UL CA with it 29/09/15: WID: RP-150861->RP-151228 29/09/15: Stat Rep: -->RP-151232 29/09/15: Release: Rel-14->Rel-13 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1683 | 0 | Release 13 Features on Internet of Things (IoT) | - | 1 | Rel-13 | SP,RP,CP,GP | 2013-09-12 08:00 | 2015-05-12 10:00 | 100% | - | - |  |  | - | - |  |  |  |  | Mon 04/03/13 | Mon 04/03/13
1684 | 620063 | Service Requirements Maintenance for Machine-Type Communications (MTC) | SRMMTC | 1 | Rel-13 | S1 | 2015-09-15 08:00 | 2016-06-10 17:00 | 100% | SP-130600 | - | KPN | toon.norp@tno.nl | SP#65 completed. Linked to Rel-13 SEES, Rel-12 Support for Interworking with M2M Service Enablement (MTCe-SIMSE), Service Requirement Maintenance (MTCe-SRM). Decide which MTC reqs with no Stage 2 should be removed/maintained in Rel-13. | 22.368 | 62 | 32 |  |  | Tue 26/11/13 | Wed 03/09/14
1685 | 700012 | Cellular (Narrowband) Internet of Things | CIoT | 1 | Rel-13 |  | 2015-09-15 08:00 | 2017-12-15 17:00 | 100% | [6 empty] | 70 | 36 |  |  | Mon 07/12/15 | NA
1686 | 700016 | Stage 2 of CIoT | CIoT | 2 | Rel-13 | S2 | 2015-10-05 08:00 | 2015-10-05 17:00 | 100% | SP-150844 |  | Intel, Puneet Jain | puneet.jain@intel.com | 7/3/16: 0%->95 | 23.401, 23.682, 23.251 | 70 | 36 |  |  | Mon 07/12/15 | Mon 07/03/16
1687 | 700046 | Security Aspects of CIoT (aka NB-IoT) | CIoT | 2 | Rel-13 | S3 | 2015-11-02 08:00 | 2016-06-10 17:00 | 100% | SP-150844 |  | Tim Evans, Vodafone |  | 7/3/16: 0%->39; 19/9/16: 39%->100 | 33.401 | 70 | 36 |  |  | Mon 07/12/15 | Mon 19/09/16
1688 | 700013 | CT aspects of CIoT | CIoT-CT | 2 | Rel-13 | C1 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | CP-160292 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 11/6/16: WID:CP-150795->CP-160292 |  | 70 | 36 |  |  | Mon 07/12/15 | Sat 11/06/16
1689 | 700014 | CT1 aspects of CIoT | CIoT-CT | 3 | Rel-13 | C1 | 2015-12-07 08:00 | 2016-03-11 17:00 | 100% | CP-160292 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 7/3/16: 0%->35; 11/6/16: 35%->100; 11/6/16: WID:CP-150795->CP-160292 | 24.301, 24.008, 23.122 | 70 | 36 |  |  | Mon 07/12/15 | Sat 11/06/16
1690 | 700051 | CT3 aspects of CIoT | CIoT-CT | 3 | Rel-13 | C3 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | CP-160292 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 7/3/16: 0%->90; 11/6/16: WID:CP-150795->CP-160292; 13/6/16: 90%->100 | 29.061, 29.212 | 70 | 36 |  |  | Mon 07/12/15 | Mon 13/06/16
1691 | 700015 | CT4 aspects of CIoT | CIoT-CT | 3 | Rel-13 | C4 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | CP-160292 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 7/3/16: 0%->65; 11/6/16: WID:CP-150795->CP-160292; 13/6/16: 65%->100 | 29.272, 29.274, 23.008, 23.007, 29.128, 29.275, 29.230, 29.336, 29.281, 29.002, 29.303 | 70 | 36 |  |  | Mon 07/12/15 | Mon 13/06/16
1692 | 700052 | CT6 aspects of CIoT | CIoT-CT | 3 | Rel-13 | C6 | 2015-12-07 08:00 | 2016-06-15 17:00 | 100% | CP-160292 |  | Intel, Vivek Gupta | vivek.g.gupta@intel.com | 11/6/16: WID:CP-150795->CP-160292; 13/6/16: 0%->100 | 31.102 | 70 | 36 |  |  | Mon 07/12/15 | Mon 13/06/16
1693 | 720042 | Charging Aspects of CIoT | CIoT-CH | 2 | Rel-13 | S5 | 2016-05-12 08:00 | 2016-06-13 17:00 | 100% | SP-160395 |  | Gardella, Maryse (Nokia) | Gardella, Maryse (Nokia) | 32.25x; 13/6/16: 0%->100 | 32.25x, 32.240, 32.251, 32.274, 32.299, 32.298, 32.297 | 72 | 37 |  |  | Mon 13/06/16 | Mon 13/06/16
1694 | 690063 | RAN aspects of CIoT aka Narrowband Internet of Things (IOT) | NB_IOT | 2 | Rel-13 | R1 | 2015-09-15 08:00 | 2016-12-15 17:00 | 100% | RP-151621 | - | Vodafone |  | no Perf. part; note: WI only stays in REL-13 because of PCG decision |  | 69 | 35 |  |  | Tue 29/09/15 | NA
1695 | 690163 | Core part: Narrowband Internet of Things (IOT) | NB_IOT-Core | 3 | Rel-13 | R1 | 2015-09-15 08:00 | 2016-06-15 17:00 | 100% | RP-160933 | - | Vodafone |  | no Perf. part; note: WI only stays in REL-13 because of PCG decision1/1/16: Compl:0%->25% 22/3/16: Compl:25%->75%;1/7/16: Com | 36.802 | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/07/16
1696 | 700257 | Perf. part: Narrowband Internet of Things (IOT) | NB_IOT-Perf | 3 | Rel-13 | R4 | 2015-12-15 08:00 | 2016-12-15 17:00 | 100% | RP-162134 |  | Vodafone |  | 22/3/16: WID: RP-152284->RP-160656; 1/7/16: WID: RP-160656->RP-16093326/9/16: Compl:0%->60%26/9/16: CD:Thu 15/09/16->Thu 15/12/16; 20/12/16: Compl:60%->100%; 20/12/16: WID: RP-160933->RP-162134 |  | 70 | 36 |  |  | Fri 01/01/16 | Tue 20/12/16
1697 | 720043 | Management for NB-IoT | NB_IOT-OAM | 2 | Rel-13 | S5 | 2016-05-12 08:00 | 2016-06-15 17:00 | 100% | SP-160396 |  | Huawei, Kai ZHANG | kai.zhangkai@huawei.com | 13/6/16: 0%->100 | 28.657, 28.658, 28.659, 32.425 | 72 | 37 |  |  | Mon 13/06/16 | Mon 13/06/16
1698 | 710065 | UE Conformance Test Aspects - Narrowband Internet of Things (NB-IOT) | NB_IOT-UEConTest | 2 | Rel-13 | R5 | 2016-03-15 08:00 | 2017-12-15 17:00 | 100% | RP-160047 |  | CMCC |  | testing REL-13 NB_IOT-Core1/7/16: Compl:0%->5%; 26/9; 20/12/1; 21/3/17: Compl: ; |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 08/01/18
1699 | 690006 | Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things | CIoT_EC_GSM | 1 | Rel-13 | G1,G2 | 2015-09-25 13:00 | 2016-09-15 17:00 | 69% | GP-151039 |  | Marteen Sunberg, Ericsson | Marteen.Sunberg@Ericsson.com | 7/12/15: 0%->60 |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
1700 | 700003 | Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things Core part | CIoT_EC_GSM-Core | 2 | Rel-13 | G1,G2 | 2015-09-25 13:00 | 2016-05-12 17:00 | 100% | GP-151039 |  | Marteen Sunberg, Ericsson | Marteen.Sunberg@Ericsson.com | 7/12/15:created by MCC to distinguish core versus test parts. 2/3/16: FCD: 11/15->05/16, 40->90%; 13/6/16: 90%->100 |  | 70 | 36 |  |  | Mon 07/09/15 | Mon 13/06/16
1701 | 700004 | Test for CIoT_EC_GSM | CIoT_EC_GSM_GERAN3new | 2 | Rel-13 | G3 | 2015-11-11 08:00 | 2016-05-12 17:00 | 0% | GP-151149 |  | Sierra Wireless S.A | Marteen.Sunberg@Ericsson.com | 7/12/15: created GERAN. 2/3/16: G1,G2->G3, Acronym: CIoT_EC_GSM-Test->CIoT_EC_GSM_GERAN3new |  | 70 | 36 |  |  | Mon 07/09/15 | Wed 02/03/16
1702 | 721201 | Perf. Part: Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things | CIoT_EC_GSM-Perf | 2 | Rel-13 | R6 | 2016-06-15 08:00 | 2016-09-15 17:00 | 100% | RP-160929 |  | Ericsson |  | related to GERAN REL-13 WI CIoT_EC_GSM-Core26/9/16: Compl:0%->100% |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 26/09/16
1703 | 720097 | MS Conformance Test Aspects - Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things | CIoT_EC_GSM-MSConTest | 2 | Rel-13 | R5 | 2016-06-15 08:00 | 2016-09-15 17:00 | 100% | RP-160753 |  | Ericsson |  | tested REL-13 WI: CIoT_EC_GSM-Core26/9/16: Compl |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 26/09/16
1704 | 690005 | Extended DRX cycle for Power Consumption | eDRX | 1 | Rel-13 | S2,R2,G2 | 2014-12-03 08:00 | 2016-09-15 17:00 | 93% | SP-150369 |  | Miguel Griot | mgriot@qti.qualcomm.com | June2015: WID:SP-150254->SP-150369 | 23.401, 23.060, 23.682, 23.271, 23.272 | 68 | 35 |  |  | Thu 18/06/15 | Thu 18/06/15
1705 | 660008 | Study on Extended DRX cycle for Power Consumption Optimization | FS_eDRX | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-12-11 17:00 | 100% | SP-140881 |  | Miguel Griot, Qualcomm | mgriot@qti.qualcomm.com | No Ran aspects yet. GERAN in FS_uPoD.29/1: TS number added Mar15: 0->30%; June2015: Compl:30%->95, Exc S granted in SP-150352; 07/09/15: 95%->100 | 23.770 | 66 | 34 |  |  | Wed 03/12/14 | Mon 07/09/15
1706 | 680052 | Stage 2 for Extended DRX cycle for Power Consumption | eDRX | 2 | Rel-13 | S2 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | SP-150369 |  | Miguel Griot | mgriot@qti.qualcomm.com | June2015: WID:SP-150254->SP-150369; 07/09/15: 0%->95; 7/12/15: 95%->99 | 23.401, 23.060, 23.682, 23.271, 23.272 | 68 | 35 |  |  | Thu 18/06/15 | Mon 07/12/15
1707 | 690010 | CT aspects of extended DRX cycle | eDRX-CT | 2 | Rel-13 | ct | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-150541 |  | Catovic, Amer, Qualcomm | Catovic, Amer, Qualcomm | 14/09/15: WID:CP-150499->CP-150541 |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 14/09/15
1708 | 690020 | CT1 aspects of extended DRX cycle | eDRX-CT | 3 | Rel-13 | C1 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-150541 |  | Catovic, Amer, Qualcomm | Catovic, Amer, Qualcomm | 14/09/15: WID:CP-150499->CP-150541; 7/12/15: 25%->80. FCD ->03/16. ES in CP-150723; 7/3/16: 80%->100 | 24.301, 24.008, 29.118 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
1709 | 690030 | CT3 aspects of extended DRX cycle | eDRX-CT | 3 | Rel-13 | C3 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-150541 |  | Catovic, Amer, Qualcomm | Catovic, Amer, Qualcomm | 14/09/15: WID:CP-150499->CP-150541. FCD ->03/16. ES in CP-150723; 8/12/15: 0%->100 | 29.338, 23.007, 29.274, 29.060, 29.172 | 69 | 35 |  |  | Mon 07/09/15 | Tue 08/12/15
1710 | 690021 | CT4 aspects of extended DRX cycle | eDRX-CT | 3 | Rel-13 | C4 | 2015-09-07 08:00 | 2015-12-17 17:00 | 100% | CP-150541 |  | Catovic, Amer, Qualcomm | Catovic, Amer, Qualcomm | 14/09/15: WID:CP-150499->CP-150541; 7/12/15: 40%->100; 8/12/15: 100%->95; 8/3/16: 95%->100 | 29.212 | 69 | 35 |  |  | Mon 07/09/15 | Tue 08/03/16
1711 | 700034 | CT6 aspects of extended DRX cycle | eDRX-CT | 3 | Rel-13 | C6 | 2015-09-07 08:00 | 2016-03-11 17:00 | 100% | CP-150541 |  | Catovic, Amer, Qualcomm | Catovic, Amer, Qualcomm | 7/12/15: Added. FCD ->03/16. ES in CP-150723; 8/3/16: 0%->100 |  | 70 | 36 |  |  | Mon 07/09/15 | Tue 08/03/16
1712 | 670057 | RAN enhancements for extended DRX in LTE | LTE_extDRX | 2 | Rel-13 | R2 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-150493 |  | Qualcomm |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1713 | 670157 | Core part: RAN enhancements for extended DRX in LTE | LTE_extDRX-Core | 3 | Rel-13 | R2 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-151339 | RP-151338 | Qualcomm |  | 03/07/15: Compl:0%->15% 03/07/15: Stat Rep: ->RP-150798 29/09/15: Compl:15%->35% 29/09/15: WID: RP-150493->RP-151339 29/09/15: Stat Rep: RP-150798->RP-151338 ; 22/3/16: Compl:95%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
1714 | 710071 | UE Conformance Test Aspects - RAN enhancements for extended DRX in LTE | LTE_extDRX-UEConTest | 2 | Rel-13 | R5 | 2016-03-15 08:00 | 2016-09-15 17:00 | 100% | RP-160602 | - | Qualcomm |  | testing REL-13 LTE_extDRX-Core and CT1 feature eDRX-CT; |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
1715 | 690001 | Extended DRX (eDRX) for GSM | eDRX_GSM | 2 | Rel-13 | G2,G1 | 2015-08-28 13:00 | 2016-05-12 17:00 | 44% | GPC150624 |  | John Diachina, Ericsson LM | John.Diachina@Ericsson.com | 07/09/15: 0%->40; 7/12/15: 40%->100 | 43.064, 44.018, 44.060, 45.008, 48.018, 43.022 | 69 | 35 |  |  | Wed 12/08/15 | Mon 07/12/15
1716 | 700001 | Core Part: Extended DRX (eDRX) for GSM | eDRX_GSM-Core | 3 | Rel-13 | G2,G1 | 2015-08-28 13:00 | 2015-11-20 17:00 | 100% | GPC150624 |  | John Diachina, Ericsson LM | John.Diachina@Ericsson.com | 7/12/15: created by MCC to distinguish Core versus test parts | 43.064, 44.018, 44.060, 45.008, 48.018, 43.022 | 70 | 36 |  |  | Wed 12/08/15 | Mon 07/12/15
1717 | 700002 | MS test: Extended DRX (eDRX) for GSM | eDRX_GSM_GERAN3new | 3 | Rel-13 | G3 | 2015-12-07 08:00 | 2016-05-12 17:00 | 15% | GP-151148 |  | Sierra Wireless S.A | John.Diachina@Ericsson.com | 7/12/15: created by GERAN. 2/3/16: G1,G2->G3. Acronym: eDRX_GSM-Test -> eDRX_GSM_GERAN3new (to conform to WID); 0->15% |  | 70 | 36 |  |  | Wed 12/08/15 | Wed 02/03/16
1718 | 670027 | Optimizations to Support High Latency Communications | HLcom | 1 | Rel-13 | S2 | 2014-09-19 08:00 | 2015-12-16 17:00 | 100% | SP-150030 |  | Ericsson, Hans Rönneke | hans.ronneke(at)ericsson.com |  | 23.401, 23.060, 23.682 | 67 | 34 |  |  | Thu 05/03/15 | Thu 05/03/15
1719 | 650035 | Study on Optimizations to support High Latency communications | FS_HLcom | 2 | Rel-13 | S2 | 2014-09-19 08:00 | 2015-06-17 17:00 | 100% | SP-140635 | - | Ericsson | hans.ronneke@ericsson.com | Dec.14: 0->30%. Mar15: 70%; June2015: Compl:70%->100 | New TR 23.709 | 65 | 33 |  |  | Tue 05/08/14 | Mon 15/06/15
1720 | 680005 | Optimizations to Support High Latency Communications | HLcom | 2 | Rel-13 | S2 | 2015-03-05 08:00 | 2015-06-15 17:00 | 100% | SP-150252 |  | Ericsson, Hans Rönneke | hans.ronneke(at)ericsson.com | June 2015: created by MCC as a result of the split of the one-line Feature into a several-lines Feature (now Stage 2 and Stage 3 aspects); June2015: Compl:0%->100. WID: SP-150030->SP-150252 | 23.401, 23.060, 23.682 | 67 | 34 |  |  | Mon 15/06/15 | Thu 18/06/15
1721 | 680015 | CT aspects of Optimizations to Support High Latency | HLcom-CT | 2 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150399 |  | Yong Yang, Ericsson | frank.yong.yang@ericsson.com | 07/09/15: 0%->80; 7/12/15: 80%->100 | 29.274, 29.060, 29.281, 23.008, 29.272, 29.230, 29.002, 29.336, 29.xyz | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1722 | 650033 | Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1 | 1 | Rel-13 | R1,R4,R2 | 2014-09-12 08:00 | 2017-09-15 17:00 | 99% | RP-141660 | - | Ericsson | johan.bergman@ericsson.com | Triggered by Rel-12 TR 36.888 Study on Provision of low-cost MTC UEs based on LTE (FS_LC_MTC_LTE) and Low cost & enhanced coverage MTC UE for LTE (LC_MTC_UE) | LTE | 65 | 33 |  |  | Mon 16/06/14 | Sun 05/10/14
1723 | 650133 | Core part: Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1-Core | 2 | Rel-13 | R1,R2,R4 | 2014-09-12 08:00 | 2016-03-15 17:00 | 100% | RP-150492 | RP-151186 | Ericsson | johan.bergman@ericsson.com | 3/3/15: WID: RP-141865; Stat Rep: -->RP-141785 1st Apr 15: Compl:10%->25% 1st Apr 15: WID: RP-141865->RP-150492 1st Apr 15: Stat Rep: RP-141785->RP-150495 03/07/15: Compl:25%->45% 03/07/15: Stat Rep: RP-150495->RP-150583 29/09/15: Compl:45%->65% 29/09/ | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.302, 36.306, 36.321, 36.331 | 65 | 33 |  |  | Mon 16/06/14 | Tue 22/03/16
1724 | 650233 | Perf. Part: Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1-Perf | 2 | Rel-13 | R4 | 2014-09-12 08:00 | 2016-12-15 17:00 | 100% | RP-150492 |  | Ericsson | johan.bergman@ericsson.com | ; WID: RP-142043->RP-141865; Stat Rep: -->RP-141785 1st Apr 15: WID: RP-141865->RP-150492 1st Apr 15: Stat Rep: RP-141785->RP-150495 03/07/15: Stat Rep: RP-150495->RP-150583 29/09/15: Stat Rep: RP-150583->RP-151186 ;26/9/16: Compl:70%-; | 36.101, 36.104, 36.133 | 65 | 33 |  |  | Mon 16/06/14 | Tue 20/12/16
1725 | 710067 | UE Conformance Test Aspects - Further LTE Physical Layer Enhancements for MTC | LTE_MTCe2_L1-UEConTest | 2 | Rel-13 | R5 | 2016-03-15 08:00 | 2017-09-15 17:00 | 100% | RP-171156 |  | Ericsson |  | testing REL-13 LTE_MTCe2_L1-Core; 1/7/16: Compl:0%->6%; 26/; 2; 21/3/17: Compl:70% ; |  | 71 | 36 |  |  | Tue 22/03/16 | Tue 19/09/17
1726 | 690045 | EGPRS Access Security Enhancements in relation to Cellular IoT | EASE_EC_GSM | 1 | Rel-13 | S3 | 2015-09-16 08:00 | 2016-03-11 17:00 | 100% | SP-150462 |  | Vesa Torvinen, Ericsson |  | 7/12/15: 0%->5; 28/1/16: 33.420 added; 7/3/16: 5%->80; 11/6/16: 80%->98; 19/9/16: 98%->99; 21/3/17: 99%->100->99%; 7/6/17: 99%->100 | New 33.420 | 69 | 35 |  |  | Wed 16/09/15 | Wed 07/06/17
1727 | 640050 | Group based Enhancements | GROUPE | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2015-12-16 17:00 | 100% | SP-140706 | - | Huawei | ZhangWanqiang@huawei.com | - | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Fri 12/12/14
1728 | 640150 | TR for Group based Enhancements | GROUPE | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 100% | SP-140706 | - | Huawei, Wanqiang Zhang | ZhangWanqiang@huawei.com | Dec.14: 20->70%. Mar15: 90%; June2015: Compl:90%->100 | New TR 23.769 | 64 | 33 |  |  | Fri 30/05/14 | Mon 15/06/15
1729 | 640250 | Stage 2 for Group based Enhancements | GROUPE | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 100% | SP-140706 | - | Huawei | ZhangWanqiang@huawei.com | Mar15: 0->20%; June2015: Compl:20%->100 | 23.682, TBD | 64 | 33 |  |  | Fri 30/05/14 | Mon 15/06/15
1730 | 640350 | TR on Security for Group based Enhancements | GROUPE | 2 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-06-12 17:00 | 100% | SP-140706 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. 3/3/15: 5->10%.; June2015: Compl:10%->60; 11/12/15: 60%->100 | New TR 33.889 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
1731 | 640450 | Security for Group based Enhancements | GROUPE | 2 | Rel-13 | S3 | 2014-06-23 08:00 | 2015-09-16 17:00 | 100% | SP-140706 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | -; 11/12/15: 0%->100 | 33.187 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
1732 | 680016 | CT aspects of Group based Enhancements | GROUPE-CT | 2 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150816 |  | Peter Schmitt, Huawei | Peter.Schmitt@huawei.com | 7/12/15: WID:CP-150240->CP-150816 | 24.008, 24.301, 29.468, 29.272, 23.008, 29.336, 29.303, 29.002, 29.230, 29.305, 23.003 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1733 | 680028 | CT1 aspects of Group based Enhancements | GROUPE-CT | 3 | Rel-13 | C1 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150816 |  | Peter Schmitt, Huawei | Peter.Schmitt@huawei.com | 07/09/15: 0%->15; 7/12/15: 15%->100; 7/12/15: WID:CP-150240->CP-150816 | 24.008, 24.301 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1734 | 680029 | DELETED: CT3 aspects of Group based Enhancements | GROUPE-CT | 3 | Rel-13 | C3 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150816 |  | Peter Schmitt, Huawei | Peter.Schmitt@huawei.com | 7/12/15: WID:CP-150240->CP-150816. CT3 task removed | 29.468 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1735 | 680030 | CT4 aspects of Group based Enhancements | GROUPE-CT | 3 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150816 |  | Peter Schmitt, Huawei | Peter.Schmitt@huawei.com | 07/09/15: 0%->80; 7/12/15: 80%->100; 7/12/15: WID:CP-150240->CP-150816 | 29.272, 23.008, 29.336, 29.303, 29.002, 29.230, 29.305, 23.003 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1736 | 640049 | Monitoring Enhancements | MONTE | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2016-03-11 17:00 | 100% | SP-140705 | - | Intel | puneet.jain@intel.com | Linked to Rel-13 Feature Architecture Enhancements for Service Exposure (AESE). Although service requirements (TS 22.368 clause 7.2.8) are motivated by MTC, the solution may apply to normal UEs; 5/10/15: 32.278 added; | 32.278 | 64 | 33 |  |  | Fri 30/05/14 | Mon 05/10/15
1737 | 640149 | TR for Monitoring Enhancements | MONTE | 2 | Rel-13 | S2 | 2014-09-17 08:00 | 2015-06-17 17:00 | 100% | SP-140705 | - | Intel, Puneet Jain | puneet.jain@intel.com | Dec.14: 25->85%. Mar15: 100% | New TR 23.789 | 64 | 33 |  |  | Fri 30/05/14 | Mon 05/10/15
1738 | 640249 | Stage 2 for Monitoring Enhancements | MONTE | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 100% | SP-140705 | - | Intel, Puneet Jain | puneet.jain@intel.com | -; June2015: Compl:0%->100 | 23.682, TBD | 64 | 33 |  |  | Fri 30/05/14 | Mon 15/06/15
1739 | 640349 | TR on Security for Monitoring Enhancements | MONTE | 2 | Rel-13 | S3 | 2014-06-18 08:00 | 2015-06-12 17:00 | 100% | SP-140705 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs.3/3/15: 5->10%.; June2015: Compl:10%->15; 11/12/15: 15%->100 | New TR 33.889 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
1740 | 640449 | Security for Monitoring Enhancements | MONTE | 2 | Rel-13 | S3 | 2014-06-23 08:00 | 2015-09-16 17:00 | 100% | SP-140705 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | -; 11/12/15: 0%->100 | 33.187 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
1741 | 690044 | Charging aspects of MONTE | MONTE-CH | 2 | Rel-13 | S5 | 2015-09-16 08:00 | 2016-03-11 17:00 | 100% | SP-150571 | - | Huawei(Li Li, jasmine.li@huawei.com) | jasmine.li@huawei.com | 7/10/15: acronym changed from "MONTE" to "MONTE-CH"; 7/12/15: 0%->50. ES in SP-150709 (wrong UID in the ES); 7/3/16: 25%->100 | 32.27x, 32.240, 32.299, 32.298 | 69 | 35 |  |  | Fri 30/05/14 | Mon 07/03/16
1742 | 680011 | Monitoring Enhancements CT aspects | MONTE-CT | 2 | Rel-13 | C4 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150422 |  | Peter Schmitt, Huawei | peter.schmitt@huawei.com | 14/09/15: WID:CP-150396->CP-150422 |  | 68 | 35 |  |  | Mon 15/06/15 | Mon 14/09/15
1743 | 680025 | CT1 aspects of Monitoring Enhancements | MONTE-CT | 3 | Rel-13 | C1 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150422 |  | Peter Schmitt, Huawei | peter.schmitt@huawei.com | 07/09/15: 0%->95; 14/09/15: WID:CP-150396->CP-150422; 7/12/15: 95%->100 | 24.301, 24.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1744 | 680026 | CT3 aspects of Monitoring Enhancements | MONTE-CT | 3 | Rel-13 | C3 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150422 |  | Peter Schmitt, Huawei | peter.schmitt@huawei.com | 07/09/15: 0%->100; 14/09/15: WID:CP-150396->CP-150422 | 29.214, 29.213, 29.201 | 68 | 35 |  |  | Mon 15/06/15 | Mon 14/09/15
1745 | 680027 | CT4 aspects of Monitoring Enhancements | MONTE-CT | 3 | Rel-13 | C4 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150422 |  | Peter Schmitt, Huawei | peter.schmitt@huawei.com | 61907/09/15: 0%->50; 14/09/15: WID:CP-150396->CP-150422; 7/12/15: 50%->85. FCD -> 03/16, ES in CP-150619; 7/3/16: 85%->100 | New TS 29.128, 29.272, 29.002, 29.336, 29.230, 23.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
1746 | 640046 | Dedicated Core Networks | DECOR | 1 | Rel-13 | S2 | 2014-06-18 08:00 | 2016-03-11 17:00 | 100% | SP-150249 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | 06/15: WID: SP-140707-> SP-150249 | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Thu 18/06/15
1747 | 640146 | TR for Dedicated Core Networks | DECOR | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2014-12-12 17:00 | 100% | SP-150249 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | Dec.14: 30->100%. 06/15: WID: SP-140707-> SP-150249 | New TR 23.707 | 64 | 33 |  |  | Fri 30/05/14 | Thu 18/06/15
1748 | 640246 | Stage 2 for Dedicated Core Networks | DECOR | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-03-18 17:00 | 100% | SP-150249 | - | NTT DOCOMO | Daisuke Fujishima (fujishimad@nttdocomo.co.jp) | Mar15: 0->70%; June2015: Compl:70%->100, WID: SP-140707-> SP-150249 | 23.060, 23.401, 23.236 | 64 | 33 |  |  | Fri 30/05/14 | Thu 18/06/15
1749 | 690004 | CT aspects of Dedicated Core Networks | DECOR-CT | 2 | Rel-13 | ct | 2015-06-25 09:36 | 2016-03-11 17:00 | 100% | CP-150423 |  | Huawei, Xiaoyan SHI (Sean.shixiaoyan@huawei.com) | Huawei, Xiaoyan SHI (Sean.shixiaoyan@huawei.com) |  |  | 69 | 35 |  |  | Mon 07/09/15 | Mon 14/09/15
1750 | 690014 | CT1 aspects for Dedicated Core Networks CT aspects | DECOR-CT | 3 | Rel-13 | C1 | 2015-09-07 08:00 | 2015-12-17 17:00 | 100% | CP-150423 |  | Huawei |  | 7/12/15: 0%->100 | 24.301, 24.008 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/12/15
1751 | 690013 | CT4 aspects for Dedicated Core Networks CT aspects | DECOR-CT | 3 | Rel-13 | C4 | 2015-06-25 09:36 | 2016-03-11 17:00 | 100% | CP-150423 |  |  |  | 7/12/15: 70%->90. FCD -> 03/16, ES CP-150617; 7/3/16: 90%->100 | 29.274, 29.060, 23.003, 29.272, 29.002, 29.305, 23.008, 29.230, 29.303, 23.007 | 69 | 35 |  |  | Mon 07/09/15 | Mon 07/03/16
1752 | 680066 | Dedicated Core Networks RAN Aspects | DECOR-UTRA_LTE | 2 | Rel-13 | R3 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151048 | - | Ericsson |  | no Perf. part; note: DECOR is a REL-13 SA2 WI; |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
1753 | 680166 | Core part: Dedicated Core Networks | DECOR-UTRA_LTE-Core | 3 | Rel-13 | R3 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151048 | RP-151290 | Ericsson |  | no Perf. part; note: DECOR is a REL-13 SA2 WI; 29/09/15: Compl:0%->30% 29/09/15: Stat Rep: -->RP-1512901/1/16: Compl:30%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
1754 | 610030 | Service Exposure and Enablement Support | SEES | 1 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-09-17 17:00 | 100% | SP-130505 | S1-143301 | KPN | toon.norp@tno.nl | SP#62 completion 06/14=>09/14. Linked to Rel-12 Study TR 22.888 (FS_MTCe) and to Features Rel-11 SIMTC & Rel-12 MTCe and MOSAP | Stage 1 | 61 | 31 |  |  | Mon 26/08/13 | Tue 26/11/13
1755 | 610130 | TR on Stage 1 for Service Exposure and Enablement Support | SEES | 2 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130505 | S1-143301 | KPN | toon.norp@tno.nl | SP#64 completed. TR 22.853v200 for Approval. External requirements from oneM2M TR0001(oneM2M Use Case collection), TS0002 (M2M Requirements) | New TR 22.853 | 61 | 31 |  |  | Mon 26/08/13 | Tue 27/05/14
1756 | 610230 | Stage 1 for Service Exposure and Enablement Support | SEES | 2 | Rel-13 | S1 | 2013-09-12 08:00 | 2014-09-17 17:00 | 100% | SP-130505 | S1-143301 | KPN | toon.norp@tno.nl | SP#65 completed | 22.101, 22.115, 22.368, TBD | 61 | 31 |  |  | Mon 26/08/13 | Thu 28/08/14
1757 | 640048 | Architecture Enhancements for Service capability Exposure | AESE | 1 | Rel-13 | S2,S3 | 2014-06-18 08:00 | 2016-03-11 17:00 | 100% | SP-140704 | - | Intel | puneet.jain@intel.com | - | Stage 2 | 64 | 33 |  |  | Fri 30/05/14 | Fri 12/12/14
1758 | 640148 | TR for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S2 | 2014-06-18 08:00 | 2015-03-18 17:00 | 100% | SP-140704 | - | Intel, Puneet Jain | puneet.jain@intel.com | Dec.14: 30->65%. Mar15: 75%; June2015: Compl:75%->100 | New TR 23.708 | 64 | 33 |  |  | Fri 30/05/14 | Mon 15/06/15
1759 | 640248 | Stage 2 for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S2 | 2014-06-23 08:00 | 2015-06-17 17:00 | 100% | SP-140704 | - | Intel, Puneet Jain | puneet.jain@intel.com | -; June2015: Compl:0%->100 | TS 23.682, TS 33.187 | 64 | 33 |  |  | Fri 30/05/14 | Mon 15/06/15
1760 | 640348 | TR on Security for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S3 | 2014-06-23 08:00 | 2015-06-17 17:00 | 100% | SP-140704 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. Dec.14: 0->40%. 3/3/15: 45%.; June2015: Compl:45%->60; 11/12/15: 60%->100 | New TR 33.889 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
1761 | 640448 | Security for Architecture Enhancements for Service capability Exposure | AESE | 2 | Rel-13 | S3 | 2014-06-23 08:00 | 2015-09-16 17:00 | 100% | SP-140704 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | -; 11/12/15: 0%->100 | 33.187 | 64 | 33 |  |  | Fri 30/05/14 | Fri 11/12/15
1762 | 680001 | CT aspects of Architecture Enhancements for Service capability Exposure | AESE-CT | 2 | Rel-13 | C3 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150576 |  | Yizhuang Wu, Huawei | wuyizhuang@huawei.com | 14/09/15: WID:CP-150402->CP-150487->CP-150576 |  | 68 | 35 |  |  | Mon 15/06/15 | Mon 14/09/15
1763 | 680023 | CT3 aspects of Architecture Enhancements for Service capability Exposure | AESE-CT | 3 | Rel-13 | C3 | 2015-06-15 08:00 | 2016-03-11 17:00 | 100% | CP-150576 |  | Yizhuang Wu, Huawei. FCD+3, ES in 642 | wuyizhuang@huawei.com | 07/09/15: 0%->35; 14/09/15: WID:CP-150402->CP-150487->CP-150576; 7/12/15: 35%->90; 7/3/16: 90%->100 | 29.154 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/03/16
1764 | 680024 | CT4 aspects of Architecture Enhancements for Service capability Exposure | AESE-CT | 3 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-12-16 17:00 | 100% | CP-150576 |  | Yizhuang Wu, Huawei | wuyizhuang@huawei.com | 07/09/15: 0%->40; 14/09/15: WID:CP-150402->CP-150487->CP-150576; 7/12/15: 40%->100 | 29.201, 29.336, 29.230, 29.272, 23.008 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
1765 | 621000 | Rel-13 LTE Carrier Aggregation (CA) | LTE_CA_Rel13 | 1 | Rel-13 | R4 | 2013-12-09 08:00 | 2018-12-14 17:00 | 93% | - | - | - | - | Acronym changed from "LTE_CA_Rel-13" to "LTE_CA_Rel13" |  | 58 | 30 |  |  | Fri 14/12/12 | Thu 15/01/15
1766 | 690080 | LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12 | LTE_CA_B4_B4_B5_B12 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151208 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
1767 | 690180 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12 | LTE_CA_B4_B4_B5_B12-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151208 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
1768 | 690280 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12 | LTE_CA_B4_B4_B5_B12-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151208 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
1769 | 690081 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5 | LTE_CA_B2_B4_B4_B5 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151210 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
1770 | 690181 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5 | LTE_CA_B2_B4_B4_B5-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151210 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
1771 | 690281 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5 | LTE_CA_B2_B4_B4_B5-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151210 | - | US Cellular |  | 13/6/16: moved from Rel-14 to Rel-13 (was a mistake) |  | 69 | 35 |  |  | Tue 29/09/15 | Mon 13/06/16
1772 | 620023 | LTE Advanced inter-band CA of Band 8 and Band 27 | LTE_CA_B8_B27 | 2 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-12-15 17:00 | 30% | RP-140120 | - | KT | ilwhan.kim@kt.com | Inter-band CA 2DL/1UL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 09/09/14
1773 | 620123 | Core part:LTE Advanced inter-band CA of Band 8 and Band 27 | LTE_CA_B8_B27-Core | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-12-15 17:00 | 30% | RP-140120 | RP-151131 | KT | ilwhan.kim@kt.com | CD:Thu 18/06/15->Mon 15/06/15; Compl:10%->10%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->15% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:15%->30% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053 | 36.101, 36.104, 36.133, generic TR 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Tue 29/09/15
1774 | 620223 | Perf. part:LTE Advanced inter-band CA of Band 8 and Band 27 | LTE_CA_B8_B27-Perf | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-12-15 17:00 | 30% | RP-140120 | RP-151131 | KT | ilwhan.kim@kt.com | CD:Thu 18/06/15->Mon 15/06/15; Compl:10%->10%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->15% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:15%->30% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053 | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Tue 29/09/15
1775 | 620032 | LTE Advanced 3 band CA (3DL/1UL) for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27 | 2 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-12-15 17:00 | 25% | RP-131754 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 09/09/14
1776 | 620132 | Core part:LTE Advanced 3 band CA (3DL/1UL) for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27-Core | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-12-15 17:00 | 25% | RP-131754 | RP-151131 | KT | Chungwoo HWANG (cwhwang@kt.com) | CD:Thu 18/06/15->Mon 15/06/15; Compl:25%->25%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:25%->30% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:30%->25% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Tue 29/09/15
1777 | 620232 | Perf. part:LTE Advanced 3 band CA (3DL/1UL) for Band 3, Band 8 and Band 27 | LTE_CA_B3_B8_B27-Perf | 3 | Rel-13 | R4 | 2013-12-09 08:00 | 2015-12-15 17:00 | 25% | RP-131754 | RP-151131 | KT | Chungwoo HWANG (cwhwang@kt.com) | CD:Thu 18/06/15->Mon 15/06/15; Compl:25%->25%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:25%->30% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:30%->25% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-15053 | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Tue 29/09/15
1778 | 630033 | LTE Advanced inter-band CA of Band 7 and Band 22 | LTE_CA_B7_B22 | 2 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-06-15 17:00 | 100% | RP-140094 | - | Orange, Ericsson | erika.tejedor@ericsson.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
1779 | 630133 | Core part:LTE Advanced inter-band CA of Band 7 and Band 22 | LTE_CA_B7_B22-Core | 3 | Rel-13 | R4 | 2014-03-06 08:00 | 2015-06-15 17:00 | 100% | RP-140094 | RP-150536 | Orange, Ericsson | erika.tejedor@ericsson.com | CD:Thu 11/12/14->Mon 15/06/15; Compl:10%->10%; Stat Rep: RP-141084->RP-141732 03/07/15: Compl:10%->100% 03/07/15: Stat Rep: RP-141732->RP-150536 | 36.101, 36.104, 36.133, generic TR 36.851 (2 Band CA with 1UL), | 63 | 32 |  |  | Mon 10/03/14 | Thu 18/06/15
1780 | 630233 | Perf. part:LTE Advanced inter-band CA of Band 7 and Band 22 | LTE_CA_B7_B22-Perf | 3 | Rel-13 | R4 | 2014-03-11 08:00 | 2015-06-15 17:00 | 100% | RP-140094 | RP-150536 | Orange, Ericsson | erika.tejedor@ericsson.com | CD:Thu 11/12/14->Mon 15/06/15; Compl:0%->0%; Stat Rep: RP-141084->RP-141732 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-141732->RP-150536 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Thu 18/06/15
1781 | 640022 | LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12 | 2 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-06-15 17:00 | 100% | RP-141232 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Sun 21/09/14
1782 | 640122 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12-Core | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-06-15 17:00 | 100% | RP-141232 | RP-150536 | U.S. Cellular | sebastian.thalanany@uscellular.com | CD:Thu 12/03/15->Sun 15/03/15; Compl:0%->40%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:40%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, 36.141, 36.307, generic new Rel-13 TR36.8xy [similar to Rel-12 TR 36.853 (3 Band CA with 1UL)] | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1783 | 640222 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 2 and Band 12 | LTE_CA_B2_B2_B12-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-06-15 17:00 | 100% | RP-141232 | RP-150536 | U.S. Cellular | sebastian.thalanany@uscellular.com | CD:Thu 18/06/15->Mon 15/06/15; Compl:0%->10%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:10%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1784 | 640025 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8 | 2 | Rel-13 | R4 | 2014-06-16 08:00 | 2015-06-15 17:00 | 100% | RP-140692 | - | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
1785 | 640125 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8-Core | 3 | Rel-13 | R4 | 2014-06-16 08:00 | 2015-06-15 17:00 | 100% | RP-150874 | RP-150536 | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | ; WID: RP-142043->RP-141832; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:60%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-141832->RP-150874 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1786 | 640225 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 3 and Band 8 | LTE_CA_B3_B3_B8-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-06-15 17:00 | 100% | RP-150874 | RP-150536 | CHTTL | Po-Han Hsieh (pohanhsieh@cht.com.tw) | ; WID: RP-142043->RP-141832; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-141832->RP-150874 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1787 | 640032 | LTE Advanced 3 Band CA (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42 | 2 | Rel-13 | R4 | 2014-06-16 08:00 | 2015-06-15 17:00 | 100% | RP-140974 | - | Huawei | leo.liuye@huawei.com | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
1788 | 640132 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42-Core | 3 | Rel-13 | R4 | 2014-06-16 08:00 | 2015-06-15 17:00 | 100% | RP-140974 | RP-150536 | Huawei | leo.liuye@huawei.com | CD:Thu 11/12/14->Sun 15/03/15; Compl:30%->50%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:50%->60% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:60%->100% 03/07/15: Stat Rep: RP-150013->RP-15 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1789 | 640232 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 41, Band 42 and Band 42 | LTE_CA_B41_B42_B42-Perf | 3 | Rel-13 | R4 | 2014-06-18 08:00 | 2015-06-15 17:00 | 100% | RP-140974 | RP-150536 | Huawei | leo.liuye@huawei.com | CD:Thu 11/12/14->Sun 15/03/15; Compl:0%->0%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:0%->60% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:60%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1790 | 650037 | LTE Advanced inter-band CA of Band 3 and Band 38 | LTE_CA_B3_B38 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141129 | - | Nokia Networks | iwajlo.angelow@nsn.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1791 | 650137 | Core part:LTE Advanced inter-band CA of Band 3 and Band 38 | LTE_CA_B3_B38-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-150717 | RP-150536 | Nokia Networks | iwajlo.angelow@nsn.com | CD:Thu 11/12/14->Sun 15/03/15; Compl:0%->90%; Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:90%->100% 03/07/15: WID: RP-141129->RP-150717 03/07/15: Stat Rep: RP-150013->RP-15 | 36.101, 36.104, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1792 | 650237 | Perf. Part:LTE Advanced inter-band CA of Band 3 and Band 38 | LTE_CA_B3_B38-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-150717 | RP-150536 | Nokia Networks | iwajlo.angelow@nsn.com | CD:Thu 11/12/14->Sun 15/03/15; Compl:0%->90%; Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:90%->100% 03/07/15: WID: RP-141129->RP-150717 03/07/15: Stat Rep: RP-150013->RP-15 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1793 | 650038 | LTE Advanced inter-band CA of Band 2 and Band 28 | LTE_CA_B2_B28 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141145 | - | Huawei | alf.ahlstrom@huawei.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1794 | 650138 | Core part:LTE Advanced inter-band CA of Band 2 and Band 28 | LTE_CA_B2_B28-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141145 | RP-150536 | Huawei | alf.ahlstrom@huawei.com | CD:Fri 11/12/15->Sun 15/03/15; Compl:0%->50%; Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1795 | 650238 | Perf. Part:LTE Advanced inter-band CA of Band 2 and Band 28 | LTE_CA_B2_B28-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141145 | RP-150536 | Huawei | alf.ahlstrom@huawei.com | CD:Thu 12/03/15->Sun 15/03/15; Compl:0%->0%; Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1796 | 650039 | LTE Advanced inter-band CA of Band 4 and Band 28 | LTE_CA_B4_B28 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141146 | - | Huawei | alf.ahlstrom@huawei.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1797 | 650139 | Core part:LTE Advanced inter-band CA of Band 4 and Band 28 | LTE_CA_B4_B28-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141146 | RP-150536 | Huawei | alf.ahlstrom@huawei.com | CD:Fri 11/12/15->Sun 15/03/15; Compl:0%->35%; Stat Rep: -->RP-141732 1st Apr 15: Compl:35%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1798 | 650239 | Perf. Part:LTE Advanced inter-band CA of Band 4 and Band 28 | LTE_CA_B4_B28-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141146 | RP-150536 | Huawei | alf.ahlstrom@huawei.com | CD:Thu 12/03/15->Sun 15/03/15; Compl:0%->0%; Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1799 | 650040 | LTE Advanced inter-band CA of Band 20 and Band 40 | LTE_CA_B20_B40 | 2 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-12-15 17:00 | 100% | RP-141168 | - | Ericsson | imadur.rahman@ericsson.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1800 | 650140 | Core part:LTE Advanced inter-band CA of Band 20 and Band 40 | LTE_CA_B20_B40-Core | 3 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-12-15 17:00 | 100% | RP-141168 | RP-151131 | Ericsson | imadur.rahman@ericsson.com | CD:Wed 11/03/15->Sun 15/03/15; Compl:0%->30%; Stat Rep: -->RP-141732 1st Apr 15: Compl:30%->70% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013-> | 36.101, 36.104, 36.133, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
1801 | 650240 | Perf. Part:LTE Advanced inter-band CA of Band 20 and Band 40 | LTE_CA_B20_B40-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-141168 | RP-151131 | Ericsson | imadur.rahman@ericsson.com | CD:Thu 12/03/15->Sun 15/03/15; Compl:0%->0%; Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:0%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-1 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
1802 | 650041 | LTE Advanced inter-band CA of Band 1 and Band 40 | LTE_CA_B1_B40 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-141312 | - | KT | ilwhan.kim@kt.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1803 | 650141 | Core part:LTE Advanced inter-band CA of Band 1 and Band 40 | LTE_CA_B1_B40-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-141312 | RP-151131 | KT | ilwhan.kim@kt.com | CD:Fri 12/06/15->Mon 15/06/15; Compl:0%->70%; Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/1 | 36.101, 36.104, 36.133, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
1804 | 650241 | Perf. Part:LTE Advanced inter-band CA of Band 1 and Band 40 | LTE_CA_B1_B40-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-141312 | RP-151131 | KT | ilwhan.kim@kt.com | CD:Fri 11/12/15->Mon 15/06/15; Compl:0%->70%; Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->70% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/1 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Fri 01/01/16
1805 | 650042 | LTE Advanced inter-band CA of Band 3 and Band 40 | LTE_CA_B3_B40 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141674 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1806 | 650142 | Core part:LTE Advanced inter-band CA of Band 3 and Band 40 | LTE_CA_B3_B40-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-150832 | RP-150536 | KT | Chungwoo HWANG (cwhwang@kt.com) | CD:Fri 11/12/15->Mon 15/06/15; Compl:0%->70%; Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: WID: RP-141674->RP-150832 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1807 | 650242 | Perf. Part:LTE Advanced inter-band CA of Band 3 and Band 40 | LTE_CA_B3_B40-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-150832 | RP-150536 | KT | Chungwoo HWANG (cwhwang@kt.com) | CD:Fri 12/06/15->Mon 15/06/15; Compl:0%->70%; Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->80% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: WID: RP-141674->RP-150832 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1808 | 650043 | LTE Advanced inter-band CA of Band 20 and Band 31 | LTE_CA_B20_B31 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141336 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1809 | 650143 | Core part:LTE Advanced inter-band CA of Band 20 and Band 31 | LTE_CA_B20_B31-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-142007 | RP-150536 | Huawei | Liu Liehai (liuliehai@huawei.com) | ; WID: RP-142043->RP-142007; Stat Rep: -->RP-141732 1st Apr 15: Compl:75%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1810 | 650243 | Perf. Part:LTE Advanced inter-band CA of Band 20 and Band 31 | LTE_CA_B20_B31-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-142007 | RP-150536 | Huawei | Liu Liehai (liuliehai@huawei.com) | ; WID: RP-142043->RP-142007; Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1811 | 650044 | LTE Advanced inter-band CA of Band 3 and Band 31 | LTE_CA_B3_B31 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141337 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1812 | 650144 | Core part:LTE Advanced inter-band CA of Band 3 and Band 31 | LTE_CA_B3_B31-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-150318 | RP-150536 | Huawei | Liu Liehai (liuliehai@huawei.com) | CD:Fri 11/12/15->Sun 15/03/15; Compl:0%->50%; Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->75% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141337->RP-150318 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:75%->100% 03/07/1 | 36.101, 36.104, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1813 | 650244 | Perf. Part:LTE Advanced inter-band CA of Band 3 and Band 31 | LTE_CA_B3_B31-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-150318 | RP-150536 | Huawei | Liu Liehai (liuliehai@huawei.com) | CD:Thu 12/03/15->Sun 15/03/15; Compl:0%->0%; Stat Rep: -->RP-141732 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141337->RP-150318 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-15 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1814 | 650045 | LTE Advanced inter-band CA of Band 5 and Band 40 | LTE_CA_B5_B40 | 2 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-06-15 17:00 | 100% | RP-141675 | - | SK Telecom | haesung.park@sk.com | Inter-band CA 2DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1815 | 650145 | Core part:LTE Advanced inter-band CA of Band 5 and Band 40 | LTE_CA_B5_B40-Core | 3 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-06-15 17:00 | 100% | RP-150285 | RP-150536 | SK Telecom | haesung.park@sk.com | ; WID: RP-142043->RP-141888; Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->80% 1st Apr 15: WID: RP-141888->RP-150285 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1816 | 650245 | Perf. Part:LTE Advanced inter-band CA of Band 5 and Band 40 | LTE_CA_B5_B40-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-150285 | RP-150536 | SK Telecom | haesung.park@sk.com | ; WID: RP-142043->RP-141888; Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->80% 1st Apr 15: WID: RP-141888->RP-150285 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1817 | 650047 | LTE Advanced intra-band contiguous CA in Band 42 for 3DL | LTE_CA_C_B42_3DL | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141677 | - | CATT | Yuexia Song (songyuexia@catt.cn) | Intra-band contig. CA 3DL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1818 | 650147 | Core part: LTE Advanced intra-band contiguous CA in Band 42 for 3DL | LTE_CA_C_B42_3DL-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-151027 | RP-150536 | CATT | Yuexia Song (songyuexia@catt.cn) | CD:Fri 12/06/15->Mon 15/06/15; Compl:0%->70%; Stat Rep: -->RP-141732 1st Apr 15: Compl:70%->99% 1st Apr 15: WID: RP-141677->RP-150319 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-150319->RP-151027 03/07/15: Sta | 36.101, 36.104, 36.133, New TR 36.833-5-42 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1819 | 650247 | Perf. Part: LTE Advanced intra-band contiguous CA in Band 42 for 3DL | LTE_CA_C_B42_3DL-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-151027 | RP-150536 | CATT | Yuexia Song (songyuexia@catt.cn) | CD:Fri 12/06/15->Mon 15/06/15; Compl:0%->0%; Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: WID: RP-141677->RP-150319 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-150319->RP-151027 03/07/15: Stat | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1820 | 650049 | LTE Advanced 3 Band CA (3DL/1UL) of Band 8, Band 41 and Band 41 | LTE_CA_B8_B41_B41 | 2 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-06-15 17:00 | 100% | RP-141290 | - | China Mobile | PAN, Qun (panqun@chinamobile.com) | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1821 | 650149 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 8, Band 41 and Band 41 | LTE_CA_B8_B41_B41-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141845 | RP-150536 | China Mobile | PAN, Qun (panqun@chinamobile.com) | ; WID: RP-142043->RP-141845; Stat Rep: -->RP-141732 1st Apr 15: Compl:80%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1822 | 650249 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 8, Band 41 and Band 41 | LTE_CA_B8_B41_B41-Perf | 3 | Rel-13 | R4 | 2014-09-12 08:00 | 2015-06-15 17:00 | 100% | RP-141845 | RP-150536 | China Mobile | PAN, Qun (panqun@chinamobile.com) | ; WID: RP-142043->RP-141845; Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1823 | 650051 | LTE Advanced 3 Band CA (3DL/1UL) of Band 38, Band 40 and Band 40 | LTE_CA_B38_B40_B40 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141655 | - | Samsung | xutao.zhou@samsung.com | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1824 | 650151 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 38, Band 40 and Band 40 | LTE_CA_B38_B40_B40-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141655 | RP-150536 | Samsung | xutao.zhou@samsung.com | CD:Fri 12/06/15->Mon 15/06/15; Compl:0%->0%; Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->70% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:70%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1825 | 650251 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 38, Band 40 and Band 40 | LTE_CA_B38_B40_B40-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141655 | RP-150536 | Samsung | xutao.zhou@samsung.com | CD:Fri 12/06/15->Mon 15/06/15; Compl:0%->0%; Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->70% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:70%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1826 | 650053 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 5 and Band 29 | LTE_CA_B2_B5_B29 | 2 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141667 | - | Huawei | SHAN Huiping (shanhuiping@huawei.com) | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
1827 | 650153 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 5 and Band 29 | LTE_CA_B2_B5_B29-Core | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141667 | RP-150536 | Huawei | SHAN Huiping (shanhuiping@huawei.com) | CD:Fri 11/12/15->Mon 15/06/15; Compl:0%->50%; Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.101, 36.104, 36.133, New TR 36.8xy (inter-band CA 2DL/1UL (introduce CA_B5-B29), New TR 36.8xz (inter-band CA 3DL/1UL) | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1828 | 650253 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 5 and Band 29 | LTE_CA_B2_B5_B29-Perf | 3 | Rel-13 | R4 | 2014-09-15 08:00 | 2015-06-15 17:00 | 100% | RP-141667 | RP-150536 | Huawei | SHAN Huiping (shanhuiping@huawei.com) | CD:Fri 12/06/15->Mon 15/06/15; Compl:0%->0%; Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Thu 18/06/15
1829 | 660072 | LTE CA Enhancement Beyond 5 Carriers | LTE_CA_enh_b5C | 2 | Rel-13 |  | 2014-12-15 08:00 | 2018-09-14 17:00 | 65% | RP-142286 |  | Nokia Networks | Nokia | FCD: 06/16->12/15, Rel-14?->Rel-13 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 15/01/15
1830 | 660172 | Core part: LTE CA Enhancement Beyond 5 Carriers | LTE_CA_enh_b5C-Core | 3 | Rel-13 | R1 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-151984 | RP-151285 | Nokia Networks | Nokia | FCD: 06/16->12/15, Rel-14?->Rel-13 1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142286->RP-150277 1st Apr 15: Stat Rep: ->RP-150272 03/07/15: Compl:10%->40% 03/07/15: WID: RP-150277->RP-150771 03/07/15: Stat Rep: RP-150272->RP-150769 29/09/15: Compl:4 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1831 | 660272 | Perf. part: LTE CA Enhancement Beyond 5 Carriers | LTE_CA_enh_b5C-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-06-15 17:00 | 100% | RP-151984 | RP-151285 | Nokia Networks | Nokia | 1st Apr 15: WID: RP-142286->RP-150277 1st Apr 15: Stat Rep: ->RP-150272 03/07/15: WID: RP-150277->RP-150771 03/07/15: Stat Rep: RP-150272->RP-150769 29/09/15: Stat Rep: RP-150769->RP-151285; 22/3/16: ; |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/07/16
1832 | 730074 | UE Conformance Test Aspects - LTE CA Enhancement Beyond 5 Carriers: PUCCH on Scell | LTE_CA_enh_b5C_PUCCH-UEConTest | 3 | Rel-13 | R5 | 2016-09-15 08:00 | 2018-09-14 17:00 | 20% | RP-171764 |  | Huawei |  | ; 20/12/16: Compl:0%->5%19/6/17: Compl:5%->8%; 19/9/17: Compl:8%->15%; 8/1/18: 27/3/18 |  | 66 |  |  |  | Mon 26/09/16 | Tue 27/03/18
1833 | 660080 | HSPA Dual-Band UL CA | HSUPA_DB_MC | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-142237 |  | Qualcomm | Qualcomm |  |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 15/01/15
1834 | 660180 | Core part: HSPA Dual-Band UL CA | HSUPA_DB_MC-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-151852 | RP-151281 | Qualcomm | Qualcomm | 1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142237->RP-150129 1st Apr 15: Stat Rep: ->RP-150127 03/07/15: Compl:10%->40% 03/07/15: Stat Rep: RP-150127->RP-150761 29/09/15: Compl:40%->50% 29/09/15: Stat Rep: RP-150761->RP-151281; |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1835 | 660280 | Perf. part: HSPA Dual-Band UL CA | HSUPA_DB_MC-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-151852 | RP-151281 | Qualcomm | Qualcomm | 1st Apr 15: WID: RP-142237->RP-150129 1st Apr 15: Stat Rep: ->RP-150127 03/07/15: Stat Rep: RP-150127->RP-150761 29/09/15: Stat Rep: RP-150761->RP-1512811/1/16: Compl:0%->90% ; |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
1836 | 660081 | LTE Advanced inter-band CA of Band 25 and Band 26 | LTE_CA_B25_B26 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142020 |  | Sprint | Sprint |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1837 | 660181 | Core part:LTE Advanced inter-band CA of Band 25 and Band 26 | LTE_CA_B25_B26-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150115 | RP-150536 | Sprint | Sprint | 1st Apr 15: Compl:0%->95% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142020->RP-150115 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1838 | 660281 | Perf. part:LTE Advanced inter-band CA of Band 25 and Band 26 | LTE_CA_B25_B26-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150115 | RP-150536 | Sprint | Sprint | 1st Apr 15: Compl:0%->95% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142020->RP-150115 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1839 | 660082 | LTE Advanced inter-band CA of Band 3 and Band 41 | LTE_CA_B3_B41 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142239 |  | China Telecom | China Telecom |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1840 | 660182 | Core part:LTE Advanced inter-band CA of Band 3 and Band 41 | LTE_CA_B3_B41-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-151446 | RP-151131 | China Telecom | China Telecom | 1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131; 29/09/1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1841 | 660282 | Perf. part:LTE Advanced inter-band CA of Band 3 and Band 41 | LTE_CA_B3_B41-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-151446 | RP-151131 | China Telecom | China Telecom | 1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131; 29/09/1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1842 | 660083 | LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 3 and Band 3 | LTE_CA_B1_B3_B3 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-141777 |  | China Unicom | China Unicom |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1843 | 660183 | Core part:LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 3 and Band 3 | LTE_CA_B1_B3_B3-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-141777 | RP-151131 | China Unicom | China Unicom | 1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
1844 | 660283 | Perf. part:LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 3 and Band 3 | LTE_CA_B1_B3_B3-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-141777 | RP-151131 | China Unicom | China Unicom | 03/07/15: Compl:0%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
1845 | 660084 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 19 and Band 28 | LTE_CA_B1_B19_B28 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-141791 |  | NTT DOCOMO | NTT DOCOMO |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1846 | 660184 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 19 and Band 28 | LTE_CA_B1_B19_B28-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-150639 | RP-151131 | NTT DOCOMO | NTT DOCOMO | 1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141791->RP-150639 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP- |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
1847 | 660284 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 19 and Band 28 | LTE_CA_B1_B19_B28-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-150639 | RP-151131 | NTT DOCOMO | NTT DOCOMO | 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141791->RP-150639 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
1848 | 660085 | LTE Advanced 3 Band CA (3DL/1UL) of Band 21, Band 42 and Band 42 | LTE_CA_B21_B42_B42 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-141792 |  | NTT DOCOMO | NTT DOCOMO |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1849 | 660185 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 21, Band 42 and Band 42 | LTE_CA_B21_B42_B42-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150640 | RP-150536 | NTT DOCOMO | NTT DOCOMO | 1st Apr 15: Compl:0%->90% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:90%->100% 03/07/15: WID: RP-141792->RP-150640 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1850 | 660285 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 21, Band 42 and Band 42 | LTE_CA_B21_B42_B42-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150640 | RP-150536 | NTT DOCOMO | NTT DOCOMO | 03/07/15: Compl:0%->100% 03/07/15: WID: RP-141792->RP-150640 03/07/15: Stat Rep: ->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1851 | 660086 | LTE Advanced 3 Band CA (3DL/1UL) of Band 7, Band 40 and Band 40 | LTE_CA_B7_B40_B40 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-141802 |  | ZTE | ZTE |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1852 | 660186 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 7, Band 40 and Band 40 | LTE_CA_B7_B40_B40-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-150614 | RP-151131 | ZTE | ZTE | 1st Apr 15: Compl:0%->40% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->75% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141802->RP-150614 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:75%->100% 29/09/15: Stat Rep: RP- |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
1853 | 660286 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 7, Band 40 and Band 40 | LTE_CA_B7_B40_B40-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-150614 | RP-151131 | ZTE | ZTE | 1st Apr 15: Compl:0%->40% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->75% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141802->RP-150614 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:75%->100% 29/09/15: Stat Rep: RP- |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
1854 | 660087 | LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 8 and Band 28 | LTE_CA_B1_B8_B28 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 40% | RP-141826 |  | Softbank Mobile | Softbank Mobile |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1855 | 660187 | Core part:LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 8 and Band 28 | LTE_CA_B1_B8_B28-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 40% | RP-150447 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1856 | 660287 | Perf. part:LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 8 and Band 28 | LTE_CA_B1_B8_B28-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 40% | RP-150447 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1857 | 660088 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7_Bwset | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-141881 |  | Ericsson | Ericsson | Acronym changed from LTE_CA_B3_B7_B7 |  | 66 | 34 |  |  | Mon 12/01/15 | Wed 18/03/15
1858 | 660188 | Core part: Additional bandwidth combination set for LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7_Bwset-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-141881 | RP-150536 | Ericsson | Ericsson | Acronym changed from LTE_CA_B3_B7_B7-Core 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1859 | 660288 | Perf. Part: Additional bandwidth combination set for LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7_BWset-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-141881 | RP-150536 | Ericsson | Ericsson | Acronym changed from LTE_CA_B3_B7_B7-Perf 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1860 | 660089 | LTE Advanced 3 Band CA (3DL/1UL) of Band 7, Band 7 and Band 28 | LTE_CA_B7_B7_B28 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-141882 |  | Ericsson | Ericsson |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1861 | 660189 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 7, Band 7 and Band 28 | LTE_CA_B7_B7_B28-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-141882 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1862 | 660289 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 7, Band 7 and Band 28 | LTE_CA_B7_B7_B28-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-141882 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1863 | 660090 | LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 3 and Band 40 | LTE_CA_B1_B3_B40 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-141946 |  | KT | KT |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1864 | 660190 | Core part:LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 3 and Band 40 | LTE_CA_B1_B3_B40-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-151258 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141946->RP-151258 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1865 | 660290 | Perf. part:LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 3 and Band 40 | LTE_CA_B1_B3_B40-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-151258 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141946->RP-151258 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1866 | 660091 | LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 8 and Band 40 | LTE_CA_B1_B8_B40 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-141947 |  | KT | KT |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1867 | 660191 | Core part:LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 8 and Band 40 | LTE_CA_B1_B8_B40-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-151259 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141947->RP-151259 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1868 | 660291 | Perf. part:LTE Advanced 3 band CA (3DL/1UL) of Band 1, Band 8 and Band 40 | LTE_CA_B1_B8_B40-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-151259 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141947->RP-151259 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1869 | 660092 | LTE Advanced 3 band CA (3DL/1UL) of Band 3, Band 8 and Band 40 | LTE_CA_B3_B8_B40 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-141949 |  | KT | KT |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1870 | 660192 | Core part:LTE Advanced 3 band CA (3DL/1UL) of Band 3, Band 8 and Band 40 | LTE_CA_B3_B8_B40-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-151261 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->95% 29/09/15: WID: RP-141949->RP-151261 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1871 | 660292 | Perf. part:LTE Advanced 3 band CA (3DL/1UL) of Band 3, Band 8 and Band 40 | LTE_CA_B3_B8_B40-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-151261 | RP-151131 | KT | KT | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->90% 29/09/15: WID: RP-141949->RP-151261 29/09/15: Stat Rep: RP-1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1872 | 660093 | LTE Advanced 3 Band CA (3DL) of Band 3, Band 7 and Band 8 | LTE_CA_B3_B7_B8 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142013 |  | Ericsson | Ericsson |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1873 | 660193 | Core part:LTE Advanced 3 Band CA (3DL) of Band 3, Band 7 and Band 8 | LTE_CA_B3_B7_B8-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142013 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->95% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:95%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1874 | 660293 | Perf. part:LTE Advanced 3 Band CA (3DL) of Band 3, Band 7 and Band 8 | LTE_CA_B3_B7_B8-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142013 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1875 | 660094 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 28 | LTE_CA_B1_B3_B28 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142038 |  | Nokia Networks | Nokia Networks |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1876 | 660194 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 28 | LTE_CA_B1_B3_B28-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150719 | RP-150536 | Nokia Networks | Nokia Networks | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-142038->RP-150719 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1877 | 660294 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 28 | LTE_CA_B1_B3_B28-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150719 | RP-150536 | Nokia Networks | Nokia Networks | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: WID: RP-142038->RP-150719 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1878 | 660095 | LTE Advanced 3 band CA (3DL/1UL) of Band 3, Band 8 and Band 28 | LTE_CA_B3_B8_B28 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 40% | RP-142193 |  | Softbank Mobile | Softbank Mobile |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1879 | 660195 | Core part:LTE Advanced 3 band CA (3DL/1UL) of Band 3, Band 8 and Band 28 | LTE_CA_B3_B8_B28-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 40% | RP-142193 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131; |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1880 | 660295 | Perf. part:LTE Advanced 3 band CA (3DL/1UL) of Band 3, Band 8 and Band 28 | LTE_CA_B3_B8_B28-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 40% | RP-142193 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1881 | 660096 | LTE Advanced 3 Band CA (3DL/1UL) of Band 8, Band 42 and Band 42 | LTE_CA_B8_B42_B42 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-142194 |  | Softbank Mobile | Softbank Mobile |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1882 | 660196 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 8, Band 42 and Band 42 | LTE_CA_B8_B42_B42-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-142194 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/ |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
1883 | 660296 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 8, Band 42 and Band 42 | LTE_CA_B8_B42_B42-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-142194 | RP-151131 | Softbank Mobile | Softbank Mobile | 1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131; |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
1884 | 660097 | LTE Advanced 3 Band CA (3DL/1UL) of Band 28, Band 40 and Band 40 | LTE_CA_B28_B40_B40 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142206 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1885 | 660197 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 28, Band 40 and Band 40 | LTE_CA_B28_B40_B40-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150676 | RP-151131 | Huawei | Huawei | 1st Apr 15: Compl:0%->30% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142206->RP-150233 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:30%->60% 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: WID: RP-150233->RP-150676 03/07/15: |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1886 | 660297 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 28, Band 40 and Band 40 | LTE_CA_B28_B40_B40-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150676 | RP-151131 | Huawei | Huawei | 1st Apr 15: WID: RP-142206->RP-150233 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: WID: RP-150233->RP-150676 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131; |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1887 | 660098 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 40 and Band 40 | LTE_CA_B3_B40_B40 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142207 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1888 | 660198 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 40 and Band 40 | LTE_CA_B3_B40_B40-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-151071 | RP-150536 | Huawei | Huawei | 1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->100% 03/07/15: WID: RP-142207->RP-151071 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1889 | 660298 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 40 and Band 40 | LTE_CA_B3_B40_B40-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-151071 | RP-150536 | Huawei | Huawei | 03/07/15: Compl:0%->100% 03/07/15: WID: RP-142207->RP-151071 03/07/15: Stat Rep: ->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1890 | 660099 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 7 and Band 28 | LTE_CA_B1_B7_B28 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142208 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1891 | 660199 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 7 and Band 28 | LTE_CA_B1_B7_B28-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150234 | RP-150536 | Huawei | Huawei | 1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: WID: RP-142208->RP-150234 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1892 | 660299 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 7 and Band 28 | LTE_CA_B1_B7_B28-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150234 | RP-150536 | Huawei | Huawei | 1st Apr 15: WID: RP-142208->RP-150234 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:0%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1893 | 661000 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 7 | LTE_CA_B1_B3_B7 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142209 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1894 | 661100 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 7 | LTE_CA_B1_B3_B7-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142209 | RP-151131 | Huawei | Huawei | 1st Apr 15: Compl:0%->30% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:30%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:40%->50% 29/09/15: CD:Tue 1 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1895 | 661200 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 7 | LTE_CA_B1_B3_B7-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142209 | RP-151131 | Huawei | Huawei | 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1896 | 661001 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 3 and Band 5 | LTE_CA_B3_B3_B5 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142238 |  | Intel | Intel |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1897 | 661101 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 3 and Band 5 | LTE_CA_B3_B3_B5-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142238 | RP-150536 | Intel | Intel | 1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1898 | 661201 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 3 and Band 5 | LTE_CA_B3_B3_B5-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142238 | RP-150536 | Intel | Intel | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1899 | 661002 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 7 and Band 28 | LTE_CA_B3_B7_B28 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142244 |  | Ericsson | Ericsson |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1900 | 661102 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 7 and Band 28 | LTE_CA_B3_B7_B28-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142244 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1901 | 661202 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 7 and Band 28 | LTE_CA_B3_B7_B28-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-142244 | RP-150536 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536 |  | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
1902 | 661003 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30 | LTE_CA_B2_B2_B12_B30 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142198 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1903 | 661103 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30 | LTE_CA_B2_B2_B12_B30-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150449 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142198->RP-150449 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1904 | 661203 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30 | LTE_CA_B2_B2_B12_B30-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150449 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142198->RP-150449 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1905 | 661004 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30 | LTE_CA_B2_B2_B5_B30 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142199 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1906 | 661104 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30 | LTE_CA_B2_B2_B5_B30-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150448 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: WID: RP-142199->RP-150448 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1907 | 661204 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30 | LTE_CA_B2_B2_B5_B30-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150448 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142199->RP-150448 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1908 | 661005 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30 | LTE_CA_B2_B2_B29_B30 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142200 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1909 | 661105 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30 | LTE_CA_B2_B2_B29_B30-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150450 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142200->RP-150450 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1910 | 661205 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30 | LTE_CA_B2_B2_B29_B30-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150450 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142200->RP-150450 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1911 | 661006 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30 | LTE_CA_B2_B4_B12_B30 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142201 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1912 | 661106 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30 | LTE_CA_B2_B4_B12_B30-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150452 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142201->RP-150452 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1913 | 661206 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30 | LTE_CA_B2_B4_B12_B30-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150452 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142201->RP-150452 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1914 | 661007 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30 | LTE_CA_B2_B4_B5_B30 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142202 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1915 | 661107 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30 | LTE_CA_B2_B4_B5_B30-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150451 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142202->RP-150451 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1916 | 661207 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30 | LTE_CA_B2_B4_B5_B30-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150451 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142202->RP-150451 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1917 | 661008 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30 | LTE_CA_B2_B4_B29_B30 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142203 |  | AT&T | AT&T |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1918 | 661108 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30 | LTE_CA_B2_B4_B29_B30-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150453 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142203->RP-150453 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1919 | 661208 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 29 and Band 30 | LTE_CA_B2_B4_B29_B30-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150453 | RP-151131 | AT&T | AT&T | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142203->RP-150453 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1920 | 661009 | LTE Advanced 4 Band CA (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41 | LTE_CA_B25_B41_B41_B41 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142204 |  | Alcatel-Lucent | Alcatel-Lucent |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1921 | 661109 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41 | LTE_CA_B25_B41_B41_B41-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142204 | RP-151131 | Alcatel-Lucent | Alcatel-Lucent | 1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1922 | 661209 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41 | LTE_CA_B25_B41_B41_B41-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142204 | RP-151131 | Alcatel-Lucent | Alcatel-Lucent | 1st Apr 15: Compl:0%->25% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:25%->75% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:75%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1923 | 661010 | LTE Advanced dual uplink inter-band CA Class A1 in REL-13 | LTE_CA_2UL_R13-A1 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-141935 |  | Huawei | Huawei |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1924 | 661110 | Core part:LTE Advanced dual uplink inter-band CA Class A1 in REL-13 | LTE_CA_2UL_R13-A1-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150678 | RP-151131 | Huawei | Huawei | 1st Apr 15: Compl:0%->40% 1st Apr 15: WID: RP-141935->RP-150411 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->60% 03/07/15: WID: RP-150411->RP-150678 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: Stat Rep: RP-150 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1925 | 661210 | Perf. part:LTE Advanced dual uplink inter-band CA Class A1 in REL-13 | LTE_CA_2UL_R13-A1-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150678 | RP-151131 | Huawei | Huawei | 1st Apr 15: Compl:0%->40% 1st Apr 15: WID: RP-141935->RP-150411 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->60% 03/07/15: WID: RP-150411->RP-150678 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: Stat Rep: RP-150 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1926 | 661011 | LTE Advanced dual uplink inter-band CA Class A2 in REL-13 | LTE_CA_2UL_R13-A2 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-141975 |  | Qualcomm | Qualcomm |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1927 | 661111 | Core part:LTE Advanced dual uplink inter-band CA Class A2 in REL-13 | LTE_CA_2UL_R13-A2-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150408 | RP-151131 | Qualcomm | Qualcomm | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1928 | 661211 | Perf. part:LTE Advanced dual uplink inter-band CA Class A2 in REL-13 | LTE_CA_2UL_R13-A2-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150408 | RP-151131 | Qualcomm | Qualcomm | 1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1929 | 661012 | LTE Advanced dual uplink inter-band CA Class A3 in REL-13 | LTE_CA_2UL_R13-A3 | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142010 |  | Ericsson | Ericsson |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1930 | 661112 | Core part:LTE Advanced dual uplink inter-band CA Class A3 in REL-13 | LTE_CA_2UL_R13-A3-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150409 | RP-151131 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142010->RP-150409 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:25%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->75% 29/09/15: Stat Rep: RP-150536->RP-151131; |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1931 | 661212 | Perf. part:LTE Advanced dual uplink inter-band CA Class A3 in REL-13 | LTE_CA_2UL_R13-A3-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150409 | RP-151131 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142010->RP-150409 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:25%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->75% 29/09/15: Stat Rep: RP-150536->RP-151131; |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1932 | 661013 | LTE Advanced intra-band non-contiguous CA in Band 41 for 4 DL | LTE_CA_NC_B41_4DL | 2 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142022 |  | Alcatel-Lucent | Alcatel-Lucent |  |  | 66 | 34 |  |  | Mon 12/01/15 | Mon 12/01/15
1933 | 661113 | Core part:LTE Advanced intra-band non-contiguous CA in Band 41 for 4 DL | LTE_CA_NC_B41_4DL-Core | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142022 | RP-151131 | Alcatel-Lucent | Alcatel-Lucent | 1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Tue 15/03/16->Tue 15/12/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
1934 | 661213 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 41 for 4 DL | LTE_CA_NC_B41_4DL-Perf | 3 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-142022 | RP-151131 | Alcatel-Lucent | Alcatel-Lucent | 1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Tue 18/12/18->Tue 15/12/15 1st Apr 15: Stat Rep: -->RP-150013 03/07/15: Compl:10%->25% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:25%->50% 29/09/15: Stat Rep: RP-150536->RP-151131 ; |  | 66 | 31 |  |  | Sat 14/09/13 | Fri 01/01/16
1935 | 670065 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 42 | LTE_CA_B1_B3_B42 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150121 |  | NTT DOCOMO, INC. |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1936 | 670165 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 42 | LTE_CA_B1_B3_B42-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150641 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150121->RP-150641 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1937 | 670265 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 42 | LTE_CA_B1_B3_B42-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150641 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150121->RP-150641 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1938 | 670066 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 19 and Band 42 | LTE_CA_B1_B19_B42 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150122 |  | NTT DOCOMO, INC. |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1939 | 670166 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 19 and Band 42 | LTE_CA_B1_B19_B42-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150642 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150122->RP-150642 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1940 | 670266 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 19 and Band 42 | LTE_CA_B1_B19_B42-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150642 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150122->RP-150642 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1941 | 670067 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 21 and Band 42 | LTE_CA_B1_B21_B42 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150123 |  | NTT DOCOMO, INC. |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1942 | 670167 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 21 and Band 42 | LTE_CA_B1_B21_B42-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150643 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150123->RP-150643 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1943 | 670267 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 21 and Band 42 | LTE_CA_B1_B21_B42-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150643 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150123->RP-150643 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1944 | 670068 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 19 and Band 42 | LTE_CA_B3_B19_B42 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150124 |  | NTT DOCOMO, INC. |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1945 | 670168 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 19 and Band 42 | LTE_CA_B3_B19_B42-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150644 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150124->RP-150644 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1946 | 670268 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 19 and Band 42 | LTE_CA_B3_B19_B42-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150644 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150124->RP-150644 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1947 | 670069 | LTE Advanced 3 Band CA (3DL/1UL) of Band 19, Band 21 and Band 42 | LTE_CA_B19_B21_B42 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150125 |  | NTT DOCOMO, INC. |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1948 | 670169 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 19, Band 21 and Band 42 | LTE_CA_B19_B21_B42-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150645 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150125->RP-150645 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1949 | 670269 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 19, Band 21 and Band 42 | LTE_CA_B19_B21_B42-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150645 | RP-150536 | NTT DOCOMO, INC. |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150125->RP-150645 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1950 | 670070 | Additional bandwidth combination set for LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7_BWset | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150429 |  | Rogers Communications |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1951 | 670170 | Core part: Additional bandwidth combination set for LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7_BWset-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150429 | RP-151131 | Rogers Communications |  | 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1952 | 670270 | Perf. part: Additional bandwidth combination set for LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7_BWset-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150429 | RP-151131 | Rogers Communications |  | 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1953 | 670071 | Additional bandwidth combination set for LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12_BWset | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150430 |  | Rogers Communications |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1954 | 670171 | Core part: Additional bandwidth combination set for LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12_BWset-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150430 | RP-151131 | Rogers Communications |  | 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1955 | 670271 | Perf. part: Additional bandwidth combination set for LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12_BWset-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150430 | RP-151131 | Rogers Communications |  | 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1956 | 670072 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 7 and Band 12 | LTE_CA_B2_B7_B12 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-150431 |  | Rogers Communications |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1957 | 670172 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 7 and Band 12 | LTE_CA_B2_B7_B12-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-150431 | RP-151131 | Rogers Communications |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ; 1/122/3/16: Compl:0%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
1958 | 670272 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 7 and Band 12 | LTE_CA_B2_B7_B12-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-150431 | RP-151131 | Rogers Communications |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 122/3/16: Compl:0%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
1959 | 670073 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4 and Band 7 | LTE_CA_B2_B4_B7 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-150432 |  | Rogers Communications |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1960 | 670173 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4 and Band 7 | LTE_CA_B2_B4_B7-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-150432 | RP-151131 | Rogers Communications |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-1511311/1/16:22/3/16: Compl:0%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
1961 | 670273 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4 and Band 7 | LTE_CA_B2_B4_B7-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-150432 | RP-151131 | Rogers Communications |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 1/1/1; 22/3/16: Compl:0%->100% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
1962 | 670074 | LTE Advanced 3 Band CA (3DL/1UL) of Band 7, Band 20 and Band 38 | LTE_CA_B7_B20_B38 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150433 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1963 | 670174 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 7, Band 20 and Band 38 | LTE_CA_B7_B20_B38-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150433 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->30% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1964 | 670274 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 7, Band 20 and Band 38 | LTE_CA_B7_B20_B38-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150433 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->30% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1965 | 670075 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12 | LTE_CA_B2_B4_B4_B12 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150073 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1966 | 670175 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12 | LTE_CA_B2_B4_B4_B12-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150660 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150073->RP-150660 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1967 | 670275 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 4 and Band 12 | LTE_CA_B2_B4_B4_B12-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150660 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150073->RP-150660 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1968 | 670076 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12 | LTE_CA_B2_B2_B4_B12 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150074 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1969 | 670176 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12 | LTE_CA_B2_B2_B4_B12-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150659 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150074->RP-150659 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1970 | 670276 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12 | LTE_CA_B2_B2_B4_B12-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150659 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150074->RP-150659 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1971 | 670077 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4 | LTE_CA_B2_B2_B4_B4 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150075 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1972 | 670177 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4 | LTE_CA_B2_B2_B4_B4-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150658 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150075->RP-150658 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1973 | 670277 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4 | LTE_CA_B2_B2_B4_B4-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150658 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->95% 03/07/15: WID: RP-150075->RP-150658 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1974 | 670078 | LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40 | LTE_CA_B1_B3_B5_B40 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150434 |  | SK Telecom |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1975 | 670178 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40 | LTE_CA_B1_B3_B5_B40-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-151216 | RP-151131 | SK Telecom |  | 03/07/15: Compl:0%->30% 03/07/15: WID: RP-150434->RP-150617 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150617->RP-151216 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1976 | 670278 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40 | LTE_CA_B1_B3_B5_B40-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-151216 | RP-151131 | SK Telecom |  | 03/07/15: WID: RP-150434->RP-150617 03/07/15: Stat Rep: ->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150617->RP-151216 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1977 | 670079 | LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8 | LTE_CA_B1_B3_B7_B8 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150435 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1978 | 670179 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8 | LTE_CA_B1_B3_B7_B8-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150435 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->40% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:40%->45% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1979 | 670279 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8 | LTE_CA_B1_B3_B7_B8-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150435 | RP-151131 | Nokia Networks |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1980 | 670080 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29 | LTE_CA_B2_B4_B5_B29 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150436 |  | Huawei |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1981 | 670180 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29 | LTE_CA_B2_B4_B5_B29-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150436 | RP-151131 | Huawei |  | 03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->95% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1982 | 670280 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29 | LTE_CA_B2_B4_B5_B29-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150436 | RP-151131 | Huawei |  | 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->95% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1983 | 670081 | LTE Advanced dual uplink inter-band CA FDD-TDD | LTE_CA_2UL_FDD_TDD | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150064 |  | KDDI |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1984 | 670181 | Core part:LTE Advanced dual uplink inter-band CA FDD-TDD | LTE_CA_2UL_FDD_TDD-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150064 | RP-151131 | KDDI |  | 03/07/15: Compl:0%->70% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:70%->90% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1985 | 670281 | Perf. part:LTE Advanced dual uplink inter-band CA FDD-TDD | LTE_CA_2UL_FDD_TDD-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150064 | RP-151131 | KDDI |  | 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->90% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1986 | 670082 | LTE Advanced dual uplink inter-band CA Class A4 | LTE_CA_2UL_R13-A4 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150410 |  | Nokia Networks |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1987 | 670182 | Core part:LTE Advanced dual uplink inter-band CA Class A4 in REL-13 | LTE_CA_2UL_R13-A4-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150616 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->25% 03/07/15: WID: RP-150410->RP-150616 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1988 | 670282 | Perf. Part:LTE Advanced dual uplink inter-band CA Class A4 in REL-13 | LTE_CA_2UL_R13-A4-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150616 | RP-151131 | Nokia Networks |  | 03/07/15: Compl:0%->25% 03/07/15: WID: RP-150410->RP-150616 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1989 | 670083 | LTE Advanced 3DL/2UL inter-band CA | LTE_CA_3DL_2UL | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150479 |  | Nokia Corporation |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1990 | 670183 | Core part:LTE Advanced 3DL/2UL inter-band CA | LTE_CA_3DL_2UL-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-151230 | RP-151131 | Nokia Corporation |  | 03/07/15: Compl:0%->25% 03/07/15: CD:Tue 15/03/16->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: WID: RP-150479->RP-151230 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1991 | 670283 | Perf. part:LTE Advanced 3DL/2UL inter-band CA | LTE_CA_3DL_2UL-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-151230 | RP-151131 | Nokia Corporation |  | 03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: WID: RP-150479->RP-151230 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1992 | 670084 | LTE Advanced intra-band non-contiguous CA in Band 42 for 3DL | LTE_CA_NC_B42_3DL | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150246 |  | Huawei |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1993 | 670184 | Core part:LTE Advanced intra-band non-contiguous CA in Band 42 for 3DL | LTE_CA_NC_B42_3DL-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150246 | RP-150536 | Huawei |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1994 | 670284 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 42 for 3DL | LTE_CA_NC_B42_3DL-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-06-15 17:00 | 100% | RP-150246 | RP-150536 | Huawei |  | 03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: ->RP-150536 |  | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
1995 | 670085 | LTE Advanced intra-band contiguous CA in Band 8 | LTE_CA_C_B8 | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150437 |  | CMCC |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1996 | 670185 | Core part: LTE Advanced intra-band contiguous CA in Band 8 | LTE_CA_C_B8-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-151177 | RP-151131 | CMCC |  | 03/07/15: Compl:0%->60% 03/07/15: WID: RP-150437->RP-150809 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:60%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150809->RP-151177 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1997 | 670285 | Perf. part: LTE Advanced intra-band contiguous CA in Band 8 | LTE_CA_C_B8-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-151177 | RP-151131 | CMCC |  | 03/07/15: WID: RP-150437->RP-150809 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->50% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150809->RP-151177 29/09/15: Stat Rep: RP-150536->RP-151131; |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
1998 | 670086 | LTE Advanced intra-band contiguous CA in Band 42 for 4DL | LTE_CA_C_B42_4DL | 2 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150438 |  | CATT |  |  |  | 67 | 34 |  |  | Wed 01/04/15 | Wed 01/04/15
1999 | 670186 | Core part: LTE Advanced intra-band contiguous CA in Band 42 for 4DL | LTE_CA_C_B42_4DL-Core | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150438 | RP-151131 | CATT |  | 03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2000 | 670286 | Perf. part: LTE Advanced intra-band contiguous CA in Band 42 for 4DL | LTE_CA_C_B42_4DL-Perf | 3 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150438 | RP-151131 | CATT |  | 03/07/15: Compl:0%->50% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2001 | 680077 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 8 and Band 11 | LTE_CA_B1_B8_B11 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-150609 | - | Softbank Mobile |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2002 | 680177 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 8 and Band 11 | LTE_CA_B1_B8_B11-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-150609 | RP-151131 | Softbank Mobile |  | 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
2003 | 680277 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 8 and Band 11 | LTE_CA_B1_B8_B11-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-150609 | RP-151131 | Softbank Mobile |  | 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
2004 | 680078 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 20 and Band 32 | LTE_CA_B3_B20_B32 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 90% | RP-150864 | - | Ericsson |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2005 | 680178 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 20 and Band 32 | LTE_CA_B3_B20_B32-Core | 3 | Rel-14 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 90% | RP-150864 | RP-151131 | Ericsson |  | 29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-1511311/22/3/16: Compl:50%->90% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2006 | 680278 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 20 and Band 32 | LTE_CA_B3_B20_B32-Perf | 3 | Rel-14 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 90% | RP-150864 | RP-151131 | Ericsson |  | 29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 ; 22/3/16: Compl:50%->90% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2007 | 680079 | LTE Advanced 3 Band CA (3DL/1UL) for Band 7, Band 42 and Band 42 | LTE_CA_B7_B42_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151012 | - | Huawei |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2008 | 680179 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 7, Band 42 and Band 42 | LTE_CA_B7_B42_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151012 | RP-151131 | Huawei |  | 29/09/15: Compl:0%->70% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2009 | 680279 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 7, Band 42 and Band 42 | LTE_CA_B7_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151012 | RP-151131 | Huawei |  | 29/09/15: Compl:0%->70% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2010 | 680080 | LTE Advanced 3 Band CA (3DL/1UL) for Band 20, Band 42 and Band 42 | LTE_CA_B20_B42_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-151013 | - | Huawei |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2011 | 680180 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 20, Band 42 and Band 42 | LTE_CA_B20_B42_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-151013 | RP-151131 | Huawei |  | 29/09/15: Compl:0%->100% 29/09/15: CD:Tue 15/12/15->Tue 15/09/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
2012 | 680280 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 20, Band 42 and Band 42 | LTE_CA_B20_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-151013 | RP-151131 | Huawei |  | 29/09/15: Compl:0%->100% 29/09/15: CD:Tue 15/12/15->Tue 15/09/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
2013 | 680081 | LTE Advanced 3 Band CA (3DL/1UL) for Band 3, Band 7 and Band 38 | LTE_CA_B3_B7_B38 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151014 | - | Nokia Networks |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2014 | 680181 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 3, Band 7 and Band 38 | LTE_CA_B3_B7_B38-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151014 | RP-151131 | Nokia Networks |  | 29/09/15: Compl:0%->60% 29/09/15: Stat Rep: -->RP-1511311/1/16: Compl: |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2015 | 680281 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 3, Band 7 and Band 38 | LTE_CA_B3_B7_B38-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151014 | RP-151131 | Nokia Networks |  | 29/09/15: Compl:0%->60% 29/09/15: Stat Rep: -->RP-151131; 1/1/16: Comp |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2016 | 680082 | LTE Advanced 3 Band CA (3DL/1UL) of Band 28, Band 41 and Band 41 | LTE_CA_B28_B41_B41 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151111 | - | KDDI |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2017 | 680182 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 28, Band 41 and Band 41 | LTE_CA_B28_B41_B41-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151111 | RP-151131 | KDDI |  | 29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2018 | 680282 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 28, Band 41 and Band 41 | LTE_CA_B28_B41_B41-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151111 | RP-151131 | KDDI |  | 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2019 | 680083 | LTE Advanced 3 Band CA (3DL/1UL) of Band 28, Band 42 and Band 42 | LTE_CA_B28_B42_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151112 | - | KDDI |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2020 | 680183 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 28, Band 42 and Band 42 | LTE_CA_B28_B42_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151158 | RP-151131 | KDDI |  | 29/09/15: Compl:0%->40% 29/09/15: WID: RP-151112->RP-151158 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2021 | 680283 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 28, Band 42 and Band 42 | LTE_CA_B28_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151158 | RP-151131 | KDDI |  | 29/09/15: WID: RP-151112->RP-151158 29/09/15: Stat Rep: -->RP-151131; |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2022 | 680085 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12 | LTE_CA_B2_B4_B7_B12 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-150628 | - | Rogers Communications |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2023 | 680185 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12 | LTE_CA_B2_B4_B7_B12-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-150628 | RP-151131 | Rogers Communications |  | 29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:0%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2024 | 680285 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12 | LTE_CA_B2_B4_B7_B12-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-150628 | RP-151131 | Rogers Communications |  | 29/09/15: Stat Rep: -->RP-151131 ; 22/3/16: Compl:0%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2025 | 680086 | LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42 | LTE_CA_B1_B3_B19_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150632 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2026 | 680186 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42 | LTE_CA_B1_B3_B19_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150632 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2027 | 680286 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42 | LTE_CA_B1_B3_B19_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150632 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2028 | 680087 | LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42 | LTE_CA_B1_B3_B42_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150633 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2029 | 680187 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42 | LTE_CA_B1_B3_B42_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150633 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2030 | 680287 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42 | LTE_CA_B1_B3_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150633 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2031 | 680088 | LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42 | LTE_CA_B1_B19_B42_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150634 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2032 | 680188 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42 | LTE_CA_B1_B19_B42_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150634 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2033 | 680288 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42 | LTE_CA_B1_B19_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150634 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2034 | 680089 | LTE Advanced 4 Band CA (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B3_B19_B42_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150635 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2035 | 680189 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B3_B19_B42_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150635 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2036 | 680289 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B3_B19_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150635 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2037 | 680090 | LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42 | LTE_CA_B1_B19_B21_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150636 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2038 | 680190 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42 | LTE_CA_B1_B19_B21_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150636 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2039 | 680290 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42 | LTE_CA_B1_B19_B21_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150636 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2040 | 680091 | LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42 | LTE_CA_B1_B21_B42_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150637 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2041 | 680191 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42 | LTE_CA_B1_B21_B42_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150637 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2042 | 680291 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42 | LTE_CA_B1_B21_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150637 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2043 | 680092 | LTE Advanced 4 Band CA (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B19_B21_B42_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150638 | - | NTT DOCOMO, INC. |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2044 | 680192 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B19_B21_B42_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150638 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2045 | 680292 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B19_B21_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150638 | RP-151131 | NTT DOCOMO, INC. |  | 29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2046 | 680093 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12 | LTE_CA_B2_B4_B5_B12 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150728 | - | U.S. Cellular |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2047 | 680193 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12 | LTE_CA_B2_B4_B5_B12-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150728 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2048 | 680293 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 4, Band 5 and Band 12 | LTE_CA_B2_B4_B5_B12-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150728 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2049 | 680094 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5 | LTE_CA_B2_B2_B4_B5 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150731 | - | U.S. Cellular |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2050 | 680194 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5 | LTE_CA_B2_B2_B4_B5-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150731 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2051 | 680294 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5 | LTE_CA_B2_B2_B4_B5-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150731 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2052 | 680095 | LTE Advanced 4-Band CA (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12 | LTE_CA_B2_B2_B12_B12 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150732 | - | U.S. Cellular |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2053 | 680195 | Core part:LTE Advanced 4-Band CA (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12 | LTE_CA_B2_B2_B12_B12-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150732 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2054 | 680295 | Perf. part:LTE Advanced 4-Band CA (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12 | LTE_CA_B2_B2_B12_B12-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150732 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2055 | 680096 | LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30 | LTE_CA_B4_B4_B5_B30 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151015 | - | AT&T |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2056 | 680196 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30 | LTE_CA_B4_B4_B5_B30-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151015 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2057 | 680296 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30 | LTE_CA_B4_B4_B5_B30-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151015 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 ; 22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2058 | 680097 | LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30 | LTE_CA_B4_B4_B12_B30 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151016 | - | AT&T |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2059 | 680197 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30 | LTE_CA_B4_B4_B12_B30-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151016 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2060 | 680297 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30 | LTE_CA_B4_B4_B12_B30-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151016 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2061 | 680098 | LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30 | LTE_CA_B4_B4_B29_B30 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151017 | - | AT&T |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2062 | 680198 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30 | LTE_CA_B4_B4_B29_B30-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151017 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 ; 22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2063 | 680298 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30 | LTE_CA_B4_B4_B29_B30-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-03-15 17:00 | 100% | RP-151017 | RP-151131 | AT&T |  | 29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100% |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 22/03/16
2064 | 681000 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12 | LTE_CA_B2_B2_B5_B12 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151018 | - | U.S. Cellular |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2065 | 681100 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12 | LTE_CA_B2_B2_B5_B12-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151018 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2066 | 681200 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12 | LTE_CA_B2_B2_B5_B12-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151018 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2067 | 681001 | LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12 | LTE_CA_B2_B5_B12_B12 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151019 | - | U.S. Cellular |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2068 | 681101 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12 | LTE_CA_B2_B5_B12_B12-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151019 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2069 | 681201 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12 | LTE_CA_B2_B5_B12_B12-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151019 | RP-151131 | U.S. Cellular |  | 29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2070 | 681002 | LTE Advanced 3DL/2UL mixed intra- and inter-band CA | LTE_CA_3DL_2UL_inter_intra | 2 | Rel-14 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150817 | - | Nokia Networks |  | covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE; pure intra-band CA combinations are also covered by this WI; note: There is already a REL-13 WI LTE_CA_3DL_2UL whi |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2071 | 681102 | Core part:LTE Advanced 3DL/2UL mixed intra- and inter-band CA | LTE_CA_3DL_2UL_inter_intra-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP151576 | RP-151131 | Nokia Networks |  | covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE; pure intra-band CA combinations are also covered by this WI; note: There is already a REL-13 WI LTE_CA_3DL_2UL |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2072 | 681202 | Perf. part:LTE Advanced 3DL/2UL mixed intra- and inter-band CA | LTE_CA_3DL_2UL_inter_intra-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP151576 | RP-151131 | Nokia Networks |  | covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE; pure intra-band CA combinations are also covered by this WI; note: There is already a REL-13 WI LTE_CA_3DL_2UL |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2073 | 681003 | LTE Advanced intra-band contiguous CA in Band 5 | LTE_CA_C_B5 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151035 | - | Intel |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2074 | 681103 | Core part: LTE Advanced intra-band contiguous CA in Band 5 | LTE_CA_C_B5-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151035 | RP-151131 | Intel |  | 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2075 | 681203 | Perf. part: LTE Advanced intra-band contiguous CA in Band 5 | LTE_CA_C_B5-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151035 | RP-151131 | Intel |  | 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2076 | 681004 | Additional bandwidth combination set for LTE Advanced intra-band non-contiguous CA in Band 4 | LTE_CA_NC_B4_BWset | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-151034 | - | Nokia Networks |  | LTE_CA_NC_B4 was completed in REL-12 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2077 | 681104 | Core part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous CA in Band 4 | LTE_CA_NC_B4_BWset-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-151034 | RP-151131 | Nokia Networks |  | LTE_CA_NC_B4 was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
2078 | 681204 | Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous CA in Band 4 | LTE_CA_NC_B4_BWset-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-151034 | RP-151131 | Nokia Networks |  | LTE_CA_NC_B4 was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
2079 | 681005 | LTE Advanced intra-band non-contiguous CA in Band 5 | LTE_CA_NC_B5 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151036 | - | Intel |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2080 | 681105 | Core part:LTE Advanced intra-band non-contiguous CA in Band 5 | LTE_CA_NC_B5-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151036 | RP-151131 | Intel |  | 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2081 | 681205 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 5 | LTE_CA_NC_B5-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151036 | RP-151131 | Intel |  | 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2082 | 681006 | LTE Advanced intra-band non-contiguous CA in Band 42 for 4DL | LTE_CA_NC_B42_4DL | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151102 | - | Huawei |  |  |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 03/07/15
2083 | 681106 | Core part:LTE Advanced intra-band non-contiguous CA in Band 42 for 4DL | LTE_CA_NC_B42_4DL-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151102 | RP-151131 | Huawei |  | 29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2084 | 681206 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 42 for 4DL | LTE_CA_NC_B42_4DL-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151102 | RP-151131 | Huawei |  | 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2085 | 680074 | Additional bandwidth combination set for LTE Advanced inter-band CA of Band 2 and Band 12 | LTE_CA_B2_B12_BWset | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-150585 | - | Nokia Networks |  | LTE_CA_B2_B12 was completed as REL-12 WI |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2086 | 680174 | Core part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 2 and Band 12 | LTE_CA_B2_B12_BWset-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-150585 | RP-151131 | Nokia Networks |  | LTE_CA_B2_B12 was completed as REL-12 WI 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
2087 | 680274 | Perf. part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 2 and Band 12 | LTE_CA_B2_B12_BWset-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-150585 | RP-151131 | Nokia Networks |  | LTE_CA_B2_B12 was completed as REL-12 WI 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
2088 | 680076 | Additional bandwidth combination set 2 for LTE Advanced inter-band CA of Band 4 and Band 12 | LTE_CA_B4_B12_BWset2 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-150947 | - | Nokia Networks |  | LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 03/07/15
2089 | 680176 | Core part: Additional bandwidth combination set 2 for LTE Advanced inter-band CA of Band 4 and Band 12 | LTE_CA_B4_B12_BWset2-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-150947 | RP-151131 | Nokia Networks |  | LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
2090 | 680276 | Perf. part: Additional bandwidth combination set 2 for LTE Advanced inter-band CA of Band 4 and Band 12 | LTE_CA_B4_B12_BWset2-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-09-15 17:00 | 100% | RP-150947 | RP-151131 | Nokia Networks |  | LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131 |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 29/09/15
2091 | 680072 | Introduction of 1447-1467MHz Band for TD-LTE in China | LTE_TDD_1447MHz_China | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2016-09-15 17:00 | 100% | RP-151037 | - | Huawei |  | Aug 15: TR numb added |  | 68 | 35 |  |  | Wed 12/08/15 | Wed 12/08/15
2092 | 680172 | Core part: Introduction of 1447-1467MHz Band for TD-LTE in China | LTE_TDD_1447MHz_China-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151037 | RP-151242 | Huawei |  | Aug 15: TR numb added 29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151242 | 36.892 | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2093 | 680272 | Perf. part: Introduction of 1447-1467MHz Band for TD-LTE in China | LTE_TDD_1447MHz_China-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151037 | RP-151242 | Huawei |  | 29/09/15: Stat Rep: -->RP-151242 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2094 | 710068 | UE Conformance Test Aspects - Introduction of 1447-1467MHz Band for TD-LTE in China | LTE_TDD_1447MHz_China-UEConTest | 3 | Rel-13 | R5 | 2016-03-15 08:00 | 2016-09-15 17:00 | 100% | RP-161679 | - | Huawei |  | testing REL-13 LTE_TDD_1447MHz_China-Core; 1/7/16: C; |  | 71 | 36 |  |  | Tue 22/03/16 | Mon 26/09/16
2095 | 680084 | LTE Advanced 4 Band CA (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42 | LTE_CA_B41_B41_B42_B42 | 2 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-150627 |  | ZTE |  |  |  | 68 | 35 |  |  | Wed 12/08/15 | Wed 12/08/15
2096 | 680184 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42 | LTE_CA_B41_B41_B42_B42-Core | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151562 | RP-151131 | ZTE |  | 29/09/15: Compl:0%->40% 29/09/15: WID: RP-150627->RP-151562 29/09/15: Stat Rep: ->RP-151131 |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 01/01/16
2097 | 680284 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42 | LTE_CA_B41_B41_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151562 | RP-151131 | ZTE |  | 29/09/15: Compl:0%->40% 29/09/15: WID: RP-150627->RP-151562 29/09/15: Stat Rep: ->RP-151131 |  | 68 | 35 |  |  | Wed 12/08/15 | Fri 01/01/16
2098 | 690073 | LTE Advanced inter-band CA for Band 5 and Band 38 | LTE_CA_B5_B38 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151367 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2099 | 690173 | Core part:LTE Advanced inter-band CA for Band 5 and Band 38 | LTE_CA_B5_B38-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151367 | - | Huawei |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2100 | 690273 | Perf. part:LTE Advanced inter-band CA for Band 5 and Band 38 | LTE_CA_B5_B38-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151367 | - | Huawei |  | ; 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2101 | 690074 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 11 and Band 18 | LTE_CA_B1_B11_B18 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151156 | - | KDDI |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2102 | 690174 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 11 and Band 18 | LTE_CA_B1_B11_B18-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151156 | - | KDDI |  | ; 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2103 | 690274 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 11 and Band 18 | LTE_CA_B1_B11_B18-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151156 | - | KDDI |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2104 | 690075 | LTE Advanced 3 Band CA (3DL/1UL) of Band 5, Band 40, and Band 40 | LTE_CA_B5_B40_B40 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151200 | - | ZTE |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2105 | 690175 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 5, Band 40, and Band 40 | LTE_CA_B5_B40_B40-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151200 | - | ZTE |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2106 | 690275 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 5, Band 40, and Band 40 | LTE_CA_B5_B40_B40-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151200 | - | ZTE |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2107 | 690076 | LTE Advanced 3 Band CA (3DL/1UL) for Band 3, Band 41 and Band 42 | LTE_CA_B3_B41_B42 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151365 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2108 | 690176 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 3, Band 41 and Band 42 | LTE_CA_B3_B41_B42-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151365 | - | Huawei |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2109 | 690276 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 3, Band 41 and Band 42 | LTE_CA_B3_B41_B42-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151365 | - | Huawei |  | ; 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2110 | 690077 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 41, and Band 41 | LTE_CA_B3_B41_B41 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151448 | - | ZTE |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2111 | 690177 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 41, and Band 41 | LTE_CA_B3_B41_B41-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151448 | - | ZTE |  | ; 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2112 | 690277 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 41, and Band 41 | LTE_CA_B3_B41_B41-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151448 | - | ZTE |  | 1/1/16: Compl:0%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2113 | 690078 | LTE Advanced 4 Band CA (4DL1UL) of Band 39, Band 41, Band 41 and Band 41 | LTE_CA_B39_B41_B41_B41 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151175 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2114 | 690178 | Core part:LTE Advanced 4 Band CA (4DL1UL) of Band 39, Band 41, Band 41 and Band 41 | LTE_CA_B39_B41_B41_B41-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151175 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2115 | 690278 | Perf. part:LTE Advanced 4 Band CA (4DL1UL) of Band 39, Band 41, Band 41 and Band 41 | LTE_CA_B39_B41_B41_B41-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151175 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2116 | 690079 | LTE Advanced 4 Band CA (4DL1UL) of Band 39, Band 39, Band 41 and Band 41 | LTE_CA_B39_B39_B41_B41 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151176 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2117 | 690179 | Core part:LTE Advanced 4 Band CA (4DL1UL) of Band 39, Band 39, Band 41 and Band 41 | LTE_CA_B39_B39_B41_B41-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151176 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2118 | 690279 | Perf. part:LTE Advanced 4 Band CA (4DL1UL) of Band 39, Band 39, Band 41 and Band 41 | LTE_CA_B39_B39_B41_B41-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151176 | - | CMCC |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2119 | 690082 | LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40 | LTE_CA_B1_B3_B8_B40 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151262 | - | KT |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2120 | 690182 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40 | LTE_CA_B1_B3_B8_B40-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151262 | - | KT |  | ; 1/1 |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2121 | 690282 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 1, Band 3, Band 8 and Band 40 | LTE_CA_B1_B3_B8_B40-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151262 | - | KT |  | 1 |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2122 | 690083 | LTE Advanced 4 Band CA (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40 | LTE_CA_B3_B28_B40_B40 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151363 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2123 | 690183 | Core part:LTE Advanced 4 Band CA (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40 | LTE_CA_B3_B28_B40_B40-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151363 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2124 | 690283 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40 | LTE_CA_B3_B28_B40_B40-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151363 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2125 | 690084 | LTE Advanced 4 Band CA (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40 | LTE_CA_B28_B40_B40_B40 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151364 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2126 | 690184 | Core part:LTE Advanced 4 Band CA (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40 | LTE_CA_B28_B40_B40_B40-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151364 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2127 | 690284 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40 | LTE_CA_B28_B40_B40_B40-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151364 | - | Huawei |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2128 | 690085 | LTE Advanced 4 Band CA (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B7_B7_B28 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151511 | - | Telstra |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2129 | 690185 | Core part:LTE Advanced 4 Band CA (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B7_B7_B28-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151511 | - | Telstra |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2130 | 690285 | Perf. part:LTE Advanced 4 Band CA (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B7_B7_B28-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151511 | - | Telstra |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2131 | 690089 | LTE Advanced 5 Band CA (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B1_B3_B19_B42_B42 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151159 | - | NTT DOCOMO |  |  | 36.857-13 | 69 | 35 |  |  | Tue 29/09/15 | NA
2132 | 690189 | Core part:LTE Advanced 5 Band CA (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B1_B3_B19_B42_B42-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151159 | - | NTT DOCOMO |  |  | 36.857-13 | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2133 | 690289 | Perf. part:LTE Advanced 5 Band CA (5DL/1UL) of Band 1, Band 3, Band 19, Band 42 and Band 42 | LTE_CA_B1_B3_B19_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151159 | - | NTT DOCOMO |  |  | 36.857-13 | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2134 | 690090 | LTE Advanced 5 Band CA (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B1_B19_B21_B42_B42 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151160 | - | NTT DOCOMO |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2135 | 690190 | Core part:LTE Advanced 5 Band CA (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B1_B19_B21_B42_B42-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151160 | - | NTT DOCOMO |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2136 | 690290 | Perf. part:LTE Advanced 5 Band CA (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42 | LTE_CA_B1_B19_B21_B42_B42-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151160 | - | NTT DOCOMO |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2137 | 690091 | LTE Advanced 5 Band CA (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B1_B3_B7_B7_B28 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 100% | RP-151512 | - | Telstra |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2138 | 690191 | Core part:LTE Advanced 5 Band CA (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B1_B3_B7_B7_B28-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 100% | RP-160141 | - | Telstra |  | ; 22/3/16: Compl:95%->100%; |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
2139 | 690291 | Perf. part:LTE Advanced 5 Band CA (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B1_B3_B7_B7_B28-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 100% | RP-160141 | - | Telstra |  | 22/3/16: Compl:95%->100%; |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
2140 | 690092 | LTE Advanced 5 Band CA (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B3_B7_B7_B28 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 100% | RP-151513 | - | Telstra |  |  |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2141 | 690192 | Core part:LTE Advanced 5 Band CA (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B3_B7_B7_B28-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 100% | RP-151513 | - | Telstra |  | 22/3/16: Compl:95%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
2142 | 690292 | Perf. part:LTE Advanced 5 Band CA (5DL/1UL) of Band 3, Band 3, Band 7, Band 7 and Band 28 | LTE_CA_B3_B3_B7_B7_B28-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2016-03-15 17:00 | 100% | RP-151513 | - | Telstra |  | ; 22/3/16: Compl:95%->100% |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
2143 | 690093 | LTE Advanced 3 Band CA (3DL/3UL) of Band 39, Band 41 and Band 41 | LTE_CA_3DL3UL_B39_B41_B41 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151402 | - | CATT |  | TDD case |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2144 | 690193 | Core part:LTE Advanced 3 Band CA (3DL/3UL) of Band 39, Band 41 and Band 41 | LTE_CA_3DL3UL_B39_B41_B41-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151402 | - | CATT |  | TDD case |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2145 | 690293 | Perf. part:LTE Advanced 3 Band CA (3DL/3UL) of Band 39, Band 41 and Band 41 | LTE_CA_3DL3UL_B39_B41_B41-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151402 | - | CATT |  | TDD case |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2146 | 690094 | LTE Advanced 3 Band CA (3DL/3UL) of Band 39, Band 39 and Band 41 | LTE_CA_3DL3UL_B39_B39_B41 | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151403 | - | CATT |  | TDD case; 5/10/15: 36.899-13 added; | 36.899-13 | 69 | 35 |  |  | Tue 29/09/15 | Mon 05/10/15
2147 | 690194 | Core part:LTE Advanced 3 Band CA (3DL/3UL) of Band 39, Band 39 and Band 41 | LTE_CA_3DL3UL_B39_B39_B41-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151403 | - | CATT |  | TDD case |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2148 | 690294 | Perf. part:LTE Advanced 3 Band CA (3DL/3UL) of Band 39, Band 39 and Band 41 | LTE_CA_3DL3UL_B39_B39_B41-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151403 | - | CATT |  | TDD case |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2149 | 690095 | Additional bandwidth combination set for LTE Advanced intra-band non-contiguous CA in Band 7 | LTE_CA_NC_B7_BWset | 2 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151462 | - | Huawei |  | LTE_CA_NC_B7 was completed in REL-12 |  | 69 | 35 |  |  | Tue 29/09/15 | NA
2150 | 690195 | Core part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous CA in Band 7 | LTE_CA_NC_B7_BWset-Core | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151462 | - | Huawei |  | LTE_CA_NC_B7 was completed in REL-12 ; |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2151 | 690295 | Perf. part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous CA in Band 7 | LTE_CA_NC_B7_BWset-Perf | 3 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151462 | - | Huawei |  | LTE_CA_NC_B7 was completed in REL-12 ; |  | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2152 | 700065 | UE Conformance Test Aspects - Rel-13 LTE CA configurations | LTE_CA_Rel13-UEConTest | 2 | Rel-13 | R5 | 2015-12-15 08:00 | 2018-12-14 17:00 | 62% | RP-161553 |  | Ericsson |  | ; 22/3/16: Compl:0%->5%;1/7/16: Compl:5%->22%26/9/16: Compl:22%->; 2 21/3/17: Compl:39% ; |  | 70 | 36 |  |  | Fri 01/01/16 | Wed 27/06/18
2153 | 610034 | (Small) Technical Enhancements and Improvements for Rel-13 | TEI13 | 1 | Rel-13 | SP,CP,RP,GP | 2013-09-18 08:00 | 2015-12-21 17:00 | 100% | - | PCG-31 | - | - | - | - | 61 | 31 |  |  | Mon 12/01/15 | Sat 14/09/13
2154 | 710001 | (Small) Test Technical Enhancements and Improvements for Rel-13 | TEI13_Test | 1 | Rel-13 | SP,CP,RP,GP | 2013-09-18 08:00 | 2015-12-21 17:00 | 100% | - | PCG-31 | - | - | Created upon demand of RAN5 | - | 61 | 31 |  |  | Mon 12/01/15 | Wed 24/02/16
2155 | 699999 | Awaiting formal work item | DUMMY | 1 | Rel-13 | SP,CP,RP,GP | 2013-09-18 08:00 | 2015-12-21 17:00 | 100% | [6 empty] | 69 | 35 |  |  | Mon 07/09/15 | NA
2156 | 690007 | (Small) Security Enhancements and Improvements for Rel-13 | SEC13 | 1 | Rel-13 | S3 | 2006-12-12 08:00 | 2015-12-21 17:00 | 100% | - | PCG-31 | - | - | - | - | 61 | 31 |  |  | Mon 12/01/15 | Sat 14/09/13
2157 | 0 | Release 13 IoT related Studies | - | 1 | Rel-13 | SP,R2 | 2013-09-12 08:00 | 2015-12-25 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 04/03/13 | Mon 04/03/13
2158 | 620012 | Study on Power saving for Machine-Type Communications (MTC) devices | FS_uPoD | 1 | Rel-13 | G2,G1 | 2014-08-12 11:12 | 2015-08-14 17:00 | 100% | GP-131136 | - | China Mobile | Jing Han (hanjing@chinamobile.com) | GP#65 completion 02/15=>05/15. GP#60 approved WID. Linked to Rel-12 Feature MTCe, Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP). Dec.14: 30->40%; June2015: Compl:40%->75; 07/09/15: 75%->100 | 43.869 | 60 | 32 |  |  | Fri 22/11/13 | Wed 30/09/15
2159 | 640001 | Study on Cellular system support for ultra Low Complexity and low throughput Internet of Things | FS_IoT_LC | 1 | Rel-13 | G1,G2 | 2014-05-30 08:00 | 2015-08-28 17:00 | 100% | GP-150354 | - | Vodafone | chris.pudney@vodafone.com | GP#62 approved WID. Dec.14: 15->40%; June2015: Compl:40%->75; 07/09/15: 75%->100; 14/09/15: WID:GP-140421->GP-150354 | 45.8xy | 66 | 33 |  |  | Fri 30/05/14 | Mon 14/09/15
2160 | 670029 | Study on architecture enhancements of cellular systems for ultra low complexity and low throughput Internet of Things | FS_AE_CIoT | 1 | Rel-13 | S2 | 2015-03-13 08:00 | 2015-12-11 17:00 | 100% | SP-150167 |  | puneet.jain@intel.com | puneet.jain@intel.com | 07/09/15: 0%->20; 07/09/15: 20%->65; 7/12/15: 65%->95; 7/3/16: 95%->100 | New TR 23.8xx | 67 | 34 |  |  | Fri 13/03/15 | Mon 07/03/16
2161 | 670036 | Study on Battery Efficient Security for very low Throughput Machine Type Communication Devices | FS_BEST_MTC_Sec | 1 | Rel-13 | S3 | 2015-03-13 08:00 | 2015-12-11 17:00 | 100% | SP-150171 |  | Barry, Aguibou, VODAFONE Group Plc | Barry, Aguibou, VODAFONE Group Plc | TR number added; June2015: Compl:0%->10; 7/12/15: 10%->50; 11/12/15: 50%->75; 7/3/16: 75%->95; 19/9/16: 95%->100; 6/10/16: 33.163 added; | 32.863; 33.163 | 67 | 34 |  |  | Fri 13/03/15 | Thu 06/10/16
2162 | 650013 | Study on Small data transmission enhancements for UMTS | FS_UTRA_SDATA | 1 | Rel-13 | R1,R3 | 2014-09-16 08:00 | 2015-06-15 17:00 | 100% | RP-141861 | RP-150843 | Ericsson | gerardo.agni.medina.acosta@ericsson.com | 3/3/15: WID: RP-141861; Stat Rep: -->RP-141859. Impacted TR number added. 1st Apr 15: Compl:30%->55% 1st Apr 15: Stat Rep: RP-141859->RP-150196 03/07/15: Compl:55%->100% 03/07/15: Stat Rep: RP-150196->RP-150843 | 25.705 | 65 | 33 |  |  | Mon 15/09/14 | Thu 18/06/15
2163 | 570034 | Study on Application specific Congestion control for Data Communication | FS_ACDC | 1 | Rel-13 | S1 | 2012-09-17 14:43 | 2014-09-17 17:00 | 100% | SP-130415 | S1-143305 | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#65 completed. SP#64 TR 22.806v200 for Approval. ACDC is applicable to UTRAN and E-UTRAN. Possible overlap with RAN2 TR 36.848 Study on smart congestion mitigation in E-UTRAN (prioritising MMTEL voice over other traffic during congestion) | 22.806 | 57 | 29 |  |  | Fri 31/08/12 | Fri 29/08/14
2164 | 610031 | Study on enhancements for Infrastructure based data Communication Between Devices | FS_eICBD | 1 | Rel-13 | S1 | 2013-09-14 08:00 | 2014-09-17 17:00 | 100% | SP-130418 | S1-143309 | KPN | toon.norp@tno.nl | SP#65 completed. TR 22.807v200 for Approval | 22.807 | 61 | 31 |  |  | Mon 26/08/13 | Thu 28/08/14
2165 | 0 | Release 13 other Studies | - | 1 | Rel-13 | SP,R2 | 2013-09-12 08:00 | 2015-12-25 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 04/03/13 | Mon 04/03/13
2166 | 600046 | Study on Isolated E-UTRAN Operation for Public Safety | FS_IOPS | 1 | Rel-13 | S1 | 2013-06-25 08:00 | 2014-06-18 17:00 | 100% | SP-130596 | - | General Dynamics | paul.piggin@gd-broadband.com | SP#64 completed. TR 22.897v200 for Approval. Linked to Rel-12 TR 22.803 (FS_ProSe) and FeaturES in CP-150ProSe, GCSE_LTE | 22.897 | 60 | 31 |  |  | Thu 30/05/13 | Tue 27/05/14
2167 | 660059 | Study on architecture enhancements for Public Safety | FS_IOPS_St2 | 1 | Rel-13 | S2 | 2014-12-12 08:00 | 2015-06-12 17:00 | 100% | SP-140714 |  |  | phil.young@gd-broadband.com | June2015: Compl:0%->100 |  | 66 | 34 |  |  | Fri 12/12/14 | Mon 15/06/15
2168 | 670095 | Study on Security Aspects of Isolated E-UTRAN Operation for Public Safety | FS_IOPS_Sec | 1 | Rel-13 | S3 | 2015-03-12 08:00 | 2015-09-18 17:00 | 100% | SP-150074 |  | Paul Piggin, General Dynamics UK | paul.piggin@gd-broadband.com | TR added; June2015: Compl:0%->30; 7/12/15: 30%->100 | New TR 33.897 | 67 | 34 |  |  | Thu 02/04/15 | Mon 07/12/15
2169 | 610033 | (SA66: on hold) Study on Co-ordinated packet data network gateway (P-GW) change for SIPTO | FS_CSIPTO | 1 | Rel-13 | S1 | 2013-09-13 08:00 | 2014-06-18 17:00 | 100% | SP-130417 | - | Intel | Eric.siow@intel.com | SP#64 completed. TR 22.828v200 for Approval. Linked to FeaturES in CP-150Rel-10 LIPA_SIPTO & Rel-12 LIMONET | 22.828 | 61 | 31 |  |  | Mon 26/08/13 | Fri 12/12/14
2170 | 620069 | Study on Flexible Mobile Service Steering | FS_FMSS | 1 | Rel-13 | S1 | 2013-12-13 08:00 | 2014-09-17 17:00 | 100% | SP-130597 | S1-143310 | China Mobile | Lu Lu (lulu@chinamobile.com) | SP#65 completed. TR 22.808v200 for Approval. Study supporting traffic classification and service chain selection capabilities per operator’s policy in order to realize efficient and flexible mobile service steering in the Gi-LAN network | 22.808 | 62 | 32 |  |  | Tue 26/11/13 | Thu 28/08/14
2171 | 620070 | Study on Enhanced Calling Information Presentation | FS_ECIP | 1 | Rel-13 | S1 | 2013-12-13 08:00 | 2014-09-17 17:00 | 100% | SP-130598 | S1-143311 | China Mobile | LI Xiaofan (lixiaofan@chinamobile.com | SP#65 completed. TR 22.810v200 for Approval. Linked to Multimedia Telephony Service for IMS (UID_7038), Customized Alerting Tone (CAT) UID_370028, Customized Ringing Signal (CRS) UID_380067 | 22.810 | 62 | 32 |  |  | Tue 26/11/13 | Thu 28/08/14
2172 | 630017 | Study on RAN Sharing Enhancements on GERAN and UTRAN | FS_GUSH | 1 | Rel-13 | S1 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140073 | - | Telefónica | chris.friel@telefonica.com | SP#65 completed. Update on GERAN and UTRAN of Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) | 22.852 updates | 63 | 32 |  |  | Wed 05/02/14 | Fri 29/08/14
2173 | 520035 | Study on Usage Monitoring Enhancements for Service, Application and Subscriber Group | FS_UMONC_sas | 1 | Rel-13 | S2 | 2011-06-08 08:00 | 2014-12-12 17:00 | 100% | SP-140403 | - | China Telecom | Jinyan Li (lijy@ctbri.com.cn) | SP#64 revived. Added to the Title "for Service, Application and Subscriber Group", Changed Acronym: FS_UMONC=>FS_UMONC_sas | 23.858 | 52 | 27 |  |  | Thu 19/05/11 | Thu 19/06/14
2174 | 520335 | Deleted - SA1 part of Study on Usage Monitoring Control PCC Enhancement | - | 2 | - | S1 | 2011-06-08 08:00 | 2012-06-20 17:00 | 100% | SP-120554 | - | ZTE | Li.Mian@zte.com.cn | SP#56 completed | 23.858 | 52 | 27 | SP-58 | PCG-31 | Thu 19/05/11 | Mon 09/09/13
2175 | 520135 | SA2 part of Study on Usage Monitoring Control PCC Enhancement | FS_UMONC_sas | 2 | Rel-13 | S2 | 2013-06-14 14:55 | 2014-12-12 17:00 | 100% | SP-150029 | - | China Telecom | Jinyan Li (lijy@ctbri.com.cn) | SP#64 revived. Updated WID SP-120554=>SP-140403. Changed Justification/objectives/Rapporteut ZTE=>China Unciom. SP#58 SA2 stopped (at 70% completion). Dec.14: 80->100%. Mar 15: WID SP-140403->SP-150029 | 23.858 | 52 | 27 |  |  | Thu 19/05/11 | Thu 05/03/15
2176 | 520235 | Deleted - SA5 part of Study on Usage Monitoring Control enhancement | - | 2 | - | S5 | 2012-03-02 08:00 | 2012-09-12 17:00 | 100% | SP-120554 | - | Huawei | Hui Cai (Sarah.Cai@huawei.com) | SP#57 stopped | 32.858 | 52 | 27 | SP-57 | PCG-29 | Thu 19/05/11 | Thu 30/08/12
2177 | 500034 | Study on Security aspects of Integration of Single Sign-On (SSO) frameworks with 3GPP networks | FS_SSO_Int_Sec | 1 | Rel-13 | S3 | 2010-12-28 08:00 | 2015-06-12 17:00 | 100% | SP-150368 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#65 moved to Rel-13. Updated WID SP-100734=>SP-140576. Completion 09/14=>06/15. Dec.14: 60->65%; June2015: Compl:65%->100; June2015: WID:SP-140576->SP-150368 | 33.895 | 50 | 26 |  |  | Thu 25/11/10 | Thu 18/06/15
2178 | 610043 | Study on Subscriber Privacy Impact in 3GPP | FS_SPI | 1 | Rel-13 | S3 | 2013-09-17 08:00 | 2015-12-16 17:00 | 100% | SP-130399 | - | China Unicom | Feng Gao (gaofeng149@chinaunicom.cn) | SP#65 moved to Rel-13. Completion 09/14=>12/15. Related to SA1 TR 22.949 Rel-6 Study on Privacy Capability (PrivCap) UID_31030 studied generalized privacy capability (protection of personal data and non-disclosure of identity). Dec.14: 80->85; June2015 | 33.849 | 61 | 31 |  |  | Tue 03/09/13 | Mon 07/03/16
2179 | 610045 | Study on Enhancements of OAM aspects of Distributed Mobility Load Balancing (MLB) SON function | FS_D_MLB_SON_OAM | 1 | Rel-13 | S5 | 2014-09-15 08:00 | 2016-06-13 17:00 | 100% | SP-130430 | - | Cisco | Vladimir Yanover (vyanover@cisco.com) | SP#64 completion 06/14=>12/14. Dec.14: 20->25%, CD: 12/14->06/15; June2015: Compl:25%->30; 7/12/15: 30%->45; 7/3/16: 45%->50; 13/6/16: 50%->100 | 32.860 | 61 | 31 |  |  | Mon 09/09/13 | Mon 13/06/16
2180 | 620059 | Study on Application and Partitioning of Itf-N | FS_OAM_AP_Itf-N | 1 | Rel-13 | S5 | 2013-12-17 08:00 | 2015-09-11 17:00 | 100% | SP-130681 | - | China Mobile | Li Jian (lijian@chinamobile.com), Hu Yaxi (huyaxi@cmdi.chinamobile.com) | -Dec.14: 15->30%, CD: 12/14->09/15; June2015: Compl:30%->60; 07/09/15: 60%->100 | 32.861 | 62 | 32 |  |  | Thu 28/11/13 | Mon 07/09/15
2181 | 620060 | Study on Charging aspects on Roaming End-to-end scenarios with VoLTE IMS and interconnecting networks | FS_REVOLTE_IMS_CH | 1 | Rel-13 | S5 | 2013-12-17 08:00 | 2015-06-12 17:00 | 100% | SP-130609 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | SP#64 moved to Rel-13. Completion 06/14=>12/14. Dec.14: 35->55, CD: 12/14->06/15. Mar 15: 55->75%; June2015: Compl:75%->100 | 32.849 | 62 | 32 |  |  | Thu 28/11/13 | Mon 15/06/15
2182 | 640054 | Study on Network Management of Virtualized Networks | FS_OAM_VIRNET | 1 | Rel-13 | S5 | 2014-06-11 08:00 | 2015-06-17 17:00 | 100% | SP-140398 | - | China Mobile, Huawei | Liu Jinglei (liujinglei@chinamobile.com), zoulan@huawei.com | Dec.14: 10->25%. Mar 15: 25->60%; June2015: Compl:60%->85; 07/09/15: 85%->100 | 32.842 | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/09/15
2183 | 590010 | Study on Review of dedicated 3GPP UICC features | FS_Red_UCe | 1 | Rel-13 | C6 | 2013-03-13 08:00 | 2015-12-16 17:00 | 100% | CP-130168 | - | BlackBerry | Adrian Buckley (abuckley@blackberry.com) | CP#65 TR 31.901v100 for Information. Moved to Rel-13. Completion 09/14=>12/15. Waiting for feedback from external organizations (PTCRB/PVG). Dec.14: 65->100% | 31.901 | 59 | 30 |  |  | Wed 20/02/13 | Wed 03/12/14
2184 | 490006 | Study on Solutions for GSM/EDGE BTS Energy Saving | FS_Energy_BTS | 1 | Rel-13 | G1,G2 | 2011-08-30 08:00 | 2015-11-20 17:00 | 100% | GP-101638 | - | Nokia Networks | juergen.hofmann@nokia.com | GP#63 moved to Rel-13. Completion 08/14=>11/14. GP#55 TR 45.926v100 for Information. GP#47 approved WID. Dec.14: 90->95%. 3/3/15: start date corrected (was 03/09). 7/9/15: FCD: 8/15->11/15; 7/12/15: 95%->100 | 45.926 | 47 | 25 |  |  | Sun 05/09/10 | Mon 07/12/15
2185 | 590034 | Study on Downlink MIMO | FS_DOMIMO | 1 | Rel-13 | G1,G2 | 2014-08-14 08:00 | 2016-05-12 17:00 | 100% | GP-130288 | - | Nokia Networks | juergen.hofmann@nokia.com | GP#62 completion 08/14=>02/15. Moved to Rel-13. GP#57 approved WID. Dec.14: 50->65%, CD: 02/15->05/15. 7/9/15: FCD: 11/15->02/16; 2/3/16: 65%->75, FCD: 02/16->05/16; 11/9/17: 75%->100 | 45.8xy | 57 | 30 |  |  | Mon 04/03/13 | Mon 11/09/17
2186 | 640017 | Study on MIMO OTA antenna test function for LTE | FS_LTE_MIMO_OTA_ATF | 1 | Rel-13 | R4 | 2013-03-18 08:00 | 2014-12-15 17:00 | 100% | RP-141325 | RP-142045 | Keysight | Moray_Rumney@keysight.com | CD:Thu 11/12/14->Mon 15/12/14; Compl:60%->100%; Stat Rep: RP-141124->RP-142045 | 36.509, new TR 37.978 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2187 | 620013 | Stopped at 20% - Study on UpLink MultiUser Multiple-Input Multiple-Output (UL MU-MIMO) | FS_UL_MU_MIMO | 1 | Rel-13 | G1,G2 | 2014-04-17 11:12 | 2016-02-19 17:00 | 100% | GP-131131 | - | Huawei | Chao Luo (chluo@huawei.com) | GP#62 completion 11/14=>02/15. GP#60 approved WID. Dec.14: 02/15->05/15. 02/03/16: stopped at 20% | 45.876 | 60 | 32 | SP#71 |  | Fri 22/11/13 | Wed 03/12/14
2188 | 570022 | Study on LTE FDD in the bands 1980-2010 MHz and 2170-2200 MHz | FS_LTE_1980_2170_Korea | 1 | Rel-13 | R4 | 2012-09-11 08:00 | 2015-12-15 17:00 | 100% | RP-151855 | RP-151274 | KT | Chungwoo HWANG (cwhwang@kt.com) | CD:Thu 11/12/14->Sun 15/03/15; Compl:85%->90%; Stat Rep: RP-141153->RP-141851 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: WID: RP-141154->RP-150119 1st Apr 15: Stat Rep: RP-141851->RP-150120 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: S | LTE 36.861 | 57 | 29 |  |  | Mon 03/09/12 | Fri 01/01/16
2189 | 600020 | Study on Positioning enhancements for E-UTRA | FS_LCSenh_LTE | 1 | Rel-13 | R4 | 2012-05-01 14:36 | 2014-12-15 17:00 | 100% | RP-130680 | RP-142224 | Huawei | Jie Cui (cuijie@huawei.com) | WID: RP-140667->RP-130680; Stat Rep: RP-140639->RP-142224. 3/3/15: R1 removed as 2nd responsible WG | LTE 36.855 | 60 | 31 |  |  | Mon 17/06/13 | Tue 03/03/15
2190 | 620045 | Study on Multi-RAT joint coordination | FS_MultiRAT_JC | 1 | Rel-13 | R4 | 2013-12-06 08:00 | 2015-06-15 17:00 | 100% | RP-150417 | RP-150807 | China Mobile | Kimba Dit Adamou, Boubacar (jinba@chinamobile.com) | ; WID: RP-142043->RP-132086; Stat Rep: RP-141301->RP-141838 1st Apr 15: Compl:55%->85% 1st Apr 15: WID: RP-132086->RP-150417 1st Apr 15: Stat Rep: RP-141838->RP-150187 03/07/15: Compl:85%->100% 03/07/15: Stat Rep: RP-150187->RP-150807 | UTRA, LTE 37.870 | 62 | 32 |  |  | Wed 27/11/13 | Thu 18/06/15
2191 | 640016 | Study on Advanced Wireless Services (AWS) - Extension band for LTE | FS_LTE_AWS_EXT | 1 | Rel-13 | R4 | 2013-12-16 08:00 | 2014-12-15 17:00 | 100% | RP-141037 | RP-141968 | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | CD:Thu 11/12/14->Mon 15/12/14; Compl:10%->100%; Stat Rep: RP-141429->RP-141968. 5/5/15: 2nd TR number added (to be clarified why two TR for a same topic) | 36.849, 36.869 | 64 | 33 |  |  | Mon 16/06/14 | Tue 05/05/15
2192 | 640018 | Study on Indoor Positioning Enhancements for UTRA and LTE | FS_UTRA_LTE_iPos_enh | 1 | Rel-13 | R1,R4 | 2014-06-18 08:00 | 2015-09-15 17:00 | 100% | RP-141102 | RP-151178 | NextNav | Vogedes Jerome (jvogedes@NextNav.com) | CD:Thu 17/09/15->Tue 15/09/15; Compl:0%->8%; Stat Rep: RP-141101->RP-141818 1st Apr 15: Compl:8%->30% 1st Apr 15: Stat Rep: RP-141818->RP-150080 03/07/15: Compl:30%->75% 03/07/15: Stat Rep: RP-150080->RP-150595 29/09/15: Compl:75%->100% 29/09/15: Stat | UTRA, LTE 37.857 | 64 | 33 |  |  | Mon 16/06/14 | Tue 29/09/15
2193 | 650014 | Study on Downlink enhancements for UMTS | FS_UTRA_EDL | 1 | Rel-13 | R2,R1 | 2014-09-12 08:00 | 2015-06-15 17:00 | 100% | RP-150224 | RP-150681 | Huawei | jun.chen@huawei.com | WID: RP-141901; Stat Rep: -->RP-142233 1st Apr 15: Compl:40%->80% 1st Apr 15: WID: RP-141901->RP-150224 1st Apr 15: Stat Rep: RP-142233->RP-150223. 5/5/15: R4 replaced by R1 (correction mistake) 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150223-> | UTRA TR 25.706 | 65 | 33 |  |  | Mon 15/09/14 | Thu 18/06/15
2194 | 650015 | Study on Elevation Beamforming/Full-Dimension (FD) MIMO for LTE | FS_LTE_EBF_FDMIMO | 1 | Rel-13 | R1 | 2014-09-12 08:00 | 2015-06-15 17:00 | 100% | RP-150930 | RP-150734 | Nokia Networks (DL), Samsung (UL) | bishwarup.mondal@nsn.com, hyoungju.ji@samsung.com | 3/3/15: WID: RP-141831; Stat Rep: -->RP-141822, impacted TR number added. 1st Apr 15: Compl:30%->45% 1st Apr 15: Stat Rep: RP-141822->RP-150346. 5/5/15: "R4" replaced by "R1" (correction mistake) 03/07/15: Compl:45%->100% 03/07/15: WID: RP-141831->RP-1 | 36.897 | 65 | 33 |  |  | Mon 15/09/14 | Thu 18/06/15
2195 | 650016 | Study on Licensed-Assisted Access using LTE | FS_LTE_LAA | 1 | Rel-13 | R1,R2,R4 | 2014-09-16 08:00 | 2015-06-15 17:00 | 100% | RP-141817 | RP-150624 | Ericsson, Huawei | havish.koorapaty@ericsson.com, david.mazzarese@huawei.com | 3/3/15: WID: RP-141817; Stat Rep: -->RP-141816. Impacted TR number added. 1st Apr 15: Compl:30%->40% 1st Apr 15: Stat Rep: RP-141816->RP-150414 03/07/15: Compl:40%->100% 03/07/15: Stat Rep: RP-150414->RP-150624 | 36.889 | 65 | 33 |  |  | Mon 15/09/14 | Thu 18/06/15
2196 | 660027 | Study on EPC Signalling Improvement for Race Scenarios | FS_EPC_SIG_RACE | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-09-11 17:00 | 100% | CP-140997 |  | Huawei |  | Mar15: 0->20%; June2015: Compl:20%->80; 07/09/15: 80%->95; 7/12/15: 95%->100 | New TR 29.811 | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/12/15
2197 | 660057 | Study on Video Enhancements in 3GPP Multimedia Services | FS_VE_3MS | 1 | Rel-13 | S4 | 2014-12-12 08:00 | 2015-12-11 17:00 | 100% | SP-140741 |  | Ye-Kui Wang, Qualcomm Incorporated | yekuiw@qti.qualcomm.com | Mar. 15: 0->20%; June2015: Compl:20%->40; 07/09/15: 40%->80; 7/12/15: 80%->100 |  | 66 | 34 |  |  | Fri 12/12/14 | Mon 07/12/15
2198 | 660063 | Study on possible additional configuration for LTE TDD | FS_LTE_TDD_add_config | 1 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-150652 | RP-151283 | NTT DOCOMO, Hideaki Takahashi | NTT DOCOMO | TR 36.825 rapporteur: CATT. TR number added. 1st Apr 15: Compl:0%->5% 1st Apr 15: Stat Rep: ->RP-150151 03/07/15: Compl:5%->35% 03/07/15: WID: RP-142248->RP-150652 03/07/15: Stat Rep: RP-150151->RP-150805 29/09/15: Compl:35%->100% 29/09/15: Stat Rep: R | 36.825 | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
2199 | 660064 | Study on Network-Assisted Interference Cancellation and Suppression for UMTS | FS_UTRA_NAICS | 1 | Rel-13 | R1 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-150174 | RP-151235 | Huawei | Huawei | TS number added 1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-142250->RP-150174 1st Apr 15: Stat Rep: ->RP-150175. 5/5/15: "R4" replaced by "R1" (correction mistake) 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150175->RP-150679 29/09/15: Compl:65%- | 25.766 | 66 | 34 |  |  | Mon 12/01/15 | Tue 29/09/15
2200 | 660065 | Study on Enhanced Multiuser Transmissions and Network Assisted Interference Cancellation for LTE | FS_LTE_MUTX_NAIC | 1 | Rel-13 | R1 | 2014-12-15 08:00 | 2015-03-15 17:00 | 0% | RP-142315 | RP-150213 | MediaTek | MediaTek | 1st Apr 15: CD:Tue 15/12/15->Sun 15/03/15 1st Apr 15: Stat Rep: ->RP-150213. 5/5/15: "R4" replaced by "R1" (correction mistake) |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 05/05/15
2201 | 660066 | Study on Support of single-cell point-to-multipoint transmission in LTE | FS_LTE_SC_PTM | 1 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150177 | RP-150695 | Jeff GAO | gaoyongqiang@huawei.com | deleted 660062 (duplicated). 29/1: TR number added 1st Apr 15: Compl:0%->25% 1st Apr 15: WID: RP-142205->RP-150177 1st Apr 15: Stat Rep: ->RP-150176 03/07/15: Compl:25%->100% 03/07/15: Stat Rep: RP-150176->RP-150695 | TR 36.890 | 66 | 34 |  |  | Mon 12/01/15 | Thu 18/06/15
2202 | 660067 | Study on Extension of Dual Connectivity in E-UTRAN | FS_LTE_dualC_ext | 1 | Rel-13 | R3 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150170 | RP-150849 | Samsung | Samsung | 1st Apr 15: WID: RP-142257->RP-150170 1st Apr 15: Stat Rep: ->RP-150163 03/07/15: Compl:85%->100% 03/07/15: Stat Rep: RP-150163->RP-150849. 7/10/15: responsible group corrected (R4->R3) | 36.875 | 66 | 34 |  |  | Mon 12/01/15 | Wed 07/10/15
2203 | 660068 | Study on further enhancements of small cell higher layer aspects for LTE | FS_LTE_SC_enh2_hilayer | 1 | Rel-13 | R3 | 2014-12-15 08:00 | 2015-09-15 17:00 | 100% | RP-142283 | RP-151243 | Huawei | Huawei | 03/07/15: Compl:10%->30% 03/07/15: Stat Rep: RP-150226->RP-150683 29/09/15: Compl:30%->100% 29/09/15: Stat Rep: RP-150683->RP-151243. 7/10/15: responsible group corrected (R4->R3) and TS (37.876->36.876) | 36.876 | 66 | 34 |  |  | Mon 12/01/15 | Wed 07/10/15
2204 | 660069 | Study on RAN sharing enhancements for UMTS | FS_RSE_UTRA_GUSH | 1 | Rel-13 | R3 | 2014-12-15 08:00 | 2015-06-15 17:00 | 100% | RP-150686 | RP-150684 | Huawei | Huawei | 03/07/15: Compl:10%->100% 03/07/15: WID: RP-142284->RP-150686 03/07/15: Stat Rep: RP-150227->RP-150684. 7/10/15: responsible group corrected (R4->R3) | 25.756 | 66 | 34 |  |  | Mon 12/01/15 | Wed 07/10/15
2205 | 660070 | Study on LTE DL 4 Rx antenna ports | FS_LTE_4Rx_AP_DL | 1 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-03-13 17:00 | 100% | RP-150457 | RP-150138 | Ericsson | Ericsson | 1st Apr 15: Compl:0%->100% 1st Apr 15: WID: RP-142299->RP-150457 1st Apr 15: Stat Rep: ->RP-150138 |  | 66 | 34 |  |  | Mon 12/01/15 | Wed 01/04/15
2206 | 660071 | Study on performance enhancements for high speed scenario in LTE | FS_LTE_high_speed | 1 | Rel-13 | R4 | 2014-12-15 08:00 | 2015-12-15 17:00 | 100% | RP-150159 | RP-151313 | NTTDoCoMo | NTTDoCoMo | TR Rapporteur is Huawei 1st Apr 15: Compl:0%->5% 1st Apr 15: WID: RP-142307->RP-150159 1st Apr 15: Stat Rep: ->RP-150517 03/07/15: Compl:5%->40% 03/07/15: Stat Rep: RP-150517->RP-150793 29/09/15: Compl:40%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 2 |  | 66 | 34 |  |  | Mon 12/01/15 | Fri 01/01/16
2207 | 660061 | Study on Enhanced Multiuser Transmissions and Network | FS_MUIC_LTE | 1 | Rel-13 | R1 | 2014-12-12 08:00 | 2015-12-11 17:00 | 0% | RP-142315 |  | Pei-Kai Liao | pk.liao@mediatek.com | TR added | 36.891 | 67 | 34 |  |  | Fri 12/12/14 | Thu 29/01/15
2208 | 670040 | Study on regulatory aspects for flexible duplex for E-UTRAN | FS_LTE_flex_duplex_reg | 1 | Rel-13 | RP | 2016-06-15 08:00 | 2016-12-15 17:00 | 100% | RP-150470 | RP-151307 | LG Electronics Inc. |  | TR added 03/07/15: Compl:0%->5% 03/07/15: Stat Rep: -->RP-150770 29/09/15: Compl:5%->100% 29/09/15: Stat Rep: RP-150770->RP-151307 | 36.882 | 67 | 34 |  |  | Wed 01/04/15 | Tue 29/09/15
2209 | 670043 | Study on Downlink Multiuser Superposition Transmission for LTE | FS_LTE_MUST | 1 | Rel-13 | R1 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-151100 | RP-151345 | Mediatek |  | TR added 03/07/15: Compl:0%->30% 03/07/15: WID: RP-150496->RP-151100 03/07/15: Stat Rep: -->RP-150857 29/09/15: Compl:30%->50% 29/09/15: Stat Rep: RP-150857->RP-151345 | 36.859 | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2210 | 670044 | Study on Measurement gap enhancement for LTE | FS_LTE_meas_gap | 1 | Rel-13 | R4 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150515 | RP-151317 |  |  | 03/07/15: Compl:0%->15% 03/07/15: CD:Thu 10/12/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150754 03/07/15: Release: REL-13->Rel-13. Aug 15: TR numb added 29/09/15: Compl:15%->65% 29/09/15: Stat Rep: RP-150754->RP-151317 | 36.894 | 67 |  |  |  | Mon 11/05/15 | Fri 01/01/16
2211 | 670087 | Study on Phase 1 of the Support of Emergency services over WLAN | FS_SEW | 1 | Rel-13 | S2 | 2015-03-12 08:00 | 2015-06-18 17:00 | 100% | SP-150251 |  | Laurent Thiebaut, Alcatel Lucent | Laurent.thiebaut@alcatel-lucent.com | June2015: Compl:0%->100, SP-150151->SP-150251 | new 23.771 | 67 | 34 |  |  | Wed 01/04/15 | Thu 18/06/15
2212 | 670093 | Study on EGPRS Access Security Enhancements with relation to cellular IoT | FS_EASE_IoT | 1 | Rel-13 | S3 | 2015-03-12 08:00 | 2015-12-11 17:00 | 100% | SP-150145 |  | Vesa Torvinen, Ericsson |  | TR added; June2015: Compl:0%->25; 7/12/15: 25%->70; 28/1/16: 33.420 added; 7/3/16: 70%->100 | New 33.860; 33.420 | 67 | 34 |  |  | Thu 02/04/15 | Mon 07/03/16
2213 | 680013 | Study on SCC AS Restoration | FS_SCCAS_RES | 1 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-06-15 17:00 | 100% | CP-150398 |  | Hao Zhang,, China Mobile | zhanghao@chinamobile.com | 07/09/15: 5%->20; 7/12/15: 20%->100 | New 29.812 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2214 | 680018 | Study on S6a/S6d Shared Data Update | FS_eSDU | 1 | Rel-13 | C4 | 2015-06-15 08:00 | 2015-12-11 17:00 | 100% | CP-150400 |  | Ulrich Wiehe, Nokia Networks | ulrich.wiehe@nokia.com | 07/09/15: 0%->20; 7/12/15: 20%->100 | New 29.813 | 68 | 35 |  |  | Mon 15/06/15 | Mon 07/12/15
2215 | 680055 | Study on Network Assistance for Network Synchronization in LTE | FS_LTE_NW_SYNC | 1 | Rel-14 | R3 | 2015-06-15 08:00 | 2016-12-15 17:00 | 100% | RP-151252 |  | Huawei |  | Aug 15: TR numb added 29/09/15: Compl:0%->15% 29/09/15: WID: RP-151084->RP-151252 29/09/15: Stat Rep: -->RP-151240 22/3/16: Compl:60%->80%; 22/3/16: CD:Tue 15/03/16->Wed 15/06/16; ; | New 36.898 | 68 | 35 |  |  | Fri 03/07/15 | Tue 20/12/16
2216 | 680056 | Study onLTE Advanced inter-band CA of Band 20 and Band 28 | FS_LTE_CA_B20_B28 | 1 | Rel-13 | R4 | 2015-06-15 08:00 | 2015-12-15 17:00 | 100% | RP-151515 | RP-151231 | TeliaSonera |  | 29/09/15: Compl:0%->20% 29/09/15: WID: RP-151101->RP-151515 29/09/15: Stat Rep: -->RP-151231 |  | 68 | 35 |  |  | Fri 03/07/15 | Fri 01/01/16
2217 | 690003 | Study on Impacts of the Diameter Base Protocol Specification Update | FS_DBPU | 1 | Rel-13 | C4 | 2015-09-07 08:00 | 2015-12-18 17:00 | 100% | CP-150575 |  | Huawei, Peter Schmitt |  | 7/3/16: 0%->79; 13/6/16: 79%->99; 2/12/16: 99%->100 | 29.274, 29.060, 23.003, 29.272, 29.002, 29.305, 23.008, 29.230, 29.303, 23.007, 24.301, 24.008 | 69 | 35 |  |  | Mon 07/09/15 | Fri 02/12/16
2218 | 690061 | Study on new AWS-3/4 Band for LTE | FS_LTE_AWS_3_4 | 1 | Rel-13 | R4 | 2015-09-15 08:00 | 2015-12-15 17:00 | 100% | RP-151626 | - | Dish Network |  |  | 36.870 | 69 | 35 |  |  | Tue 29/09/15 | Fri 01/01/16
2219 | 720087 | Study on multi-node testing for LAA | FS_LTE_LAA_multinode_test | 1 | Rel-13 | R4 | 2016-06-15 08:00 | 2017-06-15 17:00 | 100% | RP-162144 |  | Huawei |  | coexistence testing for REL-13 WI LTE_LAA26/9/16: Compl:0%->10%26/9/16: WID: RP-161197->RP-161672; 20/12/16: Compl:10%->30%; 20/12/16: CD:Thu 15/12/16->Wed 15/03/17; 20/12/16: WID: RP-161672->RP-162144; 21/3/17: CD:Wed 15/03/17->Thu 15/06/17; |  | 72 | 37 |  |  | Fri 01/07/16 | Mon 19/06/17
2220 | 560435 | Stopped - Study on Compliance of 3GPP SA5 specifications to the NGMN NGCOR | FS_OAM_NGMN_NGCOR | 1 | Rel-13 | S5 | 2012-06-26 08:00 | 2017-12-15 17:00 | 100% | SP-140787 | - | Huawei | zoulan@huawei.com | SP#65 updated WID SP-140349=>SP-140539. Dec.14: 35->45, 12/14: 28.821 added. Mar 15: 45->50%; June2015: Compl:50%->60. 07/09/15: FCD: 09/15->12/15; 7/12/15: FCD:12/15->03/16; 21/3/17:marked as stopped, was 60% | TR 32.837, TR 28.821 | 56 | 29 |  |  | Mon 14/05/12 | Tue 21/03/17
2221 | 0 | Release 12 Features | - | 1 | Rel-12 | SP,CP,RP,GP | 2013-10-14 08:00 | 2014-12-12 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 08/09/11 | Wed 17/09/14
2222 | 0 | Stage 1 - ONLY Features | - | 1 | Rel-12 | SP,CP | 2011-09-27 08:00 | 2014-03-05 17:00 | 100% | - | - | - | - | - | - | 58 | 30 |  |  | Fri 14/12/12 | Fri 14/12/12
2223 | 490030 | SIPTO Service Continuity of IP Data Session | SIPTO_SC | 1 | Rel-12 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-100589 | - | Vodafone | mona.mustapha@vodafone.com | SP#57 moved to Rel-12 (Reason: Stage 2 for requirements in TS 22.101 clause 4.3.5 have not been implemented in Rel-11). Linked to Rel-10 Local IP Access and Selected Internet IP Traffic Offload (LIPA_SIPTO) | Stage 1 | 49 | 25 |  |  | Wed 01/09/10 | Thu 30/08/12
2224 | 490130 | Stage 1 for SIPTO Service Continuity of IP Data Session | SIPTO_SC-SA1 | 2 | Rel-12 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-100589 | - | Vodafone | mona.mustapha@vodafone.com | SP#57 moved to Rel-12. SP#53 completed | 22.101, 22.220 | 49 | 25 |  |  | Wed 01/09/10 | Thu 30/08/12
2225 | 500031 | Interworking between Mobile Operators using the Evolved Packet System and Data Application Providers | MOSAP | 1 | Rel-12 | S1,S2 | 2010-12-16 08:00 | 2013-12-11 17:00 | 100% | SP-120427 | - | Cisco | Vojislav Vucetic (vvucetic@cisco.com) | SP#58 Stage 2 stopped (TR only, no normative work done) | Stage 1 | 50 | 26 |  |  | Mon 29/11/10 | Thu 22/11/12
2226 | 500131 | Stage 1 for MOSAP | MOSAP-SA1 | 2 | Rel-12 | S1 | 2010-12-16 08:00 | 2011-09-21 17:00 | 100% | SP-120427 | - | Cisco | Vojislav Vucetic (vvucetic@cisco.com) | SP#53 completed | 22.278 | 50 | 26 |  |  | Mon 29/11/10 | Sat 09/06/12
2227 | 520025 | TR on Stage 2 for MOSAP | MOSAP-SA2TR | 2 | Rel-12 | S2 | 2011-06-06 08:00 | 2013-12-11 17:00 | 100% | SP-120427 | - | Intel | chang.hong.shan@intel.com | SP#62 completed. TR 23.862v200 for Approval. SP#58 frozen as v100. | new TR 23.862 | 52 | 27 |  |  | Thu 26/05/11 | Thu 22/11/12
2228 | 520026 | Deleted - Stage 2 for MOSAP | MOSAP-SA2Del | 2 | Rel-12 | S2 | 2011-06-14 08:00 | 2012-12-12 17:00 | 100% | SP-120427 | - | Intel | chang.hong.shan@intel.com | SP#58 stopped (no normative work done) | TBD | 52 | 27 | SP-58 | PCG-30 | Thu 26/05/11 | Thu 22/11/12
2229 | 520027 | IMS Network-Independent Public User Identities | INIPUI | 1 | Rel-12 | S1 | 2011-06-08 08:00 | 2012-06-20 17:00 | 100% | SP-120425 | - | Vodafone | mona.mustapha@vodafone.com | Triggered by Rel-11 TR 22.894 (FS_INIPUI) | Stage 1 | 52 | 27 |  |  | Thu 19/05/11 | Tue 19/06/12
2230 | 520127 | Stage 1 for IMS Network-Independent Public User Identities | INIPUI-SA1 | 2 | Rel-12 | S1 | 2011-06-08 08:00 | 2012-06-20 17:00 | 100% | SP-120425 | - | Vodafone | mona.mustapha@vodafone.com | SP#56 re-completed. Updated WID SP-110381=>SP-120425 (Re-opened & moved to Rel-12 by adding new reqs & removing reqs from Rel-11). SP#53 Rel-11 Stage 1 completed | 22.115, 22.228 | 52 | 27 |  |  | Thu 19/05/11 | Tue 19/06/12
2231 | 530043 | Service and Media Reachability for Users over Restrictive Firewalls | SMURFs | 1 | Rel-12 | S1 | 2011-09-21 08:00 | 2012-06-20 17:00 | 100% | SP-110653 | - | Vodafone | mona.mustapha@vodafone.com | SP#56 Stage 1 completed | Stage 1 | 53 | 27 |  |  | Tue 19/07/11 | Thu 15/09/11
2232 | 530143 | Stage 1 for Service and Media Reachability for Users over Restrictive Firewalls | SMURFs-SA1 | 2 | Rel-12 | S1 | 2011-09-21 08:00 | 2012-06-20 17:00 | 100% | SP-110653 | - | Vodafone | mona.mustapha@vodafone.com | SP#56 completed | 22.278 | 53 | 27 |  |  | Tue 19/07/11 | Fri 08/06/12
2233 | 550024 | Advanced IP Interconnection of Services (IPXS) for national interconnect | IPXSNAT | 1 | Rel-12 | S1 | 2012-03-06 08:00 | 2012-09-12 17:00 | 100% | SP-120428 | - | KPN | toon.norp@tno.nl | SP#57 Stage 1 completed. Linked to Rel-11 Feature Advanced IP Interconnection of Services (IPXS) UID_470051. | Stage 1 | 55 | 28 |  |  | Wed 22/02/12 | Tue 07/08/12
2234 | 550124 | Stage 1 for Advanced IP Interconnection of Services (IPXS) for national interconnect | IPXSNAT-SA1 | 2 | Rel-12 | S1 | 2012-03-06 08:00 | 2012-09-12 17:00 | 100% | SP-120428 | - | KPN | toon.norp@tno.nl | SP#57 completed | 22.228 CR#0161 | 55 | 28 |  |  | Wed 22/02/12 | Mon 14/01/13
2235 | 550025 | Integration of Single Sign-On (SSO) frameworks with 3GPP networks | SSO_Int | 1 | Rel-12 | S1 | 2012-03-08 08:00 | 2012-09-12 17:00 | 100% | SP-120184 | - | InterDigital | christopher.wallace@interdigital.com | SP#57 Stage 1 completed. Triggered by Rel-12 TR 22.895. Linked to SA3 33.8xy (Study on Security aspects of SSO_Int), 33.914 (SSO application security for common IMS based on SIP Digest), 33.924 (i/w GBA and OpenID), 33.980 (i/w GBA and Liberty Alliance) | Stage 1 | 55 | 28 |  |  | Wed 22/02/12 | Tue 07/08/12
2236 | 550125 | Stage 1 for Integration of Single Sign-On (SSO) frameworks with 3GPP networks | SSO_Int-SA1 | 2 | Rel-12 | S1 | 2012-03-08 08:00 | 2012-09-12 17:00 | 100% | SP-120184 | - | InterDigital | christopher.wallace@interdigital.com | SP#57 completed | 22.101 | 55 | 28 |  |  | Wed 22/02/12 | Tue 07/08/12
2237 | 560019 | Explicit Communication Transfer Blind (ECT Blind) service interactions | ECTB | 1 | Rel-12 | S1 | 2012-06-18 08:00 | 2012-06-20 17:00 | 100% | SP-120301 | - | Orange | philippe.lottin@orange.com | SP#56 WID approved & Stage 1 completed | Stage 1 | 56 | 29 |  |  | Mon 14/05/12 | Fri 08/06/12
2238 | 560119 | Stage 1 for Explicit Communication Transfer Blind (ECT Blind) service interactions | ECTB-SA1 | 2 | Rel-12 | S1 | 2012-06-18 08:00 | 2012-06-20 17:00 | 100% | SP-120301 | - | Orange | philippe.lottin@orange.com | SP#56 new WID approved & work completed. Clarify the service interactions between ECT Blind and other MMTEL Supplementary Services | 22.173 | 56 | 29 |  |  | Mon 14/05/12 | Fri 08/06/12
2239 | 570027 | IMS access via Digital Video Broadcast - Return Channel via Satellite (DVB-RCS2) | IMSSat | 1 | Rel-12 | S1 | 2012-02-02 08:00 | 2012-09-12 17:00 | 100% | SP-120543 | - | KPN | toon.norp@tno.nl | SP#57 Stage 1 completed. Integrate Satcom access with IMS. Specify DVB-RCS2 as an IP Connectivity Access Network for IMS | Stage 1 | 57 | 29 |  |  | Mon 06/08/12 | Wed 08/08/12
2240 | 570127 | Stage 1 for IMS access via DVB-RCS2 | IMSSat-SA1 | 2 | Rel-12 | S1 | 2012-02-02 08:00 | 2012-09-12 17:00 | 100% | SP-120543 | - | KPN | toon.norp@tno.nl | SP#57 completed. Definition of DVB-RCS2 as a non-3GPP IP Connectivity Access Network for IMS | 22.228 | 57 | 29 |  |  | Mon 06/08/12 | Wed 08/08/12
2241 | 580060 | Sequential Flexible Alerting | SEQ_FA | 1 | Rel-12 | S1 | 2012-12-10 08:00 | 2012-12-12 17:00 | 100% | SP-120895 | - | Orange | bruno.tossou@orange-ftgroup.com | SP#58 approved WID & Stage 1 completed. Currently Flexible Alerting (FA) group members are simultaneously alerted by the incoming call. Add the possibility to alert FA group members sequentially. 22/01: acronym modified | Stage 1 | 58 | 30 |  |  | Fri 16/11/12 | Thu 22/01/15
2242 | 580160 | Stage 1 for Sequential Flexible Alerting | SEQ_FA | 2 | Rel-12 | S1 | 2012-12-10 08:00 | 2012-12-12 17:00 | 100% | SP-120895 | - | Orange | bruno.tossou@orange-ftgroup.com | SP#58 approved WID & Stage 1 completed | 22.173 | 58 | 30 |  |  | Fri 16/11/12 | Wed 21/11/12
2243 | 580061 | Language and Modality Information for communications | LangInfo | 1 | Rel-12 | S1 | 2012-12-11 08:00 | 2013-03-06 17:00 | 100% | SP-130108 | - | Orange | philippe.lottin@orange.com | SP#59 Stage 1 completed. Triggered by Rel-11 Study on Non Voice Emergency Services (FS_NOVES) TR 22.871 use case 10 | Stage 1 | 58 | 30 |  |  | Fri 16/11/12 | Tue 19/02/13
2244 | 580161 | Stage 1 for Language and Modality Information for communications | LangInfo-SA1 | 2 | Rel-12 | S1 | 2012-12-11 08:00 | 2013-03-06 17:00 | 100% | SP-130108 | - | Orange | philippe.lottin@orange.com | SP#59 completed. Updated WID SP-120937=>SP-130108 | 22.228 | 58 | 30 |  |  | Fri 16/11/12 | Tue 19/02/13
2245 | 590040 | Emergency Session Identification | ESID | 1 | Rel-12 | S1 | 2013-03-04 08:00 | 2013-03-06 17:00 | 100% | SP-130126 | - | Telecom Italia | carmen.catalano@telecomitalia.it | SP#59 Stage 1 completed. | Stage 1 | 59 | 30 |  |  | Tue 19/02/13 | Tue 19/02/13
2246 | 590140 | Stage 1 for Emergency Session Identification | ESID-SA1 | 2 | Rel-12 | S1 | 2013-03-04 08:00 | 2013-03-06 17:00 | 100% | SP-130126 | - | Telecom Italia | carmen.catalano@telecomitalia.it | SP#59 completed (22.101 CR#0445) | 22.101 | 59 | 30 |  |  | Tue 19/02/13 | Tue 19/02/13
2247 | 590041 | Deleted - Application and Service Access Control | ASAC | 1 | Rel-12 | S1 | 2013-03-06 08:00 | 2013-06-19 17:00 | 100% | SP-130124 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#60 stopped and Rel-13 FS_ACDC continues. Triggered by TR 22.806 Study on Application specific Congestion control for Data Communication (FS_ACDC) UID_570034 | Stage 1 | 59 | 30 | SP-60 | PCG-31 | Tue 19/02/13 | Tue 19/02/13
2248 | 590141 | Deleted - Stage 1 for Application and Service Access Control | ASAC-SA1del | 2 | Rel-12 | S1 | 2013-03-06 08:00 | 2013-06-19 17:00 | 100% | SP-130124 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#60 stopped and Rel-13 FS_ACDC contd. Allow/prohibit for E-UTRAN idle mode UE initiation of particular applications defined by operator and subject to regional regulations. Prevent/mitigate overload of AN/CN defined by operator (congestion or disaster) | 22.011 | 59 | 30 | SP-60 | PCG-31 | Tue 19/02/13 | Tue 19/02/13
2249 | 590042 | Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode | PMOC | 1 | Rel-12 | S1 | 2013-03-04 08:00 | 2013-03-06 17:00 | 100% | SP-130111 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#59 Stage 1 completed | Stage 1 | 59 | 30 |  |  | Tue 19/02/13 | Tue 19/02/13
2250 | 590142 | Stage 1 for Prevention of Mobile-Originating signalling and/or data traffic of UE in Connected mode | PMOC-SA1 | 2 | Rel-12 | S1 | 2013-03-04 08:00 | 2013-03-06 17:00 | 100% | SP-130111 | - | NTT DOCOMO | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#59 completed | 22.011 | 59 | 30 |  |  | Tue 19/02/13 | Tue 19/02/13
2251 | 0 | SA1/SA2 Features | - | 1 | Rel-12 | SP,CP,RP | 2013-05-17 08:00 | 2014-03-07 17:00 | 100% | - | - | - | - | - | - | 58 | 30 |  |  | Fri 14/12/12 | Fri 14/12/12
2252 | 500028 | LIPA Mobility and SIPTO at the Local Network | LIMONET | 1 | Rel-12 | S2,C4,C1,R3 | 2010-10-15 08:00 | 2014-03-06 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | CP#63 completed. SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility). Linked to UID_450035 Local IP Access and Selected IP Traffic Offload (LIPA_SIPTO) | Stage 2/3 | 50 | 26 |  |  | Fri 26/11/10 | Wed 27/02/13
2253 | 500128 | TR on Stage 2 for LIPA Mobility and SIPTO at the Local Network | LIMONET-SA3 | 2 | Rel-12 | S2 | 2010-10-15 08:00 | 2013-03-06 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#59 completed. TR 23.859 v100 for Information and Approval | new TR 23.859 | 50 | 26 |  |  | Fri 26/11/10 | Wed 27/02/13
2254 | 500328 | BB1: SIPTO at the Local Network | LIMONET-SIPTO | 2 | Rel-12 | S2 | 2010-10-22 08:00 | 2014-03-05 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#60 completed | 23.060, 23.401 | 50 | 26 |  |  | Fri 26/11/10 | Thu 06/06/13
2255 | 501328 | Stage 2 for SIPTO at the Local Network | LIMONET-SIPTO-SA2 | 3 | Rel-12 | S2 | 2010-10-22 08:00 | 2013-06-19 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#60 completed | 23.060, 23.401 | 50 | 26 |  |  | Fri 26/11/10 | Thu 06/06/13
2256 | 530015 | Stage 3 CN aspects of SIPTO at the Local Network | LIMONET-SIPTO | 3 | Rel-12 | C4,C1 | 2011-09-24 08:00 | 2014-03-05 17:00 | 100% | CP-130274 | - | Huawei | peter.schmitt@huawei.com | CP#63 completed | Stage 3 | 53 | 27 |  |  | Sat 27/08/11 | Wed 29/01/14
2257 | 530115 | CT4 part of Stage 3 CN aspects of SIPTO at the Local Network | LIMONET-SIPTO-CT4 | 4 | Rel-12 | C4 | 2011-09-24 08:00 | 2013-09-06 17:00 | 100% | CP-130274 | - | Huawei | peter.schmitt@huawei.com | CP#61 completed | 23.003, 23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.303 | 53 | 27 |  |  | Sat 27/08/11 | Sat 10/08/13
2258 | 530215 | CT1 part of Stage 3 CN aspects of SIPTO at the Local Network | LIMONET-SIPTO-CT1 | 4 | Rel-12 | C1 | 2011-09-24 08:00 | 2014-03-05 17:00 | 100% | CP-130274 | - | Huawei | peter.schmitt@huawei.com | CP#63 completed | 24.008, 24.301 | 53 | 27 |  |  | Sat 27/08/11 | Wed 29/01/14
2259 | 590020 | RAN aspects for SIPTO at the Local Network | LIMONET-RAN | 2 | Rel-12 | R3 | 2013-03-04 08:00 | 2014-03-06 17:00 | 100% | RP-130372 | - | Huawei | zheng.zhou@huawei.com | - | UTRA, LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
2260 | 590120 | Core part: RAN aspects for SIPTO at the Local Network | LIMONET-RAN-Core | 3 | Rel-12 | R3 | 2013-03-04 08:00 | 2014-03-06 17:00 | 100% | RP-130372 | RP-131512 | Huawei | zheng.zhou@huawei.com | RP#62 completed | 25.401, 25.413, 25.423, 25.467, 25.469, 36.300, 36.413, 36.423 | 59 | 30 |  |  | Tue 26/02/13 | Fri 29/11/13
2261 | 501228 | Deleted - BB2: Stand-alone L-GW and associated Mobility for LIPA and SIPTO at the Local Network | LIMONET-LIPA | 2 | Rel-12 | S2 | 2010-10-22 08:00 | 2012-12-12 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility) | 23.060, 23.401 | 50 | 26 | SP-58 | PCG-30 | Fri 26/11/10 | Wed 27/02/13
2262 | 500228 | Deleted - Stage 2 for stand-alone L-GW and associated Mobility for LIPA and SIPTO at the Local Network | LIMONET-LIPA-del1 | 3 | Rel-12 | S2 | 2010-10-22 08:00 | 2012-12-12 17:00 | 100% | SP-120926 | - | Huawei | zhufenqin@huawei.com | SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility) | 23.060, 23.401 | 50 | 26 | SP-58 | PCG-30 | Fri 26/11/10 | Wed 27/02/13
2263 | 530016 | Deleted - Stage 3 CN aspects of LIPA Mobility | LIMONET-LIPA-del2 | 3 | Rel-12 | C1,C4 | 2011-09-24 08:00 | 2012-12-12 17:00 | 100% | CP-110820 | - | Huawei | christian.herrero@huawei.com | SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility) | Stage 3 | 53 | 27 | SP-58 | PCG-30 | Sat 27/08/11 | Wed 06/06/12
2264 | 530116 | Deleted - CT1 part of CN aspects of LIPA Mobility | LIMONET-LIPA-del3 | 4 | Rel-12 | C1 | 2011-09-24 08:00 | 2012-12-12 17:00 | 100% | CP-110820 | - | Huawei | christian.herrero@huawei.com | SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility) | 24.008, 24.301 | 53 | 27 | SP-58 | PCG-30 | Sat 27/08/11 | Wed 06/06/12
2265 | 530216 | Deleted - CT4 part of CN aspects of LIPA Mobility | LIMONET-LIPA-del4 | 4 | Rel-12 | C4 | 2011-09-24 08:00 | 2012-12-12 17:00 | 100% | CP-110820 | - | Huawei | christian.herrero@huawei.com | SP#58 CT Stage 3 part stopped because of SA stopping Stage 2 for BB2 LIMONET-LIPA on Mobility) | 29.060, 29.274, 29.281, 29.303, 29.002, 29.272, 29.275, 29.282, 29.305 | 53 | 27 | SP-58 | PCG-30 | Sat 27/08/11 | Mon 18/02/13
2266 | 510049 | Operator Policies for IP Interface Selection | OPIIS | 1 | Rel-12 | S2,C1 | 2011-03-23 08:00 | 2013-12-06 17:00 | 100% | SP-120738 | - | LG Electronics | taehyeon.kim@lge.com | Linked to Rel-10 IFOM IP Flow Mobility and seamless WLAN offload (non-seamless WLAN offload aspects) & Rel-11 LIMONET (support traffic offload at local network) | Stage 2/3 | 51 | 26 |  |  | Mon 21/02/11 | Wed 27/02/13
2267 | 510149 | TR on Stage 2 for Operator Policies for IP Interface Selection | OPIIS | 2 | Rel-12 | S2 | 2011-03-23 08:00 | 2012-12-12 17:00 | 100% | SP-120738 | - | LG Electronics | taehyeon.kim@lge.com | SP#58 completed | new TR 23.853 | 51 | 26 |  |  | Mon 21/02/11 | Mon 10/12/12
2268 | 510249 | Stage 2 for Operator Policies for IP Interface Selection | OPIIS | 2 | Rel-12 | S2 | 2011-04-04 08:00 | 2013-03-06 17:00 | 100% | SP-120738 | - | LG Electronics | taehyeon.kim@lge.com | SP#59 completed (23.402 CR#152: Introduction of Inter-APN Routing Policies) | 23.402 | 51 | 26 |  |  | Mon 21/02/11 | Wed 27/02/13
2269 | 600047 | Stage 3 for Operator Policies for IP Interface Selection | OPIIS-CT | 2 | Rel-12 | C1 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130215 | - | LG Electronics | Jaehyun Kim (jaehyun7.kim@lge.com) | CP#62 completed. Specify Inter-APN Routing Policies for selecting an IP interface to route IP flows among a choice of available interfacES in CP-150both 3GPP and non-3GPP accesses | 24.302, 24.312 | 60 | 31 |  |  | Tue 28/05/13 | Mon 18/11/13
2270 | 520029 | Short Message Service (SMS) submit and delivery without MSISDN in IMS | SMSMI | 1 | Rel-12 | S2,C1,C4 | 2011-06-08 08:00 | 2013-12-06 17:00 | 100% | SP-120321 | - | Nokia Siemens Networks | curt.wong@nsn.com | Linked to Rel-7 SMSIP (Support of SMS over generic 3GPP IP access), Rel-11 SIMTC, Rel-12 TR 22.988 SA1 Study on alternatives to E.164 for MTC | Stage 2/3 | 52 | 27 |  |  | Thu 26/05/11 | Mon 18/11/13
2271 | 520129 | TR on Stage 2 for SMS submit and delivery without MSISDN in IMS | SMSMI-SA2TR | 2 | Rel-12 | S2 | 2011-06-08 08:00 | 2012-12-12 17:00 | 100% | SP-120321 | - | Nokia Siemens Networks | curt.wong@nsn.com | SP#58 completed | new TR 23.863 | 52 | 27 |  |  | Thu 26/05/11 | Thu 22/11/12
2272 | 520229 | Stage 2 for SMS submit and delivery without MSISDN in IMS | SMSMI-SA2 | 2 | Rel-12 | S2 | 2011-06-13 08:00 | 2012-12-12 17:00 | 100% | SP-120321 | - | Nokia Siemens Networks | curt.wong@nsn.com | SP#58 completed | 23.204, 23.682 | 52 | 27 |  |  | Thu 26/05/11 | Sat 09/06/12
2273 | 590013 | Stage 3 for SMS submit and delivery without MSISDN in IMS | SMSMI-CT | 2 | Rel-12 | C1,C4 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | CP-130090 | - | NSN | peter.leis@nsn.com | CP#62 completed. Address scenario IMS client to IMS client SMS (comprises SMS receive and send SMS without requiring an MSISDN associated as part of their subscription record in HSS | Stage 3 | 59 | 30 |  |  | Sat 16/02/13 | Mon 18/11/13
2274 | 590113 | CT1 part of Stage 3 for SMS submit and delivery without MSISDN in IMS | SMSMI-CT | 3 | Rel-12 | C1 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | CP-130090 | - | NSN | peter.leis@nsn.com | CP#62 completed | 23.040, 24.341 | 59 | 30 |  |  | Sat 16/02/13 | Mon 18/11/13
2275 | 590213 | CT4 part of Stage 3 for SMS submit and delivery without MSISDN in IMS | SMSMI-CT | 3 | Rel-12 | C4 | 2013-03-01 08:00 | 2013-09-06 17:00 | 100% | CP-130090 | - | NSN | peter.leis@nsn.com | CP#61 completed | 23.008, 29.002, 29.305, 29.328, 29.338 | 59 | 30 |  |  | Sat 16/02/13 | Mon 18/11/13
2276 | 530042 | IMS-based Telepresence | IMS_TELEP | 1 | Rel-12 | S1,C1,C3,C4,IETF | 2010-03-22 13:00 | 2014-12-09 17:00 | 66% | SP-110588 | - | Orange | bruno.tossou@orange-ftgroup.com | This feature does not introduce any changes to the IMS architecture, and no stage 2 impacts are identified | Stage 1/2/3 | 53 | 27 |  |  | Tue 19/07/11 | Fri 08/06/12
2277 | 530142 | Stage 1 for IMS-based Telepresence | IMS_TELEP | 2 | Rel-12 | S1 | 2011-09-22 08:00 | 2012-06-20 17:00 | 100% | SP-110588 | - | Orange | bruno.tossou@orange-ftgroup.com | SP#56 completed. 2/4/15: acronym changed to IMS_TELEP | 22.228 | 53 | 27 |  |  | Tue 19/07/11 | Thu 02/04/15
2278 | 580001 | CT part for IMS Telepresence (Stage 2/3) | IMS_TELEP | 2 | Rel-12 | C1,C3,C4,IETF | 2010-03-22 13:00 | 2014-12-09 17:00 | 64% | CP-140624 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#65 updated WID CP-140196=>CP-140624. 2/4/15: acronym changed to IMS_TELEP | Stage 2/3 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
2279 | 580002 | TR on CT part of IMS Telepresence (Stage 2/3) | IMS_TELEP | 3 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-06-13 17:00 | 100% | CP-140624 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#64 completed. 2/4/15: acronym changed to IMS_TELEP | New TR 24.803 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
2280 | 580003 | CT1 part of IMS Telepresence (Stage 3) | IMS_TELEP | 3 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-12-09 17:00 | 100% | CP-140624 | CP-140616 | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#65 TS 24.103v100 for Information. Updated WID CP-140196=>CP-140624. Completion 09/14=>12/14. Exception in CP-140616. Dec.14: 90->100%. 2/4/15: acronym changed to IMS_TELEP | 24.147, 24.166, 24.229, New TS 24.103 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
2281 | 641001 | (IETF) CT1 part of IMS Telepresence (draft-ietf-mmusic-sctp-sdp) | IMS_TELEP | 3 | Rel-12 | C1-IETF | 2010-03-22 13:00 | 2014-12-05 17:00 | 50% | CP-140624 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress. 2/4/15: acronym changed to IMS_TELEP | draft-ietf-mmusic-sctp-sdp | 64 | 33 |  |  | Fri 06/06/14 | Thu 02/04/15
2282 | 641002 | (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-framework ) | IMS_TELEP | 3 | Rel-12 | C1-IETF | 2010-03-22 13:00 | 2014-12-05 17:00 | 50% | CP-140624 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress. 2/4/15: acronym changed to IMS_TELEP | draft-ietf-clue-framework | 64 | 33 |  |  | Fri 06/06/14 | Thu 02/04/15
2283 | 641003 | (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-datachannel) | IMS_TELEP | 3 | Rel-12 | C1-IETF | 2010-03-22 13:00 | 2014-12-05 17:00 | 50% | CP-140624 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress. 2/4/15: acronym changed to IMS_TELEP | draft-ietf-clue-datachannel | 64 | 33 |  |  | Fri 06/06/14 | Thu 02/04/15
2284 | 641004 | (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-signaling) | IMS_TELEP | 3 | Rel-12 | C1-IETF | 2010-03-22 13:00 | 2014-12-05 17:00 | 50% | CP-140624 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress. 2/4/15: acronym changed to IMS_TELEP | draft-ietf-clue-signaling | 64 | 33 |  |  | Fri 06/06/14 | Thu 02/04/15
2285 | 641005 | (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-data-model-schema) | IMS_TELEP | 3 | Rel-12 | C1-IETF | 2010-03-22 13:00 | 2014-12-05 17:00 | 50% | CP-140624 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress. 2/4/15: acronym changed to IMS_TELEP | draft-ietf-clue-data-model-schema | 64 | 33 |  |  | Fri 06/06/14 | Thu 02/04/15
2286 | 580004 | CT3 part of IMS Telepresence (Stage 3) | IMS_TELEP | 3 | Rel-12 | C3 | 2012-12-07 08:00 | 2014-09-11 17:00 | 100% | CP-140624 | - | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#65 completed. 2/4/15: acronym changed to IMS_TELEP | 29.165 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
2287 | 610011 | CT4 part of IMS Telepresence (Stage 2/3) | IMS_TELEP | 3 | Rel-12 | C4 | 2013-09-13 08:00 | 2014-12-09 17:00 | 100% | CP-140624 | CP-140477 | Huawei | Weiwei(Tommy) Yang (tommy@huawei.com) | CP#65 updated WID CP-140196=>CP-140624. Completion 09/14=>12/14. Exception in CP-140477. Mar.15: 0->100%. 2/4/15: acronym changed to IMS_TELEP | 23.333, 29.333 | 61 | 31 |  |  | Sun 11/08/13 | Thu 02/04/15
2288 | 560020 | Group Communication System Enablers for LTE | GCSE_LTE | 1 | Rel-12 | S1,S2,S3,C3,C4,R3,C1 | 2012-06-18 08:00 | 2015-03-13 17:00 | 100% | SP-140433 | - | Nokia Networks | Juergen.Merkel@nsn.com | Linked to Rel-12 FS_ProSe TR 22.803 Study on Proximity-based Services. External requirements: NIST, MESA, APCO Global Alliance, TCCA. Specify 3GPP system enablers to support group communication over LTE for Public Safety | Stage 1/2/3 | 56 | 29 |  |  | Mon 14/05/12 | Sun 07/09/14
2289 | 560120 | Stage 1 for Group Communication System Enablers for LTE | GCSE_LTE | 2 | Rel-12 | S1 | 2012-06-18 08:00 | 2013-06-19 17:00 | 100% | SP-140433 | - | Nokia Networks | Juergen.Merkel@nsn.com | SP#60 completed. TS 22.468 v100 for 1-step Approval | New TS 22.468 | 56 | 29 |  |  | Mon 14/05/12 | Sun 07/09/14
2290 | 590037 | TR on Architecture enhancements to support Group Communication System Enablers for LTE | GCSE_LTE | 2 | Rel-12 | S2 | 2013-03-07 08:00 | 2014-03-07 17:00 | 100% | SP-140433 | - | Nokia Networks | rainer.liebhart@nsn.com | SP#63 completed. TR 23.768v200 for Approval | New TR 23.768 | 59 | 30 |  |  | Thu 21/02/13 | Sun 07/09/14
2291 | 590038 | Stage 2 for Group Communication System Enablers for LTE | GCSE_LTE | 2 | Rel-12 | S2 | 2013-03-12 08:00 | 2014-09-16 17:00 | 100% | SP-140433 | - | Nokia Networks | rainer.liebhart@nsn.com | SP#65 completed. Updated WID SP-140113=>SP-140433. SP#63 TS 23.468v100 for 1-step Approval | New TS 23.468 | 59 | 30 |  |  | Thu 21/02/13 | Mon 15/09/14
2292 | 610135 | TR on Security for Group Communication System Enablers for LTE (Stage 2) | GCSE_LTE | 2 | Rel-12 | S3 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-140433 | - | Nokia Networks | anja.jerichow@nsn.com | SP#64 completed. TR 33.888v100 for 1-step Approval | New TR 33.888 | 61 | 31 |  |  | Tue 03/09/13 | Sun 07/09/14
2293 | 610035 | Security for Group Communication System Enablers for LTE (Stage 2) | GCSE_LTE | 2 | Rel-12 | S3 | 2013-09-13 08:00 | 2014-06-18 17:00 | 100% | SP-140433 | - | Nokia Networks | anja.jerichow@nsn.com | SP#64 completed | 33.246 | 61 | 31 |  |  | Tue 03/09/13 | Sun 07/09/14
2294 | 640010 | CT aspects of Group Communication System Enablers for LTE | GCSE_LTE-CT | 2 | Rel-12 | C3,C4,C1 | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140559 | - | Nokia Networks | thomas.belling@nsn.com | CP#65 updated WID CP-140452=>C3-143199 (added CT1 part) | Stage 3 | 64 | 33 |  |  | Tue 10/06/14 | Sat 06/09/14
2295 | 640110 | CT3 part of Group Communication System Enablers for LTE | GCSE_LTE-CT | 3 | Rel-12 | C3 | 2014-06-13 08:00 | 2014-09-11 17:00 | 100% | CP-140559 | - | Nokia Networks | thomas.belling@nsn.com | CP#65 completed. TS 29.468v200 for Approval | 29.212, 29.213, 29.214, 29.274, New TS 29.468 | 64 | 33 |  |  | Tue 10/06/14 | Sat 06/09/14
2296 | 640210 | CT4 part of Group Communication System Enablers for LTE | GCSE_LTE-CT | 3 | Rel-12 | C4 | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140559 | CP-140725 | Nokia Networks | thomas.belling@nsn.com | CP#65 completion 09/14=>12/14. Exception in CP-140725. Dec.14: 35->100 | 23.007, 23.008 | 64 | 33 |  |  | Tue 10/06/14 | Thu 04/12/14
2297 | 650008 | CT1 part of Group Communication System Enablers for LTE | GCSE_LTE-CT | 3 | Rel-12 | C1 | 2014-09-12 08:00 | 2014-12-09 17:00 | 100% | CP-140559 | CP-140614 | Nokia Networks | thomas.belling@nsn.com | CP#65 updated WID CP-140452=>CP-140559 (added CT1 part). Exception in CP-140614. Dec.14: 90->100% | 24.301 | 65 | 33 |  |  | Wed 30/07/14 | Thu 04/12/14
2298 | 640037 | Group Call eMBMS congestion management for LTE | GCSE_LTE-MBMS_CM | 2 | Rel-12 | R3 | 2014-06-16 08:00 | 2015-03-13 17:00 | 100% | RP-141035 | - | Alcatel-Lucent | hakon.helmers@alcatel-lucent.com | - | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2299 | 640137 | Core part: Group Call eMBMS congestion management for LTE | GCSE_LTE-MBMS_CM-Core | 3 | Rel-12 | R3 | 2014-06-16 08:00 | 2015-03-13 17:00 | 100% | RP-141035 | RP-150081 | Alcatel-Lucent | hakon.helmers@alcatel-lucent.com | CD:Thu 11/12/14->Sun 15/03/15; Compl:25%->80%; Stat Rep: RP-141327->RP-141863 1st Apr 15: Compl:80%->100% 1st Apr 15: Stat Rep: RP-141863->RP-150081 | 36.413 | 64 | 33 |  |  | Mon 16/06/14 | Wed 01/04/15
2300 | 560022 | Machine-Type and other mobile data applications Communications enhancements | MTCe | 1 | Rel-12 |  | 2009-12-10 08:00 | 2016-05-12 17:00 | 98% | SP-130327 | - | Intel | puneet.jain@intel.com | - | Stage 1/2/3 | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
2301 | 560021 | Stage 1 for Support for Interworking with M2M Service Enablement | MTCe-SIMSE | 2 | Rel-12 | S1 | 2012-06-18 08:00 | 2013-03-06 17:00 | 100% | SP-120436 | - | KPN | toon.norp@tno.nl | SP#59 completed. Define requirements for interworking with M2M service enablement layer specified by ETSI TC M2M in TS 102 689 ( specification for Service Enablement layer) | 22.368 | 56 | 29 |  |  | Mon 14/05/12 | Tue 19/02/13
2302 | 570030 | Stage 1 for Machine-Type and other mobile data applications Communications – Service Requirement Maintenance | MTCe-SRM | 2 | Rel-12 | S1 | 2012-09-13 08:00 | 2013-03-06 17:00 | 100% | SP-130105 | - | KPN | toon.norp@tno.nl | SP#59 completed. Updated WID SP-120541=>SP-130105 | 22.101, 22.368 | 57 | 29 |  |  | Mon 06/08/12 | Tue 19/02/13
2303 | 560722 | TR on Security aspects of Machine-Type Communications | MTCe-SA3TR | 2 | Rel-12 | S3 | 2009-12-10 08:00 | 2014-03-07 17:00 | 100% | SP-130327 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#63 completed. TR 33.868v100 for 1-step Approval. Was Rel-10 UID_460023 (Security for NIMTC). Was Rel-11 UID_490028 (TR on Security aspects of MTC). SP#56 activity transferred to Rel-12 Feature MTCe | New TR 33.868 | 56 | 29 |  |  | Thu 16/08/12 | Thu 27/02/14
2304 | 560522 | Security and Privacy aspects for Machine-Type and other mobile data applications Communications enhancements (Stage 2) | MTCe-SA3 | 2 | Rel-12 | S3 | 2012-06-22 08:00 | 2014-03-07 17:00 | 100% | SP-130327 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#63 completed. TS 33.187v100 for 1-step Approval | New TS 33.187 | 56 | 29 |  |  | Sat 02/06/12 | Thu 27/02/14
2305 | 560122 | BB1: Small Data and Device Triggering Enhancements (SDDTE) | MTCe-SDDTE | 2 | Rel-12 | S2,C4,C3 | 2012-06-18 08:00 | 2014-09-11 17:00 | 100% | SP-120450 | - | Intel | puneet.jain@intel.com | - | - | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
2306 | 560622 | TR on Stage 2 BB1: Small Data and Device Triggering Enhancements | MTCe-SDDTE | 3 | Rel-12 | S2 | 2012-06-18 08:00 | 2013-12-11 17:00 | 100% | SP-120450 | - | Intel | puneet.jain@intel.com | SP#62 completed. TR 23.887v200 for Approval | New TR 23.887 | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
2307 | 562122 | Stage 2 for BB1: Small Data and Device Triggering Enhancements | MTCe-SDDTE | 3 | Rel-12 | S2 | 2012-06-26 08:00 | 2013-12-11 17:00 | 100% | SP-120450 | - | Intel | puneet.jain@intel.com | SP#62 completed | 23.682 | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
2308 | 630001 | Stage 3 for BB1: Small Data and Device Triggering Enhancements | MTCe-SDDTE-CT | 3 | Rel-12 | C4,C3 | 2014-03-05 08:00 | 2014-09-11 17:00 | 100% | CP-140489 | - | Huawei | peter.schmitt@huawei.com | CP#65 updated WID CP-140272=>CP-140489 | Stage 3 | 63 | 32 |  |  | Wed 29/01/14 | Tue 29/07/14
2309 | 630101 | CT4 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement | MTCe-SDDTE-CT | 4 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-09-11 17:00 | 100% | CP-140489 | - | Huawei | peter.schmitt@huawei.com | CP#65 completed. Updated WID CP-140272=>CP-140489 | 29.002, 29.336, 23.008, 29.337, 29.338, 29.230 | 63 | 32 |  |  | Wed 29/01/14 | Tue 29/07/14
2310 | 630201 | CT3 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement | MTCe-SDDTE-CT | 4 | Rel-12 | C3 | 2014-03-05 08:00 | 2014-06-13 17:00 | 100% | CP-140489 | - | Huawei | peter.schmitt@huawei.com | CP#64 completed | 29.368 | 63 | 32 |  |  | Wed 29/01/14 | Tue 29/07/14
2311 | 560222 | Deleted - BB2: Monitoring Enhancements (MONTE) | MTCe-MONTE | 2 | Rel-12 | S2 | 2012-06-18 08:00 | 2012-12-12 17:00 | 100% | SP-120438 | - | Intel | puneet.jain@intel.com | SP#58 stopped (at 20% completion) | 23.682 | 56 | 29 | SP-58 | PCG-30 | Fri 13/04/12 | Fri 14/12/12
2312 | 560322 | BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP | 2 | Rel-12 |  | 2012-06-18 08:00 | 2016-05-12 17:00 | 93% | SP-120442 | - | Ericsson | peter.hedman@ericsson.com | - | - | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
2313 | 561622 | TR on Stage 2 BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP | 3 | Rel-12 | S2 | 2012-06-18 08:00 | 2013-12-11 17:00 | 100% | SP-120442 | - | Ericsson | peter.hedman@ericsson.com | SP#62 completed. TR 23.887v200 for Approval | New TR 23.887 | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
2314 | 562322 | Stage 2 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP | 3 | Rel-12 | S2 | 2012-06-26 08:00 | 2013-12-11 17:00 | 100% | SP-120442 | - | Ericsson | peter.hedman@ericsson.com | SP#62 completed | 23.060, 23.401, 23.682 | 56 | 29 |  |  | Fri 13/04/12 | Thu 28/11/13
2315 | 620007 | Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT | 3 | Rel-12 |  | 2013-12-06 08:00 | 2016-03-15 17:00 | 100% | CP-130714 | - | Ericsson | mikael.wass@ericsson.com | - | Stage 3 | 62 | 32 |  |  | Mon 18/11/13 | Mon 18/11/13
2316 | 620107 | CT1 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT1 | 4 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-09-11 17:00 | 100% | CP-130714 | - | Ericsson | mikael.wass@ericsson.com | CP#65 completed | 24.008, 24.301 | 62 | 32 |  |  | Mon 18/11/13 | Mon 28/07/14
2317 | 620207 | Deleted - CT4 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT4 | 4 | Rel-12 | C4 | 2013-12-09 08:00 | 2014-09-11 17:00 | 100% | CP-130714 | - | Ericsson | mikael.wass@ericsson.com | CP#65 stopped (no inpact on CT4) | 29.274, 29.060, 23.008 | 62 | 32 | CP-65 | PCG-33 | Mon 18/11/13 | Sun 25/05/14
2318 | 620307 | CT6 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT6 | 4 | Rel-12 | C6 | 2013-12-09 08:00 | 2014-12-09 17:00 | 100% | CP-130714 | CP-140697 | Ericsson | mikael.wass@ericsson.com | CP#65 completion 09/14=>12/14. Exception in CP-140697; June2015: Compl:90%->100 | 31.101, 31.102, 31.111 | 62 | 32 |  |  | Mon 18/11/13 | Mon 15/06/15
2319 | 690068 | UE Conformance Test Aspects - UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-UEConTest | 4 | Rel-12 | R5 | 2015-09-15 08:00 | 2016-03-15 17:00 | 100% | RP-151161 | - | Ericsson |  | tested: MTCe-UEPCOP was a REL-12 SA2 WI; NAS over LTE and UTRA;1/1/16: Compl:0%->25%22/3/16: C |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 22/03/16
2320 | 650009 | Support of Power Saving Mode in GERAN | MTCe-UEPCOP-GERAN | 3 | Rel-12 | G1 | 2014-08-25 08:00 | 2014-08-29 17:00 | 100% | GP-140628 |  | Ericsson | sajal.kumar.das@ericsson.com | GP#63 approved WID and completed | 43.022 | 63 | 33 |  |  | Fri 29/08/14 | Fri 29/08/14
2321 | 700005 | Testing of Support of Power Saving Mode in GERAN | MTCe-UEPCOP_GERAN3new | 3 | Rel-12 | G3 | 2015-11-11 08:00 | 2016-05-12 17:00 | 10% | GP-151186 |  | Ericsson | sajal.kumar.das@ericsson.com | 7/12/15: created.02/3/16: acronym: MTCe-UEPCOP-GERAN_test->MTCe-UEPCOP_GERAN3new; 2/3/16: 0%->10 |  | 70 | 36 |  |  | Fri 29/08/14 | Wed 02/03/16
2322 | 560422 | Deleted - BB4: Group based MTC feature (GROUP) | MTCe-GROUP | 2 | Rel-12 | S2 | 2012-06-20 08:00 | 2012-12-12 17:00 | 100% | SP-120267 | - | KPN | Annemieke Kips | SP#58 stopped (at 25% completion) | 23.682 | 56 | 29 | SP-58 | PCG-30 | Fri 13/04/12 | Fri 14/12/12
2323 | 620043 | RAN enhancements for Machine-Type and other mobile data applications Communications | MTCe-RAN | 2 | Rel-12 | R2,R3 | 2014-02-03 15:24 | 2014-09-12 17:00 | 100% | RP-140752 | - | ZTE | sergio.parolari@zte.com.cn | Triggered by TR 23.887 Machine Type and other mobile data applications Communications Enhancements (MTCe), TR 37.869 Study on Enhancements MTC and other Mobile Data Applications; RAN aspects (FS_MTCe_RAN), Rel-11 TR 23.888 SIMTC | UTRA, LTE | 62 | 32 |  |  | Sat 07/12/13 | Sat 07/12/13
2324 | 620143 | Core part: RAN enhancements for Machine-Type and other mobile data applications Communications | MTCe-RAN-Core | 3 | Rel-12 | R2,R3 | 2014-02-03 15:24 | 2014-09-12 17:00 | 100% | RP-140752 | RP-141096 | ZTE | sergio.parolari@zte.com.cn | RP#65 completed | 25.300, 25.304, 25.413, 36.300, 36.304, 36.413, 36.423 | 62 | 32 |  |  | Sat 07/12/13 | Mon 15/09/14
2325 | 600012 | Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE | 1 | Rel-12 | R1,R2,R4 | 2013-06-15 | 2016-12-15 17:00 | 100% | RP-130848 | - | Vodafone | eric.bouton@vodafone.com | Triggered by Rel-11 TR 36.888 (FS_LC_MTC_UE) | LTE | 60 | 31 |  |  | Mon 17/06/13 | Tue 09/09/14
2326 | 600112 | Core part: Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE-Core | 2 | Rel-12 | R1,R2,R4 | 2013-06-15 | 2014-12-15 17:00 | 100% | RP-140522 | RP-142024 | Vodafone | eric.bouton@vodafone.com | ; CD:Thu 18/06/15->Mon 15/06/15; WID: RP-130848->RP-140522; Stat Rep: RP-141221->RP-142024 | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
2327 | 600212 | Perf. part: Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE-Perf | 2 | Rel-12 | R4 | 2013-06-15 | 2015-06-15 17:00 | 100% | RP-150940 | RP-150915 | Vodafone | eric.bouton@vodafone.com | ; CD:Thu 18/06/15->Mon 15/06/15; WID: RP-130848->RP-140522; Stat Rep: RP-141221->RP-142024 1st Apr 15: Compl:65%->90% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-142024->RP-150149 03/07/15: Compl:90%->100% 03/07/15: WID: RP-14052 | 36.101, 36.104, 36.133 | 60 | 31 |  |  | Mon 17/06/13 | Thu 18/06/15
2328 | 670048 | UE Conformance Test Aspects - Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE-UEConTest | 2 | Rel-12 | R5 | 2015-03-16 08:00 | 2016-12-15 17:00 | 100% | RP-160069 |  | Ericsson |  | 03/07/15: Compl:0%->13% 03/07/15: WID: RP-150135->RP-150838 03/07/15: Stat Rep: ->RP-150833 29/09/15: Compl:13%->25% 29/09/15: Stat Rep: RP-150833->RP-151165 ; 1/1/16: Compl:25%->70% ; 1/1/16: CD:Tue 15/12/15->Tue 15/03/16 |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 20/12/16
2329 | 560024 | Policy and Charging Control for supporting fixed broadband access networks | P4C | 1 | Rel-12 | S2,S1,S5,C3,C1,C4 | 2012-06-20 08:00 | 2014-12-12 17:00 | 100% | SP-120443 | - | Huawei | marco.spini@huawei.com | Linked to BBF, IETF work. SP#58 stopped BB3 to BB6. Split BB1 and BB2 into TR and Stage 2 work | Stage 1/2/3 | 56 | 29 |  |  | Fri 13/04/12 | Tue 08/01/13
2330 | 570031 | Stage 1 for Policy and Charging Support for Fixed Mobile Convergence | P4C-FMC | 2 | Rel-12 | S1 | 2012-09-10 08:00 | 2012-09-12 17:00 | 100% | SP-120542 | - | Huawei | amar.deol@huawei.com | SP#57 completed | 22.278 | 57 | 29 |  |  | Mon 06/08/12 | Tue 08/01/13
2331 | 560124 | BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO (Non Seamless WLAN Offload) traffic from 3GPP UEs in fixed broadband access networks (P4C-F) | P4C-F | 2 | Rel-12 | S2,S5,C3,C1,C4 | 2012-06-20 08:00 | 2014-12-12 17:00 | 100% | SP-120275 | - | Huawei | marco.spini@huawei.com | - | - | 56 | 29 |  |  | Mon 04/06/12 | Tue 08/01/13
2332 | 560724 | TR on Stage 2 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (P4C-F) | P4C-F-SA2TR | 3 | Rel-12 | S2 | 2012-06-20 08:00 | 2014-12-12 17:00 | 100% | SP-120275 | - | Huawei | marco.spini@huawei.com | SP#64 TR 23.896 was never sent for approval due to incomplete P4C BBs. SP#61 TR 23.896v100 for Information. Dec.14: 90->100%. Mar15: 23.896 for approval. | new TR 23.896 | 56 | 29 |  |  | Mon 04/06/12 | Fri 13/03/15
2333 | 562124 | Stage 2 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (P4C-F) | P4C-F-SA2 | 3 | Rel-12 | S2 | 2012-06-20 08:00 | 2013-12-11 17:00 | 100% | SP-120275 | - | Huawei | marco.spini@huawei.com | SP#62 completed | 23.139, 23.203 | 56 | 29 |  |  | Mon 04/06/12 | Thu 28/11/13
2334 | 610012 | Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | P4C-F-CT3 | 3 | Rel-12 | C3,C1,C4 | 2013-09-06 08:00 | 2014-06-13 17:00 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | - | Stage 3 | 61 | 31 |  |  | Mon 12/08/13 | Wed 16/04/14
2335 | 610112 | CT3 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | P4C-F-CT3 | 4 | Rel-12 | C3 | 2013-09-06 08:00 | 2014-06-13 17:00 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#64 completed | 29.212, 29.213, 29.215, 29.219 | 61 | 31 |  |  | Mon 12/08/13 | Wed 16/04/14
2336 | 620009 | CT1 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | P4C-F-CT3 | 4 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-03-05 17:00 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#63 completed | 24.302 | 62 | 32 |  |  | Tue 19/11/13 | Wed 29/01/14
2337 | 620010 | CT4 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks | P4C-F-CT3 | 4 | Rel-12 | C4 | 2013-12-06 08:00 | 2014-06-13 17:00 | 100% | CP-130776 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#64 completed | 29.273 | 62 | 32 |  |  | Tue 19/11/13 | Wed 16/04/14
2338 | 600042 | Policy and Charging Enforcement Function (PCEF) based Charging for traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (Stage 2/3) | P4C-F-CH_P | 3 | Rel-12 | S5 | 2013-06-21 08:00 | 2014-09-17 17:00 | 100% | SP-130261 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#65 completed. Introduce Charging Characteristics in Convergent scenario, Include missing fixed user location information for NSWO | Stage 2 (32.240, 32.251), Stage 3 (32.298, 32.299) | 60 | 31 |  |  | Sun 02/06/13 | Tue 26/08/14
2339 | 600043 | Traffic Detection Function (TDF) based Charging for traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (Stage 2/3) | P4C-F-CH_T | 3 | Rel-12 | S5 | 2013-06-24 08:00 | 2014-06-18 17:00 | 100% | SP-130262 | - | Openet Telecom | alan.mcnamee@openet.com | SP#64 completed | Stage 2 (32.240, 32.251), Stage 3 (32.298, 32.299) | 60 | 31 |  |  | Sun 02/06/13 | Tue 10/06/14
2340 | 560224 | BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI) | P4C-TI | 2 | Rel-12 | S2 | 2012-06-20 08:00 | 2013-06-19 17:00 | 100% | SP-120444 | - | Alcatel-Lucent | konstantin.livanos@alcatel-lucent.com | - | - | 56 | 29 |  |  | Mon 04/06/12 | Tue 08/01/13
2341 | 560824 | TR on Stage 2 for BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI) | P4C-TI-SA2TR | 3 | Rel-12 | S2 | 2012-06-20 08:00 | 2013-06-19 17:00 | 100% | SP-120444 | - | Alcatel-Lucent | konstantin.livanos@alcatel-lucent.com | SP#60 completed | new TR 23.839 | 56 | 29 |  |  | Mon 04/06/12 | Mon 17/06/13
2342 | 562224 | Stage 2 for BB2: Policy and Charging Control for 3GPP UEs connected to BroadBand Forum access network as Trusted network in Interworking scenario (P4C-TI) | P4C-TI-SA2 | 3 | Rel-12 | S2 | 2012-06-20 08:00 | 2013-06-19 17:00 | 100% | SP-120444 | - | Alcatel-Lucent | konstantin.livanos@alcatel-lucent.com | SP#60 completed | 23.139, 23.203 | 56 | 29 |  |  | Mon 04/06/12 | Thu 06/06/13
2343 | 560324 | Deleted - BB3: Policy and Charging Control for 3GPP UEs connected to fixed broadband access network via S2b and S2c reference points for EPC routed traffic (P4C-S2bc) | P4C-S2bc | 2 | Rel-12 | S2 | 2012-06-21 08:00 | 2012-12-12 17:00 | 100% | SP-120445 | - | ZTE | Tricci So (tso@zteusa.com) | SP#58 stopped (at 0% completion) | 23.139, 23.203, new TR 23.896 | 56 | 29 | SP-58 | PCG-30 | Mon 04/06/12 | Tue 08/01/13
2344 | 560424 | Deleted - BB4: Policy and Charging Control for EPC routed traffic over fixed broadband access networks of 3GPP UEs connected via H(e)NB in convergent scenarios (P4C-HeNB) | P4C-HeNB | 2 | Rel-12 | S2 | 2012-06-21 08:00 | 2012-12-12 17:00 | 100% | SP-120278 | - | NEC | Stefan.Schmid@neclab.eu | SP#58 stopped (at 0% completion) | 23.139, 23.203, new TR 23.896 | 56 | 29 | SP-58 | PCG-30 | Mon 04/06/12 | Tue 08/01/13
2345 | 560524 | Deleted - BB5: Policy and Charging Control for supporting Layer 2 traffic in fixed broadband access network (P4C-FL2) | P4C-FL2 | 2 | Rel-12 | S2 | 2012-06-21 08:00 | 2012-12-12 17:00 | 100% | SP-120279 | - | Huawei | marco.spini@huawei.com | SP#58 stopped (at 0% completion) | 23.139, 23.203, new TR 23.896 | 56 | 29 | SP-58 | PCG-30 | Mon 04/06/12 | Tue 08/01/13
2346 | 560624 | Deleted - BB6: Policy and Charging Control for 3GPP UEs connected to fixed broadband access networks via S2a reference point for EPC routed traffic in convergence (P4C-TC) | P4C-TC | 2 | Rel-12 | S2 | 2012-06-20 08:00 | 2012-12-12 17:00 | 100% | SP-120280 | - | ZTE | Tricci So (tso@zteusa.com) | SP#58 stopped (at 30% completion) | 23.139, 23.203, new TR 23.896 | 56 | 29 | SP-58 | PCG-30 | Mon 04/06/12 | Tue 08/01/13
2347 | 560025 | IMS Business Trunking for IP-PBX in Static Mode of Operation | BusTI | 1 | Rel-12 | S2,S1,C1,C3 | 2011-09-28 16:12 | 2014-12-09 17:00 | 100% | SP-120862 | - | Deutsche Telekom | michele.zarri@telekom.com | Linked to Rel-11 IPXS Feature UID_470051 Advanced IP Interconnection of Services. This WI defines a generic framework for interconnecting with any type of IMS based network including IP-PBXs. | Stage 1/2/3 | 56 | 29 |  |  | Fri 11/05/12 | Mon 10/12/12
2348 | 560325 | Stage 1 for IMS Business Trunking for IP-PBX in Static Mode of Operation | BusTI-SA1 | 2 | Rel-12 | S1 | 2011-09-28 16:12 | 2012-09-12 17:00 | 100% | SP-120862 | - | Deutsche Telekom | kurt.bischinger@t-mobile.at | SP#57 completed. 22.228CR#0171 | 22.228 | 56 | 29 |  |  | Fri 11/05/12 | Mon 10/12/12
2349 | 560125 | TR on IMS Business Trunking for IP-PBX in Static Mode of Operation | BusTI-SATR | 2 | Rel-12 | S2,S1 | 2012-06-18 08:00 | 2013-06-19 17:00 | 100% | SP-120862 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#60 completed | new TR 23.897 | 56 | 29 |  |  | Fri 11/05/12 | Thu 06/06/13
2350 | 560225 | Stage 2 for IMS Business Trunking for IP-PBX in Static Mode of Operation | BusTI-SA2 | 2 | Rel-12 | S2 | 2012-06-25 08:00 | 2013-06-19 17:00 | 100% | SP-120862 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#60 completed | 23.228 | 56 | 29 |  |  | Fri 11/05/12 | Thu 06/06/13
2351 | 610007 | CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3) | BusTI-CT | 2 | Rel-12 | C1,C3 | 2013-09-06 08:00 | 2014-12-09 17:00 | 100% | CP-140197 | - | Deutsche Telekom | michael.kreipl@telekom.de | - | Stage 3 | 61 | 31 |  |  | Sat 10/08/13 | Mon 03/03/14
2352 | 610107 | CT1 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3) | BusTI-CT | 3 | Rel-12 | C1 | 2013-09-06 08:00 | 2014-12-09 17:00 | 100% | CP-140197 | CP-140607 | Deutsche Telekom | michael.kreipl@telekom.de | CP#65 completion 09/14=>12/14. Exception in CP-140607. Dec.14: 85->100% | 23.218, 24.229, 24.525 (transfer of ETSI TS 182 025) | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
2353 | 610207 | CT3 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3) | BusTI-CT | 3 | Rel-12 | C3 | 2013-09-06 08:00 | 2014-06-11 17:00 | 100% | CP-140197 | - | Deutsche Telekom | michael.kreipl@telekom.de | CP#64 completed | 29.165 | 61 | 31 |  |  | Sat 10/08/13 | Wed 16/04/14
2354 | 560026 | WLAN Network Selection for 3GPP Terminals | WLAN_NS | 1 | Rel-12 | S2,S1,S3,C1 | 2012-06-18 08:00 | 2014-12-09 17:00 | 100% | SP-120847 | - | Intel | vivek.g.gupta@intel.com | Evaluate and if needed enhance existing 3GPP solutions for WLAN network selection taking into account WFA Hotspot 2.0 solutions | Stage 1/2/3 | 56 | 29 |  |  | Fri 11/05/12 | Mon 10/12/12
2355 | 560126 | TR on Stage 2 for WLAN Network Selection for 3GPP Terminals | WLAN_NS-SATR | 2 | Rel-12 | S2,S1 | 2012-06-18 08:00 | 2013-12-11 17:00 | 100% | SP-120847 | - | Intel | vivek.g.gupta@intel.com | SP#62 completed | New TR 23.865 | 56 | 29 |  |  | Fri 11/05/12 | Thu 28/11/13
2356 | 560226 | Stage 2 for WLAN Network Selection for 3GPP Terminals | WLAN_NS-SA2 | 2 | Rel-12 | S2 | 2012-06-22 08:00 | 2013-12-11 17:00 | 100% | SP-120847 | - | Intel | vivek.g.gupta@intel.com | SP#62 completed | 23.402, 23.865 | 56 | 29 |  |  | Thu 22/11/12 | Thu 28/11/13
2357 | 580055 | Deleted - TR on Security Aspects of WLAN Network Selection for 3GPP Terminals | WLAN_Nsdel | 2 | Rel-12 | S3 | 2012-12-13 08:00 | 2014-03-07 17:00 | 100% | SP-120847 | - | Huawei | Lydia Xu (xuyixian@huawei.com) | SP#63 stopped (84% complete) | New TR 33.865 | 58 | 30 | CP-63 | PCG-32 | Fri 02/11/12 | Tue 04/03/14
2358 | 620005 | CT aspects of WLAN Network Selection for 3GPP Terminals (Stage 3) | WLAN_NS-CT | 2 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-12-09 17:00 | 100% | CP-130712 | CP-140622 | Qualcomm | Amer Catovic, amerc@qualcomm.com | CP#65 completion 09/14=>12/14. CP#65 exception CP-140622. Dec.14: 95->100% | 24.302, 24.312 | 62 | 32 |  |  | Tue 19/11/13 | Thu 04/12/14
2359 | 570028 | Deleted - IMS Registration Control | IMS_RegCon | 1 | Rel-12 | S1,S2,C1,C4 | 2012-01-31 08:00 | 2013-12-11 17:00 | 100% | SP-120735 | - | China Mobile | lulu@chinamobile.com | SP#62 stopped. Specify for fixed line the requirement of controlling user registration to IMS based on network information related to user location (e.g. IP address, DSLAM information) | Stage 1/2/3 | 57 | 29 | SP-62 | PCG-32 | Mon 06/08/12 | Tue 10/12/13
2360 | 570128 | Deleted - Stage 1 for IMS Registration Control | IMS_RegCon-del1 | 2 | Rel-12 | S1 | 2012-01-31 08:00 | 2012-09-12 17:00 | 100% | SP-120735 | - | China Mobile | lulu@chinamobile.com | SP#57 completed | 22.228 | 57 | 29 | SP-62 | PCG-32 | Mon 06/08/12 | Tue 10/12/13
2361 | 580056 | Deleted - Stage 2 for IMS Registration Control | IMS_RegCon-del2 | 2 | Rel-12 | S2 | 2012-12-13 08:00 | 2013-12-11 17:00 | 100% | SP-120735 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 stopped at 50% completion | 23.228 | 58 | 30 | SP-62 | PCG-32 | Tue 13/11/12 | Tue 10/12/13
2362 | 600016 | Deleted - CT aspects of IMS registration control | IMS_RegCon-CT | 2 | Rel-12 | C1,C4 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | CP-130217 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 no CT/Stage 3 work is needed (stopped at 0% completion) | Stage 2/3 | 60 | 31 | SP-62 | PCG-32 | Tue 28/05/13 | Tue 10/12/13
2363 | 600116 | Deleted - CT1 aspects of CT aspects of IMS registration control (Stage 2/3) | IMS_RegCon-CT1 | 3 | Rel-12 | C1 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | CP-130217 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 no CT/Stage 3 work is needed (stopped at 0% completion) | 23.218, 24.229 | 60 | 31 | SP-62 | PCG-32 | Tue 28/05/13 | Tue 10/12/13
2364 | 600216 | Deleted - CT4 aspects of CT aspects of IMS registration control (Stage 3) | IMS_RegCon-CT4 | 3 | Rel-12 | C4 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | CP-130217 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | SP#62 no CT/Stage 3 work is needed (stopped at 0% completion) | 29.228, 29.229, 23.008 | 60 | 31 | SP-62 | PCG-32 | Tue 28/05/13 | Tue 10/12/13
2365 | 580059 | Proximity-based Services | ProSe | 1 | Rel-12 |  | 2012-12-13 08:00 | 2017-06-15 17:00 | 100% | SP-140574 | - | Qualcomm | Rich Hovey (rhovey@qualcomm.com) | SP#65 SA3 updated the SA-wide WID SP-140300=>SP-140574 (Moved the TR phase to Rel-13 as a stand-alone Study). Triggered by Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) UID_530044 | Stage 1/2 | 58 | 30 |  |  | Fri 16/11/12 | Mon 15/09/14
2366 | 580159 | Stage 1 for Proximity-based Services | ProSe-SA1 | 2 | Rel-12 | S1 | 2012-12-13 08:00 | 2013-06-19 17:00 | 100% | SP-140574 | - | Qualcomm | Rich Hovey (rhovey@qualcomm.com) | SP#60 completed | 22.115, 22.278 | 58 | 30 |  |  | Fri 16/11/12 | Mon 15/09/14
2367 | 580259 | TR on Stage 2 for Proximity-based Services | ProSe-SA2TR | 2 | Rel-12 | S2 | 2012-12-13 08:00 | 2014-03-07 17:00 | 100% | SP-140574 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#63 completed. TR 23.703v200 for Approval | New TR 23.703 | 58 | 30 |  |  | Fri 16/11/12 | Mon 15/09/14
2368 | 580359 | Stage 2 for Proximity-based Services | ProSe-SA2 | 2 | Rel-12 | S2 | 2012-12-19 08:00 | 2014-06-18 17:00 | 100% | SP-140574 | - | Qualcomm | Haris Zisimopoulos (harisz@qti.qualcomm.com) | SP#64 completed open issue/alignment to RAN/SA3 decisions. SP#63 TS 23.303v100 for 1-step Approval | New TS 23.303 | 58 | 30 |  |  | Fri 16/11/12 | Mon 15/09/14
2369 | 590036 | Security for Proximity-based Services | ProSe-SA3 | 2 | Rel-12 | S3 | 2013-03-13 08:00 | 2014-12-12 17:00 | 100% | SP-140574 | SP-140584 | Qualcomm | Adrian Escott (aescott@qti.qualcomm.com) | SP#65 re-opened. Completion 06/14=>12/14. Exception in SP-140584. Updated WID SP-140300=>SP-140574 (Moved the TR phase to Rel-13 as a stand-alone Study). SP#64 completed. TS 33.303 v100 for 1-step Approval; Aug2015: 90%->100 | 33.220, New TS 33.303 | 59 | 30 |  |  | Wed 20/02/13 | Fri 14/08/15
2370 | 651104 | (IETF) Security for Proximity-based Services (ietf-avtcore-srtp-aes-gcm) | ProSe | 2 | Rel-12 | S3-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 100% | SP-140574 | - | Atle Monrad | atle.monrad@ericsson.com | Submitted to IESG for publication; 7/3/16: 75%->100 | RFC 7714 (was ietf-avtcore-srtp-aes-gcm) | 65 | 33 |  |  | Mon 15/09/14 | Mon 07/03/16
2371 | 640039 | Charging Aspects of Proximity-based Services | ProSe-CH | 2 | Rel-12 | S5 | 2014-06-19 08:00 | 2015-03-13 17:00 | 100% | SP-140401 | SP-140543 | Qualcomm | Cheng Hong (hongc@qti.qualcomm.com) | SP#65 exception in SP-140543. Mar15: 85->100% | Stage 2/3 | 64 | 33 |  |  | Fri 06/06/14 | Thu 05/03/15
2372 | 640139 | Study on Charging support for ProSe one-to-many Direct Communication for Public Safety use | ProSe-CH-SA5TR | 3 | Rel-12 | S5 | 2014-06-19 08:00 | 2014-12-12 17:00 | 100% | SP-140401 | SP-140543 | Qualcomm | Cheng Hong (hongc@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Exception in SP-140543. TR 32.844v100 for Information. Dec.14: CD: 09/14->12/14, 60->100% | New TR 32.844 | 64 | 33 |  |  | Fri 06/06/14 | Fri 12/12/14
2373 | 640239 | Specification of Charging Aspects of Proximity-based Services | ProSe-CH-SA5 | 3 | Rel-12 | S5 | 2014-06-19 08:00 | 2015-03-13 17:00 | 100% | SP-140401 | SP-140543 | Qualcomm | Cheng Hong (hongc@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Exception in SP-140543. SP#65 TR 32.277v100 for Information. Dec.14: CD: 09/14->03/15, 40->75%. Mar15: 75->100% | 32.240, 32.297, 32.298, 32.299, New TS 32.277 | 64 | 33 |  |  | Fri 06/06/14 | Thu 05/03/15
2374 | 630006 | CT aspects of Proximity-based Services (Stage 3) | ProSe-CT | 2 | Rel-12 |  | 2014-03-05 08:00 | 2014-12-09 17:00 | 100% | CP-140290 | - | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#64 updated WID CP-140194=>CP-140290 | Stage 3 | 63 | 32 |  |  | Wed 29/01/14 | Mon 03/03/14
2375 | 630106 | CT1 part of CT aspects of Proximity-based Services | ProSe-CT | 3 | Rel-12 | C1 | 2014-03-05 08:00 | 2014-12-09 17:00 | 100% | CP-140290 | CP-140615 | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#65 completion 09/14=>12/14. Exception in CP-140615. TS 24.333/4v200 for Approval. Dec.14: 90->100% | 24.301, 23.122, New TSs (24.333, 24.334) | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
2376 | 630206 | CT3 part of CT aspects of Proximity-based Services | ProSe-CT | 3 | Rel-12 | C3 | 2014-03-05 08:00 | 2014-12-09 17:00 | 100% | CP-140290 | CP-140568 | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#65 completion 09/14=>12/14. TS 29.343v100 for 1-step Approval. Exception in CP-140568. Dec.14: 90->100 | New TS 29.343 | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
2377 | 630306 | CT4 part of CT aspects of Proximity-based Services | ProSe-CT | 3 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-12-09 17:00 | 100% | CP-140290 | CP-140484 | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#65 completion 09/14=>12/14. TS 29.344/5v100 for 1-step Approval. Exception in CP-140484. Dec.14: 90->100 | 29.272, 23.008, 23.003, New TSs (29.344, 29.345) | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
2378 | 630406 | CT6 part of CT aspects of Proximity-based Services | ProSe-CT | 3 | Rel-12 | C6 | 2014-03-06 08:00 | 2014-12-09 17:00 | 100% | CP-140290 | CP-140695 | Qualcomm | Lena Chaponniere (lguellec@qti.qualcomm.com) | CP#65 completion 09/14=>12/14. Exception in CP-140695. Dec.14: 60->100% | 31.102 | 63 | 32 |  |  | Wed 29/01/14 | Wed 03/12/14
2379 | 630030 | LTE Device to Device Proximity Services | LTE_D2D_Prox | 2 | Rel-12 |  | 2014-03-11 08:00 | 2017-06-15 17:00 | 100% | RP-140955 | - | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | follow-up of TR 36.843 FS_LTE_D2D_Prox | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
2380 | 630130 | Core part: LTE Device to Device Proximity Services | LTE_D2D_Prox-Core | 3 | Rel-12 | R1,R2,R4 | 2014-03-15 | 2015-03-13 17:00 | 100% | RP-142043 | RP-150094 | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | ; CD:Sat 15/03/14->Sun 15/03/15Compl:0%->95%; CD:Fri 13/03/15->Sun 15/03/15; Stat Rep: RP-141244->RP-141894 1st Apr 15: Compl:95%->100% 1st Apr 15: Stat Rep: RP-141894->RP-150094 | 36.101, 36.133, 36.211, 36.212, 36.213, 36.214, 36.300, 36.304, 36.306, 36.321, 36.322, 36.323, 36.331, 36.413, 36.423, New TR 36.877 | 63 | 32 |  |  | Mon 10/03/14 | Wed 01/04/15
2381 | 630230 | Perf. part: LTE Device to Device Proximity Services | LTE_D2D_Prox-Perf | 3 | Rel-12 | R4 | 2014-03-11 08:00 | 2015-12-15 17:00 | 100% | RP-142043 | RP-151276 | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | ; CD:Sat 15/03/14->Sun 15/03/15; Stat Rep: RP-141244->RP-141894 1st Apr 15: Compl:10%->25% 1st Apr 15: Stat Rep: RP-141894->RP-150094 03/07/15: Compl:25%->70% 03/07/15: Stat Rep: RP-150094->RP-150760 29/09/15: Compl:70%->95% 29/09/15: CD:Tue 15/09/15-> | 36.101, 36.133 | 63 | 32 |  |  | Mon 10/03/14 | Fri 01/01/16
2382 | 670046 | UE Conformance Test Aspects – LTE Device-to-Device Proximity Services | LTE_D2D_Prox-UEConTest | 3 | Rel-12 | R5 | 2015-03-16 08:00 | 2017-06-15 17:00 | 100% | RP-160382 |  | Qualcomm | svora@qti.qualcomm.com | rapporteur e-mail added 03/07/15: Compl:0%->10% 03/07/15: Stat Rep: ->RP-150765 29/09/15: Compl:10%->30% 29/09/15: CD:Tue 15/12/15->Wed 15/06/16 29/09/15: Stat Rep: RP-150765->RP-151280 1/1/16: Compl:30%->45% 1/1/16: WID: RP-1; ; |  | 67 | 34 |  |  | Wed 01/04/15 | Mon 19/06/17
2383 | 580062 | Web Real Time Communication access to IMS | IMS_WebRTC | 1 | Rel-12 | S1,S2,S3 | 2012-12-14 08:00 | 2014-12-12 17:00 | 88% | SP-130707 | - | China Mobile | lulu@chinamobile.com | IETF RTCWEB and W3C WEBRTC groups are specifying a browser-based client to support communication services. Interoperability for WebRTC clients to access 3GPP IMS is needed. | Stage 1/2 | 58 | 30 |  |  | Fri 16/11/12 | Mon 09/09/13
2384 | 580162 | Stage 1 for Web Real Time Communication access to IMS | IMS_WebRTC | 2 | Rel-12 | S1 | 2012-12-14 08:00 | 2013-06-19 17:00 | 100% | SP-130707 | - | China Mobile | lulu@chinamobile.com | SP#60 completed | 22.101, 22.228 | 58 | 30 |  |  | Fri 16/11/12 | Mon 09/09/13
2385 | 600040 | TR on Stage 2 for Web Real Time Communication access to IMS | IMS_WebRTC | 2 | Rel-12 | S2 | 2013-06-19 08:00 | 2013-12-11 17:00 | 100% | SP-130707 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#62 completed. TR 23.701v100 for Information & Approval | New TR 23.701 | 60 | 31 |  |  | Thu 06/06/13 | Mon 09/09/13
2386 | 600041 | Stage 2 for Web Real Time Communication access to IMS | IMS_WebRTC | 2 | Rel-12 | S2 | 2013-06-19 08:00 | 2014-03-07 17:00 | 100% | SP-130707 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#63 completed | 23.228 | 60 | 31 |  |  | Thu 06/06/13 | Tue 04/02/14
2387 | 631001 | (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-overview) | IMS_WebRTC | 2 | Rel-12 | C1-IETF | 2013-06-25 08:00 | 2014-12-12 17:00 | 50% | SP-130707 | - | Uwe Rauschenbach | Uwe Rauschenbach | In WGLC. Mar15: responsible WG changed from S2-IETF | draft-ietf-rtcweb-overview | 63 | 32 |  |  | Mon 10/02/14 | Tue 10/03/15
2388 | 620067 | TR on Security for Web Real Time Communication access to IMS | IMS_WebRTC | 2 | Rel-12 | S3 | 2013-12-11 08:00 | 2014-09-17 17:00 | 100% | SP-130707 | - | Ericsson | oscar.ohlsson@ericsson.com | SP#65 completed. TR 33.871v200 for Approval | New TR 33.871 | 62 | 32 |  |  | Thu 05/12/13 | Thu 04/09/14
2389 | 610036 | Security for Web Real Time Communication access to IMS | IMS_WebRTC | 2 | Rel-12 | S3 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130707 | - | Ericsson | oscar.ohlsson@ericsson.com | SP#64 completed | 33.203, 33.328 | 61 | 31 |  |  | Tue 03/09/13 | Mon 09/06/14
2390 | 630003 | CT aspects of Web Real Time Communication (WebRTC) Access to IMS | IMS_WebRTC-CT | 2 | Rel-12 | C1,C4,IETF | 2014-03-05 08:00 | 2014-12-09 17:00 | 93% | CP-140192 | - | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | - | Stage 3 | 63 | 32 |  |  | Wed 29/01/14 | Sat 06/09/14
2391 | 630103 | CT1 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS | IMS_WebRTC-CT1 | 3 | Rel-12 | C1 | 2014-03-05 08:00 | 2014-12-09 17:00 | 100% | CP-140192 | CP-140621 | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | CP#65 TS 24.371v100 for Information. Completion 09/14=>12/14. Exception in CP-140621. Dec.14: 70->90%. 3/3/15: 100% cpltd. | 24.229, New TS 24.371 | 63 | 32 |  |  | Wed 29/01/14 | Tue 03/03/15
2392 | 641006 | (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-data-channel) | IMS_WebRTC-data | 3 | Rel-12 | C1-IETF | 2014-03-06 08:00 | 2014-12-09 17:00 | 90% | CP-140192 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Submitted to IESG for publication. Mar15: In RFC-Editors queue | draft-ietf-rtcweb-data-channel | 64 | 33 |  |  | Fri 06/06/14 | Tue 10/03/15
2393 | 641007 | (IETF) Web Real Time Communication access to IMS (draft-ietf-rtcweb-stun-consent-freshness) | IMS_WebRTC-stun | 3 | Rel-12 | C1-IETF | 2014-03-06 08:00 | 2014-12-09 17:00 | 100% | CP-140192 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Mar15: Publication requested; 7/3/16: 50%->100 | draft-ietf-rtcweb-stun-consent-freshness | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/03/16
2394 | 651001 | (IETF) Web Real Time Communication access to IMS (draft-ietf-sipcore-sip-authn) | IMS_WebRTC-yusef | 3 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-05 17:00 | 25% | CP-140192 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress | draft-yusef-sipcore-sip-oaut | 65 | 33 |  |  | Tue 02/09/14 | Sat 06/09/14
2395 | 660031 | Deleted - (IETF) Web Real Time Communication access to IMS (draft-holmberg-sipcore-auth-id) | IMS_WebRTC-holmb | 3 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 100% | CP-140192 |  | christer.holmberg@ericsson.com |  | 7/3/16: 25%->100 since deleted (draft no longer needed). | draft-holmberg-sipcore-auth-id | 66 | 34 |  |  | Thu 04/12/14 | Mon 07/03/16
2396 | 630203 | CT4 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS | IMS_WebRTC-CT4 | 3 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-12-09 17:00 | 100% | CP-140192 | CP-140732 | China Mobile | Jiang Yi (jiangyi@chinamobile.com) | CP#65 completion 09/14=>12/14. Exception in CP-140732. Dec.14: 30->80%. Mar. 15: 100% | 23.334, 29.334 | 63 | 32 |  |  | Wed 29/01/14 | Wed 04/03/15
2397 | 580063 | Usage Monitoring Control PCC enhancement | UMONC | 1 | Rel-12 | S2,C3 | 2012-12-13 08:00 | 2013-09-06 17:00 | 100% | SP-120928 | - | ZTE | bi.yifeng@zte.com.cn | SP#59 Stage 2 completed. Triggered by Rel-12 TR 23.858 Study on Usage Monitoring Control enhancement (UID_520035) | Stage 2/3 | 58 | 30 |  |  | Sun 18/11/12 | Wed 27/02/13
2398 | 580163 | Stage 2 for Usage Monitoring Control PCC enhancement | UMONC | 2 | Rel-12 | S2 | 2012-12-13 08:00 | 2013-03-06 17:00 | 100% | SP-120928 | - | ZTE | bi.yifeng@zte.com.cn | SP#59 completed. 23.203 CR#0782 (Time Based Usage Monitoring), CR#0784 (Usage Monitoring via Online Charging System) | 23.203 | 58 | 30 |  |  | Sun 18/11/12 | Wed 27/02/13
2399 | 600048 | CT3 aspects of Usage Monitoring Control PCC enhancement (Stage 3) | UMONC-CT3 | 2 | Rel-12 | C3 | 2013-06-14 08:00 | 2013-09-06 17:00 | 100% | CP-130396 | - | ZTE | zhou.xiaoyun@zte.com.cn | CP#61 completed. 2/4/15: acronym changed to "UMONC-CT3" | 29.212, 29.214, 29.215 | 60 | 31 |  |  | Wed 29/05/13 | Thu 02/04/15
2400 | 590039 | Application Based Charging | ABC | 1 | Rel-12 | S2,S5,C3 | 2013-03-07 08:00 | 2014-06-18 17:00 | 100% | SP-130328 | - | Allot | Alla Goldner (agoldner@allot.com) | Triggered by TR 23.800 Study on Application Based Charging (FS_ABC) UID_560038 | Stage 2/3 | 59 | 30 |  |  | Thu 21/02/13 | Thu 06/06/13
2401 | 590139 | Stage 2 for Application Based Charging | ABC-SA2 | 2 | Rel-12 | S2 | 2013-03-07 08:00 | 2013-06-19 17:00 | 100% | SP-130328 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#60 completed | 23.203 | 59 | 30 |  |  | Thu 21/02/13 | Thu 25/07/13
2402 | 600011 | Charging for Application Based Charging | ABC-CT5 | 2 | Rel-12 | S5 | 2013-06-19 08:00 | 2014-06-18 17:00 | 100% | SP-130328 | - | Openet Telecom | alan.mcnamee@openet.com | SP#64 completed | 32.240, 32.251, 32.296, 32.298, 32.299 | 60 | 31 |  |  | Wed 29/05/13 | Tue 10/06/14
2403 | 600049 | CT3 aspects of Application Based Charging (Stage 3) | ABC-CT3 | 2 | Rel-12 | C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130353 | - | Allot | Alla Goldner (agoldner@allot.com) | CP#62 completed | 29.212, 29.213, 29.214, 29.215, 29.219 | 60 | 31 |  |  | Wed 29/05/13 | Mon 21/10/13
2404 | 610038 | Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG | 1 | Rel-12 | S2,C1,C4 | 2013-09-09 08:00 | 2014-12-09 17:00 | 100% | SP-130391 | - | ZTE | Tricci So (tso@zteusa.com) | - | Stage 2/3 | 61 | 31 |  |  | Thu 25/07/13 | Mon 09/09/13
2405 | 610138 | Stage 2 for Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG-SA2 | 2 | Rel-12 | S2 | 2013-09-11 08:00 | 2014-03-07 17:00 | 100% | SP-130391 | - | ZTE | Tricci So (tso@zteusa.com) | SP#63 completed | 23.402 | 61 | 31 |  |  | Thu 25/07/13 | Tue 04/02/14
2406 | 610009 | Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG-St3 | 2 | Rel-12 | C1,C4 | 2013-09-09 08:00 | 2014-12-09 17:00 | 100% | CP-130715 | - | ZTE | Joy Zhou (zhou.xingyue@zte.com.cn) | CP#62 updated WID CP-130580=>CP-130715 | Stage 3 | 61 | 31 |  |  | Sat 10/08/13 | Thu 28/11/13
2407 | 610109 | CT1 part of Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG-St3 | 3 | Rel-12 | C1 | 2013-09-09 08:00 | 2014-12-09 17:00 | 100% | CP-130715 | CP-140608 | ZTE | Joy Zhou (zhou.xingyue@zte.com.cn) | CP#65 completion 09/14=>12/14. Exception in CP-140608. TS 24.244 v200 for Approval. Dec.14: 95->100% | 24.302, New TS 24.244 (WLAN control plane protocol for trusted WLAN access to EPC) | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
2408 | 610209 | CT4 part of Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG-St3 | 3 | Rel-12 | C4 | 2013-09-09 08:00 | 2014-09-11 17:00 | 100% | CP-130715 | - | ZTE | Joy Zhou (zhou.xingyue@zte.com.cn) | CP#65 completed | 29.273, 29.274, 29.275 | 61 | 31 |  |  | Sat 10/08/13 | Mon 28/07/14
2409 | 610039 | Optimized Offloading to WLAN in 3GPP-RAT Mobility | WORM | 1 | Rel-12 | S2,C1 | 2013-09-12 08:00 | 2014-06-13 17:00 | 100% | SP-130392 | - | BlackBerry | Steve Barrett (sbarrett@blackberry.com) | Linked to TR 23.890 Study on Optimized Offloading to WLAN in 3GPP-RAT mobility (FS_WORM), SAE for support for non-3GPP accesses, Multi-Access PDN Connectivity (MAPCON), IP Flow Mobility and Seamless WLAN Offload (IFOM), CS Fallback in EPS (SAES-CSFB) | Stage 2/3 | 61 | 31 |  |  | Thu 25/07/13 | Mon 09/09/13
2410 | 610139 | Stage 2 for Optimized Offloading to WLAN in 3GPP-RAT Mobility | WORM-SA2 | 2 | Rel-12 | S2 | 2013-09-12 08:00 | 2013-12-11 17:00 | 100% | SP-130392 | - | BlackBerry | Steve Barrett (sbarrett@blackberry.com) | SP#62 completed | 23.272, 23.401, 23.402 | 61 | 31 |  |  | Thu 25/07/13 | Thu 28/11/13
2411 | 620003 | CT aspects of Optimized Offloading to WLAN in 3GPP-RAT Mobility (Stage 3) | WORM-CT | 2 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-06-13 17:00 | 100% | CP-140109 |  | Intel | Chen-ho Chin (chen-hox.chin@intel.com) | CP#64 completed. Stage 3 enabling differentiation/prioritization of 3GPP RATs relative to WLAN for traffic flow routing based on Inter-System Routing Policies | 24.302, 24.312 | 62 | 32 |  |  | Mon 18/11/13 | Mon 26/05/14
2412 | 610040 | Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN | 1 | Rel-12 | S2,C3,C1,C4 | 2013-09-12 08:00 | 2014-09-11 17:00 | 100% | SP-130393 | - | Alcatel-Lucent | Laurent.thiebaut@alcatel-lucent.com | Rel-11 Network Provided Location Information for IMS (NWK-PL2IMS) covers the case where UE is served by a 3GPP RAN. This WI covers the case where the UE is served by a TWAN | Stage 2/3 | 61 | 31 |  |  | Thu 25/07/13 | Mon 09/09/13
2413 | 610140 | Stage 2 for Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN-SA2 | 2 | Rel-12 | S2 | 2013-09-12 08:00 | 2014-03-07 17:00 | 100% | SP-130393 | - | Alcatel-Lucent | Laurent.thiebaut@alcatel-lucent.com | SP#63 completed | 23.203, 23.228, 23.402 | 61 | 31 |  |  | Thu 25/07/13 | Tue 04/02/14
2414 | 620008 | CT aspects of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case (Stage 3) | NETLOC_TWAN-CT | 2 | Rel-12 | C3,C1,C4 | 2013-12-06 08:00 | 2014-09-11 17:00 | 100% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | - | Stage 3 | 62 | 32 |  |  | Tue 19/11/13 | Tue 19/11/13
2415 | 620108 | CT3 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN-CT | 3 | Rel-12 | C3 | 2013-12-06 08:00 | 2014-06-13 17:00 | 100% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | CP#64 completed | 29.212, 29.214 | 62 | 32 |  |  | Tue 19/11/13 | Wed 16/04/14
2416 | 620208 | CT1 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN-CT | 3 | Rel-12 | C1 | 2013-12-09 08:00 | 2014-09-11 17:00 | 100% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | CP#65 completed | 24.229 | 62 | 32 |  |  | Tue 19/11/13 | Mon 28/07/14
2417 | 620308 | CT4 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case | NETLOC_TWAN-CT | 3 | Rel-12 | C4 | 2013-12-06 08:00 | 2014-09-11 17:00 | 100% | CP-130810 | - | China Telecom | Xia Xu (xiaxu@ctbri.com.cn) | CP#65 completed | 29.273, 29.274, 29.275, 29.328, 29.329 | 62 | 32 |  |  | Tue 19/11/13 | Mon 28/07/14
2418 | 620061 | Core Network Overload - User Location Information reporting improvement | CNO_ULI | 1 | Rel-12 | S2,C3,C4,S5 | 2013-12-11 08:00 | 2014-09-17 17:00 | 100% | SP-130717 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | - | Stage 2/3 | 62 | 32 |  |  | Thu 28/11/13 | Sun 28/09/14
2419 | 620161 | Stage 2 for Core Network Overload - User Location Information reporting improvement | CNO_ULI-SA2 | 2 | Rel-12 | S2 | 2013-12-11 08:00 | 2014-03-07 17:00 | 100% | SP-130717 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | SP#63 completed | 23.060, 23.203, 23.401 | 62 | 32 |  |  | Thu 28/11/13 | Tue 04/02/14
2420 | 650017 | Charging aspects of Core Network Overload – User Location Information reporting improvements | CNO_ULI-CH | 2 | Rel-12 | S5 | 2014-09-15 08:00 | 2014-09-17 17:00 | 100% | SP-140541 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#65 New WID approved & completed. Introduction of Presence Reporting Areas for Charging | 32.251, 32.298, 32.299 | 65 | 33 |  |  | Sun 24/08/14 | Wed 10/09/14
2421 | 630004 | CT aspects of Core Network Overload – User Location Information reporting improvements | CNO_ULI-CT | 2 | Rel-12 | C3,C4 | 2014-03-05 08:00 | 2014-09-11 17:00 | 100% | CP-140093 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | Specify Stage 3 procedures to support the ULI signalling optimizations | Stage 3 | 63 | 32 |  |  | Wed 29/01/14 | Wed 29/01/14
2422 | 630104 | CT3 part of CT aspects of Core Network Overload – User Location Information reporting improvements | CNO_ULI-CT | 3 | Rel-12 | C3 | 2014-03-05 08:00 | 2014-06-13 17:00 | 100% | CP-140093 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | CP#64 completed | 29.212, 29.213 | 63 | 32 |  |  | Wed 29/01/14 | Tue 03/06/14
2423 | 630204 | CT4 part of CT aspects of Core Network Overload – User Location Information reporting improvements | CNO_ULI-CT | 3 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-09-11 17:00 | 100% | CP-140093 | - | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | CP#65 completed | 23.008, 29.060, 29.274 | 63 | 32 |  |  | Wed 29/01/14 | Mon 28/07/14
2424 | 560028 | Rel-12 Security small Enhancements | SEC12 | 1 | Rel-12 | S3 | 2011-03-23 08:00 | 2014-09-17 17:00 | 100% | - | - | - | - | SEC12 is an umbrella Feature for Security related TEI12 type of changes that are not part of any other dedicated feature | Stage 2/3 | 56 | 29 |  |  | Sat 02/06/12 | Thu 04/09/14
2425 | 510054 | Security aspects of Public Warning System | PWS_Sec | 1 | Rel-12 | S3,S1 | 2011-03-23 08:00 | 2014-09-17 17:00 | 100% | SP-140299 | - | ST-Ericsson | john.mattsson@ericsson.com | - | - | 51 | 26 |  |  | Sat 02/06/12 | Mon 09/06/14
2426 | 560029 | Stage 1 for Protection against false PWS Warning Notifications | PWS_Sec-SA1 | 2 | Rel-12 | S1 | 2012-06-15 08:00 | 2012-09-12 17:00 | 100% | SP-120433 | - | Vodafone | adrian.neal@vodafone.com | SP#57 completed. Specify reqs to protect against false PWS Warning Notifications (Optional as not all regions/countries require this functionality). WID covers all objectivES in CP-150SA3 PWS_Sec Feature-level WID replacing the original Stage 1 UID_510154 | 22.268 | 56 | 29 |  |  | Thu 07/06/12 | Tue 07/08/12
2427 | 510354 | TR on SA3 part for Security aspects of Public Warning System | PWS_Sec-SA3TR | 2 | Rel-12 | S3 | 2011-03-23 08:00 | 2014-09-17 17:00 | 100% | SP-140299 | - | ST-Ericsson | john.mattsson@ericsson.com | SP#65 completed. TR 33.969v100 for 1-step Approval. Former TR 33.869 changed to 33.969. | New TR 33.869 changed to 33.969 | 51 | 26 |  |  | Sat 02/06/12 | Thu 04/09/14
2428 | 511354 | Deleted - SA3 part for Security aspects of Public Warning System | PWS_Sec-del1 | 2 | Rel-12 | S3 | 2011-03-30 08:00 | 2014-06-18 17:00 | 100% | SP-140299 | - | ST-Ericsson | john.mattsson@ericsson.com | SP#64 stopped | New TS 33.269 | 51 | 26 | SP-64 | PCG-33 | Sat 02/06/12 | Mon 09/06/14
2429 | 510154 | Deleted - Stage 1 for Security aspects of Public Warning System | PWS_Sec-del2 | 2 | Rel-12 | S1 | 2011-03-23 08:00 | 2012-06-20 17:00 | 100% | SP-120434 | - | ST-Ericsson | john.mattsson@ericsson.com | Completed in Rel-9 under PWS. SP#55 stopped, Stage 1 requirements removed from Rel-9 onwards (SP-120172). AP 55/1: SA1 to align Stage 1 PWS security for Rel-12. SA1 new WID PWS Security UID_560029. | 22.268 | 51 | 26 | SP-56 | PCG-29 | Sat 02/06/12 | Tue 26/06/12
2430 | 510254 | Deleted - Stage 2 for Security aspects of Public Warning System | PWS_Sec-del3 | 2 | Rel-12 | S2 | 2011-03-23 08:00 | 2011-09-21 17:00 | 100% | SP-120434 | - | ST-Ericsson | john.mattsson@ericsson.com | SP#53 work stopped as already done in previous releases | 23.401 | 51 | 26 | SP-53 | PCG-27 | Sat 02/06/12 | Mon 20/02/12
2431 | 510454 | Deleted - CT1 part for Security aspects of Public Warning System | PWS_Sec-del4 | 2 | Rel-12 | C1 | 2011-03-25 08:00 | 2012-06-20 17:00 | 100% | SP-120434 | - | ST-Ericsson | mikael.wass@ericsson.com | TSG#56 work stopped. SP#56 updated WID SP-110223=>SP-120334 (removed all but SA3 impacted specs) | 23.041 | 51 | 26 | SP-56 | PCG-29 | Sat 02/06/12 | Fri 08/06/12
2432 | 510554 | Deleted - RAN2 part for Security aspects of Public Warning System | PWS_Sec-del5 | 2 | Rel-12 | R2 | 2011-03-25 08:00 | 2011-09-16 17:00 | 100% | SP-120434 | - | ST-Ericsson | john.mattsson@ericsson.com | RP#53 work stopped as no WI in RAN | 36.331 | 51 | 26 | RP-53 | PCG-27 | Sat 02/06/12 | Mon 20/02/12
2433 | 520031 | Security enhancements for usage of Generic Bootstrapping Architecture (GBA) from the browser (Stage 2) | Web_GBA | 1 | Rel-12 | S3 | 2011-06-08 08:00 | 2013-06-20 08:00 | 100% | SP-120890 | - | Nokia | Silke.Holtmanns@nokia.com | SP#60 completed | 33.220, 33.222, New TR 33.823 | 52 | 27 |  |  | Tue 17/05/11 | Mon 01/07/13
2434 | 560030 | Extended IMS media plane security features | eMEDIASEC | 1 | Rel-12 | S3,C4,C1,C3,IETF | 2012-06-20 08:00 | 2014-12-09 17:00 | 97% | SP-120447 | - | Vodafone | Aguibou.Barry@vodafone.com | Triggered by Rel-11 TR 33.829 Study on Extended IMS media plane security features (FS_eMEDIASEC) | Stage 2/3 | 56 | 29 |  |  | Sat 02/06/12 | Tue 19/02/13
2435 | 560130 | SA3 part of Extended IMS media plane security features (Stage 2) | eMEDIASEC-SA3 | 2 | Rel-12 | S3 | 2012-06-20 08:00 | 2014-06-18 17:00 | 100% | SP-120447 | - | Vodafone | Aguibou.Barry@vodafone.com | SP#64 completed | 33.328 | 56 | 29 |  |  | Sat 02/06/12 | Tue 10/06/14
2436 | 611003 | (IETF) SA3 part of Extended IMS media plane security features (RFC 7345) | eMEDIASECSA3IETF | 2 | Rel-12 | S3-IETF | 2012-06-20 08:00 | 2014-09-12 17:00 | 100% | SP-120447 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | SP#65 completed | RFC 7345 (was draft-ietf-mmusic-udptl-dtls) | 61 | 31 |  |  | Mon 23/09/13 | Tue 02/09/14
2437 | 580005 | CT aspects of Extended IMS media plane security features (Stage 2/3) | eMEDIASEC-CT | 2 | Rel-12 | C4,C1,C3,IETF | 2012-12-13 08:00 | 2014-12-09 17:00 | 95% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | - | Stage 2/3 | 58 | 30 |  |  | Wed 14/11/12 | Tue 19/11/13
2438 | 600051 | TR on Extended IMS media plane security features and TCP related NAT traversal support; IMS H.248 profiles aspects | eMEDIASEC-CT | 3 | Rel-12 | C4 | 2012-12-13 08:00 | 2014-09-11 17:00 | 100% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#65 completed. TR 29.828v200 for Approval. 2/4/15: acronym changed to eMEDIASEC-CT | New TR 29.828 | 58 | 30 |  |  | Wed 14/11/12 | Thu 02/04/15
2439 | 580006 | CT4 part of CT aspects of Extended IMS media plane security features | eMEDIASEC-CT | 3 | Rel-12 | C4 | 2012-12-19 08:00 | 2014-12-09 17:00 | 100% | CP-130597 | CP-140479 | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#65 completion 09/14=>12/14. Exception in CP-140479. Dec.14: 90->100. 2/4/15: acronym changed to eMEDIASEC-CT | 23.334, 29.334, 29.238, 23.333, 29.333 | 58 | 30 |  |  | Wed 14/11/12 | Thu 02/04/15
2440 | 621001 | (IETF) CT4 part of Extended IMS media plane security features (RFC 7345) | eMEDIASEC-CT | 3 | Rel-12 | C4-IETF | 2012-12-18 08:00 | 2014-09-11 17:00 | 100% | CP-130597 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT | RFC 7345 (was draft-ietf-mmusic-udptl-dtls) | 62 | 32 |  |  | Wed 27/11/13 | Thu 02/04/15
2441 | 641009 | (IETF) CT4 part of Extended IMS media plane security features (draft-schwarz-mmusic-sdp-for-gw) | eMEDIASEC-CT | 3 | Rel-12 | C4-IETF | 2014-06-12 08:00 | 2014-12-09 17:00 | 0% | CP-130597 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Work in progress. 2/4/15: acronym changed to eMEDIASEC-CT; 22/3/18: 100%->0 | draft-schwarz-mmusic-sdp-for-gw | 64 | 33 |  |  | Thu 12/06/14 | Thu 22/03/18
2442 | 580007 | CT1 part of CT aspects of Extended IMS media plane security features | eMEDIASEC-CT | 3 | Rel-12 | C1 | 2012-12-13 08:00 | 2014-09-11 17:00 | 100% | CP-130597 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT | 23.218, 24.147, 24.229, 24.247 | 58 | 30 |  |  | Wed 14/11/12 | Thu 02/04/15
2443 | 621002 | (IETF) CT1 part of Extended IMS media plane security features (RFC 7345) | eMEDIASEC-CT | 3 | Rel-12 | C1-IETF | 2014-03-06 08:00 | 2014-09-11 17:00 | 100% | CP-130597 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#65 completed. 2/4/15: acronym changed to eMEDIASEC-CT | RFC 7345 (was draft-ietf-mmusic-udptl-dtls) | 62 | 32 |  |  | Wed 27/11/13 | Thu 02/04/15
2444 | 580008 | CT3 part of CT aspects of Extended IMS media plane security features | eMEDIASEC-CT | 3 | Rel-12 | C3 | 2012-12-19 08:00 | 2014-12-09 17:00 | 100% | CP-130597 | CP-140569 | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#65 completion 06/14=>12/14. Level 100%=>80%. Exception in CP-140569. CP#64 completed. Dec.14: 80->100. 2/4/15: acronym changed to eMEDIASEC-CT | 29.162 | 58 | 30 |  |  | Wed 14/11/12 | Thu 02/04/15
2445 | 570032 | Lawful Interception in the 3GPP Rel-12 | LI12 | 1 | Rel-12 | S3 | 2012-09-17 08:00 | 2014-12-12 17:00 | 100% | SP-130650 | - | PIDS, Alcatel-Lucent | Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com | 3/3/15: 75->100% | 33.106, 33.107, 33.108 | 57 | 29 |  |  | Fri 31/08/12 | Tue 03/03/15
2446 | 580064 | Tunneling of UE Services over Restrictive Access Networks (Stage 2/3) | TURAN | 1 | Rel-12 | S3,C1 | 2012-12-13 08:00 | 2014-06-18 17:00 | 100% | SP-130245 | - | Acme Packet | Prashant Kumar (PKumar@acmepacket.com) | Linked to Rel-12 SMURFs. Related to TS 22.278 (EPS) cl.7.1.8 Service Reachability (Firewall traversal for IP based services for non-3GPP access), TS 22.228 (IMS) cl.5 (support Firewall traversal), TR 33.830 (Study on Firewall traversal) | Stage 2/3 | 58 | 30 |  |  | Mon 12/11/12 | Wed 20/02/13
2447 | 580164 | SA3 part of Tunneling of UE Services over Restrictive Access Networks (Stage 2/3) | TURAN-SA3 | 2 | Rel-12 | S3 | 2012-12-13 08:00 | 2014-06-18 17:00 | 100% | SP-130245 | - | Acme Packet | Prashant Kumar (PKumar@acmepacket.com) | SP#64 completed | 33.203, 33.402 | 58 | 30 |  |  | Mon 12/11/12 | Mon 09/06/14
2448 | 600050 | CT aspects of Tunneling of UE Services over Restrictive Access Networks (Stage 3) | TURAN-CT | 2 | Rel-12 | C1 | 2013-06-14 08:00 | 2014-06-13 17:00 | 100% | CP-130716 | - | Huawei | Haitao Wei (weihaitao@huawei.com) | CP#64 completed. Stage 3 for 2 new SA3 solutions for firewall traversal: 1) UE access to PLMN IP-based services via restrictive non-3GPP Ans, 2) UE access to IMS services via restrictive ANs | 24.229, 24.302, New TS 24.322 | 60 | 31 |  |  | Tue 28/05/13 | Mon 26/05/14
2449 | 620065 | Specification of the TUAK Algorithm Set | STAS | 1 | Rel-12 | S3 | 2013-12-09 08:00 | 2014-06-18 17:00 | 100% | SP-140814 | - | Vodafone | aguibou.barry@vodafone.com | SP#64 completed. Triggered by SP-130602 LS from ETSI SAGE (TUAK as alternative to Milenage). 12/14: new TS added | New TSs: 35.231, 35.232, 35.233, TR 35.9nn, TR 35.9nn, TR 35.9nn | 62 | 32 |  |  | Fri 22/11/13 | Fri 12/12/14
2450 | 470030 | Codec for Enhanced Voice Services | EVS_codec | 1 | Rel-12 | S4,S1,C4,C1,C3 | 2010-03-25 08:00 | 2016-03-15 17:00 | 100% | SP-140151 | - | Huawei | lei.miao@huawei.com | Triggered by UID_370045 Study on enhanced voice service requirements for EPS (TR 22.813) | - | 47 | 24 |  |  | Wed 10/03/10 | Thu 27/02/14
2451 | 470031 | Stage 1 for Codec for Enhanced Voice Services | EVS_codec-SA1 | 2 | Rel-12 | S1 | 2010-03-25 08:00 | 2010-03-25 17:00 | 100% | SP-140007 | - | Huawei | lei.miao@huawei.com | SP#47 completed | 22.173 | 47 | 24 |  |  | Wed 10/03/10 | Mon 22/03/10
2452 | 470032 | Stage 2/3 for Codec for Enhanced Voice Services | EVS_codec-SA4 | 2 | Rel-12 | S4 | 2010-03-25 08:00 | 2014-12-12 17:00 | 100% | SP-140151 | SP-140467 | Huawei | lei.miao@huawei.com | SP#65 completion 09/14=>12/14. Exception in SP-140467. TS 26.441v200 for Approval. TSs 26.442/44/45/46/47/48/49/50/51v100 for 1-step Approval. Ongoing TS 26.443 EVS Codec ANSI C code (floating point). Dec.14: 90->95 | 26.114, New TS (26.441, 26.442, 26.443, 26.444, 26.445, 26.446, 26.447, 26.448, 26.449, 26.450, 26.451) | 47 | 24 |  |  | Wed 10/03/10 | Fri 26/06/15
2453 | 470132 | TR on Performance characterization of Codec for Enhanced Voice Services | EVS_codec-SA4TR | 2 | Rel-12 | S4 | 2010-03-25 08:00 | 2014-12-12 17:00 | 100% | SP-140151 | SP-140467 | Huawei | lei.miao@huawei.com | SP#65 completion 09/14=>12/14. Ongoing TR 26.952 EVS Codec Performance Characterization. Exception in SP-140467 | New TR 26.952 | 47 | 24 |  |  | Wed 10/03/10 | Fri 26/06/15
2454 | 650005 | CT impacts of codec for Enhanced Voice Services | EVS_codec-CT | 2 | Rel-12 | C4,C1,C3 | 2014-09-16 08:00 | 2014-12-09 17:00 | 100% | CP-140800 | - | Nokia Networks | Jan.Kall@nsn.com | Stage 3; WID: CP-140492-> CP-140800 |  | 65 | 33 |  |  | Tue 29/07/14 | Tue 09/12/14
2455 | 650105 | CT4 part of CT impacts of codec for Enhanced Voice Services | EVS_codec-CT | 3 | Rel-12 | C4 | 2014-09-16 08:00 | 2014-12-09 17:00 | 100% | CP-140800 | CP-140478 | Nokia Networks | Jan.Kall@nsn.com | CP#65 exception in CP-140478. Dec.14: 0->100; WID: CP-140492-> CP-140800 | 23.334, 29.232, 29.238, 29.332, 29.333, 29.334 | 65 | 33 |  |  | Tue 29/07/14 | Tue 09/12/14
2456 | 650205 | CT1 part of CT impacts of codec for Enhanced Voice Services | EVS_codec-CT | 3 | Rel-12 | C1 | 2014-09-16 08:00 | 2014-12-09 17:00 | 100% | CP-140800 | CP-140618 | Nokia Networks | Jan.Kall@nsn.com | CP#65 exception in CP-140618. Dec.14: 0->100%; WID: CP-140492-> CP-140800 | 24.229 | 65 | 33 |  |  | Tue 29/07/14 | Tue 09/12/14
2457 | 650305 | CT3 part of CT impacts of codec for Enhanced Voice Services | EVS_codec-CT | 3 | Rel-12 | C3 | 2014-09-16 08:00 | 2014-12-09 17:00 | 100% | CP-140800 | CP-140560 | Nokia Networks | Jan.Kall@nsn.com | CP#65 exception in CP-140560. Dec.14: 20->100; WID: CP-140492-> CP-140800 | 29.163, 29.292 | 65 | 33 |  |  | Tue 29/07/14 | Tue 09/12/14
2458 | 670050 | UE Conformance Test Aspects - Codec for Enhanced Voice Services (EVS) | EVS_codec-UEConTest | 2 | Rel-12 | R5 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-150836 | RP-151164 | Ericsson |  | 03/07/15: Compl:0%->25% 03/07/15: WID: RP-150137->RP-150836 03/07/15: Stat Rep: ->RP-150831 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150831->RP-1511641/1/16: Compl:75%->95%1/1/16: CD:Tue 15/12/15->Tue 15/03/16; |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
2459 | 560040 | Coordination of Video Orientation | CVO | 1 | Rel-12 | S4,C4,C1,C3 | 2012-06-07 08:00 | 2013-12-06 17:00 | 100% | SP-120228 | - | Ericsson | frederic.gabin@ericsson.com | CP#62 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering | - | 56 | 29 |  |  | Thu 07/06/12 | Tue 19/11/13
2460 | 560140 | SA4 part of Coordination of Video Orientation | CVO-SA4 | 2 | Rel-12 | S4 | 2012-06-07 08:00 | 2013-03-06 17:00 | 100% | SP-120228 | - | Ericsson | frederic.gabin@ericsson.com | SP#59 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering | 26.114, 26.141, 26.234, 26.346 | 56 | 29 |  |  | Thu 07/06/12 | Sat 16/02/13
2461 | 600006 | CT aspects of Coordination of Video Orientation | CVO-CT | 2 | Rel-12 | C4,C1,C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | Complete CVO support (both, basic 2 bit orientation and additional option for extra 6 bit granularity) within CN protocols/procedures for IMS nodes, e.g. IMS ALG/AGW,IBCF/TrGW,MRFC/MRFP & add support of CVO-related SDP attributes to be negotiated by UE | Stage 2/3 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
2462 | 600106 | CT4 part of CT aspects of Coordination of Video Orientation | CVO-CT | 3 | Rel-12 | C4 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334 | 60 | 31 |  |  | Tue 28/05/13 | Wed 29/01/14
2463 | 600206 | CT1 part of CT aspects of Coordination of Video Orientation | CVO-CT | 3 | Rel-12 | C1 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 24.229 | 60 | 31 |  |  | Tue 28/05/13 | Mon 18/11/13
2464 | 600306 | CT3 part of CT aspects of Coordination of Video Orientation | CVO-CT | 3 | Rel-12 | C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130393 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 29.162, 29.163 | 60 | 31 |  |  | Tue 28/05/13 | Mon 18/11/13
2465 | 570033 | High Efficiency Video Coding | HEVC | 1 | Rel-12 | S4,IETF | 2012-09-12 08:00 | 2014-12-05 17:00 | 100% | SP-130569 | - | Qualcomm | Ye-Kui Wang (yekuiw@qti.qualcomm.com) | Specify the support of HEVC in 3GPP services (PSS, DASH, MTSI, MMS, MBMS, IMS Messaging and Presence) | - | 57 | 29 |  |  | Thu 30/08/12 | Wed 16/04/14
2466 | 570133 | TR on Evaluation of High Efficiency Video Coding for 3GPP Services | HEVC-SA4TR | 2 | Rel-12 | S4 | 2012-09-12 08:00 | 2014-06-19 08:00 | 100% | SP-130569 | - | Qualcomm | Ye-Kui Wang (yekuiw@qti.qualcomm.com) | SP#64 completed. TR 26.906v200 for Approval | New TR 26.906 | 57 | 29 |  |  | Thu 30/08/12 | Wed 16/04/14
2467 | 570233 | High Efficiency Video Coding in 3GPP services PSS, MBMS, DASH, MMS, MTSI, IMS Messaging and Presence | HEVC-SA4 | 2 | Rel-12 | S4 | 2012-09-17 08:00 | 2014-06-18 17:00 | 100% | SP-130569 | - | Qualcomm | Ye-Kui Wang (yekuiw@qti.qualcomm.com) | SP#64 completed | 26.114, 26.140, 26.141, 26.234, 26.244, 26.247, 26.346 | 57 | 29 |  |  | Thu 30/08/12 | Wed 16/04/14
2468 | 631002 | (IETF) High Efficiency Video Coding | HEVC-SA4IETF | 2 | Rel-12 | S4-IETF | 2012-09-17 08:00 | 2014-12-05 17:00 | 100% | SP-130569 | - | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | Submitted to IESG for publication. 7/10/15: Rapporteur added; 7/3/16: 50%->95; 13/6/16: 95%->100 | draft-ietf-payload-rtp-h265=>RFC7798 | 63 | 32 |  |  | Mon 10/02/14 | Mon 13/06/16
2469 | 580065 | Mobile stereoscopic 3D services extensions | M3DV_Ext | 1 | Rel-12 | S4 | 2012-12-12 08:00 | 2013-09-11 17:00 | 100% | SP-120768 | - | Huawei | lukasz.kondrad@huawei.com | SP#61 completed. Related to Rel-11 Study On Mobile 3D Video Coding (FS_M3DVC) TR 26.905 and Rel-11 Mobile 3D Video Coding (M3DVC) | 26.114, 26.245, 26.247, 26.430 | 58 | 30 |  |  | Mon 12/11/12 | Wed 24/07/13
2470 | 580066 | IMS-based Streaming and Download Delivery Enhancements | IMS_SDE | 1 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-03-07 17:00 | 100% | SP-120767 | - | Intel | ozgur.oyman@intel.com | Provide an extension of IMS based PSS and MBMS user services | - | 58 | 30 |  |  | Mon 12/11/12 | Fri 19/04/13
2471 | 580166 | TR on IMS-based Streaming and Download Delivery Enhancements | IMS_SDE-SA4TR | 2 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-03-07 17:00 | 100% | SP-120767 | - | Intel | ozgur.oyman@intel.com | SP#63 completed. Identify use cases and requirements based on Rel-10/11 PSS and MBMS functionality to be addressed for IMS-based streaming and download enhancements | new TR 26.827 | 58 | 30 |  |  | Mon 12/11/12 | Wed 29/01/14
2472 | 580266 | Specification on IMS-based Streaming and Download Delivery Enhancements | IMS_SDE-SA4 | 2 | Rel-12 | S4 | 2012-12-13 08:00 | 2014-03-07 17:00 | 100% | SP-120767 | - | Intel | ozgur.oyman@intel.com | SP#63 completed. Develop procedures towards enabling the IMS-based extensions of the identified use casES in CP-150TS 26.237. Refine existing MBMS download procedures to enable IMS-based MBMS file repair with the use of conventional HTTP web servers. | 26.237 | 58 | 30 |  |  | Mon 12/11/12 | Wed 29/01/14
2473 | 580067 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE | ART_LTE | 1 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-12-12 17:00 | 100% | SP-120769 | - | Qualcomm | Andre Schevciw (aschevci@qualcomm.com) | Triggered by Rel-12 Feature Codec for Enhanced Voice Services (EVS_codec) UID_470030. Need for super wideband acoustic requirements and test methods | Stage 3 | 58 | 30 |  |  | Mon 12/11/12 | Fri 19/04/13
2474 | 580167 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - NarrowBand and WideBand aspects | ART_LTE-NBWB | 2 | Rel-12 | S4 | 2012-12-12 08:00 | 2013-12-11 17:00 | 100% | SP-120771 | - | Sony Mobile Communications | Peter.Isberg@sony.com | SP#62 completed | 26.131, 26.132 | 58 | 30 |  |  | Mon 12/11/12 | Mon 18/11/13
2475 | 580267 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - UE Delay aspects | ART_LTE-UED | 2 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-09-17 17:00 | 100% | SP-120770 | - | AT&T, Orange | luisa.marchetto@att.com, stephane.ragot@orange.com | SP#65 completed | 26.131, 26.132 | 58 | 30 |  |  | Mon 12/11/12 | Wed 13/08/14
2476 | 580367 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - Super wideband and fullband aspects | ART_LTE-SUPER | 2 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-12-12 17:00 | 100% | SP-120772 | SP-140470 | Sony Mobile Communications | peter.isberg@sonymobile.com | SP#65 completion 09/14=>12/14. Exception in SP-140470. Dec.14: 65->100 | 26.131, 26.132 | 58 | 30 |  |  | Mon 12/11/12 | Wed 03/12/14
2477 | 590043 | MBMS Improvements | MI | 1 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-12-12 17:00 | 100% | SP-130024 | SP-140471 | Ericsson | eric.turcotte@ericsson.com | Stage 3 based on existing Stage 2 in TS 23.246 MBMS Architecture and functional description |  | 59 | 30 |  |  | Wed 20/02/13 | Fri 05/09/14
2478 | 590343 | TR on Enhanced MBMS Operation | MI-EMOTR | 2 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-12-12 17:00 | 100% | SP-140212 | SP-140471 | Huawei | Zhiming Li (lizhiming@huawei.com) | SP#65 completion 09/14=>12/14. Exception in SP-140471. SP#63 TR 26.848v100 for Information. Dec.14: 85->100. | New TR 26.848 | 59 | 30 |  |  | Wed 20/02/13 | Thu 05/03/15
2479 | 590143 | Enhanced MBMS Operation | MI-EMO | 2 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-12-12 17:00 | 100% | SP-140212 | SP-140471 | Huawei | Zhiming Li (lizhiming@huawei.com) | SP#65 completion 09/14=>12/14. Exception in SP-140471. Dec.14: 85->100 | 26.247, 26.346 | 59 | 30 |  |  | Wed 20/02/13 | Thu 05/03/15
2480 | 590443 | TR on MBMS operation on Demand | MI-MooDTR | 2 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-12-12 17:00 | 100% | SP-130026 | SP-140471 | Qualcomm | Charles Lo (clo@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Exception in SP-140471. SP#63 TR 26.849v100 for Information. Dec.14: 75->100 | New TR 26.849 | 59 | 30 |  |  | Wed 20/02/13 | Thu 05/03/15
2481 | 590243 | MBMS operation on Demand | MI-MooD | 2 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-12-12 17:00 | 100% | SP-130026 | SP-140471 | Qualcomm | Charles Lo (clo@qti.qualcomm.com) | SP#65 completion 09/14=>12/14. Exception in SP-140471. Dec.14: 75->100 | 26.346 | 59 | 30 |  |  | Wed 20/02/13 | Thu 05/03/15
2482 | 590044 | End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI | 1 | Rel-12 | S4 | 2013-03-06 08:00 | 2015-09-14 17:00 | 100% | SP-140600 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 completed. Updated WID SP-130670=>SP-140594. Reduced Scope & Objectives. Moved work on new TR 26.924, etc. to Rel-13. Co-ordinate with CT1/3/4. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040 | 26.114 | 59 | 30 |  |  | Wed 20/02/13 | Tue 09/09/14
2483 | 670098 | S4 aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI | 2 | Rel-12 | S4 | 2013-03-06 08:00 | 2014-09-16 17:00 | 100% | SP-140600 | - | Ericsson | tomas.frankkila@ericsson.com | SP#65 completed. Updated WID SP-130670=>SP-140594. Reduced Scope & Objectives. Moved work on new TR 26.924, etc. to Rel-13. Co-ordinate with CT1/3/4. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040 | 26.114 | 59 | 30 |  |  | Wed 20/02/13 | Tue 09/09/14
2484 | 600007 | CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 2 | Rel-12 | C3,C1,C4 | 2013-06-21 08:00 | 2015-09-14 17:00 | 100% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | Stage 2/3. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100% | Stage 2/3 | 60 | 31 |  |  | Wed 20/02/13 | Tue 05/05/15
2485 | 600107 | CT3 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 3 | Rel-12 | C3 | 2013-06-21 08:00 | 2015-09-14 17:00 | 100% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | Dec.14: CD: 09/14->09/15. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100% | 29.162, 29.163, 29.213, 29.214 | 60 | 31 |  |  | Wed 29/05/13 | Tue 05/05/15
2486 | 600207 | CT1 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 3 | Rel-12 | C1 | 2013-06-21 08:00 | 2014-09-12 17:00 | 100% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | CP#64 completion 06/14=>09/14. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100% | 24.229 | 60 | 31 |  |  | Wed 29/05/13 | Tue 05/05/15
2487 | 600307 | CT4 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions | E2EMTSI-CT | 3 | Rel-12 | C4 | 2013-06-21 08:00 | 2014-09-12 17:00 | 100% | CP-130397 | - | Ericsson | susana.fernandez@ericsson.com | CP#64 completion 06/14=>09/14. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100% | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334 | 60 | 31 |  |  | Wed 29/05/13 | Tue 05/05/15
2488 | 620066 | Video Coding Enhancements in IMS Messaging and Presence | VCEIMP | 1 | Rel-12 | S4 | 2013-12-11 08:00 | 2014-03-07 17:00 | 100% | SP-130579 | - | Ericsson | frederic.gabin@ericsson.com | SP#63 completed. Linked to Rel-6 Media Codecs and Formats for IMS Messaging and Presence (PRESNC-COFIMP) UID_34025. Work item which gave rise to TS 26.141 | 26.141 | 62 | 32 |  |  | Fri 29/11/13 | Wed 29/01/14
2489 | 640057 | Video Telephony Robustness Improvements | VTRI | 1 | Rel-12 | S4 | 2014-06-18 08:00 | 2014-09-16 17:00 | 100% | SP-140218 | - | Qualcomm | Muhammed Coban (mcoban@qti.qualcomm.com) | SP#65 completed. Linked to E2EMTSI (End-to-End Multimedia Telephony Service for IMS extensions). Add Reqs&guidelines for video telephony robustness to improve service perf. for PLI, Generic NACK, and FIR messages within overall bitrate limit | 26.114 | 64 | 33 |  |  | Fri 06/06/14 | Wed 13/08/14
2490 | 560031 | Rel-12 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM12 | 1 | Rel-12 | S5 | 2011-09-21 08:00 | 2014-12-12 17:00 | 100% | - | - | - | - | OAM12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI | - | 56 | 29 |  |  | Wed 18/04/12 | Wed 18/04/12
2491 | 560131 | Rel-12 Self-Organizing Networks (SON) - OAM aspects | OAM12-SON | 2 | Rel-12 | S5 | 2011-09-21 08:00 | 2013-12-11 17:00 | 100% | - | - | - | - | OAM12-SON is an umbrella BB also for SON related TEI12 type of changes that are not part of any other dedicated feature/WI | - | 56 | 29 |  |  | Wed 18/04/12 | Mon 19/11/12
2492 | 560033 | Multi-vendor Plug and Play eNB connection to the network | SON-NM-MUPPET | 3 | Rel-12 | S5 | 2011-09-21 08:00 | 2013-12-11 17:00 | 100% | SP-120777 | - | NSN | anatoly.andrianov@nsn.com | SP#62 completed. TS 32.508v200 for Approval, TS 32.509v100 for 1-step Approval | 32.501, New TSs (32.508, 32.509) | 56 | 29 |  |  | Wed 18/04/12 | Wed 27/11/13
2493 | 560035 | Compliance of 3GPP SA5 specifications to the NGMN Next Generation Converged Operations Requirements (NGCOR) | OAM-NGMN_NGCOR | 2 | Rel-12 | S5 | 2012-06-20 08:00 | 2014-09-17 17:00 | 100% | SP-140321 | - | Huawei | christian.toche@huawei.com | SP#65 moved to Rel-13 OAM-PMID (Converged management Performance Management Interface Definition) UID_560235 | - | 56 | 29 |  |  | Mon 14/05/12 | Mon 25/08/14
2494 | 560135 | Converged Management Model Alignment (Phase 2) | OAM-MODAL | 3 | Rel-12 | S5 | 2012-06-20 08:00 | 2014-09-17 17:00 | 100% | SP-140322 | - | NSN | olaf.pollakowski@nsn.com | SP#65 completed. TR 28.280v100 for 1-step Approval | 32.156, new TR 28.820 | 56 | 29 |  |  | Mon 14/05/12 | Mon 25/08/14
2495 | 560335 | 3GPP Fault Management Solution Profile for NGMN NGCOR | OAM-FMSP | 3 | Rel-12 | S5 | 2012-06-20 08:00 | 2013-06-19 17:00 | 100% | SP-120778 | - | Ericsson | thomas.tovinger@ericsson.com | SP#60 completed. TS 28.390v200 for Approval | new TS 28.390 | 56 | 29 |  |  | Wed 23/05/12 | Thu 13/06/13
2496 | 530050 | Network Management for 3GPP Interworking WLAN | OAM-IWLAN | 2 | Rel-12 | S5 | 2011-09-21 08:00 | 2014-09-17 17:00 | 100% | SP-140542 | - | China Mobile | Chengang@chinamobile.com, lijian@chinamobile.com | SP#65 updated WID SP-120779=>SP-140542 (removed parts on CN and non-3GPP access). Discontinue I-WLAN spec. | - | 53 | 27 |  |  | Sat 27/08/11 | Wed 10/09/14
2497 | 530150 | Performance measurements part Network Management for 3GPP Interworking WLAN | OAM-IWLAN-SA5P | 3 | Rel-12 | S5 | 2011-09-22 08:00 | 2014-09-17 17:00 | 100% | SP-140542 | - | China Mobile | Chengang@chinamobile.com, lijian@chinamobile.com | SP#65 completed. TS 28.402v100 for 1-step Approval, withdraw New TS 28.401 (CN and non-3GPP access i/w PMs). Moved PMs for EPC and non-3GPP access i/w from 28.401=>28.402 | new TS 28.401, withdrawn new TS 28.402 | 53 | 27 |  |  | Sat 27/08/11 | Wed 10/09/14
2498 | 530250 | NIM part Network Management for 3GPP Interworking WLAN | OAM-IWLAN-SA5NM | 3 | Rel-12 | S5 | 2011-09-21 08:00 | 2013-12-11 17:00 | 100% | SP-140542 | - | China Mobile | Chengang@chinamobile.com, lijian@chinamobile.com | SP#65 discontinue I-WLAN specs: Move parts (e.g. IOCs) applicable for EPC and non-3GPP access interworking NRMs from 28.601/2/6 to 28.611/2/6. Withdraw 28.601/2/6 (CN and non-3GPP access i/w NRMs). SP#62 completed. TSs 28.601/2/6/11/12/16 for Approval | 32.632, 32.636, 32.752, 32.756, new TS (28.611, 28.612, 28.616, withdrawn 28.601, 28.602, 28.606) | 53 | 27 |  |  | Sat 27/08/11 | Wed 10/09/14
2499 | 580053 | Rel-12 Network Infrastructure Management | OAM12-NIM | 2 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-12-12 17:00 | 100% | - | - | - | - | - | - | 58 | 30 |  |  | Thu 15/11/12 | Mon 19/11/12
2500 | 620056 | Alarm quality improvements | OAM-AMI-SA5 | 3 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-12-12 17:00 | 100% | SP-130611 | SP-140544 | TeliaSonera | tommy.berggren@teliasonera.com | SP#65 completion 09/14=>12/14. Exception in SP-140544. Triggered by Rel-12 TR 32.859 Study on Alarm Management (FS_OAM_AM) . Dec.14: 50->100 | 32.111-1, 32.111-2, 32.111-6 | 62 | 32 |  |  | Thu 28/11/13 | Thu 04/12/14
2501 | 630012 | Radio Planning Tool (RPT) interface | OAM-RPTi-SA5 | 3 | Rel-12 | S5 | 2014-03-07 08:00 | 2014-12-12 17:00 | 100% | SP-140026 | SP-140546 | Nokia Networks | olaf.pollakowski@nsn.com | SP#65 completion 09/14=>12/14. Exception in SP-140546. SP#65 v100 TS 28.667/8 for Information. Dec.14: 60->100 | 32.101, New TSs (28.667, 28.668, 28.669) | 63 | 32 |  |  | Thu 27/02/14 | Thu 04/12/14
2502 | 580054 | Deleted - Rel-12 Performance Management | OAM12-PM | 2 | Rel-12 | S5 | 2013-06-21 08:00 | 2014-09-16 17:00 | 100% | - | - | - | - | OAM12-PM is an umbrella BB also for PM related TEI12 type of changes that are not part of any other dedicated feature/WI | - | 58 | 30 | SP-69 |  | Thu 15/11/12 | Tue 19/08/14
2503 | 620057 | OAM aspects of Network Sharing | OAM-SHARE | 2 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-12-12 17:00 | 100% | SP-130607 | SP-140545 | Orange | jeanmichel.cornily@orange.com | SP#65 completion 09/14=>12/14. Exception in SP-140545. Triggered by Rel-12 TR 32.851 Study on OAM aspects of Network Sharing (FS_OAM_SHARE), Rel-6 Network Sharing (NTShar) UID_31018 | Stage 1/2/3 | 62 | 32 |  |  | Thu 28/11/13 | Wed 10/09/14
2504 | 620157 | OAM aspects of Network Sharing - Concepts and high-level requirements | OAM-SHARE-SA5c | 3 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-12-12 17:00 | 100% | SP-130607 | SP-140545 | Orange | jeanmichel.cornily@orange.com | SP#65 completion 09/14=>12/14. Exception in SP-140545. LM 80->100 | new TS 32.130 | 62 | 32 |  |  | Thu 28/11/13 | Thu 04/12/14
2505 | 620257 | OAM aspects of Network Sharing - Impacts on existing specifications | OAM-SHARE-SA5imp | 3 | Rel-12 | S5 | 2013-12-12 08:00 | 2014-12-12 17:00 | 100% | SP-130607 | SP-140545 | Orange | jeanmichel.cornily@orange.com | SP#65 completion 09/14=>12/14. Exception in SP-140545. Dec.14: 60->100 | 28.401,28.621/2/3,28.651/2/3,28.654/5/6,28.657/8/9,28.701/2/3,28.731/2/3,28.734/5/6,32.101/2,32.111-1/2/3/6,32.121/2/6,32.155,32.171/2/6,32.300/1/2/6,32.311/2/6,32.321/2/6,32.331/2/6,32.341/2/6,32.351/352/6,32.361/2/6,32.381/2/6,32.405/6/7/8/9/10/11/12/41 | 62 | 32 |  |  | Thu 28/11/13 | Thu 04/12/14
2506 | 570037 | Rel-12 Charging | CH12 | 1 | Rel-12 | S5 | 2012-12-12 08:00 | 2014-06-18 17:00 | 100% | - | - | - | - | CH12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI | - | 57 | 29 |  |  | Wed 19/09/12 | Wed 19/09/12
2507 | 580051 | Short Message Service - Service Center (SMS-SC) Offline Charging | SMS-SC-CH | 2 | Rel-12 | S5 | 2012-12-12 08:00 | 2014-03-10 08:00 | 100% | SP-140027 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Stage 2/3. SP#63 completed. Updated WID SP-120775=>SP-140027 | 32.240, 32.274, 32.297, 32.298, 32.299 | 58 | 30 |  |  | Tue 20/11/12 | Thu 27/02/14
2508 | 610041 | Charging per IP - Connectivity Access Network (IP-CAN) Session (Stage 2/3) | CHIPS | 2 | Rel-12 | S5 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130642 | - | Ericsson | david.shrader@ericsson.com | SP#64 completed. 12/15: Acronym reverted back from CHIPCAN to CHIPS | 32.251, 32.298, 32.299 | 61 | 31 |  |  | Wed 04/09/13 | Mon 07/12/15
2509 | 610042 | Charging using an Alternative Roaming Provider (Stage 2/3) | CHARP | 2 | Rel-12 | S5 | 2013-09-12 08:00 | 2014-06-18 17:00 | 100% | SP-130428 | - | Ericsson | david.shrader@ericsson.com | SP#64 completed. TS 32.276v200 for Approval, 32.293v100 for 1-step Approval | 32.240, 32.299, New TSs [32.276 (Voice Call Service Charging), 32.293 (Proxy Function)] | 61 | 31 |  |  | Wed 04/09/13 | Tue 10/06/14
2510 | 620058 | Charging for IMS centralized service (ICS) control (Stage 2/3) | CHICS | 2 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-06-18 17:00 | 100% | SP-130610 | - | NSN | Gerald.Goermer@nsn.com | SP#64 completed. Align SA5 Charging specifications with Rel-8 Feature IMS Centralized Service control (ICSRA) and subsequent enhancements under TEIx (SA2 23.292 ICSRA Stage 2, CT3 29.292, CT1 24.607, 24.611) | 32.250, 32.298 | 62 | 32 |  |  | Fri 06/12/13 | Tue 10/06/14
2511 | 530018 | IMS Emergency PSAP Callback (Stage 3) | EMC_PC | 1 | Rel-12 | C1,C3,IETF | 2011-09-21 08:00 | 2014-06-13 17:00 | 100% | CP-130218 | - | Ericsson | christer.holmberg@ericsson.com | Dep. IETF ECRIT on PSAP call back. Fulfill SA1/2 Rel-7 EMC1 reqs UID_32045 PS domain and IMS impacts for supporting IMS Emergency calls (related to BB UID_1653 Emergency Call Enhancements for IP& PS Based Calls | Stage 3 | 53 | 27 |  |  | Sat 27/08/11 | Mon 18/11/13
2512 | 530118 | CT1 part of IMS Emergency PSAP Callback | EMC_PC | 2 | Rel-12 | C1 | 2011-09-22 08:00 | 2014-06-13 17:00 | 100% | CP-130218 | - | Ericsson | christer.holmberg@ericsson.com | CP#64 completed. 2/4/15: acronym changed to EMC_PC | 24.229, tied to completion of IETF dependencies: 24.604, 24.605, 24.610, 24.611, 24.629 | 53 | 27 |  |  | Sat 27/08/11 | Thu 02/04/15
2513 | 531004 | (IETF) CT1 part of IMS Emergency PSAP Callback (RFC 7090) | EMC_PC | 2 | Rel-12 | C1-IETF | 2011-09-21 08:00 | 2014-06-13 17:00 | 100% | CP-130218 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#64 completed. 2/4/15: acronym changed to EMC_PC | RFC 7090 (was draft-ietf-ecrit-psap-callback | 53 | 27 |  |  | Sun 28/08/11 | Thu 02/04/15
2514 | 530218 | CT3 part of IMS Emergency PSAP Callback | EMC_PC | 2 | Rel-12 | C3 | 2011-09-24 08:00 | 2013-09-06 17:00 | 100% | CP-130218 | - | Ericsson | christer.holmberg@ericsson.com | CP#61 completed. 2/4/15: acronym changed to EMC_PC | 29.163, 29.165 | 53 | 27 |  |  | Sat 27/08/11 | Thu 02/04/15
2515 | 601001 | (IETF) CT3 part of IMS Emergency PSAP Callback (RFC 7090) | EMC_PC | 2 | Rel-12 | C3-IETF | 2011-09-21 08:00 | 2014-06-13 17:00 | 100% | CP-130218 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#64 completed. 2/4/15: acronym changed to EMC_PC | RFC 7090 (was draft-ietf-ecrit-psap-callback) | 60 | 31 |  |  | Mon 10/06/13 | Thu 02/04/15
2516 | 570008 | Interworking between a PLMN with WLAN to access the EPC and a PDN (Stage 3) | SAES_WLAN_EPC_intwk | 1 | Rel-12 | C3 | 2012-09-10 08:00 | 2013-09-06 17:00 | 100% | CP-130395 | - | Huawei | Christian.Herrero@huawei.com | CP#61 completed. Linked to Rel-8 Feature SAES in CP-150System Architecture Evolution specification - Evolved Packet System (non RAN aspects) UID_320005 | 29.061 | 57 | 29 |  |  | Mon 13/08/12 | Mon 12/08/13
2517 | 580009 | Reporting Enhancements in Warning Message Delivery (Stage 2/3) | REP_WMD | 1 | Rel-12 | C1,C4,R3 | 2012-12-07 08:00 | 2014-06-13 17:00 | 100% | CP-130480 | - | one2many | peter.sanders@one2many.eu | Stage 1 for Cell Broadcast does not exist. This WID enhances the reporting capabilities of Warning Message Delivery. Introduce LTE functionality requested by regulators, equivalent to existing 2G/3G functionality. | Stage 2/3 | 58 | 30 |  |  | Mon 19/11/12 | Wed 04/09/13
2518 | 580010 | CT1 part of Reporting Enhancements in Warning Message Delivery (Stage 2) | REP_WMD-CT1 | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-03-04 17:00 | 100% | CP-130480 | - | one2many | peter.sanders@one2many.eu | CP#63 completed | 23.041 | 58 | 30 |  |  | Mon 19/11/12 | Mon 03/03/14
2519 | 580011 | CT4 part of Reporting Enhancements in Warning Message Delivery (Stage 2/3) | REP_WMD-CT4 | 2 | Rel-12 | C4 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | CP-130480 | - | one2many | peter.sanders@one2many.eu | CP#64 completed | 23.007, 29.168 | 58 | 30 |  |  | Mon 19/11/12 | Sun 25/05/14
2520 | 590021 | Public Warning System - Reset/Failure/Restart in Warning Message Delivery in LTE | REP_WMD-RFR_PWS | 2 | Rel-12 | R3 | 2013-03-04 08:00 | 2014-06-13 17:00 | 100% | RP-130398 | - | one2many, Huawei | peter.sanders@one2many.eu, Dai Mingzeng (daimingzeng@huawei.com) | - | LTE | 59 | 30 |  |  | Tue 26/02/13 | Fri 01/03/13
2521 | 590121 | Core part: PWS - Reset/Failure/Restart in Warning Message Delivery in LTE | REP_WMD-RFR_PWS-Core | 3 | Rel-12 | R3 | 2013-03-04 08:00 | 2014-06-13 17:00 | 100% | RP-130398 | RP-140637 | one2many, Huawei | peter.sanders@one2many.eu, Dai Mingzeng (daimingzeng@huawei.com) | RP#64 completed | 36.413 | 59 | 30 |  |  | Tue 26/02/13 | Tue 04/03/14
2522 | 580012 | Single Radio Voice Call Continuity (SRVCC) before ringing (Stage 3) | bSRVCC | 1 | Rel-12 | C1,C3,R5 | 2012-12-07 08:00 | 2014-03-06 17:00 | 100% | CP-130219 | - | NTT DOCOMO | keisuke.sasada.kx@nttdocomo.com | Linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056. TS 23.237 Rel-12 CR#0444 under TEI12 | GERAN, UTRA, LTE | 58 | 30 |  |  | Mon 19/11/12 | Mon 10/06/13
2523 | 580112 | CT1 part of Single Radio Voice Call Continuity (SRVCC) before ringing | bSRVCC | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2013-06-14 17:00 | 100% | CP-130219 | - | NTT DOCOMO | keisuke.sasada.kx@nttdocomo.com | CP#60 completed. 2/4/15: acronym changed to bSRVCC | 24.008, 24.237 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
2524 | 600008 | CT3 part of Single Radio Voice Call Continuity (SRVCC) before ringing | bSRVCC | 2 | Rel-12 | C3 | 2013-06-12 08:00 | 2013-06-14 17:00 | 100% | CP-130219 | - | NTT DOCOMO | keisuke.sasada.kx@nttdocomo.com | CP#60 completedbSRVCC | 29.165 | 60 | 31 |  |  | Tue 28/05/13 | Thu 02/04/15
2525 | 620017 | Test part: Single Radio Voice Call Continuity (SRVCC) before ringing | bSRVCC-UEConTest | 2 | Rel-12 | R5 | 2013-12-06 08:00 | 2014-03-06 17:00 | 100% | RP-131919 | RP-140422 | NTT DOCOMO | Masahiro.Tamaoki.eu@nttdocomo.com | RP#63 completed. Testing for CT1 TS 24.237 (IMS service continuity Stage 3) | 34.229-1, 34.229-2, 36.523-1, 36.523-2 | 62 | 32 |  |  | Mon 25/11/13 | Sat 14/12/13
2526 | 580013 | IMS Stage 3 IETF Protocol Alignment - phase 6 | IMSProtoc6 | 1 | Rel-12 | C1,C3,IETF | 2012-12-07 08:00 | 2014-12-09 17:00 | 97% | CP-120905 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | - | Stage 3 | 58 | 30 |  |  | Mon 19/11/12 | Thu 06/12/12
2527 | 580014 | CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 | IMSProtoc6 | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-11 17:00 | 100% | CP-120905 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#65 completed. 4/2/15: acronym changed to IMSProtoc6 | 23.218, 24.229, 24.930 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
2528 | 601002 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-holmberg-sipcore-received-realm) | IMSProtoc6 | 2 | Rel-12 | C1-IETF | 2013-05-21 08:00 | 2014-12-09 17:00 | 100% | CP-120905 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6; 21/3/17: 50%->100 | draft-holmberg-sipcore-received-realm | 60 | 31 |  |  | Mon 10/06/13 | Tue 21/03/17
2529 | 651002 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-jesske-sipcore-sip-tree-cap-indicators) | IMSProtoc6 | 2 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-05 17:00 | 25% | CP-120905 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6 | draft-allen-sipcore-sip-tree-cap-indicators | 65 | 33 |  |  | Tue 02/09/14 | Thu 02/04/15
2530 | 660038 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-ietf-insipid-session-id) | IMSProtoc6 | 2 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 100% | CP-120905 |  | christer.holmberg@ericsson.com |  | work in progress. 4/2/15: acronym changed to IMSProtoc6; 21/3/17: 25%->100 | draft-ietf-insipid-session-id | 65 | 34 |  |  | Thu 04/12/14 | Tue 21/03/17
2531 | 580015 | CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 | IMSProtoc6 | 2 | Rel-12 | C3 | 2014-06-06 08:00 | 2014-09-11 17:00 | 100% | CP-120905 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#65 completed. 4/2/15: acronym changed to IMSProtoc6 | 29.163, 29.165 | 58 | 30 |  |  | Mon 19/11/12 | Thu 02/04/15
2532 | 611001 | (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-holmberg-sipcore-received-realm) | IMSProtoc6 | 2 | Rel-12 | C3-IETF | 2013-09-06 08:00 | 2014-12-05 17:00 | 100% | CP-120905 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6; 21/3/17: 50%->100 | draft-holmberg-sipcore-received-realm | 61 | 31 |  |  | Fri 23/08/13 | Tue 21/03/17
2533 | 580016 | SAE Protocol Development - Phase 3 | SAES3 | 1 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-11 17:00 | 100% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005 | Stage 2/3 | 58 | 30 |  |  | Mon 19/11/12 | Sat 16/02/13
2534 | 580017 | SAE Protocol Development (Stage 3) - Phase 3 | SAES3-CT1 | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-11 17:00 | 100% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | CP#65 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 58 | 30 |  |  | Tue 20/11/12 | Mon 26/05/14
2535 | 580018 | CS Fallback in EPS - Phase 3 | SAES3-CSFB | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-11 17:00 | 100% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | CP#65 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 58 | 30 |  |  | Tue 20/11/12 | Mon 26/05/14
2536 | 580019 | SAE for support for non-3GPP accesses - Phase 3 | SAES3-non3GPP | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2014-09-11 17:00 | 100% | CP-120704 | - | InterDigital | behrouz.aghili@interdigital.com | CP#65 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 58 | 30 |  |  | Tue 20/11/12 | Mon 26/05/14
2537 | 580020 | IM-SSF Application Server Service Data Descriptions (Stage 2/3) | IMS_SSFDD | 1 | Rel-12 | C4,C1 | 2012-12-07 08:00 | 2013-06-14 17:00 | 100% | CP-120756 | - | Huawei | susan.shishufeng@huawei.com | CP#60 completed | Stage 2/3 | 58 | 30 |  |  | Mon 19/11/12 | Wed 29/05/13
2538 | 580021 | Stage 2 for IM-SSF Application Server Service Data Descriptions | IMS_SSFDD | 2 | Rel-12 | C1 | 2012-12-07 08:00 | 2013-03-01 17:00 | 100% | CP-120756 | - | Huawei | susan.shishufeng@huawei.com | CP#59 completed | 23.218 | 58 | 30 |  |  | Mon 19/11/12 | Sat 16/02/13
2539 | 580022 | Stage 3 for IM-SSF Application Server Service Data Descriptions | IMS_SSFDD | 2 | Rel-12 | C4 | 2012-12-10 08:00 | 2013-06-14 17:00 | 100% | CP-120756 | - | Huawei | susan.shishufeng@huawei.com | CP#60 completed | 29.328, 29.329, 29.364 | 58 | 30 |  |  | Mon 19/11/12 | Wed 29/05/13
2540 | 580023 | Diameter based interface between SGSN and SMS central functions (Stage 2/3) | Dia_SGSN_SMS | 1 | Rel-12 | C4,C1 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | CP-130437 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#62 completed | Stage 2/3 | 58 | 30 |  |  | Tue 20/11/12 | Mon 18/11/13
2541 | 590015 | Stage 2 for Diameter based interface between SGSN and SMS central functions | Dia_SGSN_SMS | 2 | Rel-12 | C1 | 2013-03-07 08:00 | 2013-12-06 17:00 | 100% | CP-130437 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#62 completed | 23.040 | 59 | 30 |  |  | Sat 16/02/13 | Mon 18/11/13
2542 | 580123 | Stage 3 for Diameter based interface between SGSN and SMS central functions | Dia_SGSN_SMS | 2 | Rel-12 | C4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | CP-130437 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#62 completed | 29.002, 29.230, 29.272, 29.305, 29.336, 29.337, 29.338 | 58 | 30 |  |  | Tue 20/11/12 | Mon 18/11/13
2543 | 580024 | Diameter based interface between SGSN-GMLC (Stage 3) | Dia_SGSN_GMLC | 1 | Rel-12 | C4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | CP-130598 | - | Cisco | Nirav Salot (nsalot@cisco.com) | CP#62 completed. Updated WID CP-130273=>CP-130598. No Stage 2 impact. Define a Diameter variant for the protocol used over existing reference points between SGSN and GMLC for LCS (replace the use of MAP by Diameter protocol) | 29.002, 29.172, 29.173, 29.230, 29.272 | 58 | 30 |  |  | Tue 20/11/12 | Mon 18/11/13
2544 | 590009 | IMS impacts on UICC Application Aspects (Stage 3) | IMS_UApAs | 1 | Rel-12 | C6 | 2013-03-04 08:00 | 2014-12-09 17:00 | 100% | CP-130169 | CP-140696 | Giesecke & Devrient | sergi.espi@gi-de.com | CP#65 completion 09/14=>12/14. Exception in CP-140696. Dec.14: 85->100% | 31.102, 31.103, 31.111, 31.130 | 59 | 30 |  |  | Wed 20/02/13 | Wed 03/12/14
2545 | 590012 | eMBMS restoration procedures | eMBMS_Rest | 1 | Rel-12 | C4,C3 | 2013-03-01 08:00 | 2014-09-11 17:00 | 100% | CP-140271 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#62 completed. Linked to Rel-9 MBMS support in EPS (MBMS_EPS). Rel-10 CT Features EPC Node Restoration with/out Idle mode Signalling Reduction (ISR) activated (EPC_NR/EPC_NR_ISR) | Stage 3 | 59 | 30 |  |  | Thu 07/03/13 | Mon 18/11/13
2546 | 590112 | CT4 part of eMBMS restoration procedures | eMBMS_Rest | 2 | Rel-12 | C4 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | CP-140271 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#62 completed | 23.007, 23.008, 29.274 | 59 | 30 |  |  | Thu 07/03/13 | Mon 18/11/13
2547 | 610006 | CT3 part of eMBMS restoration procedures | eMBMS_Rest | 2 | Rel-12 | C3 | 2013-09-04 08:00 | 2014-09-11 17:00 | 100% | CP-140271 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#65 completed | 29.061 | 61 | 31 |  |  | Thu 07/03/13 | Fri 01/08/14
2548 | 590014 | Dual Radio VCC enhancements (Stage 2/3) | eDRVCC | 1 | Rel-12 | C1,C3.S2 | 2012-09-19 08:00 | 2013-12-06 17:00 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#62 completed. Stage 2 in Rel-12 TEI12 TS 23.237 CR#0431, CR#0440, CR#0441, CR#0453 (pre-alerting). Stage 3 linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056 (Stage 2 in TS 23.237). 2/4/15: acronym changed to eDRVCC | Stage 2/3 | 59 | 30 |  |  | Sat 16/02/13 | Mon 18/11/13
2549 | 590114 | Stage 2 for Dual Radio VCC enhancements | eDRVCC | 2 | Rel-12 | S2 | 2012-09-19 08:00 | 2013-03-01 17:00 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | Stage 2 in Rel-12 TEI12 TS 23.237 CR#0431, CR#0440, CR#0441, CR#0453 (pre-alerting). 2/4/15: acronym changed to eDRVCC | 23.237 | 59 | 30 |  |  | Sat 16/02/13 | Thu 02/04/15
2550 | 590214 | Stage 3 for Dual Radio VCC enhancements | eDRVCC | 2 | Rel-12 | C1,C3 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#62 completed | Stage 3 | 59 | 30 |  |  | Tue 19/02/13 | Mon 18/11/13
2551 | 590314 | CT1 part of Stage 3 for Dual Radio VCC enhancements | eDRVCC | 3 | Rel-12 | C1 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#62 completed. 2/4/15: acronym changed to eDRVCC | 24.237, 24.292 | 59 | 30 |  |  | Sat 16/02/13 | Thu 02/04/15
2552 | 590414 | CT3 part of Stage 3 for Dual Radio VCC enhancements | eDRVCC | 3 | Rel-12 | C3 | 2013-03-01 08:00 | 2013-09-06 17:00 | 100% | CP-130091 | - | Ericsson | Jan.Holm@ericsson.com | CP#61 completed. 2/4/15: acronym changed to eDRVCC | 29.165 | 59 | 30 |  |  | Sat 16/02/13 | Thu 02/04/15
2553 | 600009 | CT aspects of Signalling of Image Size (Stage 2/3) | SIS_CT | 1 | Rel-12 | C4,C1,C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed. SA4 Rel-8 MTSI Video: Dynamic Rate Adaptation/Signalling of Image Size UID_34041 has included service aspects to support image attribute (a=imageattr) in TS 26.114 as in RFC 6236. But associated CN aspects were not included | Stage 2/3 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
2554 | 600109 | CT4 part of Signalling of Image Size | SIS_CT | 2 | Rel-12 | C4 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 23.333, 23.334, 29.238, 29.332, 29.333, 29.334 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
2555 | 600209 | CT1 part of CT Aspects of Signalling of Image Size | SIS_CT | 2 | Rel-12 | C1 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 24.229 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
2556 | 600309 | CT3 part of CT Aspects of Signalling of Image Size | SIS_CT | 2 | Rel-12 | C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130394 | - | Ericsson | nevenka.biondic@ericsson.com | CP#62 completed | 29.162, 29.163 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
2557 | 600010 | IMS Centralized Services (ICS) InterWorking Enhancement in Mobile Switching Center Server (MSC-S) | ICS_IWE | 1 | Rel-12 | C3 | 2013-06-14 08:00 | 2013-12-06 17:00 | 100% | CP-130352 | - | Orange | marianne.mohali@orange.com | CP#62 completed. Stage 3 enhancement interworking between IMS and MSC-S for IMS Centralized Services (ICS) | 29.292 | 60 | 31 |  |  | Tue 28/05/13 | Tue 19/11/13
2558 | 610002 | GPRS Tunnelling Protocol for the Control plane (GTP-C) Overload Control Mechanisms | GOCMe | 1 | Rel-12 | C4 | 2013-09-06 08:00 | 2014-09-11 17:00 | 100% | CP-140488 | - | Cisco | Nirav Salot (nsalot@cisco.com) | CP#65 completed. Updated WID CP-130433=>CP-140488 | 23.008, 29.230, 29.273, 29.274, 29.303, New TR 29.807 | 61 | 31 |  |  | Sat 10/08/13 | Mon 28/07/14
2559 | 610004 | Proxy Call Session Control Function (P-CSCF) restoration enhancements (Stage 2/3) | PCSCF_RES | 1 | Rel-12 | C4,C3,C1 | 2013-04-03 16:12 | 2014-12-09 17:00 | 100% | CP-140490 | - | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 updated WID CP-140443=>CP-140490. Based TR 29.806, solutions B and D are selected for standardization. Dec.14: 95->100 | Stage 2/3 | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
2560 | 610104 | TR on Proxy Call Session Control Function (P-CSCF) restoration enhancements | PCSCF_RES | 2 | Rel-12 | C4 | 2013-09-06 08:00 | 2014-09-11 17:00 | 100% | CP-140490 | - | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 completed. TR 29.806v200 for Approval | New TR 29.806 | 61 | 31 |  |  | Sat 10/08/13 | Sat 06/09/14
2561 | 640999 | Common for HSS & PCRF solutions | PCSCF_RES | 2 | Rel-12 | C4,C3,C1 | 2013-04-03 16:12 | 2014-12-09 17:00 | 100% | CP-140490 | - | Ericsson | maria.cruz.bartolome@ericsson.com | - | - | 64 | 33 |  |  | Tue 29/07/14 | Tue 29/07/14
2562 | 610204 | CT4 part of Common for HSS & PCRF solutions | PCSCF_RES | 3 | Rel-12 | C4 | 2013-09-06 08:00 | 2014-12-09 17:00 | 100% | CP-140490 | CP-140481 | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 completion 09/14=>12/14. Exception in CP-140481. Dec.14: 90->100 | 23.380, 29.060, 29.274 | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
2563 | 640014 | CT1 part of Common for HSS & PCRF solutions | PCSCF_RES | 3 | Rel-12 | C1 | 2013-04-03 16:12 | 2014-12-05 17:00 | 100% | CP-140490 | - | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 completed | 24.008 | 64 | 33 |  |  | Sat 10/08/13 | Sat 06/09/14
2564 | 650002 | CT3 part of Common for HSS & PCRF solutions | PCSCF_RES | 3 | Rel-12 | C3 | 2013-05-03 16:12 | 2014-12-09 17:00 | 100% | CP-140490 | CP-140687 | Huawei | susan.shishufeng@huawei.com | CP#65 updated WID CP-140443=>CP-140490 (added CT3 part). Exception in CP-140687 | 29.061, 29.165 | 65 | 33 |  |  | Sat 10/08/13 | Tue 03/06/14
2565 | 640998 | HSS based solution | PCSCF_RES | 2 | Rel-12 | C4,C1 | 2013-04-03 16:12 | 2014-12-09 17:00 | 100% | CP-140490 | - | Ericsson | maria.cruz.bartolome@ericsson.com | - | - | 64 | 33 |  |  | Tue 29/07/14 | Tue 29/07/14
2566 | 610210 | CT4 part of HSS based solution | PCSCF_RES | 3 | Rel-12 | C4 | 2013-09-06 08:00 | 2014-12-09 17:00 | 100% | CP-140490 | CP-140481 | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 completion 09/14=>12/14. Exception in CP-140481. Dec.14: 90->100 | 29.002, 29.228, 29.229, 29.272, 29.305 | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
2567 | 640114 | CT1 part of HSS based solution | PCSCF_RES | 3 | Rel-12 | C1 | 2013-04-03 16:12 | 2014-12-09 17:00 | 100% | CP-140490 | CP-140605 | Ericsson | maria.cruz.bartolome@ericsson.com | CP#65 completion 09/14=>12/14. Exception in CP-140605. Dec.14: 65->100% | 24.229 | 64 | 33 |  |  | Sat 10/08/13 | Thu 04/12/14
2568 | 640997 | PCRF based solution | PCSCF_RES | 2 | Rel-12 | C3,C1 | 2013-04-03 16:12 | 2014-12-09 17:00 | 100% | CP-140490 | - | Huawei | susan.shishufeng@huawei.com | - | - | 64 | 33 |  |  | Tue 29/07/14 | Tue 29/07/14
2569 | 640015 | CT3 part of PCRF based solution | PCSCF_RES | 3 | Rel-12 | C3 | 2013-05-03 16:12 | 2014-12-09 17:00 | 100% | CP-140490 | CP-140687 | Huawei | susan.shishufeng@huawei.com | CP#65 updated WID CP-140443=>CP-140490 (added CT3 part). Exception in CP-140687 | 29.212, 29.213, 29.214, 29.215 | 64 | 33 |  |  | Sat 10/08/13 | Tue 03/06/14
2570 | 640214 | CT1 part of PCRF based solution | PCSCF_RES | 3 | Rel-12 | C1 | 2013-04-03 16:12 | 2014-12-09 17:00 | 100% | CP-140490 | CP-140605 | Huawei | susan.shishufeng@huawei.com | CP#65 completion 09/14=>12/14. Exception in CP-140605. Dec.14: 65->100 | 24.229 | 64 | 33 |  |  | Sat 10/08/13 | Thu 04/12/14
2571 | 610008 | Updating IMS to conform to RFC 6665 (Stage 3) | UP6665 | 1 | Rel-12 | C1,C3 | 2013-09-09 08:00 | 2015-03-13 17:00 | 100% | CP-130717 | - | BlackBerry | Andrew Allen (aallen@blackberry.com) | Stage 3. Review the references related to RFC 3265 in the 3GPP IMS specifications and determine the impact of the RFC 6665 changes | Stage 3 | 61 | 31 |  |  | Thu 25/07/13 | Mon 09/09/13
2572 | 610108 | CT1 part of Updating IMS to conform to RFC 6665 | UP6665 | 2 | Rel-12 | C1 | 2013-09-09 08:00 | 2014-12-09 17:00 | 100% | CP-130717 | CP-140620 | BlackBerry | Andrew Allen (aallen@blackberry.com) | CP#65 completion 09/14=>12/14. Exception in CP-140620. 3/3/15: 100% cpltd. | 23.218, 24.141, 24.147, 24.229, 24.237, 24.292, 24.337, 24.341, 24.604, 24.606, 24.623, 24.628, 24.629, 24.642 | 61 | 31 |  |  | Thu 25/07/13 | Tue 03/03/15
2573 | 610208 | CT3 part of Updating IMS to conform to RFC 6665 | UP6665 | 2 | Rel-12 | C3 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | CP-130717 | - | BlackBerry | Andrew Allen (aallen@blackberry.com) | CP#62 completed | 29.163, 29.165 | 61 | 31 |  |  | Thu 25/07/13 | Tue 19/11/13
2574 | 670033 | (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-ietf-sipcore-refer-clarifications) | UP6665 | 2 | Rel-12 | C1-IETF | 2015-03-13 08:00 | 2015-03-13 17:00 | 100% | CP-130717 |  | BlackBerry | Andrew Allen (aallen@blackberry.com) | Added as per CT chair indications on 12th March 2015, no WID, no end date | draft-ietf-sipcore-refer-clarification | 67 | 34 |  |  | Fri 13/03/15 | Fri 13/03/15
2575 | 670034 | (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-ietf-sipcore-refer-explicit-subscription) | UP6665 | 2 | Rel-12 | C1-IETF | 2015-03-13 08:00 | 2015-03-13 17:00 | 100% | CP-130717 |  | BlackBerry | Andrew Allen (aallen@blackberry.com) | Added as per CT chair indications on 12th March 2015, no WID, no end date; 14/09/15: 50%->100 | draft-ietf-sipcore-refer-explicit-subscription | 67 | 34 |  |  | Fri 13/03/15 | Mon 14/09/15
2576 | 670035 | (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-roach-sipcore-6665-clarifications) | UP6665 | 2 | Rel-12 | C1-IETF | 2015-03-13 08:00 | 2015-03-13 17:00 | 100% | CP-130717 |  | BlackBerry | Andrew Allen (aallen@blackberry.com) | Added as per CT chair indications on 12th March 2015, no WID, no end date; 14/09/15: 50%->100 | draft-roach-sipcore-6665-clarification | 67 | 34 |  |  | Fri 13/03/15 | Mon 14/09/15
2577 | 620004 | IMS Operator Determined Call Barring enhancements (Stage 3) | eIODB | 1 | Rel-12 | C1,C3 | 2013-12-06 08:00 | 2014-09-11 17:00 | 100% | CP-130711 | - | Ericsson | Jorgen.Axell@ericsson.com | Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CP#60 decision | Stage 3 | 62 | 32 |  |  | Mon 18/11/13 | Mon 18/11/13
2578 | 620104 | CT1 part of IMS Operator Determined Call Barring enhancements | eIODB | 2 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-06-13 17:00 | 100% | CP-130711 | - | Ericsson | Jorgen.Axell@ericsson.com | CP#64 completed | 24.229, 24.315 | 62 | 32 |  |  | Mon 18/11/13 | Mon 26/05/14
2579 | 620204 | CT3 part of IMS Operator Determined Call Barring enhancements | eIODB | 2 | Rel-12 | C3 | 2013-12-09 08:00 | 2014-09-11 17:00 | 100% | CP-130711 | - | Ericsson | Jorgen.Axell@ericsson.com | CP#65 completed | 29.165 | 62 | 32 |  |  | Mon 18/11/13 | Fri 01/08/14
2580 | 620006 | Signalling Improvements for Network Efficiency (Stage 3) | SINE | 1 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-12-09 17:00 | 100% | CP-130713 | CP-140617 | Huawei | Lin Shu (shulin@huawei.com) | CP#65 completion 09/14=>12/14. Exception in CP-140617.Dec.14: 80->85%. 3/3/15: 100% cpltd. | 24.008, 24.301 | 62 | 32 |  |  | Mon 18/11/13 | Tue 03/03/15
2581 | 630002 | Interactive Connectivity Establishment (ICE, IETF RFC 5245) impacts on IMS H.248 profiles | ICEH248 | 1 | Rel-12 | C4,C3 | 2014-03-05 08:00 | 2014-09-11 17:00 | 100% | CP-140266 | - | NSN | Jan.Kall@nsn.com | Add optional ICE support as defined in Rel-8 TS (23.228, 24.229) to Iq, Ix, Mn, Mp, Mc interfaces. SA2 Rel-12 TS 23.228 requires support for ICE in eP-CSCF, eIMS-AGW for WebRTC | Stage 2/3 | 63 | 32 |  |  | Wed 29/01/14 | Tue 03/06/14
2582 | 630102 | CT4 part of ICE impacts on IMS H.248 profiles (Stage 2/3) | ICEH248 | 2 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-09-11 17:00 | 100% | CP-140266 | - | NSN | Jan.Kall@nsn.com | CP#65 completed | 23.333, 23.334, 29.232, 29.238, 29.332, 29.333, 29.334 | 63 | 32 |  |  | Wed 29/01/14 | Mon 28/07/14
2583 | 630202 | CT3 part of ICE impacts on IMS H.248 profiles (Stage 2) | ICEH248 | 2 | Rel-12 | C3 | 2014-03-05 08:00 | 2014-06-13 17:00 | 100% | CP-140266 | - | NSN | Jan.Kall@nsn.com | CP#64 completed | 29.162, 29.163, 29.292 | 63 | 32 |  |  | Wed 29/01/14 | Tue 03/06/14
2584 | 630005 | Transfer of ETSI business trunking specifications | IMS_Corp2 | 1 | Rel-12 | C1,S1 | 2014-03-05 08:00 | 2014-12-09 17:00 | 100% | SP-140170 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com, Youssef Chadli | Rel-12 enhancements to business trunking (BusTI). ETSI E2NA(14)000019 asked 3GPP to take responsibility of business communications over IMS: TS 181 019, TS 182 023, TS 182 024, TS 182 025, TR 183 060 | - | 63 | 32 |  |  | Wed 29/01/14 | Fri 07/03/14
2585 | 630105 | SA1 part of Transfer of ETSI business trunking specifications | IMS_Corp2 | 2 | Rel-12 | S1 | 2014-03-05 08:00 | 2014-09-17 17:00 | 100% | SP-140170 | S1-143300 | Alcatel-Lucent | betsy.covell@alcatel-lucent.com | SP#65 completed. TS 22.519v200 for Approval | New TS 22.519 (ETSI TS 181 019) | 63 | 32 |  |  | Thu 06/03/14 | Wed 03/09/14
2586 | 630205 | CT1 part of Transfer of ETSI business trunking specifications | IMS_Corp2 | 2 | Rel-12 | C1 | 2014-03-05 08:00 | 2014-12-09 17:00 | 100% | SP-140170 | CP-140619 | Alcatel-Lucent | keith.drage@alcatel-lucent.com, Youssef Chadli | CP#65 TS 24.525v200 for Approval. TR 24.969v100 for Information. Completion 09/14=>12/14. Exception in CP-140619. Dec.14: 90->100 | New TSs [24.523 (TS 182 023), 24.524 (TS 182 024), 24.525 (TS 182 025)], New TR 24.969 (TR 183 069) | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
2587 | 630008 | Support of ALT-C attribute | ALTC | 1 | Rel-12 | C4,C1,C3 | 2014-03-10 08:00 | 2014-12-09 17:00 | 100% | CP-140191 | - | Orange | lionel.morand@orange.com | SA2 TS 23.228 requires UEs supporting IPv4, IPv6 or both IPv4 and IPv6 IP address formats shall be supported by IMS. Specify procedures to support altc SDP attribute within IMS for terminating communications destined to an enterprise network. | - | 63 | 32 |  |  | Wed 29/01/14 | Mon 03/03/14
2588 | 630108 | CT4 part of Support of ALT-C attribute | ALTC | 2 | Rel-12 | C4 | 2014-03-10 08:00 | 2014-12-09 17:00 | 100% | CP-140191 | CP-140485 | Orange | lionel.morand@orange.com | CP#65 completion 09/14=>12/14. Exception in CP-140485. Dec.14: 0->100 | 23.334, 29.238, 29.334 | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
2589 | 630208 | CT1 part of Support of ALT-C attribute | ALTC | 2 | Rel-12 | C1 | 2014-03-10 08:00 | 2014-12-09 17:00 | 100% | CP-140191 | CP-140611 | Orange | lionel.morand@orange.com | CP#65 completion 09/14=>12/14. Exception in CP-140611. Dec.14: 0->100 | 24.229 | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
2590 | 630308 | CT3 part of Support of ALT-C attribute | ALTC | 2 | Rel-12 | C3 | 2014-03-10 08:00 | 2014-12-09 17:00 | 100% | CP-140191 | CP-140563 | Orange | lionel.morand@orange.com | CP#65 completion 09/14=>12/14. Exception in CP-140563. Dec.14: 0->100 | 29.162 | 63 | 32 |  |  | Wed 29/01/14 | Thu 04/12/14
2591 | 640003 | Diameter Overload Control Mechanisms | DOCME | 1 | Rel-12 | C4,IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140273 | - | Orange | lionel.morand@orange.com | Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME) | - | 64 | 33 |  |  | Sun 25/05/14 | Mon 16/06/14
2592 | 640103 | CT4 part of Diameter Overload Control Mechanisms | DOCME | 2 | Rel-12 | C4 | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140273 | CP-140486 | Orange | lionel.morand@orange.com | CP#65 completion 09/14=>12/14. Exception in CP-140486. Dec.14: 70->100 | 29.228, 29.229, 29.272, 29.273, 29.328, 29.329, 29.336, 29.337, 29.344, 29.345 | 64 | 33 |  |  | Sun 25/05/14 | Thu 04/12/14
2593 | 641010 | (IETF) Diameter Overload Control Mechanisms (draft-ietf-dime-ovli) | DOCME | 2 | Rel-12 | C4-IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140273 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Mar15: In WGLC; 7/3/16: 50%->100 | draft-ietf-dime-ovli | 64 | 33 |  |  | Sun 25/05/14 | Mon 07/03/16
2594 | 640004 | Impacts of RFC7044 for introduction of the new History-Info header field | HISTORY_CT | 1 | Rel-12 | C1,C3 | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140285 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | IETF updated RFC4244 for History-Info header field to RFC7044. IETF introduced new features which could be useful for 3GPP use cases. | - | 64 | 33 |  |  | Mon 07/04/14 | Mon 07/04/14
2595 | 640104 | CT1 part of Impacts of RFC7044 for introduction of the new History-Info header field | HISTORY_CT | 2 | Rel-12 | C1 | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140285 | CP-140609 | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | CP#65 completion 09/14=>12/14. Exception in CP-140609. Dec.14: 85->100 | 24.229, 24.259, 24.604 | 64 | 33 |  |  | Mon 07/04/14 | Thu 04/12/14
2596 | 640204 | CT3 part of Impacts of RFC7044 for introduction of the new History-Info header field | HISTORY_CT | 2 | Rel-12 | C3 | 2014-06-13 08:00 | 2014-09-11 17:00 | 100% | CP-140285 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | CP#65 completed | 29.163, 29.165, 29.292 | 64 | 33 |  |  | Mon 07/04/14 | Thu 31/07/14
2597 | 640007 | Indication of NNI Routeing scenarios in SIP requests | NNI_RS | 1 | Rel-12 | C1,C3,IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140288 | - | Ericsson | Jan.Holm@ericsson.com | Triggered by TR 24.802 Study on Indication of Network to Network Interface (NNI) Routeing scenarios in SIP requests UID_580025 | - | 64 | 33 |  |  | Mon 07/04/14 | Mon 07/04/14
2598 | 640107 | CT1 part of Indication of NNI Routeing scenarios in SIP requests | NNI_RS | 2 | Rel-12 | C1 | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140288 | CP-140613 | Ericsson | Jan.Holm@ericsson.com | CP#65 completion 09/14=>12/14. Exception in CP-140613. Dec.14: 95->100 | 24.229 | 64 | 33 |  |  | Mon 07/04/14 | Thu 04/12/14
2599 | 641008 | (IETF) CT1 part of Indication of NNI Routeing scenarios in SIP requests (draft-holmberg-dispatch-iotl) | NNI_RS | 2 | Rel-12 | C1-IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140288 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | Publication requested; 7/3/16: 50%->100 | draft-holmberg-dispatch-iotl | 64 | 33 |  |  | Fri 06/06/14 | Mon 07/03/16
2600 | 640207 | CT3 part of Indication of NNI Routeing scenarios in SIP requests | NNI_RS | 2 | Rel-12 | C3 | 2014-06-13 08:00 | 2014-09-11 17:00 | 100% | CP-140288 | - | Ericsson | Jan.Holm@ericsson.com | CP#65 completed | 29.079, 29.165 | 64 | 33 |  |  | Mon 07/04/14 | Thu 31/07/14
2601 | 640008 | Unstructured Supplementary Service Data (USSD) method selection (Stage 3) | USSD_MS | 1 | Rel-12 | C1 | 2014-06-11 08:00 | 2014-06-13 17:00 | 100% | CP-140450 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#64 approved WID & completed. Related to R11 USSD simulation service in IMS (delivery of UE originating USSD request using IMS, I.e. introduce 2nd method for delivery of UE originating USSD request to network (additional to USSD using CS domain) | 24.173, 24.390, New TS 24.391 | 64 | 33 |  |  | Mon 07/04/14 | Thu 12/06/14
2602 | 640009 | Representational State Transfer (REST) reference point between Application Function (AF) and Protocol Converter (PC) | REST_AF_PC | 1 | Rel-12 | C3 | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140451 | CP-140561 | Alcatel-Lucent | horst.brinkmann@alcatel-lucent.com | CP#65 completion 09/14=>12/14. TS 29.201v200 for Approval. Exception in CP-140561. Dec.14: 80->100 | 29.213, 29.214, new TS 29.201 | 64 | 33 |  |  | Tue 10/06/14 | Thu 04/12/14
2603 | 640011 | Overload Control for PCC based Diameter applications | DOCME-PCC | 1 | Rel-12 | C3,IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140405 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME) | - | 64 | 33 |  |  | Tue 10/06/14 | Mon 16/06/14
2604 | 640111 | CT3 part of Overload Control for PCC based Diameter applications | DOCME-PCC | 2 | Rel-12 | C3 | 2014-06-13 08:00 | 2014-09-11 17:00 | 100% | CP-140405 | - | Huawei | Xia Haitao (xiahaitao@huawei.com) | CP#65 completed | 29.212, 29.213, 29.214 | 64 | 33 |  |  | Tue 10/06/14 | Thu 31/07/14
2605 | 641011 | (IETF) Overload Control for PCC based Diameter applications | DOCME-PCC | 2 | Rel-12 | C3-IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140405 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | work in progress; 7/3/16: 50%->100 | draft-ietf-dime-ovli | 64 | 33 |  |  | Tue 10/06/14 | Mon 07/03/16
2606 | 650004 | Network Initiated USSD Simulation Services in IMS | USSI-NET | 1 | Rel-12 | C1 | 2014-09-12 08:00 | 2014-12-09 17:00 | 100% | CP-140625 | CP-140610 | AT&T | Martin Dolly (md3135@att.com) | CP#65 exception in CP-140610. Dec.14: 75->100 | 24.390 | 65 | 33 |  |  | Mon 28/07/14 | Thu 04/12/14
2607 | 530002 | Introduction of ER-GSM band for GSM-R | RT_ERGSM | 1 | Rel-12 | G1,C1,G3new | 2011-09-16 08:00 | 2014-02-28 17:00 | 100% | GP-130889 | - | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | Use of band 870-876/915-921 MHz for land mobile service on national possibilities/market demand - as per ECC/DEC/(04)06. Introduction of ERGSM band, Performance requirements and Deployment scenarios. | GERAN | 51 | 27 |  |  | Tue 06/09/11 | Fri 07/03/14
2608 | 530102 | GERAN1 part of Introduction of ER-GSM band for GSM-R | RT_ERGSM | 2 | Rel-12 | G1 | 2011-09-16 08:00 | 2014-02-28 17:00 | 100% | GP-130889 | - | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | GP#61 completed. GP#51 approved WID | 45.001, 45.005, 45.008, 45.050 | 51 | 27 |  |  | Tue 06/09/11 | Fri 07/03/14
2609 | 610016 | Test part: Introduction of ER-GSM band for GSM-R | RT_ERGSM | 2 | Rel-12 | G3new | 2013-09-02 08:00 | 2014-02-28 17:00 | 100% | GP-130889 | - | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | GP#61 completed | 51.010, 51.021 | 59 | 31 |  |  | Wed 04/09/13 | Fri 07/03/14
2610 | 530202 | CT1 part of Introduction of ER-GSM band for GSM-R | RT_ERGSM | 2 | Rel-12 | C1 | 2011-09-28 08:00 | 2013-12-06 17:00 | 100% | GP-130889 | - | Kapsch Carriercom, Sierra Wireless | thomas.chatelet@kapsch.net, Rémi Lascoux (rlascoux@sierrawireless.com) | CP#62 completed. Added ERGSM capability indication (24.008 CR#2469R1) | 24.008 | 53 | 27 |  |  | Tue 06/09/11 | Tue 19/11/13
2611 | 570002 | Downlink Multi Carrier GERAN | DMCG | 1 | Rel-12 | G2,G1,C1,G3new | 2012-09-10 08:00 | 2015-03-13 17:00 | 91% | GP-140190 | - | Ericsson | paul.schliwa-bertling@ericsson.com | Linked to Rel-7 Downlink Dual Carrier UID_50579 (Previous work on multiple carriers on the downlink was limited to two). Ref: TR 45.912 Feasibility study for evolved GERAN, TS 43.064 GPRS Stage 2 | GERAN | 55 | 29 |  |  | Mon 03/09/12 | Sat 01/03/14
2612 | 570102 | Core part: Downlink Multi Carrier GERAN | DMCG | 2 | Rel-12 | G2,G1 | 2013-07-22 08:00 | 2014-05-30 17:00 | 100% | GP-140190 | - | Ericsson | paul.schliwa-bertling@ericsson.com | GP#62 completed. GP#55 approved WID | 43.064, 44.004, 44.018, 44.060, 45.002, 45.003, 45.005, 45.008, 48.018 | 55 | 29 |  |  | Mon 03/09/12 | Fri 30/05/14
2613 | 570202 | CT part: Downlink Multi Carrier GERAN | DMCG | 2 | Rel-12 | C1 | 2012-09-10 08:00 | 2014-09-11 17:00 | 100% | GP-140190 | - | Ericsson | paul.schliwa-bertling@ericsson.com | CP#65 completed | 24.008 | 55 | 29 |  |  | Mon 03/09/12 | Mon 28/07/14
2614 | 570302 | Test part: Downlink Multi Carrier GERAN | DMCG-MStest | 2 | Rel-12 | G3new | 2012-09-10 08:00 | 2015-03-13 17:00 | 80% | GP-120930 | - | ST-Ericsson | hakan.e.grunditz@stericsson.com | GP#63 completion 08/14=>11/14. Dec.14: 35->80%, CD:11/14->03/15 | 51.010-1, 51.010-2 | 55 | 29 |  |  | Mon 03/09/12 | Wed 03/12/14
2615 | 590033 | Mobile Station Receive Diversity (MSRD) for Voice Services over Adaptive Multi-user channels on One Slot (VAMOS) | MSRD_VAMOS | 1 | Rel-12 | G1,G2,C1,G3new | 2013-03-01 08:00 | 2014-11-21 17:00 | 100% | GP-130849 | GP-140579 | Nokia Networks, Microsoft | Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft) | GP#63 completion 08/14=>11/14. Exception in GP-140579. Linked to Rel-7 Mobile Station Receive Diversity (DARP Phase II) UID_50569, Rel-9 Voice Services over Adaptive Multiuser channels on One Slot (VAMOS) UID_420002 | GERAN | 57 | 30 |  |  | Mon 04/03/13 | Fri 29/08/14
2616 | 590333 | CT1 introduction of MS capability support for MS supporting MSRD for VAMOS | MSRD_VAMOS | 2 | Rel-12 | C1 | 2013-03-01 08:00 | 2013-12-06 17:00 | 100% | GP-130849 | - | Nokia Networks, Microsoft | Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft) | CP#62 completed | 24.008 | 57 | 30 |  |  | Mon 04/03/13 | Fri 29/08/14
2617 | 590133 | MSRD for VAMOS - Performance Requirements | MSRD_VAMOS-PerfReq | 2 | Rel-12 | G1,G2 | 2013-11-28 13:00 | 2014-11-21 17:00 | 100% | GP-130849 | GP-140579 | Nokia Networks, Microsoft | Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft) | GP#63 completion 08/14=>11/14. Exception in GP-140579. Dec.14: 95->100 | 44.018, 45.001, 45.002, 45.005, 45.008, 45.009 | 57 | 30 |  |  | Mon 04/03/13 | Wed 03/12/14
2618 | 590233 | MSRD for VAMOS - MS Conformance Test | MSRD_VAMOS-Test | 2 | Rel-12 | G3new | 2013-03-06 08:00 | 2014-11-21 17:00 | 100% | GP-130849 | GP-140579 | Nokia Networks, Microsoft | Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft) | GP#63 completion 08/14=>11/14. Exception in GP-140579. Dec.14: 85->100 | 51.010-1, 51.010-2 | 57 | 30 |  |  | Mon 04/03/13 | Wed 03/12/14
2619 | 620014 | New Training Sequence Codes (TSC) for GERAN | NewToN | 1 | Rel-12 | G1,G2,C1 | 2013-11-22 08:00 | 2014-12-09 17:00 | 93% | GP-131139 | GP-140542 | Ericsson | Mårten Sundberg | GP#63 completion 08/14=>11/14. Exception in GP-140542. GP#60 approved WID. Triggered by GP-131041, GP#40 GP-081949 (WID VAMOS). Linked to Rel-9 VAMOS (Previous work where new TSCs were defined for GMSK modulation) UID_420002 | GERAN | 60 | 32 |  |  | Fri 22/11/13 | Tue 27/05/14
2620 | 620114 | GERAN1 part of New Training Sequence Codes (TSC) for GERAN | NewToN | 2 | Rel-12 | G1 | 2013-11-22 08:00 | 2014-11-21 17:00 | 100% | GP-131139 | GP-140542 | Ericsson | Mårten Sundberg | GP#63 completion 08/14=>11/14. Exception in GP-140542. Dec.14: 80->100% | 45.001, 45.002, 45.008, 45.009, 45.050 | 60 | 32 |  |  | Fri 22/11/13 | Wed 03/12/14
2621 | 620214 | GERAN2 part of New Training Sequence Codes (TSC) for GERAN | NewToN | 2 | Rel-12 | G2 | 2013-11-22 08:00 | 2014-11-19 17:00 | 80% | GP-131139 | GP-140542 | Ericsson | Mårten Sundberg | GP#63 completion 08/14=>11/14. Exception in GP-140542. | 44.018, 44.060 | 60 | 32 |  |  | Fri 22/11/13 | Fri 30/05/14
2622 | 620314 | CT1 part of New Training Sequence Codes (TSC) for GERAN (Stage 3) | NewToN | 2 | Rel-12 | C1 | 2013-11-22 08:00 | 2014-12-09 17:00 | 100% | GP-131139 | CP-140604 | Ericsson | Mårten Sundberg | CP#65 completion 09/14=>12/14. CP#65 exception in CP-140604. 3/3/15: 100% cpltd. | 24.008 | 60 | 32 |  |  | Fri 22/11/13 | Tue 03/03/15
2623 | 550016 | Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS | HSPA_LTE_measRP_MIMO | 1 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-12-06 17:00 | 100% | RP-120368 | - | Vodafone | Luis Anaya | RP#59 moved to Rel-12. Triggered by FS_HSPA_LTE_measRP_MIMO_multi-antenna. Core functionality exists since Rel-6 & Rel-7 (MIMO). Adds a very generic test method to test UEs with 2 or more Rx antennas | UTRA, LTE | 55 | 28 |  |  | Thu 23/02/12 | Thu 14/03/13
2624 | 550116 | Perf. Part: Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS | HSPA_LTE_measRP_MIMO-Perf | 2 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-12-06 17:00 | 100% | RP-120368 | RP-131507 | Vodafone | luis.anaya@vodafone.com | RP#62 completed. Rx diversity (defined as Rel-6 HSDPA RAN4 enhanced type 1 req.) & MIMO (defined as Rel-7 HSDPA MIMO for HSPA). Rx diversity & MIMO (defined as part of Rel-8 basic LTE WI) | new TR 37.977 | 55 | 28 |  |  | Thu 23/02/12 | Fri 30/08/13
2625 | 570021 | Further enhancements to H(e)NB mobility - Part 3 (Stage 2/3) | EHNB_enh3 | 1 | Rel-12 | R3,R2 | 2012-09-12 08:00 | 2013-12-06 17:00 | 100% | RP-130741 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | Triggered by FS_EHNB_enh (TR 37.803) | UTRA, LTE | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/06/13
2626 | 570121 | Core part: Further enhancements to H(e)NB mobility - Part 3 | EHNB_enh3-Core | 2 | Rel-12 | R3,R2 | 2012-09-12 08:00 | 2013-12-06 17:00 | 100% | RP-130741 | RP-131508 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#62 completed | 25.304, 25.331, 25.367, 25.467, 25.469, 36.300, 36.331 | 57 | 29 |  |  | Tue 04/09/12 | Fri 29/11/13
2627 | 590019 | Support for BeiDou Navigation Satellite System (BDS) for UTRA and LTE | LCS_BDS | 1 | Rel-12 | R2,R3,R4,R5 | 2013-03-04 08:00 | 2015-06-15 17:00 | 100% | RP-130416 | - | CATR | Ying Du (duying1@catr.cn) | BeiDou = Chinese Navigation Satellite System. Location Services (LCS) TS 22.071 Stage 1, TS 23.271 Stage 2 | UTRA, LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 05/03/13
2628 | 590119 | Core part: Support for BeiDou Navigation Satellite System (BDS) for UTRA | LCS_BDS-UTRA-Core | 2 | Rel-12 | R2,R3 | 2013-06-02 08:00 | 2014-03-06 17:00 | 100% | RP-130416 | RP-131500 | ZTE | Huang He (huang.he4@zte.com.cn) | RP#62 completed | 25.305, 25.306, 25.331, 25.453, 25.413, 25.423, 25.433 | 59 | 30 |  |  | Tue 26/02/13 | Fri 29/11/13
2629 | 590219 | Perf. part: Support for BeiDou Navigation Satellite System (BDS) for UTRA | LCS_BDS-UTRA-Perf | 2 | Rel-12 | R4 | 2013-03-07 08:00 | 2014-06-13 17:00 | 100% | RP-130416 | RP-140714 | ZTE | Ling Soonleh (soonleh.ling@zte.com.cn) | RP#64 completed. TS 25.173v100 for 1-step Approval | 25.172 (FDD), new TS 25.173 (TDD) | 59 | 30 |  |  | Tue 26/02/13 | Wed 11/06/14
2630 | 590319 | Core part: Support for BeiDou Navigation Satellite System (BDS) for LTE | LCS_BDS-LTE-Core | 2 | Rel-12 | R2 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-130416 | RP-131525 | CATR | Ying Du (duying1@catr.cn) | RP#62 completed | 36.305, 36.355 | 59 | 30 |  |  | Tue 26/02/13 | Fri 29/11/13
2631 | 590419 | Perf. part: Support for BeiDou Navigation Satellite System (BDS) for LTE | LCS_BDS-LTE-Perf | 2 | Rel-12 | R4 | 2013-03-07 08:00 | 2014-06-13 17:00 | 100% | RP-130416 | RP-140713 | ZTE | Ling Soonleh (soonleh.ling@zte.com.cn) | RP#64 completed | 36.171 | 59 | 30 |  |  | Tue 26/02/13 | Thu 12/06/14
2632 | 640013 | Test part: BeiDou Navigation Satellite System (BDS) Positioning Support for LTE and UMTS | LCS_BDS-UEConTest | 2 | Rel-12 | R5 | 2014-06-15 | 2015-06-15 17:00 | 100% | RP-140730 | RP-150656 | CATT | Chen Xiaiozhong (chenxiaozhong@catt.cn) | ; Stat Rep: RP-141350->RP-141950 1st Apr 15: Compl:80%->90% 1st Apr 15: Stat Rep: RP-141950->RP-150357 03/07/15: Compl:90%->100% 03/07/15: Stat Rep: RP-150357->RP-150656 | 34.108, 36.508, 37.571-1, 37.571-2, 37.571-3, 37.571-4, 37.571-5 | 64 | 33 |  |  | Tue 10/06/14 | Thu 18/06/15
2633 | 620011 | Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN | 1 | Rel-12 | G2,G1,G3new | 2013-11-22 08:00 | 2015-03-13 17:00 | 93% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#60 approved WID. Based on the same framework used in Rel-8 Support for Additional Navigation Satellite Systems (ANSS) for LCS UID_38001 | GERAN | 60 | 32 |  |  | Fri 22/11/13 | Sat 01/03/14
2634 | 620111 | GERAN2 part of Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN | 2 | Rel-12 | G2 | 2013-11-22 08:00 | 2014-08-29 17:00 | 100% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#63 completed | 44.031, 49.031, 44.071, 48.031 | 60 | 32 |  |  | Fri 22/11/13 | Fri 29/08/14
2635 | 620211 | GERAN1 part of Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN | 2 | Rel-12 | G1 | 2013-11-22 08:00 | 2014-08-29 17:00 | 100% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#63 completed | 43.059, 45.005 | 60 | 32 |  |  | Fri 22/11/13 | Fri 29/08/14
2636 | 630009 | Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN3new | LCS_BDS_GERAN-GERAN3new | 2 | Rel-12 | G3new | 2014-03-01 08:00 | 2015-03-13 17:00 | 80% | GP-140244 |  | CATR | Zhou DaiWei, China Academy of Telecommunication Research, zhoudaiwei@catr.cn | Dec.14: 25->80%, CD: 11/14->03/15 | 51010-1, 51.010-2, 51.010-7 | 61 | 32 |  |  | Sat 01/03/14 | Fri 29/08/14
2637 | 620311 | Deleted - Test part: Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN-MStest | 2 | Rel-12 | G3new | 2013-11-22 08:00 | 2014-02-28 17:00 | 100% | GP-140211 | - | ZTE | Wang Xinhui (wangxinhui@zte.com.cn) | GP#61 stopped | 51.010-1 | 60 | 32 | GP-61 | PCG-32 | Fri 22/11/13 | Sat 01/03/14
2638 | 600019 | Deleted - New Base Station specification structure | BSspec_struc | 1 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-130851 | - | Ericsson | johan.skold@ericsson.com | Triggered by Rel-12 TR 37.810 Study on Base Station specification structure (FS_BSspec_struc) | UTRA, LTE, MSR | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Mon 17/06/13
2639 | 600119 | Deleted - Core part: New Base Station specification structure | BSspec_struc-Core | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-130851 | RP-131513 | Ericsson | johan.skold@ericsson.com | RP#62 stopped (at 20% completion) | 25.104, 25.105, 36.104, 37.104, 37.810, New TR 37.811 (New BS specification structure), New TS 37.xya (New RF core specification) | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Fri 29/11/13
2640 | 600219 | Deleted - Perf. part: New Base Station specification structure | BSspec_struc-Perf | 2 | Rel-12 | R4 | 2013-06-20 08:00 | 2013-12-06 17:00 | 100% | RP-130851 | RP-131514 | Ericsson | johan.skold@ericsson.com | RP#62 stopped (at 0% completion) | 25.113, 25.141, 25.142, 36.113, 36.141, 37.113, 37.141, 37.810, New TS 37.xyz (New RF test specification, New TS 37.xyw (ew EMC specification) | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Fri 29/11/13
2641 | 600021 | L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL | 1 | Rel-12 | R4,R2,R3 | 2013-06-17 08:00 | 2015-12-15 17:00 | 100% | RP-140092 | - | Orange | olfa.benhaddada@orange.com | ECC(12)052 CEPT decision to harmonize 1452-1492 MHz (L-band) for mobile communications Supplemental Downlink (SDL) => standardize L-band and corresponding E-UTRA and UTRA requirements for SDL operation in Region 1 | UTRA, LTE | 60 | 31 |  |  | Mon 17/06/13 | Sat 07/12/13
2642 | 600121 | Core part: L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL-Core | 2 | Rel-12 | R4,R2,R3 | 2014-02-13 14:20 | 2014-06-13 17:00 | 100% | RP-140092 | RP-140633 | Orange | olfa.benhaddada@orange.com | RP#64 completed. RP#65 forgotten TR 37.814 v100 for 1-step Approval | 25.101, 25.104, 25.113, 25.133, 25.307, 25.327, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 36.331, 37.104, 37.113, new TR 37.814 | 60 | 31 |  |  | Mon 17/06/13 | Mon 15/09/14
2643 | 600221 | Perf. part: L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL-Perf | 2 | Rel-12 | R4 | 2013-06-17 08:00 | 2014-06-13 17:00 | 100% | RP-140092 | RP-140633 | Orange | olfa.benhaddada@orange.com | RP#64 completed | 25.133, 25.141, 25.307, 25.327, 36.133, 36.141, 36.307, 37.141 | 60 | 31 |  |  | Mon 17/06/13 | Thu 12/06/14
2644 | 670047 | UE Conformance Test Aspects - L-band for Supplemental Downlink in E-UTRA and UTRA | LTE_UTRA_SDL_BandL-UEConTest | 2 | Rel-12 | R5 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-150835 | RP-151163 | Ericsson |  | 03/07/15: Compl:0%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-150134->RP-150835 03/07/15: Stat Rep: ->RP-150830 29/09/15: Compl:85%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150830->RP-151163; 1/1/16 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
2645 | 600027 | LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | LTE_HRPD_SON | 1 | Rel-12 | R3,S2,C4,G2 | 2013-06-18 08:00 | 2014-06-13 17:00 | 100% | RP-130831 | - | China Telecom | Jinlian_wu@189.cn | Triggered by Rel-12 TR 37.813 (FS_LTE_HRPD_SON). SA2 should verify the architecture solution in TR 37.813 for inter-RAT load balancing between LTE-HRPD. CT4 should specify the RIM extension to support the feature. | UTRA, LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 17/06/13
2646 | 610103 | Stage 2 for LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | LTE_HRPD_SON | 2 | Rel-12 | S2 | 2013-09-11 08:00 | 2013-12-11 17:00 | 100% | - | - | Huawei | Huan Li (ivy.lihuan@huawei.com) | SP#62 completed | 23.402 | 61 | 31 |  |  | Thu 15/08/13 | Thu 28/11/13
2647 | 600127 | Core part: LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | LTE_HRPD_SON-Core | 2 | Rel-12 | R3 | 2013-06-18 08:00 | 2014-06-13 17:00 | 100% | RP-130831 | RP-140745 | China Telecom | Jinlian_wu@189.cn | RP#64 completed | 36.300, 36.413 | 60 | 31 |  |  | Mon 17/06/13 | Thu 12/06/14
2648 | 610003 | CT aspects for LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON (Stage 3) | LTE_HRPD_SON-CT | 2 | Rel-12 | C4 | 2013-09-04 08:00 | 2013-09-06 17:00 | 100% | CP-130434 | - | Huawei | Xiaoyan SHI (sean.shixiaoyan@huawei.com | CP#61 WID approved & Completed | 29.274, 29.276, 29.280 | 61 | 31 |  |  | Sun 11/08/13 | Tue 13/08/13
2649 | 610015 | GERAN aspects for LTE-HRPD inter-RAT SON, RAN Information Management (RIM) - Stage 3 | LTE_HRPD_SON-RIM | 2 | Rel-12 | G2 | 2013-08-26 08:00 | 2013-08-30 17:00 | 100% | GP-130817 | - | Alcatel-Lucent | marguerite.woch@alcatel-lucent.com | GP#59 WID approved & Completed | 48.018 | 59 | 31 |  |  | Sun 11/08/13 | Tue 01/10/13
2650 | 620042 | Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon | 1 | Rel-12 | R4,R2 | 2013-12-15 | 2018-09-14 17:00 | 99% | RP-132061 | - | Ericsson | christopher.callender@ericsson.com | - | UTRA, LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 09/09/14
2651 | 620142 | Core part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon-Core | 2 | Rel-12 | R4,R2 | 2013-12-15 | 2014-12-15 17:00 | 100% | RP-132061 | RP-141787 | Ericsson | christopher.callender@ericsson.com | ; CD:Thu 18/12/14->Mon 15/12/14; WID: RP-141966->RP-142235; Stat Rep: RP-141600->RP-141787 | 25.133, 25.331, 36.133 | 62 | 32 |  |  | Sat 07/12/13 | Mon 12/01/15
2652 | 620242 | Perf. part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon-Perf | 2 | Rel-12 | R4 | 2013-12-15 | 2015-06-15 17:00 | 100% | RP-132061 | RP-150596 | Ericsson | christopher.callender@ericsson.com | ; CD:Fri 12/06/15->Mon 15/06/15; WID: RP-141966->RP-142235; Stat Rep: RP-141600->RP-141787 1st Apr 15: Compl:5%->40% 1st Apr 15: Stat Rep: RP-141787->RP-150063 03/07/15: Compl:40%->100% 03/07/15: Stat Rep: RP-150063->RP-150596 | 25.133, 36.133 | 62 | 32 |  |  | Sat 07/12/13 | Thu 18/06/15
2653 | 700064 | UE Conformance Test Aspects - Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon-UEConTest | 2 | Rel-12 | R5 | 2015-12-15 08:00 | 2018-09-14 17:00 | 100% | RP-171889 |  | Ericsson |  | 22/3/16: Compl:0%->4%1/7/16: CD:Thu 15/09/16->Thu 15/12/16; 26/9/16: Com 21/3/17: Compl ; 2 ;; 16/1/19: 35%->100 |  | 70 | 36 |  |  | Fri 01/01/16 | Wed 16/01/19
2654 | 620048 | WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw | 1 | Rel-12 | R2,S2,C1,C4 | 2013-12-06 08:00 | 2014-12-09 17:00 | 100% | RP-140981 | - | Intel | sasha.sirotkin@intel.com | Triggered by Rel-12 TR 37.834 Study on WLAN/3GPP Radio Interworking (FS_UTRA_LTE_WLAN_interw) | UTRA, LTE | 62 | 32 |  |  | Mon 09/12/13 | Mon 09/12/13
2655 | 620148 | Core part: WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw-Core | 2 | Rel-12 | R2 | 2013-12-06 08:00 | 2014-09-12 17:00 | 100% | RP-140981 | RP-141310 | Intel | sasha.sirotkin@intel.com | SP#65 completed | 25.304, 25.306, 25.331, 36.304, 36.306, 36.331 | 62 | 32 |  |  | Mon 09/12/13 | Tue 09/09/14
2656 | 630013 | SA2 aspects of WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw-SA2 | 2 | Rel-12 | S2 | 2014-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-140169 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | SP#65 completed | 23.402, 23.401, 23.060, 23.251 | 63 | 32 |  |  | Fri 07/03/14 | Mon 15/09/14
2657 | 640006 | CT aspects of WLAN/3GPP Radio Interworking (Stage 2/3) | UTRA_LTE_WLAN_interw-CT | 2 | Rel-12 | C1,C4 | 2014-09-09 08:00 | 2014-12-09 17:00 | 100% | CP-140623 | - | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#65 revised WID CP-140287=>CP-140623 (added CT4 part) | Stage 2/3 | 64 | 33 |  |  | Mon 07/04/14 | Tue 09/09/14
2658 | 640106 | CT1 part of CT aspects of WLAN/3GPP Radio Interworking (Stage 3) | UTRA_LTE_WLAN_interw-CT | 3 | Rel-12 | C1 | 2014-09-09 08:00 | 2014-12-09 17:00 | 100% | CP-140623 | CP-140720 | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#65 completion 09/14=>12/14. Exception in CP-140720. 78%->95%. 12/12: 95->78%. 3/3/15: 100% cpltd. | 24.008, 24.301, 24.302, 24.312 | 64 | 33 |  |  | Mon 07/04/14 | Tue 03/03/15
2659 | 650001 | CT4 part of CT aspects of WLAN/3GPP Radio Interworking (Stage 2/3) | UTRA_LTE_WLAN_interw-CT | 3 | Rel-12 | C4 | 2014-09-12 08:00 | 2014-12-09 17:00 | 100% | CP-140623 | CP-140482 | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#65 revised WID CP-140287=>CP-140623 (added CT4 part). Exception in CP-140482. Dec.14: 50->100 | 23.008, 29.002, 29.272, 29.274, 29.305 | 65 | 33 |  |  | Mon 28/07/14 | Thu 04/12/14
2660 | 660075 | UE Conformance Test Aspects – WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw-UEConTest | 1 | Rel-12 | R5 | 2014-12-15 08:00 | 2016-03-15 17:00 | 100% | RP-151270 | RP-151264 | Intel | Intel | Rel13->Rel-12; Moved at appropriate place 1st Apr 15: Compl:0%->5% 1st Apr 15: Stat Rep: ->RP-150098 03/07/15: Compl:5%->20% 03/07/15: Stat Rep: RP-150098->RP-150929 29/09/15: Compl:20%->60% 29/09/15: WID: RP-141879->RP-151270 29/09/15: Stat Rep: RP-15 |  | 66 | 34 |  |  | Mon 12/01/15 | Tue 22/03/16
2661 | 551000 | Rel-12 LTE Carrier Aggregation (CA) | LTE_CA_Rel-12 | 1 | Rel-12 | R4 | 2011-09-19 08:00 | 2016-12-15 17:00 | 100% | - | - | - | - | LTE_CA_Rel-12 | LTE | 58 | 30 |  |  | Fri 14/12/12 | Fri 14/12/12
2662 | 530025 | LTE Advanced inter-band CA of Band 1 and Band 7 | LTE_CA_B1_B7 | 2 | Rel-12 | R4 | 2011-09-19 08:00 | 2014-09-12 17:00 | 100% | RP-141487 | - | Ericsson | christian.bergljung@ericsson.com | Inter-band CA 2DL | LTE | 53 | 27 |  |  | Thu 15/09/11 | Sat 07/12/13
2663 | 530125 | Core part:LTE Advanced inter-band CA of Band 1 and Band 7 | LTE_CA_B1_B7-Core | 3 | Rel-12 | R4 | 2011-09-19 08:00 | 2014-09-12 17:00 | 100% | RP-141487 | RP-141084 | Ericsson | christian.bergljung@ericsson.com | RP#65 completed. Updated WID RP-132042=>RP-141487 | 36.101, 36.104, new generic TR 36.851 | 53 | 27 |  |  | Thu 15/09/11 | Sat 20/09/14
2664 | 530225 | Perf. part:LTE Advanced inter-band CA of Band 1 and Band 7 | LTE_CA_B1_B7-Perf | 3 | Rel-12 | R4 | 2011-10-03 08:00 | 2014-09-12 17:00 | 100% | RP-141487 | RP-141084 | Ericsson | christian.bergljung@ericsson.com | RP#65 completed | 36.141, 36.307 | 53 | 27 |  |  | Thu 15/09/11 | Mon 08/09/14
2665 | 530029 | LTE Advanced intra-band non-contiguous CA in Band 25 | LTE_CA_NC_B25 | 2 | Rel-12 | R4 | 2011-09-19 08:00 | 2013-06-14 17:00 | 100% | RP-130179 | - | Sprint | George.Cummings@sprint.com | Intra-band NC | LTE | 53 | 27 |  |  | Thu 15/09/11 | Fri 07/06/13
2666 | 530129 | Core part:LTE Advanced intra-band non-contiguous CA in Band 25 | LTE_CA_NC_B25-Core | 3 | Rel-12 | R4 | 2011-09-19 08:00 | 2013-06-14 17:00 | 100% | RP-130179 | RP-130563 | Sprint | George.Cummings@sprint.com | RP#60 completed. TR 36.841 for 1-step Approval | 36.101, 36.104, 36.133, new TR 36.833-2-25 | 53 | 27 |  |  | Thu 15/09/11 | Fri 07/06/13
2667 | 530229 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 25 | LTE_CA_NC_B25-Perf | 3 | Rel-12 | R4 | 2011-09-19 08:00 | 2013-06-14 17:00 | 100% | RP-130179 | RP-130759 | Sprint | George.Cummings@sprint.com | RP#60 completed | 36.141, 36.307 | 53 | 27 |  |  | Thu 15/09/11 | Mon 10/06/13
2668 | 550010 | Deleted -LTE Advanced inter-band CA of Band 3 and Band 5 with 2UL | LTE_CA_B3_B5_2UL | 2 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-03-01 17:00 | 100% | RP-120867 | - | SK Telecom | Seungpyo Hong | Inter-band 2UL | LTE | 55 | 28 | RP-59 | PCG-30 | Thu 23/02/12 | Mon 29/07/13
2669 | 550110 | Deleted - Core part:LTE Advanced inter-band CA of Band 3 and Band 5 with 2UL | LTE_CA_B3_B5_2UL-Core | 3 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-03-01 17:00 | 100% | RP-120867 | RP-130098 | SK Telecom | Seungpyo Hong | RP#59 stopped (covered by new WI LTE_CA_2UL-A4) | 36.101, 36.104, 36.133, 36.307, new generic TR 36.851 | 55 | 28 | RP-59 | PCG-30 | Thu 23/02/12 | Mon 29/07/13
2670 | 550210 | Deleted - Perf. part:LTE Advanced inter-band CA of Band 3 and Band 5 with 2UL | LTE_CA_B3_B5_2UL-Perf | 3 | Rel-12 | R4 | 2012-03-12 08:00 | 2013-03-01 17:00 | 100% | RP-120867 | RP-130099 | SK Telecom | Seungpyo Hong | RP#59 stopped (covered by new WI LTE_CA_2UL-A4) | 36.133, 36.141 | 55 | 28 | RP-59 | PCG-30 | Thu 23/02/12 | Mon 29/07/13
2671 | 670049 | UE Conformance Test Aspects - Further Rel-12 configurations for LTE Advanced CA with 2UL | LTE_CA_Rel12_2UL-UEConTest | 2 | Rel-12 | R5 | 2015-03-16 08:00 | 2016-12-15 17:00 | 100% | RP-160071 |  | Ericsson | NA | 03/07/15: Compl:0%->29% 03/07/15: Stat Rep: ->RP-150834 29/09/15: Compl:29%->55% 29/09/15: Stat Rep: RP-150834->RP-151166 1/1/16: Compl:55%->70% 1/1/16: CD:Tue 15/12/15->Tue 15/03/16 1/1/16: WID: RP-1; |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 20/12/16
2672 | 550011 | LTE Advanced intra-band non-contiguous CA in Band 3 | LTE_CA_NC_B3 | 2 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-12-06 17:00 | 100% | RP-131359 | - | SK Telecom | haesung.park@sk.com | Intra-band NC | LTE | 55 | 28 |  |  | Thu 23/02/12 | Thu 23/02/12
2673 | 550111 | Core part:LTE Advanced intra-band non-contiguous CA in Band 3 | LTE_CA_NC_B3-Core | 3 | Rel-12 | R4 | 2012-03-05 08:00 | 2013-12-06 17:00 | 100% | RP-131359 | RP-131573 | SK Telecom | haesung.park@sk.com | RP#62 completed | 36.101, 36.104, 36.133, new TR 36.833-2-03 | 55 | 28 |  |  | Thu 23/02/12 | Mon 02/12/13
2674 | 550211 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 3 | LTE_CA_NC_B3-Perf | 3 | Rel-12 | R4 | 2012-03-15 08:00 | 2013-12-06 17:00 | 100% | RP-131359 | RP-131574 | SK Telecom | haesung.park@sk.com | RP#62 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 55 | 28 |  |  | Thu 23/02/12 | Mon 02/12/13
2675 | 560015 | Deleted - LTE Advanced intra-band contiguous CA in Band 1 | LTE_CA_C_B1 | 2 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-06-14 17:00 | 100% | RP-130298 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Intra-band C | LTE | 56 | 29 | RP-60 | PCG-31 | Wed 13/06/12 | Wed 05/06/13
2676 | 560115 | Deleted - Core part: LTE Advanced intra-band contiguous CA in Band 1 | LTE_CA_C_B1-Core | 3 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-06-14 17:00 | 100% | RP-120826 | RP-130549 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#60 stopped at 10% completion (rationale in RP-130670) | 36.101, 36.104, 36.133, 36.141, 36.307, new TR 36.835 | 56 | 29 | RP-60 | PCG-31 | Wed 13/06/12 | Wed 05/06/13
2677 | 560215 | Deleted - Perf. part: LTE Advanced intra-band contiguous CA in Band 1 | LTE_CA_C_B1-Perf | 3 | Rel-12 | R4 | 2012-06-22 08:00 | 2013-06-14 17:00 | 100% | RP-120826 | RP-130550 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#60 stopped at 0% completion | 36.101, 36.104, 36.133, 36.141, 36.307 | 56 | 29 | RP-60 | PCG-31 | Wed 13/06/12 | Wed 05/06/13
2678 | 560016 | LTE Advanced intra-band non-contiguous CA in Band 4 | LTE_CA_NC_B4 | 2 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-131135 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Intra-band NC | LTE | 56 | 29 |  |  | Wed 13/06/12 | Wed 12/06/13
2679 | 560116 | Core part:LTE Advanced intra-band non-contiguous CA in Band 4 | LTE_CA_NC_B4-Core | 3 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-131135 | RP-131039 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed. Updated WID RP-130842=>RP-131135 | 36.101, 36.104, 36.133, new TR 36.833-2-04 | 56 | 29 |  |  | Wed 13/06/12 | Wed 28/08/13
2680 | 560216 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 4 | LTE_CA_NC_B4-Perf | 3 | Rel-12 | R4 | 2012-06-22 08:00 | 2013-09-06 17:00 | 100% | RP-131135 | RP-131040 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed. Updated WID RP-130842=>RP-131135 | 36.101, 36.104, 36.133, 36.141, 36.307 | 56 | 29 |  |  | Wed 13/06/12 | Wed 28/08/13
2681 | 560017 | LTE Advanced inter-band CA of Band 2 and Band 4 | LTE_CA_B2_B4 | 2 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130175 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band 1 UL | LTE | 56 | 29 |  |  | Wed 13/06/12 | Fri 07/09/12
2682 | 560117 | Core part:LTE Advanced inter-band CA of Band 2 and Band 4 | LTE_CA_B2_B4-Core | 3 | Rel-12 | R4 | 2012-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130175 | RP-131007 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 56 | 29 |  |  | Wed 13/06/12 | Wed 28/08/13
2683 | 560217 | Perf. part:LTE Advanced inter-band CA of Band 2 and Band 4 | LTE_CA_B2_B4-Perf | 3 | Rel-12 | R4 | 2012-06-22 08:00 | 2013-09-06 17:00 | 100% | RP-130175 | RP-131376 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#61 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 56 | 29 |  |  | Wed 13/06/12 | Wed 28/08/13
2684 | 570012 | LTE Advanced inter-band CA of Band 23 and Band 29 | LTE_CA_B23_B29 | 2 | Rel-12 | R4 | 2012-09-12 08:00 | 2013-06-14 17:00 | 100% | RP-130170 | - | DISH Network | mariam.sorond@dish.com, johny.kim@dish.com | Inter-band 1 UL | LTE | 57 | 29 |  |  | Mon 03/09/12 | Mon 03/09/12
2685 | 570112 | Core part:LTE Advanced inter-band CA of Band 23 and Band 29 | LTE_CA_B23_B29-Core | 3 | Rel-12 | R4 | 2012-09-12 08:00 | 2013-06-14 17:00 | 100% | RP-130170 | RP-130535 | DISH Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#60 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 57 | 29 |  |  | Mon 03/09/12 | Tue 04/06/13
2686 | 570212 | Perf. part:LTE Advanced inter-band CA of Band 23 and Band 29 | LTE_CA_B23_B29-Perf | 3 | Rel-12 | R4 | 2012-09-12 08:00 | 2013-06-14 17:00 | 100% | RP-130170 | RP-130536 | DISH Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#60 completed | 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Tue 04/06/13
2687 | 570013 | LTE Advanced inter-band CA of Band 3 and Band 26 | LTE_CA_B3_B26 | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130658 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band 1 UL | LTE | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/06/13
2688 | 570113 | Core part:LTE Advanced inter-band CA of Band 3 and Band 26 | LTE_CA_B3_B26-Core | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130658 | RP-130527 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#60 completed. Updated WID RP-130199=>RP-130658 | 36.101, 36.104, 36.133, 36.307, new generic TR 36.851 | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/06/13
2689 | 570213 | Perf. part:LTE Advanced inter-band CA of Band 3 and Band 26 | LTE_CA_B3_B26-Perf | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130658 | RP-130528 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#60 completed. Updated WID RP-130199=>RP-130658 | 36.101, 36.104, 36.133, 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/06/13
2690 | 570014 | LTE Advanced inter-band CA of Band 3 and Band 19 | LTE_CA_B3_B19 | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130198 | - | NTT DOCOMO | Kei ANDO | Inter-band 1 UL | LTE | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/09/12
2691 | 570114 | Core part:LTE Advanced inter-band CA of Band 3 and Band 19 | LTE_CA_B3_B19-Core | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130198 | RP-130525 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 57 | 29 |  |  | Mon 03/09/12 | Sat 08/06/13
2692 | 570214 | Perf. part:LTE Advanced inter-band CA of Band 3 and Band 19 | LTE_CA_B3_B19-Perf | 3 | Rel-12 | R4 | 2012-09-13 08:00 | 2013-06-14 17:00 | 100% | RP-130198 | RP-130526 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Sat 08/06/13
2693 | 570015 | Deleted -LTE Advanced inter-band CA of Band 38 and Band 39 | LTE_CA_B38_B39 | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2012-12-07 17:00 | 100% | RP-121178 | - | China Mobile | Pan Qun (panqun@chinamobile.com) | Inter-band 1 UL | LTE | 57 | 29 | RP-58 | PCG-30 | Mon 03/09/12 | Tue 11/12/12
2694 | 570115 | Deleted - Core part:LTE Advanced inter-band CA of Band 38 and Band 39 | LTE_CA_B38_B39-Core | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2012-12-07 17:00 | 100% | RP-121178 | RP-121624 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#58 stopped at 10% completion following regulatory decisions (see instead new WI LTE_CA_B39_B41) | 36.101, 36.104, 36.307, new generic TR 36.851 | 57 | 29 | RP-58 | PCG-30 | Mon 03/09/12 | Tue 11/12/12
2695 | 570215 | Deleted - Perf. part:LTE Advanced inter-band CA of Band 38 and Band 39 | LTE_CA_B38_B39-Perf | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2012-12-07 17:00 | 100% | RP-121178 | RP-121625 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#58 stopped at 0% completion following regulatory decisions (see instead new WI LTE_CA_B39_B41) | 36.133, 36.141 | 57 | 29 | RP-58 | PCG-30 | Mon 03/09/12 | Tue 11/12/12
2696 | 570016 | LTE Advanced intra-band contiguous CA in Band 3 | LTE_CA_C_B3 | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-131184 | - | China Unicom | Fei CUI (cuifei1@chinaunicom.cn) | Intra-band NC | LTE | 57 | 29 |  |  | Mon 03/09/12 | Thu 29/08/13
2697 | 570116 | Core part: LTE Advanced intra-band contiguous CA in Band 3 | LTE_CA_C_B3-Core | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-131184 | RP-131029 | China Unicom | Fei CUI (cuifei1@chinaunicom.cn) | RP#61 completed. Updated WID RP-130294=>RP-131184 (impacted specs) | 36.101, 36.104, 36.133, new TR 36.833-1-03 | 57 | 29 |  |  | Mon 03/09/12 | Wed 04/09/13
2698 | 570216 | Perf. part: LTE Advanced intra-band contiguous CA in Band 3 | LTE_CA_C_B3-Perf | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-131184 | RP-131030 | China Unicom | Fei CUI (cuifei1@chinaunicom.cn) | RP#61 completed | 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Wed 04/09/13
2699 | 570018 | LTE Advanced inter-band CA of Band 1 and Band 8 | LTE_CA_B1_B8 | 2 | Rel-12 | R4 | 2012-02-02 09:36 | 2013-06-14 17:00 | 100% | RP-130181 | - | Softbank Mobile | Kenichi Kihara | Inter-band 1 UL | LTE | 57 | 29 |  |  | Mon 03/09/12 | Wed 28/11/12
2700 | 570118 | Core part:LTE Advanced inter-band CA of Band 1 and Band 8 | LTE_CA_B1_B8-Core | 3 | Rel-12 | R4 | 2012-02-02 09:36 | 2013-06-14 17:00 | 100% | RP-130181 | RP-130515 | Softbank Mobile | Kenichi Kihara | RP#60 completed | 36.101, 36.104, new generic TR 36.851 | 57 | 29 |  |  | Mon 03/09/12 | Tue 04/06/13
2701 | 570218 | Perf. part:LTE Advanced inter-band CA of Band 1 and Band 8 | LTE_CA_B1_B8-Perf | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130181 | RP-130516 | Softbank Mobile | Kenichi Kihara | RP#60 completed | 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Tue 04/06/13
2702 | 570026 | LTE Advanced inter-band CA of Band 3 and Band 28 | LTE_CA_B3_B28 | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130189 | - | eAccess | FukumotoShiro@eaccess.net | Inter-band 1 UL | LTE | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/09/12
2703 | 570126 | Core part:LTE Advanced inter-band CA of Band 3 and Band 28 | LTE_CA_B3_B28-Core | 3 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-130189 | RP-130529 | eAccess | FukumotoShiro@eaccess.net | RP#60 completed | 36.101, 36.104, new generic TR 36.851 | 57 | 29 |  |  | Mon 03/09/12 | Wed 05/06/13
2704 | 570226 | Perf. part:LTE Advanced inter-band CA of Band 3 and Band 28 | LTE_CA_B3_B28-Perf | 3 | Rel-12 | R4 | 2012-09-12 08:00 | 2013-06-14 17:00 | 100% | RP-130189 | RP-130530 | eAccess | FukumotoShiro@eaccess.net | RP#60 completed | 36.141, 36.307 | 57 | 29 |  |  | Mon 03/09/12 | Wed 05/06/13
2705 | 580032 | LTE Advanced inter-band CA of Band 1 and Band 26 | LTE_CA_B1_B26 | 2 | Rel-12 | R4 | 2012-12-07 08:00 | 2013-09-06 17:00 | 100% | RP-130668 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band 1UL/2DL | LTE | 58 | 30 |  |  | Mon 10/12/12 | Mon 10/12/12
2706 | 580132 | Core part:LTE Advanced inter-band CA of Band 1 and Band 26 | LTE_CA_B1_B26-Core | 3 | Rel-12 | R4 | 2012-12-07 08:00 | 2013-09-06 17:00 | 100% | RP-130668 | RP-131005 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 58 | 30 |  |  | Mon 10/12/12 | Wed 28/08/13
2707 | 580232 | Perf. part:LTE Advanced inter-band CA of Band 1 and Band 26 | LTE_CA_B1_B26-Perf | 3 | Rel-12 | R4 | 2012-12-07 08:00 | 2013-09-06 17:00 | 100% | RP-130668 | RP-131006 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.141, 36.307 | 58 | 30 |  |  | Mon 10/12/12 | Wed 28/08/13
2708 | 580033 | LTE Advanced inter-band CA of Band 39 and Band 41 | LTE_CA_B39_B41 | 2 | Rel-12 | R4 | 2012-12-10 08:00 | 2014-03-06 17:00 | 100% | RP-130292 | RP-140428 | China Mobile | Pan Qun (panqun@chinamobile.com) | Inter-band 2DL | LTE | 58 | 30 |  |  | Mon 10/12/12 | Wed 05/03/14
2709 | 580133 | Core part:LTE Advanced inter-band CA of Band 39 and Band 41 | LTE_CA_B39_B41-Core | 3 | Rel-12 | R4 | 2012-12-10 08:00 | 2014-03-06 17:00 | 100% | RP-130292 | RP-140428 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#63 completed. Replaces the Stopped WI - LTE Advanced inter-band Carrier Aggregation of Band 38 and Band 39 (LTE_CA_B38_B39) UID_570015 | 36.101, 36.104, 36.307, new generic TR 36.851 | 58 | 30 |  |  | Mon 10/12/12 | Wed 05/03/14
2710 | 580233 | Perf. part:LTE Advanced inter-band CA of Band 39 and Band 41 | LTE_CA_B39_B41-Perf | 3 | Rel-12 | R4 | 2012-12-14 08:00 | 2014-03-06 17:00 | 100% | RP-130292 | RP-140428 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#63 completed | 36.133, 36.141 | 58 | 30 |  |  | Mon 10/12/12 | Wed 05/03/14
2711 | 580034 | LTE Advanced inter-band CA of Band 2 and Band 12 | LTE_CA_B2_B12 | 2 | Rel-12 | R4 | 2012-12-10 08:00 | 2014-09-12 17:00 | 100% | RP-140474 | - | US Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 2DL | LTE | 58 | 30 |  |  | Mon 10/12/12 | Mon 08/09/14
2712 | 580134 | Core part:LTE Advanced inter-band CA of Band 2 and Band 12 | LTE_CA_B2_B12-Core | 3 | Rel-12 | R4 | 2012-12-10 08:00 | 2014-09-12 17:00 | 100% | RP-140474 | RP-141084 | US Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.851 | 58 | 30 |  |  | Mon 10/12/12 | Mon 08/09/14
2713 | 580234 | Perf. part:LTE Advanced inter-band CA of Band 2 and Band 12 | LTE_CA_B2_B12-Perf | 3 | Rel-12 | R4 | 2012-12-14 08:00 | 2014-03-06 17:00 | 100% | RP-140474 | RP-140428 | US Cellular | sebastian.thalanany@uscellular.com | RP#63 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 58 | 30 |  |  | Mon 10/12/12 | Tue 04/03/14
2714 | 580035 | LTE Advanced intra-band non-contiguous CA in Band 7 | LTE_CA_NC_B7 | 2 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-130813 | - | Ericsson | christian.bergljung@ericsson.com | Intra-band NC | LTE | 58 | 30 |  |  | Mon 10/12/12 | Thu 28/02/13
2715 | 580135 | Core part:LTE Advanced intra-band non-contiguous CA in Band 7 | LTE_CA_NC_B7-Core | 3 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-130813 | RP-131575 | Ericsson | christian.bergljung@ericsson.com | RP#62 completed | 36.101, 36.104, 36.133, new TR 36.833-2-07 | 58 | 30 |  |  | Mon 10/12/12 | Mon 02/12/13
2716 | 580235 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 7 | LTE_CA_NC_B7-Perf | 3 | Rel-12 | R4 | 2012-12-14 08:00 | 2013-12-06 17:00 | 100% | RP-130813 | RP-131576 | Ericsson | christian.bergljung@ericsson.com | RP#62 completed | 36.141, 36.307 | 58 | 30 |  |  | Mon 10/12/12 | Mon 02/12/13
2717 | 580036 | LTE Advanced intra-band contiguous CA in Band 27 | LTE_CA_C_B27 | 2 | Rel-12 | R4 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-131679 | - | NII Holdings | bill.shvodian@nii.com | Intra-band contig. CA 2DL/1UL | LTE | 58 | 30 |  |  | Mon 10/12/12 | Thu 19/12/13
2718 | 580136 | Core part: LTE Advanced intra-band contiguous CA in Band 27 | LTE_CA_C_B27-Core | 3 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-131679 | RP-131567 | NII Holdings | bill.shvodian@nii.com | RP#62 completed | 36.101, 36.104, new TR 36.833-1-27 | 58 | 30 |  |  | Mon 10/12/12 | Fri 06/12/13
2719 | 580236 | Perf part: LTE Advanced intra-band contiguous CA in Band 27 | LTE_CA_C_B27-Perf | 3 | Rel-12 | R4 | 2012-12-14 08:00 | 2014-06-13 17:00 | 100% | RP-131679 | RP-140569 | NII Holdings | bill.shvodian@nii.com | RP#64 completed. TR 36.833-1-27v200 for Approval | 36.101, 36.133, 36.141, 36.307, new TR 36.833-1-27 | 58 | 30 |  |  | Mon 10/12/12 | Thu 12/06/14
2720 | 590022 | LTE Advanced inter-band CA of Band 2 and Band 13 | LTE_CA_B2_B13 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130196 | - | Ericsson | christian.bergljung@ericsson.com | Inter-band 1 UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
2721 | 590122 | Core part:LTE Advanced inter-band CA of Band 2 and Band 13 | LTE_CA_B2_B13-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130196 | RP-130523 | Ericsson | christian.bergljung@ericsson.com | RP#60 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
2722 | 590222 | Perf. part:LTE Advanced inter-band CA of Band 2 and Band 13 | LTE_CA_B2_B13-Perf | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130196 | RP-130524 | Ericsson | christian.bergljung@ericsson.com | RP#60 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
2723 | 590024 | LTE Advanced inter-band CA of Band 19 and Band 21 | LTE_CA_B19_B21 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130197 | - | NTT DOCOMO | Kei ANDO | Inter-band 1 UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
2724 | 590124 | Core part:LTE Advanced inter-band CA of Band 19 and Band 21 | LTE_CA_B19_B21-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130197 | RP-130533 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 59 | 30 |  |  | Tue 26/02/13 | Sat 08/06/13
2725 | 590224 | Perf. part:LTE Advanced inter-band CA of Band 19 and Band 21 | LTE_CA_B19_B21-Perf | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130197 | RP-130534 | NTT DOCOMO | Kei ANDO | RP#60 completed | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Sat 08/06/13
2726 | 590025 | Deleted -LTE Advanced inter-band CA of Band 8 and Band 26 | LTE_CA_B8_B26 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-130201 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band 1 UL | LTE | 59 | 30 | RP-62 | PCG-32 | Tue 26/02/13 | Tue 26/02/13
2727 | 590125 | Deleted - Core part:LTE Advanced inter-band CA of Band 8 and Band 26 | LTE_CA_B8_B26-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-130201 | RP-131549 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#62 stopped (at 20%) | 36.101, 36.104, 36.133, new generic TR 36.851 | 59 | 30 | RP-62 | PCG-32 | Tue 26/02/13 | Mon 02/12/13
2728 | 590225 | Deleted - Perf. part:LTE Advanced inter-band CA of Band 8 and Band 26 | LTE_CA_B8_B26-Perf | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-130201 | RP-131550 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#62 stopped (at 20%) | 36.141, 36.307 | 59 | 30 | RP-62 | PCG-32 | Tue 26/02/13 | Mon 02/12/13
2729 | 590029 | LTE Advanced dual uplink inter-band CA Class A1 | LTE_CA_2UL-A1 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-15 17:00 | 100% | RP-140475 | - | Huawei | Liu Ye (leo.liuye@huawei.com) | Inter-band CA 2UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 09/09/14
2730 | 590129 | Core part:LTE Advanced dual uplink inter-band CA Class A1 | LTE_CA_2UL-A1-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-15 17:00 | 100% | RP-141941 | RP-141732 | Huawei | Liu Ye (leo.liuye@huawei.com) | ; WID: RP-142043->RP-141941; Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, New generic TR 36.860 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
2731 | 590229 | Perf. part:LTE Advanced dual uplink inter-band CA Class A1 | LTE_CA_2UL-A1-Perf | 3 | Rel-12 | R4 | 2013-03-13 08:00 | 2014-12-15 17:00 | 100% | RP-141941 | RP-141732 | Huawei | Liu Ye (leo.liuye@huawei.com) | ; WID: RP-142043->RP-141941; Stat Rep: RP-141084->RP-141732 | 36.133 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
2732 | 590028 | LTE Advanced dual uplink inter-band CA Class A2 | LTE_CA_2UL-A2 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-15 17:00 | 100% | RP-130327 | - | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | Inter-band CA 2UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 09/09/14
2733 | 590128 | Core part:LTE Advanced dual uplink inter-band CA Class A2 | LTE_CA_2UL-A2-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-15 17:00 | 100% | RP-130327 | RP-141732 | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | ; Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, New generic TR 36.860 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
2734 | 590228 | Perf. part:LTE Advanced dual uplink inter-band CA Class A2 | LTE_CA_2UL-A2-Perf | 3 | Rel-12 | R4 | 2013-03-13 08:00 | 2014-12-15 17:00 | 100% | RP-130327 | RP-141732 | Qualcomm | Gene Fong (gfong@qti.qualcomm.com) | ; Stat Rep: RP-141084->RP-141732 | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
2735 | 590023 | LTE Advanced dual uplink inter-band CA Class A3 | LTE_CA_2UL-A3 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-15 17:00 | 100% | RP-140853 | - | Ericsson | christian.bergljung@ericsson.com | Inter-band CA 2UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 09/09/14
2736 | 590123 | Core part:LTE Advanced dual uplink inter-band CA Class A3 | LTE_CA_2UL-A3-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-15 17:00 | 100% | RP-140853 | RP-141732 | Ericsson | christian.bergljung@ericsson.com | ; Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, New generic TR 36.860 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
2737 | 590223 | Perf. part:LTE Advanced dual uplink inter-band CA Class A3 | LTE_CA_2UL-A3-Perf | 3 | Rel-12 | R4 | 2013-03-13 08:00 | 2014-12-15 17:00 | 100% | RP-140853 | RP-141732 | Ericsson | christian.bergljung@ericsson.com | ; Stat Rep: RP-141084->RP-141732 | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
2738 | 590031 | LTE Advanced dual uplink inter-band CA Class A4 | LTE_CA_2UL-A4 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-15 17:00 | 100% | RP-141160 | - | Nokia | petri.j.vasenkari@nokia.com | Inter-band CA 2UL. RP#65 updated WID RP-140476=>RP-141160. | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 09/09/14
2739 | 590131 | Core part:LTE Advanced dual uplink inter-band CA Class A4 | LTE_CA_2UL-A4-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-15 17:00 | 100% | RP-141967 | RP-141732 | Nokia | petri.j.vasenkari@nokia.com | ; WID: RP-142043->RP-141967; Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, New generic TR 36.860 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
2740 | 590231 | Perf. part:LTE Advanced dual uplink inter-band CA Class A4 | LTE_CA_2UL-A4-Perf | 3 | Rel-12 | R4 | 2013-03-13 08:00 | 2014-12-15 17:00 | 100% | RP-141967 | RP-141732 | Nokia | petri.j.vasenkari@nokia.com | ; WID: RP-142043->RP-141967; Stat Rep: RP-141084->RP-141732 | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
2741 | 590026 | LTE Advanced dual uplink inter-band CA Class A5 | LTE_CA_2UL-A5 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-15 17:00 | 100% | RP-141195 | - | NTT DOCOMO | kei.andou.ye@nttdocomo.com | Inter-band CA 2UL. RP#65 updated WID RP-131146=>RP-141195. Changed Rapp Renesas=>Broadcom=>NTT DOCOMO | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 09/09/14
2742 | 590126 | Core part:LTE Advanced dual uplink inter-band CA Class A5 | LTE_CA_2UL-A5-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-15 17:00 | 100% | RP-141195 | RP-141732 | NTT DOCOMO | kei.andou.ye@nttdocomo.com | ; Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, New generic TR 36.860 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
2743 | 590226 | Perf. part:LTE Advanced dual uplink inter-band CA Class A5 | LTE_CA_2UL-A5-Perf | 3 | Rel-12 | R4 | 2013-03-13 08:00 | 2014-12-15 17:00 | 100% | RP-141195 | RP-141732 | NTT DOCOMO | kei.andou.ye@nttdocomo.com | ; Stat Rep: RP-141084->RP-141732 | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
2744 | 590027 | LTE Advanced intra-band contiguous CA in Band 39 | LTE_CA_C_B39 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-03-06 17:00 | 100% | RP-131171 | - | China Mobile | Li Nan (linan@chinamobile.com) | Intra-band C 2DL/2UL | LTE | 59 | 30 |  |  | Tue 26/02/13 | Tue 26/02/13
2745 | 590127 | Core part: LTE Advanced intra-band contiguous CA in Band 39 | LTE_CA_C_B39-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-03-06 17:00 | 100% | RP-131171 | RP-140428 | China Mobile | Li Nan (linan@chinamobile.com) | RP#63 completed | 36.101, 36.104, 36.133, New TR 36.833-1-39 [instead of 36.845] | 59 | 30 |  |  | Tue 26/02/13 | Wed 05/03/14
2746 | 590227 | Perf. part: LTE Advanced intra-band contiguous CA in Band 39 | LTE_CA_C_B39-Perf | 3 | Rel-12 | R4 | 2013-03-07 08:00 | 2014-03-06 17:00 | 100% | RP-131171 | RP-140428 | China Mobile | Li Nan (linan@chinamobile.com) | RP#63 completed | 36.141, 36.307 | 59 | 30 |  |  | Tue 26/02/13 | Wed 05/03/14
2747 | 600022 | LTE Advanced intra-band non-contiguous CA: framework requirements for 2UL | LTE_CA_NC_2UL | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140267 | - | Nokia | petri.j.vasenkari@nokia.com | Intra-band non-contig. CA 2DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Tue 09/09/14
2748 | 600122 | Core part:LTE Advanced intra-band non-contiguous CA: framework requirements for 2UL | LTE_CA_NC_2UL-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-141962 | RP-141732 | Nokia | petri.j.vasenkari@nokia.com | ; WID: RP-142043->RP-141962; Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, 36.306, 36.331, New TR 36.833-4 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
2749 | 600023 | Deleted -LTE Advanced intra-band non-contiguous CA in Band 41 for 2UL | LTE_CA_NC_B41_2UL | 2 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-03-06 17:00 | 100% | RP-131237 | RP-140428 | Sprint | yang.xu@clearwire.com | Intra-band NC 2UL | LTE | 60 | 31 | RP-63 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
2750 | 600123 | Deleted - Core part:LTE Advanced intra-band non-contiguous CA in Band 41 for 2UL | LTE_CA_NC_B41_2UL-Core | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-03-06 17:00 | 100% | RP-131237 | RP-140428 | Sprint | yang.xu@clearwire.com | RP#63 stopped (5% complete). Reason: Market conditions have eliminated the need for this feature, at least for the foreseeable future | 36.101, 36.104, 36.133, new TR 36.833-3-41 | 60 | 31 | RP-63 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
2751 | 600223 | Deleted - Perf. part:LTE Advanced intra-band non-contiguous CA in Band 41 for 2UL | LTE_CA_NC_B41_2UL-Perf | 3 | Rel-12 | R4 | 2013-06-20 08:00 | 2014-03-06 17:00 | 100% | RP-131237 | RP-140428 | Sprint | yang.xu@clearwire.com | RP#63 stopped (0% complete). | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 | RP-63 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
2752 | 600024 | LTE Advanced intra-band non-contiguous CA in Band 4 for 2UL | LTE_CA_NC_B4_2UL | 2 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-12-15 17:00 | 100% | RP-131136 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Intra-band non-contig. CA 2DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Tue 09/09/14
2753 | 600124 | Core part:LTE Advanced intra-band non-contiguous CA in Band 4 for 2UL | LTE_CA_NC_B4_2UL-Core | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-12-15 17:00 | 100% | RP-141784 | RP-141732 | T-Mobile USA | nelson.ueng@t-mobile.com | ; WID: RP-142043->RP-141784; Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, new TR 36.833-4-04 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
2754 | 600224 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 4 for 2UL | LTE_CA_NC_B4_2UL-Perf | 3 | Rel-12 | R4 | 2013-06-25 08:00 | 2014-12-15 17:00 | 100% | RP-141784 | RP-141732 | T-Mobile USA | nelson.ueng@t-mobile.com | ; WID: RP-142043->RP-141784; Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
2755 | 600025 | LTE Advanced intra-band contiguous CA in Band 23 | LTE_CA_C_B23 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131265 | - | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | Intra-band C CA | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 17/06/13
2756 | 600125 | Core part: LTE Advanced intra-band contiguous CA in Band 23 | LTE_CA_C_B23-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131265 | RP-131565 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#62 completed | 36.101, 36.104, 36.133, new TR 36.833-1-23 [instead of 36.864] | 60 | 31 |  |  | Mon 17/06/13 | Mon 02/12/13
2757 | 600225 | Perf. part: LTE Advanced intra-band contiguous CA in Band 23 | LTE_CA_C_B23-Perf | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131265 | RP-131566 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#62 completed | 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 02/12/13
2758 | 600026 | LTE Advanced intra-band non-contiguous CA in Band 23 | LTE_CA_NC_B23 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-06-13 17:00 | 100% | RP-131700 | - | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | Intra-band non-contig. CA 2DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Thu 19/12/13
2759 | 600126 | Core part:LTE Advanced intra-band non-contiguous CA in Band 23 | LTE_CA_NC_B23-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131700 | RP-131577 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#62 completed | 36.101, 36.104, 36.133, new TR 36.833-2-23 | 60 | 31 |  |  | Mon 17/06/13 | Thu 19/12/13
2760 | 600226 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 23 | LTE_CA_NC_B23-Perf | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-06-13 17:00 | 100% | RP-131700 | RP-140569 | Dish Network | mariam.sorond@dish.com, johny.kim@dish.com | RP#64 completed. TR 36.833-2-23v200 for Approval | 36.101, 36.133, 36.141, 36.307, new TR 36.833-2-23 | 60 | 31 |  |  | Mon 17/06/13 | Thu 12/06/14
2761 | 600028 | LTE Advanced inter-band CA of Band 12 and Band 25 | LTE_CA_B12_B25 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131159 | - | US Cellular | sebastian.thalanany@uscellular.com | Inter-band 1UL/2DL | LTE | 60 | 31 |  |  | Wed 05/06/13 | Mon 17/06/13
2762 | 600128 | Core part:LTE Advanced inter-band CA of Band 12 and Band 25 | LTE_CA_B12_B25-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131159 | RP-131705 | US Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 60 | 31 |  |  | Wed 05/06/13 | Mon 02/12/13
2763 | 600228 | Perf. part:LTE Advanced inter-band CA of Band 12 and Band 25 | LTE_CA_B12_B25-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2013-12-06 17:00 | 100% | RP-131159 | RP-131706 | US Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.141, 36.307 | 60 | 31 |  |  | Wed 05/06/13 | Mon 02/12/13
2764 | 600029 | LTE Advanced inter-band CA of Band 1 and Band 18 - Additional bandwidth combination set | LTE_CA_B1_B18_BWset | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130669 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band 1UL/2DL | LTE | 60 | 31 |  |  | Wed 05/06/13 | Mon 17/06/13
2765 | 600129 | Core part:LTE Advanced inter-band CA of Band 1 and Band 18 - Additional bandwidth combination set | LTE_CA_B1_B18_BWset-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130669 | RP-131003 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.101, new generic TR 36.851 | 60 | 31 |  |  | Wed 05/06/13 | Wed 28/08/13
2766 | 600229 | Perf. part:LTE Advanced inter-band CA of Band 1 and Band 18 - Additional bandwidth combination set | LTE_CA_B1_B18_BWset-Perf | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130669 | RP-131004 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#61 completed | 36.307 | 60 | 31 |  |  | Wed 05/06/13 | Wed 28/08/13
2767 | 600030 | LTE Advanced inter-band CA of Band 2 and Band 5 | LTE_CA_B2_B5 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130675 | - | AT&T | marc.grant@att.com | Inter-band 2DL | LTE | 60 | 31 |  |  | Wed 05/06/13 | Mon 17/06/13
2768 | 600130 | Core part:LTE Advanced inter-band CA of Band 2 and Band 5 | LTE_CA_B2_B5-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130675 | RP-131009 | AT&T | marc.grant@att.com | RP#61 completed | 36.101, 36.104, 36.307 | 60 | 31 |  |  | Wed 05/06/13 | Fri 30/08/13
2769 | 600230 | Perf. part:LTE Advanced inter-band CA of Band 2 and Band 5 | LTE_CA_B2_B5-Perf | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-09-06 17:00 | 100% | RP-130675 | RP-131010 | AT&T | marc.grant@att.com | RP#61 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Wed 05/06/13 | Fri 30/08/13
2770 | 600031 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 5 and Band 30 | LTE_CA_B2_B5_B30 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 100% | RP-131696 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2771 | 600131 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 5 and Band 30 | LTE_CA_B2_B5_B30-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 100% | RP-131696 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. TR 36.853v200 for Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2772 | 600231 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 5 and Band 30 | LTE_CA_B2_B5_B30-Perf | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 100% | RP-131696 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2773 | 600032 | Deleted -LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 17 and Band 30 | LTE_CA_B2_B17_B30 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131130 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
2774 | 600132 | Deleted - Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 17 and Band 30 | LTE_CA_B2_B17_B30-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131130 | RP-131590 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131652 discussion | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
2775 | 600232 | Deleted - Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 17 and Band 30 | LTE_CA_B2_B17_B30-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2013-12-06 17:00 | 100% | RP-131130 | RP-131591 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131652 discussion | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
2776 | 600033 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 29 and Band 30 | LTE_CA_B2_B29_B30 | 2 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 100% | RP-141212 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2777 | 600133 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 29 and Band 30 | LTE_CA_B2_B29_B30-Core | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 100% | RP-141212 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. Updated WID RP-131697=>RP-141212 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2778 | 600233 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 29 and Band 30 | LTE_CA_B2_B29_B30-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 100% | RP-141212 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2779 | 600034 | LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 5 and Band 30 | LTE_CA_B4_B5_B30 | 2 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 100% | RP-141213 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2780 | 600134 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 5 and Band 30 | LTE_CA_B4_B5_B30-Core | 3 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 100% | RP-141213 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. Updated WID RP-131698=>RP-141213 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2781 | 600234 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 5 and Band 30 | LTE_CA_B4_B5_B30-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 100% | RP-141213 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2782 | 600035 | Deleted -LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 17 and Band 30 | LTE_CA_B4_B17_B30 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131133 | - | AT&T | marc.grant@att.com | Inter-band 3DL | LTE | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Mon 17/06/13
2783 | 600135 | Deleted - Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 17 and Band 30 | LTE_CA_B4_B17_B30-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-131133 | RP-131598 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131653 discussion | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
2784 | 600235 | Deleted - Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 17 and Band 30 | LTE_CA_B4_B17_B30-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2013-12-06 17:00 | 100% | RP-131133 | RP-131599 | AT&T | marc.grant@att.com | RP#62 stopped (25% complete) following RP-131653 discussion | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 | RP-62 | PCG-32 | Mon 17/06/13 | Wed 05/03/14
2785 | 600036 | LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 29 and Band 30 | LTE_CA_B4_B29_B30 | 2 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 100% | RP-141215 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2786 | 600136 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 29 and Band 30 | LTE_CA_B4_B29_B30-Core | 3 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 100% | RP-141215 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. Updated WID RP-131699=>RP- 141215 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2787 | 600236 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 29 and Band 30 | LTE_CA_B4_B29_B30-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 100% | RP-141215 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Mon 08/09/14
2788 | 600037 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4 and Band 13 | LTE_CA_B2_B4_B13 | 2 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 100% | RP-141434 | - | Verizon | zheng.zhao@verizonwireless.com | Inter-band CA 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
2789 | 600137 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4 and Band 13 | LTE_CA_B2_B4_B13-Core | 3 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 100% | RP-141434 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed. Updated RP-131684=>RP-141434 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
2790 | 600237 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4 and Band 13 | LTE_CA_B2_B4_B13-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 100% | RP-141434 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
2791 | 600038 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 2 and Band 13 | LTE_CA_B2_B2_B13 | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 100% | RP-141435 | - | Verizon | zheng.zhao@verizonwireless.com | Inter-band CA 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
2792 | 600138 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 2 and Band 13 | LTE_CA_B2_B2_B13-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-09-12 17:00 | 100% | RP-141435 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed. Updated WID RP-131682=>RP-141435 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
2793 | 600238 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 2 and Band 13 | LTE_CA_B2_B2_B13-Perf | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-09-12 17:00 | 100% | RP-141435 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
2794 | 600039 | LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 13 | LTE_CA_B4_B4_B13 | 2 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 100% | RP-141433 | - | Verizon | zheng.zhao@verizonwireless.com | Inter-band CA 3DL | LTE | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
2795 | 600139 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 13 | LTE_CA_B4_B4_B13-Core | 3 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 100% | RP-141433 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed. Updated WID RP-131683=>RP-141433 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
2796 | 600239 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 13 | LTE_CA_B4_B4_B13-Perf | 3 | Rel-12 | R4 | 2013-06-14 08:00 | 2014-09-12 17:00 | 100% | RP-141433 | RP-141084 | Verizon | zheng.zhao@verizonwireless.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 60 | 31 |  |  | Mon 17/06/13 | Sun 21/09/14
2797 | 610017 | LTE Advanced inter-band CA of Band 7 and Band 28 | LTE_CA_B7_B28 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131307 | - | Huawei | Liehai Liu (liuliehai@huawei.com) | Inter-band 1UL/2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
2798 | 610117 | Core part:LTE Advanced inter-band CA of Band 7 and Band 28 | LTE_CA_B7_B28-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131307 | RP-131545 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#62 completed | 36.101, 36.104, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Sat 07/09/13
2799 | 610217 | Perf. part:LTE Advanced inter-band CA of Band 7 and Band 28 | LTE_CA_B7_B28-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131307 | RP-131546 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#62 completed | 36.141 | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
2800 | 610018 | LTE Advanced inter-band CA of Band 5 and Band 25 | LTE_CA_B5_B25 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131343 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band 1UL/2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
2801 | 610118 | Core part:LTE Advanced inter-band CA of Band 5 and Band 25 | LTE_CA_B5_B25-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131343 | RP-131543 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
2802 | 610218 | Perf. part:LTE Advanced inter-band CA of Band 5 and Band 25 | LTE_CA_B5_B25-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131343 | RP-131705 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#62 completed | 36.141, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
2803 | 610019 | LTE Advanced inter-band CA of Band 1 and Band 11 | LTE_CA_B1_B11 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-131354 | - | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | Inter-band CA 2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
2804 | 610119 | Core part:LTE Advanced inter-band CA of Band 1 and Band 11 | LTE_CA_B1_B11-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-131354 | RP-140569 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | RP#64 completed | 36.101, 36.104, new generic TR 36.851 | 61 | 31 |  |  | Sat 07/09/13 | Fri 20/06/14
2805 | 610219 | Perf. part:LTE Advanced inter-band CA of Band 1 and Band 11 | LTE_CA_B1_B11-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-131354 | RP-140569 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | RP#64 completed | 36.141, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Fri 20/06/14
2806 | 610020 | LTE Advanced inter-band CA of Band 8 and Band 11 | LTE_CA_B8_B11 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 100% | RP-131355 | - | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | Inter-band CA 2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 08/09/14
2807 | 610120 | Core part:LTE Advanced inter-band CA of Band 8 and Band 11 | LTE_CA_B8_B11-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 100% | RP-131355 | RP-141084 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | RP#65 completed | 36.101, 36.104, new generic TR 36.851 | 61 | 31 |  |  | Sat 07/09/13 | Mon 08/09/14
2808 | 610220 | Perf. part:LTE Advanced inter-band CA of Band 8 and Band 11 | LTE_CA_B8_B11-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 100% | RP-131355 | RP-141084 | SoftBank Mobile | kenichi.kihara@g.softbank.co.jp | RP#65 completed | 36.141, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Mon 08/09/14
2809 | 610021 | LTE Advanced inter-band CA of Band 5 and Band 7 | LTE_CA_B5_B7 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-02 17:00 | 100% | RP-131365 | - | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | Inter-band 1UL/2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
2810 | 610121 | Core part:LTE Advanced inter-band CA of Band 5 and Band 7 | LTE_CA_B5_B7-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-02 17:00 | 100% | RP-131365 | RP-131541 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#62 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
2811 | 610221 | Perf. part:LTE Advanced inter-band CA of Band 5 and Band 7 | LTE_CA_B5_B7-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2013-12-02 17:00 | 100% | RP-131365 | RP-131542 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#62 completed | 36.141, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Mon 02/12/13
2812 | 610022 | LTE Advanced intra-band contiguous CA in Band 41 for 3DL | LTE_CA_C_B41_3DL | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2015-03-13 17:00 | 100% | RP-140100 | - | Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | Intra-band contig. CA 3DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Mon 08/09/14
2813 | 610122 | Core part: LTE Advanced intra-band contiguous CA in Band 41 for 3DL | LTE_CA_C_B41_3DL-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-09-12 17:00 | 100% | RP-140100 | RP-141084 | Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | RP#65 completed | 36.101, 36.104, 36.133, 36.307, New TR 36.833-5-41 | 61 | 31 |  |  | Sat 07/09/13 | Mon 08/09/14
2814 | 610222 | Perf. part: LTE Advanced intra-band contiguous CA in Band 41 for 3DL | LTE_CA_C_B41_3DL-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2015-03-13 17:00 | 100% | RP-142017 | RP-150013 | Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | ; WID: RP-142043->RP-142017; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: Stat Rep: RP-141732->RP-150013 | 36.141 | 61 | 31 |  |  | Sat 07/09/13 | Wed 01/04/15
2815 | 610023 | LTE Advanced intra-band non-contiguous CA in Band 2 | LTE_CA_NC_B2 | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-131366 | - | Ericsson | imadur.rahman@ericsson.com | Intra-band non-contig. CA 2DL | LTE | 61 | 31 |  |  | Sat 07/09/13 | Sat 07/09/13
2816 | 610123 | Core part:LTE Advanced intra-band non-contiguous CA in Band 2 | LTE_CA_NC_B2-Core | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-131366 | RP-140569 | Ericsson | imadur.rahman@ericsson.com | RP#64 completed. TR 36.833-2-02v100 for 1-step Approval | 36.101, 36.104, 36.133, New TR 36.833-2-02 | 61 | 31 |  |  | Sat 07/09/13 | Thu 12/06/14
2817 | 610223 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 2 | LTE_CA_NC_B2-Perf | 3 | Rel-12 | R4 | 2013-09-10 08:00 | 2014-06-13 17:00 | 100% | RP-131366 | RP-140569 | Ericsson | imadur.rahman@ericsson.com | RP#64 completed | 36.141, 36.307 | 61 | 31 |  |  | Sat 07/09/13 | Thu 12/06/14
2818 | 620018 | LTE Advanced inter-band CA of Band 1 and Band 3 | LTE_CA_B1_B3 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-132022 | - | China Unicom | Hao Chen (chenhao49@chinaunicom.cn) | Inter-band CA 2DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Sat 07/12/13
2819 | 620118 | Core part:LTE Advanced inter-band CA of Band 1 and Band 3 | LTE_CA_B1_B3-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-132022 | RP-141084 | China Unicom | Hao Chen (chenhao49@chinaunicom.cn) | RP#65 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2820 | 620218 | Perf. part:LTE Advanced inter-band CA of Band 1 and Band 3 | LTE_CA_B1_B3-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-132022 | RP-141084 | China Unicom | Hao Chen (chenhao49@chinaunicom.cn) | RP#65 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2821 | 620019 | LTE Advanced inter-band CA of Band 1 and Band 28 | LTE_CA_B1_B28 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-15 17:00 | 100% | RP-132028 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 2DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 09/09/14
2822 | 620119 | Core part:LTE Advanced inter-band CA of Band 1 and Band 28 | LTE_CA_B1_B28-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-15 17:00 | 100% | RP-141803 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ; WID: RP-142043->RP-141803; Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, 36.307, new generic TR 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Mon 12/01/15
2823 | 620219 | Perf. part:LTE Advanced inter-band CA of Band 1 and Band 28 | LTE_CA_B1_B28-Perf | 3 | Rel-12 | R4 | 2013-12-12 08:00 | 2014-12-15 17:00 | 100% | RP-141803 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ; WID: RP-142043->RP-141803; Stat Rep: RP-141084->RP-141732 | 36.133, 36.141 | 62 | 32 |  |  | Sat 07/12/13 | Mon 12/01/15
2824 | 620020 | LTE Advanced inter-band CA of Band 2 and Band 4 - Additional bandwidth combination set | LTE_CA_B2_B4_BWset | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-131656 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band 2DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 04/03/14
2825 | 620120 | Core part:LTE Advanced inter-band CA of Band 2 and Band 4 - Additional bandwidth combination set | LTE_CA_B2_B4_BWset-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-131656 | RP-140428 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#63 completed | 36.101, new generic TR 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Tue 04/03/14
2826 | 620220 | Perf. part:LTE Advanced inter-band CA of Band 2 and Band 4 - Additional bandwidth combination set | LTE_CA_B2_B4_BWset-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-131656 | RP-140428 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#63 completed | 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Tue 04/03/14
2827 | 620021 | LTE Advanced inter-band CA of Band 4 and Band 27 | LTE_CA_B4_B27 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140142 | - | NII Holdings | bill.shvodian@nii.com | Inter-band CA 2DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Thu 13/03/14
2828 | 620121 | Core part:LTE Advanced inter-band CA of Band 4 and Band 27 | LTE_CA_B4_B27-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140142 | RP-140569 | NII Holdings | bill.shvodian@nii.com | RP#64 completed | 36.101, 36.104, 36.133, new generic TR 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Fri 20/06/14
2829 | 620221 | Perf. part:LTE Advanced inter-band CA of Band 4 and Band 27 | LTE_CA_B4_B27-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140142 | RP-140569 | NII Holdings | bill.shvodian@nii.com | RP#64 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Fri 20/06/14
2830 | 620022 | LTE Advanced inter-band CA of Band 3 and Band 27 | LTE_CA_B3_B27 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-140119 | RP-140428 | KT | Chungwoo HWANG (cwhwang@kt.com) | Inter-band CA 2DL/1UL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Thu 13/03/14
2831 | 620122 | Core part:LTE Advanced inter-band CA of Band 3 and Band 27 | LTE_CA_B3_B27-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-140119 | RP-140428 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#63 completed. Updated WID RP-131752=>RP-140119 | 36.101, 36.104, 36.133, 36.307, New generic TR 36.851 | 62 | 32 |  |  | Sat 07/12/13 | Thu 13/03/14
2832 | 620222 | Perf. part:LTE Advanced inter-band CA of Band 3 and Band 27 | LTE_CA_B3_B27-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-140119 | RP-140428 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#63 completed. Updated WID RP-131752=>RP-140119 | 36.101, 36.104, 36.133, 36.141 | 62 | 32 |  |  | Sat 07/12/13 | Thu 13/03/14
2833 | 620072 | LTE Advanced inter-band CA in Band 8 and Band 20 - Additional channel bandwidth | LTE_CA_B8_B20_BW | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-132118 | RP-140428 | Vodafone | luis.anaya@vodafone.com | Inter-band 2DL | LTE | 62 | 32 |  |  | Mon 09/12/13 | Wed 05/03/14
2834 | 620172 | Core part:LTE Advanced inter-band CA in Band 8 and Band 20 - Additional channel bandwidth | LTE_CA_B8_B20_BW-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-132118 | RP-140428 | Vodafone | luis.anaya@vodafone.com | RP#63 completed | 36.101, 36.104, 36.307 | 62 | 32 |  |  | Mon 09/12/13 | Wed 05/03/14
2835 | 620272 | Perf. part:LTE Advanced inter-band CA in Band 8 and Band 20 - Additional channel bandwidth | LTE_CA_B8_B20_BW-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-03-06 17:00 | 100% | RP-132118 | RP-140428 | Vodafone | luis.anaya@vodafone.com | RP#63 completed | 36.141 | 62 | 32 |  |  | Mon 09/12/13 | Wed 05/03/14
2836 | 620024 | LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 3 and Band 8 | LTE_CA_B1_B3_B8 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141654 | - | KT | Ilwhan Kim (ilwhan.kim@kt.com) | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
2837 | 620124 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 3 and Band 8 | LTE_CA_B1_B3_B8-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141654 | RP-141084 | KT | Ilwhan Kim (ilwhan.kim@kt.com) | RP#65 completed. Updated WID RP-131753=>RP-141654 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
2838 | 620224 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 3 and Band 8 | LTE_CA_B1_B3_B8-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141654 | RP-141084 | KT | Ilwhan Kim (ilwhan.kim@kt.com) | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
2839 | 620025 | LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 5 and Band 7 | LTE_CA_B1_B5_B7 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141462 | - | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
2840 | 620125 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 5 and Band 7 | LTE_CA_B1_B5_B7-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141462 | RP-141084 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#65 completed. Updated WID RP-140209=>RP-141462 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
2841 | 620225 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 5 and Band 7 | LTE_CA_B1_B5_B7-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141462 | RP-141084 | LG Uplus | Yeonsang KOO (yskoo@lguplus.co.kr) | RP#65 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 22/09/14
2842 | 620026 | LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 4 and Band 5 | LTE_CA_B2_B4_B5 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-140186 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2843 | 620126 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 4 and Band 5 | LTE_CA_B2_B4_B5-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-140186 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2844 | 620226 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 4 and Band 5 | LTE_CA_B2_B4_B5-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-140186 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2845 | 620027 | LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 100% | RP-140189 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Tue 09/09/14
2846 | 620127 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-140189 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Tue 30/09/14
2847 | 620227 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 100% | RP-140189 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completion 09/14=>12/14 | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Fri 12/09/14
2848 | 620028 | LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 5 and Band 12 | LTE_CA_B2_B5_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-140190 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2849 | 620128 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 5 and Band 12 | LTE_CA_B2_B5_B12-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-140190 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2850 | 620228 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 5 and Band 12 | LTE_CA_B2_B5_B12-Perf | 3 | Rel-12 | R4 | 2013-12-10 08:00 | 2014-09-12 17:00 | 100% | RP-140190 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2851 | 620029 | LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 12 and Band 12 | LTE_CA_B2_B12_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-131654 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2852 | 620129 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 12 and Band 12 | LTE_CA_B2_B12_B12-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-131654 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2853 | 620229 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 12 and Band 12 | LTE_CA_B2_B12_B12-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-131654 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2854 | 620030 | LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 12 and Band 30 | LTE_CA_B2_B12_B30 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141211 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2855 | 620130 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 12 and Band 30 | LTE_CA_B2_B12_B30-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141211 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. Updated WID RP-131652=>RP-141211. | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2856 | 620230 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 2, Band 12 and Band 30 | LTE_CA_B2_B12_B30-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141211 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2857 | 620031 | LTE Advanced 3 Band CA (3DL/1UL) for Band 3, Band 7 and Band 20 | LTE_CA_B3_B7_B20 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141224 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Sun 21/09/14
2858 | 620131 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 3, Band 7 and Band 20 | LTE_CA_B3_B7_B20-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141224 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed. Updated WID RP-140244=>RP-141224 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Sun 21/09/14
2859 | 620231 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 3, Band 7 and Band 20 | LTE_CA_B3_B7_B20-Perf | 3 | Rel-12 | R4 | 2013-12-10 08:00 | 2014-09-12 17:00 | 100% | RP-141224 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Sun 21/09/14
2860 | 620033 | LTE Advanced 3 Band CA (3DL/1UL) for Band 4, Band 5 and Band 12 | LTE_CA_B4_B5_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-140191 | - | U.S. Cellular | sebastian.thalanany@uscellular.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2861 | 620133 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 4, Band 5 and Band 12 | LTE_CA_B4_B5_B12-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-140191 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2862 | 620233 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 4, Band 5 and Band 12 | LTE_CA_B4_B5_B12-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-140191 | RP-141084 | U.S. Cellular | sebastian.thalanany@uscellular.com | RP#65 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2863 | 620034 | LTE Advanced 3 Band CA (3DL/1UL) for Band 4, Band 12 and Band 12 | LTE_CA_B4_B12_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-131655 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2864 | 620134 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 4, Band 12 and Band 12 | LTE_CA_B4_B12_B12-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-131655 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2865 | 620234 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 4, Band 12 and Band 12 | LTE_CA_B4_B12_B12-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-131655 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2866 | 620035 | LTE Advanced 3 Band CA (3DL/1UL) for Band 4, Band 12 and Band 30 | LTE_CA_B4_B12_B30 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141214 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2867 | 620135 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 4, Band 12 and Band 30 | LTE_CA_B4_B12_B30-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141214 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed. Updated WID RP-131653=>RP-141214 | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2868 | 620235 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 4, Band 12 and Band 30 | LTE_CA_B4_B12_B30-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141214 | RP-141084 | AT&T | marc.grant@att.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2869 | 620037 | LTE Advanced intra-band contiguous CA in Band 42 | LTE_CA_C_B42 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140728 | - | CATT | Yuexia Song (songyuexia@catt.cn) | Intra-band contig. CA 2DL/2UL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Sat 07/12/13
2870 | 620137 | Core part: LTE Advanced intra-band contiguous CA in Band 42 | LTE_CA_C_B42-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140728 | RP-140569 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728 | 36.101, 36.104, 36.133, new TR 36.833-1-42 | 62 | 32 |  |  | Sat 07/12/13 | Thu 12/06/14
2871 | 620237 | Perf. part: LTE Advanced intra-band contiguous CA in Band 42 | LTE_CA_C_B42-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140728 | RP-140569 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#64 completed. TR 36.833-1-42v100 for 1-step Approval. Updated WID RP-132029=>RP-140728 | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Thu 12/06/14
2872 | 620036 | LTE Advanced intra-band contiguous CA in Band 7 - Additional bandwidth combinations | LTE_CA_C_B7_BW | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-131810 | - | Orange | Olfa BEN HADDADA | Intra-band contig. CA 2DL/2UL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Sat 07/12/13
2873 | 620136 | Core part: LTE Advanced intra-band contiguous CA in Band 7 - Additional bandwidth combinations | LTE_CA_C_B7_BW-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-131810 | RP-140569 | Orange | Olfa BEN HADDADA | RP#64 completed | 36.101, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Fri 20/06/14
2874 | 620236 | Perf. part: LTE Advanced intra-band contiguous CA in Band 7 - Additional bandwidth combinations | LTE_CA_C_B7_BW-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-131810 | RP-140569 | Orange | Olfa BEN HADDADA | RP#64 completed | 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Fri 20/06/14
2875 | 620038 | LTE Advanced intra-band non-contiguous CA in Band 41 for 3 DL | LTE_CA_NC_B41_3DL | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2015-03-13 17:00 | 100% | RP-140101 | - | Sprint, Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | Intra-band non-contig. CA 3DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2876 | 620138 | Core part:LTE Advanced intra-band non-contiguous CA in Band 41 for 3 DL | LTE_CA_NC_B41_3DL-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-11 17:00 | 100% | RP-140101 | RP-141084 | Sprint, Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | RP#65 completed | 36.101, 36.104, 36.133, 36.307, new TR 36.833-6-xy | 62 | 32 |  |  | Sat 07/12/13 | Mon 08/09/14
2877 | 620238 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 41 for 3 DL | LTE_CA_NC_B41_3DL-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2015-03-13 17:00 | 100% | RP-140101 | RP-150013 | Sprint, Alcatel-Lucent | man-hung.ng@alcatel-lucent.com | CD:Thu 12/03/15->Sun 15/03/15; Compl:60%->70%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: Stat Rep: RP-141732->RP-150013 | 36.141 | 62 | 32 |  |  | Sat 07/12/13 | Wed 01/04/15
2878 | 620039 | LTE Advanced intra-band non-contiguous CA in Band 42 | LTE_CA_NC_B42 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140671 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Intra-band non-contig. CA 2DL | LTE | 62 | 32 |  |  | Sat 07/12/13 | Thu 13/03/14
2879 | 620139 | Core part:LTE Advanced intra-band non-contiguous CA in Band 42 | LTE_CA_NC_B42-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140671 | RP-140569 | Huawei | Liu Liehai (liuliehai@huawei.com) | RP#64 completed. Updated WID RP-140404=>RP-140671. TR 36.833-2-42v100 for 1-step Approval | 36.101, 36.104, 36.133, new TR 36.833-2-42 | 62 | 32 |  |  | Sat 07/12/13 | Thu 12/06/14
2880 | 620239 | Perf. part:LTE Advanced intra-band non-contiguous CA in Band 42 | LTE_CA_NC_B42-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-140671 | RP-140569 | Huawei | Liu Liehai (liuliehai@huawei.com) | RP#64 completed | 36.141, 36.307 | 62 | 32 |  |  | Sat 07/12/13 | Thu 12/06/14
2881 | 620050 | LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 3 and Band 5 | LTE_CA_B1_B3_B5 | 2 | Rel-12 | R4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 100% | RP-141454 | - | SK Telecom | haesung.park@sk.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
2882 | 620150 | Core part:LTE Advanced 3 Band CA(3DL/1UL) for Band 1, Band 3 and Band 5 | LTE_CA_B1_B3_B5-Core | 3 | Rel-12 | R4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 100% | RP-141454 | RP-141084 | SK Telecom | haesung.park@sk.com | RP#65 completed. Updated WID RP-132121=>RP-141454 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
2883 | 620250 | Perf. part:LTE Advanced 3 Band CA(3DL/1UL) for Band 1, Band 3 and Band 5 | LTE_CA_B1_B3_B5-Perf | 3 | Rel-12 | R4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 100% | RP-141454 | RP-141084 | SK Telecom | haesung.park@sk.com | RP#65 completed. Updated WID RP-132121=>RP-141454 | 36.141, 36.307 | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
2884 | 620051 | LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 3 and Band 20 | LTE_CA_B1_B3_B20 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141222 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
2885 | 620151 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 3 and Band 20 | LTE_CA_B1_B3_B20-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141222 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed. Updated WID RP-141017=>RP-141222 | 36.101, 36.104, 36.133, new generic TR 36.851 (2 Band CA with 1UL), TR 36.853 (3 Band CA with 1UL) | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
2886 | 620251 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 3 and Band 20 | LTE_CA_B1_B3_B20-Perf | 3 | Rel-12 | R4 | 2013-12-10 08:00 | 2014-09-12 17:00 | 100% | RP-141222 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
2887 | 620052 | LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 7 and Band 20 | LTE_CA_B1_B7_B20 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141223 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
2888 | 620152 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 7 and Band 20 | LTE_CA_B1_B7_B20-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-141223 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed. Updated WID RP-140243=>RP-141223 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL), TR 36.851 (2 Band CA with 1UL) | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
2889 | 620252 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 1, Band 7 and Band 20 | LTE_CA_B1_B7_B20-Perf | 3 | Rel-12 | R4 | 2013-12-10 08:00 | 2014-09-12 17:00 | 100% | RP-141223 | RP-141084 | Vodafone | luis.anaya@vodafone.com | RP#65 completed | 36.101, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Mon 09/12/13 | Sun 21/09/14
2890 | 620053 | LTE Advanced 3 Band CA (3DL/1UL) for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-15 17:00 | 100% | RP-132080 | - | Vodafone | luis.anaya@vodafone.com | Inter-band CA 3DL | LTE | 62 | 32 |  |  | Mon 09/12/13 | Tue 09/09/14
2891 | 620153 | Core part:LTE Advanced 3 Band CA (3DL/1UL) for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-15 17:00 | 100% | RP-132080 | RP-141732 | Vodafone | luis.anaya@vodafone.com | CD:Thu 11/12/14->Mon 15/12/14; Compl:85%->100%; Stat Rep: RP-141084->RP-141732 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL), TR 36.851 (2 Band CA with 1UL) | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
2892 | 620253 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20-Perf | 3 | Rel-12 | R4 | 2013-12-12 08:00 | 2014-12-15 17:00 | 100% | RP-132080 | RP-141732 | Vodafone | luis.anaya@vodafone.com | CD:Thu 11/12/14->Mon 15/12/14; Compl:0%->100%; Stat Rep: RP-141084->RP-141732 | 36.101, 36.133, 36.141, 36.307 | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
2893 | 630022 | Additional bandwidth combinations for LTE Advanced inter-band CA of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700_B29_Bwset | 2 | Rel-12 | R4 | 2014-03-03 08:00 | 2014-03-06 17:00 | 100% | RP-140084 | - | AT&T | marc.grant@att.com | Inter-band 2DL/1UL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Wed 12/03/14
2894 | 630122 | Core part: Additional bandwidth combinations for LTE Advanced inter-band CA of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700_B29_BWset-Core | 3 | Rel-12 | R4 | 2014-03-03 08:00 | 2014-03-06 17:00 | 100% | RP-140084 | RP-140428 | AT&T | marc.grant@att.com | RP#63 approved WI (no Perf. Part) & completed. Rel-10 and Rel-11 versions of 36.307 affected | 36.101, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Wed 12/03/14
2895 | 630023 | Additional bandwidth combination set for LTE Advanced inter-band CA of Band 3 and Band 20 | LTE_CA_B3_B20_BWset | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140447 | - | NSN | iwajlo.angelow@nsn.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
2896 | 630123 | Core part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 3 and Band 20 | LTE_CA_B3_B20_BWset-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140447 | RP-140569 | NSN | iwajlo.angelow@nsn.com | RP#64 completed | 36.101, TR 36.851 | 63 | 32 |  |  | Mon 10/03/14 | Fri 20/06/14
2897 | 630024 | Additional bandwidth combination set for LTE Advanced inter-band CA of Band 7 and Band 20 | LTE_CA_B7_B20_BWset | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140448 | - | NSN | iwajlo.angelow@nsn.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
2898 | 630124 | Core part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 7 and Band 20 | LTE_CA_B7_B20_BWset-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140448 | RP-140569 | NSN | iwajlo.angelow@nsn.com | RP#64 completed | 36.101, TR 36.851 | 63 | 32 |  |  | Mon 10/03/14 | Fri 20/06/14
2899 | 630025 | Additional bandwidth combinations for LTE Advanced inter-band CA to support 3DL fallback | LTE_CA_3DL_FB_BW | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140454 | - | Qualcomm | Fong Gene (gfong@qti.qualcomm.com) | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
2900 | 630125 | Core part: Additional bandwidth combinations for LTE Advanced inter-band CA to support 3DL fallback | LTE_CA_3DL_FB_BW-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140454 | RP-140569 | Qualcomm | Fong Gene (gfong@qti.qualcomm.com) | RP#64 completed, Additional BW combinations added for 6 Wis: 3 open Rel-12 Wis (B1_B5_B7, B2_B29_B30, B4_B29_B30) and 3 completed Rel-11 Wis (B3_B5, B4_B5, B4_B12) | 36.101, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Fri 20/06/14
2901 | 630026 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141196 | - | Nokia Networks | iwajlo.angelow@nsn.com | Inter-band CA 3DL. Mar15: acronym reverted to LTE_CA_B3_B7_B7_ | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 10/03/15
2902 | 630126 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141196 | RP-141084 | Nokia Networks | iwajlo.angelow@nsn.com | RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted to LTE_CA_B3_B7_B7-Core_ | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Tue 10/03/15
2903 | 630226 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 7 and Band 7 | LTE_CA_B3_B7_B7-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141196 | RP-141084 | Nokia Networks | iwajlo.angelow@nsn.com | RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted from LTE_CA_B3_B7_B7-Perf_ | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Tue 10/03/15
2904 | 630027 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 19 and Band 21 | LTE_CA_B1_B19_B21 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141193 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
2905 | 630127 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 19 and Band 21 | LTE_CA_B1_B19_B21-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141193 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed. Updated WID RP-140106=>RP-141193 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
2906 | 630227 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 19 and Band 21 | LTE_CA_B1_B19_B21-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141193 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed. Updated WID RP-140106=>RP-141193 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
2907 | 630028 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 3 and Band 7 | LTE_CA_B3_B3_B7 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141126 | - | TeliaSonera | Ralf.Schuh@TeliaSonera.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
2908 | 630128 | Core part: LTE-Advanced 3 Band CA (3DL/1UL) of Band 3, Band 3 and Band 7 | LTE_CA_B3_B3_B7-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141126 | RP-141084 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#65 completed. Updated RP-140390=>RP-141126 | 36.101, 36.104, 36.133, new generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
2909 | 630228 | Perf. part: LTE-Advanced 3 Band CA (3DL/1UL) of Band 3, Band 3 and Band 7 | LTE_CA_B3_B3_B7-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141126 | RP-141084 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#65 completed. Updated RP-140390=>RP-141126 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
2910 | 630029 | LTE Advanced intra-band contiguous CA in Band 40 for 3DL | LTE_CA_C_B40_3DL | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140948 | - | China Mobile | Pan Qun (panqun@chinamobile.com) | Intra-band contig. CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
2911 | 630129 | Core part: LTE Advanced intra-band contiguous CA in Band 40 for 3DL | LTE_CA_C_B40_3DL-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140948 | RP-140569 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#64 completed. Updated WID RP-140453=>RP-140948 | 36.101, 36.104, 36.133, New TR 36.833-5-40 | 63 | 32 |  |  | Mon 10/03/14 | Fri 20/06/14
2912 | 630229 | Perf. part: LTE Advanced intra-band contiguous CA in Band 40 for 3DL | LTE_CA_C_B40_3DL-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-06-13 17:00 | 100% | RP-140948 | RP-140569 | China Mobile | Pan Qun (panqun@chinamobile.com) | RP#64 completed. Updated WID RP-140453=>RP-140948 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Fri 20/06/14
2913 | 630035 | Additional bandwidth combination set for LTE Advanced inter-band CA of Band 4 and Band 12 | LTE_CA_B4_B12_BWset | 2 | Rel-12 | R4 | 2014-03-07 08:00 | 2014-09-12 17:00 | 100% | RP-141235 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
2914 | 630135 | Core part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 4 and Band 12 | LTE_CA_B4_B12_BWset-Core | 3 | Rel-12 | R4 | 2014-03-07 08:00 | 2014-09-12 17:00 | 100% | RP-141235 | RP-141084 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#65 completed. Updated WID RP-140987=>RP-141235 (removed Perf. Part) | 36.101, generic TR 36.850 | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
2915 | 630235 | Deleted - Perf. part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 4 and Band 12 | LTE_CA_B4_B12_BWset-Perf | 3 | Rel-12 | R4 | 2014-03-07 08:00 | 2014-09-12 17:00 | 100% | RP-141235 | RP-141084 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#65 stopped. Updated WID RP-140987=>RP-141235 (removed Perf. Part) | 36.307 | 63 | 32 | RP-65 | PCG-33 | Mon 10/03/14 | Sun 21/09/14
2916 | 630036 | LTE Advanced inter-band CA of Band 41 and Band 42 | LTE_CA_B41_B42 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-140450 | - | Huawei | leo.liuye@huawei.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
2917 | 630136 | Core part:LTE Advanced inter-band CA of Band 41 and Band 42 | LTE_CA_B41_B42-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-140450 | RP-141084 | Huawei | leo.liuye@huawei.com | RP#65 completed | 36.101, 36.104, TR 36.851 | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
2918 | 630236 | Perf. Part:LTE Advanced inter-band CA of Band 41 and Band 42 | LTE_CA_B41_B42-Perf | 3 | Rel-12 | R4 | 2014-03-07 08:00 | 2014-09-12 17:00 | 100% | RP-140450 | RP-141084 | Huawei | leo.liuye@huawei.com | RP#65 completed | 36.141 | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
2919 | 630037 | LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4, and Band 12 | LTE_CA_B4_B4_B12 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141709 | - | T-Mobile USA | nelson.ueng@t-mobile.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 22/09/14
2920 | 630137 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4, and Band 12 | LTE_CA_B4_B4_B12-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141709 | RP-141084 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#65 completed. Updated WID RP-140116=>RP-141709 | 36.101, 36.104, 36.133, 36.141, 36.307, generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 22/09/14
2921 | 630237 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4, and Band 12 | LTE_CA_B4_B4_B12-Perf | 3 | Rel-12 | R4 | 2014-03-07 08:00 | 2014-09-12 17:00 | 100% | RP-141709 | RP-141084 | T-Mobile USA | nelson.ueng@t-mobile.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 22/09/14
2922 | 630038 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4, and Band 4 | LTE_CA_B2_B4_B4 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141236 | - | T-Mobile USA | nelson.ueng@T-Mobile.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
2923 | 630138 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4, and Band 4 | LTE_CA_B2_B4_B4-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-141236 | RP-141084 | T-Mobile USA | nelson.ueng@T-Mobile.com | RP#65 completed. Updated WID RP-140117=>RP-141236 | 36.101, 36.104, 36.133, 36.141, 36.307, generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
2924 | 630238 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4, and Band 4 | LTE_CA_B2_B4_B4-Perf | 3 | Rel-12 | R4 | 2014-03-07 08:00 | 2014-09-12 17:00 | 100% | RP-141236 | RP-141084 | T-Mobile USA | nelson.ueng@T-Mobile.com | RP#65 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
2925 | 630045 | Additional bandwidth combinations for LTE Advanced intra-band non-contiguous CA in Band 25 | LTE_CA_NC_B25_BWset | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-140452 | - | Huawei | Liu Liehai (liuliehai@huawei.com) | Intra-band non-contig. CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
2926 | 630145 | Core part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous CA in Band 25 | LTE_CA_NC_B25_BWset-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-140452 | RP-141084 | Huawei | Liu Liehai (liuliehai@huawei.com) | RP#65 completed | 36.101, 36.307, TR 36.833-2-25 | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
2927 | 630245 | Perf. part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous CA in Band 25 | LTE_CA_NC_B25_BWset-Perf | 3 | Rel-12 | R4 | 2014-03-07 08:00 | 2014-09-12 17:00 | 100% | RP-140452 | RP-141084 | Huawei | Liu Liehai (liuliehai@huawei.com) | RP#65 completed | 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 08/09/14
2928 | 640020 | Additional bandwidth combination set for LTE Advanced inter-band CA of Band 2 and Band 4 | LTE_CA_B2_B4_Bwset2 | 2 | Rel-12 | R4 | 2014-06-15 | 2014-09-12 17:00 | 100% | RP-140599 | - | T-Mobile USA | nelson.ueng@T-Mobile.com | Inter-band CA 2DL. Mar 15: acronym changed from LTE_CA_B2_B4_Bwset_ | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 10/03/15
2929 | 640120 | Core part: Additional bandwidth combination set 2 for LTE Advanced inter-band CA of Band 2 and Band 4 | LTE_CA_B2_B4_BWset2-Core | 3 | Rel-12 | R4 | 2014-06-15 | 2014-09-12 17:00 | 100% | RP-140599 | RP-141084 | T-Mobile USA | nelson.ueng@T-Mobile.com | Dec 14: Prev CD:Fri 12/09/14; Prev %:100%, title changed. Mar 15: Acronym changed to LTE_CA_B2_B4_BWset2-Core_ | 36.101, 36.851 | 64 | 33 |  |  | Mon 16/06/14 | Tue 10/03/15
2930 | 640021 | Additional bandwidth combination set for LTE Advanced inter-band CA of Band 2 and Band 5 | LTE_CA_B2_B5_BWset | 2 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140642 | - | AT&T | marc.grant@att.com | 2DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2931 | 640121 | Core part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 2 and Band 5 | LTE_CA_B2_B5_Bwset-Core | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140642 | RP-141732 | AT&T | marc.grant@att.com | ; WID: RP-142043->RP-141803; Stat Rep: RP-141084->RP-141732 | 36.101, 36.851 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2932 | 640221 | Perf. Part: Additional bandwidth combination set for LTE Advanced inter-band CA of Band 2 and Band 5 | LTE_CA_B2_B5_BWset-Perf | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140642 | RP-141732 | AT&T | marc.grant@att.com | CD:Thu 11/12/14->Mon 15/12/14; Compl:0%->0%; Stat Rep: RP-141084->RP-141732 | 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2933 | 640027 | E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple CA configurations | LTE_CA_Mult | 2 | Rel-12 | R4 | 2014-06-16 08:00 | 2015-03-13 17:00 | 100% | RP-141304 | - | China Mobile | Zhang Xiaoran (zhangxiaoran@chinamobile.com) | LTE | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2934 | 640127 | Perf. Part: E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple CA configurations | LTE_CA_Mult-Perf | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2015-03-13 17:00 | 100% | RP-141304 | RP-150188 | China Mobile | Zhang Xiaoran (zhangxiaoran@chinamobile.com) | CD:Thu 12/03/15->Sun 15/03/15; Compl:10%->90%; Stat Rep: RP-141303->RP-141839 1st Apr 15: Compl:90%->100% 1st Apr 15: Stat Rep: RP-141839->RP-150188 | 36.101 | 64 | 33 |  |  | Mon 16/06/14 | Wed 01/04/15
2935 | 640028 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 19 | LTE_CA_B1_B3_B19 | 2 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141004 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | Inter-band CA 3DL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2936 | 640128 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 19 | LTE_CA_B1_B3_B19-Core | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141004 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2937 | 640228 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 19 | LTE_CA_B1_B3_B19-Perf | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141004 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2938 | 640029 | LTE Advanced 3 Band CA (3DL/1UL) of Band 19, Band 42 and Band 42 | LTE_CA_B19_B42_B42 | 2 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141007 | - | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | Inter-band CA 3DL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2939 | 640129 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 19, Band 42 and Band 42 | LTE_CA_B19_B42_B42-Core | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141007 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2940 | 640229 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 19, Band 42 and Band 42 | LTE_CA_B19_B42_B42-Perf | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141007 | RP-141084 | NTT DOCOMO | teruaki.toeda.zf@nttdocomo.com | RP#65 completed | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2941 | 640030 | LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42 | 2 | Rel-12 | R4 | 2014-06-16 08:00 | 2015-03-13 17:00 | 100% | RP-141005 | - | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2942 | 640130 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42-Core | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2015-03-13 17:00 | 100% | RP-141005 | RP-150013 | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | CD:Thu 11/12/14->Sun 15/03/15; Compl:50%->70%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: Stat Rep: RP-141732->RP-150013 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Wed 01/04/15
2943 | 640230 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42-Perf | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2015-03-13 17:00 | 100% | RP-141005 | RP-150013 | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | CD:Thu 11/12/14->Tue 15/03/16; Compl:50%->70%; Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:70%->100% 1st Apr 15: CD:Tue 15/03/16->Sun 15/03/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Wed 01/04/15
2944 | 640031 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 42 and Band 42 | LTE_CA_B1_B42_B42 | 2 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141006 | - | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | Inter-band CA 3DL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2945 | 640131 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 42 and Band 42 | LTE_CA_B1_B42_B42-Core | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141006 | RP-141084 | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | RP#65 completed | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2946 | 640231 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 42 and Band 42 | LTE_CA_B1_B42_B42-Perf | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141006 | RP-141084 | NTT DOCOMO | ANDO Kei (kei.andou.ye@nttdocomo.com) | RP#65 completed | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2947 | 640035 | Additional bandwidth combination set for LTE Advanced intra-band contiguous CA in Band 40 for 3DL | LTE_CA_C_B40_3DL_BW | 2 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141127 | - | TeliaSonera | Ralf.Schuh@TeliaSonera.com | Inter-band CA 3DL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2948 | 640135 | Core part: Additional bandwidth combination set for LTE Advanced intra-band contiguous CA in Band 40 for 3DL | LTE_CA_C_B40_3DL_BW-Core | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-09-12 17:00 | 100% | RP-141127 | RP-141084 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#65 completed. Updated WID RP-140950=>RP-141127 | 36.101 | 64 | 33 |  |  | Mon 16/06/14 | Mon 08/09/14
2949 | 650054 | Perf. part: Additional bandwidth combination set for LTE Advanced intra-band contiguous CA in Band 40 for 3DL | LTE_CA_C_B40_3DL_BW-Perf | 3 | Rel-12 | R4 | 2014-09-08 08:00 | 2014-09-12 17:00 | 100% | RP-141127 | RP-141084 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#65 updated WID RP-140950=>RP-141127 (added Perf. Part). Completed. | 36.307 | 65 | 33 |  |  | Sun 21/09/14 | Sun 05/10/14
2950 | 650010 | LTE Advanced inter-band CA of Band 18 and Band 28 | LTE_CA_B18_B28 | 2 | Rel-12 | R4 | 2014-09-10 08:00 | 2014-09-12 17:00 | 100% | RP-141611 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 2DL | LTE | 65 | 33 |  |  | Mon 10/03/14 | Wed 10/09/14
2951 | 650110 | Core part:LTE Advanced inter-band CA of Band 18 and Band 28 | LTE_CA_B18_B28-Core | 3 | Rel-12 | R4 | 2014-09-10 08:00 | 2014-09-12 17:00 | 100% | RP-141611 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#65 WID approved & completed. Triggered by revised Rel-13 WID RP-140451=>RP-141610 (take out B18_B28 for Rel-12 from the Rel-13 B1_B18_B28) | 36.101, 36.104, 36.133 | 65 | 33 |  |  | Mon 10/03/14 | Wed 10/09/14
2952 | 650210 | Perf. Part:LTE Advanced inter-band CA of Band 18 and Band 28 | LTE_CA_B18_B28-Perf | 3 | Rel-12 | R4 | 2014-09-10 08:00 | 2014-09-12 17:00 | 100% | RP-141611 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | - | 36.141, 36.307 | 65 | 33 |  |  | Mon 10/03/14 | Wed 10/09/14
2953 | 630034 | LTE Advanced inter-band CA of Band 5 and Band 13 | LTE_CA_B5_B13 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140169 | - | Intel | xinrong.wang@intel.com | Inter-band CA 2DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
2954 | 630134 | Core part:LTE Advanced inter-band CA of Band 5 and Band 13 | LTE_CA_B5_B13-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140169 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:50%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic TR 36.851 (2 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2955 | 630234 | Perf. part:LTE Advanced inter-band CA of Band 5 and Band 13 | LTE_CA_B5_B13-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140169 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:10%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2956 | 630039 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140165 | - | Intel | peiling.zhang@intel.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
2957 | 630139 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140165 | RP-141732 | Intel | peiling.zhang@intel.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:90%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2958 | 630239 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 2 and Band 5 | LTE_CA_B2_B2_B5-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140165 | RP-141732 | Intel | peiling.zhang@intel.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:10%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2959 | 630040 | LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140166 | - | Intel | peiling.zhang@intel.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
2960 | 630140 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140166 | RP-141732 | Intel | peiling.zhang@intel.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:90%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2961 | 630240 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 5 | LTE_CA_B4_B4_B5-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140166 | RP-141732 | Intel | peiling.zhang@intel.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:10%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2962 | 630041 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140167 | - | Intel | xinrong.wang@intel.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
2963 | 630141 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140167 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:50%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2964 | 630241 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 5 and Band 13 | LTE_CA_B2_B5_B13-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140167 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:10%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2965 | 630042 | LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140168 | - | Intel | xinrong.wang@intel.com | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
2966 | 630142 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140168 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:50%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2967 | 630242 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 5 and Band 13 | LTE_CA_B4_B5_B13-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140168 | RP-141732 | Intel | xinrong.wang@intel.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:10%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.133, 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2968 | 630043 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140194 | - | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
2969 | 630143 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140194 | RP-141732 | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | CD:Thu 11/12/14->Mon 15/12/14; Compl:90%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2970 | 630243 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 3 and Band 26 | LTE_CA_B1_B3_B26-Perf | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-140194 | RP-141732 | China Telecom | Zhao Dong (zhaodong@ctbri.com.cn) | CD:Thu 11/12/14->Mon 15/12/14; Compl:90%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2971 | 630044 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28 | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-141610 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 3DL | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
2972 | 630144 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28-Core | 3 | Rel-12 | R4 | 2014-03-06 08:00 | 2014-12-15 17:00 | 100% | RP-141788 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ; WID: RP-142043->RP-141788; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2973 | 630244 | Perf. part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 18 and Band 28 | LTE_CA_B1_B18_B28-Perf | 3 | Rel-12 | R4 | 2014-03-11 08:00 | 2014-12-15 17:00 | 100% | RP-141788 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ; WID: RP-142043->RP-141788; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.141, 36.307 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
2974 | 640023 | LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12 | 2 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140661 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2975 | 640123 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12-Core | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140661 | RP-141732 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:0%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, 36.307, generic TR 36.851 (2 Band CA with 1UL), generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2976 | 640223 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 7 and Band 12 | LTE_CA_B4_B7_B12-Perf | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140661 | RP-141732 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:0%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.133, 36.141 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2977 | 640024 | LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7 | 2 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140662 | - | Rogers Wireless | pavlo.nebesny@rci.rogers.com | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2978 | 640124 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7-Core | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140662 | RP-141732 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:0%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, 36.307, generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2979 | 640224 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 4, Band 4 and Band 7 | LTE_CA_B4_B4_B7-Perf | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140662 | RP-141732 | Rogers Wireless | pavlo.nebesny@rci.rogers.com | CD:Thu 12/03/15->Mon 15/12/14; Compl:0%->100%; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.133, 36.141 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2980 | 640026 | LTE Advanced 3 Band CA (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41 | 2 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-12-15 17:00 | 100% | RP-140708 | - | China Mobile | PAN Qun (panqun@chinamobile.com) | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2981 | 640126 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41-Core | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-12-15 17:00 | 100% | RP-142301 | RP-141732 | China Mobile | PAN Qun (panqun@chinamobile.com) | ; WID: RP-140708->RP-142301; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2982 | 640226 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 39, Band 41 and Band 41 | LTE_CA_B39_B41_B41-Perf | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-142301 | RP-141732 | China Mobile | PAN Qun (panqun@chinamobile.com) | ; WID: RP-140708->RP-142301; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2983 | 640033 | LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41 | 2 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140963 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2984 | 640133 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41-Core | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-142297 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ; WID: RP-142043->RP-142297; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2985 | 640233 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 1, Band 41 and Band 41 | LTE_CA_B1_B41_B41-Perf | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-142297 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | Compl:100%->0%; WID: RP-142043->RP-142297; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2986 | 640034 | LTE Advanced 3 Band CA (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41 | 2 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-140964 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Inter-band CA 3DL/1UL | LTE | 64 | 33 |  |  | Mon 16/06/14 | Tue 09/09/14
2987 | 640134 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41-Core | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-142298 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | ; WID: RP-142043->RP-142298; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, generic TR 36.853 (3 Band CA with 1UL) | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2988 | 640234 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 26, Band 41 and Band 41 | LTE_CA_B26_B41_B41-Perf | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-15 17:00 | 100% | RP-142298 | RP-141732 | KDDI | Masaaki Obara (ms-obara@kddi.com) | Compl:100%->0%; WID: RP-142043->RP-142298; Stat Rep: RP-141084->RP-141732; Release: Rel-13->Rel-12 | 36.141, 36.307 | 64 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2989 | 650046 | LTE Advanced 3 Band CA (3DL/1UL) of Band 25, Band 41 and Band 41 | LTE_CA_B25_B41_B41 | 2 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-141673 | - | Alcatel-Lucent | Ng, Man Hung (man-hung.ng@alcatel-lucent.com) | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Sun 05/10/14
2990 | 650146 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 25, Band 41 and Band 41 | LTE_CA_B25_B41_B41-Core | 3 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-142018 | RP-141732 | Alcatel-Lucent | Ng, Man Hung (man-hung.ng@alcatel-lucent.com) | ; WID: RP-142043->RP-142018; Stat Rep: -->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.307, New TR 36.833-x-yz | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2991 | 650246 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 25, Band 41 and Band 41 | LTE_CA_B25_B41_B41-Perf | 3 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-142018 | RP-141732 | Alcatel-Lucent | Ng, Man Hung (man-hung.ng@alcatel-lucent.com) | ; WID: RP-142043->RP-142018; Stat Rep: -->RP-141732; Release: Rel-13->Rel-12 | 36.141 | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2992 | 650048 | LTE Advanced 3 Band CA (3DL/1UL) of Band 39, Band 39 and Band 41 | LTE_CA_B39_B39_B41 | 2 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-141288 | - | China Mobile | PAN, Qun (panqun@chinamobile.com) | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2993 | 650148 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 39, Band 39 and Band 41 | LTE_CA_B39_B39_B41-Core | 3 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-142302 | RP-141732 | China Mobile | PAN, Qun (panqun@chinamobile.com) | ; WID: RP-141288->RP-142302; Stat Rep: -->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2994 | 650248 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 39, Band 39 and Band 41 | LTE_CA_B39_B39_B41-Perf | 3 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-142302 | RP-141732 | China Mobile | PAN, Qun (panqun@chinamobile.com) | ; WID: RP-141288->RP-142302; Stat Rep: -->RP-141732; Release: Rel-13->Rel-12 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2995 | 650050 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 2 and Band 29 | LTE_CA_B2_B2_B29 | 2 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-141448 | - | AT&T | marc.grant@att.com | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2996 | 650150 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 2 and Band 29 | LTE_CA_B2_B2_B29-Core | 3 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-141448 | RP-141732 | AT&T | marc.grant@att.com | CD:Thu 11/12/14->Mon 15/12/14; Compl:0%->100%; Stat Rep: -->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2997 | 650250 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 2 and Band 29 | LTE_CA_B2_B2_B29-Perf | 3 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-141448 | RP-141732 | AT&T | marc.grant@att.com | CD:Thu 11/12/14->Mon 15/12/14; Compl:0%->100%; Stat Rep: -->RP-141732; Release: Rel-13->Rel-12 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
2998 | 650052 | LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4 and Band 29 | LTE_CA_B2_B4_B29 | 2 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-141668 | - | Huawei | SHAN Huiping (shanhuiping@huawei.com) | Inter-band CA 3DL/1UL | LTE | 65 | 33 |  |  | Mon 16/06/14 | Mon 22/09/14
2999 | 650152 | Core part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4 and Band 29 | LTE_CA_B2_B4_B29-Core | 3 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-141668 | RP-141732 | Huawei | SHAN Huiping (shanhuiping@huawei.com) | CD:Fri 11/12/15->Mon 15/12/14; Compl:0%->100%; Stat Rep: -->RP-141732; Release: Rel-13->Rel-12 | 36.101, 36.104, 36.133, New TR 36.8xx | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
3000 | 650252 | Perf. Part:LTE Advanced 3 Band CA (3DL/1UL) of Band 2, Band 4 and Band 29 | LTE_CA_B2_B4_B29-Perf | 3 | Rel-12 | R4 | 2014-09-15 08:00 | 2014-12-15 17:00 | 100% | RP-141668 | RP-141732 | Huawei | SHAN Huiping (shanhuiping@huawei.com) | CD:Thu 11/12/14->Mon 15/12/14; Compl:0%->100%; Stat Rep: -->RP-141732; Release: Rel-13->Rel-12 | 36.141, 36.307 | 65 | 33 |  |  | Mon 16/06/14 | Mon 12/01/15
3001 | 610013 | UE Conformance Test Aspects – Further Rel-12 configurations for LTE Advanced CA | LTE_CA_Rel12-UEConTest | 1 | Rel-12 | R5 | 2013-09-15 | 2015-03-13 17:00 | 100% | RP-150077 | RP-150076 | Microsoft | jussi.kuusisto@microsoft.com | ; Stat Rep: RP-141444->RP-141774 1st Apr 15: Compl:75%->100% 1st Apr 15: WID: RP-140621->RP-150077 1st Apr 15: Stat Rep: RP-141774->RP-150076 | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1, 37.571-3, 37.571-5 | 61 | 31 |  |  | Fri 30/08/13 | Wed 01/04/15
3002 | 650011 | UE Conformance Test Aspects – Further Rel-12 configurations for LTE Advanced CA with 3DL | LTE_CA_Rel12_3DL-UEConTest | 1 | Rel-12 | R5 | 2014-09-15 | 2016-03-15 17:00 | 100% | RP-151821 | RP-151464 | Microsoft | jussi.kuusisto@microsoft.com | ; Stat Rep: -->RP-141775 1st Apr 15: Compl:6%->12% 1st Apr 15: CD:Tue 15/09/15->Tue 15/12/15 1st Apr 15: WID: RP-142231->RP-150079 1st Apr 15: Stat Rep: RP-141775->RP-150078 03/07/15: Compl:12%->35% 03/07/15: WID: RP-150079->RP-150594 03/07/15: Stat Re | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1, 37.571-3, 37.571-5 | 65 | 33 |  |  | Tue 09/09/14 | Tue 22/03/16
3003 | 510033 | Deleted - Carrier based HetNet ICIC for LTE | LTE_CA_HetNet_ICIC | 1 | Rel-12 | R3,R1,R2 | 2011-03-18 08:00 | 2013-06-14 17:00 | 100% | RP-121198 | - | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#60 stopped. RP#58 on hold til June 2013 | LTE | 51 | 26 | RP-60 | PCG-31 | Mon 14/03/11 | Wed 12/06/13
3004 | 510133 | Deleted - Core part: Carrier based HetNet ICIC for LTE | LTE_CA_HetNet_ICIC-Core | 2 | Rel-12 | R3,R1,R2 | 2011-03-18 08:00 | 2013-06-14 17:00 | 100% | RP-121198 | RP-130500 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#60 stopped at 40% completion. RP#58 on hold til June 2013 | 36.300, 36.413, 36.420, 36.423 | 51 | 26 | RP-60 | PCG-31 | Mon 14/03/11 | Wed 12/06/13
3005 | 570017 | LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band | 1 | Rel-12 | R4,R2,R5 | 2012-09-12 08:00 | 2014-12-15 17:00 | 100% | RP-130843 | - | AT&T | marc.grant@att.com | RP#58 RP-121701 work can start based on FCC Order (FCC-12-130) http://hraunfoss.fcc.gov/edocs_public/attachmatch/FCC-12-130A1.pdf | LTE | 57 | 29 |  |  | Mon 03/09/12 | Tue 11/06/13
3006 | 570117 | Core part: LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band-Core | 2 | Rel-12 | R4,R2 | 2012-09-12 08:00 | 2013-06-14 17:00 | 100% | RP-130843 | RP-130569 | AT&T | marc.grant@att.com | RP#60 completed. Updated WID RP-121419=>RP-130843 | 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 36.331, new TR 36.846 | 57 | 29 |  |  | Mon 03/09/12 | Tue 11/06/13
3007 | 570217 | Perf. Part: LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band-Perf | 2 | Rel-12 | R4 | 2012-09-13 08:00 | 2013-06-14 17:00 | 100% | RP-130843 | RP-130570 | AT&T | marc.grant@att.com | RP#60 completed. Updated WID RP-121419=>RP-130843 | 36.101, 36.133, 36.141 | 57 | 29 |  |  | Mon 03/09/12 | Tue 11/06/13
3008 | 640002 | Test Part: LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band-UEConTest | 2 | Rel-12 | R5 | 2014-06-15 | 2014-12-15 17:00 | 100% | RP-140643 | RP-141773 | Ericsson | fredrik.sundstrom@ericsson.com | ; Stat Rep: RP-141166->RP-141773 | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1 | 64 | 33 |  |  | Wed 28/05/14 | Mon 12/01/15
3009 | 570019 | Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil | 1 | Rel-12 | R4,R5 | 2012-09-11 08:00 | 2013-12-06 17:00 | 100% | RP-121414 | - | Huawei | Liehai Liu (liuliehai@huawei.com) | - | LTE | 57 | 29 |  |  | Mon 03/09/12 | Fri 07/09/12
3010 | 570119 | Core part: Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil-Core | 2 | Rel-12 | R4 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-121414 | RP-130567 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#60 completed. TR 36.840 v100 for 1-step Approval | 36.101, 36.104, 36.113, 36.124, 36.133, 37.104, 37.113, 36.307, new TR 36.840 | 57 | 29 |  |  | Mon 03/09/12 | Wed 05/06/13
3011 | 570219 | Perf. part: Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil-Perf | 2 | Rel-12 | R4 | 2012-09-13 08:00 | 2013-09-06 17:00 | 100% | RP-121414 | RP-131070 | Huawei | Liehai Liu (liuliehai@huawei.com) | RP#61 completed | 36.133, 36.141, 37.141 | 57 | 29 |  |  | Mon 03/09/12 | Fri 30/08/13
3012 | 600005 | Test part: Introduction of LTE 450 MHz band in Brazil | LTE450_Brazil-UEConTest | 2 | Rel-12 | R5 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-130646 | RP-131457 | Huawei | Xiang Li (tricia.li@huawei.com) | RP#62 completed | 36.508, 36.521-1, 36.521-2, 36.521-3 | 60 | 31 |  |  | Thu 30/05/13 | Fri 29/11/13
3013 | 570020 | Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh | 1 | Rel-12 | R1,R4 | 2012-09-11 08:00 | 2016-03-15 17:00 | 100% | RP-121416 | - | Alcatel-Lucent | Min Zhang (min.hs.zhang@alcatel-lucent.com) | Stage 3 | LTE | 57 | 29 |  |  | Mon 03/09/12 | Thu 06/12/12
3014 | 570120 | Core part: Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh-Core | 2 | Rel-12 | R1 | 2012-09-11 08:00 | 2014-06-13 17:00 | 100% | RP-121416 | RP-140652 | Alcatel-Lucent | Min Zhang (min.hs.zhang@alcatel-lucent.com) | RP#64 completed | 36.211, 36.212, 36.213, 36.331 | 57 | 29 |  |  | Mon 03/09/12 | Sun 06/07/14
3015 | 570220 | Perf. part: Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh-Perf | 2 | Rel-12 | R4 | 2012-09-15 | 2014-12-15 17:00 | 100% | RP-121416 | RP-142042 | Alcatel-Lucent | ren.da@alcatel-lucent.com | ; CD:Fri 12/06/15->Mon 15/06/15; WID: RP-141966->RP-142235; Stat Rep: RP-141378->RP-142042 | 36.101 | 57 | 29 |  |  | Mon 03/09/12 | Mon 12/01/15
3016 | 670045 | UE Conformance Test Aspects - Further DL MIMO Enhancement for LTE-Advanced | LTE_eDL_MIMO_enh-UEConTest | 2 | Rel-12 | R5 | 2015-03-16 08:00 | 2016-03-15 17:00 | 100% | RP-150071 | RP-151189 | ZTE |  | 03/07/15: Compl:0%->10% 03/07/15: Stat Rep: ->RP-150606 29/09/15: Compl:10%->70% 29/09/15: Stat Rep: RP-150606->RP-1511891/1/16: Compl:70%->75% |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 22/03/16
3017 | 570025 | Deleted - New Carrier Type for LTE | LTE_NCT | 1 | Rel-12 | R1,R2,R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-122028 | - | Ericsson | daniel.n.larsson@ericsson.com | RP#61 stopped. Continue discussion on use cases and requirements for a NCT in LTE beyond Rel-12. Action: Ericsson to provide at RP#62 a summary of work done so far | LTE | 57 | 29 | RP-61 | PCG-31 | Mon 03/09/12 | Tue 10/09/13
3018 | 570125 | Deleted - Core part: New Carrier Type for LTE | LTE_NCT-Core | 2 | Rel-12 | R1,R2,R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-122028 | RP-130984 | Ericsson | daniel.n.larsson@ericsson.com | RP#61 stopped at 20% completion | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.321, 36.331 | 57 | 29 | RP-61 | PCG-31 | Mon 03/09/12 | Tue 10/09/13
3019 | 570225 | Deleted - Perf. part: New Carrier Type for LTE | LTE_NCT-Perf | 2 | Rel-12 | R4 | 2012-09-17 08:00 | 2013-09-06 17:00 | 100% | RP-122028 | RP-130985 | Ericsson | daniel.n.larsson@ericsson.com | RP#61 stopped at 0% completion | 36.101, 36.104, 36.133, 36.141 | 57 | 29 | RP-61 | PCG-31 | Mon 03/09/12 | Tue 10/09/13
3020 | 580027 | Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA | 1 | Rel-12 | R1,R2,R3,R4 | 2012-12-07 08:00 | 2018-03-15 17:00 | 99% | RP-121772 | - | CATT | Zukang Shen (shenzukang@catt.cn) | Stage 3. Triggered by Rel-11 TR 36.828 Study on Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation (FS_LTE_TDD_eIMTA) UID_510039 | LTE | 58 | 30 |  |  | Mon 03/09/12 | Mon 10/12/12
3021 | 580127 | Core part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA-Core | 2 | Rel-12 | R1,R2,R3,R4 | 2012-12-07 08:00 | 2014-06-13 17:00 | 100% | RP-121772 | RP-140724 | CATT | Zukang Shen (shenzukang@catt.cn) | RP#64 completed | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.214, 36.300, 36.321, 36.331, 36.413, 36.423 | 58 | 30 |  |  | Mon 03/09/12 | Sun 06/07/14
3022 | 580227 | Perf. part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA-Perf | 2 | Rel-12 | R4 | 2012-12-15 | 2015-09-15 17:00 | 100% | RP-121772 | RP-151447 | CATT | Zukang Shen (shenzukang@catt.cn) | ; CD:Thu 18/06/15->Mon 15/06/15; WID: RP-141966->RP-142235; Stat Rep: RP-141342->RP-141948 1st Apr 15: Compl:30%->55% 1st Apr 15: Stat Rep: RP-141948->RP-150154 03/07/15: Compl:55%->95% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150 | 36.101, 36.104, 36.133, 36.141 | 58 | 30 |  |  | Mon 03/09/12 | Tue 29/09/15
3023 | 690072 | UE Conformance Test Aspects - Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA-UEConTest | 2 | Rel-12 | R5 | 2015-09-15 08:00 | 2018-03-15 17:00 | 100% | RP-151398 |  | CATT |  | tested: REL-12 WI LTE_TDD_eIMTA-Core;1/1/16: Compl:0%->5%; 22/3/16: Compl:5%->15% 21/3/ 19 827/3/ |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 27/03/18
3024 | 580029 | HetNet Mobility enhancements for LTE | HetNet_eMOB_LTE | 1 | Rel-12 | R2,R4 | 2012-04-13 10:48 | 2014-09-12 17:00 | 100% | RP-122007 | - | Alcatel-Lucent | sudeep.palat@alcatel-lucent.com | Stage 3. Triggered by Rel-11 TR 36.839 Study on HetNet mobility enhancements for LTE (FS_HetNet_eMOB_LTE) | LTE | 58 | 30 |  |  | Mon 10/12/12 | Tue 09/09/14
3025 | 580129 | Core part: HetNet Mobility enhancements for LTE | HetNet_eMOB_LTE-Core | 2 | Rel-12 | R2,R4 | 2012-04-13 10:48 | 2014-09-12 17:00 | 100% | RP-122007 | RP-141413 | Alcatel-Lucent | sudeep.palat@alcatel-lucent.com | SP#65 completed | 36.133, 36.304, 36.331 | 58 | 30 |  |  | Mon 10/12/12 | Tue 09/09/14
3026 | 580030 | Further enhancements for HeNB mobility-X2-GW | EHNB_enh2_X2GW | 1 | Rel-12 | R3 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-122006 | - | Alcatel-Lucent | Philippe.Godin@alcatel-lucent.com | Rel-10 H(e)NB Mobility Enhancements adds signalling via horizontal RAN interfaces (Iurh, X2) to support H(e)NB to H(e)NB mobility. Rel-11 TR37.803 triggered WI UID_560014 partly completed in Rel-11; remaining work including solution definition is Rel-12 | LTE | 58 | 30 |  |  | Mon 10/12/12 | Mon 10/12/12
3027 | 580130 | Core part: Further enhancements for HeNB mobility-X2-GW | EHNB_enh2_X2GW-Core | 2 | Rel-12 | R3 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-122006 | RP-140592 | Alcatel-Lucent | Philippe.Godin@alcatel-lucent.com | RP#64 completed | 36.300, 36.413, 36.423 | 58 | 30 |  |  | Mon 10/12/12 | Thu 12/06/14
3028 | 580031 | 8 Rx Antennas for LTE UL | LTE_UL_8Rx | 1 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-121709 | - | China Telecom | Shan Yang (yangshan@ctbri.com.cn) | WI has perf. part only (as change from 4Rx to 8Rx has no Core spec impact) | LTE | 58 | 30 |  |  | Mon 03/09/12 | Mon 10/12/12
3029 | 580231 | Perf. part: 8 Rx Antennas for LTE UL | LTE_UL_8Rx-Perf | 2 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-121709 | RP-131523 | China Telecom | Shan Yang (yangshan@ctbri.com.cn) | RP#62 completed | 36.104, 36.141 | 58 | 30 |  |  | Mon 03/09/12 | Fri 29/11/13
3030 | 600013 | LTE TDD-FDD joint operation including CA | LTE_CA_TDD_FDD | 1 | Rel-12 | R1,R2,R4 | 2013-04-12 16:44 | 2014-12-15 17:00 | 100% | RP-140465 | - | Nokia | lars.e.lindh@nokia.com | - | LTE | 60 | 31 |  |  | Mon 17/06/13 | Thu 13/03/14
3031 | 600113 | Core part: LTE TDD-FDD joint operation including CA | LTE_CA_TDD_FDD-Core | 2 | Rel-12 | R1,R2,R4 | 2013-04-12 16:44 | 2014-06-13 17:00 | 100% | RP-140465 | RP-140982 | Nokia, China Mobile (for TR) | lars.e.lindh@nokia.com, Xiaodong Shen (shenxiaodong@chinamobile.com) | RP#64 completed | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.331, new TR 36.847 | 60 | 31 |  |  | Mon 17/06/13 | Thu 12/06/14
3032 | 600213 | Perf. part: LTE TDD-FDD joint operation including CA | LTE_CA_TDD_FDD-Perf | 2 | Rel-12 | R4 | 2013-06-15 | 2014-12-15 17:00 | 100% | RP-140465 | RP-141972 | Nokia | lars.e.lindh@nokia.com | ; CD:Thu 18/06/15->Mon 15/06/15; WID: RP-130848->RP-140522; Stat Rep: RP-141374->RP-141972 | 36.101, 36.104, 36.133 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
3033 | 600014 | LTE Coverage Enhancements | Cov_Enh_LTE | 1 | Rel-12 | R1,R2,R4,R5 | 2013-03-01 15:38 | 2015-06-15 17:00 | 100% | RP-130833 | - | China Telecom | Xiaoming She (shexm@ctbri.com.cn) | Triggered by Rel-11 TR 36.824 (FS_Cov_Enh_LTE) | LTE | 60 | 31 |  |  | Mon 17/06/13 | Mon 17/06/13
3034 | 600114 | Core part: LTE Coverage Enhancements | Cov_Enh_LTE-Core | 2 | Rel-12 | R1,R2,R4 | 2013-03-01 15:38 | 2014-06-13 17:00 | 100% | RP-130833 | RP-140683 | China Telecom | Xiaoming She (shexm@ctbri.com.cn) | RP#64 completed | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.321, 36.331 | 60 | 31 |  |  | Mon 17/06/13 | Thu 12/06/14
3035 | 600214 | Perf. part: LTE Coverage Enhancements | Cov_Enh_LTE-Perf | 2 | Rel-12 | R4 | 2013-06-15 | 2014-12-15 17:00 | 100% | RP-130833 | RP-141833 | China Telecom | Xiaoming She (shexm@ctbri.com.cn) | ; CD:Thu 18/06/15->Mon 15/06/15; WID: RP-141966->RP-142235; Stat Rep: RP-141149->RP-141833 | 36.101, 36.104, 36.133, 36.141 | 60 | 31 |  |  | Mon 17/06/13 | Mon 12/01/15
3036 | 650012 | Test part: LTE Coverage Enhancements | Cov_Enh_LTE-UEConTest | 2 | Rel-12 | R5 | 2014-09-15 | 2015-06-15 17:00 | 100% | RP-141150 | RP-150631 | China Telecom | YANG Shan (yangshan@ctbri.com.cn) | ; Stat Rep: -->RP-141834 03/07/15: Compl:5%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: RP-141834->RP-150631 | 36.508, 36.523-1, 36.523-2, 36.523-3 | 65 | 33 |  |  | Tue 09/09/14 | Thu 18/06/15
3037 | 610024 | Further MBMS operations support for E-UTRAN | MBMS_LTE_OS | 1 | Rel-12 | R2,R1,R3,R4 | 2013-09-15 | 2014-12-15 17:00 | 100% | RP-140282 | - | Verizon | yeesin.chan@verizonwireless.com | Solutions for Minimization of Drive Tests (MDT), in order to reduce the need for manual drive testing for MBMS. | LTE | 61 | 31 |  |  | Sat 07/09/13 | Tue 09/09/14
3038 | 610124 | Core part: Further MBMS operations support for E-UTRAN | MBMS_LTE_OS-Core | 2 | Rel-12 | R2,R1,R3,R4 | 2013-09-15 | 2014-12-15 17:00 | 100% | RP-140282 | RP-141821 | Verizon | yeesin.chan@verizonwireless.com | ; CD:Thu 18/06/15->Mon 15/06/15; WID: RP-130848->RP-140522; Stat Rep: RP-141431->RP-141821 | 36.133, 36.214, 36.300, 36.304, 36.306, 36.331, 36.413, 36.423, 37.320 | 61 | 31 |  |  | Sat 07/09/13 | Mon 12/01/15
3039 | 620073 | Perf. part: Further MBMS operations support for E-UTRAN | MBMS_LTE_OS-Perf | 2 | Rel-12 | R4 | 2013-12-15 | 2014-12-15 17:00 | 100% | RP-140282 | RP-141821 | Verizon | yeesin.chan@verizonwireless.com | ; CD:Wed 17/12/14->Mon 15/12/14; WID: RP-130848->RP-140522; Stat Rep: RP-141431->RP-141821 | 36.133 | 62 | 32 |  |  | Wed 18/12/13 | Mon 12/01/15
3040 | 620040 | Dual connectivity for LTE | LTE_SC_enh_dualC | 1 | Rel-12 | R2,R1,R3,R4,S2,C4 | 2013-12-15 | 2017-09-15 17:00 | 99% | RP-141266 | - | NTT DOCOMO | tooru.uchino.fv@nttdocomo.com | Triggered by TR 36.842 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Higher-layer aspects (UID_580044) | LTE | 62 | 32 |  |  | Sat 07/12/13 | Mon 15/09/14
3041 | 620140 | Core part: Dual connectivity for LTE | LTE_SC_enh_dualC-Core | 2 | Rel-12 | R2,R1,R3,R4 | 2013-12-15 | 2014-12-15 17:00 | 100% | RP-141797 | RP-141796 | NTT DOCOMO, NEC | RAN1/2/4 tooru.uchino.fv@nttdocomo.com, RAN3 Chenghock Ng (ngcheng@da.jp.nec.com) | ; CD:Wed 18/03/15->Sun 15/03/15; WID: RP-130848->RP-140522; Stat Rep: RP-141264->RP-141796 | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.322, 36.323, 36.331, 36.410, 36.413, 36.420, 36.423, new RAN3 TS 36.425 | 62 | 32 |  |  | Sat 07/12/13 | Mon 12/01/15
3042 | 620240 | Perf. part: Dual Connectivity for LTE | LTE_SC_enh_dualC-Perf | 2 | Rel-12 | R4 | 2013-12-15 | 2015-06-15 17:00 | 100% | RP-141797 | RP-150791 | NTT DOCOMO | kunihiko.teshima.hg@nttdocomo.com | ; Stat Rep: RP-141264->RP-141796 1st Apr 15: Compl:15%->45% 1st Apr 15: Stat Rep: RP-141796->RP-150160 03/07/15: Compl:45%->100% 03/07/15: Stat Rep: RP-150160->RP-150791 | 36.101, 36.104, 36.133 | 62 | 32 |  |  | Sat 07/12/13 | Thu 18/06/15
3043 | 631000 | SA2 part of Dual connectivity for LTE | LTE_SC_enh_dualC-S2 | 2 | Rel-12 | S2 | 2014-03-19 08:00 | 2014-09-17 17:00 | 100% | - | - | - | - | SP#64 Three CRs agreed in SP-140262 (23.251CR0099, 23.401CR2658&CR2707). Dec.14:99->100% | 23.251, 23.401 | 63 | 32 |  |  | Thu 19/06/14 | Wed 03/12/14
3044 | 650006 | CT aspects of Dual connectivity for LTE | LTE_SC_enh_dualC-CT | 2 | Rel-12 | C4 | 2014-09-12 08:00 | 2014-12-09 17:00 | 100% | CP-140493 | CP-140487 | Huawei | Xiaoyan SHI (sean.shixiaoyan@huawei.com) | Stage 2/3. CP#65 exception in CP-140487. LM70->100 | 23.007, 23.008, 29.274, 29.281 | 65 | 33 |  |  | Tue 29/07/14 | Thu 04/12/14
3045 | 680070 | UE Conformance Test Aspects - Dual connectivity for LTE | LTE_SC_enh_dualC-UEConTest | 2 | Rel-12 | R5 | 2015-06-15 08:00 | 2017-09-15 17:00 | 100% | RP-150840 |  | Ericsson |  | tested Core part: LTE_SC_enh_dualC-Core 29/09/15: Compl:0%->3% 29/09/15: Stat Rep: -->RP-1511671/1/16: Compl:3%->15%1/1/16: CD:Tue 15/03/16->Wed 15/06/16; ; |  | 68 | 35 |  |  | Fri 03/07/15 | Tue 19/09/17
3046 | 620041 | E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1 | 1 | Rel-12 | R1,R2,R4 | 2013-12-15 | 2017-06-15 17:00 | 100% | RP-141459 | - | Huawei | Elean FAN (fanxiaoan@huawei.com) | Triggered by TR 36.872 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects (UID_580041) | LTE | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
3047 | 620141 | Core part: E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1-Core | 2 | Rel-12 | R1,R2,R4 | 2013-12-15 | 2014-12-15 17:00 | 100% | RP-141459 | RP-141899 | Huawei | Elean FAN (fanxiaoan@huawei.com) | ; CD:Tue 12/05/15->Mon 15/12/14; WID: RP-130848->RP-140522; Stat Rep: RP-141632->RP-141899 | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.413, 36.423, 36.443 | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
3048 | 620241 | Perf. part: E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1-Perf | 2 | Rel-12 | R4 | 2013-12-15 | 2015-06-15 17:00 | 100% | RP-141459 | RP-150690 | Huawei | Elean FAN (fanxiaoan@huawei.com) | ; CD:Wed 18/03/15->Sun 15/03/15; WID: RP-130848->RP-140522; Stat Rep: RP-141632->RP-141899 1st Apr 15: Compl:40%->80% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141899->RP-150173 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP- | 36.101, 36.104, 36.133, 36.141 | 62 | 32 |  |  | Mon 09/12/13 | Thu 18/06/15
3049 | 680068 | UE Conformance Test Aspects - E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1-UEConTest | 2 | Rel-12 | R5 | 2015-06-15 08:00 | 2017-06-15 17:00 | 100% | RP-160414 |  | Huawei |  | tested Core part: LTE_SC_enh_L1-Core 29/09/15: Compl:0%->10% 29/09/15: CD:Wed 15/06/16->Thu 15/12/16 29/09/15: Stat Rep: -->RP-151247; 1/1/16: Compl:10%->40%; |  | 68 | 35 |  |  | Fri 03/07/15 | Mon 19/06/17
3050 | 620047 | Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB | 1 | Rel-12 | R3,R1 | 2013-12-15 | 2014-12-12 17:00 | 100% | RP-140983 | - | Samsung | Sung Hwan Won (sunghwan.won@samsung.com) | Stage 3. Rel-11 did not address support of a network interface for CoMP involving multiple eNBs with non-ideal backhaul (affected operators might not take advantage of performance benefit from inter-eNB CoMP operation). | LTE | 62 | 32 |  |  | Sat 07/12/13 | Sat 07/12/13
3051 | 620147 | Core part: Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB-Core | 2 | Rel-12 | R3,R1 | 2013-12-15 | 2014-12-12 17:00 | 100% | RP-140983 | RP-141804 | Samsung | Sung Hwan Won (sunghwan.won@samsung.com) | CD:Thu 11/12/14->Mon 15/12/14; Compl:85%->100%; Stat Rep: RP-140597->RP-141804 | 36.300, 36.423 | 62 | 32 |  |  | Sat 07/12/13 | Mon 12/01/15
3052 | 630031 | Smart Congestion Mitigation in E-UTRAN | SCM_LTE | 1 | Rel-12 | R2,S1,C1 | 2014-03-05 08:00 | 2015-09-15 17:00 | 100% | RP-140434 | - | LG Electronics | youngdae.lee@lge.com | follow-up of TR 36.848 FS_SCM_LTE | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
3053 | 630131 | Core part: Smart Congestion Mitigation in E-UTRAN | SCM_LTE-Core | 2 | Rel-12 | R2 | 2014-03-06 08:00 | 2014-09-12 17:00 | 100% | RP-140434 | RP-141292 | LG Electronics | youngdae.lee@lge.com | RP#65 completed | 36.331 | 63 | 32 |  |  | Mon 10/03/14 | Sun 21/09/14
3054 | 640105 | Stage 1 Prioritization of Multimedia Telephony (MMTel) and Mobile Originating-SMS for Access Class Barring (ACB) | - | 2 | Rel-12 | S1 | 2014-03-05 08:00 | 2014-03-07 17:00 | 100% | CP-140286 | - | - | - | SP#63 SP-140065 CR under TEI12 | 22.011 | 64 | 33 |  |  | Mon 07/04/14 | Mon 07/04/14
3055 | 640005 | CT aspects of Smart Congestion Mitigation in E-UTRAN (Stage 3) | SCM_LTE-CT | 2 | Rel-12 | C1 | 2014-06-13 08:00 | 2014-09-11 17:00 | 100% | CP-140286 | - | LG Electronics | Kim, Jaehyun (jaehyun7.kim@lge.com) | CP#65 completed | 24.173, 24.301, 24.341, 27.007 | 64 | 33 |  |  | Mon 07/04/14 | Mon 28/07/14
3056 | 670051 | UE Conformance Test Aspects - Smart Congestion Mitigation in E-UTRAN | SCM_LTE-UEConTest | 2 | Rel-12 | R5 | 2015-03-16 08:00 | 2015-09-15 17:00 | 100% | RP-150797 | RP-151445 | NTT DOCOMO |  | 03/07/15: Compl:0%->60% 03/07/15: WID: RP-150202->RP-150797 03/07/15: Stat Rep: ->RP-150794 29/09/15: Compl:60%->100% 29/09/15: Stat Rep: RP-150794->RP-151445 |  | 67 | 34 |  |  | Wed 01/04/15 | Tue 29/09/15
3057 | 630032 | Positioning Enhancements for RF Pattern Matching in E-UTRA | LCS_LTE_RFPMT | 1 | Rel-12 | R3,R2 | 2014-04-25 08:00 | 2014-06-13 17:00 | 100% | RP-140177 | - | Polaris Wireless | Gordon Scot (sgordon@polariswireless.com) | follow-up of TR 36.809 FS_LCS_LTE_RFPMT | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
3058 | 630132 | Core part: Positioning Enhancements for RF Pattern Matching in E-UTRA | LCS_LTE_RFPMT-Core | 2 | Rel-12 | R3,R2 | 2014-04-25 08:00 | 2014-06-13 17:00 | 100% | RP-140177 | RP-140591 | Polaris Wireless | Gordon Scot (sgordon@polariswireless.com) | RP#64 completed | 36.305, 36.455 | 63 | 32 |  |  | Mon 10/03/14 | Thu 12/06/14
3059 | 630046 | Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS | 1 | Rel-12 | R1,R2,R4,R3 | 2014-03-11 08:00 | 2017-03-15 17:00 | 100% | RP-141634 | - | MediaTek | Craig.Burnet@mediatek.com | follow-up of TR 36.866 FS_LTE_NAICS | LTE | 63 | 32 |  |  | Mon 10/03/14 | Tue 09/09/14
3060 | 630146 | Core part: Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS-Core | 2 | Rel-12 | R1,R2,R4,R3 | 2014-07-11 10:40 | 2014-12-15 17:00 | 100% | RP-141634 | RP-141866 | MediaTek | Craig.Burnet@mediatek.com | CD:Mon 08/12/14->Mon 15/12/14; Compl:95%->100%; Stat Rep: RP-141621->RP-141866 | 36.211, 36.213, 36.300, 36.331, 36.423 | 63 | 32 |  |  | Mon 10/03/14 | Mon 12/01/15
3061 | 630246 | Perf. part: Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS-Perf | 2 | Rel-12 | R4 | 2014-03-11 08:00 | 2015-09-15 17:00 | 100% | RP-151297 | RP-151296 | MediaTek | Craig.Burnet@mediatek.com | CD:Fri 12/06/15->Mon 15/06/15; Compl:0%->25%; Stat Rep: RP-141621->RP-141866 1st Apr 15: Compl:25%->50% 1st Apr 15: Stat Rep: RP-141866->RP-150179 03/07/15: Compl:50%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150179->RP-150862 | 36.101 | 63 | 32 |  |  | Mon 10/03/14 | Tue 29/09/15
3062 | 690070 | UE Conformance Test Aspects: Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS-UEConTest | 2 | Rel-12 | R5 | 2015-09-15 08:00 | 2017-03-15 17:00 | 100% | RP-160265 |  | Mediatek |  | tested: LTE_NAICS was a REL-12 RAN1 WI; 1/1/16: Compl:0%->35%; 1/1/16: WID: RP-151298->RP-151945; |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 21/03/17
3063 | 630047 | Performance requirements of interference cancellation and suppression receiver for SU-MIMO | LTE_SUMIMO_RX | 1 | Rel-12 | R4 | 2014-03-06 08:00 | 2015-12-15 17:00 | 100% | RP-140520 | - | Huawei | Qian Cheng (Q.Cheng@Huawei.com) | no Core part | LTE | 63 | 32 |  |  | Mon 10/03/14 | Mon 10/03/14
3064 | 630147 | Perf. part: Performance requirements of interference cancellation and suppression receiver for SU-MIMO | LTE_SUMIMO_RX-Perf | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 100% | RP-140520 | RP-150229 | Huawei | Qian Cheng (Q.Cheng@Huawei.com) | CD:Fri 13/03/15->Sun 15/03/15; Compl:50%->80%; Stat Rep: RP-141255->RP-141906 1st Apr 15: Compl:80%->100% 1st Apr 15: Stat Rep: RP-141906->RP-150229 | 36.101 | 63 | 32 |  |  | Mon 10/03/14 | Wed 01/04/15
3065 | 670052 | UE Conformance Test Aspects - Performance Requirements of Interference Cancellation and Suppression Receiver for SU-MIMO for E-UTRA | LTE_SUMIMO_RX-UEConTest | 2 | Rel-12 | R5 | 2015-03-16 08:00 | 2015-12-15 17:00 | 100% | RP-151819 | RP-151245 | Huawei |  | 03/07/15: Compl:0%->5% 03/07/15: Stat Rep: ->RP-150692 29/09/15: Compl:5%->55% 29/09/15: WID: RP-150245->RP-151463 29/09/15: Stat Rep: RP-150692->RP-1512451/1/16: Compl:55%->100%1/1/16: CD:Tue 15/03/16->Tue 15/1 |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/01/16
3066 | 580028 | HSPA signalling enhancements for more efficient resource usage for LCR | LCR_TDD_HSPA_sign_enh | 1 | Rel-12 | R1,R2,R3,R4 | 2012-12-11 08:00 | 2013-12-20 17:00 | 100% | RP-121984 | - | CATT | Yanping Xing (xingyanping@catt.cn) | Stage 2/3. Triggered by Rel-11 TR 25.874 Study on HSPA feedback and signalling efficiency enhancements for LCR TDD (FS_LCRTDD_HSPAenh) UID_540026 | UTRA | 58 | 30 |  |  | Mon 10/12/12 | Mon 10/12/12
3067 | 580128 | Core part: HSPA signalling enhancements for more efficient resource usage for LCR TDD | LCR_TDD_HSPA_sign_enh-Core | 2 | Rel-12 | R1,R2,R3 | 2012-12-15 | 2013-12-20 17:00 | 100% | RP-121984 | RP-131499 | CATT | Yanping Xing (xingyanping@catt.cn) | Prev CD:Fri 06/12/13; Prev %:100% | 25.222, 25.224, 25.331, 25.423, 25.433 | 58 | 30 |  |  | Mon 10/12/12 | Mon 08/12/14
3068 | 580228 | Perf. part: HSPA signalling enhancements for more efficient resource usage for LCR TDD | LCR_TDD_HSPA_sign_enh-Perf | 2 | Rel-12 | R4 | 2012-12-11 08:00 | 2013-09-06 17:00 | 100% | RP-121984 | RP-130968 | CATT | Yanping Xing (xingyanping@catt.cn) | RP#61 completed | 25.102 | 58 | 30 |  |  | Mon 10/12/12 | Fri 30/08/13
3069 | 600017 | HNB Positioning for UTRA | UTRA_HNB_Pos | 1 | Rel-12 | R3 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-132037 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#62 completed | UTRA | 60 | 31 |  |  | Mon 17/06/13 | Mon 09/12/13
3070 | 600117 | Core part: HNB Positioning for UTRA | UTRA_HNB_Pos-Core | 2 | Rel-12 | R3 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-132037 | RP-131974 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#62 closed at 85% completion. Not completed work on HNB positioning / No consensus (may be TEI12, if contribution and support). Updated WID RP-130868=>RP-132037 (HNB positiong was not addressed in this WI, however it was NOT remoded from the WID) | 25.305, 25.467, new TS 25.470 | 60 | 31 |  |  | Mon 17/06/13 | Mon 09/12/13
3071 | 610025 | Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh | 1 | Rel-12 | R1,R2,R3,R4 | 2013-09-15 | 2016-06-15 17:00 | 100% | RP-140771 | - | Qualcomm | arjunb@qti.qualcomm.com | Triggered by Rel-12 TR 25.702 Study on Dedicated Channel (DCH) enhancements for UMTS (FS_UTRA_DCHenh) UID_580040. Stage 2/3 | UTRA | 61 | 31 |  |  | Sat 07/09/13 | Tue 09/09/14
3072 | 610125 | Core part: Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh-Core | 2 | Rel-12 | R1,R2,R3,R4 | 2013-11-18 10:00 | 2014-09-12 17:00 | 100% | RP-140771 | RP-141137 | Qualcomm | arjunb@qti.qualcomm.com | RP#65 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433 | 61 | 31 |  |  | Sat 07/09/13 | Tue 09/09/14
3073 | 610225 | Perf. part: Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh-Perf | 2 | Rel-12 | R4 | 2013-09-15 | 2014-12-15 17:00 | 100% | RP-140771 | RP-141970 | Qualcomm | arjunb@qti.qualcomm.com | ; Stat Rep: RP-141137->RP-141970 | 25.101, 25.104, 25.133 | 61 | 31 |  |  | Sat 07/09/13 | Mon 12/01/15
3074 | 670053 | UE Conformance Test Aspects - DCH Enhancements for UMTS | UTRA_DCHenh-UEConTest | 2 | Rel-12 | R5 | 2015-03-16 08:00 | 2016-06-15 17:00 | 100% | RP-160384 | RP-151279 | Qualcomm | NA | 03/07/15: Compl:0%->15% 03/07/15: Stat Rep: ->RP-150764 29/09/15: Compl:15%->50% 29/09/15: CD:Tue 15/12/15->Wed 15/06/16 29/09/15: Stat Rep: RP-150764->RP-1512791/1/16: Compl:50%->65%; |  | 67 | 34 |  |  | Wed 01/04/15 | Fri 01/07/16
3075 | 610026 | UMTS Mobility enhancements for heterogeneous networks | UTRA_HetNet_mob | 1 | Rel-12 | R2,R3,R4 | 2013-07-23 09:12 | 2014-06-13 17:00 | 100% | RP-132039 | - | Huawei | Xudong Yang (yangxudong@huawei.com) | Triggered by Rel-12 TR 25.800 Study on UMTS heterogeneous networks (FS_UTRA_hetnet) UID_570024. Stage 2/3 | UTRA | 61 | 31 |  |  | Sat 07/09/13 | Sat 07/09/13
3076 | 610126 | Core part: UMTS Mobility enhancements for heterogeneous networks | UTRA_HetNet_mob-Core | 2 | Rel-12 | R2,R3,R4 | 2013-07-23 09:12 | 2014-06-13 17:00 | 100% | RP-132039 | RP-140636 | Huawei | Xudong Yang (yangxudong@huawei.com) | RP#64 completed. TS 25.300v100 for 1-step Approval | 25.101, 25.104, 25.133, 25.141, 25.304, 25.306, 25.331, 25.433, new TS 25.300 | 61 | 31 |  |  | Sat 07/09/13 | Thu 12/06/14
3077 | 610226 | Perf. part: UMTS Mobility enhancements for heterogeneous networks | UTRA_HetNet_mob-Perf | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2014-06-13 17:00 | 100% | RP-132039 | RP-140636 | Huawei | Xudong Yang (yangxudong@huawei.com) | RP#64 completed | 25.101, 25.104, 25.133, 25.141 | 61 | 31 |  |  | Sat 07/09/13 | Thu 12/06/14
3078 | 620054 | UMTS Heterogeneous Networks enhancements | UTRA_HetNet_enh | 1 | Rel-12 | R1,R2,R3,R4 | 2013-12-06 08:00 | 2014-12-15 17:00 | 100% | RP-141701 | - | Huawei | carmela.cozzo@huawei.com | Triggered by the 2nd part of TR 25.800 (FS_UTRA_HetNet); the 1st part is addressed by UTRA_HetNet_mob UID_610026 | UTRA | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
3079 | 620154 | Core part: Heterogeneous Networks enhancements | UTRA_HetNet_enh-Core | 2 | Rel-12 | R1 | 2013-12-06 08:00 | 2014-09-12 17:00 | 100% | RP-141701 | RP-141702 | Huawei | carmela.cozzo@huawei.com | RP#65 completed. Updated WID RP-140463=>RP-141701 | 25.101, 25.211, 25.212, 25.213, 25.214, 25.300, 25.302, 25.306, 25.308, 25.319, 25.331, 25.423, 25.433 | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
3080 | 620254 | Perf. part: Heterogeneous Networks enhancements | UTRA_HetNet_enh-Perf | 2 | Rel-12 | R4 | 2013-12-15 | 2014-12-15 17:00 | 100% | RP-141701 | RP-141898 | Huawei | carmela.cozzo@huawei.com | ; Stat Rep: RP-141702->RP-141898 | 25.101, 25.104, 25.133, 25.141 | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
3081 | 620055 | Enhanced Broadcast of System Information | UTRA_SIBenh | 1 | Rel-12 | R2,R1,R3,R4 | 2013-12-06 08:00 | 2014-12-15 17:00 | 100% | RP-140131 | - | Ericsson | martin.van.der.zee@ericsson.com | Triggered by Rel-12 UTRA TR 25.704 Study on Enhanced Broadcast of System Information (FS_UTRA_SIBenh) | UTRA | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
3082 | 620155 | Core part: Enhanced Broadcast of System Information | UTRA_SIBenh-Core | 2 | Rel-12 | R2,R1,R3,R4 | 2013-12-06 08:00 | 2014-09-12 17:00 | 100% | RP-140131 | RP-141230 | Ericsson | martin.van.der.zee@ericsson.com | RP#65 completed | 25.211, 25.212 , 25.213, 25.214, 25.301, 25.302, 25.304, 25.306, 25.321, 25.331, 25.433 | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
3083 | 620255 | Perf. part: Enhanced Broadcast of System Information | UTRA_SIBenh-Perf | 2 | Rel-12 | R4 | 2013-12-15 | 2014-12-15 17:00 | 100% | RP-140131 | RP-142080 | Ericsson | martin.van.der.zee@ericsson.com | ; Stat Rep: RP-141230->RP-142080 | 25.101, 25.104, 25.133, 25.141 | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
3084 | 620049 | Further Enhanced Uplink (EUL) enhancements | EDCH_enh | 1 | Rel-12 | R2 | 2013-12-15 | 2015-03-13 17:00 | 100% | RP-140127 | - | Ericsson | mark.curran@ericsson.com | Triggered by Rel-12 UTRA TR 25.700 Study on Further Enhanced Uplink (EUL) enhancements (FS_EDCH_enh) | UTRA | 62 | 32 |  |  | Mon 09/12/13 | Mon 15/09/14
3085 | 620149 | Core part: Further Enhanced Uplink (EUL) enhancements | EDCH_enh-Core | 2 | Rel-12 | R2,R1,R3,R4 | 2013-12-15 | 2014-12-15 17:00 | 100% | RP-140127 | RP-141860 | Ericsson | mark.curran@ericsson.com | ; Stat Rep: RP-141684->RP-141860 | 25.211, 25.212, 25.214, 25.304, 25.306, 25.308, 25.319, 25.321, 25.331, 25.423, 25.425, 25.433, 25.435 | 62 | 32 |  |  | Mon 09/12/13 | Mon 12/01/15
3086 | 620249 | Perf. part: Further Enhanced Uplink (EUL) enhancements | EDCH_enh-Perf | 2 | Rel-12 | R4 | 2013-12-15 | 2015-03-13 17:00 | 100% | RP-140127 | RP-150062 | Ericsson | mark.curran@ericsson.com | ; CD:Wed 18/03/15->Sun 15/03/15; Stat Rep: RP-141684->RP-141860 1st Apr 15: Compl:75%->100% 1st Apr 15: Stat Rep: RP-141860->RP-150062 | 25.101, 25.104, 25.133, 25.141 | 62 | 32 |  |  | Mon 09/12/13 | Wed 01/04/15
3087 | 560018 | (Small) Technical Enhancements and Improvements for Rel-12 | TEI12 | 1 | Rel-12 | SP,CP,RP,GP | 2012-12-25 13:00 | 2014-09-16 17:00 | 100% | - | - | - | - | - | - | 56 | 29 |  |  | Fri 13/07/12 | Fri 06/12/13
3088 | 660032 | (IETF) (Small) Technical Enhancements and Improvements for Rel-12 (draft-ietf-insipid-session-id) | TEI12_IETF | 1 | Rel-12 | C1-IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 100% | CP-140815 |  | Alcatel-Lucent |  | Mar15: In WGLC; 21/3/17: 50%->100 | draft-ietf-insipid-session-id | 66 | 34 |  |  | Thu 04/12/14 | Tue 21/03/17
3089 | 610001 | Test - (Small) Technical Enhancements and Improvements for Rel-12 | TEI12_Test | 1 | Rel-12 | R5,G3new | 2014-10-24 13:00 | 2015-12-11 17:00 | 100% | - | - | - | - | - | - | 61 | 31 |  |  | Mon 29/07/13 | Mon 29/07/13
3090 | 0 | Release 12 Studies | - | 1 | Rel-12 | SP,CP,GP,RP | 2013-08-05 13:00 | 2014-09-16 17:00 | 80% | - | - | - | - | - | - | - | - |  |  | Thu 08/09/11 | Thu 15/09/11
3091 | 470020 | Study on Alternatives to E.164 for Machine-Type Communications | FS_AMTC | 1 | Rel-12 | S1 | 2010-03-25 08:00 | 2012-03-07 17:00 | 100% | SP-100198 | - | T-Mobile USA | gary.jones@T-Mobile.com | SP#55 completed. Determine an alternative to E.164 for identifying individual devices and route messages between those devices | 22.988 | 47 | 24 |  |  | Tue 23/03/10 | Wed 22/02/12
3092 | 480032 | Study on enhancements for Machine-Type Communications (MTC) | FS_MTCe | 1 | Rel-12 | S1 | 2010-06-10 08:00 | 2013-03-06 17:00 | 100% | SP-100448 | - | Huawei | laurence.meriau@huawei.com | SP#59 completed. TR 22.888 v100 for Information & Approval. Study addition of new MTC-related use cases and functionality and improvements to existing requirements in TS 22.368 | 22.888 | 48 | 25 |  |  | Fri 28/05/10 | Tue 19/02/13
3093 | 490035 | Study on Integration of Single Sign-On (SSO) frameworks with 3GPP networks | FS_SSO_Int | 1 | Rel-12 | S1 | 2010-09-23 08:00 | 2012-03-07 17:00 | 100% | SP-100640 | - | InterDigital | christopher.wallace@interdigital.com | SP#55 completed. Linked to SA3 Study on Single Sign On (SSO) Application Security for IMS - based on SIP Digest (UID_480048), SA3 TR 33.924 Extended Identity Management (GBA-IdM) and SA3 TR 33.980 (LibSec) | 22.895 | 49 | 25 |  |  | Tue 31/08/10 | Wed 22/02/12
3094 | 500035 | Study on Continuity of Data Sessions to Local Networks | FS_CSN | 1 | Rel-12 | S1 | 2010-12-16 08:00 | 2011-12-14 17:00 | 100% | SP-100885 | - | NEC | joerg.swetina@neclab.eu | SP#54 completed. Linked to SA1 Rel-11 Feature UID_490030 SIPTO Service Continuity of IP Data Session (SIPTO_SC) | 22.896 | 50 | 26 |  |  | Thu 25/11/10 | Tue 29/11/11
3095 | 500036 | Study on non-MTC Mobile Data Applications Impacts | FS_MODAI | 1 | Rel-12 | S1 | 2010-12-16 08:00 | 2011-12-14 17:00 | 100% | SP-100889 | - | Huawei, China Mobile | Amar Deol (adeol@huawei.com), Gang Li | SP#54 completed. Linked to UID_490036 SA2 Rel-11 TR 23.843 Study on Core Network Overload solutions (FS_CNO) | 22.801 | 50 | 26 |  |  | Thu 25/11/10 | Tue 29/11/11
3096 | 530044 | Study on Proximity-based Services | FS_ProSe | 1 | Rel-12 | S1 | 2011-09-22 08:00 | 2013-03-05 17:00 | 100% | SP-110638 | - | Qualcomm | Rich Hovey (rhovey@qualcomm.com) | SP#59 completed | 22.803 | 53 | 27 |  |  | Thu 08/09/11 | Tue 19/02/13
3097 | 540027 | Study on User Plane Congestion management | FS_UPCON | 1 | Rel-12 | S1 | 2011-12-14 08:00 | 2012-09-12 17:00 | 100% | SP-110819 | - | KDDI | John Visser (jvisser@rogers.com) | SP#57 completed. Linked to SAPP (Service Awareness and Privacy Policies), FS_UMONC (Study on Usage Monitoring Control Enhancement), QoS_SSL (QoS Control Based on Subscriber Spending Limits) | 22.805 | 54 | 28 |  |  | Tue 29/11/11 | Tue 07/08/12
3098 | 540028 | Study on RAN Sharing Enhancements | FS_RSE | 1 | Rel-12 | S1 | 2011-12-14 08:00 | 2013-06-19 17:00 | 100% | SP-110820 | - | NEC | joerg.swetina@neclab.eu | SP#60 completed. Extend Rel-6 Network Sharing UID_31018 (basic scenarios of network/RAN sharing) to cover more complex scenarios that arise due to recent needs for more dynamic co-operation among operators | 22.852 | 54 | 28 |  |  | Tue 29/11/11 | Tue 18/06/13
3099 | 460025 | Deleted - Study on UICC/USIM enhancements | FS_U2e | 1 | Rel-12 | S1 | 2009-12-10 08:00 | 2012-03-07 17:00 | 100% | SP-090903 | - | Giesecke & Devrient | ilario.macchi@gi-de.com | SP#55 work stopped. Triggered by GSMA Smart SIM and 3GNBK projects, and to evolve from traditional USAT to multimedia USIM toolkit support, particularly to Smart Card Web Server | 22.817 | 46 | 24 | SP-55 | PCG-28 | Sun 06/12/09 | Sun 04/03/12
3100 | 490034 | Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | FS_IMS_P2P_CDS | 1 | Rel-12 | S2,S1,S3 | 2010-09-23 08:00 | 2012-12-12 17:00 | 100% | SP-120622 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | Triggered by TR 22.906 SA1 Study on IMS based Peer-to-Peer Content Distribution Services UID_450047 | 23.844 | 49 | 25 |  |  | Wed 15/09/10 | Thu 22/11/12
3101 | 490134 | SA1 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | FS_IMS_P2P_CDS | 2 | Rel-12 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-120622 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#53 completed | 23.844 | 49 | 25 |  |  | Wed 15/09/10 | Fri 08/06/12
3102 | 490234 | SA2 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | FS_IMS_P2P_CDS | 2 | Rel-12 | S2 | 2010-09-23 08:00 | 2012-06-20 17:00 | 100% | SP-120622 | - | China Mobile | Yu Qing (yuqing@chinamobile.com) | SP#56 completed. TR 23.844v100 for Information and Approval | 23.844 | 49 | 25 |  |  | Wed 15/09/10 | Thu 14/06/12
3103 | 570036 | SA3 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2) | FS_IMS_P2P_CDS | 2 | Rel-12 | S3 | 2012-09-12 08:00 | 2012-12-12 17:00 | 100% | SP-120622 | - | China Mobile | Zhu Judy(zhuhongru@chinamobile.com) | SP#58 completed. TR 33.844 v100 for Information and Approval | 33.844 | 57 | 29 |  |  | Tue 11/09/12 | Fri 02/11/12
3104 | 490036 | Study on Core Network Overload solutions | FS_CNO | 1 | Rel-12 | S2 | 2010-09-23 08:00 | 2013-12-11 17:00 | 100% | SP-120490 | - | Huawei | Mirko.Schramm@huawei.com | SP#62 completed. Linked to CT4 TR 23.857 Study on EPC Nodes Restoration (UID_490014) | 23.843 | 49 | 25 |  |  | Tue 31/08/10 | Thu 28/11/13
3105 | 490136 | Study on Core Network Overload solutions (Phase 1) | FS_CNO | 2 | Rel-12 | S2 | 2010-09-23 08:00 | 2012-12-12 17:00 | 100% | SP-120490 | - | Huawei | Mirko.Schramm@huawei.com | Phase 1: complete study of overload control related to MAP /Diameter signalling, other 3GPP Core Network signalling optimization | 23.843 | 49 | 25 |  |  | Tue 31/08/10 | Thu 30/08/12
3106 | 490236 | Study on Core Network Overload solutions (Phase 2) | FS_CNO | 2 | Rel-12 | S2 | 2010-09-23 08:00 | 2013-12-11 17:00 | 100% | SP-120490 | - | Huawei | Mirko.Schramm@huawei.com | SP#62 completed | 23.843 | 49 | 25 |  |  | Tue 31/08/10 | Thu 28/11/13
3107 | 500037 | Study on System Enhancements for Energy Efficiency | FS_SEEE | 1 | Rel-12 | S2 | 2010-12-16 08:00 | 2012-06-20 17:00 | 100% | SP-100888 | - | Huawei | frank.mademann@huawei.com | SP#56 completed | 23.866 | 50 | 26 |  |  | Thu 25/11/10 | Tue 19/06/12
3108 | 510061 | Study on S2a Mobility based On GTP and WLAN access to EPC | FS_SaMOG | 1 | Rel-12 | S2 | 2011-03-23 08:00 | 2013-09-11 17:00 | 100% | SP-120426 | - | ZTE | Tricci So (tso@zteusa.com) | SP#61 completed. Covers generic non-3GPP access (e.g. WLAN, WIMAX, CDMA/HRPD). Spin-off Feature SaMOG_WLAN. Linked to Rel-8 Support for non-3GPP accesses, Rel-10 SMOG, Rel-11 BBAI | 23.852 | 51 | 26 |  |  | Mon 21/02/11 | Thu 25/07/13
3109 | 560037 | Study on Optimized Offloading to WLAN in 3GPP-RAT Mobility | FS_WORM | 1 | Rel-12 | S2 | 2012-06-18 08:00 | 2013-09-11 17:00 | 100% | SP-120261 | - | BlackBerry | Steve Barrett (sbarrett@blackberry.com) | SP#61 completed. Linked to UID_350027 SAE for support for non-3GPP accesses (SAES-SA-FP_n3GPP), UID_410043 MAPIM, UID_450041 IFOM, UID_530046 SaMOG | 23.890 | 56 | 29 |  |  | Fri 11/05/12 | Thu 25/07/13
3110 | 560038 | Study on Application Based Charging | FS_ABC | 1 | Rel-12 | S2 | 2012-06-18 08:00 | 2013-03-06 17:00 | 100% | SP-120271 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#59 completed. Linked to Rel-11 Feature UID_500032 Service Awareness and Privacy Policies (SAPP) | 23.800 | 56 | 29 |  |  | Mon 04/06/12 | Wed 27/02/13
3111 | 410043 | Study on Multi Access PDN connectivity and IP flow Mobility | FS_MAPIM | 1 | Rel-12 | S2,S1 | 2008-08-08 08:19 | 2012-12-12 17:00 | 100% | SP-110452 | - | Qualcomm | Gerardo Giaretta (gerardog@qualcomm.com) | Spin-off Features MAPCON, IFOM. SP#58 completed FS_MAPIM part of 23.861 (continued under FS_NBIFOM) | 23.861 | 41 | 21 |  |  | Mon 15/09/08 | Wed 16/01/13
3112 | 410143 | SA1 part of Study on Multi Access PDN connectivity and IP flow Mobility | FS_MAPIM | 2 | Rel-12 | S1 | 2008-08-08 08:19 | 2011-09-21 17:00 | 100% | SP-110452 | - | Qualcomm | Gerardo Giaretta (gerardog@qualcomm.com) | SP#53 completed | 23.861 | 41 | 21 |  |  | Mon 15/09/08 | Wed 16/01/13
3113 | 410243 | SA2 part of Study on Multi Access PDN connectivity and IP flow Mobility | FS_MAPIM | 2 | Rel-12 | S2 | 2008-09-18 08:00 | 2012-12-12 17:00 | 100% | SP-110452 | - | Qualcomm | Gerardo Giaretta (gerardog@qualcomm.com) | SP#43 TR 23.861v100 for Information. SP#56 Rel-9 TR 23.861v130 renamed & progressed under new Study FS_NBIFOM. SP#58 completed the FS_MAPIM part of TR 23.861 (TR continued under FS_NBIFOM). | 23.861 | 41 | 21 |  |  | Mon 15/09/08 | Wed 16/01/13
3114 | 560039 | Deleted - Study on IP Flow Mobility support for S2a and S2b Interfaces | FS_NBIFOM | 1 | Rel-12 | S2 | 2012-06-18 08:00 | 2013-03-06 17:00 | 100% | SP-120742 | - | ZTE | Tricci So (tso@zteusa.com) | SP#59 stopped (at 40% completion). SP#56 revives dormant Study FS_MAPIM. TR 23.861 title changed from (Multi Access PDN connectivity and IP flow mobility) to (Network based IP flow mobility) | 23.861 | 56 | 29 | SP-59 | PCG-30 | Mon 04/06/12 | Wed 27/02/13
3115 | 480043 | Study on Extended IMS Media Plane Security features | FS_eMEDIASEC | 1 | Rel-12 | S3 | 2010-06-10 08:00 | 2013-03-06 17:00 | 100% | SP-100256 | - | Vodafone | Aguibou.Barry@vodafone.com | SP#59 completed. Continuation of Rel-9 Feature UID_430036 IMS Media Plane Security (MEDIASEC). Study solutions and extensions to features and functionality described in TR 33.828 and TS 33.328 | 33.829 | 48 | 25 |  |  | Wed 05/05/10 | Tue 19/02/13
3116 | 530047 | Deleted - Study on Firewall traversal (Stage 2) | FS_Fire | 1 | Rel-12 | S3 | 2011-06-17 08:00 | 2014-09-17 17:00 | 100% | SP-120849 | - | Acme Packet | Prashant Kumar (PKumar@acmepacket.com) | SP#65 stopped. Linked to Rel-12 Service and Media Reachability for Users over Restrictive Firewalls (SMURFs) UID_530043 | 33.830 | 53 | 27 | SP-65 | PCG-33 | Tue 19/07/11 | Wed 21/05/14
3117 | 550026 | Study on Security on spoofed call detection and prevention (Stage 2) | FS_SPOOF | 1 | Rel-12 | S3 | 2012-03-07 08:00 | 2014-09-17 17:00 | 100% | SP-120030 | - | China Mobile | lixiangjun@chinamobile.com | SP#65 completed. TR 33.831v100 for 1-step Approval. Linked to Rel-11 SPUCI TR 33.838 | 33.831 | 55 | 28 |  |  | Mon 20/02/12 | Wed 03/09/14
3118 | 570035 | Study on Security Assurance Methodology for 3GPP Network Elements | FS_SECAM | 1 | Rel-12 | S3 | 2012-09-13 08:00 | 2014-06-18 17:00 | 100% | SP-120654 | - | Orange | loic.habermacher@orange.com | SP#64 completed. Spin-off Rel-13 Feature SCAS. Study methodologies for specifying product security assurance and hardening requirements on 3GPP network elements (with associated test cases when feasible) | 33.805 | 57 | 29 |  |  | Fri 31/08/12 | Wed 21/05/14
3119 | 540033 | Study on Improved Support for Dynamic Adaptive Streaming over HTTP in 3GPP | FS_IS_DASH | 1 | Rel-12 | S4 | 2011-12-14 08:00 | 2014-09-16 17:00 | 100% | SP-140486 | - | Qualcomm | c_tstock@qualcomm.com | SP#65 completed. TR 26.938v200 for Approval. SP#60 TR 26.938v100 for Information. Linked to Feature UID_470034 HTTP-based Streaming and Download Services | 26.938 | 54 | 28 |  |  | Wed 14/12/11 | Fri 05/09/14
3120 | 610044 | Study on HTML5 for a new presentation layer in 3GPP services | FS_HTML5 | 1 | Rel-12 | S4 | 2013-09-12 08:00 | 2014-09-16 17:00 | 100% | SP-130357 | - | Samsung | Imed Bouazizi (i.bouazizi@sta.samsung.com) | SP#65 completed. TR 26.907v200 for Approval. SP#64 TR 26.907v100 for Information. | 26.907 | 61 | 31 |  |  | Mon 09/09/13 | Fri 05/09/14
3121 | 470050 | Study on version handling | FS_OAM_VH | 1 | Rel-12 | S5 | 2010-03-25 08:00 | 2012-12-12 17:00 | 100% | SP-100082 | - | Ericsson | thomas.tovinger@ericsson.com | SP#58 completed | 32.830 | 47 | 24 |  |  | Fri 12/02/10 | Wed 21/11/12
3122 | 510046 | Study on management of Heterogeneous Networks | FS_OAM_HetNet | 1 | Rel-12 | S5 | 2011-03-23 08:00 | 2014-06-18 17:00 | 100% | SP-130046 | - | Ericsson | ulf.hubinette@ericsson.com | SP#64 completed | 32.835 | 51 | 26 |  |  | Sat 02/06/12 | Tue 27/05/14
3123 | 540032 | Study on OAM aspects of Network Sharing | FS_OAM_SHARE | 1 | Rel-12 | S5 | 2011-12-07 08:00 | 2013-09-11 17:00 | 100% | SP-130044 | - | Alcatel-Lucent, Huawei | Padma.Sudarsan@alcatel-lucent.com, zoulan@huawei.com | SP#61 completed. Linked to Network Sharing UID_31018, SA1 22.951 (Service aspects and requirements for network sharing), SA2 23.251 (Network Sharing; Architecture) | 32.851 | 54 | 28 |  |  | Sat 02/06/12 | Wed 04/09/13
3124 | 560032 | Study on Enhanced Network Management (NM) centralized Coverage and Capacity Optimization | FS_SON_NM_CCO | 1 | Rel-12 | S5 | 2011-09-21 08:00 | 2014-09-17 17:00 | 100% | SP-140028 | - | Ericsson | robert.petersen@ericsson.com | SP#65 completed. TR 32.836v200 for Approval. SP#63 split of Rel-12 SP-130045 WID (Enhanced NM Centralized Coverage and Capacity Optimization) into a Rel-12 Study (SP-140028) and a Rel-13 Normative WID (SP-140060) | 32.836 | 56 | 29 |  |  | Wed 18/04/12 | Mon 25/08/14
3125 | 560336 | Study on WLAN management | FS_WLAN_OAM | 1 | Rel-12 | S5 | 2011-09-21 08:00 | 2014-09-17 17:00 | 100% | SP-150408 | - | Intel | joey.chou@intel.com | SP#65 revised WID SP-130042=>SP-140536 (split into Rel-12 Study & Rel-13 normative WI). Changed Title from "TR on WLAN impacts to Type-2 management interface to the 3GPP Network Manager". TR 32.841v200 for Approval. Completed; 14/09/15: WID:SP-140536-> | 28.680, 28.681, 28.682, 28.683, 28.403 | 56 | 29 |  |  | Tue 12/06/12 | Mon 14/09/15
3126 | 580052 | Study on Alarm Management | FS_OAM_AM | 1 | Rel-12 | S5 | 2012-12-07 08:00 | 2013-09-11 17:00 | 100% | SP-120774 | - | TeliaSonera | tommy.berggren@teliasonera.com | SP#61 completed | 32.859 | 58 | 30 |  |  | Wed 21/11/12 | Wed 04/09/13
3127 | 580025 | Study on Indication of Network to Network Interface (NNI) Routeing scenarios in SIP requests | FS_NNI_RS | 1 | Rel-12 | C3 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | CP-130166 | - | Ericsson | Jan.Holm@ericsson.com | CP#64 completed | 24.802 | 58 | 30 |  |  | Tue 20/11/12 | Wed 18/06/14
3128 | 580026 | Study on Diameter Overload Control Mechanisms | FS_DOCME | 1 | Rel-12 | C4 | 2012-01-05 15:53 | 2014-09-11 17:00 | 100% | CP-120917 | - | Orange | lionel.morand@orange.com | CP#65 completed. TR 29.809 v200 for Approval. Triggered by SA2 Rel-12 TR 23.843 Study on Core Network Overload solutions (FS_CNO) UID_490036. Coordinate with CT3, SA5 | 29.809 | 58 | 30 |  |  | Tue 20/11/12 | Mon 28/07/14
3129 | 590011 | Study on XML based access of AF to the PCRF | FS_XML_AF_PCRF | 1 | Rel-12 | C3 | 2013-03-01 08:00 | 2013-12-04 17:00 | 100% | CP-130167 | - | Alcatel-Lucent | horst.brinkman@alcatel-lucent.com | CP#64 completed. Investigate introducing an XML-based protocol (e.g. SOAP, Restful HTTP, etc.) between AF and PCRF for non-IMS applications | 29.817 | 59 | 30 |  |  | Sat 16/02/13 | Thu 19/06/14
3130 | 610010 | Study on Technical aspects on Roaming End-to-end scenarios with VoLTE IMS and other networks | FS_REVOLTE_IMS | 1 | Rel-12 | C3 | 2013-09-09 08:00 | 2014-12-09 17:00 | 100% | CP-130774 | - | Deutsche Telekom | Roland Jesske (r.jesske@telekom.de) | CP#65 completion 09/14=>12/14. CP#64 TR 29.949v100 for Information.Dec.14:95->100 | 29.949 | 61 | 31 |  |  | Sat 10/08/13 | Thu 04/12/14
3131 | 620001 | Study on Development of conformance requirements for the IP Multimedia Services Identity Module (ISIM) application support in ME | FS_ISIM_CR | 1 | Rel-12 | C6 | 2013-12-09 08:00 | 2014-12-09 17:00 | 100% | CP-130812 | - | Gemalto | ly-thanh.phan@gemalto.com | CP#65 completion 09/14=>12/14. Gathering of all ISIM-related conformance requirements and the assessment of CT6 coverage; June2015: Compl:30%->100 | 31.829 | 62 | 32 |  |  | Fri 22/11/13 | Mon 15/06/15
3132 | 620002 | Study on Shared Data Update for Multiple Subscribers | FS_SHARED_SubData_UPD | 1 | Rel-12 | C4 | 2013-12-06 08:00 | 2014-12-09 17:00 | 100% | CP-130809 | - | Huawei | Susan Shi (susan.shishufeng@huawei.com) | CP#65 TR 29.854v200 for Approval. Completion 09/14=>12/14. Dec.14: 80->85%. Mar.15: 100% | 29.854 | 62 | 32 |  |  | Tue 19/11/13 | Wed 04/03/15
3133 | 460001 | Study on GERAN improvements for Machine-Type Communications | FS_NIMTC_GERAN | 1 | Rel-12 | G1,G2 | 2010-05-24 08:00 | 2012-11-23 17:00 | 100% | GP-092418 | - | Ericsson | paul.schliwa-bertling@ericsson.com | GP#56 completed. GP#44 approved WID | 43.868 | 44 | 24 |  |  | Fri 20/11/09 | Fri 23/11/12
3134 | 520001 | Study on Voice services over Adaptive Multi-user channels on One Slot (VAMOS) enhancements | FS_eVAMOS | 1 | Rel-12 | GP,G2,G1 | 2010-10-27 15:16 | 2014-05-30 17:00 | 100% | GP-110991 | - | China Mobile, Huawei | Chao Luo (chluo@huawei.com), dengjuan@chinamobile.com | GP#62 completed. TR 43.801v100 for 1-step Approval. GP#50 approved WID. Triggered by Rel-8 TR 45.914 Study Multi-User-Reusing One Timeslot (MUROS) UID_50590 and Rel-9 VAMOS UID_420002 | 43.801 | 50 | 27 |  |  | Sat 21/05/11 | Fri 30/05/14
3135 | 520002 | Study on GERAN enhancements for Mobile Data Applications | FS_GERAN_eMDA | 1 | Rel-12 | G2,G1 | 2011-04-04 08:00 | 2014-08-29 17:00 | 100% | GP-110999 | - | Huawei | ming.fang@huawei.com | GP#63 completed. TR 43.802v200 for Approval. GP#50 approved WID (mobile coucou). Triggered by RAN#51 (Mar 2011) WID in RP-110454 (LTE RAN Enhancements for Diverse Data Applications) UID_510031 | 43.802 | 50 | 27 |  |  | Sat 21/05/11 | Fri 29/08/14
3136 | 500016 | Study on Inclusion of RF Pattern Matching Technologies as a positioning method in the E-UTRAN | FS_LCS_LTE_RFPMT | 1 | Rel-12 | R4 | 2010-12-10 08:00 | 2013-09-06 17:00 | 100% | RP-120885 | RP-131082 | Polaris Wireless | Scot Gordon (sgordon@polariswireless.com) | RP#61 completed. Linked to Rel-10 WI on Inclusion of RF Pattern Matching Technologies as a positioning method in the UTRAN (LCS_UMTS_RFPMT) UID_460005 | LTE 36.809 | 50 | 26 |  |  | Fri 10/12/10 | Wed 28/08/13
3137 | 530052 | Study on Provision of low-cost MTC UEs based on LTE | FS_LC_MTC_LTE | 1 | Rel-12 | R1,R2,R4 | 2011-09-19 08:00 | 2013-06-14 17:00 | 100% | RP-121441 | RP-130583 | Vodafone | prakash.bhat@vodafone.com | RP#60 completed | LTE 36.888 | 53 | 27 |  |  | Mon 19/09/11 | Fri 07/06/13
3138 | 530054 | Deleted - Study on Mobile Relay for E-UTRA | FS_LTE_mobRelay | 1 | Rel-12 | R3,R1 | 2005-05-19 14:36 | 2014-06-23 17:00 | 100% | RP-131375 | RP-140726 | CATT | Haijing Hu (huhaijing@catt.cn) | RP#64 stopped at 80% completion | LTE 36.836 | 53 | 27 | RP-64 | PCG-33 | Mon 19/09/11 | Mon 23/06/14
3139 | 570023 | Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN | FS_LTE_SC_enh_req | 1 | Rel-12 | RP | 2012-09-11 08:00 | 2012-12-07 17:00 | 100% | RP-121418 | RP-121651 | China Mobile | Hai TANG (tanghai@chinamobile.com) | RP#58 completed. TR 36.932 v100 for Information and Approval | LTE 36.932 | 57 | 29 |  |  | Mon 03/09/12 | Thu 06/12/12
3140 | 580041 | Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects | FS_LTE_SC_enh_L1 | 1 | Rel-12 | R1,R2,R4 | 2012-09-11 08:00 | 2013-09-06 17:00 | 100% | RP-122032 | RP-131618 | Huawei | Elean Fan (fanxiaoan@huawei.com) | RP#62 completed. RP#61 TR 36.872v100 for 1-step approval. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023 | LTE 36.872 | 58 | 30 |  |  | Mon 10/12/12 | Tue 03/12/13
3141 | 580044 | Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Higher-layer aspects | FS_LTE_SC_enh_hilayer | 1 | Rel-12 | R2,R3 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-122033 | RP-131619 | NTT DOCOMO | Hideaki Takahashi (h-takahashi@nttdocomo.co.jp) | RP#62 completed. Triggered by Rel-12 TR 36.932 Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN UID_570023 | LTE 36.842 | 58 | 30 |  |  | Mon 10/12/12 | Tue 03/12/13
3142 | 580038 | Study on LTE Device-to-Device Proximity Services - Radio Aspects | FS_LTE_D2D_Prox | 1 | Rel-12 | R1,R2,R3,R4 | 2012-12-17 08:00 | 2014-03-06 17:00 | 100% | RP-122009 | RP-140416 | Qualcomm | Shailesh Patil (patil@qti.qualcomm.com) | RP#63 completed. TR 36.843 for 1-step approval (90% complete). Started normative work. Linked to Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) and Feature ProSe | LTE 36.843 | 58 | 30 |  |  | Mon 10/12/12 | Fri 14/03/14
3143 | 580042 | Study on 3D-channel model for Elevation Beamforming and FD-MIMO studies for LTE | FS_LTE_3D_channel | 1 | Rel-12 | R1 | 2012-12-10 08:00 | 2014-09-12 17:00 | 100% | RP-141237 | RP-141206 | Nokia Networks | bishwarup.mondal@nsn.com | RP#65 completed. Updated WID RP-130811=>RP-141237. TR 36.873v210 for Approval. Enhance performance with 3D-beamforming or with FD-MIMO. Study new channel modelling in both vertical and horizontal dimensions awa user locations in the network | LTE 36.873 | 58 | 30 |  |  | Mon 10/12/12 | Sun 21/09/14
3144 | 580046 | Study on Energy Saving Enhancement for E-UTRAN | FS_Netw_Energy_enh_LTE | 1 | Rel-12 | R3 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-122035 | RP-140604 | China Mobile | Kimba Dit Adamou, Boubacar (jinba@chinamobile.com) | RP#64 completed. Identify potential solutions for energy saving in E-UTRAN non-overlapping scenario. Evaluate possible enhancements in overlapping scenario, so that a subset can be used for further investigation/standardization | LTE 36.887 | 58 | 30 |  |  | Mon 10/12/12 | Thu 12/06/14
3145 | 590016 | Study on Expansion of LTE_FDD_1670_US to include 1670-1680MHz Band for LTE in the US | FS_LTE_FDD_1670_US | 1 | Rel-13 | R4 | 2013-03-01 08:00 | 2014-12-15 17:00 | 100% | RP-130202 | RP-141815 | LightSquared | masoud.olfat@lightsquared.com | CD:Thu 11/12/14->Mon 15/12/14; Compl:80%->100%; Stat Rep: RP-141453->RP-141815 | LTE 36.844 | 59 | 30 |  |  | Tue 26/02/13 | Mon 12/01/15
3146 | 590017 | Study on Cell-specific Reference Signals (CRS) Interference Mitigation for homogenous deployments for LTE | FS_LTE_CRSIC | 1 | Rel-12 | R4 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-131840 | RP-131623 | Ericsson | shaohua.li@ericsson.com | RP#62 completed. Updated WID RP-130393=>RP-131840 | LTE 36.863 | 59 | 30 |  |  | Tue 26/02/13 | Thu 19/12/13
3147 | 590018 | Study on Network-Assisted Interference Cancellation and Suppression for LTE | FS_LTE_NAICS | 1 | Rel-12 | R1,R4 | 2013-03-08 08:00 | 2014-03-06 17:00 | 100% | RP-130404 | RP-132108 | MediaTek | jeff.zhuang@mediatek.com | RP#63 completed. TR 36.866 (90% complete) for Approval. Started normative work | LTE 36.866 | 59 | 30 |  |  | Tue 26/02/13 | Fri 14/03/14
3148 | 600015 | Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul | FS_COMP_LTE_nibackhaul | 1 | Rel-12 | R1 | 2013-06-18 08:00 | 2013-12-06 17:00 | 100% | RP-130847 | RP-131626 | Samsung | Hyojin Lee (hyojin257.lee@samsung.com) | RP#62 completed. Extension of Rel-11 CoMP Operation for LTE – Downlink UID_530332) | LTE 36.874 | 60 | 31 |  |  | Mon 17/06/13 | Tue 03/12/13
3149 | 610028 | Study on Group Communication for LTE | FS_LTE_GC | 1 | Rel-12 | R2,R3 | 2013-09-10 08:00 | 2014-03-06 17:00 | 100% | RP-131382 | RP-140182 | Alcatel-Lucent | chandrika.worrall@alcatel-lucent.com | RP#63 completed. Evaluate ability of LTE to meet public safety requirements agreed in SA for GC (GC is a key functionality of Land Mobile Radio/Private Mobile Radio and public safety systems) | LTE 36.868 | 61 | 31 |  |  | Sat 07/09/13 | Fri 14/03/14
3150 | 610029 | Study on Smart Congestion Mitigation in E-UTRAN | FS_SCM_LTE | 1 | Rel-12 | R2 | 2013-09-09 08:00 | 2014-03-06 17:00 | 100% | RP-132092 | RP-140102 | LG Electronics | youngdae.lee@lge.com | RP#63 completed | LTE 36.848 | 61 | 31 |  |  | Sat 07/09/13 | Fri 14/03/14
3151 | 620044 | Study on RAN aspects of RAN Sharing Enhancements for LTE | FS_RSE-RAN_LTE | 1 | Rel-12 | R3 | 2013-12-06 08:00 | 2014-06-13 17:00 | 100% | RP-132116 | RP-140746 | NEC | Siva.Vakeesar@emea.nec.com | RP#64 completed. TR 36.856v100 for 1-step approval. Triggered by SA1 Re-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE) and Rel-13 Feature RSE (TS 22.101 Stage 1) | LTE 36.856 | 62 | 32 |  |  | Wed 27/11/13 | Thu 12/06/14
3152 | 530056 | Study on RF and EMC requirements for active Antenna Array System (AAS) Base Station | FS_AAS_BS_LTE_UTRA | 1 | Rel-12 | R4,R1 | 2011-09-19 08:00 | 2013-03-01 17:00 | 100% | RP-111349 | RP-130124 | Huawei | Ronnie.zhang@huawei.com | RP#59 completed | UTRA, LTE 37.840 | 53 | 27 |  |  | Mon 19/09/11 | Thu 28/02/13
3153 | 550020 | Study on LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON | FS_LTE_HRPD_SON | 1 | Rel-12 | R3 | 2012-03-02 08:00 | 2013-06-14 17:00 | 100% | RP-121982 | RP-130585 | China Telecom | Wu Jinlian (wujl@gsta.com) | RP#60 completed | UTRA, LTE 37.813 | 55 | 28 |  |  | Thu 23/02/12 | Wed 05/06/13
3154 | 550021 | Study on Passive InterModulation (PIM) handling for UTRA and LTE Base Stations | FS_BS_PIM | 1 | Rel-12 | R4,G1 | 2012-03-05 08:00 | 2013-09-06 17:00 | 100% | RP-120268 | RP-131076 | Ericsson | johan.skold@ericsson.com | RP#61 completed (Conclusion: no spin-off WI). Linked to Rel-10 WI on Multi-standard radio Base Station RF requirements for non-contiguous spectrum deployments (MSR_NC) UID_480025 | UTRA, LTE 37.808 | 55 | 28 |  |  | Thu 23/02/12 | Fri 30/08/13
3155 | 580045 | Study on WLAN/3GPP Radio Interworking | FS_UTRA_LTE_WLAN_interw | 1 | Rel-12 | R2 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-122038 | RP-131611 | Intel | sasha.sirotkin@intel.com | RP#62 completed. Evaluate LTE-WLAN/UTRA-WLAN i/w procedures while improving (non-)seamless mobility. Deployed WLAN often under-utilized; User experience suboptimal when UE connects to overloaded WLAN. | UTRA, LTE 37.834 | 58 | 30 |  |  | Mon 10/12/12 | Tue 03/12/13
3156 | 580047 | Study on RAN Enhancements for UMTS/HSPA and LTE Interworking | FS_HSPA_LTE_interworking | 1 | Rel-12 | R3 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-122036 | RP-131612 | China Unicom | Meng Zhang (zhangmeng68@chinaunicom.cn) | RP#62 completed. TR 37.852v100 for Information & Approval | UTRA, LTE 37.852 | 58 | 30 |  |  | Mon 10/12/12 | Tue 03/12/13
3157 | 580048 | Study on Next-Generation SON for UTRA and LTE | FS_UTRA_LTE_NG_SON | 1 | Rel-12 | R3 | 2012-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-122037 | RP-140747 | NSN | krzysztof.kordybach@nsn.com | RP#64 completed. The study of SON features for small cell functionality covered by the Rel-12 small cell enhancement SIs (e.g. dual connectivity) is not in the scope of this study item | UTRA, LTE 37.822 | 58 | 30 |  |  | Mon 10/12/12 | Thu 12/06/14
3158 | 580049 | Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands) | FS_UTRA_LTE_1980_2170_REG1 | 1 | Rel-12 | R4 | 2012-12-11 08:00 | 2014-09-12 17:00 | 100% | RP-140505 | RP-141099 | DISH Network | johny.kim@dish.com, mariam.sorond@dish.com | RP#65 completed. Within EU these bands can be used for terrestrial mobile as a complement to mobile satellite services. Study adding an FDD band into UTRA/E-UTRA in applicable countries of Region 1 | UTRA, LTE 37.846 | 58 | 30 |  |  | Mon 10/12/12 | Mon 22/09/14
3159 | 580050 | Study on Base Station specification structure | FS_BSspec_struc | 1 | Rel-12 | R4 | 2012-12-10 08:00 | 2013-06-14 17:00 | 100% | RP-122039 | RP-130580 | Ericsson | johan.skold@ericsson.com | RP#60 completed (1-step approval). Study new BS spec structure to avoid duplicate work for new RF features (in case of identical features among different RATs); avoid future discussions on how to implement new featurES in CP-150single-RAT/multi-RAT specs | UTRA, LTE, MSR 37.810 | 58 | 30 |  |  | Mon 10/12/12 | Fri 07/06/13
3160 | 590032 | Study on RAN aspects of Machine Type and other mobile data applications Communications enhancements | FS_MTCe_RAN | 1 | Rel-12 | R2 | 2013-03-01 08:00 | 2013-09-06 17:00 | 100% | RP-130396 | RP-131081 | ZTE | sergio.parolari@zteitaly.com | RP#61 completed | UTRA, LTE 37.869 | 59 | 30 |  |  | Tue 26/02/13 | Fri 30/08/13
3161 | 570024 | Study on UMTS heterogeneous networks | FS_UTRA_HetNet | 1 | Rel-12 | R1,R2,R3 | 2012-06-12 08:00 | 2013-09-06 17:00 | 100% | RP-121436 | RP-131606 | Huawei | carmela.cozzo@huawei.com | RP#62 completed | UTRA 25.800 | 57 | 29 |  |  | Mon 03/09/12 | Mon 02/12/13
3162 | 580039 | Study on Scalable UMTS FDD bandwidth | FS_UTRA_SCAL | 1 | Rel-12 | R1,R4 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-130221 | RP-132035 | China Unicom | Han Xiao (hanxiao91@chinaunicom.cn) | RP#62 completed. TR 25.701v200 for Approval | UTRA TR 25.701 | 58 | 30 |  |  | Mon 10/12/12 | Wed 18/12/13
3163 | 620046 | Deleted - Study on Scalable UMTS FDD bandwidth by Filtering | FS_UTRA_SCAL_FILT | 1 | Rel-12 | R1 | 2013-12-09 08:00 | 2014-06-13 17:00 | 100% | RP-132122 | RP-140988 | China Unicom | Han Xiao (hanxiao91@chinaunicom.cn) | RP#64 stopped at 85% completion. Follow-up of Rel-12 Study on scalable UMTS FDD bandwidth (FS_UTRA_SCAL). The result is captured in the same TR 25.701 | UTRA TR 25.701 | 62 | 32 | RP-64 | PCG-33 | Wed 27/11/13 | Thu 12/06/14
3164 | 580040 | Study on Dedicated Channel (DCH) enhancements for UMTS | FS_UTRA_DCHenh | 1 | Rel-12 | R1 | 2012-12-10 08:00 | 2013-09-06 17:00 | 100% | RP-130216 | RP-131073 | Qualcomm | Arjun Bharadwaj (arjunb@qti.qualcomm.com) | RP#61 completed | UTRA TR 25.702 | 58 | 30 |  |  | Mon 10/12/12 | Fri 07/06/13
3165 | 580043 | Study on Further Enhanced Uplink (EUL) enhancements | FS_EDCH_enh | 1 | Rel-12 | R2,R1,R3 | 2012-12-10 08:00 | 2013-12-06 17:00 | 100% | RP-130347 | RP-131608 | Ericsson | alessandro.caverni@ericsson.com | RP#62 completed. TR 25.700v100 for Approval. Identify potential solutions to increase the uplink capacity, coverage and end-user performance (e.g. latency, achievable rates, etc.) | UTRA TR 25.700 | 58 | 30 |  |  | Mon 10/12/12 | Mon 02/12/13
3166 | 600018 | Study on HNB Emergency Warning Area for UTRA | FS_HNB_warn_area | 1 | Rel-12 | R3 | 2013-06-18 08:00 | 2014-03-06 17:00 | 100% | RP-131258 | RP-140129 | Alcatel-Lucent, Ip.access | Martin.Warner@alcatel-lucent.com, Kit.kilgour@ipaccess.com | RP#63 completed. TR 25.703 v100 for 1-step approval | UTRA TR 25.703 | 60 | 31 |  |  | Mon 17/06/13 | Wed 26/02/14
3167 | 610027 | Study on Enhanced Broadcast of System Information | FS_UTRA_SIBenh | 1 | Rel-12 | R2,R1 | 2013-09-09 08:00 | 2013-12-06 17:00 | 100% | RP-131386 | RP-131610 | Ericsson | martin.van.der.zee@ericsson.com | RP#62 completed. TR 25.704v100 for Information & Approval. Study need to add capacity to present SI Broadcast mechanism unchanged since R99 | UTRA TR 25.704 | 61 | 31 |  |  | Sat 07/09/13 | Tue 03/12/13
3168 | 0 | Release 11 Features | - | 1 | Rel-11 | SP,CP,GP,RP | 2013-06-02 10:00 | 2014-09-16 17:00 | 100% | - | - | - | - | - | - | - | - |  |  | Wed 31/05/06 | Tue 18/02/14
3169 | 470051 | Advanced IP Interconnection of Services | IPXS | 1 | Rel-11 | S1,S2,C1,C3 | 2010-03-25 08:00 | 2012-09-12 17:00 | 100% | SP-100876 | - | Telefónica | chris.friel@O2.com | CP#58 completed. Triggered by Rel-10 TR 22.893 UID_380083 Study on advanced requirements for IP interconnect (FS_IPXS) | - | 47 | 24 |  |  | Tue 05/03/02 | Mon 19/11/12
3170 | 470052 | Stage 1 for Advanced IP Interconnection of Services | IPXS | 2 | Rel-11 | S1 | 2010-03-25 08:00 | 2011-09-21 17:00 | 100% | SP-100876 | - | Telefónica | chris.friel@O2.com | SP#53 completed | 22.101, 22.228 | 47 | 24 |  |  | Tue 05/03/02 | Wed 24/08/11
3171 | 500025 | Stage 2 for Advanced IP Interconnection of Services | IPXS | 2 | Rel-11 | S2 | 2010-12-16 08:00 | 2011-12-14 17:00 | 100% | SP-100876 | - | Ericsson | fredrik.lindholm@ericsson.com | SP#54 completed | 23.228 | 50 | 26 |  |  | Wed 01/12/10 | Mon 28/11/11
3172 | 530004 | Stage 3 for Advanced IP Interconnection of Services | IPXS | 2 | Rel-11 | C1,C3 | 2011-09-13 08:00 | 2012-09-12 17:00 | 100% | CP-110646 | - | Ericsson | christer.holmberg@ericsson.com | CP#58 completed | Stage 3 | 53 | 27 |  |  | Mon 29/08/11 | Mon 29/08/11
3173 | 530104 | CT1 part of Stage 3 for Advanced IP Interconnection of Services | IPXS | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-12 17:00 | 100% | CP-110646 | - | Ericsson | christer.holmberg@ericsson.com | CP#58 completed | 24.229 | 53 | 27 |  |  | Mon 29/08/11 | Mon 19/11/12
3174 | 530204 | CT3 part of Stage 3 for Advanced IP Interconnection of Services | IPXS | 3 | Rel-11 | C3 | 2011-09-13 08:00 | 2012-09-07 17:00 | 100% | CP-110646 | - | Ericsson | christer.holmberg@ericsson.com | CP#57 completed | 29.165 | 53 | 27 |  |  | Mon 29/08/11 | Mon 13/08/12
3175 | 480030 | System Improvements to Machine-Type Communications | SIMTC | 1 | Rel-11 | S1,S2,S5,C1,C3,C4,C6,R2,R3,R5 | 2009-12-10 08:00 | 2014-03-06 17:00 | 100% | SP-120848 | - | KPN | toon.norp@tno.nl | SP#58 completed. Updated WID SP-110877=>SP-120848. Enhancements to Rel-10 Feature UID_410031 (NIMTC) based on Rel-11 Study on enhancements to MTC | - | 48 | 25 |  |  | Fri 28/05/10 | Mon 12/11/12
3176 | 480130 | Stage 1 for SIMTC | SIMTC | 2 | Rel-11 | S1 | 2010-06-10 08:00 | 2011-09-21 17:00 | 100% | SP-120848 | - | KPN | toon.norp@tno.nl | SP#53 completed. SP#57 added MTC definitions in 21.905 | 22.368, 21.905 (MTC definitions) | 48 | 25 |  |  | Fri 28/05/10 | Mon 12/11/12
3177 | 480230 | TR on Stage 2 for SIMTC | SIMTC | 2 | Rel-11 | S2 | 2010-06-10 08:00 | 2012-09-12 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#57 completed. TR 23.888v200 for Approval. Was Rel-10 UID_450028 (TR on Stage 2 for NIMTC) | New TR 23.888 | 48 | 25 |  |  | Fri 28/05/10 | Mon 12/11/12
3178 | 520021 | BB1: Stage 2 Reachability Aspects of SIMTC | SIMTC-Reach | 2 | Rel-11 | S2 | 2011-06-09 08:00 | 2012-06-20 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#56 completed. SP#58 updated WID SP-110877=>S3-121111 (SA3 normative work on Security aspects of SIMTC incorporated in SA2 TS 23.682) | 23.221, New 23.368 | 52 | 27 |  |  | Thu 26/05/11 | Mon 12/11/12
3179 | 520121 | Deleted - MTC Feature Control (described in TS 22.368, clause 7.1.1 and 23.888, clause 5.7) | SIMTC-Reach | 3 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | - | 52 | 27 | SP-54 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
3180 | 520221 | On-line device trigger | SIMTC-Reach | 3 | Rel-11 | S2 | 2011-06-09 08:00 | 2012-06-20 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#56 completed | New 23.682 | 52 | 27 |  |  | Thu 26/05/11 | Mon 12/11/12
3181 | 520321 | MTC Addressing | SIMTC-Reach | 3 | Rel-11 | S2 | 2011-06-09 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 completed | 23.221, New 23.682 | 52 | 27 |  |  | Thu 26/05/11 | Mon 12/11/12
3182 | 520421 | Identifiers – especially removal of MSISDN dependencies in the architecture | SIMTC-Reach | 3 | Rel-11 | S2 | 2011-06-09 08:00 | 2012-06-20 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#56 completed | New 23.682 | 52 | 27 |  |  | Thu 26/05/11 | Mon 12/11/12
3183 | 520521 | MSISDN-less / PS-Only | SIMTC-Reach | 3 | Rel-11 | S2 | 2011-06-13 08:00 | 2012-03-07 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#55 completed | 23.060, 23.272, New 23.682 | 52 | 27 |  |  | Thu 26/05/11 | Mon 12/11/12
3184 | 540014 | MTC related interfaces and functional entities to support above features (MTCsp, etc.) | SIMTC-Reach | 3 | Rel-11 | S2 | 2011-12-14 08:00 | 2012-03-07 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#55 completed | New 23.682 | 54 | 28 |  |  | Fri 25/11/11 | Mon 12/11/12
3185 | 530006 | BB1: Stage 3 (CS+PS) Reachability Aspects of SIMTC | SIMTC-ReachCSPS | 2 | Rel-11 | C1,C3,C4,C6 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | 22/01: acronym modified | Stage 3 | 53 | 27 |  |  | Mon 29/08/11 | Thu 22/01/15
3186 | 530106 | CT1 part of Stage 3 BB1: Reachability Aspects of SIMTC | SIMTC-ReachCSPS | 3 | Rel-11 | C1 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | 22/01: acronym modified | 23.040, 24.008, 24.301, 24.341, 24.368 | 53 | 27 |  |  | Mon 29/08/11 | Thu 22/01/15
3187 | 530206 | CT3 part of Stage 3 BB1: Reachability Aspects of SIMTC | SIMTC-ReachCSPS | 3 | Rel-11 | C3 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | 22/01: acronym modified | 29.061, New TS 29.368 | 53 | 27 |  |  | Mon 29/08/11 | Thu 22/01/15
3188 | 530306 | CT4 part of Stage 3 BB1: Reachability Aspects of SIMTC | SIMTC-ReachCSPS | 3 | Rel-11 | C4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | 22/01: acronym modified | 23.003, 23.008, 29.002, 29.060, 29.230, New TS (29.336, 29.337) | 53 | 27 |  |  | Mon 29/08/11 | Thu 22/01/15
3189 | 530406 | CT6 part of Stage 3 BB1: Reachability Aspects of SIMTC | SIMTC-ReachCSPS | 3 | Rel-11 | C6 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | ST Ericsson | Andrzej Winiarski | 22/01: acronym modified | 31.102 | 53 | 27 |  |  | Mon 29/08/11 | Thu 22/01/15
3190 | 530005 | Stage 2/3 for CS aspects for SIMTC | SIMTC-CS | 2 | Rel-11 | C4,C1,C6 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed. Updated WID CP-120418=>CP-120617 | Stage 2/3 | 53 | 27 |  |  | Mon 29/08/11 | Mon 13/08/12
3191 | 530105 | Deleted - Stage 2 CS aspects for SIMTC | SIMTC-CS | 3 | Rel-11 | C4 | 2011-09-16 08:00 | 2012-09-06 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 stopped | 23.012 | 53 | 27 | CP-57 | PCG-29 | Mon 29/08/11 | Mon 13/08/12
3192 | 530205 | Stage 3 CS aspects for SIMTC | SIMTC-CS | 3 | Rel-11 | C1,C6 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed | Stage 3 | 53 | 27 |  |  | Fri 15/06/12 | Mon 13/08/12
3193 | 530305 | CT1 part of Stage 3 CS aspects for SIMTC | SIMTC-CS | 4 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed | 24.008, 24.301 | 53 | 27 |  |  | Fri 15/06/12 | Mon 13/08/12
3194 | 530405 | Deleted - CT6 part of Stage 3 CS aspects for SIMTC | SIMTC-CS | 4 | Rel-11 | C6 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 stopped | 31.102 | 53 | 27 | CP-57 | PCG-29 | Fri 15/06/12 | Mon 13/08/12
3195 | 560002 | Stage 2/3 for SMS in MME architecture option and related PS-only service subscription | SIMTC-PS_Only | 2 | Rel-11 | C1,C4 | 2012-06-15 08:00 | 2012-12-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#58 completed | Stage 2/3 | 56 | 29 |  |  | Mon 23/04/12 | Sat 17/11/12
3196 | 560102 | CT1 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription | SIMTC-PS_Only | 3 | Rel-11 | C1 | 2012-06-15 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed | 23.040, 24.008, 24.011, 24.301, 29.018, 29.118 | 56 | 29 |  |  | Mon 23/04/12 | Tue 14/08/12
3197 | 560202 | CT4 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription | SIMTC-PS_Only | 3 | Rel-11 | C4 | 2012-06-15 08:00 | 2012-12-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#58 completed. TS 29.338 v200 for Approval | 23.003, 23.008, 23.012, 29.002, 29.272, 29.305, New TS 29.338 | 56 | 29 |  |  | Mon 23/04/12 | Wed 28/11/12
3198 | 530009 | RAN overload control for Machine-Type Communications | SIMTC-RAN_OC | 2 | Rel-11 | R2,R3,C1,C6 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | RP-111373 | - | Huawei | Jeff Gao (gaoyongqiang@huawei.com) | Stage 2,3. TSG#57 completed | UTRA, LTE | 53 | 27 |  |  | Thu 15/09/11 | Thu 06/09/12
3199 | 530109 | Core part: RAN overload control for Machine-Type Communications | SIMTC-RAN_OC-Core | 3 | Rel-11 | R2,R3 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-111373 | - | Huawei | Jeff Gao (gaoyongqiang@huawei.com) | RP#57 completed | 25.304, 25.331, 25.413, 36.304, 36.331, 36.413 | 53 | 27 |  |  | Thu 15/09/11 | Thu 06/09/12
3200 | 530209 | Stage 3 (CS+PS) Extended Access Barring for UTRAN and E-UTRAN | SIMTC-RAN_OC | 3 | Rel-11 | C1,C6 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#57 completed. Updated WID CP-120418=>CP-120617 | Stage 3 | 53 | 27 |  |  | Mon 29/08/11 | Fri 24/08/12
3201 | 530309 | CT1 part of Stage 3 Extended Access Barring for UTRAN and E-UTRAN | SIMTC-RAN_OC | 4 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-06-15 17:00 | 100% | CP-120617 | - | Ericsson | mikael.wass@ericsson.com | CP#56 completed | 23.122, 24.008, 24.301 | 53 | 27 |  |  | Mon 29/08/11 | Fri 01/06/12
3202 | 530409 | CT6 part of Stage 3 Extended Access Barring for UTRAN and E-UTRAN | SIMTC-RAN_OC | 4 | Rel-11 | C6 | 2011-09-20 08:00 | 2012-09-07 17:00 | 100% | CP-120617 | - | ST Ericsson | Andrzej Winiarski | CP#57 completed | 31.102 | 53 | 27 |  |  | Mon 29/08/11 | Fri 24/08/12
3203 | 610014 | Test part: System Improvements for Machine-Type Communications | SIMTC-UEConTest | 2 | Rel-11 | R5 | 2013-09-09 08:00 | 2014-03-06 17:00 | 100% | RP-140077 | RP-140075 | Ericsson | calle.hagenfeldt@ericsson.com | RP#63 completed. Updated WID RP-131341=>RP-140077 (added affected TS 36.508). Testing for core part: SIMTC-Reach, SIMTC-CS, SIMTC-PS_Only, SIMTC-RAN_OC | 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | 61 | 31 |  |  | Tue 03/09/13 | Mon 03/03/14
3204 | 540019 | BB5: Charging of SIMTC (Stage 2/3) | SIMTC-CH | 2 | Rel-11 | S5 | 2011-12-07 08:00 | 2012-12-12 17:00 | 100% | SP-120848 | - | Ericsson | patrik.teppo@ericsson.com | SP#58 completed | 32.240, 32.251, 32.298, 32.299 | 54 | 28 |  |  | Mon 24/10/11 | Mon 19/11/12
3205 | 520022 | Deleted - BB2: Stage 2 Signalling Optimizations of SIMTC | SIMTC-Sig | 2 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped. SP#58 updated WID SP-110877=>SP-120848 | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
3206 | 520122 | Deleted - Effectively maintain connectivity for a large number of MTC Devices (TS 22.368, 7.1.1) | SIMTC-Sig | 3 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
3207 | 520222 | Deleted - Small Data Transmissions (TS 22.368, 7.2.5) | SIMTC-Sig | 3 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
3208 | 530107 | Deleted - Stage 3 (CS+PS) Signalling Optimizations of SIMTC | SIMTC-Sig | 3 | Rel-11 | C1,C6 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | CP#54 work stopped | Stage 3 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Tue 13/12/11
3209 | 530207 | Deleted - CT1 part of Stage 3 Signalling Optimizations of SIMTC | SIMTC-Sig | 4 | Rel-11 | C1 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | - | 23.122, 24.008, 24.301, 24.368 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 28/11/11
3210 | 530307 | Deleted - CT6 part of Stage 3 Signalling Optimizations of SIMTC | SIMTC-Sig | 4 | Rel-11 | C6 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | ST Ericsson | Andrzej Winiarski | - | 31.102 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 28/11/11
3211 | 520023 | Deleted - BB3: Stage 2 CN-based requirements and Power Considerations of SIMTC | SIMTC-CN_Pow | 2 | Rel-11 | S2 | 2011-06-08 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
3212 | 520123 | Deleted - Charging Requirements (TS 22.368, 7.1.5) | SIMTC-CN_Pow | 3 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
3213 | 520223 | Deleted - Lower Power Consumption (TS 22.368, 7.1.1) | SIMTC-CN_Pow | 3 | Rel-11 | S2 | 2011-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
3214 | 520323 | Deleted - MTC Monitoring (TS 22.368, 7.2.8) | SIMTC-CN_Pow | 3 | Rel-11 | S2 | 2011-06-08 08:00 | 2011-12-14 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#54 work stopped | TBD | 52 | 27 | SP-55 | PCG-28 | Thu 26/05/11 | Mon 12/11/12
3215 | 530008 | Deleted - Stage 3 (CS+PS) CN-based requirements and Power Considerations of SIMTC | SIMTC-CN_Pow | 3 | Rel-11 | C1,C6 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | CP#54 work stopped | Stage 3 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Tue 13/12/11
3216 | 530108 | Deleted - CT1 part of Stage 3 CN-based requirements and Power Considerations of SIMTC | SIMTC-CN_Pow | 4 | Rel-11 | C1 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | Ericsson | mikael.wass@ericsson.com | - | 23.122, 24.008, 24.301, 24.368 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 28/11/11
3217 | 530208 | Deleted - CT6 part of Stage 3 CN-based requirements and Power Considerations of SIMTC | SIMTC-CN_Pow | 4 | Rel-11 | C6 | 2011-09-16 08:00 | 2011-12-09 17:00 | 100% | CP-110756 | - | ST Ericsson | Andrzej Winiarski | - | 31.101, 31.102 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 28/11/11
3218 | 490028 | Deleted - TR on Security aspects of Machine-Type Communications | - | 2 | Rel-11 | S3 | 2009-12-10 08:00 | 2012-06-20 17:00 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | Was Rel-10 UID_460023 (Security for NIMTC). SP#56 stopped (activity transferred to Rel-12 Feature MTCe under UID_560722). | New TR 33.868 | 49 | 25 | SP-56 | PCG-29 | Sat 18/09/10 | Mon 12/11/12
3219 | 540119 | Deleted - BB4: Secure Connection and Privacy of SIMTC | SIMTC-Sec | 2 | Rel-11 | S3 | 2011-06-08 08:00 | 2012-09-12 17:00 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#57 stopped (activity transferred to Rel-12 Feature MTCe under UID_560522) | TBD | 52 | 27 | CP-57 | PCG-29 | Thu 26/05/11 | Mon 12/11/12
3220 | 520124 | Deleted - Secure Connection MTC Feature (TS 22.368, 7.2.10) | SIMTC-Sec | 3 | Rel-11 | S3 | 2011-06-08 08:00 | 2012-09-12 17:00 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#57 stopped (activity transferred to Rel-12 Feature MTCe | TBD | 52 | 27 | CP-57 | PCG-29 | Thu 26/05/11 | Mon 12/11/12
3221 | 530058 | Deleted - MTC Location Privacy | SIMTC-Priv | 3 | Rel-11 | S3 | 2011-09-19 08:00 | 2012-09-12 17:00 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#57 stopped (activity transferred to Rel-12 Feature MTCe | TBD | 53 | 27 | CP-57 | PCG-29 | Tue 13/09/11 | Mon 12/11/12
3222 | 480330 | Deleted - Stage 2 on SA2 part for System Improvements to Machine-Type Communications | SIMTC | 2 | Rel-11 | S2 | 2010-06-10 08:00 | 2011-06-08 17:00 | 100% | SP-120848 | - | Intel | puneet.jain@intel.com | SP#52 stopped | TBD | 48 | 25 | SP-52 | PCG-27 | Fri 28/05/10 | Mon 12/11/12
3223 | 480430 | Deleted - Stage 2 on Security part for System Improvements to Machine-Type Communications | SIMTC | 2 | Rel-11 | S3 | 2010-06-10 08:00 | 2011-06-08 17:00 | 100% | SP-120848 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#52 stopped | TBD | 48 | 25 | SP-52 | PCG-27 | Fri 28/05/10 | Mon 12/11/12
3224 | 480031 | Unstructured Supplementary Service Data (USSD) simulation service in IMS | USSI | 1 | Rel-11 | S1,C1,C3 | 2010-06-10 08:00 | 2012-12-07 17:00 | 100% | SP-100408 | - | Deutsche Telekom | kurt.bischinger@t-mobile.at | CP#58 completed | - | 48 | 25 |  |  | Sun 06/06/10 | Mon 19/11/12
3225 | 480131 | Stage 1 for USSD simulation service in IMS | USSI | 2 | Rel-11 | S1 | 2010-06-10 08:00 | 2010-06-10 08:00 | 100% | SP-100408 | - | Deutsche Telekom | kurt.bischinger@t-mobile.at | SP#48 completed. Specify a CS domain USSD like service over IMS (see GSM Mobile User Initiated USSD) | 22.173 | 48 | 25 |  |  | Sun 06/06/10 | Wed 24/08/11
3226 | 520003 | Stage 3 for USSD simulation service in IMS | USSI | 2 | Rel-11 | C1,C3 | 2011-06-03 08:00 | 2012-12-07 17:00 | 100% | CP-110534 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | SP#58 completed. No stage 2 impact, as reuse existing IMS architecture in TS 23.228 | - | 52 | 27 |  |  | Wed 18/05/11 | Mon 19/11/12
3227 | 520103 | CT1 part of Stage 3 for USSD simulation service in IMS | USSI | 3 | Rel-11 | C1 | 2011-06-03 08:00 | 2012-12-07 17:00 | 100% | CP-110534 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at, TS 24.390 Rapp: lili.yang@huawei.com | CP#58 completed | 24.173, 24.229, new TS 24.390 | 52 | 27 |  |  | Wed 18/05/11 | Mon 19/11/12
3228 | 520203 | CT3 part of Stage 3 for USSD simulation service in IMS | USSI | 3 | Rel-11 | C3 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | CP-110534 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | CP#57 completed | 29.165 | 52 | 27 |  |  | Wed 18/05/11 | Mon 13/08/12
3229 | 490031 | QoS Control Based on Subscriber Spending Limits | QoS_SSL | 1 | Rel-11 | S1,S2,S5,C3 | 2010-09-23 08:00 | 2012-06-20 17:00 | 100% | SP-110519 | - | Vodafone | mona.mustapha@vodafone.com | TSG#56 completed | - | 49 | 25 |  |  | Thu 02/09/10 | Thu 14/06/12
3230 | 490131 | Stage 1 for QoS Control Based on Subscriber Spending Limits | QoS_SSL | 2 | Rel-11 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-110519 | - | Vodafone | mona.mustapha@vodafone.com | SP#53 completed. Use cases & service requirements to allow: 1) modification of QoS based on subscriber’s spending limits 2) enforcing of spending limits for roaming subscribers without having dedicated support in the visited network | 22.115 | 49 | 25 |  |  | Thu 02/09/10 | Wed 24/08/11
3231 | 510043 | Stage 2 for QoS Control Based on Subscriber Spending Limits | QoS_SSL | 2 | Rel-11 | S2 | 2011-03-23 08:00 | 2011-09-21 17:00 | 100% | SP-110519 | - | Huawei | Xu Xia (xiatony@huawei.com) | SP#53 completed | 23.203 | 51 | 26 |  |  | Thu 10/03/11 | Fri 12/08/11
3232 | 500029 | Charging for QoS Control Based on Subscriber Spending Limits (Stage 2) | QoS_SSL | 2 | Rel-11 | S5 | 2010-12-16 08:00 | 2012-06-20 17:00 | 100% | SP-110519 | - | Nokia Siemens Networks, Huawei | Gerald.Goermer@nsn.com, shan.mingjun@huawei.com | SP#56 completed | 32.240, 32.296 | 50 | 26 |  |  | Sat 27/11/10 | Mon 02/04/12
3233 | 520004 | CT3 aspects of QoS Control Based on Subscriber Spending Limits (Stage 3) | QoS_SSL-CT3 | 2 | Rel-11 | C3 | 2011-06-03 08:00 | 2012-06-15 17:00 | 100% | CP-120203 | - | Huawei | QiaoWeihua@huawei.com | CP#56 completed | 29.212, 29.213, 29.214, 29.215, new TS 29.219 | 52 | 27 |  |  | Wed 18/05/11 | Fri 20/04/12
3234 | 490032 | Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | OSCAR | 1 | Rel-11 | S1,S2 | 2010-09-23 08:00 | 2012-03-07 17:00 | 100% | SP-110347 | - | Vodafone | mona.mustapha@vodafone.com | SP#55 completed (Stage 2/3 specified under CT1 Rel-11 Feature MRB (Inclusion of Media Resource Broker) UID_530021. Triggered by S1-102236/GSMA RILTE 10_007r1 (IREG LS_038 to 3GPP on Optimal Media Routing drawbacks) | - | 49 | 25 |  |  | Tue 31/08/10 | Mon 05/03/12
3235 | 490132 | TR on Stage 2 aspects of Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | OSCAR | 2 | Rel-11 | S2 | 2010-09-23 08:00 | 2012-03-07 17:00 | 100% | SP-110347 | - | Vodafone | Susana.Sabater@vodafone.com | SP#55 completed | new TR 23.849 | 49 | 25 |  |  | Tue 31/08/10 | Mon 05/03/12
3236 | 490232 | Stage 1 for Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | OSCAR | 2 | Rel-11 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-110347 | - | Vodafone | mona.mustapha@vodafone.com | SP#53 completed | 22.115, 22.173, 22.228 | 49 | 25 |  |  | Tue 31/08/10 | Mon 05/03/12
3237 | 490332 | Deleted - Stage 2 for Optimized Service Charging and Allocation of Resources in IMS whilst Roaming | OSCAR | 2 | Rel-11 | S2 | 2010-09-28 08:00 | 2012-03-07 17:00 | 100% | SP-110347 | - | Vodafone | Susana.Sabater@vodafone.com | SP#55 no normative work in SA2. Stage 2/3 to be done in under CT1 Rel-11 Feature MRB (Inclusion of Media Resource Broker) UID_530021 | None | 49 | 25 | SP-55 | PCG-28 | Tue 31/08/10 | Mon 05/03/12
3238 | 530021 | Inclusion of Media Resource Broker (Stage 2/3) | MRB | 1 | Rel-11 | C1,C3,IETF | 2011-09-16 08:00 | 2013-06-14 17:00 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | Stage 1 and TR on Stage 2 in Rel-11 Feature OSCAR UID_490032 | Stage 2/3 | 53 | 27 |  |  | Thu 25/08/11 | Wed 06/06/12
3239 | 530121 | Stage 2 for Inclusion of Media Resource Broker | MRB | 2 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#57 completed | 23.218 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
3240 | 530221 | Stage 3 for Inclusion of Media Resource Broker | MRB | 2 | Rel-11 | C1,C3,IETF | 2011-09-16 08:00 | 2013-06-14 17:00 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#60 completed | - | 53 | 27 |  |  | Thu 25/08/11 | Wed 06/06/12
3241 | 530321 | CT1 part of Stage 3 for Inclusion of Media Resource Broker | MRB | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#57 completed | 24.229, 29.165 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
3242 | 531005 | (IETF) Inclusion of Media Resource Broker [RFC 6917 (was draft-ietf-mediactrl-mrb)] | MRB | 3 | Rel-11 | C1-IETF | 2011-09-16 08:00 | 2013-06-14 17:00 | 100% | CP-120277 | - | Keith Drage | - | CP#60 completed | RFC 6917 (was draft-ietf-mediactrl-mrb) | 53 | 27 |  |  | Thu 25/08/11 | Mon 10/06/13
3243 | 560003 | CT3 part of Stage 3 for Inclusion of Media Resource Broker | MRB | 3 | Rel-11 | C3 | 2012-06-15 08:00 | 2012-09-07 17:00 | 100% | CP-120277 | - | AT&T | Martin Dolly (md3135@att.com) | CP#57 completed | 29.165 | 56 | 29 |  |  | Fri 01/06/12 | Mon 13/08/12
3244 | 500030 | Non Voice Emergency Services | NOVES | 1 | Rel-11 | S1,S2 | 2010-12-16 08:00 | 2012-03-07 17:00 | 100% | SP-100884 | - | Qualcomm | dwilliams@qualcomm.com | SP#55 Stage 2 completed. Triggered by SA1 Rel-11 TR 22.871 Study on Non Voice Emergency Services (FS_NOVES) | - | 50 | 26 |  |  | Mon 29/11/10 | Fri 16/03/12
3245 | 500130 | Stage 1 for Non Voice Emergency Services | NOVES | 2 | Rel-11 | S1 | 2010-12-16 08:00 | 2011-09-21 17:00 | 100% | SP-100884 | - | Qualcomm | dwilliams@qualcomm.com | SP#53 completed | 22.101 | 50 | 26 |  |  | Mon 29/11/10 | Wed 24/08/11
3246 | 530045 | Stage 2 for Non Voice Emergency Services (Support of IMS Emergency Sessions with Other Media on UTRAN and E-UTRAN) | NOVES-IMSESOM | 2 | Rel-11 | S2 | 2011-09-22 08:00 | 2012-03-07 17:00 | 100% | SP-110644 | - | Alcatel-Lucent | Deb.Barclay@alcatel-lucent.com | SP#55 completed | 23.060, 23.167, 23.203, 23.401 | 53 | 27 |  |  | Fri 12/08/11 | Mon 20/02/12
3247 | 510047 | Support for 3GPP Voice Interworking with Enterprise IP-PBX | VINE | 1 | Rel-11 | S1,C1 | 2011-03-23 08:00 | 2013-03-01 17:00 | 100% | SP-110176 | - | Tatara Systems | Phillip Brown (pbrown@tatarasystems.com) | SP#53 Stage 1 completed. CP#59 completed. Triggered by Rel-11 TR 22.809 Study on Support for 3GPP Voice Interworking with Enterprise IP-PBX (FS_VINE) UID_480033 | - | 51 | 26 |  |  | Mon 21/02/11 | Sat 16/02/13
3248 | 510147 | Stage 1 for Support for 3GPP Voice Interworking with Enterprise IP-PBX | VINE | 2 | Rel-11 | S1 | 2011-03-23 08:00 | 2011-09-21 17:00 | 100% | SP-110176 | - | Tatara Systems | Phillip Brown (pbrown@tatarasystems.com) | SP#53 completed | 22.228 | 51 | 26 |  |  | Mon 21/02/11 | Wed 24/08/11
3249 | 530010 | Stage 2/3 for Support for 3GPP Voice Interworking with Enterprise IP-PBX | VINE-CT1 | 2 | Rel-11 | C1 | 2011-09-20 08:00 | 2013-03-01 17:00 | 100% | CP-110641 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#59 completed | 23.218, 24.229 | 53 | 27 |  |  | Thu 25/08/11 | Sat 16/02/13
3250 | 520028 | Anonymous Call Rejection in the CS domain | ACR_CS | 1 | Rel-11 | S1,C4,C3 | 2011-06-07 08:00 | 2011-12-02 17:00 | 100% | SP-110421 | - | Alcatel-Lucent | Betsy.Covell@alcatel-lucent.com | CP#54 completed | - | 52 | 27 |  |  | Thu 19/05/11 | Wed 23/11/11
3251 | 520128 | Stage 1 for Anonymous Call Rejection in the CS domain | ACR_CS | 2 | Rel-11 | S1 | 2011-06-07 08:00 | 2011-06-08 17:00 | 100% | SP-110421 | - | Alcatel-Lucent | Betsy.Covell@alcatel-lucent.com | SP#52 completed under TEI11. Approved WID and CRs in SP-110376 (22.082 CR#0005, 22.085 CR#0004, 22.081 CR#0007, 22.088 CR#0003, 22.004 CR#0013) | 22.004, 22.081, 22.082, 22.085, 22.088 | 52 | 27 |  |  | Thu 19/05/11 | Mon 19/09/11
3252 | 530011 | Core Network aspects of Anonymous Call Rejection in the CS domain | ACR_CS-CN | 2 | Rel-11 | C4,C3 | 2011-09-14 08:00 | 2011-12-02 17:00 | 100% | CP-110587 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#54 completed | Stage 2/3 | 53 | 27 |  |  | Sat 27/08/11 | Sat 27/08/11
3253 | 530111 | CT4 part of Core Network aspects of Anonymous Call Rejection in the CS domain (Stage 2/3) | ACR_CS-CN | 3 | Rel-11 | C4 | 2011-09-14 08:00 | 2011-12-02 17:00 | 100% | CP-110587 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#54 completed | 23.018, 23.081, 23.082, 23.085, 23.088, 23.205, 23.231, 24.088, 29.002, 29.011 | 53 | 27 |  |  | Sat 27/08/11 | Wed 23/11/11
3254 | 530211 | CT3 part of Core Network aspects of Anonymous Call Rejection in the CS domain (Stage 3) | ACR_CS-CN | 3 | Rel-11 | C3 | 2011-09-14 08:00 | 2011-09-16 17:00 | 100% | CP-110587 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#53 completed | 29.163, 29.292 | 53 | 27 |  |  | Sat 27/08/11 | Mon 29/08/11
3255 | 460026 | Support for BroadBand Forum Accesses Interworking | BBAI | 1 | Rel-11 | S2,S1,C1,C3,C4,IETF | 2009-12-10 08:00 | 2012-12-12 17:00 | 100% | SP-120539 | - | Ericsson | peter.bleckert@ericsson.com | SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#56 completed. Triggered by BBF WT 203, WT-134 (interworking btw 3GPP EPS and BBF's fixed broadband accesses) | - | 46 | 24 |  |  | Sun 06/12/09 | Thu 30/08/12
3256 | 460126 | Stage 1 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI | 2 | Rel-11 | S1 | 2009-12-10 08:00 | 2010-03-25 17:00 | 100% | SP-120539 | - | Ericsson | Olle.Eriksson@ericsson.com | SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#47 completed. Provide service requirements for supporting interworking between 3GPP EPS and the fixed broadband accesses defined by BBF | 22.278 CR#0058 | 46 | 24 |  |  | Sun 06/12/09 | Thu 30/08/12
3257 | 470022 | TR on Stage 2 for BBAI | BBAI | 2 | Rel-11 | S2 | 2010-03-26 08:00 | 2012-06-20 17:00 | 100% | SP-120539 | - | Ericsson | marco.spini@huawei.com | TR 23.839 not Approved in Rel-11; progressed in Rel-12 under P4C-TI (UID_560824) | new TR 23.839 | 47 | 24 |  |  | Fri 13/04/12 | Mon 15/04/13
3258 | 470023 | Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI | 2 | Rel-11 | S2 | 2010-03-26 08:00 | 2012-06-20 17:00 | 100% | SP-120539 | - | Ericsson | stefan.rommer@ericsson.com | SP#56 completed | 23.203, new 23.139 | 47 | 24 |  |  | Sun 06/12/09 | Sat 09/06/12
3259 | 541001 | (IETF) Stage 2 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI | 2 | Rel-11 | S2-IETF | 2011-12-12 08:00 | 2012-12-12 17:00 | 100% | SP-120539 | - | Lionel Morand | Lionel Morand | Solved by IANA-registration. No RFC needed | - | 54 | 28 |  |  | Tue 06/12/11 | Thu 22/11/12
3260 | 530012 | Stage 3 BB I - Core Network impacts: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI_BBI-CT | 2 | Rel-11 | C1,C3,C4 | 2011-09-16 08:00 | 2012-12-07 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#58 completed | Stage 3 | 53 | 27 |  |  | Mon 29/08/11 | Sat 17/11/12
3261 | 530112 | TR on Stage 3 BB I for BBAI; UE to network protocols | BBAI_BBI-CT | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-06-15 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#56 completed. Identify additional FMC specific procedurES in CP-150addition to those in 24.302 (on access authentication & authorization and tunnel management; IP mobility mode selection; security aspects) | new TR 24.820 | 53 | 27 |  |  | Mon 29/08/11 | Thu 14/06/12
3262 | 550005 | TR on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface | BBAI_BBI-CT | 3 | Rel-11 | C4 | 2012-03-02 08:00 | 2012-06-15 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#56 completed | new TR 29.839 | 55 | 28 |  |  | Mon 20/02/12 | Thu 14/06/12
3263 | 551002 | Deleted - (IETF) on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface | BBAI_BBI-CT | 3 | Rel-11 | C4-IETF | 2012-03-02 08:00 | 2012-06-15 17:00 | 100% | CP-120419 | - | Lionel Morand | - | Draft removed from 3GPP documentation | draft-so-ipsecme-ikev2-cpext | 55 | 28 | CP-56 | PCG-29 | Mon 05/03/12 | Thu 14/06/12
3264 | 530212 | CT1 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI_BBI-CT | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#57 completed | 24.229, new TS 24.139 | 53 | 27 |  |  | Mon 29/08/11 | Wed 05/09/12
3265 | 530312 | CT3 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI_BBI-CT | 3 | Rel-11 | C3 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#57 completed | 29.212, 29.213, 29.215 | 53 | 27 |  |  | Mon 29/08/11 | Mon 13/08/12
3266 | 530412 | CT4 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB | BBAI_BBI-CT | 3 | Rel-11 | C4 | 2011-09-16 08:00 | 2012-12-07 17:00 | 100% | CP-120419 | - | Ericsson | Zu.Qiang@Ericsson.com | CP#58 completed | 23.008, 29.273, 29.274, new TS 29.139 | 53 | 27 |  |  | Mon 29/08/11 | Wed 28/11/12
3267 | 490026 | Stage 1 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CTofldS1 | 2 | Rel-11 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-120419 | - | Ericsson | Olle.Eriksson@ericsson.com | SP#53 completed. 22/01: acronym modified | 22.278 | 49 | 25 |  |  | Wed 01/09/10 | Thu 22/01/15
3268 | 470024 | Stage 2 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CTofldS2 | 2 | Rel-11 | S2 | 2010-09-28 08:00 | 2012-06-20 17:00 | 100% | SP-120419 | - | Ericsson | stefan.rommer@ericsson.com | SP#56 completed. 22/01: acronym modified | 23.203, 23.401, 23.402, 23.139 | 47 | 24 |  |  | Sun 06/12/09 | Thu 22/01/15
3269 | 530013 | Stage 3 BB II - Core Network impacts: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CT | 2 | Rel-11 | C3,C1,C4 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#57 completed | Stage 3 | 53 | 27 |  |  | Mon 29/08/11 | Thu 14/06/12
3270 | 530113 | TR on Stage 3 BB II for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols | BBAI_BBII-CT | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-06-15 17:00 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#56 completed | 24.820 | 53 | 27 |  |  | Mon 29/08/11 | Thu 14/06/12
3271 | 530213 | CT1 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CT | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#57 completed | new TS 24.320 | 53 | 27 |  |  | Mon 29/08/11 | Tue 14/08/12
3272 | 530313 | CT3 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CT | 3 | Rel-11 | C3 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#57 completed | 29.212, 29.213, 29.215 | 53 | 27 |  |  | Mon 29/08/11 | Mon 13/08/12
3273 | 530413 | CT4 part of Stage 3 BB II: BBF interworking with offload in access network for WLAN and for H(e)NB | BBAI_BBII-CT | 3 | Rel-11 | C4 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-120420 | - | Ericsson | Susana.Fernandez@ericsson.com | CP#55 completed | 23.008, 29.273 | 53 | 27 |  |  | Mon 29/08/11 | Mon 13/08/12
3274 | 490027 | Deleted - Stage 1 BB III: BBF convergence and network based mobility | - | 2 | Rel-11 | S1 | 2010-09-23 08:00 | 2011-09-21 17:00 | 100% | SP-120539 | - | Huawei | Amar Deol (adeol@huawei.com) | SP#57 stopped. Updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#53 completed | 22.278 | 49 | 25 | SP-57 | PCG-29 | Wed 01/09/10 | Sat 09/06/12
3275 | 470025 | Deleted - Stage 2 BB III: BBF convergence and network based mobility | - | 2 | Rel-11 | S2 | 2010-09-28 08:00 | 2012-03-07 17:00 | 100% | SP-120539 | - | Huawei | marco.spini@huawei.com | SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#55 stopped | 23.203, 23.401, 23.402, 23.139 | 47 | 24 | SP-55 | PCG-28 | Sun 06/12/09 | Thu 30/08/12
3276 | 530014 | Deleted - Stage 3 BB III - Core Network impacts: BBF convergence and network based mobility | - | 2 | Rel-11 | C3,C1,C4 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | Stage 3 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Tue 06/03/12
3277 | 530114 | Deleted - TR on Stage 3 BB III for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | new TR 24.820 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 20/02/12
3278 | 530214 | Deleted - CT1 part of Stage 3 BB III: BBF convergence and network based mobility | - | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | TBD | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 20/02/12
3279 | 530314 | Deleted - CT3 part of Stage 3 BB III: BBF convergence and network based mobility | - | 3 | Rel-11 | C3 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | 29.212, 29.213, 29.215 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 20/02/12
3280 | 530414 | Deleted - CT4 part of Stage 3 BB III: BBF convergence and network based mobility | - | 3 | Rel-11 | C4 | 2011-09-16 08:00 | 2012-03-02 17:00 | 100% | CP-110927 | - | Huawei | qiaoweihua@huawei.com | CP#55 stopped | 23.008, 29.273 | 53 | 27 | CP-55 | PCG-28 | Mon 29/08/11 | Mon 20/02/12
3281 | 480035 | Single Radio Voice Call Continuity (SRVCC) aspect of enhancements for Multimedia Priority Service | eMPS_SRVCC | 1 | Rel-11 | S2 | 2010-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-110346 | - | NTT DoCoMo | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#54 completed. Analyze and if needed specify mechanisms for the priority handling of SRVCC with regard to LTE/EPC | Stage 2 | 48 | 25 |  |  | Sun 06/06/10 | Fri 12/08/11
3282 | 480135 | TR on SRVCC for eMPS | eMPS_SRVCC | 2 | Rel-11 | S2 | 2010-06-10 08:00 | 2011-06-08 17:00 | 100% | SP-110346 | - | NTT DoCoMo | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#52 completed | new TR 23.854 | 48 | 25 |  |  | Sun 06/06/10 | Fri 12/08/11
3283 | 480235 | Stage 2 on SRVCC for eMPS | eMPS_SRVCC | 2 | Rel-11 | S2 | 2010-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-110346 | - | NTT DoCoMo | Atsushi Minokuchi (minokuchi@nttdocomo.co.jp) | SP#54 completed | 23.216, 23.237 | 48 | 25 |  |  | Sun 06/06/10 | Sun 04/03/12
3284 | 500026 | Single Radio Video Call Continuity for 3G-CS | vSRVCC | 1 | Rel-11 | S2,C1,C3,C4 | 2010-10-15 08:00 | 2012-06-15 17:00 | 100% | SP-100704 | - | Samsung | xiaowan.ke@samsung.com | CP#56 completed. Provide Single Radio VIDEO Call Continuity from E-UTRAN to UTRAN-CS based on the agreed architecture alternative in TR 23.886 | - | 50 | 26 |  |  | Fri 26/11/10 | Mon 18/06/12
3285 | 500126 | Stage 2 for Single Radio Video Call Continuity for 3G-CS | vSRVCC | 2 | Rel-11 | S2 | 2010-10-15 08:00 | 2011-09-21 17:00 | 100% | SP-100704 | - | Samsung | xiaowan.ke@samsung.com | SP#53 completed. Triggered by Feasibility Study on video call handover capability in TR 23.886 UID_470048 Study on Single Radio Video Call Continuity for 3G-CS (FS_vSRVCC) | 23.203, 23.216, 23.237 | 50 | 26 |  |  | Fri 26/11/10 | Mon 18/06/12
3286 | 520005 | CN aspects of Single Radio Video Call Continuity for 3G-CS | vSRVCC-CT | 2 | Rel-11 | C1,C3,C4 | 2011-06-03 08:00 | 2012-06-15 17:00 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | Stage 3. CP#56 completed | - | 52 | 27 |  |  | Wed 18/05/11 | Wed 06/06/12
3287 | 520105 | CT1 aspects of Single Radio Video Call Continuity for 3G-CS | vSRVCC-CT | 3 | Rel-11 | C1 | 2011-06-03 08:00 | 2012-06-15 17:00 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | CP#56 completed | 24.008, 24.237, 24.301 | 52 | 27 |  |  | Wed 18/05/11 | Wed 06/06/12
3288 | 520205 | CT3 aspects of Single Radio Video Call Continuity for 3G-CS | vSRVCC-CT | 3 | Rel-11 | C3 | 2011-06-03 08:00 | 2011-12-02 17:00 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | CP#54 completed | 29.211, 29.212, 29.213, 29.215 | 52 | 27 |  |  | Wed 18/05/11 | Wed 06/06/12
3289 | 520305 | CT4 aspects of Single Radio Video Call Continuity for 3G-CS | vSRVCC-CT | 3 | Rel-11 | C4 | 2011-06-03 08:00 | 2011-12-02 17:00 | 100% | CP-120278 | - | NEC | gottfried.punz@neclab.eu | CP#54 completed | 29.280 | 52 | 27 |  |  | Wed 18/05/11 | Wed 06/06/12
3290 | 480038 | Network-provided Location information for IMS (NETLOC) | NWK-PL2IMS | 1 | Rel-11 | S2,S1,S5,C3,C4,C1 | 2010-06-10 08:00 | 2013-03-01 17:00 | 100% | SP-110631 | - | T-Mobile | michele.zarri@t-mobile.co.uk | Covers the case where UE is served by a 3GPP RAN. Architecture making Cell/PLMN ID (UE is camped on) available to IMS nodes when the operator needs to record this information either to fulfil legal obligations or for charging. | - | 48 | 25 |  |  | Sun 06/06/10 | Tue 13/11/12
3291 | 500027 | Stage 1 for Network-provided Location information for IMS | NWK-PL2IMS | 2 | Rel-11 | S1 | 2010-12-15 08:00 | 2011-09-21 17:00 | 100% | - | - | n/a | n/a | SP#53 completed | 22.115 | 50 | 26 |  |  | Mon 13/12/10 | Wed 21/09/11
3292 | 480138 | TR on Stage 2 for Network-provided Location information for IMS | NWK-PL2IMS | 2 | Rel-11 | S2 | 2010-06-10 08:00 | 2011-12-14 17:00 | 100% | SP-110631 | - | T-Mobile | michele.zarri@t-mobile.co.uk | SP#54 completed | new TR 23.842 | 48 | 25 |  |  | Sun 06/06/10 | Tue 06/12/11
3293 | 480238 | Stage 2 for Network-provided Location information for IMS | NWK-PL2IMS | 2 | Rel-11 | S2 | 2010-06-15 08:00 | 2012-03-07 17:00 | 100% | SP-110631 | - | T-Mobile | michele.zarri@t-mobile.co.uk | SP#55 completed | 23.060, 23.203, 23.228, 23.401 | 48 | 25 |  |  | Sun 06/06/10 | Mon 20/02/12
3294 | 490029 | Charging for Network-provided Location information for IMS | NWK-PL2IMS_CH | 2 | Rel-11 | S5 | 2010-09-23 08:00 | 2012-09-12 17:00 | 100% | SP-110700 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#57 completed | Stage 2 (32.240, 32.260), Stage 3 (32.298, 32.299) | 49 | 25 |  |  | Fri 03/09/10 | Wed 05/09/12
3295 | 550008 | CT aspects of Network-provided Location information for IMS (Stage 3) | NWK-PL2IMS-CT | 2 | Rel-11 | C3,C4,C1 | 2012-03-02 08:00 | 2013-03-01 17:00 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | Stage 3. 3/3: Acronym changed from "NWK-PL2IMS_CT" | - | 55 | 28 |  |  | Wed 22/02/12 | Tue 03/03/15
3296 | 550108 | CT3 part of CT aspects of Network-provided Location information for IMS | NWK-PL2IMS-CT | 3 | Rel-11 | C3 | 2012-03-02 08:00 | 2012-09-07 17:00 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | CP#57 completed. 3/3: Acronym changed from "NWK-PL2IMS_CT" | 29.212, 29.214, 29.215 | 55 | 28 |  |  | Wed 22/02/12 | Tue 03/03/15
3297 | 550208 | CT4 part of CT aspects of Network-provided Location information for IMS | NWK-PL2IMS-CT | 3 | Rel-11 | C4 | 2012-03-02 08:00 | 2012-06-15 17:00 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | CP#57 completed. 3/3: Acronym changed from "NWK-PL2IMS_CT" | 23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.305, 29.328, 29.329 | 55 | 28 |  |  | Wed 22/02/12 | Tue 03/03/15
3298 | 550308 | CT1 part of CT aspects of Network-provided Location information for IMS | NWK-PL2IMS-CT | 3 | Rel-11 | C1 | 2012-03-02 08:00 | 2013-03-01 17:00 | 100% | CP-120845 | - | Huawei | Qiao Weihua (qiaoweihua@huawei.com) | CP#57 completed. 3/3: Acronym changed from "NWK-PL2IMS_CT" | 24.229, 24.292 | 55 | 28 |  |  | Wed 22/02/12 | Tue 03/03/15
3299 | 500032 | Service Awareness and Privacy Policies | SAPP | 1 | Rel-11 | S2,S1,C3 | 2010-10-12 15:48 | 2011-12-02 17:00 | 100% | SP-100882 | - | Allot | Alla Goldner (agoldner@allot.com) | CP#54 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047 | - | 50 | 26 |  |  | Fri 26/11/10 | Fri 12/08/11
3300 | 500132 | Stage 1 for Service Awareness and Privacy Policies | SAPP | 2 | Rel-11 | S1 | 2010-10-12 15:48 | 2010-12-15 17:00 | 100% | SP-100882 | - | Allot | Alla Goldner (agoldner@allot.com) | For deep packet inspection (i.e. Traffic Detection Functionality) SA1 indicated that no new requirements are needed (see Objective of FS_PP SA1,SA2 Rel-10 Study on Policy solutions and enhancements UID_440047 TR 23.813) | - | 50 | 26 |  |  | Fri 26/11/10 | Thu 02/12/10
3301 | 500232 | Stage 2 for Service Awareness and Privacy Policies | SAPP | 2 | Rel-11 | S2 | 2010-10-15 08:00 | 2011-09-21 17:00 | 100% | SP-100882 | - | Allot | Alla Goldner (agoldner@allot.com) | SP#53 completed | 23.203 | 50 | 26 |  |  | Fri 26/11/10 | Fri 12/08/11
3302 | 510003 | CT3 part of Service Awareness and Privacy Policies | SAPP-CT3 | 2 | Rel-11 | C3 | 2011-03-18 08:00 | 2011-12-02 17:00 | 100% | CP-110136 | - | Allot | Alla Goldner (agoldner@allot.com) | CP#54 completed. Stage 3 to support Application Detection and Control Functionality. Update Gx / introduce Sd reference points and procedures. Update S9 reference point in roaming scenarios | 29.212, 29.213, 29.214, 29.215 | 51 | 26 |  |  | Wed 02/03/11 | Thu 24/11/11
3303 | 500033 | VPLMN Autonomous CSG Roaming | VCSG | 1 | Rel-11 | S2,C4 | 2010-10-15 08:00 | 2011-12-14 17:00 | 100% | SP-100706 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | CP#56 completed. Linked to Rel-10 UID_450053 Enhanced Home NodeB / eNodeB (EHNB). Implements Rel-9 requirements for CSG support in SA1 TS 22.220 | - | 50 | 26 |  |  | Fri 26/11/10 | Mon 13/08/12
3304 | 500133 | Stage 2 for VPLMN Autonomous CSG Roaming | VCSG | 2 | Rel-11 | S2 | 2010-10-15 08:00 | 2011-12-14 17:00 | 100% | SP-100706 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#54 completed | 23.002, 23.060, 23.401 | 50 | 26 |  |  | Fri 26/11/10 | Mon 28/11/11
3305 | 530017 | CT aspects of VPLMN Autonomous CSG Roaming | VCSG-St3 | 2 | Rel-11 | C4 | 2011-12-07 08:00 | 2011-12-07 08:00 | 100% | CP-120196 | - | ZTE | Fei Lu (lu.fei1@zte.com.cn) | CP#57 completed | 23.003, 23.007, 23.008, 23.012, 29.002, 29.230, 29.272 | 53 | 27 |  |  | Sat 27/08/11 | Mon 13/08/12
3306 | 510048 | Data Identification in Access Network Discovery and Selection Function (ANDSF) | DIDA | 1 | Rel-11 | S2,C1 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | SP-110084 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#58 completed. Linked to Rel-10 IFOM (IP Flow Mobility and seamless WLAN offload) UID_450041. Defines IP flow mobility, seamless and non seamless WLAN offload and respective ANDSF extensions | Stage 2/3 | 51 | 26 |  |  | Mon 21/02/11 | Mon 19/11/12
3307 | 510148 | TR on Stage 2 for Data Identification in ANDSF | DIDA | 2 | Rel-11 | S2 | 2011-03-23 08:00 | 2011-12-14 17:00 | 100% | SP-110084 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#54 completed | New TR 23.855 | 51 | 26 |  |  | Mon 21/02/11 | Mon 28/11/11
3308 | 510248 | Stage 2 for Data Identification in ANDSF | DIDA | 2 | Rel-11 | S2 | 2011-03-24 08:00 | 2012-03-07 17:00 | 100% | SP-110084 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#55 completed | 23.402 | 51 | 26 |  |  | Mon 21/02/11 | Mon 20/02/12
3309 | 550003 | CT aspects of Data Identification in Access Network Discovery and Selection Function (ANDSF) Stage 3 | DIDA-CT | 2 | Rel-11 | C1 | 2012-03-02 08:00 | 2012-12-07 17:00 | 100% | CP-120089 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#58 completed | 24.302, 24.312 | 55 | 28 |  |  | Mon 20/02/12 | Mon 21/01/13
3310 | 510050 | LOcation-Based Selection of gaTEways foR WLAN | LOBSTER | 1 | Rel-11 | S2,C4 | 2011-03-23 08:00 | 2012-06-15 17:00 | 100% | SP-110752 | - | ZTE | zhu.chunhui@zte.com.cn | CP#56 completed. Related to UID_350027 SAE for support for non-3GPP accesses (SAES-SA-FP_n3GPP). Enhancements to ePDG and PDN GW selection functions for S2b and S2c based on UE location | - | 51 | 26 |  |  | Fri 18/03/11 | Fri 01/06/12
3311 | 510150 | Stage 2 for LOcation-Based Selection of gaTEways foR WLAN | LOBSTER | 2 | Rel-11 | S2 | 2011-03-23 08:00 | 2011-12-14 17:00 | 100% | SP-110752 | - | ZTE | zhu.chunhui@zte.com.cn | SP#54 completed | 23.402 | 51 | 26 |  |  | Fri 18/03/11 | Sun 04/03/12
3312 | 540010 | CT aspects of LOcation-Based Selection of gaTEways foR WLAN | LOBSTER-CT | 2 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120252 | - | ZTE | zhou.xingyue@zte.com.cn | Stage 3. CP#56 completed | Stage 3 | 54 | 28 |  |  | Wed 23/11/11 | Mon 24/09/12
3313 | 540110 | CT4 part of CT aspects of LOcation-Based Selection of gaTEways foR WLAN | LOBSTER-CT | 3 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120252 | - | ZTE | zhou.xingyue@zte.com.cn | CP#56 completed | 29.273 | 54 | 28 |  |  | Wed 23/11/11 | Mon 24/09/12
3314 | 540210 | Deleted - CT1 part of CT aspects of LOcation-Based Selection of gaTEways foR WLAN | LOBSTER-CT | 3 | Rel-11 | C1 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120252 | - | ZTE | zhou.xingyue@zte.com.cn | CP#56 stopped | 24.302 | 54 | 28 | CP-56 | PCG-29 | Wed 23/11/11 | Mon 24/09/12
3315 | 530001 | Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC | 1 | Rel-11 | S2,C1,C3,C4,G2,R2,R3,R5 | 2011-09-12 08:00 | 2015-03-13 17:00 | 100% | SP-110475 | - | Orange | antoine.mouquet@orange-ftgroup.com | Stage 1 in Rel-8 TS 22.278 clause 7.1.4.2. Triggered by Rel-11 TR 23.885 Study on Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (FS_rSRVCC) UID_460030 | - | 53 | 27 |  |  | Fri 12/08/11 | Tue 20/09/11
3316 | 530101 | Stage 2 for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC | 2 | Rel-11 | S2 | 2011-09-22 08:00 | 2012-06-20 17:00 | 100% | SP-110475 | - | Orange | antoine.mouquet@orange-ftgroup.com | SP#56 completed | 23.216, 23.237 | 53 | 27 |  |  | Fri 12/08/11 | Mon 18/06/12
3317 | 530201 | CT aspects for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (Stage 3) | rSRVCC-CT | 2 | Rel-11 | C1,C3,C4 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | Stage 3 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
3318 | 530301 | CT1 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-CT | 3 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | 23.009, 24.008, 24.229, 24.237, 24.292, 24.301 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
3319 | 530401 | CT3 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-CT | 3 | Rel-11 | C3 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | 29.165, 29.292 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
3320 | 530501 | CT4 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-CT | 3 | Rel-11 | C4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-110726 | - | Ericsson | ivo.sedlacek@ericsson.com | CP#57 completed | 23.003, 23.008, 29.002, 29.230, 29.272, 29.280, 29.303, 29.305, 29.328 | 53 | 27 |  |  | Thu 25/08/11 | Tue 14/08/12
3321 | 530601 | GERAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (Stage 3) | rSRVCC-GERAN | 2 | Rel-11 | G2 | 2011-09-12 08:00 | 2013-06-28 08:48 | 100% | GP-111290 | - | ZTE | li.jing4@zte.com.cn | GP#60 completed. GP#51 approved WID | 44.018, 48.008 | 51 | 27 |  |  | Thu 25/08/11 | Wed 04/09/13
3322 | 530701 | UTRAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-RAN_UTRA | 2 | Rel-11 | R3,R2 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111334 | - | Huawei | liwei.qiu@huawei.com | RP#58 completed | UTRA | 53 | 27 |  |  | Thu 25/08/11 | Thu 25/08/11
3323 | 530801 | Core part: UTRAN aspects of Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-RAN_UTRA-Core | 3 | Rel-11 | R3,R2 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111334 | RP-121553 | Huawei | liwei.qiu@huawei.com | RP#58 completed | 25.331, 25.401, 25.413 | 53 | 27 |  |  | Thu 25/08/11 | Tue 27/11/12
3324 | 640012 | Test part: Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-UEConTest | 2 | Rel-11 | R5 | 2014-06-15 | 2015-03-13 17:00 | 100% | RP-141786 | RP-150133 | Ericsson | calle.hagenfeldt@ericsson.com | ; Stat Rep: RP-141167->RP-141771 1st Apr 15: Compl:40%->100% 1st Apr 15: Stat Rep: RP-141771->RP-150133 | 36.508, 36.523-1, 36.523-2, 36.523-3 | 64 | 33 |  |  | Tue 10/06/14 | Wed 01/04/15
3325 | 530046 | S2a Mobility based On GTP and WLAN access to EPC | SaMOG_WLAN | 1 | Rel-11 | S2,C4,C1,C3,IETF | 2011-09-22 08:00 | 2014-03-05 17:00 | 100% | SP-110642 | - | ZTE | Chunhui Zhu (zhu.chunhui@zte.com.cn) | Triggered by Rel-11 TR 23.852 FS_SaMOG UID_510061, Rel-8 UID_350027 SAE for support for non-3GPP accesses (defines PMIP-S2a) | Stage 2/3 | 53 | 27 |  |  | Fri 12/08/11 | Wed 19/02/14
3326 | 530146 | Stage 2 for S2a Mobility based On GTP and WLAN access to EPC | SaMOG_WLAN | 2 | Rel-11 | S2 | 2011-09-22 08:00 | 2012-03-07 17:00 | 100% | SP-110642 | - | ZTE | zhu.chunhui@zte.com.cn | SP#55 completed | 23.002, 23.203, 23.402 | 53 | 27 |  |  | Fri 12/08/11 | Mon 20/02/12
3327 | 540011 | CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 2 | Rel-11 | C4,C1,C3,IETF | 2011-12-02 08:00 | 2014-03-05 17:00 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | - | Stage 3 | 54 | 28 |  |  | Wed 26/10/11 | Wed 23/11/11
3328 | 540111 | CT4 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 3 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#57 completed | 23.003, 23.007, 23.008, 29.273, 29.274, 29.281, 29.303 | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
3329 | 561010 | Deleted - (IETF) CT4 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 3 | Rel-11 | C4-IETF | 2012-04-23 08:00 | 2014-03-05 17:00 | 100% | CP-110802 | - | Lionel Morand | - | CP#63 Draft removed from 3GPP documentation | draft-ietf-radext-ieee802ext | 56 | 29 | CP-53 | PCG-32 | Fri 20/04/12 | Wed 19/02/14
3330 | 540211 | Deleted - CT1 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 3 | Rel-11 | C1 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#56 stopped (no CT1 impact) | 24.302 | 54 | 28 | CP-56 | PCG-29 | Wed 26/10/11 | Fri 01/06/12
3331 | 540311 | CT3 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC | SaMOG_WLAN-CN | 3 | Rel-11 | C3 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-110802 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#56 completed | 29.212, 29.213, 29.215 | 54 | 28 |  |  | Wed 26/10/11 | Fri 01/06/12
3332 | 540029 | Roaming Architecture for Voice over IMS with Local Breakout | RAVEL | 1 | Rel-11 | S2,S5,C1,C3 | 2011-11-28 17:00 | 2012-12-07 17:00 | 100% | SP-110885 | - | Deutsche Telekom | michele.zarri@telekom.com | CP#58 completed. Triggered by Rel-11 TR 23.850 Study on Roaming Architecture for Voice over IMS with Local Breakout (FS_RAVEL). GSMA CPWP LS_in S5-102806 asked 3GPP SA5 to check if CS voice charging principles also apply to voice over IMS | Stage 2/3 | 54 | 28 |  |  | Tue 25/10/11 | Tue 20/11/12
3333 | 540129 | Stage 2 for Roaming Architecture for Voice over IMS with Local Breakout | RAVEL | 2 | Rel-11 | S2 | 2011-11-28 17:00 | 2011-12-14 17:00 | 100% | SP-110885 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#54 completed | 23.002, 23.228 | 54 | 28 |  |  | Tue 25/10/11 | Mon 28/11/11
3334 | 540030 | Charging for Roaming Architecture for Voice over IMS with Local Breakout | RAVEL-CH | 2 | Rel-11 | S5 | 2011-12-14 08:00 | 2012-09-12 17:00 | 100% | SP-110886 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | Stage 2/3. SP#57 completed | 32.240, 32.260, 32.298, 32.299 | 54 | 28 |  |  | Thu 08/12/11 | Wed 05/09/12
3335 | 550004 | CT aspects of Roaming Architecture for Voice over IMS with Local Breakout (Stage 3) | RAVEL-CT | 2 | Rel-11 | C1,C3 | 2012-03-02 08:00 | 2012-12-07 17:00 | 100% | CP-120088 | - | Deutsche Telekom | reinhard.lauster@)t-mobile.at | CP#58 completed | Stage 3 | 55 | 28 |  |  | Mon 20/02/12 | Tue 20/11/12
3336 | 550104 | CT1 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout | RAVEL-CT | 3 | Rel-11 | C1 | 2012-03-02 08:00 | 2012-12-07 17:00 | 100% | CP-120088 | - | Deutsche Telekom | reinhard.lauster@)t-mobile.at | CP#58 completed | 24.229, 24.292, 24.237 | 55 | 28 |  |  | Mon 20/02/12 | Tue 20/11/12
3337 | 550204 | CT3 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout | RAVEL-CT | 3 | Rel-11 | C3 | 2012-03-02 08:00 | 2012-12-07 17:00 | 100% | CP-120088 | - | Deutsche Telekom | reinhard.lauster@)t-mobile.at | CP#58 completed | 29.165, 29.162, 29.079 | 55 | 28 |  |  | Mon 20/02/12 | Tue 20/11/12
3338 | 560027 | IMS Overload Control | IOC | 1 | Rel-11 | S2,C1,C3,IETF | 2012-06-18 08:00 | 2014-12-09 17:00 | 100% | SP-120273 | - | Orange, China Mobile | Antoine MOUQUET, YU Qing | SP#57 Stage 2 completed. Moved Rel-12=>Rel-11 as CT finished Stage 3. Linked to UID_410041 Study on IMS Evolution (TR 23.812). Solutions from IETF SOC WG and existing 3GPP procedures to be re-used if possible & backward compatibility ensured | Stage 2/3 | 56 | 29 |  |  | Fri 11/05/12 | Tue 24/07/12
3339 | 560127 | Stage 2 for IMS Overload Control | IOC | 2 | Rel-11 | S2 | 2012-06-18 08:00 | 2012-09-12 17:00 | 100% | SP-120273 | - | Orange, China Mobile | antoine.mouquet@orange-ftgroup.com, YU Qing | SP#57 completed. Moved Rel-12=>Rel-11 as CT finished Stage 3. | 23.228 | 56 | 29 |  |  | Fri 11/05/12 | Tue 24/07/12
3340 | 570007 | Stage 3 for IMS Overload Control | IOC | 2 | Rel-11 | C1,C3,IETF | 2012-09-05 08:00 | 2014-12-09 17:00 | 100% | CP-120561 | - | Alcatel-Lucent | Keith Drage | - | - | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
3341 | 570107 | CT1 part of Stage 3 for IMS Overload Control | IOC | 3 | Rel-11 | C1 | 2012-09-05 08:00 | 2012-12-07 17:00 | 100% | CP-120561 | - | Alcatel-Lucent | Keith Drage | CP#58 completed | 24.229 | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
3342 | 570207 | CT3 part of Stage 3 for IMS Overload Control | IOC | 3 | Rel-11 | C3 | 2012-09-05 08:00 | 2012-12-07 17:00 | 100% | CP-120561 | - | Alcatel-Lucent | Keith Drage | CP#58 completed | 29.165 | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
3343 | 571001 | (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-control) | IOC | 3 | Rel-11 | C1-IETF,C3-IETF | 2013-07-29 08:00 | 2014-12-09 17:00 | 100% | CP-120561 | - | Keith Drage | Keith Drage | in RFC Ed-queue. Dec.14: 75->100. Mar15: impacted spec updated (was draft-ietf-soc-overload-control). Jun 15: RFC 7339 (was draft-ietf-soc-overload-control) | RFC 7339 | 57 | 29 |  |  | Mon 03/09/12 | Tue 10/03/15
3344 | 571002 | (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-rate-control) | IOC | 3 | Rel-11 | C1-IETF,C3-IETF | 2013-07-29 08:00 | 2014-12-09 17:00 | 100% | CP-120561 | - | Keith Drage | Keith Drage | Submitted to IESG for publication. Dec14: 50->90%. Mar15: 100%. Impacted RFC updated (was draft-ietf-soc-overload-rate-control). Jun 15: RFC 7415 (was draft-ietf-soc-overload-rate-control) | RFC 7415 | 57 | 29 |  |  | Mon 03/09/12 | Tue 10/03/15
3345 | 571003 | (IETF) CT part of Stage 3 for IMS Overload Control (RFC 7200) | IOC | 3 | Rel-11 | C1-IETF,C3-IETF | 2013-07-29 08:00 | 2014-06-13 17:00 | 100% | CP-120561 | - | Keith Drage | Keith Drage | CP#64 completed | RFC 7200 (was draft-ietf-soc-load-control-event-package) | 57 | 29 |  |  | Mon 13/08/12 | Fri 06/06/14
3346 | 520030 | Rel-11 Security small Enhancements | SEC11 | 1 | Rel-11 | S3 | 2011-06-08 08:00 | 2012-09-12 17:00 | 100% | - | - | - | - | SEC11 is an umbrella Feature for Security related TEI11 type of changes that are not part of any other dedicated feature | - | 52 | 27 |  |  | Tue 19/04/11 | Thu 16/08/12
3347 | 520032 | Lawful Interception in the 3GPP Rel-11 | LI11 | 1 | Rel-11 | S3 | 2011-06-10 08:00 | 2012-06-20 17:00 | 100% | SP-110424 | - | PIDS, Alcatel-Lucent | Koen Jaspers (k.b.jaspers@minjus.nl), terry.jacobson@alcatel-lucent.com | Stage 1/2/3. SP#56 completed | 33.106, 33.107, 33.108 | 52 | 27 |  |  | Tue 17/05/11 | Fri 08/06/12
3348 | 440055 | ZUC EEA3 and EIA3 (new Encryption & Integrity EPS security Algorithms) | EEA3_EIA3 | 1 | Rel-11 | S3,R5 | 2009-06-04 08:00 | 2012-09-07 17:00 | 100% | SP-090457 | - | CATR | Yuan Qi (yuanqi@catr.cn) | RP#57 completed testing | - | 44 | 23 |  |  | Mon 18/05/09 | Tue 04/09/12
3349 | 440155 | ZUC EEA3 and EIA3 | EEA3_EIA3 | 2 | Rel-11 | S3 | 2009-06-04 08:00 | 2011-12-14 17:00 | 100% | SP-090457 | - | CATR | Yuan Qi (yuanqi@catr.cn) | SP#53 completed new EPS algorithms e.g. for China | 33.401, New (35.221, 35.222, 35.223, 35.924) | 44 | 23 |  |  | Mon 18/05/09 | Mon 12/12/11
3350 | 560009 | Conformance Test Aspects – ZUC (EEA3 and EIA3 Encryption & Integrity EPS security Algorithms) | EEA3_EIA3_UEConTest | 2 | Rel-11 | R5 | 2012-06-18 08:00 | 2012-09-07 17:00 | 100% | RP-120631 | RP-120968 | CATR | Ms Jun Chen (chenjun@catr.cn) | RP#57 completed. Testing for SA3 TSs 33.401, new (35.221, 35.222, 35.223) | 36.523-1, 36.523-2, 36.523-3 | 56 | 29 |  |  | Mon 04/06/12 | Tue 04/09/12
3351 | 480039 | Specification of Protection against Unsolicited Communication for IMS (produced TR-only) | SPUCI | 1 | Rel-11 | S3 | 2010-06-10 08:00 | 2012-03-07 17:00 | 100% | SP-100428 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#55 completed (No normative work). TR 33.838v200 for Approval & abandoned new TS 33.237. Continuation of Rel-9 UID_410027/410029. Builds on TR 33.937 Study of Mechanisms for PUCI | New TR 33.838, abandoned New TS 33.237 | 48 | 25 |  |  | Wed 05/05/10 | Mon 05/03/12
3352 | 510053 | H(e)NB security features for UE mobility scenarios (Stage 2) | HNB_mob_Sec | 1 | Rel-11 | S3 | 2011-03-23 08:00 | 2012-03-07 17:00 | 100% | SP-110025 | - | Huawei | Marcus Wong (mwong@huawei.com) | SP#55 completed. Add HeNB Security extensions to Extended H(e)NB Features (EHNBF) UID_450053 | 33.320 | 51 | 26 |  |  | Mon 14/02/11 | Mon 20/02/12
3353 | 540012 | Generic Bootstrapping Architecture (GBA) extensions for re-use of SIP Digest credentials | GBA-ext | 1 | Rel-11 | S3,C4,C1 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | SP-110884 | - | Nokia | Silke.Holtmanns@nokia.com | Stage 2/3. CP#57 completed | - | 54 | 28 |  |  | Mon 28/11/11 | Tue 14/08/12
3354 | 540112 | Stage 2 for GBA extensions for re-use of SIP Digest credentials | GBA-ext | 2 | Rel-11 | S3 | 2011-12-14 08:00 | 2012-03-07 17:00 | 100% | SP-110884 | - | Nokia | Silke.Holtmanns@nokia.com | SP#55 completed | 33.220 | 54 | 28 |  |  | Mon 28/11/11 | Mon 20/02/12
3355 | 540212 | Stage 3 for GBA extensions for re-use of SIP Digest credentials | GBA-ext-St3 | 2 | Rel-11 | C4,C1 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110804 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | Stage 3 | 54 | 28 |  |  | Wed 23/11/11 | Tue 14/08/12
3356 | 540312 | CT4 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials | GBA-ext-St3 | 3 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110804 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | 29.109 | 54 | 28 |  |  | Wed 23/11/11 | Tue 14/08/12
3357 | 540412 | CT1 part of Stage 3 for GBA extensions for re-use of SIP Digest credentials | GBA-ext-St3 | 3 | Rel-11 | C1 | 2011-12-05 08:00 | 2012-09-07 17:00 | 100% | CP-110804 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | 24.109 | 54 | 28 |  |  | Wed 23/11/11 | Tue 14/08/12
3358 | 520033 | Extensions of Acoustic Test Specifications in TS 26.131 and TS 26.132 | Ext_ATS | 1 | Rel-11 | S4 | 2011-06-08 08:00 | 2012-09-12 17:00 | 100% | SP-110309 | - | Orange, Qualcomm | stephane.ragot@orange-ftgroup.com, Andre Schevciw (aschevci@qualcomm.com) | SP#57 completed | 26.131, 26.132 | 52 | 27 |  |  | Thu 26/05/11 | Mon 20/08/12
3359 | 530048 | Enhancements to Multimedia: PSS, MMS, and MBMS Enhancements and Performance Improvements | EMM | 1 | Rel-11 | S4 | 2011-09-07 08:00 | 2013-03-06 17:00 | 100% | SP-120025 | - | Qualcomm | Nikolai Leung (nleung@qualcomm.com) | Stage 3. SP#59 completed | 26.140, 26.234, 26.247, New TR 26.951=>26.851 | 53 | 27 |  |  | Wed 07/09/11 | Sat 16/02/13
3360 | 530148 | Enhancement to FEC for MBMS | EMM-EFEC | 2 | Rel-11 | S4 | 2011-09-21 08:00 | 2013-03-06 17:00 | 100% | SP-120182 | - | Qualcomm | Thomas Stockhammer (c_tstock@qualcomm.com) | SP#59 completed | 26.346, new TR 26.947 | 53 | 27 |  |  | Wed 07/09/11 | Sat 16/02/13
3361 | 530248 | Download Delivery Enhancements for MBMS | EMM-DDE | 2 | Rel-11 | S4 | 2011-09-21 08:00 | 2012-12-12 17:00 | 100% | SP-120025 | - | Qualcomm | Nikolai Leung (nleung@qualcomm.com) | SP#58 completed | 26.346, new TR 26.951=>26.851 | 53 | 27 |  |  | Wed 07/09/11 | Tue 11/12/12
3362 | 530348 | IMS-based PSS and MBMS Streaming Synchronization Enhancements | EMM-IPME | 2 | Rel-11 | S4 | 2011-09-07 08:00 | 2012-09-12 17:00 | 100% | SP-120025 | - | InterDigital Communications | hang.liu@interdigital.com | SP#58 completed | 26.237, new TR 26.951=>26.851 | 53 | 27 |  |  | Wed 07/09/11 | Tue 11/12/12
3363 | 560041 | Mobile 3D Video Coding | M3DV | 1 | Rel-11 | S4 | 2012-06-07 08:00 | 2012-09-12 17:00 | 100% | SP-120229 | - | Orange | gilles.teniou@orange.com | SP#57 completed. Triggered by UID_520036 Rel-11 Study on Mobile 3D Video Coding (FS_M3DVC) TR 26.905. | 26.140, 26.234, 26.244, 26.245, 26.247, 26.346, 26.430, 26.905 | 56 | 29 |  |  | Thu 07/06/12 | Mon 20/08/12
3364 | 510051 | Rel-11 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM11 | 1 | Rel-11 | S5 | 2011-03-23 08:00 | 2013-03-07 08:00 | 100% | - | - | - | - | OAM11 is an umbrella Feature also for OAM&P related TEI11 type of changes that are not part of any other dedicated feature/WI | - | 51 | 26 |  |  | Tue 22/02/11 | Tue 22/02/11
3365 | 510151 | Rel-11 Network Infrastructure Management | OAM11-NIM | 2 | Rel-11 | S5 | 2011-03-23 08:00 | 2013-03-07 08:00 | 100% | - | - | - | - | - | - | 51 | 26 |  |  | Tue 22/02/11 | Tue 22/02/11
3366 | 510056 | IRP framework enhancements to support Management of Converged Networks | OAM-FMC-IRP | 3 | Rel-11 | S5 | 2011-03-23 08:00 | 2013-03-07 08:00 | 100% | SP-120652 | - | Nokia Siemens Networks, Ericsson | thomas.tovinger@ericsson.com, olaf.pollakowski@nsn.com | SP#59 completed. Triggered by SA5 Studies TR 32.833, 32.828, 32.831 | 32.101/103/150, new (28.620/621/622/623/624/625/626/627/628/629/631/632/633/651/652/653/654/655/656/657/658/659/661/662/663/671/672/673/674/675/676/701/702/703/704/705/706/707/708/709/731/732/733/734/735/736/751/752/753, 32.107/156/157/853/854 | 51 | 26 |  |  | Wed 09/03/11 | Wed 05/12/12
3367 | 510251 | Rel-11 Performance Management | OAM11-PM | 2 | Rel-11 | S5 | 2011-03-23 08:00 | 2012-12-12 17:00 | 100% | - | - | - | - | - | - | 51 | 26 |  |  | Tue 22/02/11 | Mon 19/11/12
3368 | 510057 | IMS Performance Management enhancements | OAM-ePM-IMS | 3 | Rel-11 | S5 | 2011-03-23 08:00 | 2012-03-07 17:00 | 100% | SP-110134 | - | ZTE | guo.wenjie1@zte.com.cn | SP#55 completed | 32.409 | 51 | 26 |  |  | Tue 22/02/11 | Mon 05/03/12
3369 | 510058 | Enhanced Management of UE based network performance measurements | OAM-ePM-UE | 3 | Rel-11 | S5 | 2011-03-23 08:00 | 2012-12-12 17:00 | 100% | SP-110135 | - | Huawei, Ericsson, Nokia Siemens Networks | Zou Lan (zlan@huawei.com), ulf.hubinette@ericsson.com, gyula.bodog@nsn.com | SP#58 completed | 32.421, 32.422, 32.423, 32.441, 32.442, 32.446 | 51 | 26 |  |  | Tue 22/02/11 | Wed 21/11/12
3370 | 520034 | CN performance measurements enhancement | OAM-ePM-CN | 3 | Rel-11 | S5 | 2011-06-08 08:00 | 2012-09-12 17:00 | 100% | SP-110275 | - | China Mobile | Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com), Li Jian (lijian@chinamobile.com) | SP#57 completed | 32.406, 32.407, 32.426 | 52 | 27 |  |  | Thu 19/05/11 | Fri 31/08/12
3371 | 530049 | Management of CA for LTE | OAM-CA | 3 | Rel-11 | S5 | 2011-09-21 08:00 | 2012-12-12 17:00 | 100% | SP-120776 | - | Nokia Siemens Networks, Ericsson | yizhi.yao@nsn.com, per.elmdahl@ericsson.com | SP#58 completed. Updated WID SP-110636=>SP-120776. Stage 2 in Rel-10 RAN Feature UID_460007 Carrier Aggregation for LTE (LTE_CA) | 32.425 | 53 | 27 |  |  | Sat 27/08/11 | Tue 20/11/12
3372 | 510351 | Rel-11 Self-Organizing Networks (SON) - OAM aspects | OAM11-SON | 2 | Rel-11 | S5 | 2011-03-23 08:00 | 2013-03-06 17:00 | 100% | - | - | - | - | - | - | 51 | 26 |  |  | Tue 22/02/11 | Tue 22/02/11
3373 | 510059 | UTRAN Self-Organizing Networks (SON) management | OAM-SON-UTRAN | 3 | Rel-11 | S5 | 2011-03-23 08:00 | 2012-09-12 17:00 | 100% | SP-120552 | - | Huawei | kai.zhangkai@huawei.com | SP#57 completed. Updated WID SP-110518=>SP-120552 | UTRA 32.405, 32.500, 32.511, 32.521, 32.522, 32.526, 32.642, 32.646 | 51 | 26 |  |  | Tue 22/02/11 | Fri 31/08/12
3374 | 530051 | LTE Self-Organizing Networks (SON) coordination management | OAM-SON-LTE_COORD | 3 | Rel-11 | S5 | 2011-09-21 08:00 | 2013-03-06 17:00 | 100% | SP-110637 | - | Huawei, Nokia Siemens Networks | kai.zhangkai@huawei.com, clemens.suerbaum@nsn.com | SP#59 completed | LTE 32.425, 32.500, 32.521, 32.522, 32.526, 32.762, 32.766 | 53 | 27 |  |  | Sat 27/08/11 | Sat 16/02/13
3375 | 540031 | Inter-RAT Energy Saving Management | OAM-IRAT-ESM | 3 | Rel-11 | S5 | 2011-12-07 08:00 | 2012-12-12 17:00 | 100% | SP-110701 | - | Nokia Siemens Networks, Huawei | clemens.suerbaum@nsn.com, xiahaitao@huawei.com | SP#58 completed. Triggered by Rel-11 TR 32.834 (Study on OAM aspects of inter-RAT Energy Saving) UID_510045. Needs coordination with RAN WGs | 32.405, 32.551, 32.522, 32.526, 32.642, 32.646, 32.762, 32.766 | 54 | 28 |  |  | Tue 22/11/11 | Mon 19/11/12
3376 | 510052 | Rel-11 Charging Management small Enhancements | CH11 | 1 | Rel-11 | S5 | 2010-03-25 08:00 | 2012-12-12 17:00 | 100% | - | - | - | - | CH11 is an umbrella Feature also for OAM&P related TEI11 type of changes that are not part of any other dedicated feature/WI | TR 30.821 | 51 | 26 |  |  | Tue 22/02/11 | Tue 22/02/11
3377 | 470045 | Add solutions for Rc - reference point within the Online Charging System (OCS) | CH-Rc | 2 | Rel-11 | S5 | 2010-03-25 08:00 | 2011-09-21 17:00 | 100% | SP-110129 | - | Huawei | shan.mingjun@huawei.com | SP#53 completed. Stage 3 (Stage 1 in 22.115). Triggered by Rel-10 TR 32.825 SA5 Study on Rc Reference Point Functionalities and Message Flows (UID_410044) | 32.296, 32.299 | 47 | 24 |  |  | Fri 12/02/10 | Fri 26/08/11
3378 | 510060 | Charging for Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Data Bases | PEST-CH | 2 | Rel-11 | S5 | 2011-03-21 08:00 | 2011-09-21 17:00 | 100% | SP-110126 | - | Ericsson | patrik.teppo@@ericsson.com | SP#53 completed. Stage 3 | 32.251, 32.298, 32.299 | 51 | 26 |  |  | Tue 22/02/11 | Fri 26/08/11
3379 | 550019 | Unification of Charging session from SIP AS and SRVCC functions in IMS | UCHIMS_AS-SRVCC | 2 | Rel-11 | S5 | 2012-03-07 08:00 | 2012-12-12 17:00 | 100% | SP-120042 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | Stage 2/3. SP#58 completed | 32.260, 32.275, 32.298, 32.299 | 55 | 28 |  |  | Wed 22/02/12 | Wed 05/12/12
3380 | 510029 | Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | IOI_IMS_CH | 1 | Rel-11 | S5,S1,C1 | 2010-10-27 08:00 | 2012-06-15 17:00 | 100% | SP-110132 | - | Deutsche Telekom | matthias.seibel@telekom.de | Stage 2/3. CP#56 completed. Stage 1 in SA1 22.115 | - | 51 | 26 |  |  | Tue 22/02/11 | Fri 01/06/12
3381 | 510129 | Stage 1 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | IOI_IMS_CH | 2 | Rel-11 | S1 | 2010-10-27 08:00 | 2011-09-21 17:00 | 100% | SP-110132 | - | Deutsche Telekom | matthias.seibel@telekom.de | SP#53 completed under IPXS | 22.115 | 51 | 26 |  |  | Tue 22/02/11 | Fri 07/10/11
3382 | 510229 | Stage 2/3 SA5 part of Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | IOI_IMS_CH | 2 | Rel-11 | S5 | 2010-10-27 13:48 | 2011-12-07 17:00 | 100% | SP-110132 | - | Deutsche Telekom | matthias.seibel@telekom.de | SP#54 completed | 32.240, 32.260, 32.298, 32.299 | 51 | 26 |  |  | Tue 22/02/11 | Mon 24/10/11
3383 | 520006 | Stage 3 for Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment | IOI_IMS_CH | 2 | Rel-11 | C1 | 2011-06-07 08:00 | 2012-06-15 17:00 | 100% | CP-110440 | - | Deutsche Telekom | martin.huelsemann@telekom.de] | CP#56 completed | 24.229 | 52 | 27 |  |  | Mon 23/05/11 | Fri 01/06/12
3384 | 480011 | User Data Convergence - Data Model | UDC_DM | 1 | Rel-11 | C4,S1 | 2010-03-25 08:00 | 2012-09-07 17:00 | 100% | CP-110384 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#57 completed. SP#48 Stage 1 completed as Rel-10 | - | 48 | 25 |  |  | Wed 26/05/10 | Mon 13/08/12
3385 | 480036 | Stage 1 for UDC Data Model | UDC_DM | 2 | Rel-11 | S1 | 2010-03-25 08:00 | 2011-09-21 17:00 | 100% | - | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | SP#53 completed under Rel-10 UDC | 22.101 | 48 | 25 |  |  | Wed 26/05/10 | Mon 19/09/11
3386 | 480111 | TR on User Data Convergence (UDC) Data Model | UDC_DM | 2 | Rel-11 | C4 | 2010-06-04 08:00 | 2012-09-07 17:00 | 100% | CP-110384 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#57 completed | new TR 29.935 | 48 | 25 |  |  | Wed 26/05/10 | Tue 25/09/12
3387 | 480211 | User Data Convergence (UDC) Data Model | UDC_DM | 2 | Rel-11 | C4 | 2010-06-04 08:00 | 2012-09-07 17:00 | 100% | CP-110384 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#57 completed | 29.335 | 48 | 25 |  |  | Wed 26/05/10 | Mon 13/08/12
3388 | 510004 | Definition of the UICC Application for Hosting Party Module | HPM_UICC | 1 | Rel-11 | C6 | 2011-03-18 08:00 | 2012-06-15 17:00 | 100% | CP-110289 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#56 completed | 31.102, New TS 31.104 | 51 | 26 |  |  | Thu 03/03/11 | Tue 25/09/12
3389 | 520007 | Usability improvement of Inter-IMS Network to Network Interface (II-NNI) specification for inter-connection by means of Option Item list | NNI_OI | 1 | Rel-11 | C3 | 2011-06-07 08:00 | 2012-06-15 17:00 | 100% | CP-110533 | - | NTT | arai.kenjiro@lab.ntt.co.jp | CP#56 completed. Stage 3 (No architectural change, specify the list of selectable items related to control plane signalling directly for the same architecture) | 29.165 | 52 | 27 |  |  | Wed 18/05/11 | Fri 01/06/12
3390 | 520008 | enhanced Nodes Restoration for EPC (Stage 2/3) | eNR_EPC | 1 | Rel-11 | C4,C1,C3,IETF | 2011-06-03 08:00 | 2013-12-06 17:00 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration UID_490014 | - | 52 | 27 |  |  | Wed 18/05/11 | Thu 28/11/13
3391 | 520108 | CT4 part of enhanced Nodes Restoration for EPC | eNR_EPC | 2 | Rel-11 | C4 | 2011-06-03 08:00 | 2012-12-07 17:00 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | CP#58 completed | 23.007, 23.008, 23.018, 29.274, 29.275 | 52 | 27 |  |  | Wed 18/05/11 | Tue 20/11/12
3392 | 581001 | (IETF) CT4 part of enhanced Nodes Restoration for EPC (RFC 7077) | eNR_EPC | 2 | Rel-11 | C4-IETF | 2012-12-07 08:00 | 2013-12-06 17:00 | 100% | CP-120449 | - | Lionel Morand | Lionel Morand | CP#62 completed | RFC 7077 (was draft-ietf-netext-update-notifications) | 58 | 30 |  |  | Sat 24/11/12 | Thu 28/11/13
3393 | 540013 | CT1 part of enhanced Nodes Restoration for EPC | eNR_EPC | 2 | Rel-11 | C1 | 2011-12-02 08:00 | 2012-03-02 17:00 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | CP#55 completed | 29.118 | 54 | 28 |  |  | Wed 23/11/11 | Wed 05/09/12
3394 | 570009 | CT3 part of enhanced Nodes Restoration for EPC | eNR_EPC | 2 | Rel-11 | C3 | 2012-09-10 08:00 | 2012-12-07 17:00 | 100% | CP-120449 | - | ZTE | lu.fei1@zte.com.cn | CP#58 completed | 29.212 | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
3395 | 520009 | Reference Location Information (Stage 3) | RLI | 1 | Rel-11 | C4,C1 | 2011-06-03 08:00 | 2011-09-16 17:00 | 100% | CP-110386 | - | Huawei | susan.shishufeng@Huawei.com | CP#53 completed. Stage 2 clause C.1.1 of SA2 TS 23.167 CR#0182 (WI code: TEI11) | - | 52 | 27 |  |  | Wed 18/05/11 | Wed 01/06/11
3396 | 520109 | CT4 part of Reference Location Information (Stage 3) | RLI | 2 | Rel-11 | C4 | 2011-06-03 08:00 | 2011-06-03 08:00 | 100% | CP-110386 | - | Huawei | susan.shishufeng@Huawei.com | CP#52 completed | 23.008, 29.228, 29.328, 29.329 | 52 | 27 |  |  | Wed 18/05/11 | Thu 02/06/11
3397 | 520209 | CT1 part of Reference Location Information (Stage 3) | RLI | 2 | Rel-11 | C1 | 2011-06-03 08:00 | 2011-09-16 17:00 | 100% | CP-110386 | - | Huawei | susan.shishufeng@Huawei.com | CP#53 completed | 24.229 | 52 | 27 |  |  | Wed 18/05/11 | Wed 01/06/11
3398 | 520010 | IMS Stage 3 IETF Protocol Alignment - phase 5 | IMSProtoc5 | 1 | Rel-11 | C1,C3,IETF | 2011-06-07 08:00 | 2014-09-12 17:00 | 85% | CP-110437 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#57 completed | - | 52 | 27 |  |  | Wed 18/05/11 | Thu 28/02/13
3399 | 520110 | CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 | IMSProtoc5 | 2 | Rel-11 | C1 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | CP-110437 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#57 completed | 23.218, 24.229, 24.930 | 52 | 27 |  |  | Wed 18/05/11 | Tue 14/08/12
3400 | 591001 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (RFC 7315) | IMSProtoc5 | 2 | Rel-11 | C1-IETF | 2013-03-01 08:00 | 2014-09-12 17:00 | 100% | CP-110437 | - | Roland Jesske | Roland Jesske | CP#65 completed | RFC 7315 (was draft-drage-sipping-rfc3455bis), draft-mohali-dispatch-originating-cdiv-parameter | 59 | 30 |  |  | Thu 21/02/13 | Tue 02/09/14
3401 | 800113 | (IETF) A P-Served-User Header Field Parameter for Originating CDIV session case in SIP (RFC8498) | IMSProtoc5 | 2 | Rel-11 | C1-IETF | 2013-03-01 08:00 | 2014-09-12 17:00 | 100% | CP-110437 |  | Roland Jesske | Roland Jesske |  |  | 80 | 41 |  |  | Wed 27/06/18 | NA
3402 | 611002 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (RFC 7135) | IMSProtoc5 | 2 | Rel-11 | C1-IETF | 2013-09-06 08:00 | 2014-06-13 17:00 | 100% | CP-110437 | - | Roland Jesske | Roland Jesske | CP#64 completed | RFC 7135 (was draft-polk-local-emergency-rph-namespace) | 61 | 31 |  |  | Fri 23/08/13 | Fri 06/06/14
3403 | 520210 | CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 5 | IMSProtoc5 | 2 | Rel-11 | C3 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | CP-110437 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#57 completed | 29.163, 29.165 | 52 | 27 |  |  | Wed 18/05/11 | Tue 14/08/12
3404 | 581002 | Deleted - (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (avasarala-dispatch-comm-div-notification) | IMSProtoc5 | 2 | Rel-11 | C3-IETF | 2012-12-07 08:00 | 2014-09-12 17:00 | 100% | CP-110437 | - | Andrew Allen | Andrew Allen | CP#64 Draft removed from 3GPP documentation | draft-avasarala-dispatch-comm-div-notification | 58 | 30 | CP-65 | PCG-33 | Wed 18/05/11 | Tue 02/09/14
3405 | 530003 | Service Identification for RRC Improvements in GERAN (Stage 2/3) | SIRIG | 1 | Rel-11 | S2,C4,C3,G2 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | TSG#57, GP#55 completed. CT defined a generic solution (not only for GERAN) | GERAN | 51 | 27 |  |  | Tue 06/09/11 | Thu 06/09/12
3406 | 560008 | Stage 2 for Service Identification for RRC Improvements in GERAN | SIRIG | 2 | Rel-11 | S2 | 2012-06-18 08:00 | 2012-09-07 17:00 | 100% | - | - | - | - | SP#57 completed | 23.060, 23.251 | 56 | 29 |  |  | Mon 18/06/12 | Fri 31/08/12
3407 | 540018 | CN aspects of Service Identification for RRC Improvements in GERAN | SIRIG | 2 | Rel-11 | C4,C3 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | CP#57 completed | - | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
3408 | 540118 | CT4 part of CN aspects of Service Identification for RRC Improvements in GERAN | SIRIG | 3 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | CP#57 completed | 29.281 | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
3409 | 550009 | Deleted - CT3 part of CN aspects of Service Identification for RRC Improvements in GERAN | SIRIG | 3 | Rel-11 | C3 | 2012-03-02 08:00 | 2012-06-15 17:00 | 100% | CP-120033 | - | China Mobile | zhanghao@chinamobile.com | CP#56 stopped (SA2 decided NO CT3 impact) | 29.212 | 55 | 28 | CP-56 | PCG-29 | Mon 20/02/12 | Fri 20/04/12
3410 | 530103 | GERAN2 part of Service Identification for RRC Improvements in GERAN | SIRIG | 2 | Rel-11 | G2 | 2011-09-19 08:00 | 2012-08-31 17:00 | 100% | GP-111876 | - | China Mobile, Huawei | Juan Deng, Yang Zhao | GP#55 completed. GP#51 approved WID | 48.018 | 51 | 27 |  |  | Tue 06/09/11 | Fri 31/08/12
3411 | 530019 | SAE Protocol Development - Phase 2 | SAES2 | 1 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-110639 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed. Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005 | - | 53 | 27 |  |  | Sat 27/08/11 | Tue 14/08/12
3412 | 530119 | SAE Protocol Development (Stage 3) - Phase 2 | SAES2 | 2 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-110639 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 53 | 27 |  |  | Thu 08/09/11 | Tue 14/08/12
3413 | 530219 | CS Fallback in EPS - Phase 2 | SAES2-CSFB | 2 | Rel-11 | C1 | 2011-09-16 08:00 | 2012-09-07 17:00 | 100% | CP-110639 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed | 23.122, 24.008, 24.167, 24.229, 24.301, 24.302, 24.303, 24.304, 24.305, 24.312, 29.018, 29.118 | 53 | 27 |  |  | Thu 08/09/11 | Tue 14/08/12
3414 | 530020 | GCSMSC and GCR Redundancy for VGCS/VBS (Stage 2/3) | RT_VGCS_Red | 1 | Rel-11 | C1 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120279 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed. Stage 2/3 adding a CN internal functionality, not affecting Voice Group Call Service (VGCS)/VBS as perceived by service subscriber. Hence, no Stage 1 impact for VGCS/VBS (42.068, 42.069) | Stage 2/3 | 53 | 27 |  |  | Sat 27/08/11 | Tue 14/08/12
3415 | 530120 | CT1 part of GCSMSC and GCR Redundancy for VGCS/VBS | RT_VGCS_Red | 2 | Rel-11 | C1 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | CP-120279 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#57 completed | 43.068, 43.069 | 53 | 27 |  |  | Sat 27/08/11 | Tue 14/08/12
3416 | 530220 | Deleted - CT4 part of GCSMSC and GCR Redundancy for VGCS/VBS | RT_VGCS_Red | 2 | Rel-11 | C4 | 2011-09-19 08:00 | 2012-06-15 17:00 | 100% | CP-120279 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#56 stopped (no CT4 impact) | 29.002 | 53 | 27 | CP-56 | PCG-29 | Sat 27/08/11 | Tue 25/09/12
3417 | 540015 | Support of RFC 6140 in IMS | GINI | 1 | Rel-11 | C1 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110760 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#57 completed. Stage 3. Support procedures and protocol extensions in RFC6140 "Registration for Multiple Phone Numbers in SIP" to IMS for complex UEs. Ensure co-existence with NGCN IP-PBX registration procedures already defined in IMS. | 24.229 | 54 | 28 |  |  | Tue 22/11/11 | Tue 14/08/12
3418 | 540017 | Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority | eMPS_Gateway | 1 | Rel-11 | C4,C3 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110806 | - | Telcordia | Viqar Shaikh | CP#57 completed. Stage 3. Stage 1 for MPS in 22.153. Details of any MGW actions for priority needs to be further studied within the scope of this WI. | Stage 3 | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
3419 | 540117 | CT4 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority | eMPS_Gateway | 2 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110806 | - | Telcordia | Viqar Shaikh | CP#57 completed | 23.333, 23.334, 29.232, 29.238, 29.332, 29.333, 29.334 | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
3420 | 540217 | CT3 part of Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority | eMPS_Gateway | 2 | Rel-11 | C3 | 2011-12-02 08:00 | 2012-09-07 17:00 | 100% | CP-110806 | - | Telcordia | Viqar Shaikh | CP#57 completed | 29.162, 29.163, 29.292 | 54 | 28 |  |  | Wed 26/10/11 | Mon 13/08/12
3421 | 550007 | Inter-IMS Network to Network Interface (II-NNI) enhancements: SIP timers applicability (Stage 3) | NNI_timers | 1 | Rel-11 | C3 | 2012-03-02 08:00 | 2012-09-07 17:00 | 100% | CP-120082 | - | Telecom Italia | antonio.ascolese@telecomitalia.it | CP#57 completed | 29.165 | 55 | 28 |  |  | Wed 22/02/12 | Mon 13/08/12
3422 | 560005 | AT commands for Universal Resource Identifier (URI) support | ATURI | 1 | Rel-11 | C1 | 2012-06-15 08:00 | 2013-03-01 17:00 | 100% | CP-120275 | - | Intel | frank.kowalewski@intel.com | CP#59 completed. Define new AT cmd for URI addresses for IMS services (eg VoLTE). 27.007(AT cmd to control MT functions and GSM/UMTS/LTE network services from TE), 27.005(AT commands for SMS). Currently address types for AT cmd based on dialling# | 27.005, 27.007 | 56 | 29 |  |  | Sat 02/06/12 | Sat 16/02/13
3423 | 560006 | PS Additional Number (Stage 3) | PSAN | 1 | Rel-11 | C4 | 2012-06-15 08:00 | 2012-09-07 17:00 | 100% | CP-120253 | - | Deutsche Telekom | Yvette.koza@t-mobile.at | CP#57 completed. Stage 1 in Rel-11 SA1 TS 22.101 clause 17.7.3 (No Stage 2 needed since no architecture impact) | 23.003, 23.008, 29.002, 29.272, 29.230 | 56 | 29 |  |  | Mon 23/04/12 | Mon 13/08/12
3424 | 560007 | Generic IMS User Group Over Sh | GenUG_Sh | 1 | Rel-11 | C4 | 2012-06-15 08:00 | 2012-09-07 17:00 | 100% | CP-120254 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#57 completed | 29.364 | 56 | 29 |  |  | Sat 02/06/12 | Mon 13/08/12
3425 | 570010 | IMS Operator Determined Call Barring | IODB | 1 | Rel-11 | C1,C4 | 2012-09-07 08:00 | 2013-06-14 17:00 | 100% | CP-120685 | - | Orange | Youssef.Chadli@Orange.com | LS_in C4-121615 GSMA IREG RILTE concluded that TS 22.041 clause 5.4 Stage 1 requirements are not covered by stage 3 specifications | - | 57 | 29 |  |  | Mon 13/08/12 | Thu 06/09/12
3426 | 570110 | CT1 part of IMS Operator Determined Call Barring | IODB | 2 | Rel-11 | C1 | 2012-09-10 08:00 | 2013-06-14 17:00 | 100% | CP-120685 | - | Orange | Youssef.Chadli@Orange.com | CP#60 completed. Handling of premium rate numbers remained OPEN in Rel-11 (shifted to Rel-12). CP-130384 LS_out sent to SA1 / GSMA informing this TSG CT decision. | New TS 24.315 | 57 | 29 |  |  | Mon 13/08/12 | Thu 13/06/13
3427 | 570210 | CT4 part of IMS Operator Determined Call Barring | IODB | 2 | Rel-11 | C4 | 2012-09-07 08:00 | 2013-03-12 17:00 | 100% | CP-120685 | - | Orange | Youssef.Chadli@Orange.com | CP#58 completed | 23.008 , 23.015 , 29.328 , 29.329 , 29.364 | 57 | 29 |  |  | Mon 13/08/12 | Sat 17/11/12
3428 | 570011 | Enhanced T.38 FAX support (Stage 3) | MMTel_T.38_FAX | 1 | Rel-11 | C3,C1,C4 | 2012-09-06 08:00 | 2012-12-07 17:00 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#58 completed. Linked to Rel-8 Feature: IMS Multimedia Telephony Service (IMS-MMTel) UID_7038. SA1 added FAX stage 1 requirement only in Rel-10 under TEI10 to TS 22.173 (CR#0064) | - | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
3429 | 570111 | CT3 part of Enhanced T.38 FAX support | MMTel_T.38_FAX | 2 | Rel-11 | C3 | 2012-09-07 08:00 | 2012-12-07 17:00 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#58 completed | 29.163 | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
3430 | 570211 | CT1 part of Enhanced T.38 FAX support | MMTel_T.38_FAX | 2 | Rel-11 | C1 | 2012-09-07 08:00 | 2012-12-07 17:00 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#58 completed | 24.229 | 57 | 29 |  |  | Mon 13/08/12 | Mon 19/11/12
3431 | 570311 | CT4 part of Enhanced T.38 FAX support | MMTel_T.38_FAX | 2 | Rel-11 | C4 | 2012-09-06 08:00 | 2012-09-07 17:00 | 100% | CP-120673 | - | NEC | Naoaki Suzuki (n-suzuki@en.jp.nec.com) | CP#57 completed | 29.332 | 57 | 29 |  |  | Mon 13/08/12 | Tue 20/11/12
3432 | 540016 | Deleted - Enhancement of the Protocols for SMS over SGs (Stage 3) | PROTOC_SMS_SGs | 1 | Rel-11 | C4,C1 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped. Reason: Protocols for SMS over SGs is replaced by the SIMTC SMS in MME solution (as solution not only for MTC user but for general subscribers) | Stage 3 | 54 | 28 | CP-56 | PCG-29 | Wed 26/10/11 | Tue 19/06/12
3433 | 540116 | Deleted - TR Study on enhancement of protocols for SMS service over SGs | PROTOC_SMS_SGs | 2 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped (abandonned new TR 29.818) | new TR 29.818 | 54 | 28 | CP-56 | PCG-29 | Wed 26/10/11 | Tue 19/06/12
3434 | 540216 | Deleted - CT4 part of Enhancement of the Protocols for SMS over SGs | PROTOC_SMS_SGs | 2 | Rel-11 | C4 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped (abandonned new TS 29.218 Diameter based protocols for SMS service over SGs) | 29.305, new TS 29.218 | 54 | 28 | CP-56 | PCG-29 | Wed 26/10/11 | Tue 19/06/12
3435 | 540316 | Deleted - CT1 part of Enhancement of the Protocols for SMS over SGs | PROTOC_SMS_SGs | 2 | Rel-11 | C1 | 2011-12-02 08:00 | 2012-06-15 17:00 | 100% | CP-120034 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#56 stopped | 23.040, 24.011, 43.068 | 54 | 28 | CP-56 | PCG-29 | Wed 26/10/11 | Wed 13/06/12
3436 | 510001 | Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 1 | Rel-11 | G2,S2,C1 | 2011-03-04 08:00 | 2013-05-17 17:00 | 100% | GP-121090 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#58 completed. GP#49 approved WID. Standardization of management of MOCN supporting MSs/UES in CP-150GERAN. Continuation of Rel-10 MOCN-GERAN UID_490001 | GERAN | 49 | 26 |  |  | Fri 04/03/11 | Fri 17/05/13
3437 | 510101 | GERAN part of Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 2 | Rel-11 | G2 | 2011-03-04 08:00 | 2013-05-17 17:00 | 100% | GP-121090 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#58 completed. GP#49 approved WID | 44.018, 44.060, 45.002, 45.008, 48.008, 48.018 | 49 | 26 |  |  | Fri 04/03/11 | Fri 17/05/13
3438 | 510201 | Stage 2 for Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 2 | Rel-11 | S2 | 2011-06-08 08:00 | 2012-03-07 17:00 | 100% | SP-110390 | - | Alcatel-Lucent | nicolas.drevon@alcatel-lucent.com | SP#55 completed | 23.251, 23.272 | 49 | 26 |  |  | Fri 04/03/11 | Tue 06/12/11
3439 | 510301 | CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 2 | Rel-11 | C1,C4 | 2011-06-03 08:00 | 2012-12-07 17:00 | 100% | CP-120563 | - | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#58 completed | - | 49 | 26 |  |  | Sat 02/06/12 | Mon 19/11/12
3440 | 510401 | CT1 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 3 | Rel-11 | C1 | 2011-06-03 08:00 | 2012-12-07 17:00 | 100% | CP-120563 | - | Alcatel-Lucent | jennifer.liu@alcatel-lucent.com | CP#58 completed | 24.008 | 49 | 26 |  |  | Fri 04/03/11 | Mon 19/11/12
3441 | 560004 | CT4 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN | Full_MOCN-GERAN | 3 | Rel-11 | C4 | 2012-06-13 08:00 | 2012-09-07 17:00 | 100% | CP-120563 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | CP#57 completed | 23.003 | 54 | 29 |  |  | Sat 02/06/12 | Mon 19/11/12
3442 | 560042 | Stage 2 for Gateway Core Network Sharing for GERAN | Full_MOCN-GERAN-GWCN | 2 | Rel-11 | S2 | 2012-06-18 08:00 | 2013-03-06 17:00 | 100% | SP-120268 | - | Vodafone | chris.pudney@vodafone.com | SP#59 completed. (23.251CR0062R2 as TEI11. TS 23.251 specifies both MOCN and GWCN for E-UTRAN and UTRAN, but GWCN is not yet supported on GERAN. Extend Full_MOCN-GERAN to also cover GWCN GERAN | 23.251 | 56 | 29 |  |  | Mon 04/06/12 | Thu 22/11/12
3443 | 540003 | Medium range/local area requirements for multicarrier BTS | MRLA | 1 | Rel-11 | G1 | 2011-11-25 08:00 | 2012-11-23 17:00 | 100% | GP-111780 | - | Ericsson | Eric Nordström | GP#56 completed. GP#52 approved WID | GERAN | 52 | 28 |  |  | Fri 25/11/11 | Fri 23/11/12
3444 | 540103 | Core part: Medium range/local area requirements for multicarrier BTS | MRLA-Core | 2 | Rel-11 | G1 | 2011-11-25 08:00 | 2012-11-23 17:00 | 100% | GP-111899 | - | Ericsson | Eric Nordström | Stage 3. GP#56 completed. GP#52 approved WID | 45.005 | 52 | 28 |  |  | Fri 25/11/11 | Fri 23/11/12
3445 | 540203 | Perf. part: Medium range/local area requirements for multicarrier BTS | MRLA-Perf | 2 | Rel-11 | G1 | 2011-11-28 08:00 | 2012-11-23 17:00 | 100% | GP-111782 | - | Ericsson | Eric Nordström | Test spec. GP#56 completed. GP#52 approved WID | 51.021 | 52 | 28 |  |  | Fri 25/11/11 | Fri 23/11/12
3446 | 550023 | Domain Specific Access Control in GERAN | GDSAC | 1 | Rel-11 | G2 | 2012-03-05 08:00 | 2012-08-31 17:00 | 100% | GP-120452 | - | Vodafone | chris.pudney@vodafone.com | GP#55 completed. GP#53 approved WID. Work is dependent upon Full_MOCN-GERAN (UID_510001) | GERAN 44.018 | 53 | 28 |  |  | Wed 18/04/12 | Fri 31/08/12
3447 | 500020 | Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB | 1 | Rel-11 | R4,R2,R3,R5 | 2010-12-10 08:00 | 2013-03-01 17:00 | 100% | RP-111396 | - | Sprint | John.J.Humbert@Sprint.com | Stage 3. Triggered by R4 Rel-10 LTE TR 37.806 Study on Extending 850 MHz (UID_440016) | UTRA, LTE | 50 | 26 |  |  | Fri 10/12/10 | Thu 23/02/12
3448 | 500120 | Core part: Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB-Core | 2 | Rel-11 | R4,R2,R3 | 2010-12-10 08:00 | 2012-03-02 17:00 | 100% | RP-111396 | RP-120075 | Sprint | John.J.Humbert@Sprint.com | RP#55 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141 | 50 | 26 |  |  | Fri 10/12/10 | Thu 23/02/12
3449 | 500220 | Perf. part: Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB-Perf | 2 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-03-02 17:00 | 100% | RP-111396 | RP-120076 | Sprint | John.J.Humbert@Sprint.com | RP#55 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141 | 50 | 26 |  |  | Fri 10/12/10 | Thu 23/02/12
3450 | 510016 | Test part: Extending 850 MHz Upper Band (814 – 849 MHz) | e850_UB-UEConTest | 2 | Rel-11 | R5 | 2011-03-18 08:00 | 2013-03-01 17:00 | 100% | RP-110377 | RP-130043 | Sprint | John.J.Humbert@Sprint.com | RP#59 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 51 | 26 |  |  | Thu 10/03/11 | Wed 27/02/13
3451 | 530030 | Further Self Optimizing Networks (SON) enhancements | SONenh2_LTE_UTRA | 1 | Rel-11 | R3,R2 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-120314 | - | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | Stage 1/2/3 | UTRA, LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3452 | 530130 | Core part: Further Self Optimizing Networks (SON) enhancements | SONenh2_LTE_UTRA-Core | 2 | Rel-11 | R3,R2 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-120314 | RP-121557 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#58 completed | 25.331, 25.401, 25.410, 25.413, 25.423, 25.433, 36.300, 36.331, 36.413, 36.423 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3453 | 530033 | Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN | eMDT_UMTSLTE | 1 | Rel-11 | R2,R1,R3,R4,R5 | 2011-09-19 08:00 | 2013-12-06 17:00 | 100% | RP-121204 | - | MediaTek | Johan Johansson | Stage 2/3 | UTRA, LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3454 | 530133 | Core part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN | eMDT_UMTSLTE-Core | 2 | Rel-11 | R2,R1,R3,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-121204 | RP-121556 | MediaTek | Johan Johansson | RP#58 completed | 25.133, 25.123, 25.304, 25.331, 25.413, 25.423, 36.133, 36.304, 36.306, 36.331, 36.413, 36.423, 37.320, 36.300 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3455 | 590001 | Test part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN | eMDT_UMTSLTE-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2013-12-06 17:00 | 100% | RP-130172 | RP-131447 | NTT DoCoMo | masahiro.tamaoki.eu@nttdocomo.com | RP#62 completed | 34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 29/01/13 | Tue 13/08/13
3456 | 530036 | Network Energy Saving for E-UTRAN | Netw_Energy_LTE | 1 | Rel-11 | R3,GP | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120620 | - | China Mobile | yangning@chinamobile.com | Stage 2/3 | LTE, GERAN | 53 | 27 |  |  | Thu 15/09/11 | Thu 15/09/11
3457 | 530136 | Core part: Network Energy Saving for E-UTRAN | Netw_Energy_LTE-Core | 2 | Rel-11 | R3 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120620 | RP-121016 | China Mobile | yangning@chinamobile.com | RP#57 completed. Inter-RAT aspect can affect UTRA and GERAN as well | 25.413, 36.300, 36.413, 36.423 | 53 | 27 |  |  | Thu 15/09/11 | Thu 06/09/12
3458 | 570001 | GERAN part: Network Energy Saving for E-UTRAN | - | 2 | Rel-11 | GP | 2012-08-27 08:00 | 2012-08-31 17:00 | 100% | GP-121178 | - | Alcatel-Lucent | marguerite.woch@alcatel-lucent.com | GP#55 approved WID and completed. Stage 3. ChangES in CP-150RIM protocol and in SON Transfer RIM application to provide support for Energy Savings Indication feature | 48.018 [Serving GPRS Support Node (SGSN); BSS GPRS protocol (BSSGP)] | 55 | 29 |  |  | Sat 01/09/12 | Sat 01/09/12
3459 | 530037 | E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR | 1 | Rel-11 | R4,G1 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111383 | - | Ericsson | johan.skold@ericsson.com | Stage 3. GERAN BS RF requirements specs need aligned with RAN4 ongoing Rel-11 Feature UID_530037 E-UTRA medium range and MSR medium range/local area BS class requirements (medBS_class_LTE_MSR) | UTRA, LTE, GERAN | 53 | 27 |  |  | Thu 15/09/11 | Thu 15/09/11
3460 | 530137 | Core part: E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR-Core | 2 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111383 | RP-121558 | Ericsson | johan.skold@ericsson.com | RP#58 completed. TR 37.809 v200 for Approval | 25.104, 36.104, 37.104, new TR 37.809 | 53 | 27 |  |  | Thu 15/09/11 | Wed 05/12/12
3461 | 530237 | Perf. part: E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR-Perf | 2 | Rel-11 | R4 | 2011-09-23 08:00 | 2012-12-07 17:00 | 100% | RP-111383 | RP-121559 | Ericsson | johan.skold@ericsson.com | RP#58 completed | 25.141, 36.141, 37.141 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
3462 | 540002 | GERAN part: E-UTRA medium range and MSR medium range/local area BS class requirements | medBS_class_LTE_MSR-GERAN | 2 | Rel-11 | G1 | 2011-11-28 08:00 | 2012-11-23 17:00 | 100% | GP-111779 | - | Ericsson | Eric Nordström | GP#56 completed. GP#52 approved WID | 45.005, 51.021 | 52 | 28 |  |  | Fri 25/11/11 | Fri 23/11/12
3463 | 550015 | RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station | MB_MSR_RF | 1 | Rel-11 | R4,G1 | 2012-02-06 16:12 | 2014-03-06 17:00 | 100% | RP-120857 | - | Huawei | Liu Ye (leo.liuye@huawei.com) | - | UTRA, LTE, GERAN | 55 | 28 |  |  | Thu 23/02/12 | Tue 04/09/12
3464 | 550115 | Core part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station | MB_MSR_RF-Core | 2 | Rel-11 | R4,G1 | 2012-02-06 16:12 | 2012-12-07 17:00 | 100% | RP-120857 | RP-121985 | Huawei | Liu Ye (leo.liuye@huawei.com) | RP#58 completed | 25.104, 25.105, 36.104, 37.104, new TR 37.812 | 55 | 28 |  |  | Thu 23/02/12 | Wed 05/12/12
3465 | 550215 | Perf. part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station | MB_MSR_RF-Perf | 2 | Rel-11 | R4,G1 | 2012-03-08 08:00 | 2014-03-06 17:00 | 100% | RP-120857 | RP-140064 | Huawei | Liu Ye (leo.liuye@huawei.com) | RP#63 completed | 25.141, 25.142, 36.141, 37.141 | 55 | 28 |  |  | Thu 23/02/12 | Mon 03/03/14
3466 | 560013 | Further enhancements to H(e)NB mobility - Part 1 | EHNB_enh1 | 1 | Rel-11 | R3,R2 | 2012-06-15 08:00 | 2012-12-07 17:00 | 100% | RP-121427 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | Stage 2/3. Triggered by FS_EHNB_enh (UTRA, LTE TR 37.803 under AI 12.3.2). Compare also Rel-10 WI HNB_HENB_mob_enh RP-110183 | UTRA, LTE | 56 | 29 |  |  | Wed 13/06/12 | Tue 27/11/12
3467 | 560113 | Core part: Further enhancements to H(e)NB mobility - Part 1 | EHNB_enh1-Core | 2 | Rel-11 | R3,R2 | 2012-06-15 08:00 | 2012-12-07 17:00 | 100% | RP-121427 | RP-121563 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#58 completed | 25.413, 25.467, 25.469, 36.300, 36.413, 36.423 | 56 | 29 |  |  | Wed 13/06/12 | Tue 27/11/12
3468 | 560014 | Further enhancements to H(e)NB mobility - Part 2 | EHNB_enh2 | 1 | Rel-11 | R3,R2 | 2012-06-19 08:00 | 2012-12-07 17:00 | 100% | RP-121712 | - | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | Stage 2/3. Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Triggered by FS_EHNB_enh (UTRA, LTE TR 37.803 under AI 12.3.2) | UTRA, LTE | 56 | 29 |  |  | Wed 13/06/12 | Tue 27/11/12
3469 | 560114 | Core part: Further enhancements to H(e)NB mobility - Part 2 | EHNB_enh2-Core | 2 | Rel-11 | R3,R2 | 2012-06-19 08:00 | 2012-12-07 17:00 | 100% | RP-121712 | RP-121564 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#58 completed Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Updated WID RP-121147=>RP-121712 | 25.413, 25.467, 25.469, 25.471 | 56 | 29 |  |  | Wed 13/06/12 | Tue 27/11/12
3470 | 430011 | Network-Based Positioning Support for LTE | LCS_LTE-NBPS | 1 | Rel-11 | R2,R1,R3,R4 | 2009-03-05 08:00 | 2014-06-13 17:00 | 100% | RP-131259 | - | TruePosition | terri.brooks@trueposition.com | - | LTE | 43 | 22 |  |  | Fri 06/03/09 | Tue 04/09/12
3471 | 430111 | Core part: Network-Based Positioning Support for LTE | LCS_LTE-NBPS-Core | 2 | Rel-11 | R2,R1,R3,R4 | 2009-03-05 08:00 | 2013-06-12 17:00 | 100% | RP-131259 | RP-130483 | TruePosition | terri.brooks@trueposition.com | RP#60 completed | 36.214, 36.300, 36.305, 36.401, 36.413, 36.455, new TS (36.111, 36.456, 36.457, 36.458, 36.459) | 43 | 22 |  |  | Fri 06/03/09 | Thu 29/08/13
3472 | 430211 | Perf. part: Network-Based Positioning Support for LTE | LCS_LTE-NBPS-Perf | 2 | Rel-11 | R4 | 2009-03-24 08:00 | 2014-06-13 17:00 | 100% | RP-131259 | RP-140626 | TruePosition | terri.brooks@trueposition.com | RP#64 completed. TS 36.112v100 for 1-step Approval | 36.111, new TS 36.112 | 43 | 22 |  |  | Fri 06/03/09 | Wed 11/06/14
3473 | 480026 | Service continuity improvements for MBMS for LTE | MBMS_LTE_SC | 1 | Rel-11 | R2,R3,R5 | 2010-06-04 08:00 | 2014-03-06 17:00 | 100% | RP-120258 | - | Huawei | David.Lecompte@huawei.com | - | LTE | 48 | 25 |  |  | Fri 04/06/10 | Fri 13/07/12
3474 | 480126 | Core part: Service continuity improvements for MBMS for LTE | MBMS_LTE_SC-Core | 2 | Rel-11 | R2,R3 | 2010-06-04 08:00 | 2012-09-07 17:00 | 100% | RP-120258 | RP-121001 | Huawei | David.Lecompte@huawei.com | RP#57 completed | 25.446, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.443, 36.444, 36.445 | 48 | 25 |  |  | Fri 04/06/10 | Thu 06/09/12
3475 | 590002 | Test part: Service continuity improvements for MBMS for LTE | MBMS_LTE_SC-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2014-03-06 17:00 | 100% | RP-130296 | RP-140074 | Ericsson | leif.mattisson@ericsson.com | RP#63 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 26/02/13 | Mon 03/03/14
3476 | 510021 | Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE | 1 | Rel-11 | R1,R2,R3,R4,R5 | 2011-03-22 08:00 | 2014-12-15 17:00 | 100% | RP-120860 | - | China Mobile | ShenXiaodong@chinamobile.com | - | LTE | 51 | 26 |  |  | Mon 14/03/11 | Wed 05/12/12
3477 | 510121 | Core part: Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-120860 | RP-121986 | China Mobile | ShenXiaodong@chinamobile.com | RP#58 completed | 36.101, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.304, 36.321, 36.331, 36.413, 36.423 | 51 | 26 |  |  | Mon 14/03/11 | Wed 05/12/12
3478 | 510221 | Perf. part: Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE-Perf | 2 | Rel-11 | R4 | 2011-03-23 08:00 | 2013-12-06 17:00 | 100% | RP-120860 | RP-131463 | China Mobile | ShenXiaodong@chinamobile.com | RP#62 completed | 36.101, 36.104, 36.133, 36.141 | 51 | 26 |  |  | Mon 14/03/11 | Fri 29/11/13
3479 | 600001 | Test part: Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE-UEConTest | 2 | Rel-11 | R5 | 2013-06-15 | 2014-12-15 17:00 | 100% | RP-130649 | RP-141847 | ZTE | Carolyn Taylor (carolyn.tayl@zte.com.cn) | ; Stat Rep: RP-141131->RP-141847 | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 60 | 31 |  |  | Wed 22/05/13 | Mon 12/01/15
3480 | 510028 | New Band LTE Downlink FDD 716-728 MHz (Band 29, CA of Band 2 and Band 29 and of Band 4 and Band 29) | LTE_DL_FDD700 | 1 | Rel-11 | R4 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-110435 | - | AT&T | marc.grant@att.com | Stage 3 | LTE | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
3481 | 510128 | Core part: New Band LTE Downlink FDD 716-728 MHz (Band 29), CA of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700-Core | 2 | Rel-11 | R4 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-110710 | RP-121604 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.141, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
3482 | 510228 | Perf. part: New Band LTE Downlink FDD 716-728 MHz (Band 29), CA of Band 2 and Band 29 and of Band 4 and Band 29 | LTE_DL_FDD700-Perf | 2 | Rel-11 | R4 | 2011-03-29 08:00 | 2012-12-07 17:00 | 100% | RP-110435 | RP-121605 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
3483 | 510031 | LTE RAN Enhancements for Diverse Data Applications | LTE_eDDA | 1 | Rel-11 | R2,R5 | 2011-03-18 08:00 | 2013-09-06 17:00 | 100% | RP-120256 | - | BlackBerry | Gordon Young (gyoung@rim.com) | Stage 2/3 | LTE | 51 | 26 |  |  | Mon 14/03/11 | Wed 28/08/13
3484 | 510131 | Core part: LTE RAN Enhancements for Diverse Data Applications | LTE_eDDA-Core | 2 | Rel-11 | R2 | 2011-03-18 08:00 | 2012-12-07 17:00 | 100% | RP-120256 | RP-121571 | BlackBerry | Gordon Young (gyoung@rim.com) | RP#58 completed | 36.300, 36.321, 36.331, new TR 36.822 | 51 | 26 |  |  | Mon 14/03/11 | Thu 29/11/12
3485 | 590003 | Test part: LTE RAN Enhancements for Diverse Data Applications | LTE_eDDA-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2013-09-06 17:00 | 100% | RP-130338 | RP-130946 | BlackBerry | Enikő Sokondár (esokondar@rim.com) | RP#61 completed | 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 26/02/13 | Wed 28/08/13
3486 | 510032 | LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB | 1 | Rel-11 | R1,R2,R4,R5 | 2011-03-23 08:00 | 2013-03-01 17:00 | 100% | RP-120602 | - | NII Holdings | bill.shvodian@nii.com | Stage 3 | LTE | 51 | 26 |  |  | Mon 14/03/11 | Sat 09/06/12
3487 | 510132 | Core part: LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB-Core | 2 | Rel-11 | R1,R2,R4 | 2011-06-15 08:00 | 2012-09-07 17:00 | 100% | RP-120602 | RP-120570 | NII Holdings | bill.shvodian@nii.com | RP#56 completed | 25.101, 25.104, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.307, 37.104, 37.113 | 51 | 26 |  |  | Mon 14/03/11 | Sat 09/06/12
3488 | 510232 | Perf. part: LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB-Perf | 2 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-06-15 17:00 | 100% | RP-120602 | RP-120571 | NII Holdings | bill.shvodian@nii.com | RP#56 completed | 25.123, 25.133, 25.141, 36.133, 36.141, 37.141 | 51 | 26 |  |  | Mon 14/03/11 | Sat 09/06/12
3489 | 560010 | Test part: LTE E850 - Lower Band for Region 2 (non-US), Band 27 | LTE_e850_LB-UEConTest | 2 | Rel-11 | R5 | 2012-06-18 08:00 | 2013-03-01 17:00 | 100% | RP-120603 | RP-130045 | NII Holdings | bill.shvodian@nii.com | RP#59 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1 | 56 | 29 |  |  | Wed 06/06/12 | Wed 27/02/13
3490 | 520017 | LTE for 700 MHz Digital Dividend | LTE_APAC700 | 1 | Rel-11 | R4,R2,R3,R5 | 2011-06-07 08:00 | 2013-06-14 17:00 | 100% | RP-110875 | - | Ericsson | olav.queseth@ericsson.com | Stage 3. Asian Pacific American Caucus (APAC) Asia-Pacific Telecommunity (APT) Wireless Forum | LTE | 52 | 27 |  |  | Thu 02/06/11 | Sat 09/06/12
3491 | 520117 | Core part: LTE for 700 MHz Digital Dividend | LTE_APAC700-Core | 2 | Rel-11 | R4,R2,R3 | 2011-06-07 08:00 | 2012-06-15 17:00 | 100% | RP-110875 | RP-120572 | Ericsson | olav.queseth@ericsson.com | RP#56 completed. TR 36.820 v100 for Information and Approval | 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.113, new TR 36.820 | 52 | 27 |  |  | Thu 02/06/11 | Sat 09/06/12
3492 | 520217 | Perf. part: LTE for 700 MHz Digital Dividend | LTE_APAC700-Perf | 2 | Rel-11 | R4 | 2011-06-09 08:00 | 2012-06-15 17:00 | 100% | RP-110875 | RP-120573 | Ericsson | olav.queseth@ericsson.com | RP#56 completed | 36.133, 36.141, 37.141 | 52 | 27 |  |  | Thu 02/06/11 | Sat 09/06/12
3493 | 560011 | Test part: LTE for 700 MHz Digital Dividend | LTE_APAC700-UEConTest | 2 | Rel-11 | R5 | 2012-06-18 08:00 | 2013-06-14 17:00 | 100% | RP-120600 | RP-130467 | Ericsson | fredrik.sundstrom@ericsson.com | RP#60 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2, 36.523-3, 37.571-1 | 56 | 29 |  |  | Wed 06/06/12 | Mon 03/06/13
3494 | 520019 | Relays for LTE (part 2) | LTE_Relay2 | 1 | Rel-11 | R4 | 2009-12-04 08:00 | 2013-06-14 17:00 | 100% | RP-110914 | - | Ericsson | christian.hoymann@ericsson.com | Continuation of Rel-10 (open RAN4 Core & Perf parts) | LTE | 46 | 24 |  |  | Mon 30/11/09 | Mon 06/06/11
3495 | 520119 | Core part: Relays for LTE (part 2) | LTE_Relay2-Core | 2 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | RP-110914 | RP-121008 | Ericsson | christian.hoymann@ericsson.com | RP#57 completed. TS 36.116, TR 36.826 v100 for Information & Approval. RP#52 Core part not completed in Rel-10 | 36.133, new RAN4 (36.116, 36.826) | 52 | 27 |  |  | Fri 03/06/11 | Tue 04/09/12
3496 | 520219 | Perf. part: Relays for LTE (part 2) | LTE_Relay2-Perf | 2 | Rel-11 | R4 | 2009-12-04 08:00 | 2013-06-14 17:00 | 100% | RP-110914 | RP-130487 | Ericsson | christian.hoymann@ericsson.com | RP#60 completed. New TS 36.117 v100 for 1-step Approval. RP#52 transferred completely from Rel-10 UID_460213 | 36.133, new TS 36.117 (E-UTRA Relay conformance testing) | 46 | 24 |  |  | Mon 30/11/09 | Tue 04/06/13
3497 | 530031 | Signalling and Procedure for Interference Avoidance for in-device coexistence | SPIA_IDC_LTE | 1 | Rel-11 | R2,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111355 | - | China Mobile | Zhenping HU | Stage 2/3 | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3498 | 530131 | Core part: Signalling and Procedure for Interference Avoidance for in-device coexistence | SPIA_IDC_LTE-Core | 2 | Rel-11 | R2,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111355 | RP-121573 | China Mobile | Zhenping HU | RP#58 completed | 36.133, 36.300, 36.306, 36.321, 36.331 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3499 | 530231 | Perf. part: Signalling and Procedure for Interference Avoidance for in-device coexistence | SPIA_IDC_LTE-Perf | 2 | Rel-11 | R4 | 2011-09-20 08:00 | 2012-12-07 17:00 | 100% | RP-111356 | RP-121574 | China Mobile | Zhenping HU | RP#58 completed | 36.133 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3500 | 530032 | Coordinated Multi-Point Operation for LTE | COMP_LTE | 1 | Rel-11 | R1,R2,R3,R4,R5 | 2011-09-19 08:00 | 2014-12-15 17:00 | 100% | RP-111365 | - | Huawei, Samsung | Juho Lee (juho95.lee@samsung.com), david.mazzarese@huawei.com | Stage 3. Triggered by Rel-11 TR 36.819 Study on Coordinated Multi-Point Operation for LTE (FS_CoMP_LTE) | LTE | 53 | 27 |  |  | Thu 15/09/11 | Thu 15/09/11
3501 | 530132 | Core part: Coordinated Multi-Point Operation for LTE – Uplink | COMP_LTE_UL-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111365 | RP-121575 | Huawei | david.mazzarese@huawei.com | RP#58 completed | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.423 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3502 | 530232 | Perf. part: Coordinated Multi-Point Operation for LTE – Uplink | COMP_LTE_UL-Perf | 2 | Rel-11 | R4 | 2011-09-23 08:00 | 2012-12-07 17:00 | 100% | RP-111365 | RP-121576 | Huawei | Xinwei Zhi (zhixinwei@huawei.com) | RP#58 completed | 36.101, 36.104, 36.133, 36.141 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3503 | 530332 | Core part: Coordinated Multi-Point Operation for LTE – Downlink | COMP_LTE_DL-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111365 | RP-121577 | Samsung | Juho Lee (juho95.lee@samsung.com) | RP#58 completed | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.306, 36.321, 36.331, 36.423 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3504 | 530432 | Perf. part: Coordinated Multi-Point Operation for LTE – Downlink | COMP_LTE_DL-Perf | 2 | Rel-11 | R4 | 2011-09-23 08:00 | 2013-12-06 17:00 | 100% | RP-111365 | RP-131465 | Samsung | xutao.zhou@samsung.com | RP#62 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 53 | 27 |  |  | Thu 15/09/11 | Fri 29/11/13
3505 | 590004 | Test part: Coordinated Multi-Point Operation for LTE | COMP_LTE-UEConTest | 2 | Rel-11 | R5 | 2013-03-15 | 2014-12-15 17:00 | 100% | RP-130376 | RP-141782 | Samsung | Stoyan.Baev@partner.samsung.com |  | 36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 29/01/13 | Mon 12/01/15
3506 | 540025 | Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl | 1 | Rel-11 | R1,R2,R4,R5 | 2011-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-120871 | - | Alcatel-Lucent | sigen.ye@alcatel-lucent.com | Stage 3. RP#58 Core completed. Triggered by UID_510037 Rel-11 TR 36.871 Study on further Downlink MIMO enhancements for LTE-Advanced (FS_LTE_eDL_MIMO_enh) | LTE | 54 | 28 |  |  | Wed 07/12/11 | Wed 28/11/12
3507 | 540125 | Core part: Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl-Core | 2 | Rel-11 | R1,R2,R4 | 2011-12-09 08:00 | 2012-12-07 17:00 | 100% | RP-120871 | RP-121579 | Alcatel-Lucent | sigen.ye@alcatel-lucent.com | RP#58 completed | 36.101, 36.211, 36.212, 36.213, 36.331 | 54 | 28 |  |  | Wed 07/12/11 | Wed 28/11/12
3508 | 540225 | Perf. part: Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl-Perf | 2 | Rel-11 | R4 | 2011-12-16 08:00 | 2014-06-13 17:00 | 100% | RP-120871 | RP-140651 | Alcatel-Lucent | teck.hu@alcatel-lucent.com | RP#64 completed | 36.101, 36.104, 36.133, 36.141 | 54 | 28 |  |  | Wed 07/12/11 | Wed 11/06/14
3509 | 590005 | Test part: Enhanced downlink control channel(s) for LTE Advanced | LTE_enh_dl_ctrl-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2014-09-12 17:00 | 100% | RP-130304 | RP-141256 | Huawei | Xu Kai (xk.xukai@huawei.com) | RP#65 completed | 36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 29/01/13 | Tue 09/09/14
3510 | 550012 | Public Safety Broadband High Power UE for Band 14 for Region 2 | LTE_B14_PSBB_HPUE | 1 | Rel-11 | R4,R5 | 2012-03-05 08:00 | 2013-09-06 17:00 | 100% | RP-120362 | - | Motorola Solutions | xiaowei.jin@motorolasolutions.com | Stage 3 | LTE | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
3511 | 550112 | Core part: Public Safety Broadband High Power UE for Band 14 for Region 2 | LTE_B14_PSBB_HPUE-Core | 2 | Rel-11 | R4 | 2012-03-05 08:00 | 2012-12-07 17:00 | 100% | RP-120362 | RP-121581 | Motorola Solutions | xiaowei.jin@motorolasolutions.com | RP#58 completed. TR 36.837 v100 for Information and Approval | 36.101, new TR 36.837 | 55 | 28 |  |  | Thu 23/02/12 | Wed 05/12/12
3512 | 590006 | Test part: Public Safety Broadband High Power UE for Band 14 for Region 2 | LTE_B14_PSBB_HPUE-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2013-09-06 17:00 | 100% | RP-130169 | RP-130949 | Motorola Solutions | xiaowei.jin@motorolasolutions.com | RP#61 completed | 36.521-1, 36.521-2 | 59 | 30 |  |  | Tue 26/02/13 | Thu 29/08/13
3513 | 550013 | Improved Minimum Performance Requirements for E-UTRA: Interference Rejection | LTE_Interf_Rej | 1 | Rel-11 | R4,R5 | 2012-03-05 08:00 | 2014-09-12 17:00 | 100% | RP-120382 | - | Renesas Mobile | Timo Roman | RP#58 completed. Triggered by FS_enh_perf_UE_LTE. Adds Perf. requirements for demodulation of the already specified PDSCH with the transmission modes defined in Rel-8 to Rel-10 | LTE | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
3514 | 550113 | Perf. part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection | LTE_Interf_Rej-Perf | 2 | Rel-11 | R4 | 2012-03-05 08:00 | 2012-12-07 17:00 | 100% | RP-120382 | RP-121582 | Renesas Mobile | Timo Roman | RP#58 completed | 36.101 | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
3515 | 600002 | Test part: Improved Minimum Performance Requirements for E-UTRA: Interference Rejection | LTE_Interf_Rej-UEConTest | 2 | Rel-11 | R5 | 2013-06-18 08:00 | 2014-09-12 17:00 | 100% | RP-140491 | RP-141602 | Broadcom | jarkko.hellsten@kolumbus.fi | RP#65 completed. TR 36.904 for 1-step Approval. Testing for 36.101 | 36.508, 36.521-1, 36.521-2, New TR 36.904 | 60 | 31 |  |  | Wed 22/05/13 | Sun 07/09/14
3516 | 550014 | Additional special subframe configuration for LTE TDD | LTE_TDD_add_subframe | 1 | Rel-11 | R4,R2,R3,R5 | 2012-03-05 08:00 | 2013-06-14 17:00 | 100% | RP-120384 | - | China Mobile | Xiaodong Shen | Stage 3. Exists already for 1UL a WI LTE_CA_B3_B5 | LTE | 55 | 28 |  |  | Thu 23/02/12 | Tue 28/02/12
3517 | 550114 | Core part: Additional special subframe configuration for LTE TDD | LTE_TDD_add_subframe-Core | 2 | Rel-11 | R4,R2,R3 | 2012-03-05 08:00 | 2012-09-07 17:00 | 100% | RP-120384 | RP-121019 | China Mobile | Xiaodong Shen | RP#57 completed | 36.211, 36.213, 36.331, 36.423 | 55 | 28 |  |  | Thu 23/02/12 | Thu 06/09/12
3518 | 590007 | Test part: Additional special subframe configuration for LTE TDD | LTE_TDD_add_subframe-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2013-06-14 17:00 | 100% | RP-130305 | RP-130475 | Huawei | Li Xiang (tricia.li@huawei.com) | RP#60 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 59 | 30 |  |  | Tue 26/02/13 | Tue 04/06/13
3519 | 580158 | Rel-11 LTE Carrier Aggregation (CA) | LTE_CA_Rel-11 | 1 | Rel-11 | R1,R2,R3,R4,R5 | 2010-12-10 08:00 | 2014-12-12 17:00 | 100% | - | - | - | - | LTE_CA_Rel-11 | LTE | 58 | 30 |  |  | Fri 30/11/12 | Fri 30/11/12
3520 | 510030 | LTE CA Enhancements | LTE_CA_enh | 2 | Rel-11 | R1,R2,R3,R4,R5 | 2011-03-15 | 2014-12-12 17:00 | 100% | RP-121999 | - | Nokia | lars.e.lindh@nokia.com | Stage 3 | LTE | 51 | 26 |  |  | Mon 14/03/11 | Tue 04/09/12
3521 | 510130 | Core part: LTE CA Enhancements | LTE_CA_enh-Core | 3 | Rel-11 | R1,R2,R4,R3 | 2011-03-22 08:00 | 2013-08-27 10:00 | 100% | RP-121999 | RP-130059 | Nokia | lars.e.lindh@nokia.com | RP#59 completed. New TR 36.823 v100 for Information and Approval | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, new TR 36.823 | 51 | 26 |  |  | Mon 14/03/11 | Wed 27/02/13
3522 | 510230 | Perf. part: LTE CA Enhancements | LTE_CA_enh-Perf | 3 | Rel-11 | R4 | 2011-03-15 | 2014-12-12 17:00 | 100% | RP-121999 | RP-141969 | Nokia | lars.e.lindh@nokia.com | ; Stat Rep: RP-141377->RP-141969 | 36.101, 36.104, 36.133, 36.141 | 51 | 26 |  |  | Mon 14/03/11 | Mon 12/01/15
3523 | 600003 | Test part: LTE CA Enhancements | LTE_CA_enh-UEConTest | 3 | Rel-11 | R5 | 2013-06-18 08:00 | 2014-09-12 17:00 | 100% | RP-140619 | RP-141443 | Microsoft | jussi.kuusisto@microsoft.com | SP#65 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 60 | 31 |  |  | Wed 22/05/13 | Tue 09/09/14
3524 | 570006 | UE Conformance Test Aspects – LTE Advanced CA of Intra-band contiguous and Inter-band configurations | LTE_CA_intraC_inter_UEConTest | 2 | Rel-11 | R5 | 2012-09-11 08:00 | 2013-12-06 17:00 | 100% | RP-121814 | RP-131446 | Nokia | jussi.kuusisto@nokia.com | RP#62 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1 | 57 | 29 |  |  | Wed 05/09/12 | Fri 07/06/13
3525 | 580258 | Rel-11 inter-band CA | - | 2 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | - | - | - | - | LTE_CA_Rel-11 | LTE | 58 | 30 |  |  | Fri 30/11/12 | Fri 30/11/12
3526 | 480023 | LTE Advanced CA of Band 3 and Band 7 | LTE_CA_B3_B7 | 3 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | RP-120830 | - | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#57 completed. In Europe Band 3,7,20 are interesting for LTE and LTE-Advanced deployment. Different CA combinations for these bands are of high priority for Region 1 | LTE | 48 | 25 |  |  | Fri 04/06/10 | Tue 04/09/12
3527 | 480123 | Core part: LTE Advanced CA of Band 3 and Band 7 | LTE_CA_B3_B7-Core | 4 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-09-07 17:00 | 100% | RP-120830 | RP-121022 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | 48 | 25 |  |  | Fri 04/06/10 | Tue 04/09/12
3528 | 480223 | Perf. part: LTE Advanced CA of Band 3 and Band 7 | LTE_CA_B3_B7-Perf | 4 | Rel-11 | R4 | 2010-12-17 08:00 | 2012-12-07 17:00 | 100% | RP-120830 | RP-121023 | TeliaSonera | Ralf.Schuh@TeliaSonera.com | RP#57 completed | 36.133, 36.141 | 48 | 25 |  |  | Fri 04/06/10 | Tue 04/09/12
3529 | 500017 | LTE Advanced CA of Band 4 and Band 17 | LTE_CA_B4_B17 | 3 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | RP-121458 | - | AT&T | marc.grant@att.com | Stage 3. RP#57 Core completed. RP#58 Perf completed | LTE | 50 | 26 |  |  | Fri 10/12/10 | Mon 26/11/12
3530 | 500117 | Core part: LTE Advanced CA of Band 4 and Band 17 | LTE_CA_B4_B17-Core | 4 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-09-07 17:00 | 100% | RP-121458 | RP-121024 | AT&T | marc.grant@att.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.850 | 50 | 26 |  |  | Fri 10/12/10 | Tue 04/09/12
3531 | 500217 | Perf. part: LTE Advanced CA of Band 4 and Band 17 | LTE_CA_B4_B17-Perf | 4 | Rel-11 | R4 | 2010-12-17 08:00 | 2012-12-07 17:00 | 100% | RP-121458 | RP-121595 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | 50 | 26 |  |  | Fri 10/12/10 | Mon 26/11/12
3532 | 500018 | LTE Advanced CA of Band 4 and Band 13 | LTE_CA_B4_B13 | 3 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | RP-120905 | - | Ericsson | christian.bergljung@ericsson.com | Stage 3. RP#57 Core completed. RP#58 Perf completed | LTE | 50 | 26 |  |  | Fri 10/12/10 | Tue 27/11/12
3533 | 500118 | Core part: LTE Advanced CA of Band 4 and Band 13 | LTE_CA_B4_B13-Core | 4 | Rel-11 | R4 | 2010-12-10 08:00 | 2012-09-07 17:00 | 100% | RP-120905 | RP-121026 | Ericsson | christian.bergljung@ericsson.com | RP#57 completed | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | 50 | 26 |  |  | Fri 10/12/10 | Tue 04/09/12
3534 | 500218 | Perf. part: LTE Advanced CA of Band 4 and Band 13 | LTE_CA_B4_B13-Perf | 4 | Rel-11 | R4 | 2010-12-21 08:00 | 2012-12-07 17:00 | 100% | RP-120905 | RP-121594 | Ericsson | christian.bergljung@ericsson.com | RP#58 completed | 36.101, 36.133, 36.141 | 50 | 26 |  |  | Fri 10/12/10 | Tue 27/11/12
3535 | 510022 | LTE Advanced CA of Band 4 and Band 12 | LTE_CA_B4_B12 | 3 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-120877 | - | Leap Wireless | Bill Chandler (bchandler@cricketcommunications.com) | Stage 3. RP#58 completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
3536 | 510122 | Core part: LTE Advanced CA of Band 4 and Band 12 | LTE_CA_B4_B12-Core | 4 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-120877 | RP-121592 | Leap Wireless | Bill Chandler (bchandler@cricketcommunications.com) | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
3537 | 510222 | Perf. part: LTE Advanced CA of Band 4 and Band 12 | LTE_CA_B4_B12-Perf | 4 | Rel-11 | R4 | 2011-03-29 08:00 | 2012-12-07 17:00 | 100% | RP-120877 | RP-121593 | Leap Wireless | Bill Chandler (bchandler@cricketcommunications.com) | RP#58 completed | 36.133, 36.141 | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
3538 | 510023 | LTE Advanced CA of Band 5 and Band 12 | LTE_CA_B5_B12 | 3 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-120221 | - | US Cellular | sebastian.thalanany@uscellular.com | Stage 3. RP#58 completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
3539 | 510123 | Core part: LTE Advanced CA of Band 5 and Band 12 | LTE_CA_B5_B12-Core | 4 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2012-12-07 17:00 | 100% | RP-120221 | RP-121596 | US Cellular | sebastian.thalanany@uscellular.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
3540 | 510223 | Perf. part: LTE Advanced CA of Band 5 and Band 12 | LTE_CA_B5_B12-Perf | 4 | Rel-11 | R4 | 2011-03-25 08:00 | 2012-12-07 17:00 | 100% | RP-120221 | RP-121597 | US Cellular | sebastian.thalanany@uscellular.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
3541 | 510024 | LTE Advanced CA of Band 7 and Band 20 | LTE_CA_B7_B20 | 3 | Rel-11 | R4 | 2011-03-22 08:00 | 2012-09-07 17:00 | 100% | RP-120889 | - | Huawei | Steven Chen | Stage 3. RP#57 completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Tue 04/09/12
3542 | 510124 | Core part: LTE Advanced CA of Band 7 and Band 20 | LTE_CA_B7_B20-Core | 4 | Rel-11 | R4 | 2011-03-22 08:00 | 2012-09-07 17:00 | 100% | RP-120889 | RP-121032 | Huawei | Steven Chen | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Tue 04/09/12
3543 | 510224 | Perf. part: LTE Advanced CA of Band 7 and Band 20 | LTE_CA_B7_B20-Perf | 4 | Rel-11 | R4 | 2011-03-25 08:00 | 2012-09-07 17:00 | 100% | RP-120889 | RP-121033 | Huawei | Steven Chen | RP#57 completed | 36.133, 36.141 | 51 | 26 |  |  | Mon 14/03/11 | Tue 04/09/12
3544 | 510025 | LTE Advanced CA of Band 2 and Band 17 | LTE_CA_B2_B17 | 3 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | RP-110432 | - | AT&T | marc.grant@att.com | Stage 3. RP#57 Core completed. RP#58 Perf completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
3545 | 510125 | Core part: LTE Advanced CA of Band 2 and Band 17 | LTE_CA_B2_B17-Core | 4 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-09-07 17:00 | 100% | RP-110432 | RP-121034 | AT&T | marc.grant@att.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Tue 04/09/12
3546 | 510225 | Perf. part: LTE Advanced CA of Band 2 and Band 17 | LTE_CA_B2_B17-Perf | 4 | Rel-11 | R4 | 2011-03-25 08:00 | 2012-12-07 17:00 | 100% | RP-110432 | RP-121585 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
3547 | 510026 | LTE Advanced CA of Band 4 and Band 5 | LTE_CA_B4_B5 | 3 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | RP-110433 | - | AT&T | marc.grant@att.com | Stage 3. RP#58 completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
3548 | 510126 | Core part: LTE Advanced CA of Band 4 and Band 5 | LTE_CA_B4_B5-Core | 4 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | RP-110433 | RP-121757 | AT&T | marc.grant@att.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Wed 28/11/12
3549 | 510226 | Perf. part: LTE Advanced CA of Band 4 and Band 5 | LTE_CA_B4_B5-Perf | 4 | Rel-11 | R4 | 2011-03-25 08:00 | 2012-12-07 17:00 | 100% | RP-110433 | RP-121589 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
3550 | 510027 | LTE Advanced CA of Band 5 and Band 17 | LTE_CA_B5_B17 | 3 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | RP-110434 | - | AT&T | marc.grant@att.com | Stage 3. RP#58 completed | LTE | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
3551 | 510127 | Core part: LTE Advanced CA of Band 5 and Band 17 | LTE_CA_B5_B17-Core | 4 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-12-07 17:00 | 100% | RP-110434 | RP-121598 | AT&T | marc.grant@att.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, new generic TR 36.850 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
3552 | 510227 | Perf. part: LTE Advanced CA of Band 5 and Band 17 | LTE_CA_B5_B17-Perf | 4 | Rel-11 | R4 | 2011-03-25 08:00 | 2012-12-07 17:00 | 100% | RP-110434 | RP-121599 | AT&T | marc.grant@att.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 51 | 26 |  |  | Mon 14/03/11 | Mon 26/11/12
3553 | 530023 | LTE Advanced CA of Band 3 and Band 20 | LTE_CA_B3_B20 | 3 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120887 | - | Vodafone | tim.frost@vodafone.com | Stage 3. RP#57 completed | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
3554 | 530123 | Core part: LTE Advanced CA of Band 3 and Band 20 | LTE_CA_B3_B20-Core | 4 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120887 | RP-121046 | Vodafone | tim.frost@vodafone.com | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
3555 | 530223 | Perf. part: LTE Advanced CA of Band 3 and Band 20 | LTE_CA_B3_B20-Perf | 4 | Rel-11 | R4 | 2011-09-20 08:00 | 2012-09-07 17:00 | 100% | RP-120887 | RP-121047 | Vodafone | tim.frost@vodafone.com | RP#57 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
3556 | 530024 | LTE Advanced CA of Band 8 and Band 20 | LTE_CA_B8_B20 | 3 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-120888 | - | Vodafone | Luis.Anaya@vodafone.com | Stage 3. RP#58 completed | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3557 | 530124 | Core part: LTE Advanced CA of Band 8 and Band 20 | LTE_CA_B8_B20-Core | 4 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-120888 | RP-121600 | Vodafone | Luis.Anaya@vodafone.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3558 | 530224 | Perf. part: LTE Advanced CA of Band 8 and Band 20 | LTE_CA_B8_B20-Perf | 4 | Rel-11 | R4 | 2011-09-23 08:00 | 2012-12-07 17:00 | 100% | RP-120888 | RP-121601 | Vodafone | Luis.Anaya@vodafone.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3559 | 530026 | LTE Advanced CA of Band 3 and Band 5 | LTE_CA_B3_B5 | 3 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120899 | - | SK Telecom | Haesung Park | Stage 3. RP#57 completed | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
3560 | 530126 | Core part: LTE Advanced CA of Band 3 and Band 5 | LTE_CA_B3_B5-Core | 4 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120899 | RP-121042 | SK Telecom | Haesung Park | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
3561 | 530226 | Perf. part: LTE Advanced CA of Band 3 and Band 5 | LTE_CA_B3_B5-Perf | 4 | Rel-11 | R4 | 2011-09-21 08:00 | 2012-09-07 17:00 | 100% | RP-120899 | RP-121043 | SK Telecom | Haesung Park | RP#57 completed | 36.133, 36.141 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
3562 | 530027 | LTE Advanced CA of Band 4 and Band 7 | LTE_CA_B4_B7 | 3 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-121152 | - | Rogers Wireless | takwing.wan@rci.rogers.com | Stage 3. RP#58 completed | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3563 | 530127 | Core part: LTE Advanced CA of Band 4 and Band 7 | LTE_CA_B4_B7-Core | 4 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-121152 | RP-121590 | Rogers Wireless | takwing.wan@rci.rogers.com | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, new generic TR 36.850 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3564 | 530227 | Perf. part: LTE Advanced CA of Band 4 and Band 7 | LTE_CA_B4_B7-Perf | 4 | Rel-11 | R4 | 2011-09-23 08:00 | 2012-12-07 17:00 | 100% | RP-121152 | RP-121591 | Rogers Wireless | takwing.wan@rci.rogers.com | RP#58 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3565 | 540020 | LTE Advanced CA of Band 11 and Band 18 | LTE_CA_B11_B18 | 3 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-12-07 17:00 | 100% | RP-120898 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Stage 3. RP#58 completed | LTE | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/12/12
3566 | 540120 | Core part: LTE Advanced CA of Band 11 and Band 18 | LTE_CA_B11_B18-Core | 4 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-12-07 17:00 | 100% | RP-120898 | RP-121602 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/12/12
3567 | 540220 | Perf. part: LTE Advanced CA of Band 11 and Band 18 | LTE_CA_B11_B18-Perf | 4 | Rel-11 | R4 | 2011-12-15 08:00 | 2012-12-07 17:00 | 100% | RP-120898 | RP-121603 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#58 completed | 36.133 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/12/12
3568 | 540021 | LTE Advanced CA of Band 1 and Band 18 | LTE_CA_B1_B18 | 3 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-120892 | - | KDDI | Masaaki Obara (ms-obara@kddi.com) | Stage 3. RP#57 completed | LTE | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
3569 | 540121 | Core part: LTE Advanced CA of Band 1 and Band 18 | LTE_CA_B1_B18-Core | 4 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-120892 | RP-121052 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.307, new generic TR 36.850 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
3570 | 540221 | Perf. part: LTE Advanced CA of Band 1 and Band 18 | LTE_CA_B1_B18-Perf | 4 | Rel-11 | R4 | 2011-12-13 08:00 | 2012-09-07 17:00 | 100% | RP-120892 | RP-121053 | KDDI | Masaaki Obara (ms-obara@kddi.com) | RP#57 completed | 36.133, 36.141 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
3571 | 540022 | LTE Advanced CA of Band 1 and Band 19 | LTE_CA_B1_B19 | 3 | Rel-11 | R4,R2 | 2011-12-12 08:00 | 2012-09-07 17:00 | 100% | RP-120866 | - | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | Stage 3. RP#56 completed. Updated WID RP-111765=>RP-120866 | LTE | 54 | 28 |  |  | Wed 07/12/11 | Fri 15/06/12
3572 | 540122 | Core part: LTE Advanced CA of Band 1 and Band 19 | LTE_CA_B1_B19-Core | 4 | Rel-11 | R4,R2 | 2012-03-05 08:00 | 2012-09-07 17:00 | 100% | RP-120866 | RP-120552 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#56 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | 54 | 28 |  |  | Wed 07/12/11 | Fri 15/06/12
3573 | 540222 | Perf. part: LTE Advanced CA of Band 1 and Band 19 | LTE_CA_B1_B19-Perf | 4 | Rel-11 | R4 | 2011-12-12 08:00 | 2012-06-15 17:00 | 100% | RP-120866 | RP-120553 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#56 completed | 36.133, 36.141 | 54 | 28 |  |  | Wed 07/12/11 | Fri 15/06/12
3574 | 540023 | LTE Advanced CA of Band 1 and Band 21 | LTE_CA_B1_B21 | 3 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-12-07 17:00 | 100% | RP-121173 | - | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | Stage 3. RP#57 completed. Updated WID RP-111764=>RP-121173 | LTE | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
3575 | 540123 | Core part: LTE Advanced CA of Band 1 and Band 21 | LTE_CA_B1_B21-Core | 4 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-121173 | RP-121054 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
3576 | 540223 | Perf. part: LTE Advanced CA of Band 1 and Band 21 | LTE_CA_B1_B21-Perf | 4 | Rel-11 | R4 | 2011-12-13 08:00 | 2012-12-07 17:00 | 100% | RP-121173 | RP-121055 | NTT DoCoMo | Hiromasa Umeda (umedah@nttdocomo.co.jp) | RP#57 completed | 36.133, 36.141 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
3577 | 550018 | LTE Advanced CA of Band 3 and Band 8 | LTE_CA_B3_B8 | 3 | Rel-11 | R4 | 2012-03-05 08:00 | 2012-12-07 17:00 | 100% | RP-121162 | - | KT | Chungwoo HWANG (cwhwang@kt.com) | Stage 3. RP#58 completed | LTE | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
3578 | 550118 | Core part: LTE Advanced CA of Band 3 and Band 8 | LTE_CA_B3_B8-Core | 4 | Rel-11 | R4 | 2012-03-05 08:00 | 2012-12-07 17:00 | 100% | RP-121162 | RP-121586 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#58 completed. RP#59 new generic TR 36.850v100 for Information and Approval | 36.101, 36.104, 36.133, 36.307, new generic TR 36.850 | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
3579 | 550218 | Perf. part: LTE Advanced CA of Band 3 and Band 8 | LTE_CA_B3_B8-Perf | 4 | Rel-11 | R4 | 2012-03-06 08:00 | 2012-12-07 17:00 | 100% | RP-121162 | RP-121587 | KT | Chungwoo HWANG (cwhwang@kt.com) | RP#58 completed | 36.133, 36.141 | 55 | 28 |  |  | Thu 23/02/12 | Tue 27/11/12
3580 | 580358 | Rel-11 intra-band CA | - | 2 | Rel-11 | RP | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | - | - | - | - | LTE_CA_Rel-11 | LTE | 58 | 30 |  |  | Fri 30/11/12 | Fri 30/11/12
3581 | 520015 | LTE Advanced CA in Band 38 | LTE_CA_B38 | 3 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | RP-110862 | - | Huawei | ronnie.zhang@huawei.com | Stage 3. RP#57 completed. WI only covers intra-band contiguous and not non-contiguous aspects | LTE | 52 | 27 |  |  | Thu 02/06/11 | Tue 04/09/12
3582 | 520115 | Core part: LTE Advanced CA in Band 38 | LTE_CA_B38-Core | 4 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | RP-110862 | RP-121060 | Huawei | ronnie.zhang@huawei.com | RP#57 completed. TR 36.830 v100 for Information & Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new TR 36.833-1-38 [instead of 36.830] | 52 | 27 |  |  | Thu 02/06/11 | Tue 04/09/12
3583 | 520215 | Perf. part: LTE Advanced CA in Band 38 | LTE_CA_B38-Perf | 4 | Rel-11 | R4 | 2011-06-08 08:00 | 2012-09-07 17:00 | 100% | RP-110862 | RP-121061 | Huawei | ronnie.zhang@huawei.com | RP#57 completed | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141 | 52 | 27 |  |  | Thu 02/06/11 | Tue 04/09/12
3584 | 520016 | LTE Advanced CA in Band 41 | LTE_CA_B41 | 3 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-03-02 17:00 | 100% | RP-120249 | - | Clearwire | michael.hart@clearwire.com | RP#55 completed. WI only covers intra-band contiguous and not non-contiguous aspects. | LTE | 52 | 27 |  |  | Thu 02/06/11 | Thu 23/02/12
3585 | 520116 | Core part: LTE Advanced CA in Band 41 | LTE_CA_B41-Core | 4 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-03-02 17:00 | 100% | RP-120249 | RP-120126 | Clearwire | michael.hart@clearwire.com | RP#55 completed. Updated WID RP-110673=>RP-120249. TR 36.827 v100 for Information + Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, new TR 36.833-1-41 [instead of 36.827] | 52 | 27 |  |  | Thu 02/06/11 | Thu 23/02/12
3586 | 520216 | Perf. part: LTE Advanced CA in Band 41 | LTE_CA_B41-Perf | 4 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-03-02 17:00 | 100% | RP-120249 | RP-120127 | Clearwire | michael.hart@clearwire.com | RP#55 completed | 36.101, 36.104, 36.133, 36.141, 36.307 | 52 | 27 |  |  | Thu 02/06/11 | Thu 23/02/12
3587 | 530028 | LTE Advanced CA in Band 7 | LTE_CA_B7 | 3 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-121193 | - | China Unicom | Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn) | Stage 3. RP#57 completed. Updated WID RP-111356=>RP-121193. WI only covers intra-band contiguous and not non-contiguous aspects | LTE | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
3588 | 530128 | Core part: LTE Advanced CA in Band 7 | LTE_CA_B7-Core | 4 | Rel-11 | R4 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-121193 | RP-121062 | China Unicom | Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn) | RP#57 completed. TR 36.831 v100 for Information & Approval | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new TR 36.833-1-07 [instead of 36.831] | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
3589 | 530228 | Perf. part: LTE Advanced CA in Band 7 | LTE_CA_B7-Perf | 4 | Rel-11 | R4 | 2011-09-20 08:00 | 2012-09-07 17:00 | 100% | RP-121193 | RP-121063 | China Unicom | Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn) | RP#57 completed | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141 | 53 | 27 |  |  | Thu 15/09/11 | Tue 04/09/12
3590 | 450016 | UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest | 1 | Rel-11 | R4,R5 | 2009-09-18 08:00 | 2016-09-15 17:00 | 100% | RP-111381 | - | CATR | Guo Lin (guolin@emcite.com) | - | UTRA | 45 | 23 |  |  | Tue 15/09/09 | Sat 17/09/11
3591 | 450116 | Core part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest-Core | 2 | Rel-11 | R4 | 2009-09-18 08:00 | 2011-12-09 17:00 | 100% | RP-111381 | RP-111456 | CATR | Guo Lin (guolin@emcite.com) | RP#54 completed | 25.144, 25.914, 34.114 | 45 | 23 |  |  | Tue 15/09/09 | Tue 29/11/11
3592 | 520011 | Test part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest-UEConTest | 2 | Rel-11 | R5 | 2011-06-15 | 2016-09-15 17:00 | 100% | RP-110629 | RP-151187 | ZTE | carolyn.tayl@zte.com.cn | 1st Apr 15: CD:Mon 15/06/15->Wed 15/06/16 1st Apr 15: Stat Rep: RP-141846->RP-150068 03/07/15: Stat Rep: RP-150068->RP-150603 29/09/15: Stat Rep: RP-150603->RP-151187 | 34.114 | 52 | 27 |  |  | Mon 23/05/11 | Mon 26/09/16
3593 | 500019 | Eight carrier HSDPA | 8C_HSDPA | 1 | Rel-11 | R1,R2,R3,R4 | 2010-09-15 17:00 | 2012-12-07 17:00 | 100% | RP-101419 | - | Ericsson | johan.hultell@ericsson.com | Stage 3 | UTRA | 50 | 26 |  |  | Fri 10/12/10 | Tue 04/09/12
3594 | 500119 | Core part: Eight carrier HSDPA | 8C_HSDPA-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2010-09-15 17:00 | 2012-06-15 17:00 | 100% | RP-101419 | RP-120971 | Ericsson | johan.hultell@ericsson.com | RP#57 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306 | 50 | 26 |  |  | Fri 10/12/10 | Tue 04/09/12
3595 | 500219 | Perf. part: Eight carrier HSDPA | 8C_HSDPA-Perf | 2 | Rel-11 | R4 | 2010-12-15 08:00 | 2012-12-07 17:00 | 100% | RP-101419 | RP-120972 | Ericsson | johan.hultell@ericsson.com | RP#57 completed | 25.101, 25.104, 25.133, 25.141 | 50 | 26 |  |  | Fri 10/12/10 | Tue 04/09/12
3596 | 500021 | UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD | LCR_TDD_UE_demod_mc | 1 | Rel-11 | R4,R5 | 2010-12-10 08:00 | 2012-03-02 17:00 | 100% | RP-111244 | - | China Mobile | Li Nan (linan@chinamobile.com) | Stage 3 | UTRA | 50 | 26 |  |  | Fri 10/12/10 | Mon 12/09/11
3597 | 500121 | Perf. part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD | LCR_TDD_UE_demod_mc-Perf | 2 | Rel-11 | R4 | 2010-12-10 08:00 | 2011-09-16 17:00 | 100% | RP-111244 | RP-110996 | China Mobile | Li Nan (linan@chinamobile.com) | RP#53 completed. TR 25.873v100 for Approval | 25.102, new TR 25.873 | 50 | 26 |  |  | Fri 10/12/10 | Mon 12/09/11
3598 | 530038 | Test part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD | LCR_TDD_UE_demod_mc-UEConTest | 2 | Rel-11 | R5 | 2011-09-19 08:00 | 2012-03-02 17:00 | 100% | RP-111181 | RP-120052 | China Mobile | Ma Shuai (mashuai@chinamobile.com) | RP#55 completed | 34.108, 34.122 | 53 | 27 |  |  | Tue 06/09/11 | Thu 23/02/12
3599 | 500022 | Uplink Transmit Diversity for HSPA | HSPA_UL_TxDiv | 1 | Rel-11 | R1,R4,R2,R3,R5 | 2010-12-10 08:00 | 2014-06-13 17:00 | 100% | RP-120367 | - | Huawei | zongjie.wang@huawei.com | Stage 2/3 | UTRA | 50 | 26 |  |  | Fri 10/12/10 | Tue 28/02/12
3600 | 500122 | Core part: Uplink Transmit Diversity for HSPA - Closed Loop | HSPA_UL_TxDiv-CL-Core | 2 | Rel-11 | R1,R4,R2,R3 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | RP-120367 | RP-121542 | Huawei | zongjie.wang@huawei.com | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.319, 25.321, 25.331, 25.423, 25.433 | 50 | 26 |  |  | Fri 10/12/10 | Wed 28/11/12
3601 | 500222 | Perf. part: Uplink Transmit Diversity for HSPA - Closed Loop | HSPA_UL_TxDiv-CL-Perf | 2 | Rel-11 | R4 | 2010-12-14 08:00 | 2013-09-06 17:00 | 100% | RP-120367 | RP-130477 | Huawei | zongjie.wang@huawei.com | RP#61 completed | 25.101, 25.104, 25.133, 25.141 | 50 | 26 |  |  | Fri 10/12/10 | Fri 30/08/13
3602 | 500322 | Core part: Uplink Transmit Diversity for HSPA - Open Loop | HSPA_UL_TxDiv-OL-Core | 2 | Rel-11 | R4,R1,R2,R3 | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | RP-120367 | RP-121544 | Huawei | zongjie.wang@huawei.com | RP#58 completed | 25.101, 25.133, 25.306, 25.319, 25.321, 25.331, 25.423, 25.433 | 50 | 26 |  |  | Fri 10/12/10 | Wed 28/11/12
3603 | 500422 | Perf. part: Uplink Transmit Diversity for HSPA - Open Loop | HSPA_UL_TxDiv-OL-Perf | 2 | Rel-11 | R4 | 2010-12-14 08:00 | 2012-12-07 17:00 | 100% | RP-120367 | RP-121545 | Huawei | zongjie.wang@huawei.com | RP#58 completed | 25.101, 25.133 | 50 | 26 |  |  | Fri 10/12/10 | Wed 28/11/12
3604 | 590008 | Test part: Uplink Transmit Diversity for HSPA | HSPA_UL_TxDiv-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2014-06-13 17:00 | 100% | RP-130351 | RP-140767 | Qualcomm | Shubhang Vora (svora@qti.qualcomm.com) | RP#64 completed | 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 59 | 30 |  |  | Tue 29/01/13 | Tue 10/06/14
3605 | 510018 | Introduction of New Configuration for 4C-HSDPA | 4C_HSDPA_Config | 1 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2012-06-15 17:00 | 100% | RP-110308 | - | Telus Communications | jorge.delrio@telus.com | - | UTRA | 51 | 26 |  |  | Mon 14/03/11 | Wed 01/06/11
3606 | 510118 | Core part: Introduction of New Configuration for 4C-HSDPA | 4C_HSDPA_Config-Core | 2 | Rel-11 | R4,R2 | 2011-03-22 08:00 | 2011-12-09 17:00 | 100% | RP-110308 | RP-111463 | Telus Communications | jorge.delrio@telus.com | RP#54 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new TS 25.327 | 51 | 26 |  |  | Mon 14/03/11 | Wed 07/12/11
3607 | 510218 | Perf. part: Introduction of New Configuration for 4C-HSDPA | 4C_HSDPA_Config-Perf | 2 | Rel-11 | R4 | 2011-03-24 08:00 | 2012-06-15 17:00 | 100% | RP-110308 | RP-120475 | Telus Communications | jorge.delrio@telus.com | RP#56 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new TS 25.327 | 51 | 26 |  |  | Mon 14/03/11 | Sat 09/06/12
3608 | 510019 | Non-contiguous 4C-HSDPA operation | NC_4C_HSDPA | 1 | Rel-11 | R4,R2,R3 | 2011-03-23 08:00 | 2013-03-01 17:00 | 100% | RP-110416 | - | Ericsson | muhammad.kazmi@ericsson.com | - | UTRA | 51 | 26 |  |  | Mon 14/03/11 | Wed 27/02/13
3609 | 510119 | Core part: Non-contiguous 4C-HSDPA operation | NC_4C_HSDPA-Core | 2 | Rel-11 | R4,R2,R3 | 2011-06-15 08:00 | 2012-09-07 17:00 | 100% | RP-110416 | RP-120842 | Ericsson | muhammad.kazmi@ericsson.com | RP#56 completed | 25.101, 25.104, 25.133, 25.331, 25.423, 25.433 | 51 | 26 |  |  | Mon 14/03/11 | Sat 16/06/12
3610 | 510219 | Perf. part: Non-contiguous 4C-HSDPA operation | NC_4C_HSDPA-Perf | 2 | Rel-11 | R4 | 2011-03-23 08:00 | 2013-03-01 17:00 | 100% | RP-110416 | RP-130049 | Ericsson | muhammad.kazmi@ericsson.com | RP#59 completed | 25.101, 25.104, 25.133, 25.141 | 51 | 26 |  |  | Mon 14/03/11 | Wed 27/02/13
3611 | 510020 | Further Enhancements to CELL_FACH | Cell_FACH_enh | 1 | Rel-11 | R1,R2,R3,R4,R5 | 2011-03-18 08:00 | 2015-03-13 17:00 | 100% | RP-111321 | - | Qualcomm | Ravi Agarwal | - | UTRA | 51 | 26 |  |  | Mon 14/03/11 | Fri 16/09/11
3612 | 510120 | Core part: Further Enhancements to CELL_FACH | Cell_FACH_enh-Core | 2 | Rel-11 | R2,R1,R3,R4 | 2011-03-18 08:00 | 2012-12-07 17:00 | 100% | RP-111321 | RP-121547 | Qualcomm | Ravi Agarwal | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.306, 25.308, 25.319, 25.321, 25.331, 25.423, 25.433 | 51 | 26 |  |  | Mon 14/03/11 | Tue 27/11/12
3613 | 510220 | Perf. part: Further Enhancements to CELL_FACH | Cell_FACH_enh-Perf | 2 | Rel-11 | R4 | 2011-03-24 08:00 | 2013-12-06 17:00 | 100% | RP-111321 | RP-131459 | Qualcomm | Heechoon Lee (heechoon@qti.qualcomm.com) | RP#62 completed | 25.101, 25.104, 25.133, 25.141 | 51 | 26 |  |  | Mon 14/03/11 | Fri 29/11/13
3614 | 600004 | Test part: Further Enhancements to CELL_FACH | Cell_FACH_enh-UEConTest | 2 | Rel-11 | R5 | 2013-06-15 | 2015-03-13 17:00 | 100% | RP-130644 | RP-150132 | Ericsson | leif.mattisson@ericsson.com | ; Stat Rep: RP-141164->RP-141770 1st Apr 15: Compl:92%->100% 1st Apr 15: Stat Rep: RP-141770->RP-150132 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | 60 | 31 |  |  | Wed 22/05/13 | Wed 01/04/15
3615 | 530034 | HSDPA Multiflow Data Transmission | HSDPA_MFTX | 1 | Rel-11 | R2,R1,R3,R4,R5 | 2011-09-19 08:00 | 2015-03-13 17:00 | 100% | RP-111375 | - | Nokia Siemens Networks | Alexander Sayenko | Stage 2,3 | UTRA | 53 | 27 |  |  | Thu 15/09/11 | Thu 15/09/11
3616 | 530134 | Core part: HSDPA Multiflow Data Transmission | HSDPA_MFTX-Core | 2 | Rel-11 | R2,R1,R3,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111375 | RP-121551 | Nokia Siemens Networks | Alexander Sayenko | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.214, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3617 | 530234 | Perf. part: HSDPA Multiflow Data Transmission | HSDPA_MFTX-Perf | 2 | Rel-11 | R4 | 2011-09-20 08:00 | 2013-09-06 17:00 | 100% | RP-111375 | RP-130959 | Nokia Siemens Networks | kamil.bechta@nsn.com | RP#61 completed | 25.101, 25.104, 25.133, 25.141 | 53 | 27 |  |  | Thu 15/09/11 | Thu 29/08/13
3618 | 620016 | Test part: HSDPA Multiflow Data Transmission | HSDPA_MFTX-UEConTest | 2 | Rel-11 | R5 | 2013-12-15 | 2015-03-13 17:00 | 100% | RP-131692 | RP-150126 | Qualcomm | Shubhang Vora (svora@qti.qualcomm.com) | ; Stat Rep: RP-141136->RP-141961 1st Apr 15: Compl:90%->100% 1st Apr 15: Stat Rep: RP-141961->RP-150126 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 62 | 32 |  |  | Mon 25/11/13 | Wed 01/04/15
3619 | 530035 | Four Branch MIMO transmission for HSDPA | 4Tx_HSDPA | 1 | Rel-11 | R1,R2,R3,R4 | 2011-09-19 08:00 | 2013-12-06 17:00 | 100% | RP-111393 | - | Ericsson | johan.hultell@ericsson.com | Stage 3 | UTRA | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3620 | 530135 | Core part: Four Branch MIMO transmission for HSDPA | 4Tx_HSDPA-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-111393 | RP-121549 | Ericsson | johan.hultell@ericsson.com | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306 | 53 | 27 |  |  | Thu 15/09/11 | Tue 27/11/12
3621 | 530235 | Perf. part: Four Branch MIMO transmission for HSDPA | 4Tx_HSDPA-Perf | 2 | Rel-11 | R4 | 2011-09-21 08:00 | 2013-12-06 17:00 | 100% | RP-111393 | RP-131460 | Ericsson | johan.hultell@ericsson.com | RP#62 completed | 25.101, 25.104, 25.133, 25.141 | 53 | 27 |  |  | Thu 15/09/11 | Fri 29/11/13
3622 | 540009 | MIMO with 64QAM for HSUPA | MIMO_64QAM_HSUPA | 1 | Rel-11 | R1,R2,R3,R4 | 2011-12-09 08:00 | 2013-09-06 17:00 | 100% | RP-121794 | - | Nokia Siemens Networks | Karri Ranta-aho | Specified UE and BS performance requirements for uplink MIMO together with QPSK and 16QAM modulations for E-DCH/HSUPA. 64QAM is for future releases | UTRA | 54 | 28 |  |  | Wed 07/12/11 | Wed 27/02/13
3623 | 540109 | Core part: MIMO with 64QAM for HSUPA | MIMO_64QAM_HSUPA-Core | 2 | Rel-11 | R1,R2,R3,R4 | 2011-12-09 08:00 | 2012-12-07 17:00 | 100% | RP-121794 | RP-121554 | Nokia Siemens Networks | Karri Ranta-aho | RP#58 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.321, 25.331, 25.423, 25.433, 26.306 | 54 | 28 |  |  | Wed 07/12/11 | Wed 27/02/13
3624 | 540209 | Perf. part: MIMO with 64QAM for HSUPA | MIMO_64QAM_HSUPA-Perf | 2 | Rel-11 | R4 | 2011-12-13 08:00 | 2013-09-06 17:00 | 100% | RP-121794 | RP-130960 | Nokia Siemens Networks | kamil.bechta@nsn.com | RP#61 completed | 25.101, 25.104, 25.133, 25.141 | 54 | 28 |  |  | Wed 07/12/11 | Thu 29/08/13
3625 | 540024 | HSDPA Dual-Band Multi-Carrier combinations | HSDPA_DB_MC | 1 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-111746 | - | Ericsson | muhammad.kazmi@ericsson.com | Stage 3 | UTRA | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
3626 | 540124 | Core part: HSDPA Dual-Band Multi-Carrier combinations | HSDPA_DB_MC-Core | 2 | Rel-11 | R4,R2 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-111746 | RP-120987 | Ericsson | muhammad.kazmi@ericsson.com | RP#57 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new TS 25.327 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
3627 | 540224 | Perf. part: HSDPA Dual-Band Multi-Carrier combinations | HSDPA_DB_MC-Perf | 2 | Rel-11 | R4 | 2011-12-09 08:00 | 2012-09-07 17:00 | 100% | RP-111746 | RP-120988 | Ericsson | muhammad.kazmi@ericsson.com | RP#57 completed | 25.101, 25.104, 25.141 | 54 | 28 |  |  | Wed 07/12/11 | Tue 04/09/12
3628 | 620015 | Split TTCN Test Models for IMS testing in TS 34.229-3 | IMS-CCR_Test2 | 1 | Rel-11 | R5 | 2013-12-09 08:00 | 2014-09-12 17:00 | 100% | RP-140440 | RP-141155 | Spirent | richard.catmur@spirent.com | SP#65 completed. TS 34.229-4 for Approval. Split out of old TS 34.229-3 a new TS 34.229-4 | 34.229-3, New TS 34.229-4 | 62 | 32 |  |  | Mon 25/11/13 | Tue 09/09/14
3629 | 480004 | (Small) Technical Enhancements and Improvements for Rel-11 | TEI11 | 1 | Rel-11 | SP,CP,RP,GP | 2010-06-18 08:00 | 2012-09-20 17:00 | 100% | - | - | - | - | SP#50 EU-Alert is introduced under Public Warning System in parallel with the already existing ETWS and CMAS. SA1 22.268 CR#9r1 adds EU-ALERT specific requirements & CT1 23.041 CRs# | - | 48 | 25 |  |  | Tue 02/06/09 | Mon 13/12/10
3630 | 560001 | Test - (Small) Technical Enhancements and Improvements for Rel-11 | TEI11_Test | 1 | Rel-11 | R5,G3new | 2012-06-15 08:00 | 2013-12-11 17:00 | 100% | - | - | - | - | - | - | 56 | 29 |  |  | Wed 13/06/12 | Wed 13/06/12
3631 | 571004 | (IETF) (Small) Technical Enhancements and Improvements for Rel-11 (RFC 7077) | TEI11_IETF | 1 | Rel-11 | C4-IETF | 2012-09-07 08:00 | 2013-12-06 17:00 | 100% | - | - | Lionel Morand | Lionel Morand | CP#62 completed | RFC 7077 (was draft-ietf-netext-update-notifications) | 57 | 29 | - |  | Mon 03/09/12 | Thu 28/11/13
3632 | 0 | Release 11 Studies | - | 1 | Rel-11 | SP,CP,GP,RP | 2009-12-10 08:00 | 2009-12-10 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 03/04/12
3633 | 450047 | Study on IMS based Peer-to-Peer Content Distribution Services | FS_IMS_P2P | 1 | Rel-11 | S1,S2 | 2009-09-11 08:00 | 2010-06-10 17:00 | 100% | SP-090491 | - | China Mobile | Li Gang (ligangyf@chinamobile.com) | SP#48 completed. 3/3/15: start date corrected (was 05/09) | 22.906 | 45 | 23 |  |  | Mon 21/09/09 | Tue 03/03/15
3634 | 460024 | Study on Non Voice Emergency Services | FS_NOVES | 1 | Rel-11 | S1 | 2009-12-10 08:00 | 2011-09-21 17:00 | 100% | SP-090897 | - | Qualcomm | dwilliams@qualcomm.com | SP#53 completed. Spin-off Feature UID_500030 Non Voice Emergency Services (NOVES) | 22.871 | 46 | 24 |  |  | Sun 06/12/09 | Wed 24/08/11
3635 | 480033 | Study on Support for 3GPP Voice Interworking with Enterprise IP-PBX | FS_VINE | 1 | Rel-11 | S1,S2 | 2010-09-23 08:00 | 2011-03-23 17:00 | 100% | SP-100411 | - | Tatara Systems | Phillip Brown (pbrown@tatarasystems.com) | SP#51 completed. Support Interworking between 3GPP networks and Enterprise environments to provide enterprise voice services via 3GPP mobile devices | 22.809 | 48 | 25 |  |  | Sun 06/06/10 | Mon 06/06/11
3636 | 490033 | Study on IMS Network-Independent Public User Identities | FS_INIPUI | 1 | Rel-11 | S1 | 2010-09-23 08:00 | 2011-06-08 17:00 | 100% | SP-100652 | - | Vodafone | mona.mustapha@vodafone.com | SP#52 completed | 22.894 | 49 | 25 |  |  | Tue 21/09/10 | Wed 18/05/11
3637 | 410041 | Study on IMS Evolution | FS_eIMS | 1 | Rel-11 | S2 | 2008-09-18 08:00 | 2011-12-14 17:00 | 100% | SP-100360 | - | China Mobile | Li Gang (ligangyf@chinamobile.com), Yu Qing (yuqing@chinamobile.com) | SP#54 completed | 23.812 | 41 | 21 |  |  | Mon 15/09/08 | Mon 28/11/11
3638 | 440047 | Study on Policy solutions and enhancements | FS_PP | 1 | Rel-11 | S2,S1 | 2009-06-12 08:00 | 2011-06-10 17:00 | 100% | SP-090895 | - | AT&T | farooq.bari@att.com | SP#52 completed. 3/3/15: start and finish dates corrected (was start on Jan-00, ends on Jan-02) | 23.813 | 44 | 23 |  |  | Sun 31/05/09 | Tue 03/03/15
3639 | 440048 | Study on IPv6 Migration | FS_IP6M | 1 | Rel-11 | S2 | 2009-06-04 08:00 | 2011-06-08 17:00 | 100% | SP-090362 | - | China Mobile | Li Lianyuan (lilianyuan@chinamobile.com), Liu Hong (liuhongyfw@chinamobile.com) | SP#52 completed | 23.975 | 44 | 23 |  |  | Sun 31/05/09 | Thu 26/05/11
3640 | 460030 | Study on Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | FS_rSRVCC | 1 | Rel-11 | S2 | 2009-12-10 08:00 | 2011-12-14 17:00 | 100% | SP-090806 | - | Orange | delphin.barankanira@orange-ftgroup.com | SP#54 completed. Study on "reverse direction" from UTRAN/GERAN to E-UTRAN/HSPA (Rel-8 SRVCC was in the other direction E-UTRAN/HSPA to GERAN/UTRAN) | 23.885 | 46 | 24 |  |  | Sun 06/12/09 | Sun 04/03/12
3641 | 510044 | Study on Roaming Architecture for Voice over IMS with Local Breakout | FS_RAVEL | 1 | Rel-11 | S2 | 2011-03-23 08:00 | 2011-12-14 17:00 | 100% | SP-110087 | - | Deutsche Telekom | michele.zarri@telekom.com | SP#54 completed. Linked to Rel-11 OSCAR (Optimized Service Charging and Allocation of ResourcES in CP-150IMS whilst Roaming) UID_490032. Related to LBO/home routing decision | 23.850 | 51 | 26 |  |  | Mon 21/02/11 | Mon 28/11/11
3642 | 380084 | Study on UTRAN key management enhancements | FS_UKM | 1 | Rel-11 | S3 | 2007-12-20 08:00 | 2012-03-07 17:00 | 100% | SP-090283 | - | Ericsson | karl.norrman@ericsson.com | SP#55 completed | 33.859 | 38 | 21 |  |  | Thu 20/12/07 | Tue 20/11/12
3643 | 480048 | Study on Single Sign On (SSO) Application Security for IMS - based on SIP Digest | FS_SSO_APS | 1 | Rel-11 | S3 | 2010-06-10 08:00 | 2012-06-20 17:00 | 100% | SP-100639 | - | Nokia | Silke.Holtmanns@nokia.com | SP#56 completed. SP#55 TR 33.914v200 approved (converted 33.804). Study reuse of non-UICC credentials (in particular SIP Digest) to provide security for access to applications. Provide reference material for IMS based non-UICC based SSO to applications | 33.914 converted to 33.804 | 48 | 25 |  |  | Mon 07/06/10 | Wed 13/06/12
3644 | 520036 | Study on Mobile 3D Video Coding | FS_M3DVC | 1 | Rel-11 | S4 | 2011-06-08 08:00 | 2012-06-20 17:00 | 100% | SP-110310 | - | Orange | gilles.teniou@orange-ftgroup.com | SP#56 completed. Extends Rel-10 work on 3D video formats UID_480044 Improved Video Coding Support for PSS and MBMS | 26.905 | 52 | 27 |  |  | Thu 26/05/11 | Mon 20/08/12
3645 | 480047 | Study on Management of Converged Networks | FS_ManCon | 1 | Rel-11 | S5 | 2010-06-10 08:00 | 2012-09-12 17:00 | 100% | SP-100377 | - | Nokia Siemens Networks | Jörg Schmidt (J.Schmidt@nsn.com) | SP#57 completed. TR 32.833v200 for Approval | 32.833 | 48 | 25 |  |  | Wed 26/05/10 | Thu 30/08/12
3646 | 490039 | Study on User Data Convergence (UDC) information model handling and provisioning: Example Use Cases | FS_UDC_AppUseCase | 1 | Rel-11 | S5 | 2010-09-23 08:00 | 2011-12-14 17:00 | 100% | SP-110127 | - | Alcatel-Lucent | Nick Mazzarella (njmazzarella@alcatel-lucent.com) | SP#54 completed | 32.901 | 49 | 25 |  |  | Fri 03/09/10 | Mon 02/04/12
3647 | 510045 | Study on OAM aspects of inter-RAT Energy Saving | FS_OAM_ES_iRAT | 1 | Rel-11 | S5 | 2011-03-23 08:00 | 2011-12-14 17:00 | 100% | SP-110138 | - | Nokia Siemens Networks | clemens.suerbaum@nsn.com | SP#54 completed. Triggered by Rel-10 UID_430044 TR 32.826 Study on Energy Savings Management (FS_OAM_ESM) and UID_470037 OAM aspects of Energy Saving in Radio Networks (OAM-ES) | 32.834 | 51 | 26 |  |  | Wed 09/03/11 | Mon 02/04/12
3648 | 480015 | Study on impacts on UE-Core Network signalling from Energy Saving | FS_UE-CN_ES | 1 | Rel-11 | C1 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-100330 | - | NEC | gottfried.punz@nw.neclab.eu | CP#52 completed. Linked to SA5 UID_430044 (FS_OAM-ESM) & UID_470037 (OAM-ES), RAN3 UID_470015 (FS_Energy_LTE), RAN1 UID_460016 (FS_Energy_UMTS) | 24.826 | 48 | 25 |  |  | Sat 29/05/10 | Mon 23/05/11
3649 | 490014 | Study on EPC Nodes Restoration | FS_EPC_NR | 1 | Rel-11 | C4 | 2010-09-17 08:00 | 2012-12-07 17:00 | 100% | CP-100700 | - | ZTE | lu.fei1@zte.com.cn | CP#58 completed. Continue work in Rel-11 especially to cover handling of Idle mode Signalling Reduction (ISR). Linked to SA2 UID_490036 Study on Core Network Overload solutions | 23.857 | 49 | 25 |  |  | Wed 01/09/10 | Wed 14/11/12
3650 | 480003 | Study on Signal Precoding enhancements for EGPRS2 DL | FS_SPEED | 1 | Rel-11 | G1,G2 | 2010-09-03 08:00 | 2012-03-02 17:00 | 100% | GP-111281 | - | Ericsson | marten.sundberg@ericsson.com | GP#53 completed (03/12). GP#46 approved WID. | GERAN 45.860 | 46 | 25 |  |  | Thu 27/05/10 | Fri 02/03/12
3651 | 470014 | Study on Coordinated Multi-Point operation for LTE | FS_CoMP_LTE | 1 | Rel-11 | R1,R2,R3 | 2010-12-10 08:00 | 2011-09-16 17:00 | 100% | RP-101425 | RP-111343 | Samsung | bruno.clerckx@samsung.com | RP#53 completed | LTE 36.819 | 47 | 24 |  |  | Fri 19/03/10 | Fri 27/05/11
3652 | 480028 | Study on Signalling and procedure for interference avoidance for in-device coexistence | FS_SPIA_IDC | 1 | Rel-11 | R2,R4 | 2010-06-04 08:00 | 2011-09-16 17:00 | 100% | RP-100671 | RP-111057 | China Mobile | Zhenping Hu (huzhenping@chinamobile.com) | RP#53 completed. Studied coexistence scenario of LTE and Industrial, Scientific and Medical (ISM) Radio within the same device working in adjacent frequencies | LTE 36.816 | 48 | 25 |  |  | Tue 01/06/10 | Mon 12/09/11
3653 | 510034 | Study on HetNet mobility enhancements for LTE | FS_HetNet_eMOB_LTE | 1 | Rel-11 | R2,R1,R3,R4 | 2011-03-18 08:00 | 2012-09-07 17:00 | 100% | RP-110709 | RP-121085 | Alcatel-Lucent | sudeep.palat@alcatel-lucent.com | RP#57 completed. TR 36.839 v100 for Information & Approval | LTE 36.839 | 51 | 26 |  |  | Mon 21/03/11 | Mon 03/09/12
3654 | 510037 | Study on further Downlink MIMO enhancements for LTE-Advanced | FS_LTE_eDL_MIMO_enh | 1 | Rel-11 | R1 | 2011-03-18 08:00 | 2011-12-09 17:00 | 100% | RP-111366 | RP-111550 | Alcatel-Lucent | federico.boccardi@alcatel-lucent.com | RP#54 completed | LTE 36.871 | 51 | 26 |  |  | Mon 21/03/11 | Thu 08/12/11
3655 | 510039 | Study on Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | FS_LTE_TDD_eIMTA | 1 | Rel-11 | R1,R4 | 2011-03-22 08:00 | 2012-06-15 17:00 | 100% | RP-110450 | RP-120587 | CATT | Zukang Shen (shenzukang@catt.cn) | RP#56 completed. TR 36.828 for Information and Approval | LTE 36.828 | 51 | 26 |  |  | Mon 21/03/11 | Sat 09/06/12
3656 | 530053 | Study on LTE Coverage Enhancements | FS_Cov_Enh_LTE | 1 | Rel-11 | R1,R2 | 2011-09-19 08:00 | 2012-06-15 17:00 | 100% | RP-120225 | RP-120589 | China Telecom | Peng Chen (chenpeng@ctbri.com.cn) | RP#56 completed. TR 36.824 v200 for Approval | LTE 36.824 | 53 | 27 |  |  | Mon 19/09/11 | Sat 09/06/12
3657 | 530055 | Study on Enhanced performance requirement for LTE UE | FS_enh_perf_UE_LTE | 1 | Rel-11 | R4,R1 | 2011-09-19 08:00 | 2012-03-02 17:00 | 100% | RP-111378 | RP-120167 | NTT DoCoMo | Yuta Sagae | RP#55 completed. TR 36.829 v100 for Information + Approval | LTE 36.829 | 53 | 27 |  |  | Mon 19/09/11 | Mon 27/02/12
3658 | 550022 | Study on Measurements of radio performances for LTE terminals - Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) test methodology | FS_LTE_OTA | 1 | Rel-11 | R4 | 2012-03-05 08:00 | 2012-09-07 17:00 | 100% | RP-120412 | RP-121083 | CATR | Xudong An (anxudong@emcite.com) | RP#57 completed | LTE 25.914, New TR 37.902 | 55 | 28 |  |  | Thu 23/02/12 | Mon 03/09/12
3659 | 430020 | Study on Measurement of Radiated Performance for MIMO and multi-antenna reception for HSPA and LTE terminals | FS_HSPA_LTE_measRP_MIMO_multi-antenna | 1 | Rel-11 | R4 | 2009-03-06 08:00 | 2012-03-02 17:00 | 100% | RP-111754 | RP-120154 | Vodafone | Tim.frost@vodafone.com | RP#55 completed. TR 37.976 v200 for Approval | UTRA, LTE 37.976 | 43 | 22 |  |  | Fri 06/03/09 | Thu 23/02/12
3660 | 440016 | Study on Extending 850 MHz | FS_e850 | 1 | Rel-11 | R4 | 2009-05-30 08:00 | 2012-09-07 17:00 | 100% | RP-090666 | RP-121080 | Ericsson | christian.bergljung@ericsson.com | RP#57 completed. TR 37.806 v200 for Approval | UTRA, LTE 37.806 | 44 | 23 |  |  | Tue 26/05/09 | Tue 04/09/12
3661 | 450015 | Study on RAN improvements for Machine-Type Communications | FS_NIMTC_RAN | 1 | Rel-11 | R2,R1,R3,R4 | 2009-09-18 08:00 | 2011-09-16 17:00 | 100% | RP-100330 | RP-111052 | Huawei | Jeff Gao (gaoyq@huawei.com) | RP#53 completed. TR 37.868v100 for Approval (No WID change: RAN overload only). Triggered by TR 22.868 Study on Facilitating Machine to Machine Communication in GSM and UMTS (M2M) UID_7027 and Rel-10 NIMTC UID_410030 | UTRA, LTE 37.868 | 45 | 23 |  |  | Tue 15/09/09 | Tue 06/09/11
3662 | 500002 | Study on UE Application Layer Data Throughput Performance | FS_UE_App_Data_Perf | 1 | Rel-11 | R5,R4 | 2010-09-16 08:00 | 2011-09-16 17:00 | 100% | RP-101422 | RP-111543 | Spirent | ron.borsato@spirent.com | RP#54 completed | UTRA, LTE 37.901 | 50 | 26 |  |  | Wed 08/12/10 | Tue 29/11/11
3663 | 510036 | Study on further enhancements for HNB and HeNB | FS_EHNB_enh | 1 | Rel-11 | R3,R2 | 2011-03-18 08:00 | 2012-06-15 17:00 | 100% | RP-120373 | RP-120579 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#56 completed. TR 37.803 v200 for Approval | UTRA, LTE 37.803 | 51 | 26 |  |  | Mon 21/03/11 | Sat 09/06/12
3664 | 510038 | Study on Interference analysis between 800~900 MHz bands | FS_B800_B900_Interf_LTE | 1 | Rel-11 | R4 | 2011-03-23 08:00 | 2012-06-15 17:00 | 100% | RP-111752 | RP-120586 | LG Uplus | Koo Yeon Sang (yskoo@lguplus.co.kr) | RP#56 completed. Impacts TR 37.804 Study on UMTS/LTE in 900 MHz band (Japan, Korea) UID_520018 | UTRA, LTE impacts TR 37.804 | 51 | 26 |  |  | Mon 21/03/11 | Wed 06/06/12
3665 | 520018 | Study on UMTS/LTE in 900 MHz band (Japan, Korea) | FS_UTRA_LTE_900MHz | 1 | Rel-11 | R4 | 2011-06-07 08:00 | 2012-06-15 17:00 | 100% | RP-120617 | RP-120580 | NTT DoCoMo | Masahiro Fujii (fujiima@nttdocomo.co.jp) | RP#56 completed. Updated WID RP-111751=>RP-120617. TR 37.804 v100 for Information and Approval. Linked to Study on Interference analysis between 800~900 MHz bands UID_510038 | UTRA, LTE 37.804 | 52 | 27 |  |  | Fri 27/05/11 | Wed 06/06/12
3666 | 500014 | Study on Uplink MIMO | FS_UTRA_UL_MIMO | 1 | Rel-11 | R1 | 2010-12-10 08:00 | 2011-09-16 17:00 | 100% | RP-101432 | RP-111048 | Qualcomm | Sharad Sambhwani | RP#53 completed (1-step Approval) | UTRA 25.871 | 50 | 26 |  |  | Wed 08/12/10 | Fri 02/09/11
3667 | 500015 | Study on HSDPA Multipoint Transmission | FS_HSDPA_MP_TX | 1 | Rel-11 | R1,R2,R3 | 2010-12-10 08:00 | 2011-09-16 17:00 | 100% | RP-101439 | RP-111049 | Nokia Siemens Networks | karri.ranta-aho@nsn.com | RP#53 completed | UTRA 25.872 | 50 | 26 |  |  | Wed 08/12/10 | Fri 09/09/11
3668 | 530057 | Study on UE Over The Air (OTA) test method with Head and Hand Phantoms | FS_OTA_phantoms_UTRA | 1 | Rel-11 | R4,R5 | 2011-09-19 08:00 | 2012-09-07 17:00 | 100% | RP-120208 | RP-121078 | Nokia | petri.j.vasenkari@nokia.com | RP#57 completed | UTRA 25.914 | 53 | 27 |  |  | Mon 19/09/11 | Thu 06/09/12
3669 | 540026 | Study on HSPA feedback and signalling efficiency enhancements for LCR TDD | FS_LCRTDD_HSPAenh | 1 | Rel-11 | R1 | 2011-12-07 08:00 | 2012-09-07 17:00 | 100% | RP-111766 | RP-121079 | TD Tech | limei.wei@td-tech.com | RP#57 completed. TR 25.874 v100 for Information & Approval | UTRA 25.874 | 54 | 28 |  |  | Wed 07/12/11 | Sat 09/06/12
3670 | 510035 | Deleted - Study on Enhanced Uplink Transmission for LTE | FS_eUL_TX_LTE | 1 | Rel-11 | R1 | 2011-03-22 08:00 | 2012-06-15 17:00 | 100% | RP-120259 | RP-120585 | Huawei | Yongxing Zhou | RP#56 stopped. RP-120856 discussion: most content moved to Rel-11 Coordinated Multi-Point Operation for LTE – Uplink (COMP_LTE_UL) and RAN1 has no time to look at it | LTE 36.8xy | 51 | 26 | RP-56 | PCG-29 | Mon 21/03/11 | Mon 18/06/12
3671 | 0 | Release 10 Features | - | 1 | Rel-10 | CP,GP,RP,SP | 2008-12-11 08:00 | 2011-09-21 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/05/06 | Tue 09/02/10
3672 | 390073 | Enhancements for Multimedia Priority Service | eMPS | 1 | Rel-10 | S1,S2,C4,C3,C1 | 2006-03-13 08:00 | 2011-03-18 17:00 | 100% | SP-080051 | - | Telcordia | jgarraha@telcordia.com | CP#51 completed. SP#49 moved Stage 1 from Rel-9 & Completed Stage 2. SP#40 Stage 1 completed. Continuation of Rel-8 Feature PRIOR (UID_340044) | - | 39 | 21 |  |  | Fri 28/03/03 | Tue 01/03/11
3673 | 390074 | Stage 1 on enhancements for Multimedia Priority Service | ePRIOR-St1 | 2 | Rel-10 | S1 | 2006-03-13 08:00 | 2008-06-05 17:00 | 100% | SP-080051 | - | Telcordia | jgarraha@telcordia.com | 22/01: acronym modified | 22.153, 22.278 | 39 | 21 |  |  | Fri 28/03/03 | Thu 22/01/15
3674 | 460029 | Stage 2 on enhancements for Multimedia Priority Service | ePRIOR-St2 | 2 | Rel-10 | S2 | 2009-12-10 08:00 | 2010-09-23 17:00 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | 22/01: acronym modified | - | 46 | 24 |  |  | Sun 06/12/09 | Thu 22/01/15
3675 | 460329 | Stage 2 on eMPS for CSFB | ePRIOR-St2 | 3 | Rel-10 | S2 | 2009-12-10 08:00 | 2010-09-23 17:00 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | 22/01: acronym modified | 23.002, 23.203, 23.221, 23.228, 23.272, 23.401 | 46 | 24 |  |  | Sun 06/12/09 | Thu 22/01/15
3676 | 460429 | Stage 2 on eMPS for EPS Bearer Service | ePRIOR-St2 | 3 | Rel-10 | S2 | 2009-12-10 08:00 | 2010-09-23 17:00 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | 22/01: acronym modified | 23.002, 23.203, 23.221, 23.228, 23.272, 23.401 | 46 | 24 |  |  | Sun 06/12/09 | Thu 22/01/15
3677 | 460529 | Stage 2 on eMPS for IMS Aspects | ePRIOR-St2 | 3 | Rel-10 | S2 | 2009-12-10 08:00 | 2010-09-23 17:00 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | 22/01: acronym modified | 23.002, 23.203, 23.221, 23.228, 23.272, 23.401 | 46 | 24 |  |  | Sun 06/12/09 | Thu 22/01/15
3678 | 460229 | Deleted - TR 23.854 on Stage 2 on enhancements for Multimedia Priority Service | - | 2 | Rel-10 | S2 | 2009-12-10 08:00 | 2010-12-16 17:00 | 100% | SP-100647 | - | Telcordia, NTT DoCoMo | Vijay Varma, Katsutoshi Nishida | SP#49 TR 23.854 v100 for Information. SP#50 moved to Rel-11 SRVCC aspect of enhancements for Multimedia Priority Service UID_480135 (place holder for solution alternatives and agreed functions to be reflected in affected existing TS) | new TR 23.854 | 46 | 24 | SP-50 | PCG-27 | Sun 06/12/09 | Tue 30/11/10
3679 | 490008 | Stage 3 on enhancements for Multimedia Priority Service | eMPS-CN | 2 | Rel-10 | C4,C3,C1 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | Stage 3 | 49 | 25 |  |  | Wed 01/09/10 | Thu 09/12/10
3680 | 490108 | CT4 part on Stage 3 on enhancements for Multimedia Priority Service | eMPS-CN | 3 | Rel-10 | C4 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | 23.008, 29.002, 29.228, 29.229, 29.272, 29.274, 29.277, 29.328, 29.329 | 49 | 25 |  |  | Wed 01/09/10 | Mon 28/02/11
3681 | 490208 | CT3 part on Stage 3 on enhancements for Multimedia Priority Service | eMPS-CN | 3 | Rel-10 | C3 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | 29.212, 29.213, 29.214 | 49 | 25 |  |  | Wed 01/09/10 | Tue 01/03/11
3682 | 490308 | CT1 part on Stage 3 on enhancements for Multimedia Priority Service | eMPS-CN | 3 | Rel-10 | C1 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100878 | - | Ericsson | Philip.hodges@ericsson.com | CP#51 completed | 24.008, 24.229, 24.301 | 49 | 25 |  |  | Wed 01/09/10 | Mon 28/02/11
3683 | 410030 | Network Improvements for Machine-Type Communications | NIMTC | 1 | Rel-10 | S1,S2,S5,C1,C4,C6,G2,R2,R3,R5,G3new | 2008-09-18 08:00 | 2013-11-22 17:00 | 100% | SP-100863 | - | KPN | toon.norp@tno.nl | Triggered by Rel-8 UID_7027 Study on Facilitating Machine to Machine Communication in GSM and UMTS (FS_M2M) TR 22.868 | - | 41 | 21 |  |  | Mon 15/09/08 | Mon 28/02/11
3684 | 410031 | Stage 1 for Network Improvements for Machine-Type Communications | NIMTC | 2 | Rel-10 | S1 | 2008-09-18 08:00 | 2010-03-25 17:00 | 100% | SP-100863 | - | KPN | toon.norp@tno.nl | SP#47 completed | 22.011, New 22.368 | 41 | 21 |  |  | Mon 15/09/08 | Tue 09/03/10
3685 | 450028 | Deleted - TR on Stage 2 for Network Improvements for Machine-Type Communications | NIMTC | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-12-16 17:00 | 100% | SP-100863 | - | Samsung | erik.guttman@partner.samsung.com | SP#50 updated WID SP-090832=>SP-100863 (TR 23.888 not submitted for approval to conclude Rel-10 NIMTC as it will continue to serve as basis for Rel-11 SIMTC work item) | New TR 23.888 | 45 | 23 | SP-50 | PCG-26 | Mon 21/09/09 | Wed 01/12/10
3686 | 490037 | Stage 2 for Network Improvements for Machine-Type Communications | NIMTC | 2 | Rel-10 | S2 | 2010-08-30 08:00 | 2010-09-23 17:00 | 100% | SP-100863 | - | Samsung | erik.guttman@partner.samsung.com | SP#49 completed | 23.060, 23.236, 23.401 | 45 | 23 |  |  | Mon 21/09/09 | Mon 13/12/10
3687 | 460023 | Deleted - Security for Network Improvements for Machine-Type Communications | NIMTC | 2 | Rel-10 | S3 | 2009-12-10 08:00 | 2010-09-23 17:00 | 100% | SP-100863 | - | Samsung | Rajavelsamy R (rajvel@samsung.com) | SP#49 stopped (activity transferred to Rel-11 Feature SIMTC under UID_490028 "TR on Security aspects of Machine-Type Communications". | New TR 33.868 | 46 | 24 | SP-49 | PCG-25 | Mon 21/09/09 | Mon 27/09/10
3688 | 510040 | Charging for Network Improvements for Machine-Type Communication | NIMTC-CH | 2 | Rel-10 | S5 | 2011-03-21 08:00 | 2011-03-23 17:00 | 100% | SP-110136 | - | Ericsson | patrik.teppo@@ericsson.com | SP#51 completed | 32.251, 32.298, 32.299 | 51 | 26 |  |  | Tue 22/02/11 | Tue 22/03/11
3689 | 480005 | CN part of Stage 3 for Network Improvements for Machine-Type Communications | NIMTC-CN | 2 | Rel-10 | C1,C4,C6 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 completed | Stage 3 | 48 | 25 |  |  | Wed 26/05/10 | Wed 01/06/11
3690 | 480105 | CT1 part of Stage 3 for Network Improvements for Machine-Type Communications | NIMTC-CN | 3 | Rel-10 | C1 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 completed | 23.122, 24.008, 24.301, New 24.368 | 48 | 25 |  |  | Wed 26/05/10 | Wed 01/06/11
3691 | 480205 | Deleted - CT3 part of Stage 3 for Network Improvements for Machine-Type Communications | NIMTC-CN | 3 | Rel-10 | C3 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 stopped (SA2 decided to move impact from CT3 to CT4). Updated WID CP-110147=>CP-110442 (no CT3 impact) | 29.212, 29.213, 29.215 | 48 | 25 | CP-52 | PCG-27 | Wed 26/05/10 | Wed 01/06/11
3692 | 480305 | CT4 part of Stage 3 for Network Improvements for Machine-Type Communications | NIMTC-CN | 3 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110442 | - | Ericsson | mikael.wass@ericsson.com | CP#52 completed | 23.003, 23.008, 29.002, 29.060, 29.230, 29.272, 29.274, 29.275, 29.282 | 48 | 25 |  |  | Wed 26/05/10 | Wed 01/06/11
3693 | 510005 | CT6 part of Stage 3 for Network Improvements for Machine-Type Communications | NIMTC-CN | 3 | Rel-10 | C6 | 2011-03-18 08:00 | 2011-06-03 17:00 | 100% | - | - | Sagem-Orga | heiko.kruse@sagem-orga.com | CP#52 completed | 31.102 | 51 | 26 |  |  | Thu 10/03/11 | Wed 18/05/11
3694 | 490003 | GERAN part of Network Improvements for Machine-Type Communications (Stage 3) | NIMTC | 2 | Rel-10 | G2 | 2010-09-03 08:00 | 2011-09-02 17:00 | 100% | GP-101647 | - | Vodafone, Ericsson | leo.patanapongpibul@vodafone.com, john.diachina@ericsson.com | GP#51 completed. GP#47 approved WID | 44.018, 44.060 | 47 | 25 |  |  | Sun 05/09/10 | Mon 05/09/11
3695 | 570003 | MS Conformance Test Aspects for GERAN - Network Improvements for Machine-Type Communications | NIMTC_GERAN-MSTest | 2 | Rel-10 | G3new | 2012-08-27 08:00 | 2013-11-22 17:00 | 100% | GP-121141 | - | ST-Ericsson | hakan.e.grunditz@stericsson.com | GP#60 completed. GP#55 approved WID. Testing for CT1 part of Stage 3 for NIMTC UID_480105, GERAN part of NIMTC (Stage 3) UID_490003 | 51.010-1, 51.010-2 | 55 | 29 |  |  | Thu 23/08/12 | Fri 22/11/13
3696 | 490024 | RAN mechanisms to avoid CN overload due to Machine-Type Communications | NIMTC-RAN_overload | 2 | Rel-10 | R2,R3 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | RP-101026 | RP-110063 | Huawei | Jeff Gao (gaoyq@huawei.com) | RP#51 completed | UTRA, LTE 25.331, 25.413, 36.331, 36.413 | 49 | 25 |  |  | Mon 20/09/10 | Mon 14/03/11
3697 | 570004 | UE Conformance Test Aspects - Network Improvements for Machine-Type Communications | NIMTC-UEConTest | 2 | Rel-10 | R5 | 2012-09-11 08:00 | 2013-06-14 17:00 | 100% | RP-121124 | RP-130465 | Ericsson | calle.hagenfeldt@ericsson.com | RP#60 completed. Testing for CT1 part of Stage 3 UID_480105, RAN mechanisms to avoid CN overload due to MTC UID_490024 | 34.123-1, 34.123-2, 34.123-3, 36.523-1, 36.523-2, 36.523-3 | 57 | 29 |  |  | Wed 05/09/12 | Mon 03/06/13
3698 | 430035 | Multi Access PDN Connectivity | MAPCON | 1 | Rel-10 | S2,C4,C1,C3 | 2009-03-13 08:00 | 2011-03-18 17:00 | 100% | SP-090659 | - | Telecom Italia | ivano.guardini@telecomitalia.it | CP#51 completed. SP#49 Stage 2 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control) | - | 43 | 22 |  |  | Thu 05/03/09 | Tue 08/02/11
3699 | 430135 | Stage 2 for Multi Access PDN Connectivity | MAPCON | 2 | Rel-10 | S2 | 2009-03-13 08:00 | 2010-09-23 17:00 | 100% | SP-090659 | - | Telecom Italia | ivano.guardini@telecomitalia.it | SP#49 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control) | 23.237, 23.401, 23.402 | 43 |  |  |  | Mon 25/10/10 | Mon 25/10/10
3700 | 500004 | CT aspects of Multi Access PDN Connectivity | MAPCON-St3 | 2 | Rel-10 | C4,C1,C3 | 2010-11-15 08:00 | 2011-03-18 17:00 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#51 completed | - | 50 | 26 |  |  | Mon 25/10/10 | Thu 09/12/10
3701 | 500104 | CT4 aspects of Multi Access PDN Connectivity | MAPCON-St3 | 3 | Rel-10 | C4 | 2010-11-15 08:00 | 2010-12-10 17:00 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#50 completed | 29.273, 29.272, 29.002, 23.008 | 50 | 26 |  |  | Mon 25/10/10 | Thu 09/12/10
3702 | 500204 | CT1 aspects of Multi Access PDN Connectivity | MAPCON-St3 | 3 | Rel-10 | C1 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#51 completed | 24.302, 24.312 | 50 | 26 |  |  | Mon 25/10/10 | Mon 28/02/11
3703 | 500304 | CT3 aspects of Multi Access PDN Connectivity | MAPCON-St3 | 3 | Rel-10 | C3 | 2010-11-15 08:00 | 2011-03-18 17:00 | 100% | CP-100709 | - | ZTE | Xingyue (Joy) Zhou (zhou.xingyue@zte.com.cn) | CP#51 completed | 29.215 | 50 | 26 |  |  | Mon 25/10/10 | Tue 01/03/11
3704 | 440052 | IMS Service Continuity – Inter Device Transfer enhancements | IMS_SC_eIDT | 1 | Rel-10 | S1,S2,C1,IETF | 2009-06-04 08:00 | 2012-12-07 17:00 | 100% | SP-090452 | - | Huawei | Amar Deol (adeol@huawei.com) | CP#51 completed. SP#47 Stage 1 completed. Rel-9 set Inter-Device Transfer requirements UID_410033 (IMS_SCC-IDT). Adds IDT scenarios and requirements | - | 44 | 23 |  |  | Mon 25/05/09 | Tue 09/03/10
3705 | 440152 | Stage 1 - IMS Service Continuity – Inter Device Transfer enhancements | IMS_SC_eIDT | 2 | Rel-10 | S1 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090452 | - | Huawei | Amar Deol (adeol@huawei.com) | SP#47 completed | 22.228 | 44 | 23 |  |  | Mon 25/05/09 | Tue 09/03/10
3706 | 450029 | Stage 2 - IMS Inter-UE Transfer enhancements | IMS_SC_eIDT | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-100167 | - | Huawei | Lee Valerius (lvalerius@huawei.com) | SP#49 completed | 23.237, 23.292, new 23.831 | 45 | 23 |  |  | Mon 21/09/09 | Mon 06/09/10
3707 | 470001 | Stage 3 - IMS Inter-UE Transfer enhancements | IMS_SC_eIDT | 2 | Rel-10 | C1 | 2010-03-19 08:00 | 2011-03-18 17:00 | 100% | CP-110285 | - | Huawei | georg.mayer@huawei.com | CP#51 completed. WID updated CP-100334=>CP-110285 | 24.216, 24.229, 24.237, new (24.837, 24.337) | 47 | 24 |  |  | Wed 17/03/10 | Thu 17/03/11
3708 | 521001 | (IETF) Stage 3 - IMS Inter-UE Transfer enhancements | IMS_SC_eIDT | 2 | Rel-10 | C1-IETF | 2010-03-19 08:00 | 2012-12-07 17:00 | 100% | CP-110285 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#58 completed | RFC 6809 (was draft-ietf-sipcore-proxy-feature) | 52 | 27 |  |  | Mon 20/06/11 | Tue 04/12/12
3709 | 450030 | IP-Short-Message-Gateway enhancements for CPM-SMS Interworking | CPM-SMS | 1 | Rel-10 | S1,S2,C3 | 2009-09-24 08:00 | 2010-09-17 17:00 | 100% | SP-090615 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | CP#49 completed. SP#47 Stage 1 completed. IP-SM-GW enhancements for interworking with OMA CPM | - | 45 | 23 |  |  | Tue 08/09/09 | Tue 09/03/10
3710 | 450031 | Stage 1 for CPM-SMS | CPM-SMS | 2 | Rel-10 | S1 | 2009-09-24 08:00 | 2010-03-25 17:00 | 100% | SP-090615 | - | China Mobile | Qing Huang | SP#47 completed. External requirements (Stage 1 in OMA-RD-CPM-V1_0-20090310-C) | 22.340 | 45 | 23 |  |  | Tue 08/09/09 | Tue 09/03/10
3711 | 450032 | Stage 2 for CPM-SMS | CPM-SMS | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-03-25 17:00 | 100% | SP-090615 | - | Orange | antoine.mouquet@orange-ftgroup.com | SP#47 completed | 23.204, new TR 23.824 | 45 | 23 |  |  | Tue 08/09/09 | Fri 26/02/10
3712 | 460017 | Stage 3 for IP-Short-Message-Gateway enhancements for CPM-SMS Interworking | CPM-SMS | 2 | Rel-10 | C3 | 2009-12-04 08:00 | 2010-09-17 17:00 | 100% | CP-090859 | - | Ericsson | Jan Holm | CP#49 completed. Linked to Rel-8 UID_340031 Service-Level Interworking for Messaging Services (MESSIW) 23.204 | 29.311 | 46 | 24 |  |  | Mon 30/11/09 | Wed 01/09/10
3713 | 450033 | Completion of Communications on Not Logged-in | CCNL | 1 | Rel-10 | S1,C1,C3 | 2009-09-24 08:00 | 2011-03-18 17:00 | 100% | SP-090493 | - | Deutsche Telekom | Kurt Bischinger | CP#51 completed. SP#45 Stage 1 completed | - | 45 | 23 |  |  | Tue 08/09/09 | Tue 08/09/09
3714 | 450034 | Stage 1 for Completion of Communications on Not Logged-in | CCNL | 2 | Rel-10 | S1 | 2009-09-24 08:00 | 2009-09-24 17:00 | 100% | SP-090493 | - | Deutsche Telekom | Kurt Bischinger | SP#45 completed | 22.173 CR#0056r1 | 45 | 23 |  |  | Tue 08/09/09 | Fri 01/10/10
3715 | 470002 | CT1 part of Stage 3 for Completion of Communications on Not Logged-in | CCNL | 2 | Rel-10 | C1 | 2010-03-19 08:00 | 2011-03-18 17:00 | 100% | CP-100335 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#51 completed | 24.173, 24.642 | 47 | 24 |  |  | Wed 17/03/10 | Mon 14/02/11
3716 | 480006 | CT3 part of Stage 3 for Completion of Communications on Not Logged-in | CCNL | 2 | Rel-10 | C3 | 2010-06-04 08:00 | 2010-09-17 17:00 | 100% | CP-100335 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#49 completed | 29.165 | 48 | 25 |  |  | Wed 26/05/10 | Wed 01/09/10
3717 | 450035 | Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 1 | Rel-10 | S2,S1,S3,S5,C4,C1 | 2009-09-24 08:00 | 2011-03-23 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | TSG#51 completed. Updated WID SP-100696=>SP-110131. SP#49 Stage 2 & Security completed. UID_400035 Enhanced Home NodeB/eNodeB (EHNB) formerly covered Local IP Access to Internet and Local access to Home Network from the Home NodeB/eNodeB | - | 45 | 23 |  |  | Tue 08/09/09 | Mon 13/12/10
3718 | 450037 | Stage 1 for Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 2 | Rel-10 | S1 | 2009-09-24 08:00 | 2010-03-25 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | Amar Deol (adeolf@huawei.com), Gang Li (ligangyf@chinamobile.com) | SP#47 completed | 22.101, 22.220 | 45 | 23 |  |  | Tue 08/09/09 | Tue 09/03/10
3719 | 450036 | TR on Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2011-03-18 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | SP#51 completed. TR 23.829 for Approval | New TR 23.829 | 45 | 23 |  |  | Tue 08/09/09 | Wed 01/12/10
3720 | 450039 | Security for Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 2 | Rel-10 | S3 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-110131 | - | Huawei, Qualcomm | Marcus Wong (mwong@huawei.com), Brian Rosenberg (bmr@qualcomm.com) | SP#49 completed | 33.102, 33.107, 33.108, 33.320, 33.401 | 45 | 23 |  |  | Tue 08/09/09 | Fri 23/07/10
3721 | 450040 | OAM&P for Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 2 | Rel-10 | S5 | 2009-09-24 08:00 | 2011-03-23 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | Zou Lan (zlan@huawei.com), Chen Gang (chengang@chinamobile.com) | SP#51 completed. Updated WID SP-100696=>SP-110131 | 32.581, 32.582, 32.584, 32.591, 32.592, 32.642, 32.646, 32.772, 32.782 | 45 | 23 |  |  | Tue 08/09/09 | Thu 17/03/11
3722 | 460039 | Charging for Local IP Access and Selected Internet IP Traffic Offload | LIPA_SIPTO | 2 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-03-23 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | shan.mingjun@huawei.com, Ai Chen (chenai@chinamobile.com) | SP#51 completed. Updated WID SP-100696=>SP-110131 | 32.251 | 46 | 24 |  |  | Tue 08/09/09 | Thu 17/03/11
3723 | 450238 | Stage 2/3 for Local IP Access | LIPA | 2 | Rel-10 | S2,C4,C1 | 2009-09-24 08:00 | 2011-03-18 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | - | - | 45 | 23 |  |  | Tue 08/09/09 | Mon 06/09/10
3724 | 450338 | Stage 2 for Local IP Access | LIPA | 3 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | SP#49 completed (has impacts to RAN) | 23.060, 23.401 | 45 | 23 |  |  | Tue 08/09/09 | Mon 06/09/10
3725 | 480008 | Stage 3 for Local IP Access | LIPA | 3 | Rel-10 | C4,C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100292 | - | China Mobile | Zhang Hao (zhanghao@chinamobile.com) | CP#51 completed | - | 48 | 25 |  |  | Wed 26/05/10 | Wed 26/05/10
3726 | 480108 | CT4 part of Stage 3 for Local IP Access | LIPA | 4 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100292 | - | China Mobile | Zhang Hao (zhanghao@chinamobile.com) | CP#51 completed | 23.008, 23.015, 29.002, 29.060, 29.272, 29.274, 29.281, 29.303 | 48 | 25 |  |  | Wed 26/05/10 | Tue 30/11/10
3727 | 480208 | CT1 part of Stage 3 for Local IP Access | LIPA | 4 | Rel-10 | C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100292 | - | China Mobile | Zhang Hao (zhanghao@chinamobile.com) | CP#51 completed | 24.008, 24.301 | 48 | 25 |  |  | Wed 26/05/10 | Mon 28/02/11
3728 | 450038 | Stage 2/3 for SIPTO for macro networks | SIPTO | 2 | Rel-10 | S2,C4,C1 | 2009-09-24 08:00 | 2011-03-18 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | - | - | 45 | 23 |  |  | Tue 08/09/09 | Wed 01/12/10
3729 | 450138 | Stage 2 for SIPTO for macro networks | SIPTO | 3 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-110131 | - | Huawei, China Mobile | patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com) | SP#49 completed (SIPTO GW selection for wild card APN and for GERAN. Serving-GW selection for SIPTO. Corrections and Clarifications of the SIPTO procedure) | 23.060, 23.401 | 45 | 23 |  |  | Tue 08/09/09 | Wed 01/12/10
3730 | 480007 | Stage 3 for SIPTO for macro networks | SIPTO | 3 | Rel-10 | C4,C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-110091 | - | Huawei | Caixia Qi (qcxmay@huawei.com) | CP#51 completed. Updated WID CP-100419=>CP-110091 | - | 48 | 25 |  |  | Wed 26/05/10 | Tue 08/03/11
3731 | 480107 | CT4 part of Stage 3 for SIPTO for macro networks | SIPTO | 4 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-110091 | - | Huawei | Caixia Qi (qcxmay@huawei.com) | CP#51 completed. Updated WID CP-100419=>CP-110091 | 23.003, 23.008, 29.002, 29.272, 29.303 | 48 | 25 |  |  | Wed 26/05/10 | Tue 08/03/11
3732 | 480207 | CT1 part of Stage 3 for SIPTO for macro networks | SIPTO | 4 | Rel-10 | C1 | 2010-06-04 08:00 | 2010-12-10 17:00 | 100% | CP-110091 | - | Huawei | Caixia Qi (qcxmay@huawei.com) | CP#50 completed | 24.008, 24.301 | 48 | 25 |  |  | Wed 26/05/10 | Tue 08/03/11
3733 | 450041 | IP Flow Mobility and seamless WLAN offload | IFOM | 1 | Rel-10 | S2,S1,S5,C1,C3 | 2009-09-24 08:00 | 2011-03-23 17:00 | 100% | SP-100089 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#51 completed. Triggered by Rel-10 TR 23.861 (UID_410043 Study on Multi Access PDN connectivity and IP flow mobility - MAPIM) | - | 45 | 23 |  |  | Tue 08/09/09 | Thu 10/03/11
3734 | 450042 | Stage 1 for IP Flow Mobility and seamless WLAN offload | IFOM | 2 | Rel-10 | S1 | 2009-09-24 08:00 | 2009-12-10 17:00 | 100% | SP-100089 | - | Qualcomm | David Williams (dwilliam@qualcomm.com) | SP#46 completed | 22.278 | 45 | 23 |  |  | Tue 08/09/09 | Fri 01/10/10
3735 | 450043 | Stage 2 for IP Flow Mobility and seamless WLAN offload | IFOM | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-100089 | - | Qualcomm | Gerardo Giaretta (gerardo@qualcomm.com) | SP#49 completed | 23.203, 23.402, new 23.261 | 45 | 23 |  |  | Tue 08/09/09 | Fri 01/10/10
3736 | 470021 | Charging for IP Flow Mobility and seamless WLAN offload | IFOM | 2 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100089 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#51 completed | 32.240, 32.251, 32.252, 32.298, 32.299 | 47 | 24 |  |  | Fri 12/02/10 | Wed 09/03/11
3737 | 480009 | Stage 3 for IP Flow Mobility and seamless WLAN offload | IFOM-CT | 2 | Rel-10 | C1,C3 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100715 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#51 completed | Stage 3 | 48 | 25 |  |  | Wed 26/05/10 | Thu 09/12/10
3738 | 480109 | CT1 part of Stage 3 for IP Flow Mobility and seamless WLAN offload | IFOM-CT | 3 | Rel-10 | C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100715 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#51 completed | 24.008, 24.301, 24.302, 24.303, 24.312, 24.327 | 48 | 25 |  |  | Wed 26/05/10 | Mon 28/02/11
3739 | 480209 | CT3 part of Stage 3 for IP Flow Mobility and seamless WLAN offload | IFOM-CT | 3 | Rel-10 | C3 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100715 | - | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | CP#51 completed | 29.212, 29.213, 29.214, 29.215 | 48 | 25 |  |  | Wed 26/05/10 | Tue 01/03/11
3740 | 450044 | Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 1 | Rel-10 | S2,S4,C4,C3,C1,IETF | 2009-07-15 13:48 | 2012-09-07 17:00 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | CP#52 completed. Triggered by Rel-9 UID_440013 Vocoder rate adaptation for LTE | UTRA, LTE | 45 | 23 |  |  | Tue 08/09/09 | Mon 23/05/11
3741 | 450045 | TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 2 | Rel-10 | S2,S4 | 2010-01-07 08:00 | 2010-09-23 17:00 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#48 completed | new 23.860 | 45 | 23 |  |  | Tue 08/09/09 | Wed 26/05/10
3742 | 450145 | SA4 review of TR on Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 2 | Rel-10 | S4 | 2009-09-24 08:00 | 2010-12-15 17:00 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#50 completed | new 23.860 | 45 | 23 |  |  | Tue 08/09/09 | Wed 01/12/10
3743 | 450046 | Stage 2 for Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 2 | Rel-10 | S2 | 2009-09-24 08:00 | 2010-09-23 17:00 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#49 completed | 23.060, 23.203, 23.228, 23.401 | 45 | 23 |  |  | Tue 08/09/09 | Tue 14/09/10
3744 | 490038 | SA4 aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA | 2 | Rel-10 | S4 | 2010-09-23 08:00 | 2011-03-23 17:00 | 100% | SP-100467 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#51 completed | 26.114 | 49 | 25 |  |  | Tue 14/09/10 | Fri 18/02/11
3745 | 490007 | CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 2 | Rel-10 | C4,C3,C1 | 2009-07-15 13:48 | 2012-09-07 17:00 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | Stage 2/3 | 49 | 25 |  |  | Wed 01/09/10 | Wed 09/03/11
3746 | 490107 | CT4 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 3 | Rel-10 | C4 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | 23.334, 29.334, 29.238, 23.333, 29.333, 29.232, 29.332 | 49 | 25 |  |  | Wed 01/09/10 | Tue 17/05/11
3747 | 531006 | (IETF) CT3, CT4 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 3 | Rel-10 | C3-IETF,C4-IETF | 2009-07-15 13:48 | 2012-09-07 17:00 | 100% | CP-100702 | - | Lionel Morand | - | CP#57 completed | RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp) | 53 | 27 |  |  | Wed 31/08/11 | Mon 03/09/12
3748 | 490207 | CT3 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 3 | Rel-10 | C3 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | 29.162, 29.163, 29.213, 29.235, 29.292 | 49 | 25 |  |  | Wed 01/09/10 | Tue 17/05/11
3749 | 490307 | CT1 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications | ECSRA_LAA-CN | 3 | Rel-10 | C1 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | CP-100702 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed | 24.229 | 49 | 25 |  |  | Wed 01/09/10 | Mon 23/05/11
3750 | 450053 | Extended H(e)NB features | EHNBF | 1 | Rel-10 | S1,S2,S3 | 2008-12-11 08:00 | 2010-09-23 17:00 | 100% | SP-100407 | - | NEC | joerg.swetina@neclab.eu | SP#49 completed. Adds extensions to Rel-9 functionality in UID_400035 Enhanced Home NodeB / eNodeB (EHNB) | UTRA, LTE | 45 | 23 |  |  | Tue 08/09/09 | Fri 23/07/10
3751 | 450153 | Stage 1 of Extended H(e)NB features | EHNBF | 2 | Rel-10 | S1 | 2009-09-24 08:00 | 2010-03-25 17:00 | 100% | SP-100407 | - | NEC | joerg.swetina@neclab.eu | SP#47 completed | 22.220 | 45 | 23 |  |  | Tue 08/09/09 | Tue 08/06/10
3752 | 420034 | IMS aspects of Architecture for Home NodeB | EHNB-IMS | 2 | Rel-10 | S2 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-080799 | - | Alcatel-Lucent | Nicolas Drevon | SP#47 completed. Chosen solution has no normative impacts | New 23.832 | 42 | 22 |  |  | Tue 09/12/08 | Fri 26/02/10
3753 | 480034 | Extended H(e)NB Security features (Stage 2) | EHNBF-Sec | 2 | Rel-10 | S3 | 2010-06-10 08:00 | 2010-09-23 17:00 | 100% | SP-100257 | - | Huawei | Marcus Wong (mwong@huawei.com) | SP#49 completed | 33.320 | 48 | 25 |  |  | Wed 05/05/10 | Fri 23/07/10
3754 | 460028 | Optimal Media Routing | OMR | 1 | Rel-10 | S2,S5,C3,C1 | 2010-03-25 17:00 | 2011-06-08 17:00 | 100% | SP-090803 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | CP#52 completed. SP#47 Stage 2 completed. Triggered by TR 23.894 (UID_370050 Study on System enhancements for the use of IMS servicES in CP-150local breakout) | - | 46 | 24 |  |  | Sun 06/12/09 | Tue 17/05/11
3755 | 460128 | Stage 2 for Optimal Media Routing | OMR | 2 | Rel-10 | S2 | 2010-03-25 17:00 | 2010-03-25 17:00 | 100% | SP-090803 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | SP#47 completed | 23.228 | 46 | 24 |  |  | Sun 06/12/09 | Fri 26/02/10
3756 | 480010 | Stage 3 for Optimal Media Routing | OMR | 2 | Rel-10 | C3,C1,C4 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#51 completion 03/11=>06/11. WID updated CP-100327=>CP-110134 | - | 48 | 25 |  |  | Wed 26/05/10 | Thu 10/03/11
3757 | 480110 | CT3 part of Stage 3 for Optimal Media Routeing | OMR | 3 | Rel-10 | C3 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#52 completed | 29.162, 29.163, 29.165, 29.235, new TS 29.079 | 48 | 25 |  |  | Wed 26/05/10 | Tue 17/05/11
3758 | 480210 | CT1 part of Stage 3 for Optimal Media Routeing | OMR | 3 | Rel-10 | C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#51 completed. WID updated CP-100327=>CP-110134 | 24.229 | 48 | 25 |  |  | Wed 26/05/10 | Thu 10/03/11
3759 | 480310 | Deleted - CT4 part of Stage 3 for Optimal Media Routeing | OMR | 3 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-110134 | - | Alcatel-Lucent | jim.calme@alcatel-lucent.com | CP#51 stopped (CT4 specs not impacted). WID updated CP-100327=>CP-110134 | - | 48 | 25 | CP-51 | PCG-26 | Wed 26/05/10 | Thu 10/03/11
3760 | 500013 | Charging for Optimal Media Routing | OMR | 2 | Rel-10 | S5 | 2010-12-16 08:00 | 2011-06-08 17:00 | 100% | SP-100772 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#52 completed. Stage 3: Linked to CT3 TS 29.079 OMR within the IMS; Stage 3 (UID_480110) | 32.260, 32.298, 32.299 | 50 | 26 |  |  | Sat 27/11/10 | Mon 16/05/11
3761 | 470026 | IMS Emergency Session Enhancements | IESE | 1 | Rel-10 | S1,S2,C1 | 2010-03-25 08:00 | 2011-06-03 17:00 | 100% | SP-100170 | - | Deutsche Telekom, T-Mobile | michele.zarri@t-mobile.co.uk | CP#52 completed. SP#49 completed. Source of external requirements: ETSI TISPAN TS 181.019 (Business Communication Requirements) | - | 47 | 24 |  |  | Wed 10/03/10 | Mon 23/05/11
3762 | 470027 | Stage 1 for IMS Emergency Session Enhancements | IESE | 2 | Rel-10 | S1 | 2010-03-25 08:00 | 2010-03-25 17:00 | 100% | SP-100170 | - | Deutsche Telekom, T-Mobile | Kurt Bischinger | SP#47 completed | 22.101 CR#0343 | 47 | 24 |  |  | Wed 10/03/10 | Tue 23/03/10
3763 | 470028 | Stage 2 for IMS Emergency Session Enhancements | IESE | 2 | Rel-10 | S2 | 2010-03-25 08:00 | 2010-09-23 17:00 | 100% | SP-100170 | - | Deutsche Telekom, T-Mobile | michele.zarri@t-mobile.co.uk | SP#49 completed | 23.167 | 47 | 24 |  |  | Wed 10/03/10 | Mon 06/09/10
3764 | 500005 | Stage 3 for IMS Emergency Session Enhancements | IESE | 2 | Rel-10 | C1 | 2010-12-10 08:00 | 2011-06-03 17:00 | 100% | CP-100880 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | CP#52 completed | 24.229 | 50 | 26 |  |  | Mon 25/10/10 | Mon 23/05/11
3765 | 480037 | S2b Mobility based on GTP | SMOG | 1 | Rel-10 | S2,C4,C3,C1 | 2010-06-10 08:00 | 2011-03-18 17:00 | 100% | SP-100357 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed. SP#49 Stage 2 completed. Related to Rel-10 UID_470049 Study on S2b mobility based on GTP (TR23.834), UID_350027 SAE for support for non-3GPP accesses. Stage1 in Rel-8 UID_320022 Reqs for evolution of 3GPP system architecture (AIPN-SAE) | - | 48 | 25 |  |  | Sun 06/06/10 | Fri 18/03/11
3766 | 480137 | Stage 2 for S2b Mobility based on GTP | SMOG | 2 | Rel-10 | S2 | 2010-06-10 08:00 | 2010-09-23 17:00 | 100% | SP-100357 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | SP#49 completed | 23.002, 23.203, 23.402 | 48 | 25 |  |  | Sun 06/06/10 | Mon 06/09/10
3767 | 490009 | Stage 3 for S2b Mobility based on GTP | SMOG-St3 | 2 | Rel-10 | C4,C3,C1 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 Stage 3 completed | - | 49 | 25 |  |  | Wed 01/09/10 | Fri 18/03/11
3768 | 490109 | CT4 part of Stage 3 for S2b Mobility based on GTP | SMOG-St3 | 3 | Rel-10 | C4 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed | 23.003, 23.007, 23.008, 29.273, 29.274, 29.281, 29.303 | 49 | 25 |  |  | Wed 01/09/10 | Fri 18/03/11
3769 | 490209 | CT3 part of Stage 3 for S2b Mobility based on GTP | SMOG-St3 | 3 | Rel-10 | C3 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed | 29.212, 29.213, 29.215 | 49 | 25 |  |  | Wed 01/09/10 | Fri 18/03/11
3770 | 490309 | CT1 part of Stage 3 for S2b Mobility based on GTP | SMOG-St3 | 3 | Rel-10 | C1 | 2010-09-17 08:00 | 2010-12-10 17:00 | 100% | CP-100644 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#50 completed | 24.302 | 49 | 25 |  |  | Wed 01/09/10 | Thu 25/11/10
3771 | 500006 | Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases | PEST | 1 | Rel-10 | S2,C3 | 2010-10-12 15:48 | 2011-03-18 17:00 | 100% | SP-110196 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | CP#51 completed. SP#50 Stage 2 completed. Triggered by the SA1,SA2 Rel-10 TR 23.813 Study on Policy solutions and enhancements (FS_PP) UID_440047. Provides Video Call seamless service continuity for 3G/LTE terminal user | - | 50 | 26 |  |  | Fri 26/11/10 | Sat 19/03/11
3772 | 500106 | Stage 2 for Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases | PEST | 2 | Rel-10 | S2 | 2010-10-12 15:48 | 2010-10-12 15:48 | 100% | SP-110196 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#51 updated WID SP-100702=>SP-110196. SP#49 work completed as SA2 CRs approved under TEI10 (SP-10557) | 23.002, 23.203 | 50 | 26 |  |  | Fri 26/11/10 | Sat 19/03/11
3773 | 500206 | CT3 aspects of Policy Enhancements for Sponsored Connectivity and Coherent Access to Policy related Databases | PEST-CT3 | 2 | Rel-10 | C3 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100860 | - | ZTE | zhou.xiaoyun@zte.com.cn | CP#51 completed | 29.212, 29.213, 29.214, 29.215 | 50 | 26 |  |  | Fri 26/11/10 | Tue 01/03/11
3774 | 470029 | Lawful Interception in the 3GPP Rel-10 | LI10 | 1 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106 (LI requirements), 33.107 (LI architecture and functions), 33.108 (Handover interface for LI) | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
3775 | 470129 | LI for CAT (Customer Alerting Tones) | LI10 | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
3776 | 470229 | LI for CRS (Customized Ringing Signal) | LI10 | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
3777 | 470329 | LI for EPS enhancements | LI10 | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#52 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
3778 | 470429 | LI for VCC (Voice Call Continuity) | LI10 | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
3779 | 470529 | LI for MEDIASEC (IMS Media security) | LI10 | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
3780 | 470629 | LI for H(e)NB also with Local IP Access and Selected IP Traffic Offload (LIPA, SIPTO) | LI10 | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
3781 | 470729 | LI for MBMS enhancements | LI10 | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
3782 | 470829 | LI for LCLS (Local Call Local Switch) | LI10 | 2 | Rel-10 | S3 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100108 | - | PIDS, BT | Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com | SP#51 completed | 33.106, 33.107, 33.108 | 47 | 24 |  |  | Tue 23/02/10 | Sat 12/03/11
3783 | 470033 | Optimization of IMS based PSS and MBMS User Service | OPT_IMS_PSS_MBMS_US | 1 | Rel-10 | S4 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100031 | - | Ericsson | markus.kampmann@ericsson.com | SP#51 completed. Work to enhance UID_430046 Rel-9 IMS_PSS_MBMS_US_EXT | 26.237 | 47 | 24 |  |  | Wed 10/03/10 | Wed 02/03/11
3784 | 470034 | HTTP-based Streaming and Download Services | HTTP_SDS | 1 | Rel-10 | S4,IETF | 2010-03-25 08:00 | 2011-09-21 17:00 | 100% | SP-100032 | - | Qualcomm | Thomas Stockhammer (c_tstock@qualcomm.com) | SP#52 completed. Work to enhance UID_430038 Rel-9 PSS and MBMS extensions | - | 47 | 24 |  |  | Wed 10/03/10 | Thu 26/05/11
3785 | 470134 | HTTP-based Streaming and Download Services in 3GPP | HTTP_SDS | 2 | Rel-10 | S4 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100032 | - | Qualcomm | Thomas Stockhammer (c_tstock@qualcomm.com) | SP#52 completed | 26.234, 26.244, 26.346, new TS 26.247 | 47 | 24 |  |  | Wed 10/03/10 | Thu 26/05/11
3786 | 521002 | (IETF) HTTP-based Streaming and Download Services in 3GPP | HTTP_SDS | 2 | Rel-10 | S4-IETF | 2010-03-25 08:00 | 2011-09-21 17:00 | 100% | SP-100032 | - | - | - | SP#53/IETF#81: Draft not included in 3GPP documentation. Dec.14: IETF RFC added | RFC 6381 (was draft-gellens-mime-bucket-bis) | 52 | 27 |  |  | Mon 20/06/11 | Thu 04/12/14
3787 | 480040 | PSS and MBMS enhancements | MBS_Enh | 1 | Rel-10 | S4 | 2010-06-10 08:00 | 2011-03-23 17:00 | 100% | SP-100305 | - | Ericsson | Markus.Kampmann@ericsson.com | SP#51 completed. Linked to Rel-9 Feature UID_430038 PSS and MBMS extensions (PMA-MBS_Ext). | 26.234, 26.346 | 48 | 25 |  |  | Fri 28/05/10 | Wed 02/03/11
3788 | 480041 | Enhancements and Addition of Audio Tests to 26.131 and 26.132 | EAAT | 1 | Rel-10 | S4 | 2010-06-10 08:00 | 2011-06-08 17:00 | 100% | SP-100306 | - | Vodafone | ramin.afchar@vodafone.com | SP#52 completed. Reduce fragmentation in acoustic testing (3GPP SA4, ETSI STQ, GCF CAG, CTIA) & Review existing acoustic tests to determine need for new spec | 26.131, 26.132 | 48 | 25 |  |  | Fri 28/05/10 | Tue 17/05/11
3789 | 510055 | Video Coding Enhancements in MTSI | VCEM | 1 | Rel-10 | S4 | 2011-03-21 08:00 | 2011-03-23 17:00 | 100% | SP-110050 | - | Ericsson | frederic.gabin@ericsson.com | SP#51 completed. Linked to Rel-7 UID_7040 Multimedia Telephony Service for IMS - Media handling and interaction in MTSI (MTSI-MHI) | 26.114 | 51 | 26 |  |  | Thu 10/03/11 | Wed 23/03/11
3790 | 460031 | Rel-10 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM10 | 1 | Rel-10 | S5,C4 | 2009-12-10 08:00 | 2011-09-21 17:00 | 100% | - | - | - | - | OAM10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI | TR 30.820 | 46 | 24 |  |  | Tue 01/12/09 | Fri 26/08/11
3791 | 460032 | Rel-10 Network Infrastructure Management | OAM10-NIM | 2 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-09-21 17:00 | 100% | - | - | - | - | umbrella BB | - | 46 | 24 |  |  | Tue 01/12/09 | Sat 12/12/09
3792 | 460033 | Common RAT Network Resource Model (NRM) | RAT_NRM_common | 3 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-06-08 17:00 | 100% | SP-100293 | - | Ericsson | robert.petersen@ericsson.com | SP#52 completed. Share equipment btw several RATs (RET,TMA,repeaters) to reduce costs. With existing modelling is difficult to see that several cells are affected when an antenna tilt is changed etc | 32.616, 32.642, 32.646, 32.652, 32.656, 32.762, 32.766 new (32.791, 32.792, 32.796) | 46 | 24 |  |  | Tue 01/12/09 | Mon 16/05/11
3793 | 470035 | IRP Solution Set specification organisation improvements | OAM-IRP-SS | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100774 | - | Nokia Siemens Networks, Huawei | Jörg Schmidt (J.Schmidt@nsn.com), Lan Zou (zlan@huawei.com) | SP#51 completed | 32.153, new (32.111-6,32.126,32.176,32.306,32.316,32.326,32.336,32.346,32.356,32.366,32.376,32.386,32.396,32.416,32.446,32.506/26/36,32.606,32.616,32.626,32.636,32.646,32.656,32.666,32.676,32.696,32.716,32.726,32.736,32.746,32.756,32.766,32.776,32.786) | 47 | 24 |  |  | Fri 12/02/10 | Wed 09/03/11
3794 | 470036 | Deleted - Service Oriented Architecture (SOA) for IRP continuation from Rel-9 | OAM-SOA-IRP | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100076 | - | Nokia Siemens Networks, Ericsson | Jörg Schmidt (J.Schmidt@NSN.com), edwin.tse@ericsson.com | SP#51 work stopped (Reason: lack of progress). Continuation of Rel-9 UID_440065 SOA for IRP (covering SOA Architecture & SOA-supporting Solution Set) to address SOA conforming Registration & Discovery capabilities | 32.101, 32.150 | 47 | 24 | SP-51 | PCG-26 | Mon 08/03/10 | Wed 09/03/11
3795 | 480042 | IRP Overview, Profiles & Usage Guide | OAM-NIM-IRP_OPU | 3 | Rel-10 | S5 | 2010-06-10 08:00 | 2011-06-08 17:00 | 100% | SP-110277 | - | Nokia Siemens Networks | Jörg Schmidt (J.Schmidt@NSN.com) | SP#52 completed. Updated WID SP-100777=>SP-110277 | new TS 32.103 | 48 | 25 |  |  | Wed 26/05/10 | Mon 06/06/11
3796 | 510041 | Alarm Correlation and Root Cause Analysis | OAM-AC-RCA | 3 | Rel-10 | S5 | 2011-03-23 08:00 | 2011-09-21 17:00 | 100% | SP-110137 | - | Ericsson | brendan.hassett@ericsson.com | SP#53 completed. Triggered by Rel-10 TR 32.832 Study on Alarm Correlation and Alarm Root Cause Analysis UID_480045 & TR 32.829 Study on Harmonization of 3GPP Alarm IRP and TMF Interface Program Fault Management UID_460038 | 32.111-1, 32.111-2, 32.111-6 | 51 | 26 |  |  | Wed 09/03/11 | Fri 26/08/11
3797 | 510042 | Inventory Management Network Resource Model enhancements | OAM-IM-NMR | 3 | Rel-10 | S5 | 2011-03-23 08:00 | 2011-06-08 17:00 | 100% | SP-110141 | - | Nokia Siemens Networks | olaf.pollakowski@nsn.com | SP#52 completed. Inventory NRM specified in Rel-6 is mainly hardware related. Rel-10 TR 32.828 recommends extending the scope of inventory NRM. Additionally, NGMN Top OPE Recs, v1.0 sets inventory enhancements as one of top 10 priority items | 32.690, 32.691, 32.692, 32.696 | 51 | 26 |  |  | Wed 09/03/11 | Mon 16/05/11
3798 | 460034 | Rel-10 Self-Organizing Networks (SON) - OAM aspects | OAM10-SON | 2 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-06-08 17:00 | 100% | - | - | - | - | umbrella BB | - | 46 | 24 |  |  | Tue 01/12/09 | Sat 12/12/09
3799 | 460035 | SON Self-optimization management continuation | LTE-SON-OAM_SO | 3 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-06-08 17:00 | 100% | SP-110130 | - | Huawei | Lan Zou (zlan@huawei.com) | SP#52 completed. Cont'd Rel-9 SON self-optimization management UID_390007 | 32.425, 32.521, 32.522, 32.526, 32.762, 32.766 | 46 | 24 |  |  | Tue 01/12/09 | Fri 13/05/11
3800 | 460036 | SON Self-healing management | LTE-SON-OAM_SH | 3 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-03-23 17:00 | 100% | SP-110150 | - | ZTE | zhu.weihong@zte.com.cn | SP#51 completed. WID updated SP-100776=>SP-110150. Work moved to Rel-10 after split of the Rel-9 UID_390007 SON self-optimization (removed Self-Healing handling) | 32.522, 32.526, 32.762, 32.766, new TS 32.541 | 46 | 24 |  |  | Tue 01/12/09 | Tue 22/03/11
3801 | 470037 | OAM aspects of Energy Saving in Radio Networks | OAM-ES | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-110128 | - | Nokia Siemens Networks | clemens.suerbaum@nsn.com | SP#51 completed. WID updated SP-100226=>SP-110128. Triggered by Rel-10 TR 32.826 Study on Telecommunication Management; Energy Savings Management (FS_OAM_ESM) UID_430044 | 32.425, 32.522, 32.526, 32.626, 32.762, 32.766, new TS 32.551 | 47 | 24 |  |  | Fri 12/02/10 | Thu 17/03/11
3802 | 470038 | Rel-10 Subscription Management (SuM) evolution | OAM10-SuM | 2 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100086 | - | Ericsson | leo.yang@ericsson.com | SP#51 completed | 32.172, 32.175, 32.176 | 47 | 24 |  |  | Tue 23/03/10 | Wed 09/03/11
3803 | 470039 | Rel-10 Performance Management | - | 2 | Rel-10 | S5,C4 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | - | - | - | - | umbrella BB | - | 47 | 24 |  |  | Fri 12/02/10 | Fri 12/02/10
3804 | 470040 | Key Performance Indicators (KPIs) for IMS | OAM-PM-KPI_IMS | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100083 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#51 completed | new 32.454 | 47 | 24 |  |  | Fri 12/02/10 | Wed 09/03/11
3805 | 470041 | Key Performance Indicators (KPIs) for EPC | OAM-PM-KPI_EPC | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100084 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#51 completed | new 32.455 | 47 | 24 |  |  | Fri 12/02/10 | Wed 09/03/11
3806 | 470042 | Management of UE based network performance measurements | OAM-PM-UE | 3 | Rel-10 | S5,C4 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100612 | - | Huawei, Nokia Siemens Networks, Ericsson | Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com | SP#52 completed. Stage 2/3. Linked to UID_460003 Minimization of drive tests for E-UTRAN and UTRAN (MDT_UMTSLTE) | - | 47 | 24 |  |  | Fri 12/02/10 | Tue 22/03/11
3807 | 470142 | SA5 aspects of Management of UE based network performance measurements | - | 4 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-06-08 17:00 | 100% | SP-100612 | - | Huawei, Nokia Siemens Networks, Ericsson | Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com | SP#52 completed | 32.421, 32.422, 32.423, 32.441, 32.442, 32.446 | 47 | 24 |  |  | Fri 12/02/10 | Mon 16/05/11
3808 | 510006 | CN aspects of Management of UE based network performance measurements | - | 4 | Rel-10 | C4 | 2011-02-21 08:00 | 2011-03-18 17:00 | 100% | - | - | Nokia Siemens Networks | ulrich.wiehe@nsn.com | CP#51 completed under the SA5 WI code | 23.008 (CR#0330), 29.002 (CR#1007), 29.230 (CR#0207), 29.272 (CR#0329) | 51 | 26 |  |  | Mon 28/02/11 | Mon 28/02/11
3809 | 470043 | 3G HNB and LTE HeNB Subsystem performance measurements | OAM-PM-HeNS | 3 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100081 | - | China Mobile | Chen Gang (chengang@chinamobile.com) | SP#51 completed | 32.582, 32.592, new (32.452, 32.453) | 47 | 24 |  |  | Mon 08/03/10 | Wed 09/03/11
3810 | 470044 | Rel-10 Charging Management small Enhancements | CH10 | 1 | Rel-10 | S5 | 2009-06-04 08:00 | 2011-03-23 17:00 | 100% | - | - | - | - | CH10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI | TR 30.820 | 47 | 24 |  |  | Fri 12/02/10 | Fri 12/02/10
3811 | 440063 | IWLAN mobility charging | eIWLAN_Mob | 2 | Rel-10 | S5 | 2009-06-04 08:00 | 2011-03-23 17:00 | 100% | SP-100090 | - | Orange | Jean-Luc Garcia (jl.garcia@orange-ftgroup.com) | SP#51 completed. RAT differentiation for charging. Completes Rel-8 Feature IWLAN_Mob UID_370049 Mobility between 3GPP-WLAN Interworking and 3GPP Systems. Cooperation with CT1,CT3 on affected protocols | 32.240, 32.252, 32.298, 32.299 | 44 | 23 |  |  | Tue 19/05/09 | Fri 28/01/11
3812 | 470046 | Advice of Charge (AoC) service support enhancements | eAoC | 1 | Rel-10 | S5,C1 | 2010-03-25 08:00 | 2011-06-03 17:00 | 100% | SP-100080 | - | Deutsche Telekom | matthias.seibel@telekom.de | CP#52 completed. SP#51 completed SA5. Continuation of Rel-8 BB UID_80042: Advice of Charge (AoC) support in IMS Charging (IMSTSS). Stage 2/3 work | - | 47 | 24 |  |  | Tue 23/03/10 | Mon 23/05/11
3813 | 470047 | SA5 part - AoC enhancements | eAoC | 2 | Rel-10 | S5 | 2010-03-25 08:00 | 2011-03-23 17:00 | 100% | SP-100080 | - | Deutsche Telekom | matthias.seibel@telekom.de | SP#51 completed. SA1 Stage 1 in 22.115 | 32.275, 32.280, 32.298, 32.299 | 47 | 24 |  |  | Tue 23/03/10 | Fri 28/01/11
3814 | 490010 | CT1 part - AoC enhancements (Stage 3) | eAoC | 2 | Rel-10 | C1 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | CP-100645 | - | Deutsche Telekom | reinhard.lauster@t-mobile.at | CP#52 completed. SA1 Stage 1 in 22.115, 22.173, 22.024. Add mobile-specific CAI format and volume charging elements. Extensions to existing AoC XML | 24.647 | 49 | 25 |  |  | Tue 07/09/10 | Mon 23/05/11
3815 | 470003 | IMS Stage 3 IETF Protocol Alignment - phase 4 | IMSProtoc4 | 1 | Rel-10 | C1 | 2010-03-19 08:00 | 2011-03-18 17:00 | 100% | CP-100099 | - | Alcatel-Lucent | keith.drage@alcatel-lucent.com | CP#51 completed. Ensure protocol alignment between 3GPP Stage 3 IMS work and IETF. Review capabilities provided in SIP by IETF and document whether these capabilities are supported in the IM CN Subsystem or not | 23.218, 24.229, 24.930 | 47 | 24 |  |  | Wed 17/03/10 | Mon 28/02/11
3816 | 480012 | Enhanced User Data Convergence (UDC) Model | eUDC | 1 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100295 | - | China Mobile | Lan Sizhong (lansizhong@chinamobile.com) | CP#51 completed. Specify CRUD (Create/Read/Update/Delete) operations based on SOAP protocol, which may be used by the applications having no high real-time requirement to the data access operations | 29.335 | 48 | 25 |  |  | Wed 26/05/10 | Mon 28/02/11
3817 | 480014 | Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications | II-NNI2 | 1 | Rel-10 | C3 | 2010-06-04 08:00 | 2013-03-01 17:00 | 100% | CP-100326 | - | Orange | beata.dobrowolska@orange-ftgroup.com | Improvements of Rel-9 Feature UID_440027 Operational description of the Inter-IMS Network to Network Interface (II-NNI) | - | 48 | 25 |  |  | Wed 26/05/10 | Thu 21/02/13
3818 | 480114 | Further improvements of II-NNI Stage 3 | II-NNI2 | 2 | Rel-10 | C3 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100326 | - | Orange | beata.dobrowolska@orange-ftgroup.com | CP#51 completed | 29.165 | 48 | 25 |  |  | Fri 20/04/12 | Fri 20/04/12
3819 | 561001 | (IETF) Further improvements of II-NNI Stage 3 (RFC 6794) | II-NNI2 | 2 | Rel-10 | C3-IETF | 2012-04-20 08:00 | 2013-03-01 17:00 | 100% | CP-100326 | - | Lionel Morand | Lionel Morand | CP#59 completed AUTH 48 RFC-to-be-6794 | RFC 6794 (was draft-ietf-sip-session-policy-framework) | 56 | 29 |  |  | Fri 20/04/12 | Thu 21/02/13
3820 | 561002 | (IETF) Further improvements of II-NNI Stage 3 (RFC 6809) | II-NNI2 | 2 | Rel-10 | C3-IETF | 2012-04-20 08:00 | 2012-12-07 17:00 | 100% | CP-100326 | - | christer.holmberg@ericsson.com | Christer Holmberg | CP#58 completed | RFC 6809 (was draft-ietf-sipcore-proxy-feature) | 56 | 29 |  |  | Fri 20/04/12 | Tue 04/12/12
3821 | 480013 | AT Commands for IMS-configuration | AT_IMS | 1 | Rel-10 | C1 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100376 | - | Ericsson | atle.monrad@ericsson.com | CP#51 completed. Specify 1) IMS-related AT-commands to configure MT and 2) IMS-related unsolicited response codes from MT to present to end-user | 27.007 | 48 | 25 |  |  | Sat 29/05/10 | Mon 14/02/11
3822 | 490011 | AT Commands for USIM Application Toolkit (USAT) | AT_UICC | 1 | Rel-10 | C1 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100646 | - | ST-Ericsson | magnus.mk.karlsson@stericsson.com | CP#51 completed | 27.007 | 49 | 25 |  |  | Sat 29/05/10 | Mon 14/02/11
3823 | 490012 | Communication Control for IMS by USIM (Stage 3) | CC_IMS_USIM | 1 | Rel-10 | C6 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100647 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#51 completed. Stage 1 in TS 22.038 USAT service description. Linked to CT6's UID_1273 Rel-5 BB Provisioning of IP-based multimedia services (24.229, 31.103) and UID_390021 Rel-8 BB CT6 aspects of SAE (31.102, 31.111) | 31.102, 31.103, 31.111 | 49 | 25 |  |  | Mon 06/09/10 | Thu 03/03/11
3824 | 500003 | Dynamic view of SIP message for Inter-IMS Network to Network Interface (II-NNI) (Stage 3) | NNI_DV | 1 | Rel-10 | C3 | 2010-12-10 08:00 | 2011-06-03 17:00 | 100% | CP-100795 | - | NTT | arai.kenjiro@lab.ntt.co.jp | CP#52 completed. Linked to CT3 Rel-10 Feature UID_480014 Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications (II-NNI2) | 29.165 | 50 | 26 |  |  | Fri 26/11/10 | Tue 17/05/11
3825 | 500007 | Introduction of Smart Card Web Server launch functionality | SCWS_L | 1 | Rel-10 | C6 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100883 | - | Telecom Italia | davide.pratone@telecomitalia.it | CP#51 completed. Define a solution which allows enabling to launch Smart Card Web Server servicES in CP-150an easy and simple manner | 31.102 | 50 | 26 |  |  | Sun 28/11/10 | Thu 03/03/11
3826 | 500008 | USAT using AT Commands | USAT_AT | 1 | Rel-10 | C6 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100884 | - | Giesecke & Devrient | enric.fort@gi-de.com | CP#51 completed. Stage 3 based on SA1 22.038CR#37r1 (Make USAT proactive capability reqs applicable to ME as a whole without regard to any particular configuration; e.g. a modem connected to an external display) | Stage 3 31.102, 31.111 | 50 | 26 |  |  | Sun 28/11/10 | Thu 03/03/11
3827 | 500010 | Single Radio Voice Call Continuity (SRVCC) enhancements (Stage 3) | eSRVCC | 1 | Rel-10 | C1,C4,IETF | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | CP-100881 | - | China Mobile | Jiang Y (jiangyi@chinamobile.com) | Triggered by SA2 TR 23.856 Study on Single Radio Voice Call Continuity enhancements (FS_eSRVCC) UID_440049 | - | 50 | 26 |  |  | Mon 25/10/10 | Thu 21/02/13
3828 | 500110 | CT1 part of Stage 3 for SRVCC enhancements | eSRVCC | 2 | Rel-10 | C1 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100881 | - | China Mobile | Jiang Y (jiangyi@chinamobile.com) | CP#51 completed | 24.229, 24.237 | 50 | 26 |  |  | Mon 25/10/10 | Mon 28/02/11
3829 | 500210 | CT4 part of Stage 3 for SRVCC enhancements | eSRVCC | 2 | Rel-10 | C4 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100881 | - | China Mobile | Jiang Y (jiangyi@chinamobile.com) | CP#51 completed | 23.003, 23.008, 29.002, 29.230, 29.272, 29.305, 29.328, 29.329 | 50 | 26 |  |  | Mon 25/10/10 | Mon 28/02/11
3830 | 521003 | (IETF) CT1 part of Stage 3 for SRVCC enhancements (RFC 6809) | eSRVCC | 2 | Rel-10 | C1-IETF | 2010-12-10 08:00 | 2012-12-07 17:00 | 100% | CP-100881 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#58 completed | RFC 6809 (was draft-ietf-sipcore-proxy-feature) | 52 | 27 |  |  | Mon 20/06/11 | Thu 21/02/13
3831 | 500011 | Single Radio Voice Call Continuity (SRVCC) in alerting phase (Stage 3) | aSRVCC | 1 | Rel-10 | C1,R5 | 2010-12-10 08:00 | 2013-03-01 17:00 | 100% | CP-110145 | - | ZTE | li.shitao@zte.com.cn | Builds on Rel-8 UID_390057 (IMS-Cont) TS 23.216 Stage 2. Provide Stage 3 for SRVCC PS-CS transfer of a call in alerting phase. Stage 2 TEI10 in TS 23.237 (6.3.2.1.4c/d, 6.3.2.1.7a/b) | - | 50 | 26 |  |  | Wed 16/03/11 | Mon 23/05/11
3832 | 500111 | CT aspects of Single Radio Voice Call Continuity (SRVCC) in alerting phase (Stage 3) | aSRVCC | 2 | Rel-10 | C1 | 2010-12-10 08:00 | 2011-06-03 17:00 | 100% | CP-110145 | - | ZTE | li.shitao@zte.com.cn | CP#52 completed | 24.008, 24.237 | 50 | 26 |  |  | Wed 16/03/11 | Mon 23/05/11
3833 | 570005 | Conformance test aspects SRVCC in alerting phase | aSRVCC-UEConTest | 2 | Rel-10 | R5 | 2012-09-11 08:00 | 2013-03-01 17:00 | 100% | RP-121700 | RP-130042 | NTT DoCoMo | Takao.Shimizu.rp@nttdocomo.com | RP#59 completed | 36.523-1, 36.523-2, 36.523-3, 34.229-1, 34.229-2, 34.229-3 | 57 | 29 |  |  | Wed 05/09/12 | Wed 27/02/13
3834 | 500012 | PCRF failure and restoration | PCRF_FR | 1 | Rel-10 | C4,C3 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100703 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#51 completed. Triggered by CT3 TR 29.816 Study on Policy and Charging Rules Function (PCRF) failure and restoration (FS_PCRF-FR) UID_450013 | Stage 2/3 work | 50 | 26 |  |  | Mon 25/10/10 | Tue 01/03/11
3835 | 500112 | CT4 part of PCRF failure and restoration | PCRF_FR | 2 | Rel-10 | C4 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100703 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#51 completed | Stage 2 23.007, Stage 3 29.230 | 50 | 26 |  |  | Mon 25/10/10 | Tue 01/03/11
3836 | 500212 | CT3 part of PCRF failure and restoration | PCRF_FR | 2 | Rel-10 | C3 | 2010-12-10 08:00 | 2011-03-18 17:00 | 100% | CP-100703 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#51 completed | Stage 3 29.212, 29.213, 29.214, 29.215 | 50 | 26 |  |  | Mon 25/10/10 | Tue 01/03/11
3837 | 510002 | Formalization of WLAN Files | FoWF | 1 | Rel-10 | C1 | 2011-02-23 08:00 | 2011-02-23 08:00 | 100% | CP-110288 | - | Deutsche Telekom | dieter.jacobsohn@telekom.de | CP#51 completed. TS 24.235 for Info+Approval. Define the ME files as specified in 24.234 in OMA Device Management structure | Stage 3: 24.234, New 24.235 | 51 | 26 |  |  | Thu 03/03/11 | Thu 17/03/11
3838 | 510007 | CS and IMS Interworking for CAT service - Early Session model | CIIC_ES | 1 | Rel-10 | C3 | 2011-03-16 08:00 | 2011-06-03 17:00 | 100% | CP-110283 | - | ZTE | li.shitao@zte.com.cn | CP#52 completed. Stage 1 in Rel-8 TS 22.182 Customized Alerting Tones (CAT) service. Stage 3 TS 24.182 defines 3 impl models: Gateway, Forking, Early Session. Specify missing CAT service interworking procedures btw CS & IMS networks | Stage 3 29.163, 29.235, 29.292 | 51 | 26 |  |  | Wed 02/03/11 | Thu 10/03/11
3839 | 510008 | EPC Node Restoration without Idle mode Signalling Reduction (ISR) activated | EPC_NR | 1 | Rel-10 | C4 | 2011-03-16 08:00 | 2011-03-18 17:00 | 100% | CP-110092 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | CP#51 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014 | Stage 2/3: 23.007, 29.274 | 51 | 26 |  |  | Tue 22/02/11 | Fri 18/03/11
3840 | 510108 | EPC Node Restoration with Idle mode Signalling Reduction (ISR) activated | EPC_NR_ISR | 1 | Rel-10 | C4 | 2011-03-16 08:00 | 2011-06-03 17:00 | 100% | CP-110287 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | CP#52 completed. Triggered by DRAFT TR 23.857 Study on EPC Nodes Restoration (FS_EPC_NR) UID_490014 | Stage 2/3: 23.007, 29.274 | 51 | 26 |  |  | Tue 22/02/11 | Tue 17/05/11
3841 | 510009 | Mobile Terminating Roaming Forwarding with pre-paging | MTRF | 1 | Rel-10 | C4 | 2011-03-16 08:00 | 2011-06-03 17:00 | 100% | CP-110093 | - | Ericsson | philip.hodges@ericsson.com | CP#52 completed. Provides Stage 2/3 alternative solution to Mobile Terminating Roaming Retry to solve roaming events during paging, in particular to support CSFB. Hence, no new Stage 1 requirements exist | Stage 2/3: 23.012, 23.018, 23.116, 29.002 | 51 | 26 |  |  | Tue 22/02/11 | Tue 08/03/11
3842 | 510010 | UICC access to IMS Specification | IMS-UICC-S | 1 | Rel-10 | C6,C1 | 2011-03-16 08:00 | 2011-06-03 17:00 | 100% | CP-110279 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#52 completed. Triggered by Rel-10 TR 31.828 Study on UICC access to IMS (FS_IMS-UICC) UID_480017. Specify mechanism in UICC and ME to make use of IMS functionality implemented in ME for case a) an ISIM is present b) no ISIM is present in UICC | - | 51 | 26 |  |  | Thu 03/03/11 | Wed 18/05/11
3843 | 510110 | CT6 part of UICC access to IMS Specification | IMS-UICC-S | 2 | Rel-10 | C6 | 2011-03-16 08:00 | 2011-03-18 17:00 | 100% | CP-110279 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#51 completed | 31.102, 31.103, 31.111 | 51 | 26 |  |  | Thu 03/03/11 | Thu 10/03/11
3844 | 510210 | CT1 part of UICC access to IMS Specification | IMS-UICC-S | 2 | Rel-10 | C1 | 2011-03-16 08:00 | 2011-06-03 17:00 | 100% | CP-110279 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#52 completed | 24.229 | 51 | 26 |  |  | Thu 03/03/11 | Wed 18/05/11
3845 | 550006 | Deleted - Testing for Terminal support of Rel-10 USIM, ISIM and USAT features | USIM_R10_Test | 1 | Rel-10 | C6 | 2012-03-05 08:00 | 2013-12-03 17:00 | 100% | CP-120396 | - | Gemalto | Denis.Praca@gemalto.com | CP#62 stopped (at 70% completion 06/13). Testing for New featurES in CP-150Rel-10 specifications for USIM, ISIM applications and USIM Application Toolkit (USAT) in TS 31.102, 31.103, 31.111 | 31.121, 31.124, New TS 31.ABC (Conformance Testing of specific features) | 55 | 28 | CP-62 | PCG-32 | Wed 22/02/12 | Thu 06/06/13
3846 | 440021 | CN aspects of Local Call Local Switch | LCLS-CN | 1 | Rel-10 | C4 | 2009-05-29 08:00 | 2011-03-18 17:00 | 100% | CP-100867 | - | Vodafone | David.Hutton@vodafone.com | CP#51 completed | GERAN Stage 2/3 | 44 | 23 |  |  | Wed 13/05/09 | Thu 09/12/10
3847 | 440022 | TR on CN aspects of Local Call Local Switch | LCLS-CN | 2 | Rel-10 | C4 | 2009-05-29 08:00 | 2010-09-16 17:00 | 100% | CP-100867 | - | Vodafone | David.Hutton@vodafone.com | CP#49 completed | new TR 23.889 | 44 | 23 |  |  | Wed 13/05/09 | Thu 09/12/10
3848 | 490013 | Stage 2/3 for CN aspects of Local Call Local Switch | LCLS-CN | 2 | Rel-10 | C4 | 2010-09-17 08:00 | 2011-03-18 17:00 | 100% | CP-100867 | - | Vodafone | David.Hutton@vodafone.com | CP#51 completed | 23.003, 23.009, 23.205, 23.231, 29.002, 29.205, 29.232, new TS 23.284 | 49 | 25 |  |  | Wed 01/09/10 | Mon 28/02/11
3849 | 440023 | Deleted - CT3 aspects of Local Call Local Switch | LCLS-CN | 2 | Rel-10 | C3 | 2009-05-29 08:00 | 2010-09-16 17:00 | 100% | CP-090812 | - | Vodafone | David.Hutton@vodafone.com | CP#49 stopped. Result of study TR 23.889: no CT3 specification impact | - | 44 | 23 | CP-49 | PCG-25 | Wed 13/05/09 | Wed 01/09/10
3850 | 440024 | Deleted - CT1 aspects of Local Call Local Switch | LCLS-CN | 2 | Rel-10 | C1 | 2009-05-29 08:00 | 2010-09-16 17:00 | 100% | CP-090812 | - | Vodafone | David.Hutton@vodafone.com | CP#49 stopped. Result of study TR 23.889: no CT1 specification impact | - | 44 | 23 | CP-49 | PCG-25 | Wed 13/05/09 | Wed 01/09/10
3851 | 430001 | Local Call Local Switch | LCLS | 1 | Rel-10 | GP,G2 | 2007-05-07 09:36 | 2007-05-07 09:36 | 100% | GP-101989 | - | Huawei | wang_zhixi@huawei.com | GP#50 completed. GP#41 WID approved | GERAN Stage 3: 48.008, 48.103 | 41 | 22 |  |  | Fri 20/02/09 | Sat 21/05/11
3852 | 480002 | Tightened Link Level Performance Requirements for Single Antenna MS | TIGHTER | 1 | Rel-10 | G1,G2,C1,G3new | 2010-09-03 08:00 | 2013-03-01 17:00 | 100% | GP-101083 | - | Renesas Mobile | carsten.juncker@renesasmobile.com | GP#46 approved WID | GERAN | 46 | 25 |  |  | Thu 27/05/10 | Sat 16/03/13
3853 | 480102 | CT1 part for TIGHTER | TIGHTER | 2 | Rel-10 | C1 | 2010-09-03 08:00 | 2011-06-03 17:00 | 100% | GP-101083 | - | Renesas Mobile | marko.niemi@renesasmobile.com | CP#52 completed | 24.008 | 46 | 25 |  |  | Thu 27/05/10 | Mon 23/05/11
3854 | 480202 | TIGHTER Performance Requirements | TIGHTER | 2 | Rel-10 | G1,G2 | 2010-09-03 08:00 | 2011-05-20 17:00 | 100% | GP-101084 | - | Renesas Mobile | carsten.juncker@renesasmobile.com | GP#50 completed | 45.005, 45.015 | 46 | 25 |  |  | Thu 27/05/10 | Sat 21/05/11
3855 | 480302 | TIGHTER Testing | TIGHTER | 2 | Rel-10 | G3new | 2010-09-08 08:00 | 2013-03-01 17:00 | 100% | GP-101085 | - | Renesas Mobile | carsten.juncker@renesasmobile.com | GP#57 completed | 51.010 | 46 | 25 |  |  | Thu 27/05/10 | Mon 04/03/13
3856 | 490001 | Support of Multi-Operator Core Network by GERAN | MOCN-GERAN | 1 | Rel-10 | G2,S2,C1 | 2010-05-21 08:00 | 2011-03-04 17:00 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#47 approved WID. 900 MHz spectrum re-farming to other RATs lead operators to reduce GSM capacity and therefore share their GSM networks. Hence the need for the most suitable (GE)RAN sharing method | GERAN | 47 | 25 |  |  | Thu 27/05/10 | Fri 04/03/11
3857 | 490101 | Stage 2 for Support of Multi-Operator Core Network by GERAN | MOCN-GERAN | 2 | Rel-10 | S2 | 2010-05-21 08:00 | 2010-12-16 17:00 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | SP#50 completed | 23.251 | 47 | 25 |  |  | Thu 27/05/10 | Tue 30/11/10
3858 | 490201 | CT1 part of Stage 3 for Support of Multi-Operator Core Network by GERAN | MOCN-GERAN | 2 | Rel-10 | C1 | 2010-05-21 08:00 | 2010-12-10 17:00 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | CP#50 completed | 24.008 CR#1644 | 47 | 25 |  |  | Thu 27/05/10 | Fri 04/03/11
3859 | 490301 | GERAN2 part of Stage 3 for Support of Multi-Operator Core Network by GERAN | MOCN-GERAN | 2 | Rel-10 | G2 | 2010-08-30 08:00 | 2011-03-04 17:00 | 100% | GP-101443 | - | Alcatel-Lucent | michel.robert@alcatel-lucent.com | GP#49 completed | 48.008 CR#0325, 48.018 CR#0303 | 47 | 25 |  |  | Thu 27/05/10 | Fri 04/03/11
3860 | 490002 | Enhancements of Iur-g interface | eIurg | 1 | Rel-10 | G2,R3 | 2010-09-03 08:00 | 2011-06-03 17:00 | 100% | GP-101758 | - | China Mobile, ZTE | Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn) | GP#47 approved WID | GERAN,UTRA | 47 | 25 |  |  | Sun 05/09/10 | Thu 26/05/11
3861 | 490102 | GERAN part for Enhancements of Iur-g interface (Stage 2/3) | eIurg-GERAN | 2 | Rel-10 | G2 | 2010-09-03 08:00 | 2011-03-04 17:00 | 100% | GP-101758 | - | China Mobile, ZTE | Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn) | GP#49 completed. GP#48 updated WID GP-101659=>GP-101758 (restricting the scope to GERAN BSC and TD-SCDMA RNC only). GP#47 approved WID | 43.130, 48.008 | 47 | 25 |  |  | Sun 05/09/10 | Fri 04/03/11
3862 | 490021 | Core part: Enhancements of Iur-g interface (Stage 2/3) | eIurg-RAN | 2 | Rel-10 | R3 | 2010-09-03 08:00 | 2011-06-03 17:00 | 100% | RP-101232 | RP-110526 | ZTE | Liu Junqiang (liu.junqiang@zte.com.cn) | RP#52 completed | UTRA Stage 2 (25.401, 25.420), Stage 3 (25.423) | 49 | 25 |  |  | Sun 05/09/10 | Thu 26/05/11
3863 | 380077 | 1.28 Mcps TDD Repeater | RANimp-Repeaters1.28TDD | 1 | Rel-10 | R4 | 2007-12-04 08:00 | 2010-03-19 17:00 | 100% | RP-071003 | RP-100039 | RITT | qinyan@chinattl.com | RP#47 completed | UTRA 25.113, New 25.116, 25.153 (testing) | 38 | 21 |  |  | Mon 17/12/07 | Tue 09/03/10
3864 | 450019 | 1.28 Mcps TDD Multi-carrier HSUPA | TDD_MC_HSUPA | 1 | Rel-10 | R1,R2,R3,R4 | 2009-09-18 08:00 | 2010-12-10 17:00 | 100% | RP-090990 | RP-101079 | CATR | Aihui Song (songaihui@mail.ritt.com.cn) | RP#50 completed | UTRA 25.102, 25.105, 25.123, 25.221, 25.222, 25.223, 25.224, 25.225, 25.306, 25.319, 25.321, 25.331, 25.423, 25.427, 25.433 | 45 | 23 |  |  | Tue 15/09/09 | Fri 03/12/10
3865 | 460014 | 1.28 Mcps TDD Home NodeB RF requirements | HNB_LCRTDD_RF | 1 | Rel-10 | R4 | 2009-12-04 08:00 | 2010-12-10 17:00 | 100% | RP-100607 | - | TD Tech | Li Rong (lirong@td-tech.com) | RP#50 completed. Triggered by FS_RAN-HNBLCRTDD UID_410016 Study on 1.28 Mcps TDD Home NodeB (TR 25.866) | UTRA | 46 | 24 |  |  | Mon 30/11/09 | Fri 03/12/10
3866 | 460114 | Core part: 1.28Mcps TDD Home NodeB RF requirements | HNB_LCRTDD_RF-Core | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2010-06-04 17:00 | 100% | RP-100607 | RP-100446 | TD Tech | Li Rong (lirong@td-tech.com) | RP#48 completed | 25.105 | 46 | 24 |  |  | Mon 30/11/09 | Wed 02/06/10
3867 | 460214 | Perf. part: 1.28Mcps TDD Home NodeB RF requirements | HNB_LCRTDD_RF-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2010-12-10 17:00 | 100% | RP-100607 | RP-101081 | TD Tech | Li Rong (lirong@td-tech.com) | RP#50 completed. TR 25.968 v100 for Approval | 25.142, new TR 25.968 | 46 | 24 |  |  | Mon 30/11/09 | Fri 03/12/10
3868 | 470012 | Multi-User Multiple-Input and Multiple-Output (MU-MIMO) for 1.28Mcps TDD | MUMIMO_LCR_TDD | 1 | Rel-10 | R1,R2,R3,R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-100347 | - | CATT | Yanping Xing (xingyanping@datangmobile.cn) | RP#52 completed | UTRA | 47 | 24 |  |  | Fri 19/03/10 | Tue 23/03/10
3869 | 470112 | Core part: MU-MIMO for 1.28Mcps TDD | MUMIMO_LCR_TDD-Core | 2 | Rel-10 | R1,R2,R3 | 2010-03-19 08:00 | 2010-12-10 17:00 | 100% | RP-100347 | RP-101085 | CATT | Yanping Xing (xingyanping@datangmobile.cn) | RP#50 completed | 25.221, 25.222, 25.224, 25.306, 25.308, 25.319, 25.331, 25.423, 25.425, 25.433, 25.435 | 47 | 24 |  |  | Fri 19/03/10 | Fri 03/12/10
3870 | 470212 | Perf. part: MU-MIMO for 1.28Mcps TDD | MUMIMO_LCR_TDD-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-100347 | RP-110520 | CATT | Sanjun Feng (fengsanjun@datangmobile.cn) | RP#52 completed | 25.102, 25.105, 25.142 | 47 | 24 |  |  | Fri 19/03/10 | Tue 24/05/11
3871 | 450027 | AGNSS Minimum Performance for UTRAN | AGNSSPerf_UTRAN | 1 | Rel-10 | R4,R5 | 2009-09-18 08:00 | 2011-09-16 17:00 | 100% | RP-100363 | - | Thales | Michel.monnerat@thalesaleniaspace.com | RP#53 completed. Triggered by Rel-7 UID_20050 (GNSS in UTRAN) and Rel-8 UID_400051 (Support for Additional NSS). Linked to GERAN Rel-9 UID_38002 (AGNSS Performances and Testing Procedures) | UTRA | 45 | 23 |  |  | Tue 15/09/09 | Wed 08/12/10
3872 | 450127 | AGNSS Minimum Performance Specification Development | AGNSSPerf_UTRAN | 2 | Rel-10 | R4 | 2009-09-18 08:00 | 2010-12-10 17:00 | 100% | RP-100363 | RP-101078 | Thales | Michel.monnerat@thalesaleniaspace.com | RP#50 completed | new 25.172 | 45 | 23 |  |  | Tue 15/09/09 | Wed 08/12/10
3873 | 480018 | AGNSS test case development for UMTS | AGNSSPerf_UTRAN | 2 | Rel-10 | R5 | 2010-06-04 08:00 | 2011-09-16 17:00 | 100% | RP-101405 | RP-110979 | Thales | Michel.monnerat@thalesaleniaspace.com | RP#53 completed | 34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.37.571-5, new 34.172 | 48 | 25 |  |  | Tue 01/06/10 | Tue 06/09/11
3874 | 460005 | Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN | LCS_UMTS_RFPMT | 1 | Rel-10 | R2,R3 | 2009-12-04 08:00 | 2011-03-18 17:00 | 100% | RP-091427 | RP-110048 | Polaris Wireless | Norman Shaw (nshaw@polariswireless.com) | RP#51 completed. Triggered by Study UID_380079 Evaluation of the inclusion of Path Loss Based Technology in the UTRAN (25.907) | UTRA | 46 | 24 |  |  | Mon 30/11/09 | Fri 11/03/11
3875 | 460105 | Core part: Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN | LCS_UMTS_RFPMT-Core | 2 | Rel-10 | R2,R3 | 2009-12-04 08:00 | 2011-03-18 17:00 | 100% | RP-091427 | RP-110048 | Polaris Wireless | Norman Shaw (nshaw@polariswireless.com) | RP#51 completed | 25.305, 25.453 | 46 | 24 |  |  | Mon 30/11/09 | Fri 11/03/11
3876 | 460015 | Four carrier HSDPA | 4C_HSDPA | 1 | Rel-10 | R1,R2,R3,R4,R5 | 2009-12-04 08:00 | 2013-09-06 17:00 | 100% | RP-100991 | - | Qualcomm | Arjun Bharadwaj (arjunb@qualcomm.com) | RP#53 completed | UTRA | 46 | 24 |  |  | Mon 30/11/09 | Mon 12/09/11
3877 | 460115 | Core part: Four carrier HSDPA | 4C_HSDPA-Core | 2 | Rel-10 | R1,R2,R3,R4 | 2009-12-04 08:00 | 2011-03-18 17:00 | 100% | RP-100991 | RP-110046 | Qualcomm | Arjun Bharadwaj (arjunb@qualcomm.com) | RP#51 completed. RP#52 TR 25.864 v200 for Approval | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.331, 25.423, 25.433, 26.306, new TR 25.864 | 46 | 24 |  |  | Mon 30/11/09 | Fri 27/05/11
3878 | 460215 | Perf. part: Four carrier HSDPA | 4C_HSDPA-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2011-09-16 17:00 | 100% | RP-100991 | RP-110986 | Qualcomm | Arjun Bharadwaj (arjunb@qualcomm.com) | RP#53 completed | 25.101, 25.104, 25.133, 25.141 | 46 | 24 |  |  | Mon 30/11/09 | Mon 12/09/11
3879 | 540006 | Test part: Four carrier HSDPA | 4C_HSDPA-UEConTest | 2 | Rel-10 | R5 | 2011-12-02 08:00 | 2013-09-06 17:00 | 100% | RP-111565 | RP-130940 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#61 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 54 | 28 |  |  | Thu 24/11/11 | Thu 29/08/13
3880 | 470013 | Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver | 2ant_UE_LCR_TDD | 1 | Rel-10 | R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-100168 | - | TD Tech | dafei.wang@td-tech.com | Stage 3. RP#52 completed | UTRA | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/06/11
3881 | 470113 | Core part: Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver | 2ant_UE_LCR_TDD-Core | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2010-06-04 17:00 | 100% | RP-100168 | RP-100454 | TD Tech | dafei.wang@td-tech.com | RP#48 completed | 25.102 | 47 | 24 |  |  | Fri 19/03/10 | Tue 01/06/10
3882 | 470213 | Perf. part: Performance Requirements for two-antenna 1.28Mcps TDD Type 1 and Type 2 UE receiver | 2ant_UE_LCR_TDD-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-100168 | RP-110521 | TD Tech | dafei.wang@td-tech.com | RP#52 completed | 25.102 | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/06/11
3883 | 480020 | Automatic Neighbour Relation (ANR) for UTRAN | ANR_UTRAN | 1 | Rel-10 | R3,R2,R5 | 2010-06-04 08:00 | 2012-12-07 17:00 | 100% | RP-100688 | - | ZTE | Zhai.hengxing@zte.com.cn | RP#52 Core completed. Automatic Neighbour Relation (ANR) function for UTRAN relieves operators from the burden of manually managing the Neighbour cell Relations (NRs) | UTRA | 48 | 25 |  |  | Thu 03/06/10 | Mon 15/04/13
3884 | 480120 | Core part: Automatic Neighbour Relation (ANR) for UTRAN | ANR_UTRAN-Core | 2 | Rel-10 | R3,R2 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100688 | RP-110522 | ZTE | Zhai.hengxing@zte.com.cn | RP#52 completed | 25.331, 25.413, 25.423, new TS 25.484 (Stage 2) | 48 | 25 |  |  | Thu 03/06/10 | Tue 31/05/11
3885 | 530039 | Test part: Automatic Neighbour Relation (ANR) for UTRAN | ANR_UTRAN-UEConTest | 2 | Rel-10 | R5 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-120599 | RP-121529 | Ericsson | leif.mattisson@ericsson.com | RP#58 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 | 53 | 27 |  |  | Fri 09/09/11 | Wed 28/11/12
3886 | 480021 | Support of New Band Combinations for Dual-Band Dual Cell HSDPA | DB_DC_HSDPA | 1 | Rel-10 | R4,R2 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100657 | - | AT&T | Vince Spatafora (vs5785@att.com) | RP#52 completed. Rel-9 Dual-Band Dual-Cell HSDPA (UID_430015 Support for different bands for Dual-Cell HSDPA) has one combination per region in principle. This work adds additional combinations: Band I and XI (Region 3) and Band II and V (Region 2) | UTRA | 48 | 25 |  |  | Thu 03/06/10 | Tue 24/05/11
3887 | 480121 | Core part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA | DB_DC_HSDPA-Core | 2 | Rel-10 | R4,R2 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100657 | RP-110523 | AT&T | Vince Spatafora (vs5785@att.com) | RP#52 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.141, 25.317 replaced by new TS 25.327 | 48 | 25 |  |  | Thu 03/06/10 | Tue 24/05/11
3888 | 480221 | Deleted - Perf. part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA | DB_DC_HSDPA-Perf | 2 | Rel-10 | R4,R2 | 2010-06-04 08:00 | 2010-09-17 17:00 | 100% | RP-100657 | RP-100759 | AT&T | Vince Spatafora (vs5785@att.com) | RP#49 stopped (Reason: no need for Performance work) | 25.101, 25.104, 25.141, 25.317 | 48 | 25 | RP-49 | PCG-25 | Thu 03/06/10 | Thu 09/09/10
3889 | 480022 | MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA | 1 | Rel-10 | R4,R5 | 2010-06-04 08:00 | 2012-03-02 17:00 | 100% | RP-100993 | - | Qualcomm | Heechoon Lee | RP#52 completed. RP#49 updated WID RP-100687=>RP-100993 (changed Title: MIMO Testing in HSDPA => MIMO operation with non-MIMO coexistence in HSDPA) | UTRA | 48 | 25 |  |  | Thu 03/06/10 | Mon 14/03/11
3890 | 490023 | Core part: MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA-Core | 2 | Rel-10 | R4 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | RP-100993 | RP-110524 | Qualcomm | Heechoon Lee | RP#52 completed | 25.104 | 49 | 25 |  |  | Fri 10/09/10 | Fri 27/05/11
3891 | 480122 | Perf. part: MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA-Perf | 2 | Rel-10 | R4 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100993 | RP-110525 | Qualcomm | Heechoon Lee | RP#52 completed | 25.101, 25.141 | 48 | 25 |  |  | Thu 03/06/10 | Fri 27/05/11
3892 | 510017 | Test part: MIMO operation with non-MIMO coexistence in HSDPA | MIMO_HSDPA-UEConTest | 2 | Rel-10 | R5 | 2011-03-18 08:00 | 2012-03-02 17:00 | 100% | RP-110244 | RP-120042 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#55 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 51 | 26 |  |  | Thu 10/03/11 | Thu 23/02/12
3893 | 490022 | Interfrequency detected set measurements for UMTS | Interf_dset_meas_UMTS | 1 | Rel-10 | R2,R4 | 2010-09-17 08:00 | 2010-12-10 17:00 | 100% | RP-101015 | RP-101093 | Nokia | Chris.callender@nokia.com | RP#50 completed | UTRA 25.133, 25.331 | 49 | 25 |  |  | Sat 11/09/10 | Wed 08/12/10
3894 | 460007 | Carrier Aggregation (CA) for LTE | LTE_CA | 1 | Rel-10 | R1,R2,R3,R4,R5 | 2009-12-04 08:00 | 2012-12-07 17:00 | 100% | RP-100661 | - | Nokia | Asbjorn.grovlen@nokia.com | - | LTE | 46 | 24 |  |  | Mon 30/11/09 | Mon 14/03/11
3895 | 460107 | Core part: CA for LTE | LTE_CA-Core | 2 | Rel-10 | R1,R2,R3,R4 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-100661 | RP-110535 | Nokia | lars.e.lindh@nokia.com | RP#52 completed. RP#56 new RAN4 TR (36.807, 36.808) v200 for Approval | 36.101, 36.104, 36.133, 36.211, 36.212, 36.213, 36.300, 36.302, 36.306, 36.321, 36.331, 36.413, 36.423, 37.104, new RAN4 TR (36.807, 36.808) | 46 | 24 |  |  | Mon 30/11/09 | Thu 07/06/12
3896 | 460207 | Perf. part: CA for LTE | LTE_CA-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2011-12-09 17:00 | 100% | RP-100661 | RP-111452 | Nokia | lars.e.lindh@nokia.com | RP#54 completed | 36.101, 36.104, 36.133, 36.141, 37.141 | 46 | 24 |  |  | Mon 30/11/09 | Thu 07/06/12
3897 | 530040 | Test part: CA for LTE | LTE_CA-UEConTest | 2 | Rel-10 | R5 | 2011-09-19 08:00 | 2012-12-07 17:00 | 100% | RP-121246 | RP-121528 | Nokia | jussi.kuusisto@nokia.com | RP#58 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3, 37.571-1, 37.571-3, 37.571-5 | 53 | 27 |  |  | Tue 06/09/11 | Tue 04/12/12
3898 | 460008 | Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO | 1 | Rel-10 | R1,R2,R4,R5 | 2009-12-04 08:00 | 2013-06-14 17:00 | 100% | RP-100196 | - | NTT DoCoMo | Hidekazu Taoka (taoka@nttdocomo.com) | - | LTE | 46 | 24 |  |  | Mon 30/11/09 | Fri 19/03/10
3899 | 460108 | Core part: Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO-Core | 2 | Rel-10 | R1,R2,R4 | 2009-12-04 08:00 | 2011-03-18 17:00 | 100% | RP-100196 | RP-110067 | NTT DoCoMo | Hidekazu Taoka (taoka@nttdocomo.com) | RP#51 completed. RP#56 new RAN4 TR 36.807 v200 for Approval | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.306, 36.321, 36.331, new RAN4 TR 36.807 | 46 | 24 |  |  | Mon 30/11/09 | Thu 07/06/12
3900 | 460208 | Perf. part: Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2012-03-02 17:00 | 100% | RP-091429 | RP-120053 | NTT DoCoMo | Hidekazu Taoka (taoka@nttdocomo.com) | RP#55 completed | 36.101, 36.104, 36.133, 36.141 | 46 | 24 |  |  | Mon 30/11/09 | Thu 23/02/12
3901 | 560012 | Test part: Enhanced Downlink Multiple Antenna Transmission for LTE | LTE_eDL_MIMO-UEConTest | 2 | Rel-10 | R5 | 2012-06-18 08:00 | 2013-06-14 17:00 | 100% | RP-120612 | RP-130464 | ZTE | Carolyn Taylor (carolyn.tayl@zte.com.cn) | RP#60 completed. Testing for 36.101, 36.133 | 36.508, 36.521-1, 36.521-2 | 56 | 29 |  |  | Wed 06/06/12 | Tue 04/06/13
3902 | 460009 | Uplink Multiple Antenna Transmission for LTE | LTE_UL_MIMO | 1 | Rel-10 | R1,R2,R4,R5 | 2000-01-03 08:00 | 2013-03-01 17:00 | 100% | RP-100959 | - | Huawei | Mattias.wennstrom@huawei.com | - | LTE | 46 | 24 |  |  | Mon 30/11/09 | Mon 12/09/11
3903 | 460109 | Core part: UL multiple antenna transmission for LTE | LTE_UL_MIMO-Core | 2 | Rel-10 | R1,R2,R4 | 2000-01-03 08:00 | 2001-06-29 17:00 | 100% | RP-100959 | RP-110537 | Huawei | Mattias.wennstrom@huawei.com | RP#52 completed. TR 36.817 v110 for Approval. RP#56 new TR 36.807 v200 for Approval | 36.101, 36.104, 36.133, 36.201, 36.211, 36.212, 36.213, 36.300, 36.306, 36.321, 36.331, new RAN4 (TR 36.807, 36.817) | 46 | 24 |  |  | Mon 30/11/09 | Thu 07/06/12
3904 | 460209 | Perf. part: UL multiple antenna transmission for LTE | LTE_UL_MIMO-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2011-09-16 17:00 | 100% | RP-100959 | RP-110992 | Huawei | Mattias.wennstrom@huawei.com | RP#53 completed | 36.101, 36.104, 36.133, 36.141, 36.817 | 46 | 24 |  |  | Mon 30/11/09 | Mon 12/09/11
3905 | 540007 | Test part: UL multiple antenna transmission for LTE | LTE_UL_MIMO-UEConTest | 2 | Rel-10 | R5 | 2011-12-02 08:00 | 2013-03-01 17:00 | 100% | RP-111614 | RP-130038 | Huawei | Zhang Xin (suzanna.zhang@huawei.com) | RP#59 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 54 | 28 |  |  | Thu 24/11/11 | Wed 27/02/13
3906 | 460013 | Relays for LTE | LTE_Relay | 1 | Rel-10 | R1,R2,R4,S2,S3,C4,C6 | 2009-12-04 08:00 | 2011-06-08 17:00 | 100% | RP-110911 | - | Ericsson | christian.hoymann@ericsson.com | RP#52 completed (open RAN4 Core & Perf parts moved to new Rel-11) | LTE | 46 | 24 |  |  | Mon 30/11/09 | Mon 14/02/11
3907 | 460113 | Core part: Relays for LTE | LTE_Relay-Core | 2 | Rel-10 | R1,R2,R4 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-110911 | RP-110540 | Ericsson | christian.hoymann@ericsson.com | RP#52 completed. Updated WID RP-101417=>RP-101911 (contains only Core part completed in Rel-10). Open RAN4 Core & Perf parts moved to new Rel-11 | 36.201, 36.211, 36.212, 36.213, 36.300, 36.321, 36.323, 36.331, New RAN1 TS 36.216 | 46 | 24 |  |  | Mon 30/11/09 | Thu 14/06/12
3908 | 460213 | Deleted - Perf. part: Relays for LTE | LTE_Relay-Perf | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-101417 | RP-110541 | Ericsson | christian.hoymann@ericsson.com | RP#52 stopped at 30% (no CRs so far) . Transferred completely to Rel-11 together with remaining core part | 36.133, New TS 36.117 (E-UTRA Relay conformance testing) | 46 | 24 | RP-52 | PCG-27 | Mon 30/11/09 | Mon 06/06/11
3909 | 520020 | Stage 2 for Relays for LTE | LTE_Relay | 2 | Rel-10 | S2 | 2011-06-06 08:00 | 2011-06-08 17:00 | 100% | - | - | Vodafone | chris.pudney@vodafone.com | SP#52 SP-110338 (S2-85/S2-112851) 23.401 Cat F CR#2128 Completion of Relay procedure overview | 23.401 | 52 | 27 |  |  | Mon 06/06/11 | Mon 06/06/11
3910 | 500038 | LTE Relay Nodes Security | LTE_Relay-Sec | 2 | Rel-10 | S3,C6 | 2010-12-16 08:00 | 2011-03-22 17:00 | 100% | SP-100733 | - | Qualcomm | Adrian Escott (aescott@qualcomm.com) | - | - | 50 | 26 |  |  | Thu 25/11/10 | Mon 14/02/11
3911 | 500238 | TR on LTE Relay Nodes Security | LTE_Relay-Sec | 3 | Rel-10 | S3 | 2010-12-16 08:00 | 2011-03-22 17:00 | 100% | SP-100733 | - | Qualcomm | Adrian Escott (aescott@qualcomm.com) | SP#51 completed | 33.816 | 50 | 26 |  |  | Thu 25/11/10 | Mon 14/02/11
3912 | 500138 | Security for LTE Relay Nodes (Stage 2) | LTE_Relay-Sec | 3 | Rel-10 | S3 | 2010-12-16 08:00 | 2011-03-22 17:00 | 100% | SP-100733 | - | Qualcomm | Adrian Escott (aescott@qualcomm.com) | SP#51 completed (impacting Stage 3 in CT and RAN) | 33.401 (CR#0437,0438), CT1 24.301, CT4 (29.272, 29.274), CT6 31.102, RAN2 (36.331, 36.323), RAN3 36.413 | 50 | 26 |  |  | Thu 25/11/10 | Mon 14/02/11
3913 | 510011 | CT6 aspects of LTE Relay Node Security | LTE_Relay-Sec | 3 | Rel-10 | C6 | 2011-03-16 08:00 | 2011-03-18 17:00 | 100% | - | - | n/a | n/a | CP#51 completed | 31.101, 31.102 | 51 | 26 |  |  | Thu 03/03/11 | Thu 03/03/11
3914 | 510012 | Core Network Impacts for Relay Nodes | LTE_Relay-CN | 2 | Rel-10 | C4 | 2011-03-16 08:00 | 2011-03-18 17:00 | 100% | CP-110094 | - | Vodafone | David.Hutton@vodafone.com | CP#51 completed | 23.003, 23.008, 29.303, 29.230, 29.272 | 51 | 26 |  |  | Mon 28/02/11 | Tue 08/03/11
3915 | 470007 | Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE | eICIC_LTE | 1 | Rel-10 | R1,R2,R3,R4,R5 | 2010-03-19 08:00 | 2014-06-13 17:00 | 100% | RP-100383 | - | China Mobile | Xiaodong XU (xuxiaodong@chinamobile.com) | RP#56 completed | LTE | 47 | 24 |  |  | Fri 19/03/10 | Mon 14/03/11
3916 | 470107 | Core part: Enhanced Inter-Cell Interference Control (ICIC) for non-CA based deployments of heterogeneous networks for LTE | eICIC_LTE-Core | 2 | Rel-10 | R1,R2,R3,R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-100383 | RP-110543 | China Mobile | Xiaodong XU (xuxiaodong@chinamobile.com) | RP#52 completed | 36.101, 36.133, 36.201, 36.211, 36.212, 36.213, 36.214, 36.300, 36.321, 36.331, 36.413, 36.423 | 47 | 24 |  |  | Fri 19/03/10 | Fri 27/05/11
3917 | 470207 | Perf. part: Enhanced Inter-Cell Interference Control (ICIC) for non-CA based deployments of heterogeneous networks for LTE | eICIC_LTE-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2012-06-15 17:00 | 100% | RP-100383 | RP-120461 | China Mobile | Xiaodong XU (xuxiaodong@chinamobile.com) | RP#56 completed | 36.101, 36.133 | 47 | 24 |  |  | Fri 19/03/10 | Tue 05/06/12
3918 | 550001 | Test part: Enhanced Inter-Cell Interference Control (ICIC) for non-CA based deployments of heterogeneous networks for LTE | eICIC_LTE-UEConTest | 2 | Rel-10 | R5 | 2012-03-05 08:00 | 2014-06-13 17:00 | 100% | RP-120217 | RP-140766 | Qualcomm | Anjali Mishra (ajha@qualcomm.com) | RP#64 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 55 | 28 |  |  | Thu 23/02/12 | Tue 10/06/14
3919 | 470008 | LTE TDD in 2600MHz for US | LTE_TDD_2600_US | 1 | Rel-10 | R4,R2,R3,R5 | 2010-03-19 08:00 | 2010-12-10 17:00 | 100% | RP-101003 | - | Clearwire | michael.hart@clearwire.com | RP#50 Testing completed. RP#49 Core+Perf completed | LTE | 47 | 24 |  |  | Fri 19/03/10 | Fri 03/12/10
3920 | 470108 | Core part: LTE TDD in 2600MHz for US | LTE_TDD_2600_US-Core | 2 | Rel-10 | R4,R2,R3 | 2010-03-19 08:00 | 2010-09-15 17:00 | 100% | RP-101003 | RP-100782 | Clearwire | michael.hart@clearwire.com | RP#49 completed 1st Apr 15: CD:Fri 17/09/10->Wed 15/09/10 | 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, 37.104, 37.113, 37.141, new TR 36.812 | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/04/15
3921 | 470208 | Perf. part: LTE TDD in 2600MHz for US | LTE_TDD_2600_US-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2010-09-17 17:00 | 100% | RP-101003 | RP-100783 | Clearwire | michael.hart@clearwire.com | RP#49 completed | 36.101, 36.104, 36.133, 36.141, 36.307, 37.104, 37.141, new TR 36.812 | 47 | 24 |  |  | Fri 19/03/10 | Thu 16/09/10
3922 | 480019 | UE conformance test part: LTE TDD in 2600MHz for US | LTE_TDD_2600_US-UEConTest | 2 | Rel-10 | R5 | 2010-06-04 08:00 | 2010-12-10 17:00 | 100% | RP-100615 | RP-101071 | Clearwire | michael.hart@clearwire.com | RP#50 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 48 | 25 |  |  | Tue 01/06/10 | Fri 03/12/10
3923 | 470009 | Adding 2 GHz band LTE FDD (Band 23) for Ancillary Terrestrial Component (ATC) of Mobile Satellite Service (MSS) in North America | S_Band_LTE_ATC_MSS | 1 | Rel-10 | R2,R4,R5 | 2010-03-19 08:00 | 2011-12-09 17:00 | 100% | RP-110775 | - | DBSD | Mariam.Sorond@ico.com | RP#52 completed. Updated WID RP-101401=>RP-110775 (changed in Title "LTE" to "LTE FDD (Band 23)" | LTE | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/06/11
3924 | 470109 | Core part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America | S_Band_LTE_ATC_MSS-Core | 2 | Rel-10 | R4,R2 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-110775 | RP-110545 | DBSD | Mariam.Sorond@ico.com | RP#52 completed | 25.101, 25.104, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.141, new TR 36.811 | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/06/11
3925 | 470209 | Perf. part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America | S_Band_LTE_ATC_MSS-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-110775 | RP-110546 | DBSD | Mariam.Sorond@ico.com | RP#52 completed | 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.811 | 47 | 24 |  |  | Fri 19/03/10 | Wed 01/06/11
3926 | 520012 | Test part: Adding 2 GHz band LTE FDD (Band 23) for ATC of MSS in North America | S_Band_LTE_ATC_MSS-UEConTest | 2 | Rel-10 | R5 | 2011-06-07 08:00 | 2011-12-09 17:00 | 100% | RP-110623 | RP-111444 | DBSD | Mariam.Sorond@ico.com | RP#54 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 52 | 27 |  |  | Mon 23/05/11 | Tue 29/11/11
3927 | 470010 | Adding L-Band (Band 24) LTE for Ancillary Terrestrial Component (ATC) of Mobile Satellite Service (MSS) in North America | L_Band_LTE_ATC_MSS | 1 | Rel-10 | R4,R2,R5 | 2009-12-11 08:00 | 2011-09-16 17:00 | 100% | RP-101284 | - | LightSquared | Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com | RP#53 completed | LTE | 47 | 24 |  |  | Fri 19/03/10 | Tue 06/09/11
3928 | 470110 | Core part: Adding L-Band (Band 24) LTE for ATC of MSS in North America | L_Band_LTE_ATC_MSS-Core | 2 | Rel-10 | R4,R2 | 2009-12-11 08:00 | 2010-12-10 17:00 | 100% | RP-101284 | RP-101117 | LightSquared | Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com | RP#51 completed | 25.101, 25.104, 25.141, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.307, 37.104, 37.141, new RAN4 TR 36.813 | 47 | 24 |  |  | Fri 19/03/10 | Thu 17/03/11
3929 | 470210 | Perf. part: Adding L-Band (Band 24) LTE for ATC of MSS in North America | L_Band_LTE_ATC_MSS-Perf | 2 | Rel-10 | R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-101284 | RP-110548 | LightSquared | Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com | RP#52 completed | 34.121-1, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.521-1, 36.813 | 47 | 24 |  |  | Fri 19/03/10 | Tue 24/05/11
3930 | 510015 | Test part: Adding L-Band (Band 24) LTE for ATC of MSS in North America | L_Band_LTE_ATC_MSS-UEConTest | 2 | Rel-10 | R5 | 2011-03-18 08:00 | 2011-09-16 17:00 | 100% | RP-110777 | RP-110980 | LightSquared | masoud.olfat@lightsquared.com | RP#53 completed | 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-2 | 51 | 26 |  |  | Thu 10/03/11 | Tue 06/09/11
3931 | 470011 | LTE Self Optimizing Networks (SON) enhancements | SONenh_LTE | 1 | Rel-10 | R3,R2,R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-101004 | - | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#52 completed | LTE | 47 | 24 |  |  | Fri 19/03/10 | Tue 24/05/11
3932 | 470111 | Core part: LTE Self Optimizing Networks (SON) enhancements | SONenh_LTE-Core | 2 | Rel-10 | R3,R2,R4 | 2010-03-19 08:00 | 2011-06-03 17:00 | 100% | RP-101004 | RP-110547 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#52 completed (Stage 1,2,3) | 36.300, 36.331, 36.413, 36.423 | 47 | 24 |  |  | Fri 19/03/10 | Tue 24/05/11
3933 | 480027 | Further enhancements to MBMS for LTE | MBMS_LTE_enh | 1 | Rel-10 | R2,R3,R5 | 2010-06-04 08:00 | 2012-03-02 17:00 | 100% | RP-101244 | - | Huawei | Ms Zhao Junhui (zhaojh@huawei.com) | RP#51 completed. SA2 decided not to support MBR>GBR in Rel-10 MBMS. For SA2, MBR=GBR in Rel-10 MBMS. Hence RAN removed “enabling statistical multiplexing gains for variable bit rate services” in Objectives | LTE | 48 | 25 |  |  | Fri 04/06/10 | Mon 14/03/11
3934 | 480127 | Core part: Further enhancements to MBMS for LTE | MBMS_LTE_enh-Core | 2 | Rel-10 | R2,R3 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | RP-101244 | RP-110083 | Huawei | Ms Zhao Junhui (zhaojh@huawei.com) | RP#51 completed | 25.446, 36.300, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.443, 36.444, 36.445 | 48 | 25 |  |  | Fri 04/06/10 | Mon 14/03/11
3935 | 540008 | Test part: Further enhancements to MBMS for LTE | MBMS_LTE_enh-UEConTest | 2 | Rel-10 | R5 | 2011-12-02 08:00 | 2012-03-02 17:00 | 100% | RP-111615 | RP-120049 | Huawei | Zhang Xin (suzanna.zhang@huawei.com) | RP#55 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 54 | 28 |  |  | Thu 24/11/11 | Thu 23/02/12
3936 | 380173 | UMTS/LTE 3500 MHz | RInImp8-UMTSLTE3500 | 1 | Rel-10 | R4,R2,R3,R5 | 2007-11-30 08:00 | 2013-06-14 17:00 | 100% | RP-091380 | - | Ericsson | johan.skold@ericsson.com | - | UTRA, LTE | 38 | 21 |  |  | Mon 17/12/07 | Mon 03/06/13
3937 | 380073 | Core part: UMTS/LTE 3500 MHz | RInImp8-UMTSLTE3500 | 2 | Rel-10 | R4,R2,R3 | 2007-11-30 08:00 | 2011-09-16 17:00 | 100% | RP-091380 | RP-110987 | Ericsson | johan.skold@ericsson.com | RP#53 completed. TR 37.801v200 for Approval | 25.101, 25.104, 25.113, 25.133, 25.141, 25.307, 25.307, 25.331, 25.461, 25.463, 34.124, 36.101, 36.104, 36.113, 36.141, 36.331, new 37.801 | 38 | 21 |  |  | Mon 17/12/07 | Fri 09/09/11
3938 | 420013 | Conformance Test Aspects – LTE 3500 | LTE-UEConTest_LTE3500 | 2 | Rel-10 | R5 | 2008-12-05 08:00 | 2013-06-14 17:00 | 100% | RP-080859 | RP-130461 | Ericsson | fredrik.sundstrom@ericsson.com | RP#60 completed | 36.508, 36.521-1, 36.521-2, 36.521-3 | 42 | 22 |  |  | Thu 27/11/08 | Mon 03/06/13
3939 | 420014 | Conformance Test Aspects – UMTS 3500 | RInImp-UEConTest_UMTS3500 | 2 | Rel-10 | R5 | 2008-12-05 08:00 | 2012-06-15 17:00 | 100% | RP-110386 | RP-120450 | Ericsson | fredrik.sundstrom@ericsson.com | RP#56 completed | 34.108, 34.121-1, 34.121-2 | 42 | 22 |  |  | Thu 27/11/08 | Tue 05/06/12
3940 | 460003 | Minimization of Drive Tests for E-UTRAN and UTRAN | MDT_UMTSLTE | 1 | Rel-10 | R2,R4,R3,R5 | 2009-12-04 08:00 | 2013-03-01 17:00 | 100% | RP-100360 | - | Nokia Siemens Networks | malgorzata.tomala@nsn.com | Triggered by UID_430021 TR 36.805 (Study on Minimization of drive-tests in NGN) | UTRA, LTE | 46 | 24 |  |  | Mon 30/11/09 | Wed 27/02/13
3941 | 460103 | Core part: Minimization of Drive Tests for E-UTRAN and UTRAN | MDT_UMTSLTE-Core | 2 | Rel-10 | R2,R4,R3 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-100360 | RP-110528 | Nokia Siemens Networks | malgorzata.tomala@nsn.com | RP#52 completed | 25.133, 25.215, 25.304, 25.331, 25.423, 36.133, 36.214, 36.300, 36.304, 36.331, 36.413, 36.423, new 37.320 (Stage 2) | 46 | 24 |  |  | Mon 30/11/09 | Tue 24/05/11
3942 | 530041 | Test part: Minimization of Drive Tests for E-UTRAN | MDT_UMTSLTE-UEConTest | 2 | Rel-10 | R5 | 2011-09-19 08:00 | 2013-03-01 17:00 | 100% | RP-120598 | RP-130036 | Ericsson | leif.mattisson@ericsson.com | RP#59 completed. Testing for LTE only | LTE 34.108, 34.109, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3 | 53 | 27 |  |  | Tue 06/09/11 | Wed 27/02/13
3943 | 470005 | HNB and HeNB Mobility Enhancements | HNB_HENB_mob_enh | 1 | Rel-10 | R3,R2,R5 | 2010-03-19 08:00 | 2012-12-07 17:00 | 100% | RP-110183 | - | Alcatel-Lucent | Martin,Warner@alcatel-lucent.com | - | UTRA, LTE | 47 | 24 |  |  | Fri 19/03/10 | Fri 08/04/11
3944 | 470105 | Core part: HNB and HeNB Mobility Enhancements | HNB_HENB_mob_enh-Core | 2 | Rel-10 | R3,R2 | 2010-03-19 08:00 | 2011-03-18 17:00 | 100% | RP-110183 | RP-110058 | Alcatel-Lucent | Martin.Warner@alcatel-lucent.com | RP#51 completed | 25.413, 25.467, 25.469, 36.300, 36.413, 36.423, new 25.471 | 47 | 24 |  |  | Fri 19/03/10 | Fri 11/03/11
3945 | 550002 | Test part: HeNB Mobility Enhancements | HNB_HENB_mob_enh-UEConTest_LTE | 2 | Rel-10 | R5 | 2012-03-05 08:00 | 2012-12-07 17:00 | 100% | RP-120218 | RP-121533 | Qualcomm | Anjali Mishra (ajha@qualcom.com) | RP#58 completed | 34.108, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | 55 | 28 |  |  | Thu 23/02/12 | Tue 04/09/12
3946 | 480024 | Expanded 1900 MHz Band for UTRA and LTE | E1900 | 1 | Rel-10 | R4,R2,R5 | 2010-06-04 08:00 | 2012-09-07 17:00 | 100% | RP-100676 | - | Sprint | nick.j.baustert@sprint.com | Expand UTRA and E-UTRA band 2 to include frequencies between 1910 – 1915 MHz and 1990-1995 MHz (US FCC allocation) | UTRA, LTE | 48 | 25 |  |  | Fri 04/06/10 | Tue 04/09/12
3947 | 480124 | Core part: Expanded 1900 MHz Band for UTRA and LTE | E1900-Core | 2 | Rel-10 | R4,R2 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100676 | RP-110529 | Sprint | nick.j.baustert@sprint.com | RP#52 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, new TR 36.818 | 48 | 25 |  |  | Fri 04/06/10 | Tue 24/05/11
3948 | 480224 | Perf. part: Expanded 1900 MHz Band for UTRA and LTE | E1900-Perf | 2 | Rel-10 | R4,R2 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-100676 | RP-110530 | Sprint | nick.j.baustert@sprint.com | RP#52 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.461, 25.466, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.307, 36.331, new TR 36.818 | 48 | 25 |  |  | Fri 04/06/10 | Tue 24/05/11
3949 | 520013 | Test part: Expanded 1900 MHz Band for UTRA and LTE | E1900-UEConTest | 2 | Rel-10 | R5 | 2011-06-07 08:00 | 2012-09-07 17:00 | 100% | RP-110712 | RP-120957 | Sprint | nick.j.baustert@sprint.com | RP#57 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 52 | 27 |  |  | Mon 23/05/11 | Tue 04/09/12
3950 | 480025 | Multi-Standard Radio Base Station RF requirements for non-contiguous spectrum deployments | MSR_NC | 1 | Rel-10 | R4,G1 | 2010-06-04 08:00 | 2011-11-25 17:00 | 100% | RP-101402 | - | Ericsson | johan.skold@ericsson.com | - | UTRA, LTE, GERAN | 48 | 25 |  |  | Fri 04/06/10 | Mon 12/09/11
3951 | 480125 | Core part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-Core | 2 | Rel-10 | R4 | 2010-06-04 08:00 | 2011-06-03 17:00 | 100% | RP-101402 | RP-110531 | Ericsson | johan.skold@ericsson.com | RP#52 completed | 25.104, 36.104, 37.104, new TR 37.802 | 48 | 25 |  |  | Fri 04/06/10 | Wed 01/06/11
3952 | 480225 | Perf. part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-Perf | 2 | Rel-10 | R4 | 2010-06-04 08:00 | 2011-09-16 17:00 | 100% | RP-101402 | RP-110988 | Ericsson | johan.skold@ericsson.com | RP#53 completed | 25.141, 36.141, 37.141, 37.802 | 48 | 25 |  |  | Fri 04/06/10 | Mon 12/09/11
3953 | 490004 | GERAN part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-GERAN | 2 | Rel-10 | G1 | 2010-09-03 08:00 | 2011-11-25 17:00 | 100% | GP-101618 | - | Ericsson | mats.y.samuelsson@ericsson.com | - | - | 47 | 25 |  |  | Sun 05/09/10 | Sat 21/05/11
3954 | 490104 | GERAN Core part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-GERAN | 3 | Rel-10 | G1 | 2010-09-03 08:00 | 2011-09-02 17:00 | 100% | GP-101618 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#51 completed. GP#47 approved WID | 45.005 | 47 | 25 |  |  | Sun 05/09/10 | Sat 21/05/11
3955 | 540001 | GERAN BS Test part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments | MSR_NC-GERAN | 3 | Rel-10 | G1 | 2011-09-02 08:00 | 2011-11-25 17:00 | 100% | GP-101618 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#52 completed | 51.021 | 52 | 28 |  |  | Fri 25/11/11 | Fri 25/11/11
3956 | 440044 | (Small) Technical Enhancements and Improvements for Rel-10 | TEI10 | 1 | Rel-10 | SP,CP,RP,GP | 2009-06-04 08:00 | 2011-03-23 17:00 | 100% | - | - | - | - | - | - | 44 | 23 |  |  | Tue 02/06/09 | Mon 07/03/11
3957 | 521004 | (IETF) (Small) Technical Enhancements and Improvements for Rel-10 (RFC8464) | TEI10_IETF | 1 | Rel-10 | C1-IETF | 2009-06-04 08:00 | 2014-12-04 17:00 | 100% | - | - | Andrew Allen | Andrew Allen | Not completed internet-draft, waiting for draft-montemurro to complete | draft-atarius-dispatch-meid-urn | 52 | 27 |  |  | Mon 20/06/11 | Fri 06/12/13
3958 | 531001 | (IETF) (Small) Technical Enhancements and Improvements for Rel-10 (RFC6275) | TEI10_IETF1 | 1 | Rel-10 | C1-IETF | 2009-06-04 08:00 | 2011-07-29 17:00 | 100% | - | - | - | - | SP#53/IETF#81: RFC 6275 completed | RFC 6275 (was draft-ietf-mext-rfc3775bis) | 53 | 27 |  |  | Fri 29/07/11 | Wed 31/08/11
3959 | 540004 | Test - (Small) Technical Enhancements and Improvements for Rel-10 | TEI10_Test | 1 | Rel-10 | R5,G3new | 2011-12-01 08:00 | 2012-12-07 17:00 | 100% | - | - | n/a | - | - | - | 54 | 28 |  |  | Wed 30/11/11 | Thu 06/09/12
3960 | 350014 | Deleted - Registration in Densely-populated area (RED) | RED | 1 | Rel-10 | S1 | 2007-03-12 08:00 | 2009-09-24 17:00 | 100% | SP-070133 | - | NTT DoCoMo | tanakai@nttdocomo.co.jp | SP#35 Stage 1 completed. SP#45 Stage 2 work stopped. SP#46 work stopped/abandoned | - | 35 | - | SP-46 | PCG-24 | Thu 29/03/07 | Mon 07/12/09
3961 | 370030 | Deleted - Stage 1 for RED | RED | 2 | Rel-10 | S1 | 2007-03-12 08:00 | 2007-03-15 17:00 | 100% | SP-070133 | - | NTT DoCoMo | takakurat@s1.nttdocomo.co.jp | SP#35 completed. SP#46 work stopped/abandoned | 22.101 CR#0207 | 35 |  | SP-46 | PCG-24 | Thu 29/03/07 | Mon 07/12/09
3962 | 370031 | Deleted - Stage 2 for RED | RED | 2 | Rel-10 | S2 | 2007-09-25 08:00 | 2009-09-24 17:00 | 100% | SP-070694 | - | NTT DoCoMo | tanakai@nttdocomo.co.jp | SP#45 Stage 2 work stopped | draft TR 23.880 withdrawn, 23.002, 23.060, 23.221, 23.236 | 37 |  | SP-45 | PCG-23 | Tue 25/09/07 | Tue 08/09/09
3963 | 380062 | Deleted - Network Selection for non-3GPP Access | N3GtoNSP | 1 | Rel-10 | S1,C6 | 2007-12-07 08:00 | 2009-09-24 17:00 | 100% | SP-070874 | - | Telefónica O2 | chris.friel@O2.com | SP#45 work stopped/abandoned | - | 38 | 21 | SP-45 | PCG-23 | Thu 13/12/07 | Mon 21/09/09
3964 | 380162 | Deleted - Stage 1 for N3GtoNSP | N3GtoNSP | 2 | Rel-10 | S1 | 2007-12-07 08:00 | 2009-09-24 17:00 | 100% | SP-070874 | - | Telefónica O2 | chris.friel@O2.com | SP#45 work stopped/abandoned | 22.011 | 38 | 21 | SP-45 | PCG-23 | Thu 13/12/07 | Mon 21/09/09
3965 | 380262 | Deleted - CT6 issues for N3GtoNSP | N3GtoNSP | 2 | Rel-10 | C6 | 2007-12-07 08:00 | 2009-09-24 17:00 | 100% | SP-070874 | - | Telefónica O2 | chris.friel@O2.com | SP#45 work stopped/abandoned | 36.300 | 38 | 21 | CP-45 | PCG-23 | Thu 13/12/07 | Mon 21/09/09
3966 | 420025 | Deleted - GTP-based S8 chaining | GTPchaining | 1 | Rel-10 | S2 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-080798 | - | Huawei | Haining Wang (wanghaining@huawei.com) | SP#47 work stopped (depending on ongoing related CT4 work). Stage 1 in UID_320022 Rel-8 Requirements for evolution of the 3GPP system architecture (AIPN-SAE): 22.278, 22.011, 22.246 | - | 42 | 22 | SP-47 | PCG-24 | Fri 05/12/08 | Sun 07/03/10
3967 | 420026 | Deleted - Stage 2 for GTPchaining | GTPchaining | 2 | Rel-10 | S2 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-080798 | - | Huawei | Haining Wang (wanghaining@huawei.com) | SP#47 work stopped | 23.402 | 42 | 22 | SP-47 | PCG-24 | Fri 05/12/08 | Sun 07/03/10
3968 | 430017 | Deleted - UTRAN 2 ms TTI uplink range improvement | RANimp-2mTTI_ULimp | 1 | Rel-10 | R1,R2,R3,R4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-090333 | RP-100040 | Nokia Siemens Networks | Karri Ranta-aho (karri.ranta-aho@nsn.com) | RP#47 work stopped/abandoned (no CR approved). Cell sets the TTI (Transmission Time Interval) to 2 ms | 25.133, 25.212, 25.214, 25.321, 25.331 | 43 | 22 | RP-47 | PCG-24 | Wed 07/10/09 | Tue 16/03/10
3969 | 440043 | Deleted - Enhanced Home NodeB / eNodeB continuation of Rel-9 | eEHNB | 1 | Rel-10 | S2 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | - | - | Alcatel-Lucent | Nicolas Drevon | SP#47 deleted (SA2 work moved under SA1 UID_450053). SP#44 Umbrella Feature created to host WIs moved out of Rel-9 (SA2 UID_420034 on IMS aspects of Architecture for Home NodeB) | - | 44 | 23 | SP-47 | PCG-24 | Thu 13/12/07 | Mon 01/06/09
3970 | 460010 | Deleted - Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements | FW_CPE_RF | 1 | Rel-10 | R4,R5 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-091432 | - | Verizon Wireless | zheng.zhao@verizonwireless.com | RP#52 work stopped (lack of contributions). Add new power classES in CP-150E-UTRAN UL to allow CPE type applications to be operated at higher max output power | LTE | 46 | 24 | RP-52 | PCG-27 | Mon 30/11/09 | Fri 27/05/11
3971 | 460110 | Deleted - Core part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements | FW_CPE_RF-Core | 2 | Rel-10 | R4 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-091432 | RP-110539 | Verizon Wireless | zheng.zhao@verizonwireless.com | RP#52 work stopped at 55% (lack of contributions) | 36.101 | 46 | 24 | RP-52 | PCG-27 | Mon 30/11/09 | Wed 16/03/11
3972 | 460210 | Deleted - Test part: Fixed Wireless Customer-Premises Equipment (CPE) RF Requirements | FW_CPE_RF-UEConTest | 2 | Rel-10 | R5 | 2009-12-04 08:00 | 2011-06-03 17:00 | 100% | RP-091432 | RP-110504 | Verizon Wireless | zheng.zhao@verizonwireless.com | RP#52 work stopped (lack of contributions) | 36.521-1 | 46 | 24 | RP-52 | PCG-27 | Mon 30/11/09 | Fri 27/05/11
3973 | 460012 | Deleted - Latency reductions for LTE | LTE_LATRED | 1 | Rel-10 | R2,R1 | 2009-12-04 08:00 | 2010-12-10 17:00 | 100% | RP-091449 | - | Ericsson | henrik.enbuske@ericsson.com | RP#50 work stopped (RP-101266) | LTE | 46 | 24 | RP-50 | PCG-26 | Mon 30/11/09 | Wed 08/12/10
3974 | 460112 | Deleted - Core part: Latency reductions for LTE | LTE_LATRED-Core | 2 | Rel-10 | R2,R1 | 2009-12-04 08:00 | 2010-12-10 17:00 | 100% | RP-091449 | RP-101112 | Ericsson | henrik.enbuske@ericsson.com | RP#50 work stopped (RP-101266) | 36.213, 36.300, 36.306, 36.321, 36.331 | 46 | 24 | RP-50 | PCG-26 | Mon 30/11/09 | Wed 08/12/10
3975 | 470006 | Deleted - Enhanced Interference Management for Home NodeBs | HNB_IM | 1 | Rel-10 | R3 | 2010-03-19 08:00 | 2010-09-17 17:00 | 100% | RP-100392 | RP-100754 | Qualcomm | Andrei Radulescu (aradules@qualcomm.com) | RP#49 stopped (no further standardization needed). Ensure that Enhanced Interference Management methods identified in Rel-9 for HNBs do not fail in deployments with a large penetration of CSG-aware UEs | UTRA | 47 | 24 | RP-49 | PCG-25 | Fri 19/03/10 | Thu 09/09/10
3976 | 470106 | Deleted - Core part: Enhanced Interference Management for Home NodeBs | HNB_IM-Core | 2 | Rel-10 | R3 | 2010-03-19 08:00 | 2010-09-17 17:00 | 100% | RP-100392 | RP-100754 | Qualcomm | Andrei Radulescu (aradules@qualcomm.com) | RP#49 stopped (no further standardization needed) | 25.413, 25.467, 25.469 | 47 | 24 | RP-49 | PCG-25 | Fri 19/03/10 | Thu 09/09/10
3977 | 0 | Release 10 Studies | - | 1 | Rel-10 | CP,GP,RP,SP | 2009-03-12 08:00 | 2009-03-12 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 09/02/10
3978 | 370045 | Study on enhanced voice service requirements for the Evolved Packet System (EPS) | FS_EV_EPS | 1 | Rel-10 | S1,S4 | 2007-09-03 08:00 | 2010-03-25 17:00 | 100% | SP-070698 | - | France Telecom | philippe.lottin@orange.com | SP#47 completed. TR 22.813-100 for Approval. Spin-off Feature UID_470030 Codec for Enhanced Voice Services | 22.813 | 37 |  |  |  | Tue 02/10/07 | Tue 31/08/10
3979 | 370047 | Use cases definition and service and system requirements | FS_EV_EPS-S1 | 2 | Rel-10 | S1 | 2007-09-03 08:00 | 2008-12-11 17:00 | 100% | SP-070698 | - | France Telecom | philippe.lottin@orange.com | SP#47 completed. TR 22.813-100 for Approval | 22.813 | 37 |  |  |  | Thu 04/10/07 | Tue 31/08/10
3980 | 370048 | Codec specific part of FS_EV_EPS | FS_EV_EPS-S4 | 2 | Rel-10 | S4 | 2007-09-03 08:00 | 2010-03-25 17:00 | 100% | SP-070698 | - | Ericsson | stefan.bruhn@ericson.com | SP#47 completed. TR 22.813-100 for Approval | 22.813 | 37 |  |  |  | Thu 04/10/07 | Mon 01/02/10
3981 | 380083 | Study on advanced requirements for IP interconnect | FS_IPXS | 1 | Rel-10 | S1 | 2007-12-04 08:00 | 2009-12-10 17:00 | 100% | SP-070878 | - | Telefónica O2 | chris.friel@O2.com | SP#46 completed. Linked to Rel-8 Feature UID_380060 IP Interconnection of Services (IPinterc). Spin-off Feature Rel-11 UID_470051 Advanced IP Interconnection of Services | 22.893 | 38 | 21 |  |  | Thu 20/12/07 | Wed 11/08/10
3982 | 410039 | Study on Personal Broadcast Service | FS_PBS | 1 | Rel-10 | S1 | 2008-09-18 08:00 | 2010-03-25 17:00 | 100% | SP-080504 | - | ETRI | Jaihyung Cho | SP#47 completed | 22.947 | 41 | 21 |  |  | Mon 15/09/08 | Tue 09/03/10
3983 | 410040 | Study on LCS support in SAE for non-3GPP accesses | FS_LCS_n3GPP | 1 | Rel-10 | S1 | 2008-09-18 08:00 | 2010-03-25 17:00 | 100% | SP-080648 | - | SK Telecom | jinhan.song@sktelecom.com | SP#47 completed | 22.814 | 41 | 21 |  |  | Mon 15/09/08 | Wed 11/08/10
3984 | 430030 | Study on Haptic Services | FS_Haptics | 1 | Rel-10 | S1 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090664 | - | SK Telecom | jinhan.song@sktelecom.com | SP#47 completed. Covers Mobile/Fixed/Cordless/etc terminals. Haptic (human-machine tactile communication) extend service offering & richness of user experience beyond current visual & auditory senses | 22.987 | 43 | 22 |  |  | Thu 12/02/09 | Wed 11/08/10
3985 | 370050 | Study on System enhancements for the use of IMS services in Local BreakOut and Optimal Routing of Media | FS_IMS_LBO_ORM | 1 | Rel-10 | S2 | 2007-10-01 08:00 | 2009-12-10 17:00 | 100% | SP-080556 | - | Telecom Italia, BT | mario.madella@telecomitalia.it, victor.kueh@bt.com | SP#46 completed. Spin-off Feature UID_460028 Optimal Media Routeing (OMR). Linked to Study on Multimedia Session Continuity UID_350051, Study on Centralized IMS Service Control UID_330012, IMS inter-operator service interconnection interface UID_360011 | 23.894 | 37 |  |  |  | Tue 02/10/07 | Wed 25/11/09
3986 | 390055 | Study on Intra Domain Connection of RAN Nodes to Multiple CN Nodes | FS_IDC | 1 | Rel-10 | S2 | 2008-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-080094 | - | China Mobile | LIU HONG (liuhongyfw@chinamobile.com) | SP#47 completed. Concluded no further normative work expected. Linked to 23.236 | 23.924 (was 23.823) | 39 | 21 |  |  | Thu 20/12/07 | Tue 23/03/10
3987 | 440049 | Study on Single Radio Voice Call Continuity enhancements | FS_eSRVCC | 1 | Rel-10 | S2 | 2009-06-04 08:00 | 2010-09-23 17:00 | 100% | SP-090363 | - | China Mobile | Hou zhiqiang (houzhiqiang@chinamobile.com), Jiang Yi (jiangyi@chinamobile.com) | SP#49 completed (Conclusion: select the SIP anchoring based solution for normative work CR (TEI10) introducing and completing stage-2). Analyzed performance of Rel-8 SRVCC solution from E-UTRAN/HSPA to UTRAN/GERAN | 23.856 | 44 | 23 |  |  | Sun 31/05/09 | Mon 06/09/10
3988 | 470048 | Study on Single Radio Video Call Continuity for 3G-CS | FS_vSRVCC | 1 | Rel-10 | S2 | 2010-03-25 08:00 | 2010-09-23 17:00 | 100% | SP-100168 | - | Samsung | Haris Zisimopoulos (haris.z@samsung.com) | SP#49 completed. TR 23.886v100 for Approval. Related to Rel-8 UID_350030 Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC). Study how to provide Video Call seamless service continuity for 3G/LTE terminal user | 23.886 | 47 | 24 |  |  | Wed 10/03/10 | Wed 15/09/10
3989 | 470049 | Study on S2b Mobility based on GTP | FS_SMOG | 1 | Rel-10 | S2 | 2010-03-25 08:00 | 2010-06-10 17:00 | 100% | SP-100169 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.com | SP#48 completed. Triggered by Rel-8 UID_350027 SAE for support for non-3GPP accesses. Nature of relationship: S2b one of the interfaces defined for non-3GPP accesses support in EPS. Stage 1 in Rel-8 UID_320022 (AIPN-SAE) 22.278,22.101 | 23.834 | 47 | 24 |  |  | Wed 10/03/10 | Mon 07/06/10
3990 | 430040 | Study on Surround Sound codec extension for PSS and MBMS | FS_SS_PSS_MBMS | 1 | Rel-10 | S4 | 2009-03-12 08:00 | 2011-03-23 17:00 | 100% | SP-090019 | - | Fraunhofer Gesellschaft | jan.plogsties@iis.franhofer.de | SP#51 completed. Extend Rel-8 UID_34043 (Extending PSS and MBMS User Services for optimized Mobile TV) | 26.950 | 43 | 22 |  |  | Mon 02/02/09 | Mon 14/02/11
3991 | 480044 | Study on Improved Video Coding Support | FS_IVCS | 1 | Rel-10 | S4 | 2010-06-10 08:00 | 2011-03-23 17:00 | 100% | SP-100304 | - | Nokia, ETRI | imed.bouazizi@nokia.com, jaihyung@etri.re.kr | SP#51 completed. Extends Rel-9 Improved Video Support for PSS and MBMS (UID_430039) | 26.904 | 48 | 25 |  |  | Fri 28/05/10 | Fri 18/02/11
3992 | 410044 | Study on Rc Reference Point Functionalities and Message Flows | FS_OAM_Rc | 1 | Rel-10 | S5 | 2008-09-18 08:00 | 2010-03-25 17:00 | 100% | SP-080464 | - | Huawei | shan.mingjun@huawei.com | SP#47 completed | 32.825 | 41 | 21 |  |  | Mon 15/09/08 | Tue 23/03/10
3993 | 430044 | Study on Telecommunication Management; Energy Savings Management | FS_OAM_ESM | 1 | Rel-10 | S5 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090048 | - | Orange, Vodafone | Jean-Michel Cornilly (Orange) | SP#47 completed. Study result might impact Feature UID_420011 Self Organising Networks (SON) | 32.826 | 43 | 22 |  |  | Mon 23/02/09 | Mon 08/03/10
3994 | 440069 | Study on Integration of Device Management Information with Itf-N | FS_IDMI_Itf-N | 1 | Rel-10 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-100088 | - | Motorola | Yizhi Yao (yzyao@motorola.com) | SP#47 completed | 32.827 | 44 | 23 |  |  | Mon 18/05/09 | Tue 23/03/10
3995 | 460037 | Study on Alignment of 3GPP Generic NRM IRP and TMF Shared Information Data (SID) model | FS_3GNRM_TMFSID | 1 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-03-23 17:00 | 100% | SP-090759 | - | Nokia Siemens Networks | olaf.pollakowski@nsn.com | SP#51 completed | 32.828 | 46 | 24 |  |  | Tue 01/12/09 | Wed 09/03/11
3996 | 460038 | Study on Harmonization of 3GPP Alarm IRP and TMF Interface Program (TIP) Fault Management | FS_3G_TMF_FM | 1 | Rel-10 | S5 | 2009-12-10 08:00 | 2011-03-23 17:00 | 100% | SP-090760 | - | Nokia Siemens Networks, Alcatel-Lucent | olaf.pollakowski@nsn.com, Padma.Sudarsan@alcatel-lucent.com | SP#51 completed | 32.829 | 46 | 24 |  |  | Tue 01/12/09 | Tue 22/03/11
3997 | 480045 | Study on Alarm Correlation and Alarm Root Cause Analysis | FS_AC_ARCA | 1 | Rel-10 | S5 | 2010-06-10 08:00 | 2011-03-23 17:00 | 100% | SP-100775 | - | Ericsson | edwin.tse@ericsson.com | SP#51 completed | 32.832 | 48 | 25 |  |  | Wed 26/05/10 | Wed 09/03/11
3998 | 480046 | Study on Alignment of 3GPP PM IRP and TMF Interface Program (TIP) PM | FS_3G_TMF_PM | 1 | Rel-10 | S5 | 2010-06-10 08:00 | 2011-03-23 17:00 | 100% | SP-100291 | - | Alcatel-Lucent | Padma.Sudarsan@alcatel-lucent.com | SP#51 completed | 32.831 | 48 | 25 |  |  | Wed 26/05/10 | Tue 22/03/11
3999 | 450013 | Study on Policy and Charging Rules Function (PCRF) failure and restoration | FS_PCRF-FR | 1 | Rel-10 | C3 | 2009-08-18 13:48 | 2010-09-17 17:00 | 100% | CP-090861 | - | NEC | gottfried.punz@nw.neclab.eu | CP#49 completed | 29.816 | 45 | 23 |  |  | Tue 08/09/09 | Fri 17/09/10
4000 | 480016 | Study on User Data Convergence (UDC) evolution | FS_UDCe | 1 | Rel-10 | C4 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100296 | - | Alcatel-Lucent | jean-jacques.trottin@alcatel-lucent.com | CP#51 completed. Study UDC evolution from FeaturES in CP-150Rel-9 UID_400034 and Rel-10 UID_480011 UDC Data Model | 23.845 | 48 | 25 |  |  | Wed 26/05/10 | Mon 28/02/11
4001 | 480017 | Study on UICC access to IMS | FS_IMS-UICC | 1 | Rel-10 | C6 | 2010-06-04 08:00 | 2011-03-18 17:00 | 100% | CP-100424 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#51 completed | 31.828 | 48 | 25 |  |  | Wed 26/05/10 | Thu 03/03/11
4002 | 450014 | Study on Uplink Tx Diversity for HSPA | FS_UL-TxDiv-HSPA | 1 | Rel-10 | R4 | 2009-08-18 13:48 | 2010-06-04 17:00 | 100% | RP-090987 | RP-100499 | Qualcomm | Heechoon Lee (heechoon@qualcomm.com) | RP#48 completed | UTRA 25.863 | 45 | 23 |  |  | Tue 15/09/09 | Tue 01/06/10
4003 | 460016 | Study on Solutions for Energy Saving within UTRA Node B | FS_Energy_UMTS | 1 | Rel-10 | R1,R3 | 2009-12-04 08:00 | 2010-09-17 17:00 | 100% | RP-091439 | RP-100796 | Vodafone | Prakash.bhat@vodafone.com | RP#49 completed. Based on ETSI EE TS 102 706. | UTRA 25.927 | 46 | 24 |  |  | Mon 30/11/09 | Thu 09/09/10
4004 | 470015 | Study on Potential solutions for energy saving for E-UTRAN | FS_Energy_LTE | 1 | Rel-10 | R3,R2 | 2010-02-02 10:00 | 2011-06-03 17:00 | 100% | RP-100674 | RP-110597 | China Mobile | Yang Ning (yangning@chinamobile.com) | RP#52 completed | LTE 36.927 | 47 | 24 |  |  | Fri 19/03/10 | Thu 02/06/11
4005 | 470016 | Study on Improvements of distributed antenna for 1.28Mcps TDD | FS_distr_ant_LCR_TDD | 1 | Rel-10 | R1,R2,R3 | 2010-03-05 11:36 | 2010-12-10 17:00 | 100% | RP-100178 | RP-101287 | ZTE | huang.he4@zte.com.cn | RP#50 completed. TR 25.865 v101 for Approval | UTRA 25.865 | 47 | 24 |  |  | Fri 19/03/10 | Tue 07/12/10
4006 | 400037 | Deleted - Study on Unauthenticated PS Emergency Calls | FS_UAPSEC | 1 | Rel-10 | S1 | 2008-06-05 08:00 | 2010-03-25 17:00 | 100% | SP-080320 | - | Nokia Siemens Networks | Juergen.Merkel@nsn.com | SP#47 work stopped/abandoned | 22.984 | 40 | 21 | SP-47 | PCG-24 | Thu 13/12/07 | Tue 09/03/10
4007 | 410042 | Deleted - Study on enhancements to IMS border functions for IMS Interconnection of services | FS_eIMS_IBCF | 1 | Rel-10 | S2 | 2008-09-18 08:00 | 2010-12-15 17:00 | 100% | SP-090809 | - | Starent Networks | Rajat Ghai (rghai@starentnetworks.com) | SP#50 work stopped. Additional work may be addressed as part of the Rel-11 Feature UID_470051 Advanced IP Interconnection of Services (IPXS) | 23.848 | 41 | 21 | SP-50 | PCG-26 | Mon 15/09/08 | Mon 13/12/10
4008 | 440050 | Deleted - Study on EPC Charging enhancement | FS_EPCcharg | 1 | Rel-10 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090318 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#47 work stopped. Issue covered by Rel-10 UID_460039 Charging for LIPA_SIPTO and UID_4700xy Charging for IFOM | - | 44 | 23 | SP-47 | PCG-24 | Mon 18/05/09 | Mon 06/07/09
4009 | 450012 | Deleted - Study on Interworking Proxy between GTP based and PMIP based interfaces | FS_GTP-MIP-IW | 1 | Rel-10 | C4 | 2009-09-18 08:00 | 2010-06-04 17:00 | 100% | CP-090517 | - | NTT DoCoMo | takaaki.matsuura.sp@s1.nttdocomo.com | CP#48 work stopped/abandoned | 29.875 | 45 | 23 | CP-48 | PCG-25 | Tue 08/09/09 | Wed 26/05/10
4010 | 0 | Release 9 Features | - | 1 | Rel-9 | CP,GP,RP,SP | 2000-01-01 08:00 | 2000-01-01 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/05/06 | Tue 09/02/10
4011 | 400035 | Enhanced Home NodeB / eNodeB | EHNB | 1 | Rel-9 | S1,S2,S3,S5,C1,C6,R2,R3,R4,R5,GP | 2008-06-05 08:00 | 2011-12-09 17:00 | 100% | SP-090214 | - | T-Mobile | michael.kurz@t-mobile.at | RP#54 Testing completed | UTRA, LTE | 40 | 21 |  |  | Thu 13/12/07 | Tue 29/11/11
4012 | 400047 | Stage 1 for EHNB | EHNB | 2 | Rel-9 | S1 | 2008-06-05 08:00 | 2009-06-04 17:00 | 100% | SP-080791 | - | T-Mobile | michael.kurz@t-mobile.at | CP#49 the SA1-reqs are moving. CT1 will align when the work in SA1 is clear. (was SP#44 completed.) | 22.220, 22.011 | 40 | 21 |  |  | Thu 13/12/07 | Mon 06/09/10
4013 | 410026 | Architecture aspects of EHNB | EHNB | 2 | Rel-9 | S2 | 2008-09-18 08:00 | 2009-09-24 17:00 | 100% | SP-080636 | - | T-Mobile | sebastian.speicher@telekom.de | SP#45 completed | 23.401, 23.402, 23.060, New 23.830 | 41 | 21 |  |  | Mon 15/09/08 | Wed 14/10/09
4014 | 420035 | Security aspects of Enhanced Home NodeB / eNodeB | EHNB-Sec | 2 | Rel-9 | S3 | 2008-12-11 08:00 | 2009-12-10 17:00 | 100% | SP-080879 | - | Huawei | Marcus Wong (mwong@huawei.com) | SP#46 completed | New 33.320 | 42 | 22 |  |  | Tue 09/12/08 | Mon 07/12/09
4015 | 450003 | CT1 aspects - Support of Home NB and Home eNB enhancements | EHNB-CT1 | 2 | Rel-9 | C1 | 2009-09-18 08:00 | 2010-12-10 17:00 | 100% | CP-090741 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#50 completed (Roaming aspects for manual CSG selection, Support of temporary users and CSG membership changes, Support of user controlled and operator controlled lists) | 23.122, 24.008, 24.285, 24.301 | 45 | 23 |  |  | Thu 09/07/09 | Thu 25/11/10
4016 | 450004 | CT6 aspects - Support of Home NB and Home eNB enhancements | EHNB-CT6 | 2 | Rel-9 | C6 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090741 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#47 completed. Storing of CSG related data items on the USIM | 31.102 | 45 | 23 |  |  | Thu 09/07/09 | Tue 16/03/10
4017 | 420036 | 3G HNB Gateway and LTE HeNB Gateway OAM&P | HNB-OAM_GW | 2 | Rel-9 | S5 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-100087 | - | China Mobile | GangChen (chengang@chinamobile.com) | SP#47 completed | 32.632, 32.633, 32.635, New (32.771, 32.772, 32.773, 32.775, 32.781, 32.782, 32.783, 32.785) | 42 | 22 |  |  | Wed 03/12/08 | Mon 22/03/10
4018 | 430012 | 3G HNB and LTE HeNB OAM&P Type 1 Interface | HNB_eHNB-OAM_Type1 | 2 | Rel-9 | S5 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090208 | - | Huawei | Zou Lan (zlan@huawei.com) | SP#47 completed | 32.581, 32.582, 32.583, 32.584, New (32.591, 32.592, 32.593, 32.594) | 43 | 22 |  |  | Mon 09/03/09 | Mon 08/03/10
4019 | 440066 | 3G HNB and LTE HeNB OAM&P Type 2 Interface | HNB_eHNB-OAM_Type2 | 2 | Rel-9 | S5 | 2009-05-15 08:00 | 2010-03-25 17:00 | 100% | SP-090315 | - | Ericsson | edwin.tse@ericsson.com | SP#47 completed | New (32.571, 32.572) | 44 | 23 |  |  | Mon 18/05/09 | Mon 08/03/10
4020 | 420008 | LTE FDD Home eNodeB RF Requirements | HeNB-RF_FDD | 2 | Rel-9 | R4 | 2008-12-05 08:00 | 2010-03-19 17:00 | 100% | RP-091300 | RP-100035 | Motorola | Ying Cai (yingcai@motorola.com) | RP#47 completed | 36.104, 36.141, New TR 36.921 | 42 | 22 |  |  | Thu 04/12/08 | Tue 16/03/10
4021 | 430005 | LTE TDD Home eNodeB RF Requirements | HeNB-RF_TDD | 2 | Rel-9 | R4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-091386 | RP-100036 | China Mobile | Nan Li (linan@chinamobile.com) | RP#47 completed | 36.104, 36.141, 36.300, 36.331, 36.413, New TR 36.922 | 43 | 22 |  |  | Tue 03/03/09 | Tue 16/03/10
4022 | 430025 | Home NB and Home eNB enhancements - RAN3 aspects | EHNB-RAN3 | 2 | Rel-9 | R3 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090349 | RP-091050 | Alcatel-Lucent | Martin Warner (mw15@alcatel-lucent.com) | RP#46 completed (based on high priority items specified in RP-090995) | 25.413, 25.467, 25.467, 25.468, 25.469, 25.469, 36.401, 36.413, New 25.444 | 43 | 22 |  |  | Tue 10/03/09 | Fri 27/11/09
4023 | 430026 | Home NB and Home eNB enhancements - RAN2 aspects | EHNB-RAN2 | 2 | Rel-9 | R2 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-091392 | RP-100037 | Huawei | Yang Xudong (yangxudong@huawei.com) | RP#47 completed | 25.304, 25.331, 25.367, 36.300, 36.304, 36.331 | 43 | 22 |  |  | Tue 10/03/09 | Tue 16/03/10
4024 | 490020 | Conformance Test Aspects – Home NB enhancements for FDD | EHNB-UTRA_FDD_UEConTest | 2 | Rel-9 | R5 | 2010-09-17 08:00 | 2011-12-09 17:00 | 100% | RP-111315 | RP-111679 | Huawei | trica_li@huawei.com | UTRA. RP#54 completed. Testing for UID_430026 Support of Home NB and Home eNB enhancements RAN2 aspects (25.304, 25.331, 25.367) | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 49 | 25 |  |  | Thu 09/09/10 | Wed 07/12/11
4025 | 500023 | Conformance Test Aspects – Home eNB enhancements | EHNB-LTE_UEConTest | 2 | Rel-9 | R5 | 2010-12-10 08:00 | 2011-09-16 17:00 | 100% | RP-101191 | RP-110972 | Qualcomm | Mrs Lena Chaponniere (lchaponn@qualcomm.com) | RP#53 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 50 | 26 |  |  | Fri 10/12/10 | Tue 06/09/11
4026 | 440001 | Home NB and Home eNB enhancements - GERAN aspects | EHNB-GERAN | 2 | Rel-9 | GP | 2009-05-18 08:00 | 2010-09-03 17:00 | 100% | GP-090975 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#47 completed. GP#42 WID approved | 43.055, 43.129, 44.018, 44.060, 45.008, 48.008, 48.018 | 42 | 23 |  |  | Mon 18/05/09 | Sat 04/09/10
4027 | 370026 | Value-Added Services for Short Message Service | VAS4SMS | 1 | Rel-9 | S1,C4,C1 | 2007-09-10 08:00 | 2009-12-04 17:00 | 100% | SP-070572 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | CP#46 completed | - | 37 |  |  |  | Tue 02/10/07 | Mon 16/11/09
4028 | 370126 | Stage 1 for VAS4SMS | VAS4SMS | 2 | Rel-9 | S1 | 2007-09-10 08:00 | 2008-03-12 17:00 | 100% | SP-070572 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | SP#39 completed. SP#43 Feature moved to Rel-9 | new 22.142 | 37 |  |  |  | Tue 02/10/07 | Wed 04/03/09
4029 | 410011 | CT4 aspects of VAS4SMS Interface and Signalling Flow | VAS4SMS | 2 | Rel-9 | C4 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | CP-090813 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | CP#46 completed | new 23.142 | 41 | 21 |  |  | Thu 11/09/08 | Wed 02/12/09
4030 | 410014 | CT1 aspects of VAS4SMS Interface and Signalling Flow | VAS4SMS | 2 | Rel-9 | C1 | 2008-09-09 14:36 | 2009-12-04 17:00 | 100% | CP-090813 | - | China Mobile | Wu Bin (wubin@chinamobile.com) | CP#46 completed | 23.040 | 41 | 21 |  |  | Thu 11/09/08 | Wed 02/12/09
4031 | 370027 | Definition of End-User Identity | EUI | 1 | Rel-9 | S1 | 2007-09-03 08:00 | 2008-12-11 17:00 | 100% | SP-090380 | - | Nokia Siemens Networks | Juergen.Merkel@nsn.com | SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905) | - | 38 |  |  |  | Tue 02/10/07 | Thu 05/08/10
4032 | 410024 | Stage 1 for Definition of End-User Identity | EUI | 2 | Rel-9 | S1 | 2007-09-03 08:00 | 2008-12-11 17:00 | 100% | SP-090380 | - | Nokia Siemens Networks | Juergen.Merkel@nsn.com | SP#42 closed. Stage 1 work closed at 5% completion due to lack of input (added only the EUI definition in 21.905) | 21.905 | 38 | 21 |  |  | Tue 02/10/07 | Thu 11/06/09
4033 | 380067 | Customized Ringing Signal | CRS | 1 | Rel-9 | S1,C1 | 2007-12-06 08:00 | 2009-12-03 17:00 | 100% | SP-080502 | - | SK Telecom, China Mobile | Donghee Shim (SK Telecom), Jianping Zheng (China Mobile) | CP#48 completed | - | 38 | 21 |  |  | Thu 13/12/07 | Fri 28/05/10
4034 | 410025 | Stage 1 for Customized Ringing Signal | CRS | 2 | Rel-9 | S1 | 2007-12-06 08:00 | 2008-12-11 17:00 | 100% | SP-080502 | - | SK Telecom, China Mobile | Donghee Shim (SK Telecom), Jianping Zheng (China Mobile) | SP#42 completed. | 22.173, new 22.183 | 38 | 21 |  |  | Thu 13/12/07 | Fri 05/12/08
4035 | 440041 | Stage 3 for IMS Customized Ringing Signal (CRS) Service | CRS | 2 | Rel-9 | C1 | 2009-05-29 08:00 | 2009-12-03 17:00 | 100% | CP-090444 | - | China Mobile | wangzhao | CP#48 completed | 24.173, new 24.183 | 44 | 23 |  |  | Wed 13/05/09 | Fri 28/05/10
4036 | 380057 | Public Warning System | PWS | 1 | Rel-9 | S1,C1,C4,R2,R3,R5 | 2007-12-06 08:00 | 2012-12-07 17:00 | 100% | SP-070876 | - | T-Mobile | Mark.Younge@t-mobile.com | TSG#46 completed. Larger scope than Rel-8 Feature UID_370051 (ETWS). Triggered by TR 22.968 Study UID_320025 (FS_PWS) | LTE | 38 | 21 |  |  | Thu 13/12/07 | Thu 03/12/09
4037 | 380058 | Stage 1 for Public Warning System | PWS | 2 | Rel-9 | S1 | 2007-12-06 08:00 | 2008-12-11 17:00 | 100% | SP-070876 | - | T-Mobile | Mark.Younge@t-mobile.com | SP#42 completed | 22.268 | 38 | 21 |  |  | Thu 13/12/07 | Fri 05/12/08
4038 | 440029 | Stage 3 for Public Warning System | PWS-St3 | 2 | Rel-9 | C1,C4 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090437 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | RP#46 completed | - | 44 | 23 |  |  | Wed 13/05/09 | Thu 03/12/09
4039 | 440030 | CT1 aspects of Stage 3 for Public Warning System | PWS-St3 | 3 | Rel-9 | C1 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090437 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#46 completed | 23.041 | 44 | 23 |  |  | Wed 13/05/09 | Thu 03/12/09
4040 | 440031 | CT4 aspects of Stage 3 for Public Warning System | PWS-St3 | 3 | Rel-9 | C4 | 2009-05-30 08:00 | 2009-12-04 17:00 | 100% | CP-090437 | - | Qualcomm | Ramachandran Subramanian (rsubrama@qualcomm.com) | CP#46 completed | 29.168 | 44 | 23 |  |  | Wed 13/05/09 | Thu 03/12/09
4041 | 440005 | Public Warning System (PWS) – RAN aspects | PWS-RAN | 2 | Rel-9 | R2,R3 | 2009-05-30 08:00 | 2009-12-04 17:00 | 100% | RP-090649 | RP-091052 | AT&T | don.zelmer@att.com | RP#46 completed | LTE 36.300, 36.302, 36.331, 36.413 | 44 | 23 |  |  | Wed 20/05/09 | Thu 03/12/09
4042 | 540005 | Conformance Test Aspects – Public Warning System (PWS) – RAN aspects for LTE | PWS-RAN_UEConTest | 2 | Rel-9 | R5 | 2011-12-02 08:00 | 2012-12-07 17:00 | 100% | RP-111564 | RP-121525 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#58 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 54 | 28 |  |  | Thu 24/11/11 | Tue 04/12/12
4043 | 400031 | Support of Personal Area Networks and Enhancements to Personal Network Management | PAN_EPNM | 1 | Rel-9 | S1,C1 | 2008-06-05 08:00 | 2010-06-04 17:00 | 100% | SP-080430 | - | Vodafone | armin.toepfer@vodafone.com | CP#48 completed | - | 40 | 21 |  |  | Thu 13/12/07 | Fri 28/05/10
4044 | 400043 | Stage 1 for Support of Personal Area Networks and Enhancements to Personal Network Management | PAN_EPNM | 2 | Rel-9 | S1 | 2008-06-05 08:00 | 2008-06-05 08:00 | 100% | SP-080430 | - | Vodafone | armin.toepfer@vodafone.com | SP#40 completed | 22.259 | 40 | 21 |  |  | Thu 13/12/07 | Fri 05/12/08
4045 | 430002 | Stage 2 for Support of Personal Area Networks and Enhancements to Personal Network Management | PAN_EPNM | 2 | Rel-9 | C1 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | CP-090435 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#46 completed | 23.259 | 43 | 22 |  |  | Thu 05/03/09 | Mon 16/11/09
4046 | 430102 | Stage 3 for Support of Personal Area Networks and Enhancements to Personal Network Management | PAN_EPNM | 2 | Rel-9 | C1 | 2009-03-09 08:00 | 2010-06-04 17:00 | 100% | CP-090435 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#48 completed | 24.259 | 43 | 22 |  |  | Thu 05/03/09 | Fri 28/05/10
4047 | 400032 | Multi-Media Telephony Service enhancements | eMMTel | 1 | Rel-9 | S1,S5,C1 | 2008-06-05 08:00 | 2010-03-25 17:00 | 100% | SP-080503 | - | France Telecom | philippe.lottin@orange.com | SP#47 completed | - | 40 | 21 |  |  | Thu 13/12/07 | Fri 05/12/08
4048 | 400044 | Stage 1 for eMMTel | eMMTel | 2 | Rel-9 | S1 | 2008-06-05 08:00 | 2008-12-11 17:00 | 100% | SP-080503 | - | France Telecom | philippe.lottin@orange.com | SP#42 completed | 22.173 | 40 | 21 |  |  | Thu 13/12/07 | Fri 05/12/08
4049 | 430031 | Multimedia Telephony (MMTel) Service and Supplementary Services - Online Charging and completion for Offline Charging (all supplementary services) | eMMTel-SS-CH | 2 | Rel-9 | S5 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090196 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#47 completed | 32.275, 32.298, 32.299 | 43 | 22 |  |  | Thu 26/02/09 | Mon 08/03/10
4050 | 430032 | Support of Real-time Transfer of Tariff Information (RTTI) in IMS charging | IMSTSS-RTTI-CH | 2 | Rel-9 | S5 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090306 | - | Orange | Jean-Luc Garcia (jl.garcia@orange-ftgroup.com) | SP#47 completed. Linked to SA5 Rel-8 UID_380042 AoC support in IMS Charging (IMSTSS) | 32.240, 32.280, 32.298, 32.299 | 43 | 22 |  |  | Thu 26/02/09 | Mon 08/03/10
4051 | 440032 | Stage 3 - Enhancements for Completion of Communications Supplementary service | eMMTel-CC | 2 | Rel-9 | C1 | 2009-05-30 08:00 | 2009-12-04 17:00 | 100% | CP-090490 | - | France Telecom | Youssef.chadli@orange-ftgroup.com | CP#46 completed | 24.642 | 44 | 23 |  |  | Wed 13/05/09 | Mon 16/11/09
4052 | 400034 | User Data Convergence (UDC) | UDC | 1 | Rel-9 | S1,S5,C4 | 2008-06-05 08:00 | 2010-06-10 17:00 | 100% | SP-080448 | - | Nokia Siemens Networks | juergen.merkel@nsn.com | SP#48 completed. Triggered by Rel-8 SA5 Study of Common Profile Storage Framework of User Data for network services and management (UID_320006) TR 32.808 | - | 40 | 21 |  |  | Thu 13/12/07 | Tue 31/08/10
4053 | 400046 | Stage 1 for User Data Convergence (UDC) | UDC | 2 | Rel-9 | S1 | 2008-06-05 08:00 | 2008-12-11 17:00 | 100% | SP-080448 | - | Nokia Siemens Networks | juergen.merkel@nsn.com | SP#42 completed | 22.101, new 22.985 | 40 | 21 |  |  | Thu 13/12/07 | Tue 31/08/10
4054 | 430103 | Stage 2/3 for User Data Convergence (UDC) Technical Realization | UDC-CN | 2 | Rel-9 | C4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | CP-090017 | - | Ericsson | emiliano.merino@ericsson.com | - | - | 43 | 22 |  |  | Wed 04/03/09 | Tue 09/03/10
4055 | 430003 | User Data Convergence (UDC) Technical Realization (Stage 2) | UDC-CN | 3 | Rel-9 | C4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | CP-090017 | - | Ericsson | emiliano.merino@ericsson.com | CP#47 completed | new 23.335 | 43 | 22 |  |  | Wed 04/03/09 | Tue 09/03/10
4056 | 450002 | User Data Convergence (UDC) Protocol Description | UDC-CN | 3 | Rel-9 | C4 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090516 | - | China Mobile, Ericsson | Lan Si Zhong (lansizhong@chinamobile.com), emiliano.merino@ericsson.com | CP#47 completed | new 29.335 | 45 | 23 |  |  | Wed 04/03/09 | Tue 09/03/10
4057 | 440060 | User Data Convergence (UDC) Modelling and Management | UDC-MMAN | 2 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-06-10 17:00 | 100% | SP-090309 | - | T-Mobile, China Mobile, Ericsson | istvan.aba@t-mobile.at, lansizhong@chinamobile.com, miguel.a.garcia@ericsson.com | SP#48 completed | - | 44 | 23 |  |  | Mon 18/05/09 | Wed 26/05/10
4058 | 440062 | UDC – Framework for Model Handling and Management | UDC-MMAN-MFRM | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-06-10 17:00 | 100% | SP-090311 | - | T-Mobile | istvan.aba@t-mobile.at | SP#48 completed | 32.172, new 32.181 | 44 | 23 |  |  | Mon 18/05/09 | Wed 26/05/10
4059 | 440061 | UDC – Common Baseline Information Model | UDC-MMAN-CBIM | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090310 | - | China Mobile, Ericsson | Lan Si Zhong, Miguel Garcia | SP#47 completed | 32.172, new 32.182 | 44 | 23 |  |  | Mon 18/05/09 | Mon 08/03/10
4060 | 410032 | IMS Services Centralization and Continuity | IMS_SCC | 1 | Rel-9 | S1,S2,C1 | 2008-09-18 08:00 | 2010-03-19 17:00 | 100% | SP-080633 | - | NEC | joerg.swetina@neclab.eu | CP#47 completed | - | 41 | 21 |  |  | Mon 15/09/08 | Thu 04/03/10
4061 | 410033 | Stage 1 - Inter-Device Transfer – Requirements | IMS_SCC-IDT | 2 | Rel-9 | S1 | 2008-09-18 08:00 | 2008-12-11 17:00 | 100% | SP-080507 | - | NEC | joerg.swetina@neclab.eu | SP#42 completed | 22.101, 22.228 | 41 | 21 |  |  | Mon 15/09/08 | Fri 05/12/08
4062 | 410134 | Stage 2/3 for IMS Service Continuity Enhancements: Service, Policy and Interactions | IMS_SCC-SPI | 2 | Rel-9 | S2,C1 | 2008-09-18 08:00 | 2010-03-19 17:00 | 100% | SP-080561 | - | Huawei | HengLiang Zhang (hl_zhang@huawei.com) | - | - | 41 | 21 |  |  | Mon 15/09/08 | Fri 20/07/12
4063 | 410034 | Stage 2 for IMS Service Continuity Enhancements: Service, Policy and Interactions | IMS_SCC-SPI | 3 | Rel-9 | S2 | 2008-09-18 08:00 | 2009-06-04 17:00 | 100% | SP-080561 | - | Huawei | HengLiang Zhang (hl_zhang@huawei.com) | SP#57 Removal of the MSC server assisted mid-call feature from Rel-9 by 23.237CR#0433 (CT1 proposed moving this feature to Rel-10). SP#44 completed. TR 23.838 for Approval | 23.237, 23.292, 23.216, new 23.838 | 41 | 21 |  |  | Mon 15/09/08 | Fri 20/07/12
4064 | 440034 | Stage 3 for IMS Service Continuity Enhancements: Service, Policy, Interactions and Inter UE Transfer | IMS_SCC-SPI | 3 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090440 | - | Qualcomm | Roozbeh Atarius (ratarius@qualcomm.com) | CP#47 completed | 24.216, 24.229, 24.237 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
4065 | 410135 | Stage 2/3 for IMS Centralized Services | IMS_SCC-ICS | 2 | Rel-9 | S2,C1 | 2008-09-18 08:00 | 2010-03-19 17:00 | 100% | SP-080634 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | - | 41 | 21 |  |  | Mon 15/09/08 | Tue 02/06/09
4066 | 410035 | Stage 2 for IMS Centralized Services | IMS_SCC-ICS | 3 | Rel-9 | S2 | 2008-09-18 08:00 | 2009-06-04 17:00 | 100% | SP-080634 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | SP#44 completed. TR 23.883 for Information + Approval | 23.292, new 23.883 | 41 | 21 |  |  | Mon 15/09/08 | Tue 02/06/09
4067 | 440033 | Stage 3 for Enhancements to IMS Centralized Services | IMS_SCC-ICS | 3 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090883 | - | Nokia Siemens Networks | Peter.Leis@nsn.com | CP#47 completed | 24.292, 24.604, 24.607, 24.608, 24.611, 24.623 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
4068 | 430004 | Stage 3 - IMS Centralized Services support via I1 interface | IMS_SCC-ICS_I1 | 2 | Rel-9 | C1 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | CP-090640 | - | Huawei | Lili Yang(kadyyang@huawei.com) | CP#47 completed | 24.237, 24.292, new 24.294 | 43 | 22 |  |  | Thu 05/03/09 | Tue 02/03/10
4069 | 420020 | Service Specific Access Control in EPS | SSAC | 1 | Rel-9 | S1,C1,R5 | 2008-12-11 08:00 | 2012-06-15 17:00 | 100% | SP-080882 | - | NTT DoCoMo | Frederic Thepot (thepot@docomolab-euro.com) | CP#47 completed. Triggered by TR 22.986 Study on Service Specific Access Control in EPS. As EPS is a PS-Domain only system, Domain Specific Access Control (DSAC) doesn't apply, hence SSAC allows restriction of voice and non-voice calls separately | - | 42 | 22 |  |  | Fri 05/12/08 | Thu 04/03/10
4070 | 420021 | Stage 1 for Service Specific Access Control in EPS | SSAC | 2 | Rel-9 | S1 | 2008-12-11 08:00 | 2008-12-11 17:00 | 100% | SP-080882 | - | NTT DoCoMo | Frederic Thepot (thepot@docomolab-euro.com) | SP#42 completed. If UE supports E-UTRA and IMS, SSAC is a mandatory Rel-9 function (during congestion in emergency case earthquake/tsunami improves mobile communications). | 22.011 CR0136 | 42 | 22 |  |  | Fri 05/12/08 | Tue 09/02/10
4071 | 440040 | Stage 3 for Service Specific Access Control in EPS | SSAC | 2 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090885 | - | NTT DoCoMo | Hideyuki Yamashita (yamashitahi@s1.nttdocomo.co.jp) | CP#47 completed | 24.173, 27.007 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
4072 | 520014 | Conformance Test Aspects - Service Specific Access Control | SSAC_UEConTest | 2 | Rel-9 | R5 | 2011-06-07 08:00 | 2012-06-15 17:00 | 100% | RP-110765 | RP-120447 | NTT DoCoMo | Takao.Shimizu.rp@nttdocomo.com | RP#56 completed. Testing for Stage 3 for Service Specific Access Control in EPS (24.173, 27.007) UID_440040 | 34.229-1, 34.229-2, 34.229-3 | 52 | 27 |  |  | Mon 23/05/11 | Tue 05/06/12
4073 | 380064 | Support for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS | 1 | Rel-9 | S1,S2,S3,C1,C3,C4,R2,R3,R5,IETF | 2000-01-03 08:00 | 2014-06-13 17:00 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | RP#56 completed testing. CP#47 completed. SP#48 completed | GERAN, LTE | 38 | 21 |  |  | Tue 02/10/07 | Tue 05/06/12
4074 | 410036 | Stage 1 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS | 2 | Rel-9 | S1 | 2008-01-14 08:00 | 2008-12-11 17:00 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | SP#42 completed | 22.101 | 38 | 21 |  |  | Mon 15/09/08 | Tue 09/12/08
4075 | 410037 | Stage 2 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS | 2 | Rel-9 | S2 | 2008-01-14 08:00 | 2009-06-04 17:00 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | SP#44 completed | 23.869, 23.060, 23.167, 23.203, 23.221, 23.228, 23.271, 23.401, 23.402 | 38 | 21 |  |  | Mon 15/09/08 | Mon 01/06/09
4076 | 420022 | Security aspects for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS-Sec | 2 | Rel-9 | S3 | 2008-12-12 08:00 | 2010-06-10 17:00 | 100% | SP-080844 | - | Alcatel-Lucent | Deborah Barclay | SP#48 completed | 33.401, 33.402 | 42 | 22 |  |  | Tue 09/12/08 | Wed 05/05/10
4077 | 440035 | Stage 3 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS | 2 | Rel-9 | C1,C3,C4,R5 | 2009-05-29 08:00 | 2012-06-15 17:00 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | RP#56 completed testing. CP#47 completed | GERAN, LTE | 44 | 23 |  |  | Wed 13/05/09 | Tue 05/06/12
4078 | 440036 | CT1 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPSC1 | 3 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | CP#47 completed | 23.122, 24.008, 24.229, 24.301, 24.302 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
4079 | 480029 | Conformance Test Aspects - CT1 aspects for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPS_UEConTest | 3 | Rel-9 | R5 | 2010-06-04 08:00 | 2012-06-15 17:00 | 100% | RP-100567 | RP-120445 | Samsung | stoyan.baev@partner.samsung.com | RP#56 completed | 34.108, 34.123-1, 34.123-2, 34.123-3, 34.229-1, 34.229-2, 34.229-3, 36.508, 36.523-1, 36.523-2, 36.523-3 | 48 | 25 |  |  | Fri 04/06/10 | Tue 05/06/12
4080 | 440037 | CT3 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPSC3 | 3 | Rel-9 | C3 | 2009-05-29 08:00 | 2009-09-18 17:00 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | CP#45 completed | 29.212, 29.213, 29.214, 29.215 | 44 | 23 |  |  | Wed 13/05/09 | Wed 09/09/09
4081 | 440038 | CT4 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS | IMS_EMER_GPRS_EPSC4 | 3 | Rel-9 | C4 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090564 | - | Alcatel-Lucent | Frank Alfano (falfano@alcatel-lucent.com) | CP#46 completed | 23.003, 23.008, 29.060, 29.272, 29.273, 29.274, 29.275, 29.276 | 44 | 23 |  |  | Wed 13/05/09 | Mon 16/11/09
4082 | 420041 | Support for IMS Emergency Calls over LTE | IMS_EMER_LTE | 2 | Rel-9 | R2,R3 | 2000-01-03 08:00 | 2000-10-16 17:00 | 100% | RP-081140 | RP-090698 | Alcatel-Lucent | Sudeep Palat (spalat@alcatel-lucent.com) | RP#45 completed | 36.331, 36.413 | 42 | 22 |  |  | Wed 18/02/09 | Wed 09/05/12
4083 | 470017 | Conformance Test Aspects – Support for IMS Emergency Calls over LTE | IMS_EMER_LTE_UEConTest | 2 | Rel-9 | R5 | 2010-03-25 08:00 | 2010-12-10 17:00 | 100% | RP-100118 | RP-101068 | Ericsson | leif.mattisson@ericsson.com | RP#50 completed | 36.508, 36.523-1, 36.523-2, 36.523-3 | 47 | 24 |  |  | Wed 10/03/10 | Wed 08/12/10
4084 | 410038 | Single Radio Voice Call Continuity (SRVCC) support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 2 | Rel-9 | S2,C1,C4,C3,IETF | 2008-09-18 08:00 | 2014-06-13 17:00 | 100% | SP-090099 | - | China Mobile | Yu Qing (Yuqing@chinamobile.com) | CP#56 added IETF dependency | - | 41 | 21 |  |  | Mon 15/09/08 | Thu 05/03/09
4085 | 410138 | SRVCC support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 3 | Rel-9 | S2 | 2008-09-18 08:00 | 2009-12-10 17:00 | 100% | SP-090099 | - | China Mobile | Yu Qing (Yuqing@chinamobile.com) | SP#46 completed | 23.870, 23.216, 23.237 | 41 | 21 |  |  | Mon 15/09/08 | Wed 25/11/09
4086 | 460018 | CT aspects of SRVCC support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 3 | Rel-9 | C1,C4,C3,IETF | 2009-05-29 08:00 | 2014-06-13 17:00 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | - | 46 | 24 |  |  | Wed 13/05/09 | Wed 02/12/09
4087 | 440027 | CT1 aspects of SRVCC support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 4 | Rel-9 | C1 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | 24.229, 24.237 | 44 | 23 |  |  | Wed 13/05/09 | Wed 02/12/09
4088 | 440028 | CT4 aspects of SRVCC support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 4 | Rel-9 | C4 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | 29.205, 29.280 | 44 | 23 |  |  | Wed 13/05/09 | Wed 02/12/09
4089 | 460019 | CT3 aspects of SRVCC support for IMS Emergency Calls | IMS_EMER_GPRS_EPS-SRVCC | 4 | Rel-9 | C3 | 2009-12-04 08:00 | 2009-12-04 17:00 | 100% | CP-090882 | - | China Mobile | jiangyi@chinamobile.com | CP#46 completed | 29.163 | 46 | 24 |  |  | Wed 13/05/09 | Wed 02/12/09
4090 | 561003 | (IETF) CT3 aspects of SRVCC support for IMS Emergency Calls (RFC 7254) | IMS_EMER_GPRS_EPS-SRVCC | 4 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-06-13 17:00 | 100% | CP-090882 | - | Andrew Allen | Andrew Allen | CP#64 completed | RFC 7254 (was draft-montemurro-gsma-imei-urn) | 56 | 29 |  |  | Fri 20/04/12 | Fri 06/06/14
4091 | 430006 | LCS for LTE and EPS | LCS_LTE_EPS | 1 | Rel-9 | S2,C1,C4,R2,R1,R3,R4,R5 | 2008-06-05 08:00 | 2012-03-02 17:00 | 100% | - | - | - | - | - | LTE | 43 | 22 |  |  | Wed 18/02/09 | Tue 16/03/10
4092 | 400038 | LCS Control Plane Solution for EPS | LCS_EPS-CPS | 2 | Rel-9 | S2,C4,C1 | 2008-06-05 08:00 | 2010-03-19 17:00 | 100% | SP-080445 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | Triggered by abandoned Study UID_380068 (FS_LCS_EPS). Linked to Feature UID_380064 Support for IMS Emergency Calls over GPRS and EPS | - | 40 | 21 |  |  | Thu 13/12/07 | Sat 22/11/08
4093 | 400048 | Stage 2 for LCS Control Plane Solution for EPS | LCS_EPS-CPS | 3 | Rel-9 | S2 | 2008-06-05 08:00 | 2009-06-04 17:00 | 100% | SP-080445 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | SP#44 completed | 23.891, 23.271, 23.401, 23.402 | 40 | 21 |  |  | Thu 13/12/07 | Mon 01/06/09
4094 | 440020 | CT4 aspects of Control Plane LCS in the EPC | LCS_EPS-CPS | 3 | Rel-9 | C4 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090811 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | CP#47 completed (IANA registrations outstanding). Stage 3 SLs and SLg interfaces & transport of positioning messages between E-SMLC and MME in the scope of UID_420006 (Positioning Support for LTE) | 24.080, 29.002, 29.272, 29.230, new 24.171, 29.171, 29.172, 29.173 | 44 | 23 |  |  | Wed 13/05/09 | Tue 09/03/10
4095 | 440120 | CT1 aspects of Control Plane LCS in the EPC | LCS_EPS-CPS | 3 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090811 | - | Polaris Wireless | Robert Gross (rgross@polariswireless.com) | CP#47 completed | 24.301 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
4096 | 420006 | Positioning Support for LTE | LCS_LTE | 2 | Rel-9 | R2,R1,R3,R4 | 2008-12-05 08:00 | 2008-12-05 08:00 | 100% | RP-091389 | RP-100442 | Qualcomm | Nathan Tenny (ntenny@qualcomm.com) | RP#48 completed. UID_400038 (LCS Control Plane Solution for EPS) depends on this WI | 34.213, 36.133, 36.211, 36.214, 36.300, 36.305, 36.331, 36.355, 36.410, 36.413, 36.455, new 36.171 | 42 | 22 |  |  | Wed 03/12/08 | Tue 01/06/10
4097 | 470018 | Conformance Test Aspects – Positioning Support for LTE | LCS_LTE_UEConTest | 2 | Rel-9 | R5 | 2010-03-19 08:00 | 2012-03-02 17:00 | 100% | RP-111209 | RP-120034 | Qualcomm | Shubhang Vora (svoral@qualcomm.com) | RP#55 completed. RP#56 TS 37.571-4 v200 for Approval | 36.508, 36.509, new (37.571-1, 37.571-2, 37.571-3, 37.571-4, 37.571-5) | 47 | 24 |  |  | Wed 17/03/10 | Wed 06/06/12
4098 | 400039 | MBMS support in EPS | MBMS_EPS | 1 | Rel-9 | S2,S3,S5,C3,C4,R2,R3,R4,R5 | 2008-06-05 08:00 | 2011-12-09 17:00 | 100% | SP-080737 | - | China Mobile | Liu Hong (liuhongyfw@chinamobile.com) | RP#47 completed. SP#46, CP#46 completed | LTE | 40 | 21 |  |  | Thu 13/12/07 | Tue 16/03/10
4099 | 400040 | Stage 2 for MBMS support in EPS | MBMS_EPS | 2 | Rel-9 | S2 | 2008-06-05 08:00 | 2009-06-04 17:00 | 100% | SP-080737 | - | China Mobile | Liu Hong (liuhongyfw@chinamobile.com) | SP#44 completed | 23.246 | 40 | 21 |  |  | Thu 13/12/07 | Mon 01/06/09
4100 | 420023 | Security for MBMS support in EPS | MBMS_EPS | 2 | Rel-9 | S3 | 2008-12-11 08:00 | 2009-12-10 17:00 | 100% | SP-080737 | - | China Mobile | Liu Hong (liuhongyfw@chinamobile.com) | SP#46 completed | 33.246 | 42 | 22 |  |  | Tue 09/12/08 | Wed 09/12/09
4101 | 430033 | MBMS Charging in EPS | MBMS_EPS | 2 | Rel-9 | S5 | 2009-03-06 08:00 | 2009-12-10 17:00 | 100% | SP-090052 | - | ZTE | guo.wenjie1@zte.com.cn | SP#46 completed | 32.273, 32.251, 32.298, 32.299 | 43 | 22 |  |  | Mon 23/02/09 | Tue 01/12/09
4102 | 440025 | CT4 aspects of MBMS support in EPS (Stage 3) | MBMS_EPS | 2 | Rel-9 | C4 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090325 | - | China Mobile, ZTE | wangjingyf@chinamobile.com, lu.fei1@zte.com.cn | CP#46 completed | 29.274, 29.281, 23.007, 23.008 | 44 | 23 |  |  | Wed 13/05/09 | Mon 16/11/09
4103 | 440026 | CT3 aspects of MBMS support in EPS (Stage 3) | MBMS_EPS | 2 | Rel-9 | C3 | 2009-05-29 08:00 | 2009-12-04 17:00 | 100% | CP-090330 | - | ZTE, China Mobile | zhou.xiaoyun@zte.com.cn, wangjingyf@chinamobile.com | CP#46 completed | 29.061 | 44 | 23 |  |  | Wed 13/05/09 | Wed 25/11/09
4104 | 430007 | MBMS support in LTE | MBMS_LTE | 2 | Rel-9 | R2,R3,R4 | 2009-03-06 08:00 | 2010-03-19 17:00 | 100% | RP-091457 | RP-100033 | Huawei | arnaud.meylan@huawei.com | RP#47 completed | 25.446, 36.101, 36.104, 36.141, 36.300, 36.304, 36.321, 36.322, 36.323, 36.331, 36.440, 36.441, 36.442, 36.444, 36.445 | 43 | 22 |  |  | Tue 10/03/09 | Tue 16/03/10
4105 | 500024 | Conformance Test Aspects – MBMS support in LTE | MBMS_LTE-UEConTest | 2 | Rel-9 | R5 | 2010-12-10 08:00 | 2011-12-09 17:00 | 100% | RP-101245 | RP-111437 | Huawei | Zhang Xin (zhangxin0208@huawei.com) | RP#54 completed | 36.508, 36.521-1, 36.521-2, 36.523-1, 36.523-2, 36.523-3 | 50 | 26 |  |  | Fri 10/12/10 | Tue 29/11/11
4106 | 420024 | Access Network Discovery and Selection Function enhancements | eANDSF | 1 | Rel-9 | S2,C1 | 2008-12-11 08:00 | 2010-03-19 17:00 | 100% | SP-080887 | - | Motorola | Apostolis Salkintzis (salki@motorola.com) | CP#47 completed. No new Rel-9 use cases defined. Implement service requirements not covered in Rel-8 | 22.278, SA3 33.402 CR#0055 | 42 | 22 |  |  | Fri 05/12/08 | Thu 04/03/10
4107 | 420040 | Stage 2 for Access Network Discovery and Selection Function enhancements | eANDSF | 2 | Rel-9 | S2 | 2008-12-11 08:00 | 2009-06-04 17:00 | 100% | SP-080887 | - | Motorola | Apostolis Salkintzis (salki@motorola.com) | SP#44 completed | 23.402, 23.002 | 42 | 22 |  |  | Fri 05/12/08 | Mon 01/06/09
4108 | 450006 | CT1 aspects of Access Network Discovery and Selection Function enhancements | eANDSF | 2 | Rel-9 | C1 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090742 | - | Panasonic | benjamin.limck@sg.panasonic.com | CP#47 completed | 24.302, 24.312 | 45 | 23 |  |  | Tue 08/09/09 | Tue 02/03/10
4109 | 430034 | Multiple PDN Connection to the Same APN for PMIP-based Interfaces | MUPSAP | 1 | Rel-9 | S2,C4,C1 | 2009-03-13 08:00 | 2010-03-19 17:00 | 100% | SP-090098 | - | Samsung | erik.guttman@partner.samsung.com | CP#47 completed. Continues Rel-8 SAES Stage 2 UID_320005. Stage 1 in 22.278 (EPS Service requirements) | - | 43 | 22 |  |  | Thu 05/03/09 | Thu 04/03/10
4110 | 430134 | Stage 2 for Multiple PDN Connection to the Same APN for PMIP-based Interfaces | MUPSAP | 2 | Rel-9 | S2 | 2009-03-13 08:00 | 2009-06-04 17:00 | 100% | SP-090098 | - | Samsung | erik.guttman@partner.samsung.com | SP#44 completed | 23.060, 23.203, 23.401, 23.402 | 43 | 22 |  |  | Thu 05/03/09 | Tue 08/09/09
4111 | 450007 | CT4 aspects of Multiple PDN Connection to the Same APN for PMIP-based Interfaces | MUPSAP | 2 | Rel-9 | C4 | 2009-09-18 08:00 | 2009-12-04 17:00 | 100% | CP-090515 | - | Samsung | Surjyakanta Mohapatra (surjya.kanta@samsung.com) | CP#46 completed | 29.275, 23.008, 29.282 | 45 | 23 |  |  | Thu 05/03/09 | Mon 16/11/09
4112 | 450008 | CT1 aspects of Multiple PDN Connection to the Same APN for PMIP-based Interfaces | MUPSAP | 2 | Rel-9 | C1 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090515 | - | Samsung | Surjyakanta Mohapatra (surjya.kanta@samsung.com) | CP#47 completed | 24.302 | 45 | 23 |  |  | Thu 05/03/09 | Tue 02/03/10
4113 | 450049 | System aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 1 | Rel-9 | S2,S4,C1,C3,R2,IETF | 2007-05-07 10:34 | 2012-09-12 17:00 | 100% | SP-090653 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | Triggered by RAN2 UID_440013 Vocoder rate adaptation for LTE | LTE | 45 | 23 |  |  | Thu 28/05/09 | Mon 03/09/12
4114 | 450050 | SA2 system aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 2 | Rel-9 | S2 | 2009-06-04 08:00 | 2009-09-24 17:00 | 100% | SP-090653 | - | Qualcomm | AC Mahendran (ac@qualcomm.com) | SP#45 completed (CR adding support for Explicit Congestion Notification) | 23.401 CR#1103r3 | 45 | 23 |  |  | Thu 28/05/09 | Mon 21/09/09
4115 | 450051 | SA4 system aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 2 | Rel-9 | S4 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090653 | - | Qualcomm | Nikolai Leung | SP#46 completed | 26.114 | 45 | 23 |  |  | Thu 28/05/09 | Mon 07/12/09
4116 | 440013 | Vocoder rate adaptation for LTE | LTEimp-Vocoder | 2 | Rel-9 | R2 | 2009-05-30 08:00 | 2009-09-18 17:00 | 100% | RP-090978 | RP-090704 | Alcatel-Lucent | Sudeep Palat (spalat@alcatel-lucent.com) | RP#45 completed | 36.300 CR#0114 | 44 | 23 |  |  | Thu 28/05/09 | Sat 24/10/09
4117 | 521005 | (IETF) SA4 system aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 2 | Rel-9 | S4-IETF | 2009-06-04 08:00 | 2012-09-12 17:00 | 100% | SP-090653 | - | Lionel Morand | - | SP#57 completed | RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp) | 52 | 27 |  |  | Mon 20/06/11 | Mon 03/09/12
4118 | 521006 | (IETF) CT aspects of vocoder rate adaptation for LTE | LTEimp-Vocoder | 2 | Rel-9 | C1-IETF,C3-IETF,C4-IETF | 2007-05-07 10:34 | 2012-09-07 17:00 | 100% | SP-090653 | - | Lionel Morand | - | CP#57 completed | RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp) | 52 | 27 |  |  | Mon 20/06/11 | Mon 03/09/12
4119 | 33025 | Access Security Enhancements | ACCSEC2 | 1 | Rel-9 | S3 | 2007-07-02 08:00 | 2009-06-04 17:00 | 100% | SP-040865 | - | Ericsson | Bengt.Sahlin@ericsson.com | SP#44 completed. Stopped TR 33.801. CRs 33.102,43.020 on A5/2 removal done long time ago. A5/4 introduction CRs will be done under UID_440057 128 bit encryption for GSM and GPRS. SP#26 approved WID (improved GERAN security) | 33.102, 43.020 | 26 |  |  |  | Thu 24/03/05 | Fri 06/08/10
4120 | 410027 | Protection against Unsolicited Communication for IMS (PUCI) | PUCI | 1 | Rel-9 | S3,S1 | 2008-09-18 08:00 | 2009-12-10 17:00 | 100% | SP-080482 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#46 TR 33.937 completed but no specification work done in Rel-9. Related work in OMA Categorization Based Content Screening | - | 41 | 21 |  |  | Mon 15/09/08 | Mon 07/12/09
4121 | 410028 | Stage 1 for PUCI | PUCI | 2 | Rel-9 | S1 | 2008-09-18 08:00 | 2008-12-11 17:00 | 100% | SP-080482 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#42 completed | 22.228 | 41 | 21 |  |  | Mon 15/09/08 | Fri 05/12/08
4122 | 410029 | SA3 work on PUCI | PUCI | 2 | Rel-9 | S3 | 2008-09-18 08:00 | 2009-12-10 17:00 | 100% | SP-080482 | - | NEC | Anand R. Prasad (anand@bq.jp.nec.com) | SP#46 completed. No normative work done in Rel-9 | New 33.937 | 41 | 21 |  |  | Mon 15/09/08 | Mon 07/12/09
4123 | 430036 | IMS Media Plane Security | MEDIASEC | 1 | Rel-9 | S3,C1,C4,C3,IETF | 2009-03-13 08:00 | 2012-09-14 17:00 | 100% | SP-090128 | - | Vodafone | Peter.Howard@vodafone.com | - | - | 43 | 22 |  |  | Wed 11/02/09 | Mon 03/09/12
4124 | 430136 | SA3 aspects of IMS Media Plane Security | MEDIASEC | 2 | Rel-9 | S3 | 2009-03-13 08:00 | 2010-03-25 17:00 | 100% | SP-090128 | - | Vodafone | Peter.Howard@vodafone.com | SP#47 completed | New 33.828, 33.328 | 43 | 22 |  |  | Wed 11/02/09 | Mon 01/03/10
4125 | 521007 | (IETF) SA3, CT1, CT3 aspects of IMS Media Plane Security | MEDIASEC | 2 | Rel-9 | S3-IETF,C1-IETF,C3-IETF | 2009-03-18 08:00 | 2012-09-14 17:00 | 100% | SP-090128 | - | Peter Dawes | - | CP#57 completed, ietf-draft discontinued, documented within 3GPP | draft-dawes-dispatch-mediasec-parameter | 52 | 27 |  |  | Mon 20/06/11 | Mon 03/09/12
4126 | 460020 | CN aspects of IMS Media Plane Security | MEDIASEC_CORE | 2 | Rel-9 | C1,C4,C3 | 2009-09-18 08:00 | 2010-06-04 17:00 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#48 completed | - | 45 | 23 |  |  | Wed 11/02/09 | Wed 02/12/09
4127 | 450010 | CT1 aspects of IMS Media Plane Security | MEDIASEC_CORE | 3 | Rel-9 | C1 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#47 completed | 23.218, 24.229 | 45 | 23 |  |  | Wed 11/02/09 | Tue 02/03/10
4128 | 450021 | CT4 aspects of IMS Media Plane Security | MEDIASEC_CORE | 3 | Rel-9 | C4 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#47 completed | 29.238, 23.334, 29.334 | 45 | 23 |  |  | Wed 11/02/09 | Tue 09/03/10
4129 | 460021 | CT3 aspects of IMS Media Plane Security | MEDIASEC_CORE | 3 | Rel-9 | C3 | 2009-12-04 08:00 | 2010-06-04 17:00 | 100% | CP-090884 | - | Vodafone | peter.dawes@vodafone.com | CP#48 completed | 29.162 | 46 | 24 |  |  | Wed 02/12/09 | Thu 27/05/10
4130 | 440053 | GBAPush enhancements (Generic push layer) | eGBAPush | 1 | Rel-9 | S3 | 2008-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090282 | - | Ericsson | Rolf Blom | SP#43 umbrella to host 33.224, moved from Rel-8 to Rel-9. SP#47 completed | New 33.224 | 44 | 23 |  |  | Wed 11/02/09 | Mon 21/09/09
4131 | 420039 | SA3 part of eGBAPush (Generic push layer) | eGBAPush | 2 | Rel-9 | S3 | 2008-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090282 | - | Ericsson | Rolf Blom | SP#47 completed | New 33.224 | 39 | 21 |  |  | Sat 22/03/08 | Tue 23/02/10
4132 | 440054 | Extended Identity Management | GBA-IdM | 1 | Rel-9 | S3 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090284 | - | Nokia | Silke.Holtmanns@nokia.com | SP#46 completed. Stage 1 not identified (GBA Liberty Interworking has been outlined and GBA–OpenID interworking is analogous) | New 33.924, CT4 29.109 (added service code) | 44 | 23 |  |  | Mon 18/05/09 | Tue 23/02/10
4133 | 440056 | Network Domain Security (NDS) enhancements to support backhaul security | NDS_Backhaul | 1 | Rel-9 | S3,IETF | 2009-06-04 08:00 | 2012-12-07 17:00 | 100% | SP-090286 | - | Vodafone | Peter.Howard@vodafone.com | Continuation of Rel-8 UID_390044 SAE security architecture. Covers gaps in backhaul security in SAE (also applicable to UTRAN and GERAN backhaul) | - | 44 | 23 |  |  | Mon 18/05/09 | Sat 24/11/12
4134 | 440156 | SA3 part of Network Domain Security (NDS) enhancements to support backhaul security | NDS_Backhaul | 2 | Rel-9 | S3 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090286 | - | Vodafone | Peter.Howard@vodafone.com | SP#47 completed | 33.102, 33.210, 33.310, 33.401, 33.402 | 44 | 23 |  |  | Mon 18/05/09 | Mon 01/03/10
4135 | 521008 | (IETF) SA3 part of Network Domain Security (NDS) enhancements to support backhaul security | NDS_Backhaul | 2 | Rel-9 | S3-IETF | 2009-06-04 08:00 | 2012-12-07 17:00 | 100% | SP-090286 | - | Bengt Sahlin | - | CP#58 completed | RFC 6712 (was draft-ietf-pkix-cmp-transport-protocols) | 52 | 27 |  |  | Mon 20/06/11 | Sat 24/11/12
4136 | 440256 | Deleted - CT4 part of Network Domain Security (NDS) enhancements to support backhaul security | NDS_Backhaul | 2 | Rel-9 | C4 | 2009-06-04 08:00 | 2009-12-04 17:00 | 100% | SP-090286 | - | Vodafone | Peter.Howard@vodafone.com | CP#46 completed. No impact on CT4 specs | - | 44 | 23 | CP-46 | PCG-24 | Mon 18/05/09 | Wed 25/11/09
4137 | 440057 | 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 1 | Rel-9 | S3,C1,C4,G2,G3new | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090287 | - | Ericsson | Karl Norrman | Allow 128 as an alternative to 64 bit keys (Stage 2/3 + Test spec) | - | 44 | 23 |  |  | Mon 18/05/09 | Wed 25/11/09
4138 | 440157 | SA3 part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | S3 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090287 | - | Ericsson | Karl Norrman | SP#46 completed | 33.102,43.020, New 55.226 | 44 | 23 |  |  | Mon 18/05/09 | Mon 01/03/10
4139 | 440357 | CT1 part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | C1 | 2009-06-04 08:00 | 2009-09-18 17:00 | 100% | SP-090287 | - | Ericsson | Karl Norrman | CP#45 completed | 24.008,44.064 | 44 | 23 |  |  | Mon 18/05/09 | Tue 08/09/09
4140 | 440457 | CT4 part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | C4 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090287 | - | Ericsson | Karl Norrman | CP#46 completed. Kc128 enhancements are carried as UMTS keys => no impact on CT4 29.002, 29.060 | - | 44 | 23 |  |  | Mon 18/05/09 | Mon 16/11/09
4141 | 440557 | GERAN2 part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | G2 | 2009-06-04 08:00 | 2009-09-04 17:00 | 100% | GP-091212 | - | Ericsson | Karl Norrman | GP#43 WID approved + completed | 44.018,48.008,48.018,48.058 | 44 | 23 |  |  | Mon 18/05/09 | Wed 06/01/10
4142 | 440657 | GERAN3new (testing) part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | G3new | 2009-06-04 08:00 | 2009-11-20 17:00 | 100% | GP-091212 | - | Ericsson | Karl Norrman | GP#44 completed. GP#43 WID approved | 51.010 | 44 | 23 |  |  | Mon 18/05/09 | Fri 20/11/09
4143 | 440257 | Deleted - SA2 part of 128 bit encryption for GSM and GPRS | A5/4-GEA4 | 2 | Rel-9 | S2 | 2009-06-04 08:00 | 2009-09-24 17:00 | 100% | SP-090287 | - | Ericsson | Karl Norrman | SP#45 work stopped/abandoned | 23.060 | 44 | 23 | SP-45 | PCG-23 | Mon 18/05/09 | Mon 07/09/09
4144 | 420027 | Timed Graphics | TG | 1 | Rel-9 | S4 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-080683 | - | Ericsson | clinton.priddle@ericsson.com | SP#47 completed. Provide graphics in parallel to a video stream (without requiring an umbrella scene descriptor such as 3GPP DIMS in TS 26.142) | 26.114, 26.140, 26.234, 26.244, 26.245, 26.346, New 26.430 | 42 | 22 |  |  | Sun 23/11/08 | Mon 01/02/10
4145 | 430037 | Managing MTSI Media Adaptation | M3A | 1 | Rel-9 | S4 | 2009-03-12 08:00 | 2009-12-10 17:00 | 100% | SP-090021 | - | Samsung | kyunghun.jung@samsung.com | SP#46 completed. Work extending Rel-8 UID_34041 MTSI Video - Dynamic Rate Adaptation/Signalling of Image Size. Update speech/video adaptation algorithms used by network to control MTSI client terminal in congestion or poor transmission conditions. | 26.114 | 43 | 22 |  |  | Mon 02/02/09 | Mon 07/12/09
4146 | 440046 | PSS and MBMS Aspects | PMA | 1 | Rel-9 | S4 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090261 | - | Ericsson, Nokia | Clinton.Priddle@ericsson.com, imed.bouazizi@nokia.com | Umbrella WI | - | 44 | 23 |  |  | Sun 31/05/09 | Mon 08/03/10
4147 | 430038 | PSS and MBMS extensions | PMA-MBS_Ext | 2 | Rel-9 | S4 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090262 | - | Ericsson | Clinton.Priddle@ericsson.com | SP#47 completed. Extends Rel-8 UID_34043 (PSS_MBMS_OMTV) & ensures compatibility with UID_34046 (IMS_PSS_MBMS_US) | 26.234, 26.346 | 43 | 22 |  |  | Mon 02/02/09 | Mon 08/03/10
4148 | 430039 | Improved Video Support for PSS and MBMS | PMA-IVS | 2 | Rel-9 | S4 | 2009-03-12 08:00 | 2010-03-25 17:00 | 100% | SP-090263 | - | Nokia | imed.bouazizi@nokia.com | SP#47 completed | 26.234, 26.244, 26.346, new 26.903 | 43 | 22 |  |  | Mon 02/02/09 | Mon 08/03/10
4149 | 430046 | IMS based PSS and MBMS User Service extensions | IMS_PSS_MBMS_US_EXT | 1 | Rel-9 | S4 | 2009-03-12 08:00 | 2009-12-10 17:00 | 100% | SP-090225 | - | Ericsson | Markus Kampmann | SP#46 completed. Work extending Rel-8 UID_34046 (IMS_PSS_MBMS_US), SA2 UID_410034 IMSSCC-SPI (IMS Service Continuity Enhancements: Service, Policy and Interactions) | 26.237 | 43 | 22 |  |  | Mon 02/02/09 | Mon 07/12/09
4150 | 440051 | Syndicated Feed Reception within 3GPP environments | SFR | 1 | Rel-9 | S4 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090260 | - | Ericsson | Thorsten.Lohmar@ericsson.com | SP#46 completed. TS 26.150v100 for Approval. RSS optimized for mobile use. Reuse/reference OMA's enabler DCD. | New 26.150 | 44 | 23 |  |  | Sun 31/05/09 | Mon 07/12/09
4151 | 450048 | Distortion Measurement Test Methods and Requirements | DTMR | 1 | Rel-9 | S4 | 2009-09-24 08:00 | 2010-03-25 17:00 | 100% | SP-090575 | - | Motorola | Stephen Kendall (wcsk01@motorola.com) | SP#47 completed | 26.131, 26.132 | 45 | 23 |  |  | Mon 21/09/09 | Wed 02/12/09
4152 | 420029 | Rel-9 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM9 | 1 | Rel-9 | S5 | 2008-02-22 08:00 | 2010-06-10 17:00 | 100% | - | - | - | - | OAM9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI | TR 30.819 | 42 | 22 |  |  | Tue 25/11/08 | Tue 09/02/10
4153 | 420030 | Rel-9 Network Infrastructure Management | OAM9-NIM | 2 | Rel-9 | S5 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | - | - | - | - | SP#42 umbrella BB created to host OAM WIs | - | 42 | 22 |  |  | Tue 25/11/08 | Mon 01/12/08
4154 | 420031 | Software Management for Network Elements | OAM9-NE_SWM | 3 | Rel-9 | S5 | 2008-12-11 08:00 | 2010-03-25 17:00 | 100% | SP-080756 | - | Huawei, Nokia Siemens Networks | Bidipta Das (bidipta@huawei.com), Clemens Suerbaum (clemens.suerbaum@nsn.com) | SP#47 completed | 32.531, 32.532, 32.533, new 32.537 | 42 | 22 |  |  | Wed 03/12/08 | Mon 08/03/10
4155 | 440064 | Service Oriented Architecture (SOA) for IRP | - | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090313 | - | Ericsson, Nokia Siemens Networks | edwin.tse@ericsson.com, Jörg Schmidt (joerg@cox.net) | SP#47 completed (covering SOA Architecture & SOA-supporting Solution Set). Triggered by UID_400029 Study on Service Oriented Architecture (SOA) for IRP (TR 32.824) | 32.101, 32.102, 32.150 | 44 | 23 |  |  | Mon 18/05/09 | Mon 08/03/10
4156 | 440065 | IRP SOAP Solution Sets continuation from Rel-8 | - | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090314 | - | Ericsson | John Power | SP#47 completed. Continuation of Rel-8 UID_400030 IRP SOAP Solution Sets | New (32.127/ 327/ 337/ 357/ 387/ 397/ 447/ 397/ 447/ 507/ 537), 32.121,32.122,32.123,32,32.321,32.322,32.323,32.325,32.331,32.332,32.333,32.335,32.351,32.352,32.353,32.381,32.382,32.383,32.385,32.391,32.392,32.393,32.395,32.441,32.442,32.443 | 44 | 23 |  |  | Mon 18/05/09 | Mon 22/03/10
4157 | 420032 | Rel-9 Performance Management | OAM9-PM | 2 | Rel-9 | S5 | 2009-03-12 08:00 | 2010-06-10 17:00 | 100% | - | - | - | - | SP#42 umbrella BB created to host OAM WIs | - | 42 | 22 |  |  | Tue 25/11/08 | Mon 01/12/08
4158 | 440059 | Enhancement of UTRAN Performance Measurements | - | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2009-12-10 17:00 | 100% | SP-090308 | - | China Mobile | liangshuangchun@cmdi.chinamobile.com, lijian@chinamobile.com, Bao Haitao | SP#46 completed | 32.405 | 44 | 23 |  |  | Mon 18/05/09 | Tue 01/12/09
4159 | 430041 | Enhancement of E-UTRAN Performance Measurements | - | 3 | Rel-9 | S5 | 2009-03-12 08:00 | 2010-06-10 17:00 | 100% | SP-090053 | - | Motorola, Huawei | Yizhi Yao (yzyao@motorola.com),Lan Zou (zlan@huawei.com) | SP#48 completed | 32.425 | 43 | 22 |  |  | Mon 23/02/09 | Wed 26/05/10
4160 | 430042 | Enhancement of EPC Performance Measurements | - | 3 | Rel-9 | S5 | 2009-03-12 08:00 | 2009-12-10 17:00 | 100% | SP-090049 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#46 completed | 32.426 | 43 | 22 |  |  | Wed 25/02/09 | Tue 09/02/10
4161 | 430043 | Rel-9 Self-Organizing Networks (SON) - OAM aspects | OAM9-SON | 2 | Rel-9 | S5 | 2008-02-22 08:00 | 2010-06-10 17:00 | 100% | - | - | - | - | SP#43 umbrella BB created to host OAM WIs | - | 43 | 22 |  |  | Mon 09/03/09 | Tue 09/02/10
4162 | 390007 | SON self-optimization management (moved from Rel-8 LTE_SON-OAM) | - | 3 | Rel-9 | S5 | 2008-02-22 08:00 | 2010-06-10 17:00 | 100% | SP-100091 | - | Huawei | Lan Zou (zlan@huawei.com) | SP#48 completed | 32.425, new (32.521, 32.522, 32.523, 32.525) | 39 | 21 |  |  | Fri 17/06/05 | Wed 26/05/10
4163 | 440067 | Automatic Radio Network Configuration Data Preparation | - | 3 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-06-10 17:00 | 100% | SP-090869 | - | Nokia Siemens Networks | clemens.suerbaum@nsn.com | SP#48 completed | 32.501, 32.502, 32.503, 32.505, new 32.507 | 44 | 23 |  |  | Mon 18/05/09 | Wed 26/05/10
4164 | 440058 | Rel-9 Subscription Management (SuM) evolution | OAM9-SuM | 2 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-06-10 17:00 | 100% | SP-090307 | - | Ericsson | frode.nergard@ericsson.com | SP#48 completed | 32.140, 32.141, 32.152, 32.172, 32.175 | 44 | 23 |  |  | Mon 18/05/09 | Wed 26/05/10
4165 | 420033 | Deleted - Rel-9 Trace | OAM9-Trace | 2 | Rel-9 | S5 | 2009-03-13 08:00 | 2009-12-10 17:00 | 100% | - | - | - | - | SP#46 stopped (no work in Rel-9) | - | 42 | 22 | SP-46 | PCG-24 | Tue 25/11/08 | Tue 01/12/09
4166 | 440068 | Rel-9 Charging Management small Enhancements | CH9 | 1 | Rel-9 | S5 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | - | - | - | - | CH9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI | TR 30.819 | 44 | 23 |  |  | Tue 19/05/09 | Mon 08/03/10
4167 | 400008 | CS-IBCF and CS-TrGW definition in 3GPP specifications | CS-IBCF | 1 | Rel-9 | C3,C4 | 2008-05-30 08:00 | 2010-03-19 17:00 | 100% | CP-090073 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#47 completed. Rel-8 UID_380061 (Ipinterc) covers Stage 1 in SA1 22.101, 22.228 | - | 40 | 21 |  |  | Wed 05/09/07 | Tue 02/03/10
4168 | 400109 | CT3 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications | CS-IBCF | 2 | Rel-9 | C3 | 2008-05-30 08:00 | 2010-03-19 17:00 | 100% | CP-090073 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#47 completed | 29.235 | 40 | 21 |  |  | Wed 05/09/07 | Tue 02/03/10
4169 | 400010 | CT4 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications | CS-IBCF | 2 | Rel-9 | C4 | 2008-05-30 08:00 | 2009-12-04 17:00 | 100% | CP-090073 | - | Telecom Italia | mauro.ficaccio@telecomitalia.it | CP#46 completed | 23.231, 29.232, new 29.238 | 40 | 21 |  |  | Wed 05/09/07 | Wed 25/11/09
4170 | 410008 | IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3 | IMS_IBCF | 1 | Rel-9 | C4,C3 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | CP-090019 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | - | 41 | 21 |  |  | Wed 05/09/07 | Wed 29/07/09
4171 | 410108 | CT4 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3 | IMS_IBCF | 2 | Rel-9 | C4 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | CP-090019 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | new 29.238 | 41 | 21 |  |  | Wed 05/09/07 | Mon 16/11/09
4172 | 410208 | CT3 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3 | IMS_IBCF | 2 | Rel-9 | C3 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | CP-090019 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | 29.162, 29.235 | 41 | 21 |  |  | Wed 05/09/07 | Wed 25/11/09
4173 | 410009 | IMS Application Level Gateway Control Function (ALGCF) – IMS Access Media Gateway (IMA-MGW); Iq Interface; Stage 2 and Stage 3 | IMS_AGCF | 1 | Rel-9 | C4 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | CP-090020 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | CP#46 completed | New 23.334, 29.334 | 41 | 21 |  |  | Wed 05/09/07 | Mon 16/11/09
4174 | 420016 | Enhancements of IMS Customized Alerting Tone (CAT) Service | eCAT | 1 | Rel-9 | C1 | 2008-12-05 08:00 | 2010-06-04 17:00 | 100% | CP-080796 | - | China Mobile | Jiang Yi | CP#48 completed. Stage 1 in 22.182 | - | 42 | 22 |  |  | Thu 04/12/08 | Mon 16/11/09
4175 | 420017 | Stage 3 for Enhancements of IMS Customized Alerting Tone (CAT) Service | eCAT-SS | 2 | Rel-9 | C1 | 2008-12-05 08:00 | 2010-06-04 17:00 | 100% | CP-080796 | - | China Mobile | Jiang Yi | CP#48 completed | 24.182 | 42 | 22 |  |  | Thu 04/12/08 | Fri 28/05/10
4176 | 440017 | Completion of IMS Restoration Procedures | eIMS_RP | 1 | Rel-9 | C3,C4,C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed. Continuation of Rel-8 Feature UID_400012 IMS Restoration Procedures | - | 44 | 23 |  |  | Wed 13/05/09 | Thu 01/04/10
4177 | 440018 | CT4 aspects of Completion of IMS Restoration Procedures | eIMS_RP | 2 | Rel-9 | C4 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed | 23.380, 23.820 | 44 | 23 |  |  | Wed 13/05/09 | Tue 09/03/10
4178 | 440019 | CT1 aspects of Completion of IMS Restoration Procedures | eIMS_RP | 2 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed | 24.229 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
4179 | 460022 | CT3 aspects of Completion of IMS Restoration Procedures | eIMS_RP | 2 | Rel-9 | C3 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-091050 | - | Ericsson | Emiliano Merino (emiliano.merino@ericsson.com) | CP#47 completed | 29.061, 29.212, 29.213, 29.214, 29.215 | 46 | 24 |  |  | Wed 13/05/09 | Tue 02/03/10
4180 | 440039 | IMS Stage 3 IETF Protocol Alignment - phase 3 | IMSProtoc3 | 1 | Rel-9 | C1,IETF | 2009-05-29 08:00 | 2014-12-05 17:00 | 100% | CP-090491 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed | - | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
4181 | 440139 | CT1 aspects of IMS Stage 3 - IETF Protocol Alignment - phase 3 | IMSProtoc3 | 2 | Rel-9 | C1 | 2009-05-29 08:00 | 2010-03-19 17:00 | 100% | CP-090491 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed | 23.218, 24.229, 24.930 | 44 | 23 |  |  | Wed 13/05/09 | Tue 02/03/10
4182 | 521009 | (IETF) CT1 IMS Stage 3 - IETF Protocol Alignment (RFC 7329) | IMSProtoc3 | 2 | Rel-9 | C1-IETF | 2009-05-29 08:00 | 2014-12-05 17:00 | 100% | CP-090491 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#65 completed | RFC 7329 (was draft-kaplan-insipid-session-id) | 52 | 27 |  |  | Mon 20/06/11 | Wed 03/09/14
4183 | 531007 | (IETF) CT1 IMS Stage 3 - IETF Protocol Alignment (RFC 7044) | IMSProtoc3 | 2 | Rel-9 | C1-IETF | 2011-09-13 08:00 | 2014-03-07 17:00 | 100% | CP-090491 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#63 completed | RFC 7044 (was draft-ietf-sipcore-rfc4244bis) | 53 | 27 |  |  | Tue 13/09/11 | Wed 27/11/13
4184 | 440070 | Operational description of the Inter-IMS Network to Network Interface (II-NNI) | II-NNI | 1 | Rel-9 | C3,IETF | 2009-05-29 08:00 | 2014-12-09 17:00 | 100% | CP-090331 | - | Orange | sebastien.daudet@orange-ftgroup.com | - | - | 44 | 23 |  |  | Fri 29/05/09 | Thu 28/02/13
4185 | 440170 | Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3 | 2009-05-29 08:00 | 2010-06-04 17:00 | 100% | CP-090331 | - | Orange | - | CP#48 completed | 29.165 | 44 | 23 |  |  | Fri 20/04/12 | Thu 27/05/10
4186 | 561004 | (IETF) Operational description of the Inter-IMS Network to Network Interface (RFC 7329) | II-NNI | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-09-12 17:00 | 100% | CP-090331 | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#65 complete | RFC 7329 (was draft-kaplan-insipid-session-id) | 56 | 29 |  |  | Fri 20/04/12 | Wed 03/09/14
4187 | 561005 | (IETF) Operational description of the Inter-IMS Network to Network Interface (RFC 7316) | II-NNI | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-09-12 17:00 | 100% | CP-090331 | - | Keith Drage | Keith Drage | CP#65 complete | RFC 7316 (was draft-vanelburg-dispatch-private-network-ind) | 56 | 29 |  |  | Fri 20/04/12 | Wed 03/09/14
4188 | 561006 | (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-09 17:00 | 100% | CP-090331 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Dec.14: 75->90; 7/3/16: 90%->100 | draft-ietf-salud-alert-info-urns | 56 | 29 |  |  | Fri 20/04/12 | Mon 07/03/16
4189 | 561007 | (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-09 17:00 | 100% | CP-090331 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui). Jun 15: RFC 7433 (was draft-ietf-cuss-sip-uui) | RFC 7433 | 56 | 29 |  |  | Fri 20/04/12 | Tue 10/03/15
4190 | 561008 | (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-09 17:00 | 100% | CP-090331 | - | Keith Drage | Keith Drage | In RFC Editors Queue. Dec.14: 75->90. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui-isdni). June 15: RFC 7434 (was draft-ietf-cuss-sip-uui-isdn) | RFC 7434 | 56 | 29 |  |  | Fri 20/04/12 | Thu 04/12/14
4191 | 561009 | Deleted - (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2013-12-06 17:00 | 100% | CP-090331 | - | Peter Dawes | peter.dawes@vodafone.com | CP#62 removed from Rel-8 to Rel-11. Not completed internet-draft | Rel-12 remains draft-dawes-sipping-debug | 56 | 29 | SP-69 |  | Fri 20/04/12 | Wed 27/11/13
4192 | 591002 | Deleted - (IETF) Operational description of the Inter-IMS Network to Network Interface (avasarala-dispatch-comm-div-notification) | II-NNI | 2 | Rel-9 | C3-IETF | 2013-03-01 08:00 | 2014-06-13 17:00 | 100% | CP-090331 | - | Andrew Allen | Andrew Allen | CP#64 Draft removed from 3GPP documentation | draft-avasarala-dispatch-comm-div-notification | 59 | 30 | SP-69 |  | Thu 21/02/13 | Fri 06/06/14
4193 | 450005 | Definition of Ml interface for Control Plane LCS (Stage 3) | EMC2 | 1 | Rel-9 | C1 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | CP-090746 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed [Stage 3 for Rel-7 Emergency Calls (EMC1)]. Related to Rel-9 UID_400038 LCS Control Plane Solution for EPS. Stage 2 in Rel-9 UID_400038 (23.271), UID_410037 (23.167) | 24.229 | 45 | 23 |  |  | Thu 17/09/09 | Tue 02/03/10
4194 | 450009 | PCC enhancements | PCC-Enh | 1 | Rel-9 | C3 | 2009-09-18 08:00 | 2009-12-04 17:00 | 100% | CP-090744 | - | Huawei | Wei Weihua (weiwh@huawei.com) | CP#46 completed | 29.212, 29.213, 29.215 | 45 | 23 |  |  | Thu 05/03/09 | Thu 17/09/09
4195 | 460004 | 3GPP IMS Conferencing Management Object (MO) | IMS_ConfMO | 1 | Rel-9 | C1 | 2009-12-03 08:00 | 2009-12-04 17:00 | 100% | - | - | - | - | CP#46 completed. Linked to Rel-6 UID_11051 (IMS Management objects) under the Feature UID_32021 (IMS Phase 2). MO compatible with OMA DM v1.2 & upwards and defined using OMA DM Device Description Framework (OMA-ERELD _DM-V1_2) | New 24.166 | 46 | 24 |  |  | Tue 08/12/09 | Tue 09/02/10
4196 | 470004 | In Case of Emergency (ICE) Graphics | ICE_Graphics | 1 | Rel-9 | C6 | 2010-03-17 08:00 | 2010-03-19 17:00 | 100% | CP-100178 | - | Sagem-Orga | heiko.kruse@sagem-orga.com | CP#47 approved WID and completed. Added capability to store ICE graphical information (picture). Linked to CT6 Rel-8 ICE Feature UID_380059 In Case of Emergency numbers storage and easy access on UICC | 31.102 CR#0433 | 47 | 24 |  |  | Tue 09/03/10 | Wed 17/03/10
4197 | 410023 | Rel-9 Improvements of the Radio Interface | RInImp9 | 1 | Rel-9 | RP,GP | 2008-09-12 08:00 | 2010-03-19 17:00 | 100% | - | - | - | - | RP#41 umbrella Feature created to host Rel-9 WIs | GERAN, UTRA, LTE | 41 | 21 |  |  | Tue 04/01/05 | Tue 16/03/10
4198 | 410017 | LCR TDD UE OTA Performance Requirements | RInImp9-RFLCROTA | 2 | Rel-9 | R4 | 2008-09-12 08:00 | 2009-05-29 17:00 | 100% | RP-080744 | RP-090389 | RITT | Wu Xiang (wuxiang@chinattl.com) | RP#44 completed technical work (RAN4 internal TR abandoned) | UTRA (no TR 25.8xy produced) | 41 | 21 |  |  | Thu 11/09/08 | Wed 09/09/09
4199 | 410019 | RF requirements for Multicarrier and Multi-RAT BS | RInImp9-RFmulti | 2 | Rel-9 | R4,G1 | 2008-11-21 08:00 | 2010-03-19 17:00 | 100% | RP-091381 | - | Ericsson | Johan.skold@ericsson.com | RP#47 completed. RF requirements specification applicable to Multi-Standard Radio (MSR) Base Station with multiple carriers and/or multiple 3GPP Radio Access Technologies (RAT) | GERAN, UTRA, LTE | 41 | 21 |  |  | Thu 11/09/08 | Tue 16/03/10
4200 | 420009 | RAN4 part of RF requirements for Multicarrier and Multi RAT BS | RInImp9-Rfmulti | 3 | Rel-9 | R4 | 2008-12-05 08:00 | 2010-03-19 17:00 | 100% | RP-091381 | RP-100027 | Ericsson | johan.skold@ericsson.com | RP#48 completed | UTRA, LTE 25.104, 25.105, 36.104, new 37.104, 37.113, 37.141, 37.900 | 42 | 22 |  |  | Sun 23/11/08 | Tue 01/06/10
4201 | 420001 | GERAN part of RF requirements for Multicarrier and Multi RAT BS | RInImp9-RFmulti-GERAN | 3 | Rel-9 | G1 | 2008-11-21 08:00 | 2009-11-20 17:00 | 100% | GP-081945 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#44 Core spec completed. GP#40 WID approved | GERAN 45.005, 51.021 | 40 | 22 |  |  | Sun 23/11/08 | Fri 20/11/09
4202 | 420010 | Extended UMTS/LTE 800 MHz | RInImp9-UMTSLTE800 | 2 | Rel-9 | R4,R2,R3 | 2008-12-05 08:00 | 2008-12-05 08:00 | 100% | RP-080884 | RP-090687 | NTT DoCoMo | Shingo Suwa (suwas@nttdocomo.co.jp) | RP#45 completed | UTRA, LTE 25.101, 25.104, 25.113, 25.133, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 25.306, 25.307, 25.331, 36.331, 25.461, 25.466, new 36.800 | 42 | 22 |  |  | Thu 04/12/08 | Wed 07/10/09
4203 | 430009 | UMTS/LTE 800 MHz for Europe | RInImp9-UMTSLTE800EU | 2 | Rel-9 | R4,R2,R3 | 2009-03-06 08:00 | 2009-03-06 08:00 | 100% | RP-090156 | RP-100028 | Ericsson | olav.queseth@ericsson.com | RP#47 completed | UTRA, LTE 25.101, 25.104, 25.113, 25.133, 25.141, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, new 36.810, 25.306, 25.307, 25.331, 36.331, 25.461, 25.466 | 43 | 22 |  |  | Thu 26/02/09 | Tue 16/03/10
4204 | 430010 | Performance requirement for LCR TDD with UE speeds up to 350 km/h | RInImp9-LCRTDD350 | 2 | Rel-9 | R4 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090258 | RP-091035 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#46 completed | UTRA 25.102, 25.105, 25.142 | 43 | 22 |  |  | Fri 27/02/09 | Wed 02/12/09
4205 | 440004 | Extended UMTS/LTE 1500 MHz | UMTSLTE1500 | 2 | Rel-9 | R4,R2,R3 | 2009-05-30 08:00 | 2009-05-30 08:00 | 100% | RP-090470 | RP-100029 | NTT DoCoMo | Shingo Suwa (suwas@nttdocomo.co.jp) | RP#47 completed. For potential deployment in Japan | UTRA, LTE 25.101, 25.104, 25.113, 25.133, 25.141, 25.306, 25.307, 25.331, 25.461, 25.466, 34.124, 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.331, new (36.821, 36.307) | 44 | 23 |  |  | Fri 22/05/09 | Tue 16/03/10
4206 | 440006 | Rel-9 Improvements of the Radio Interface - UE Conformance Testing | - | 1 | Rel-9 | R5 | 2009-05-19 08:00 | 2010-09-17 17:00 | 100% | - | - | - | - | - | UTRA, LTE | 44 | 23 |  |  | Mon 18/05/09 | Thu 28/05/09
4207 | 440007 | Conformance Test Aspects – UMTS/LTE in 800 MHz for Europe | RInImp-UEConTest-UMTSLTE800EU | 2 | Rel-9 | R5 | 2009-05-19 08:00 | 2010-09-17 17:00 | 100% | RP-090485 | RP-100736 | Ericsson | fredrik.sundstrom@ericsson.com | RP#49 completed. Testing for UID_430009 UMTS/LTE 800 MHz for Europe | UTRA, LTE 34.108, 34.121-1, 34.121-2, 36.508, 36.521-1, 36.521-2, 36.521-3 | 44 | 23 |  |  | Mon 18/05/09 | Wed 08/09/10
4208 | 450017 | Conformance Test Aspects – Extended UMTS/LTE 1500 MHz | UMTSLTE1500_UEConTest | 2 | Rel-9 | R5 | 2009-09-18 08:00 | 2010-06-04 17:00 | 100% | RP-091366 | RP-100487 | NTT DoCoMo | Nguyen Dung Dao (dao@nttdocomo.co.jp) | RP#48 completed | UTRA, LTE 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 36.508, 36.521-1, 36.521-2, 36.521-3, 36.523-1, 36.523-2, 36.523-3 | 45 | 23 |  |  | Tue 15/09/09 | Tue 01/06/10
4209 | 440012 | TDD UE Over The Air (Antenna) conformance testing methodology | UEAnt_TDDTest | 2 | Rel-9 | R5 | 2009-05-30 08:00 | 2009-09-18 17:00 | 100% | RP-090621 | RP-090727 | CATR | Qu Yan (quyan@emcite.com) | RP#45 completed. Finalized TDD UE test methodology based on R4 TR 25.914 (UE and MS antenna performance evaluation method) and TS 25.144 Over the Air (Antenna) minimum performance requirements for the speech mode (terminal close to head) | UTRA 34.114 | 44 | 23 |  |  | Wed 20/05/09 | Thu 10/09/09
4210 | 470019 | Conformance Test Aspects – Performance requirement for LCR TDD with UE speeds up to 350 km/h | RInImp9-LCRTDD350_UEConTest | 2 | Rel-9 | R5 | 2010-03-19 08:00 | 2010-06-04 17:00 | 100% | RP-100167 | RP-100496 | CATT | Xiaozhong Chen (chexiaozhong@datangmobile.cn) | RP#48 completed. Testing for UID_430010 Performance requirement for LCR TDD with UE speeds up to 350 km/h | UTRA 34.122 | 47 | 24 |  |  | Wed 17/03/10 | Tue 01/06/10
4211 | 450018 | Conformance Test Aspects – SMS over IMS in E-UTRAN | SMSoverIMS_UEConTest | 1 | Rel-9 | R5 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | RP-090959 | RP-100072 | Alcatel-Lucent | Nidal Khrais (khrais@alcatel-lucent.com) | RP#47 completed | LTE 34.229-1, 34.229-2, 34.229-3 | 45 | 23 |  |  | Tue 15/09/09 | Tue 16/03/10
4212 | 430013 | Rel-9 RAN improvements | - | 1 | Rel-9 | RP | 2009-03-06 08:00 | 2010-09-08 17:00 | 100% | - | - | - | - | RP#47 completed | UTRA | 43 | 22 |  |  | Fri 06/03/09 | Wed 08/09/10
4213 | 430014 | Dual-Cell HSUPA | RANimp-DC_HSUPA | 2 | Rel-9 | R1,R2,R3,R4 | 2009-03-06 08:00 | 2009-03-06 08:00 | 100% | RP-090014 | RP-100030 | Nokia Siemens Networks | Karri Ranta-aho (karri.ranta-aho@nsn.com) | RP#47 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.319, 25.306, 25.321, 25.331, 25.423, 25.433 | 43 | 22 |  |  | Fri 06/03/09 | Tue 16/03/10
4214 | 430015 | Support for different bands for Dual-Cell HSDPA | RANimp-MultiBand_DC_HSDPA | 2 | Rel-9 | R4,R2,R3 | 2009-03-06 08:00 | 2009-03-06 08:00 | 100% | RP-090973 | RP-091038 | Nokia Siemens Networks | Tuomo Säynäjäkangas (tuomo.saynajakangas@nsn.com) | RP#46 completed. RP#62 existing TS 25.317 replaced by new TS 25.327 | 25.101, 25.104, 25.133, 25.306, 25.308, 25.331, 25.423, 25.433, new 25.317 replaced by new TS 25.327 | 43 | 22 |  |  | Fri 06/03/09 | Thu 26/11/09
4215 | 430016 | Combination of DC-HSDPA with MIMO | RANimp-DC_MIMO | 2 | Rel-9 | R1,R2,R3,R4 | 2009-03-06 08:00 | 2009-03-06 08:00 | 100% | RP-090332 | RP-091039 | Ericsson | johan.bergman@ericsson.com | RP#46 completed | 25.101, 25.104, 25.133, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.321, 25.331, 26.306, 25.423, 25.433 | 43 | 22 |  |  | Fri 06/03/09 | Fri 27/11/09
4216 | 430018 | Transmit Antenna Array (TxAA) extension for non-MIMO UEs | RANimp-TxAA_nonMIMO | 2 | Rel-9 | R1,R2,R3,R4 | 2009-03-06 08:00 | 2009-03-06 08:00 | 100% | RP-090013 | RP-091040 | Nokia | Arto Lehti (arto.lehti@nokia.com) | RP#46 completed | 25.101, 25.104, 25.211, 25.212, 25.213, 25.214, 25.215, 25.308, 25.306, 25.321, 25.331, 25.423, 25.433 | 43 | 22 |  |  | Fri 06/03/09 | Thu 26/11/09
4217 | 440014 | Cell Portion for 1.28 Mcps TDD | CP_LCRTDD | 2 | Rel-9 | R3,R1,R4 | 2009-03-06 08:00 | 2010-09-08 17:00 | 100% | RP-090659 | RP-091041 | CATT | Ying Zhang (zhangying2@datangmobile.cn) | RP#46 completed | 25.102, 25.105, 25.123, 25.225, 25.423, 25.433 | 44 | 23 |  |  | Thu 28/05/09 | Thu 26/11/09
4218 | 490025 | Rel-9 RAN improvements - UE Conformance Testing | - | 1 | Rel-9 | R5 | 2010-09-17 08:00 | 2012-12-07 17:00 | 100% | - | - | - | - | - | - | 49 | 25 |  |  | Wed 08/09/10 | Mon 20/09/10
4219 | 490019 | Conformance Test Aspects – Combination of DC-HSDPA with MIMO | RANimp-DC_MIMO_UEConTest | 2 | Rel-9 | R5 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | RP-101001 | RP-110510 | Ericsson | leif.mattisson@ericsson.com | UTRA. RP#52 completed. Testing for Rel-9 UID_430016 Combination of DC-HSDPA with MIMO | UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 49 | 25 |  |  | Wed 08/09/10 | Wed 18/05/11
4220 | 510014 | Conformance Test Aspects – Dual-Cell HSUPA | RANimp-DC_HSUPA_UEConTest | 2 | Rel-9 | R5 | 2011-03-18 08:00 | 2012-12-07 17:00 | 100% | RP-110116 | RP-121524 | Ericsson | leif.mattisson@ericsson.com | RP#58 completed. Testing for Rel-9 UID_430014 Dual-Cell HSUPA | UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 51 | 26 |  |  | Thu 10/03/11 | Wed 28/11/12
4221 | 510013 | Conformance Test Aspects – Support for different bands for Dual-Cell HSDPA | RANimp-MultiBand_DC_HSDPA_UEConTest | 2 | Rel-9 | R5 | 2011-03-18 08:00 | 2012-03-02 17:00 | 100% | RP-110115 | RP-120036 | Ericsson | leif.mattisson@ericsson.com | RP#55 completed. Testing for Rel-9 UID_430015 Support for different bands for Dual-Cell HSDPA | UTRA 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 51 | 26 |  |  | Thu 10/03/11 | Thu 23/02/12
4222 | 420007 | LTE improvements | LTEimp | 1 | Rel-9 | R1,R2,R4,R5 | 2009-03-06 08:00 | 2011-06-03 17:00 | 100% | - | - | - | - | - | LTE | 42 | 22 |  |  | Tue 02/12/08 | Wed 21/01/09
4223 | 430019 | LTE Pico NodeB RF Requirements | LTEimp-Pico_eNB-RF | 2 | Rel-9 | R4 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-091155 | RP-091045 | Huawei | Liyan Yin (yinliyan@huawei.com) | RP#46 completed | 36.104, 36.141, new 36.931 | 43 | 22 |  |  | Fri 27/02/09 | Mon 08/02/10
4224 | 430029 | Enhanced Dual-Layer transmission for LTE | LTEimp-eDL | 2 | Rel-9 | R1,R2,R4 | 2009-03-06 08:00 | 2009-03-06 08:00 | 100% | RP-091385 | RP-100034 | China Mobile | Xu Xiaodong (xuxiaodong@chinamobile.com) | RP#47 completed | 36.101, 36.211, 36.212, 36.213, 36.331 | 43 | 22 |  |  | Tue 10/03/09 | Tue 01/06/10
4225 | 490018 | UE Conformance Test Aspects – Enhanced Dual-layer transmission for LTE TDD | LTEimp-eDL_UEConTest | 2 | Rel-9 | R5 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | RP-100868 | RP-110509 | China Mobile | Shanpeng Xiao (xiaoshanpeng@chinamobile.com) | RP#52 completed. Testing for UID_430029 (Enhanced Dual-Layer transmission for LTE) | 36.508, 36.521-1, 36.521-2 | 49 | 25 |  |  | Thu 09/09/10 | Wed 18/05/11
4226 | 420011 | Rel-9 Self-Organizing Networks (SON) | SON | 1 | Rel-9 | R3,R2 | 2009-03-06 08:00 | 2009-03-06 08:00 | 100% | RP-090162 | RP-100038 | Nokia Siemens Networks | krzysztof.kordybach@nsn.com | RP#47 completed | LTE 25.413, 36.300, 36.413, 36.423, 48.018, New 36.902 | 42 | 22 |  |  | Fri 05/12/08 | Wed 10/03/10
4227 | 38002 | AGNSS Performances and Testing Procedures | AGNSSPTP | 1 | Rel-9 | G1,G3new | 2008-05-16 08:00 | 2011-05-20 17:00 | 100% | GP-092342 | - | Thales | Michel.monnerat@thalesaleniaspace.com | GP#46 still ongoing MS testing. Linked to Rel-10 RAN4 UID_450027 (AGNSS Minimum Performance for UTRAN) | - |  |  |  |  | Mon 19/05/08 | Fri 12/02/10
4228 | 38003 | AGNSS Minimum Performances | AGNSSPTP-Perfreq | 2 | Rel-9 | G1 | 2008-05-16 08:00 | 2010-03-05 17:00 | 100% | GP-081786 | - | Thales | Michel.monnerat@thalesaleniaspace.com | GP#45 completed (open performance requirements alignment GPS/Galileo) | 45.005 |  |  |  |  | Mon 19/05/08 | Wed 10/03/10
4229 | 38004 | AGNSS Testing Procedures | AGNSSPTP-MStest | 2 | Rel-9 | G3new | 2008-05-16 08:00 | 2011-05-20 17:00 | 100% | GP-092343 | - | Thales | Michel.monnerat@thalesaleniaspace.com | GP#50 completed | 51.010-1, new 51.010-7 |  |  |  |  | Mon 19/05/08 | Sat 21/05/11
4230 | 420002 | Voice services over Adaptive Multi-user channels on One Slot | VAMOS | 1 | Rel-9 | GP,G1,G2,G3new | 2008-11-21 08:00 | 2012-03-02 17:00 | 100% | GP-081949 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | Triggered by UID_50590 (MUROS) Study on Multi-User Reusing-One-Slot | - | 42 | 22 |  |  | Sun 23/11/08 | Thu 27/05/10
4231 | 420003 | Stage 2 for Voice services over Adaptive Multi-user channels on One Slot | VAMOS | 2 | Rel-9 | GP,G1,G2 | 2008-11-21 08:00 | 2010-05-21 17:00 | 100% | GP-081964 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | GP#46 completed. GP#40 WID approved | 45.001 | 40 | 22 |  |  | Sun 23/11/08 | Thu 27/05/10
4232 | 420004 | Stage 3 for Voice services over Adaptive Multi-user channels on One Slot | VAMOS | 2 | Rel-9 | GP,G1,G2 | 2008-11-24 08:00 | 2011-03-04 17:00 | 100% | GP-081965 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | GP#49 completed. GP#40 WID approved | 24.008, 44.018, 45.002, 45.003, 45.004, 45.008, 48.008, 48.058 | 40 | 22 |  |  | Sun 23/11/08 | Fri 04/03/11
4233 | 420005 | VAMOS Radio Performance Requirements | VAMOS | 2 | Rel-9 | GP,G1,G2 | 2008-11-24 08:00 | 2011-05-20 17:00 | 100% | GP-081966 | - | Nokia Siemens Networks, China Mobile | juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com | GP#50 completed. GP#40 WID approved | 45.005 | 40 | 22 |  |  | Sun 23/11/08 | Sat 21/05/11
4234 | 490005 | VAMOS - MS conformance testing | VAMOS_MStest | 2 | Rel-9 | G3new | 2010-09-03 08:00 | 2012-03-02 17:00 | 100% | GP-101604 | - | BlackBerry | Raveendra Seetharam (rseetharam@rim.com) | GP#53 completed. GP#47 WID approved | 51.010-1, 51.010-2 | 47 | 25 |  |  | Sat 04/09/10 | Fri 02/03/12
4235 | 500001 | VAMOS - BTS conformance testing | VAMOS_BTStest | 2 | Rel-9 | G1 | 2010-11-26 08:00 | 2011-09-02 17:00 | 100% | GP-102005 | - | Nokia Siemens Networks | eddie.riddington@nsn.com | GP#51 completed. GP#48 WID approved | 51.021 | 48 | 26 |  |  | Sat 27/11/10 | Sat 21/05/11
4236 | 440002 | Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre (BSC-CBC) | CEBRO | 1 | Rel-9 | GP,C1 | 2009-05-15 08:00 | 2010-03-19 17:00 | 100% | GP-091022 | - | Ericsson | claes-goran.persson@ericsson.com | CP#47 completed. GP#45 completed. GP#42 WID approved | - | 42 | 23 |  |  | Mon 18/05/09 | Fri 05/03/10
4237 | 440102 | GERAN part of Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre | CEBRO | 2 | Rel-9 | GP | 2009-05-15 08:00 | 2010-03-05 17:00 | 100% | GP-091022 | - | Ericsson | claes-goran.persson@ericsson.com | GP#45 completed. GP#42 WID approved | new 48.049 | 42 | 23 |  |  | Mon 18/05/09 | Fri 05/03/10
4238 | 440202 | CT1 part of Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre | CEBRO | 2 | Rel-9 | C1 | 2009-05-15 08:00 | 2010-03-19 17:00 | 100% | GP-091022 | - | Ericsson | claes-goran.persson@ericsson.com | CP#47 completed | 23.041 | 42 | 23 |  |  | Mon 18/05/09 | Tue 02/03/10
4239 | 440003 | Hybrid Location | HILT | 1 | Rel-9 | GP | 2009-05-18 08:00 | 2009-11-20 17:00 | 100% | GP-091075 | - | TruePosition | Matt Ward (mward@trueposition.com) | GP#44 completed. GP#42 WID approved (Hybrid Integrated Location Technology=HILT) | 43.059, 48.071 | 42 | 23 |  |  | Mon 18/05/09 | Mon 07/09/09
4240 | 420099 | (Small) Technical Enhancements and Improvements for Rel-9 | TEI9 | 1 | Rel-9 | SP,CP,RP,GP | 2008-09-15 08:00 | 2009-12-10 17:00 | 100% | - | - | - | - | SP#46 completed | - | 42 | 22 |  |  | Fri 04/11/05 | Wed 25/11/09
4241 | 460002 | Test - (Small) Technical Enhancements and Improvements for Rel-9 | TEI9_Test | 1 | Rel-9 | R5,G3new | 2009-11-20 08:00 | 2010-12-24 17:00 | 100% | - | - | - | - | GP#44 created | - | 44 | 24 |  |  | Wed 25/11/09 | Sun 05/09/10
4242 | 330017 | Deleted - Services Alignment and Migration | ServAl | 1 | Rel-9 | S1 | 2006-12-06 08:00 | 2008-09-18 17:00 | 100% | SP-070126 | - | Telefónica O2 | chris.friel@O2.com | SP#41 closed (no tangible result of this work; no CR against TR 22.983). Triggered by Study UID_370086 (FSServAl) | - | 33 |  | SP-41 | PCG-21 | Fri 06/10/06 | Thu 05/08/10
4243 | 410001 | Deleted - Stage 1 for ServAl | - | 2 | Rel-9 | S1 | 2006-12-06 08:00 | 2008-09-18 17:00 | 100% | SP-070126 | - | Telefónica O2 | chris.friel@O2.com | SP#41 closed (no tangible result of this work; no CR against TR 22.983) | 22.983 | 33 | 21 | SP-41 | PCG-21 | Fri 06/10/06 | Thu 05/08/10
4244 | 380071 | Deleted - Harmonization of Gq'/Rx for Common IMS | IMS_Comm_GqRx_Harm | 1 | Rel-9 | S2 | 2008-01-14 08:00 | 2009-03-12 17:00 | 100% | SP-070822 | - | Alcatel-Lucent | geoffrey.cristallo@alcatel-lucent.be | SP#43 stopped. LS_out to TISPAN informs about stopping this activity | 23.822, 23.203 | 38 | 21 | SP-43 | PCG-22 | Tue 02/10/07 | Tue 24/03/09
4245 | 380081 | Deleted - Support of WiMAX - LTE Mobility | WiMAX_LTE_Mobility | 1 | Rel-9 | R2 | 2008-06-06 08:00 | 2009-12-25 17:00 | 100% | RP-070511 | - | Samsung | - | RP#39: No agreed WID | 36.306, 36.331, 36.413, 36.300, 36.214, 36.133, 36.304 | 38 | 21 | SP-39 | PCG-21 | Mon 17/12/07 | Tue 24/03/09
4246 | 380082 | Deleted - Support of WiMAX - UMTS Mobility | WiMAX_UMTS_Mobility | 1 | Rel-9 | R2 | 2008-06-06 08:00 | 2009-12-25 17:00 | 100% | RP-070511 | - | Intel | - | RP#39: No agreed WID | 25.306, 25.331, 25.413 | 38 | 21 | SP-39 | PCG-21 | Mon 17/12/07 | Tue 24/03/09
4247 | 380086 | Deleted - Definition of 3GPP UICC services over the new high-speed interface | UICCHS | 1 | Rel-9 | C6 | 2010-03-19 17:00 | 2010-03-19 17:00 | 100% | CP-070837 | - | Gemalto | Denis.Lheriteau@gemalto.com | CP#47 work stopped/abandoned | 31.xyz | 38 | 21 | CP-47 | PCG-24 | Thu 31/01/08 | Wed 25/11/09
4248 | 390040 | Deleted - SAES Enhancements (non RAN aspects) | SAES_Ph2 | 1 | Rel-9 | S2 | 2007-06-25 08:00 | 2008-12-08 17:00 | 100% | - | - | Nokia Siemens Networks | - | SP#39 created to host Rel-9 Wis. BUT no agreed WID | - | 39 | 21 | SP-39 | PCG-21 | Mon 31/01/05 | Tue 24/03/09
4249 | 350028 | Deleted - Functions and procedures for SAE to support LTE MBMS | SAES_Ph2 | 2 | Rel-9 | S2 | 2007-06-25 08:00 | 2008-12-08 17:00 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. WID returned to SA2 for re-consideration & remove MBMS for EPS from Rel 8 | - | 35 |  | SP-39 | PCG-21 | Thu 29/03/07 | Tue 24/03/09
4250 | 390041 | Deleted - CS over EPS | SAES_Ph2 | 2 | Rel-9 | S2 | 2008-03-12 08:00 | 2008-12-08 17:00 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. BUT no agreed WID | - | 39 | 21 | SP-39 | PCG-21 | Thu 29/03/07 | Tue 24/03/09
4251 | 390042 | Deleted - SAE for generic support for non-3GPP accesses | SAES_Ph2 | 2 | Rel-9 | S2 | 2007-06-25 08:00 | 2008-06-09 17:00 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. BUT no agreed WID | - | 39 | 21 | SP-39 | PCG-21 | Thu 29/03/07 | Tue 24/03/09
4252 | 390043 | Deleted - Single Radio Aspects of SAE for Optimized Handover with WiMAX | SAES_Ph2 | 3 | Rel-9 | S2 | 2007-06-25 08:00 | 2008-06-09 17:00 | 100% | - | - | - | - | SP#39 SAE functionality moved to Rel-9. BUT no agreed WID | - | 39 | 21 | SP-39 | PCG-21 | Thu 26/04/07 | Tue 24/03/09
4253 | 440071 | Deleted - Lawful Interception in the 3GPP Rel-9 | LI9 | 1 | Rel-9 | S3 | 2009-06-04 08:00 | 2010-03-25 17:00 | 100% | SP-090831 | - | PIDS, Nortel | Koen Jaspers, Ronald Ryan | SP#47 stopped. WI + new topics moved to Rel-10 | 33.106, 33.107, 33.108 | 44 | 23 | SP-47 | PCG-24 | Tue 02/06/09 | Mon 01/03/10
4254 | 0 | Release 9 Studies | - | 1 | Rel-9 | CP,RP,SP | 2008-06-05 08:00 | 2008-06-05 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 09/02/10
4255 | 400036 | Study on Service Specific Access Control in EPS | FS_SSAC | 1 | Rel-9 | S1 | 2008-06-05 08:00 | 2008-12-11 17:00 | 100% | SP-080319 | - | NTT DoCoMo | Shin-ichi Isobe (isobes@nttdocomo.co.jp) | SP#42 completed. Spin-off Feature UID_420020 (SSAC) | 22.986 | 40 | 21 |  |  | Thu 13/12/07 | Tue 31/08/10
4256 | 350052 | Study on CS Domain Services over EPS access | FS_CSoPS | 1 | Rel-9 | S2 | 2007-04-25 08:00 | 2009-03-12 17:00 | 100% | SP-080800 | - | T-Mobile | Karl-Heinz.Nenner@T-Mobile.net | SP#43 completed. Linked to Combinational Services UID_31064, Services Alignment and Migration (ServAl) UID_330017 and 3GPP System Architecture Evolution (SAES) UID_3208 | 23.879 | 35 |  |  |  | Thu 29/03/07 | Mon 09/08/10
4257 | 370043 | Study on Extended Support of IMS Emergency Calls | FS_IMS-eCall | 1 | Rel-9 | S2 | 2007-09-24 08:00 | 2008-12-11 17:00 | 100% | SP-070547 | - | Qualcomm | Stephen Edge | SP#42 completed | 23.868 | 37 |  |  |  | Wed 19/07/06 | Sat 22/11/08
4258 | 320031 | Study on Service Continuity for Emergency Voice Calls | FS_VCCEm | 1 | Rel-9 | S2 | 2006-06-08 08:00 | 2009-03-12 17:00 | 100% | SP-080555 | - | Nortel | Ricky Kaura (rkaura@nortel.com) | SP#43 completed | 23.826 | 32 |  |  |  | Wed 19/07/06 | Tue 24/02/09
4259 | 370053 | Study on Security Aspects of Remote Provisioning and Change of Subscription for M2M Equipment | FS_UM2M | 1 | Rel-9 | S3,C6 | 2004-04-06 15:48 | 2009-12-10 17:00 | 100% | SP-070702 | - | Ericsson | vesa.lehtovirta@ericsson.com | SP#46 completed. Triggered by the SA1 Rel-8 Study on Facilitating Machine to Machine Communication in GSM and UMTS (FS_M2M) UID_7027 in TR 22.868. | 33.812 | 37 |  |  |  | Mon 19/11/07 | Tue 08/12/09
4260 | 360006 | Study on System Maintenance over Itf-N | FS_OAM-Maint-Itf-N | 1 | Rel-9 | S5 | 2007-06-07 08:00 | 2009-09-24 17:00 | 100% | SP-070306 | - | ZTE | Shuqiang Huang (huangsq@zte.com.cn) | SP#45 completed | 32.822 | 36 |  |  |  | Mon 28/05/07 | Mon 07/09/09
4261 | 360007 | Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB | FS_OAM-SON-HNB | 1 | Rel-9 | S5 | 2007-06-07 08:00 | 2009-06-04 17:00 | 100% | SP-080461 | - | Huawei | Zou Lan (zlan@huawei.com) | SP#44 completed. Linked to SA5 TR 32.816 Study of Management for LTE and SAE (UID_340036) | 32.821 | 36 |  |  |  | Mon 28/05/07 | Mon 18/05/09
4262 | 390017 | Study on Self-healing of Self-Organizing Networks (SON) | FS_OAM-SON-SH | 1 | Rel-9 | S5 | 2008-02-22 08:00 | 2009-09-24 17:00 | 100% | SP-080076 | - | ZTE | zhu.weihong@zte.com.cn | SP#45 completed. Linked to SA5 TR 32.816 Study of Management for LTE and SAE (UID_340036) | 32.823 | 39 | 21 |  |  | Mon 28/05/07 | Mon 07/09/09
4263 | 400029 | Study on Service Oriented Architecture (SOA) for IRP | FS_OAM_SOA_IRP | 1 | Rel-9 | S5 | 2008-06-05 08:00 | 2009-06-04 17:00 | 100% | SP-080281 | - | Ericsson | edwin.tse@ericsson.com | SP#44 completed. Spin-off implementation WI UID_440064 Service Oriented Architecture (SOA) for IRP | 32.824 | 40 | 21 |  |  | Mon 28/05/07 | Tue 02/06/09
4264 | 380079 | Study on Evaluation of the inclusion of Path Loss Based Technology in the UTRAN | FS_RAN-Pathloss | 1 | Rel-9 | R4 | 2007-12-17 08:00 | 2009-12-04 17:00 | 100% | RP-071050 | RP-091080 | Polaris Wireless | Norman Shaw (nshaw@polariswireless.com) | RP#46 completed | 25.907 | 38 | 21 |  |  | Mon 17/12/07 | Thu 26/11/09
4265 | 390031 | Study on LTE-Advanced | FS_RAN_LTEA | 1 | Rel-9 | R1,R2,R3,R4 | 2008-03-21 08:00 | 2010-03-19 17:00 | 100% | RP-091360 | RP-100080 | NTT DoCoMo | Tetsushi Abe | RP#47 completed | 36.913 , New 36.814, 36.912, R2 36.806 (Relay architectures for E-UTRA), R4 36.815 (LTE-Advanced feasibility studies in RAN4) | 39 | 21 |  |  | Mon 17/12/07 | Tue 16/03/10
4266 | 410016 | Study on 1.28 Mcps TDD Home NodeB | FS_RAN-HNBLCRTDD | 1 | Rel-9 | R4 | 2008-02-20 13:00 | 2009-12-04 17:00 | 100% | RP-080767 | RP-091081 | TD Tech | Li Rong (lirong@td-tech.com) | RP#46 completed | 25.866 | 41 | 21 |  |  | Mon 17/12/07 | Thu 03/12/09
4267 | 420012 | Study on E-UTRAN Mobility Evaluation and Enhancement | FS_EUTRAN_mob | 1 | Rel-9 | R1 | 2008-12-05 08:00 | 2009-05-29 17:00 | 100% | RP-081137 | RP-090426 | Qualcomm | Rajat Prakash (rprakash@qualcomm.com) | RP#44 closed (RP-090452 R1 LS to RAN on Conclusions for LTE Mobility Study Item - no further Rel-9 action / no TR needed) | none | 42 | 22 |  |  | Thu 04/12/08 | Wed 20/05/09
4268 | 430021 | Study on Minimization of drive-tests in Next Generation Networks | FS_NGN_min_drive-tests | 1 | Rel-9 | R2 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090341 | RP-091084 | Qualcomm | Masato Kitazoe (mkitazoe@qualcomm.com) | RP#46 completed | 36.805 | 43 | 22 |  |  | Fri 06/03/09 | Fri 27/11/09
4269 | 430027 | Study on Enhanced Interference Management for HNBs | FS_eInterfMgmt_HNB | 1 | Rel-9 | R4 | 2009-03-06 08:00 | 2009-05-29 17:00 | 100% | RP-090361 | RP-090429 | Qualcomm | Farhad Meshkati (fmeshkat@qualcomm.com) | RP#44 completed. Linked to UID_420008 LTE FDD Home eNodeB RF Requirements. Spin-off RAN3 UID_440015 Study on Enhanced Interference Management Mechanisms for HNBs | 25.967 | 43 | 22 |  |  | Tue 10/03/09 | Thu 25/06/09
4270 | 440015 | Study on Enhanced Interference Management Mechanisms for HNBs | FS_eInterfMgmtMchsm_HNB | 1 | Rel-9 | R3 | 2009-05-30 08:00 | 2009-09-18 17:00 | 100% | RP-090667 | RP-090733 | Qualcomm | Farhad Meshkati (fmeshkat@qualcomm.com) | RP#45 completed. Triggered by RAN4 UID_430027 Study on Enhanced Interference Management for HNBs | 25.967 | 44 | 23 |  |  | Tue 26/05/09 | Tue 15/09/09
4271 | 320026 | Deleted - Study on Protection against SMS and MMS spam | FS_CPSMal | 1 | Rel-9 | S3 | 2006-06-08 08:00 | 2009-09-24 17:00 | 100% | SP-060446 | - | Orange | eric.gauthier@orange.ch | SP#45 work stopped/abandoned | 33.9xx | 32 |  | SP-45 | PCG-23 | Fri 23/06/06 | Mon 21/09/09
4272 | 0 | Release 8 Features | - | 1 | Rel-8 | CP,GP,RP,SP | 2006-09-19 14:36 | 2010-03-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/05/06 | Tue 09/02/10
4273 | 320005 | 3GPP System Architecture Evolution Specification - Evolved Packet System (non RAN aspects) | SAES | 1 | Rel-8 | S1,S2,S3,S5,C1,C3,C4,C6,IETF | 2006-04-12 08:00 | 2012-06-15 17:00 | 100% | SP-080132 | - | T-Mobile | michael.kurz@t-mobile.at | Role model for SAE/LTE system wide project management by SA2 in SP-060166 | - | 32 |  |  |  | Mon 31/01/05 | Tue 08/12/09
4274 | 320022 | Requirements for evolution of the 3GPP system architecture | AIPN-SAE | 2 | Rel-8 | S1 | 2006-06-08 08:00 | 2007-12-12 17:00 | 100% | SP-080132 | - | T-Mobile | michael.kurz@t-mobile.at | SP#38 completed | 22.011, 22.246, New 22.278 | 32 |  |  |  | Fri 23/06/06 | Wed 28/07/10
4275 | 370005 | High level and common (for all accesses) functions | EPS-ComF | 2 | Rel-8 | S2,S3,C1,C3,C4 | 2007-01-02 08:00 | 2009-05-29 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | CP#44 completed | - | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
4276 | 350024 | Stage 2 for High level functions | SAES-SA-HLF | 3 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-06-02 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#40 completed | New 23.402 | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
4277 | 390044 | Stage 2 Security Architecture | SAES | 3 | Rel-8 | S3 | 2008-03-12 08:00 | 2008-12-11 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | marc.blommaert.ext@nsn.com | SP#42 completed | 33.210, 33.310, New 33.401 | 39 | 21 |  |  | Wed 19/03/08 | Wed 28/07/10
4278 | 340051 | Stage 3 (CT1) for SAE impact on services, network functions and capabilities | SAES | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.229, 27.007, New 24.305 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4279 | 340054 | Stage 3 SAE impact on existing capabilities | SAES | 3 | Rel-8 | C3 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080772 | - | Huawei | Wei Weihua (weiwh@huawei.com) | CP#42 completed | 29.061 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4280 | 340062 | Stage 3 (CT4) of SAE impact on existing capabilities | SAES | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | New (29.274, 29.275) | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4281 | 340049 | Stage 2/3 for Network selection procedures | SAES | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 23.122, New 24.302 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4282 | 340023 | Stage 3 EPC interworking with external PDNs (SGi) | SAES-St3-intwk | 3 | Rel-8 | C3 | 2007-02-05 08:00 | 2009-05-29 17:00 | 100% | CP-080772 | - | Huawei | Wei Weihua (weiwh@huawei.com) | CP#44 completed | 29.061 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4283 | 340022 | Stage 3 PCC within SAE | SAES-St3-PCC | 3 | Rel-8 | C3 | 2007-02-05 08:00 | 2009-05-29 17:00 | 100% | CP-080576 | - | Ericsson | j.javier.pastor@ericsson.com | CP#44 completed | 29.212, 29.213, 29.214, New 29.215 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4284 | 340028 | Stage 3 for SAE / LTE identities | SAES | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 23.003 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4285 | 370017 | Unified guidelines for Diameter usage within 3GPP | SAES-DIAM | 3 | Rel-8 | C3 | 2007-09-21 08:00 | 2008-12-05 17:00 | 100% | CP-080055 | - | Huawei | Javier Gonzalez Gallego | CP#42 completed | New 29.909 | 37 |  |  |  | Tue 25/09/07 | Wed 28/07/10
4286 | 350025 | SAE for LTE access | SAES-LTE | 2 | Rel-8 | S2,C1,C3,C4 | 2007-01-02 08:00 | 2009-03-06 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | CP#43 completed | - | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
4287 | 340060 | CT4 Stage 3 for protocol between EPCs | SAES-LTE | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.275 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4288 | 350042 | SAES-SA-FP_LTE with GTP variant | SAES-SA-FP_LTE-GTP | 3 | Rel-8 | S2,C4 | 2007-01-02 08:00 | 2009-03-06 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | CP#43 completed | - | 35 |  |  |  | Thu 26/04/07 | Wed 28/07/10
4289 | 370006 | Stage 2 for SAES-SA-FP_LTE with GTP variant | SAES-SA-FP_LTE-GTP-St2 | 4 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | 23.401, 23.060, 23.002, 23.246, 23.203, 23.107, 23.234, 23.271 | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
4290 | 340055 | CT4 Stage 3 for GTP v2 protocol | SAES-SA-FP_LTE-GTP | 4 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4291 | 350043 | SAES-SA-FP_LTE with PMIP variant | SAES-SA-FP_LTE-IETF | 3 | Rel-8 | S2,C4 | 2007-01-02 08:00 | 2009-03-06 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | CP#43 completed | - | 34 |  |  |  | Thu 26/04/07 | Wed 28/07/10
4292 | 370007 | Stage 2 for SAES-SA-FP_LTE with PMIP variant | SAES-SA-FP_LTE-IETF-St2 | 4 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | - | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
4293 | 370018 | CT4 Stage 3 for PMIP protocol within EPC | SAES-SA-FP_LTE-IETF | 4 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.275, 29.282 | 37 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4294 | 410004 | Mobile IPv4 (MIPv4) based Mobility protocols | SAES-SA-FP_LTE-IETF | 4 | Rel-8 | C4 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-090247 | - | Motorola | Lewis Milton | CP#42 completed | 29.279 | 41 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4295 | 340020 | Stage 3 for UE Non-Access-Stratum (NAS) mobility procedures in idle and active mode | SAES-LTE | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.007, 24.301 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4296 | 340050 | Stage 3 for Session management, bearer control and QoS aspects | SAES-LTE | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.007, 24.301 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4297 | 340053 | Stage 3 for security aspects of LTE Access | SAES-LTE | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.008, 24.301 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4298 | 340025 | Stage 3 for QoS mechanisms | SAES-LTE | 3 | Rel-8 | C3 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080576 | - | Ericsson | j.javier.pastor@ericsson.com | CP#42 completed | 29.213 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4299 | 340026 | Stage 3 for EPC - HSS interface | SAES-LTE | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.272 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4300 | 350026 | SAE for Interoperation between LTE and legacy cellular PS accesses | SAES-SA-FP_3GPP | 2 | Rel-8 | S2,C1,C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | CP#43 completed | - | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
4301 | 370008 | Stage 2 for Interoperation between LTE and 2G/3G | EPSto2_3G | 3 | Rel-8 | S2 | 2007-02-05 08:00 | 2008-09-18 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#41 completed | 23.401, 23.402 | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
4302 | 380031 | Stage 3 for Inter-system mobility between E-UTRAN and 2G/3G | SAES-SA-FP_3GPP | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.008, 24.301 | 38 | 21 |  |  | Mon 19/11/07 | Wed 28/07/10
4303 | 340018 | Stage 2 GPRS enhancements for LTE access | SAES-GPRS_LTE | 3 | Rel-8 | S2 | 2007-09-04 17:00 | 2008-09-18 17:00 | 100% | SP-080132 | - | Vodafone | chris.pudney@vodafone.com | SP#41 completed | 23.401 | 34 |  |  |  | Fri 23/06/06 | Wed 28/07/10
4304 | 390008 | Stage 2 GPRS for EPC (23.060, etc.) | SAES-SA-FP_3GPP | 3 | Rel-8 | S2 | 2008-01-14 08:00 | 2008-09-18 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#41 completed | 23.060 | 39 | 21 |  |  | Wed 19/09/07 | Wed 28/07/10
4305 | 340056 | Stage 3 for EPC - GPRS | SAES-SA-FP_3GPP | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.275, 29.281 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4306 | 380032 | Stage 3 for EPC to UTRAN | SAES-SA-FP_3GPP | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.275, 29.281 | 38 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
4307 | 380033 | Stage 3 for EPC to 3GPP2 | SAES-SA-FP_3GPP | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.277, 29.276 | 38 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
4308 | 370009 | Stage 2 for Interoperation between LTE and CDMA2000 | EPStoC2k | 3 | Rel-8 | S2 | 2007-06-18 08:00 | 2008-09-18 17:00 | 100% | SP-080132 | - | Motorola, Vodafone | Irfan.Ali@motorola.com, chris.pudney@vodafone.com | SP#41 completed (except: Handover of multiple PDNs=>Rel-9) | 23.401, 23.402 | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
4309 | 360023 | Stage 3 for Inter-system mobility between E-UTRAN and CDMA2000 | SAES-SA-FP_3GPP | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.301, 24.302 | 36 |  |  |  | Wed 12/09/07 | Wed 28/07/10
4310 | 340061 | Stage 3 for MME - SGSN signalling free protocol | SAES-SA-FP_3GPP | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.272, 29.274 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4311 | 350027 | SAE for support for non-3GPP accesses | SAES-SA-FP_n3GPP | 2 | Rel-8 | S2,S3,C1,C4,IETF | 2007-01-02 08:00 | 2012-06-15 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | CP#43 completed. SP#39 retained in Rel-8 (in addition to the essential functionality defined in SP-070699). Replaces UID_340037 | - | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
4312 | 350044 | Stage 2 for Host-based Mobility aspects | SAES-SA-FP_n3GPP-HBMob | 3 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#40 completed | 23.402 | 35 |  |  |  | Thu 26/04/07 | Wed 28/07/10
4313 | 350045 | Stage 2 for Network-based Mobility aspects | SAES-SA-FP_n3GPP-NBMob | 3 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-09-18 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#41 completed | 23.402 | 35 |  |  |  | Thu 26/04/07 | Wed 28/07/10
4314 | 360022 | Stage 3 for Mobility management based on DSMIPv6 | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.303 | 35 |  |  |  | Wed 12/09/07 | Wed 28/07/10
4315 | 521011 | (IETF) Stage 3 for Mobility management based on DSMIPv6 (draft-ietf-mip6-hiopt) | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1-IETF | 2007-02-05 08:00 | 2012-06-15 17:00 | 100% | CP-080493 | - | Mark Jones | - | CP#56 completed | RFC 6610 (was draft-ietf-mip6-hiopt) | 52 | 27 |  |  | Mon 20/06/11 | Thu 14/06/12
4316 | 521012 | (IETF) Stage 3 for Mobility management based on DSMIPv6 (RFC6275) | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1-IETF | 2007-02-05 08:00 | 2011-07-29 17:00 | 100% | CP-080493 | - | - | - | SP#53/IETF#81 completed | RFC 6275 (was draft-ietf-mext-rfc3775bis) | 52 | 27 |  |  | Mon 20/06/11 | Wed 31/08/11
4317 | 390009 | Stage 3 for Mobility management based on MIP v4 | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.304 | 39 | 21 |  |  | Mon 03/03/08 | Wed 28/07/10
4318 | 380030 | Stage 3 for Inter-system mobility between E-UTRAN and non 3GPP accesses | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.008, 24.301 | 38 | 21 |  |  | Mon 19/11/07 | Wed 28/07/10
4319 | 360019 | Stage 2 for Optimized Dual-Radio Handover with WiMAX | SAES-SA-FP_n3GPP-OptWIMAX | 3 | Rel-8 | S2 | 2007-06-25 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Motorola | Irfan.Ali@motorola.com | SP#40 completed | 23.402 | 35 |  |  |  | Thu 26/04/07 | Wed 28/07/10
4320 | 390045 | Stage 2 Security aspects for non-3GPP Access | SAES-SA-FP_n3GPP | 3 | Rel-8 | S3 | 2008-03-12 08:00 | 2008-12-11 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | marc.blommaert.ext@nsn.com | SP#42 completed | 33.402, 33.210, 33.310 | 39 | 21 |  |  | Wed 19/03/08 | Wed 28/07/10
4321 | 370010 | Stage 3 security aspects for DSMIPv6 Access | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.303 | 37 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4322 | 390172 | Stage 3 security aspects for MIPv4 Access | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#42 completed | 24.304 | 39 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
4323 | 360021 | Stage 3 for Access to the EPC via non-3GPP access networks | SAES-SA-FP_n3GPP | 3 | Rel-8 | C1 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-080493 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.302, 24.312 | 36 |  |  |  | Wed 12/09/07 | Wed 28/07/10
4324 | 370011 | Stage 3 for interfaces within EPC | SAES-SA-FP_n3GPP | 3 | Rel-8 | C4 | 2007-09-19 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.274, 29.281 | 37 |  |  |  | Wed 19/09/07 | Wed 28/07/10
4325 | 340057 | Stage 3 for Interfaces EPC - non-3GPP IP access | SAES-SA-FP_n3GPP | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2009-03-06 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#43 completed | 29.273, 29.275 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4326 | 521013 | (IETF) Stage 3 for Interfaces EPC - non-3GPP IP access | SAES-SA-FP_n3GPP | 3 | Rel-8 | C4-IETF | 2007-02-05 08:00 | 2012-06-15 17:00 | 100% | CP-090247 | - | Lionel Morand | - | CP#56 completed | RFC 6611 (was draft-ietf-mip6-bootstrapping-integrated) | 52 | 27 |  |  | Mon 20/06/11 | Fri 20/04/12
4327 | 340058 | Stage 3 for AAA/HSS related | SAES-SA-FP_n3GPP | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#42 completed | 29.273 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4328 | 340059 | Stage 3 for EPC - AAA interface | SAES-SA-FP_n3GPP | 3 | Rel-8 | C4 | 2007-02-05 08:00 | 2008-12-05 17:00 | 100% | CP-090247 | - | Huawei | shahab.lavasani@huawei.com | CP#42 completed | 29.273 | 34 |  |  |  | Wed 19/07/06 | Wed 28/07/10
4329 | 360018 | Deleted (already covered) SAES-SA-FP_n3GPP Optimized Handover with CDMA | SAES-SA-FP_n3GPP-OptCDMA | 3 | Rel-8 | S2 | 2007-06-25 08:00 | 2007-06-25 08:00 | 100% | - | - | Nokia Siemens Networks | - | SP#37 stopped | - | 36 |  | SP-37 |  | Thu 26/04/07 | Tue 24/03/09
4330 | 350030 | Single Radio Voice Call Continuity for 3GPP (SRVCC) | SAES-SRVCC | 2 | Rel-8 | S2,C1,C4 | 2007-01-02 08:00 | 2009-03-06 17:00 | 100% | SP-070949 | - | Nokia Siemens Networks | curt.c.wong@nokia.com | CP#43 completed. SP#38 WID approved (extract from SAE WID SP-070817). | - | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
4331 | 350130 | Stage 2 for 2G/3G SRVCC | SAES-SRVCC | 3 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-09-18 17:00 | 100% | SP-070949 | - | Nokia Siemens Networks | curt.c.wong@nokia.com | SP#41 completed. SP#38 WID approved | New 23.216 | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
4332 | 410005 | Stage 3 for SRVCC in EPS | SAES-SRVCC | 3 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080793 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 23.009, 24.008, New 24.301 | 41 | 21 |  |  | Wed 03/09/08 | Wed 28/07/10
4333 | 410006 | MME to MSC interface for SRVCC | SAES-SRVCC | 3 | Rel-8 | C4 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080793 | - | Nokia Siemens Networks | Giorgi Gulbani | CP#43 completed | 23.003, 23.008, New (29.274, 29.277, 29.280) | 41 | 21 |  |  | Mon 01/09/08 | Wed 28/07/10
4334 | 360020 | Voice Call Continuity for CDMA2000 1X | SAES-VCC_1X | 2 | Rel-8 | S2 | 2007-06-25 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | - | 36 |  |  |  | Thu 29/03/07 | Wed 28/07/10
4335 | 350031 | SAE impacts on IMS | SAES-SA_IMS | 2 | Rel-8 | S2 | 2007-01-02 08:00 | 2008-06-05 17:00 | 100% | SP-080132 | - | Nokia Siemens Networks | balazs.bertenyi@nsn.com | SP#40 completed | - | 35 |  |  |  | Thu 29/03/07 | Wed 28/07/10
4336 | 390036 | CS Fallback in EPS | SAES-CSFB | 2 | Rel-8 | S2,C1,C4 | 2008-03-12 08:00 | 2009-03-06 17:00 | 100% | SP-080097 | - | T-Mobile, Vodafone | sabine.demel@t-mobile.at, chris.pudney@vodafone.com | CP#43 completed | - | 39 | 21 |  |  | Thu 29/03/07 | Wed 28/07/10
4337 | 400001 | Stage 2 for CS Fallback in EPS | SAES-CSFB | 3 | Rel-8 | S2 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080097 | - | T-Mobile, Vodafone | sabine.demel@t-mobile.at, chris.pudney@vodafone.com | SP#40 completed | New (23.272, 23.401) | 40 | 21 |  |  | Thu 29/03/07 | Wed 28/07/10
4338 | 400102 | CT1 part of Stage 3 for CS Fallback in EPS | SAES-CSFB | 3 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080791 | - | NEC | yannick.lair@nectech.fr | CP#43 completed | 24.007, 24.008, 24.011, 29.018, New (24.301, 24.801, 29.118) | 40 | 21 |  |  | Thu 29/03/07 | Wed 28/07/10
4339 | 400003 | CT4 part of Stage 3 for CS Fallback in EPS | SAES-CSFB | 3 | Rel-8 | C4 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080791 | - | NEC | yannick.lair@nectech.fr | CP#42 completed | 23.007, 23.008, 29.274, New 29.277 | 40 | 21 |  |  | Thu 29/03/07 | Wed 28/07/10
4340 | 390039 | System enhancements for the use of IMS services in local breakout | SAES-IMS_LBO | 2 | Rel-8 | S2 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080090 | - | Telecom Italia | mario.madella@telecomitalia.it | SP#40 completed | 23.228, 23.221, 23.203 | 39 | 21 |  |  | Tue 02/10/07 | Wed 28/07/10
4341 | 390010 | EPC Data Definitions | EPC-OAM | 2 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | - | - | - | - | SP#43 completed | - | 39 | 21 |  |  | Fri 17/06/05 | Wed 28/07/10
4342 | 380037 | EPC Network Resource Model (NRM) Integration Reference Point (IRP) | EPC-OAM | 3 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | SP-070737 | - | Huawei | WANG, Xuelong | SP#43 completed | New (32.751, 32.752, 32.753, 32.755) | 38 | 21 |  |  | Fri 17/06/05 | Mon 23/02/09
4343 | 390011 | Performance measurements for EPC | EPC-OAM | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2009-03-12 17:00 | 100% | SP-080061 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#43 completed | New 32.426 | 39 | 21 |  |  | Fri 17/06/05 | Mon 23/02/09
4344 | 380038 | EPC Charging | EPC-CH | 2 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | SP-070736 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#43 completed | 32.240, 32.296, 32.251, 32.252, 32.298, 32.299 | 38 | 21 |  |  | Fri 17/06/05 | Wed 28/07/10
4345 | 400104 | Domain Name System Procedures for Evolved Packet System (DEPS) | SAES-DEPS | 2 | Rel-8 | C4 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080280 | - | TeliaSonera | jouni.korhonen@teliasonera.com | CP#43 completed | 23.003, New 29.303 | 40 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
4346 | 410007 | InterWorking Function (IWF) between MAP based and Diameter based interfaces | SAES-MAP2Diam | 2 | Rel-8 | C4 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080644 | - | Huawei | liming49985@huawei.com | CP#43 completed. Triggered by UID_380023 (FS_MAP2Diam) | New 29.305 | 41 | 21 |  |  | Mon 19/11/07 | Wed 28/07/10
4347 | 390021 | CT6 aspects of SAE | SAES | 2 | Rel-8 | C6 | 2008-03-07 08:00 | 2011-06-03 17:00 | 100% | CP-080164 | - | Nokia | Rune Lindholm | CP#44 completed core specification | - | 39 | 21 |  |  | Wed 12/03/08 | Wed 28/07/10
4348 | 390121 | Core specification for CT6 aspects of SAE | SAES | 3 | Rel-8 | C6 | 2008-03-07 08:00 | 2009-05-29 17:00 | 100% | CP-080164 | - | Nokia | Rune Lindholm | CP#44 completed (specified Network Measurement Results collection via USAT) | 31.102, 31.111 | 39 | 21 |  |  | Wed 12/03/08 | Wed 28/07/10
4349 | 420018 | Test interworking of LTE Terminals with the USIM | SAES-USIM_LTE-Test | 3 | Rel-8 | C6 | 2008-12-05 08:00 | 2010-12-10 17:00 | 100% | CP-100598 | - | Comprion | Udo Willenbrink (uwillenbrink@comprion.com ) | CP#50 completed. Steering of Roaming test cases have been introduced. Remaining issues CSG display testing (Provide Local Information, Call Control for EPS/PDN, Event Download (Access Technology Change - Multiple Access Technologies) | 31.121, 31.124 | 42 | 22 |  |  | Wed 03/12/08 | Sun 28/11/10
4350 | 490015 | Test interworking of IP Multimedia Services Identity Module (ISIM) terminals with IP Multimedia Subsystem (IMS) | SAES-ISIM_IMS_Test | 3 | Rel-8 | C6 | 2010-09-17 08:00 | 2011-06-03 17:00 | 100% | CP-100602 | - | Comprion | Udo Willenbrink (uwillenbrink@comprion.com ) | CP#52 completed. Linked to R5 UID_1273 Provisioning of IP-based multimedia services (24.229, 31.103), R8 UID_390021 CT6 aspects of SAE, UID_420018 Test interworking of LTE Terminals with the USIM, R UID_450018 Testing SMS over IMS in E-UTRAN (34.229). | 31.121, 31.124, New TS 31.134 | 49 | 25 |  |  | Mon 06/09/10 | Wed 18/05/11
4351 | 390018 | Issues for CT1 TR 24.801 | SAES | 2 | Rel-8 | C1 | 2007-01-04 15:00 | 2008-12-05 17:00 | 100% | CP-080068 | - | Nokia Siemens Networks | robert.zaus@nsn.com | CP#43 completed | 24.801 | 39 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
4352 | 390019 | Issues for CT3 TR 29.804 | SAES | 2 | Rel-8 | C3 | 2007-02-05 08:00 | 2008-09-12 17:00 | 100% | CP-080068 | - | Ericsson | j.javier.pastor@ericsson.com | CP#41 completed | 29.804 | 39 | 21 |  |  | Wed 19/07/06 | Wed 28/07/10
4353 | 390020 | Deleted - Issues for CT4 TR 29.803 | SAES | 2 | Rel-8 | C4 | 2007-01-04 15:00 | 2008-09-12 17:00 | 100% | CP-080068 | - | Huawei | - | CP#41 Work stopped and continued in Normative specifications | 29.803 | 39 | 21 | CP-41 | PCG-21 | Wed 19/07/06 | Tue 24/03/09
4354 | 350029 | Deleted (covered by 380068): Functions and procedures for SAE to support LCS | SAES-SA-FP_LCS | 2 | Rel-8 | S2 | 2008-03-03 08:00 | 2008-03-03 08:00 | 100% | - | - | Nokia Siemens Networks | - | SP#37 stopped | - | 35 |  | SP-37 |  | Thu 29/03/07 | Tue 24/03/09
4355 | 350032 | Deleted (covered by 380064): SAE aspects of Emergency Calls | SAES-SA-EmCall | 2 | Rel-8 | S2 | 2008-03-03 08:00 | 2008-03-03 08:00 | 100% | - | - | Nokia Siemens Networks | - | SP#37 stopped | - | 35 |  | SP-37 |  | Thu 29/03/07 | Tue 24/03/09
4356 | 340019 | Deleted - CT aspects of SAES | SAES-St3 | 2 | Rel-8 | C3,C1,C4 | 2007-09-04 17:00 | 2008-03-14 17:00 | 100% | CP-060674 | - | - | - | SP#37 stopped | - | 34 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
4357 | 350019 | Deleted - CT1 aspects of SAES | SAES-St3 | 3 | Rel-8 | C1 | 2007-09-04 17:00 | 2007-09-04 17:00 | 100% | CP-060674 | - | - | - | SP#37 stopped | - | 35 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
4358 | 340052 | Deleted - Interoperability | SAES-St3-interop | 3 | Rel-8 | C1 | 2008-03-14 17:00 | 2008-03-14 17:00 | 100% | CP-060674 | - | - | - | SP#37 stopped | - | 34 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
4359 | 350020 | Deleted - CT3 aspects of SAES | SAES | 3 | Rel-8 | C3 | 2007-09-04 17:00 | 2007-09-04 17:00 | 100% | CP-060675 | - | - | - | SP#37 stopped | - | 35 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
4360 | 350021 | Deleted - CT4 aspects of SAES | SAES | 3 | Rel-8 | C4 | 2007-09-04 17:00 | 2007-09-04 17:00 | 100% | CP-060676 | - | - | - | SP#37 stopped | 29.803 | 35 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
4361 | 340021 | Deleted - UE to EPC NAS signalling (incl. MBMS and QoS aspects) | SAES-St3-sig | 3 | Rel-8 | C1 | 2008-03-14 17:00 | 2008-03-14 17:00 | 100% | CP-060674 | - | - | - | SP#37 stopped | - | 34 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
4362 | 340027 | Deleted - User and Control plane protocols | SAES-St3-prot | 3 | Rel-8 | C4 | 2007-09-21 17:00 | 2007-09-21 17:00 | 100% | CP-060676 | - | - | - | SP#37 stopped | - | 34 |  | SP-37 |  | Wed 19/07/06 | Tue 24/03/09
4363 | 340037 | Deleted - Architecture enhancements for non-3GPP accesses | SAES-non_3GPP | 2 | Rel-8 | S2 | 2007-09-04 17:00 | 2007-09-04 17:00 | 100% | SP-060926 | - | Motorola | Irfan.Ali@motorola.com | SP#34 stopped. Replaced by UID_350027 and its children | 23.402 | 34 |  | SP-34 |  | Fri 23/06/06 | Tue 24/03/09
4364 | 320030 | Deleted - Stage 2 of architecture for the 3GPP System Architecture Evolution | SAES-St2 | 2 | Rel-8 | S2 | 2007-10-02 17:00 | 2007-10-02 17:00 | 100% | SP-060926 | - | Vodafone | chris.pudney@vodafone.com | SP#34 stopped. Replaced by UIDs 340018 and 340037. (SP#34 report discussion of SP-060917.) | 23.002, 23.060, 23.107, 23.203, 23.228, 23.234, 23.246, 23.271, 23.279 | 32 |  | SP-34 |  | Wed 19/07/06 | Tue 24/03/09
4365 | 350023 | Deleted - SA aspects of System Architecture Evolution | SAES-SA | 2 | Rel-8 | S2 | 2006-04-12 08:00 | 2007-10-01 17:00 | 100% | - | - | - | - | SP#34 stopped | - |  |  | SP-34 |  | Thu 29/03/07 | Tue 24/03/09
4366 | 450022 | Conformance Test Aspects – Mobility management based on DSMIPv6 (Dual-Stack Mobile IPv6) | DSMIPv6_UEConTest | 1 | Rel-8 | R5 | 2009-09-18 08:00 | 2010-09-17 17:00 | 100% | RP-090754 | RP-100738 | Qualcomm | Lena Chaponniere (lchaponn@qualcomm.com) | RP#49 completed. Testing for CT1's UID_360022 (24.303) under Rel-8 Feature SAES | 36.508, 36.523-1, 36.523-2, 36.523-3 | 45 | 23 |  |  | Tue 15/09/09 | Thu 09/09/10
4367 | 370025 | IMS Centralized Service control | ICSRA | 1 | Rel-8 | S1,S2,C1,C3,C4,IETF | 2005-11-01 16:12 | 2014-12-09 17:00 | 100% | SP-070924 | - | AT&T | Randolph Wohlert (rwohlert@tri.sbc.com) | CP#46 completed | - | 37 |  |  |  | Tue 02/10/07 | Wed 02/12/09
4368 | 380039 | Stage 1 for ICS Requirement and Architecture | ICSRA | 2 | Rel-8 | S1 | 2007-09-03 08:00 | 2008-03-12 17:00 | 100% | SP-070924 | - | AT&T | Randolph Wohlert (rwohlert@tri.sbc.com) | SP#39 completed | 22.101 | 38 | 21 |  |  | Tue 02/10/07 | Wed 23/07/08
4369 | 380040 | Stage 2 for ICS Requirement and Architecture | ICSRA-St2 | 2 | Rel-8 | S2 | 2007-12-14 08:00 | 2008-06-05 17:00 | 100% | SP-070924 | - | Alcatel-Lucent | - | SP#40 completed | 23.292, 23.206 | 38 | 21 |  |  | Mon 03/03/08 | Wed 23/07/08
4370 | 400205 | Stage 3 for ICSRA – Protocol, Addressing, Subscriber Data | ICSRA | 2 | Rel-8 | C1,C3,C4,IETF | 2005-11-01 16:12 | 2014-12-09 17:00 | 100% | CP-091046 | - | Ericsson | sean.schneyer@ericsson.com | CP#46 completed | - | - | - |  |  | Wed 02/12/09 | Mon 07/12/09
4371 | 400005 | CT1 aspects - Stage 3 for ICSRA | ICSRA | 3 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-091046 | - | Ericsson | Sean Schneyer | CP#46 completed | 24.229, new (24.292, 24.286) | 40 | 21 |  |  | Mon 03/03/08 | Mon 07/12/09
4372 | 521014 | (IETF) CT1 aspects - Stage 3 for ICSRA (draft-ietf-salud-alert-info-urns) | ICSRA | 3 | Rel-8 | C1-IETF | 2008-05-30 08:00 | 2014-12-09 17:00 | 100% | CP-091046 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Dec.14: 75->90; 7/3/16: 90%->100 | draft-ietf-salud-alert-info-urns | 52 | 27 |  |  | Mon 20/06/11 | Mon 07/03/16
4373 | 521015 | (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 6871) | ICSRA | 3 | Rel-8 | C1-IETF | 2008-05-30 08:00 | 2013-03-01 17:00 | 100% | CP-091046 | - | Andrew Allen | - | CP#59 completed | RFC 6871 (was draft-ietf-mmusic-sdp-media-capabilities) | 52 | 27 |  |  | Mon 20/06/11 | Thu 28/02/13
4374 | 521016 | (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 7195) | ICSRA | 3 | Rel-8 | C1-IETF | 2008-05-30 08:00 | 2014-06-13 17:00 | 100% | CP-091046 | - | Andrew Allen | - | CP#64 complete | RFC 7195 (was draft-ietf-mmusic-sdp-cs) | 52 | 27 |  |  | Mon 20/06/11 | Fri 06/06/14
4375 | 521017 | (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 7006) | ICSRA | 3 | Rel-8 | C1-IETF | 2008-06-03 08:00 | 2013-12-06 17:00 | 100% | CP-091046 | - | Andrew Allen | - | CP#62 completed | RFC7006 (was draft-ietf-mmusic-sdp-miscellaneous-caps) | 52 | 27 |  |  | Mon 20/06/11 | Wed 27/11/13
4376 | 400006 | CT3 aspects - Stage 3 for ICSRA | ICSRA | 3 | Rel-8 | C3 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-091046 | - | Mavenir | Brett Wallis ( brett@mavenir.com) | CP#43 completed | new 29.292 | 40 | 21 |  |  | Mon 03/03/08 | Mon 07/12/09
4377 | 400007 | CT4 aspects - Stage 3 for ICSRA | ICSRA | 3 | Rel-8 | C4 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-091046 | - | Ericsson | Sean Schneyer | CP#42 completed | 23.003, 29.232, 23.018, 29.002 | 40 | 21 |  |  | Mon 03/03/08 | Mon 07/12/09
4378 | 521018 | (IETF) CT4 aspects - Stage 3 for ICSRA (RFC 7254) | ICSRA | 3 | Rel-8 | C4-IETF | 2005-11-01 16:12 | 2014-06-13 17:00 | 100% | CP-091046 | - | Andrew Allen | - | CP#64 complete | RFC 7254 (was draft-montemurro-gsma-imei-urn) | 52 | 27 |  |  | Mon 20/06/11 | Fri 06/06/14
4379 | 400105 | Deleted - Stage 3 for ICSRA – I1 interface | ICSRA | 3 | Rel-8 | C1 | 2008-05-30 08:00 | 2008-09-12 17:00 | 100% | CP-080492 | - | Huawei | xupeili@huawei.com | CP#41 work stopped | 24.293 | 40 | 21 | CP-41 | PCG-21 | Mon 03/03/08 | Wed 02/12/09
4380 | 370059 | IMS Multimedia Telephony and Supplementary Services | IMSTSS | 1 | Rel-8 | S1,S5,C1,C3,C4,IETF | 2007-05-02 08:00 | 2014-12-09 17:00 | 100% | - | - | - | - | SP#43 completed | - | 37 |  |  |  | Mon 19/11/07 | Mon 19/11/07
4381 | 370060 | General aspects of IMS Sup Services | IMSSS-Gal | 2 | Rel-8 | S1,C1,C3,C4 | 2007-09-03 08:00 | 2009-03-06 17:00 | 100% | SP-070691 | - | Ericsson | Susana Sabater | CP#43 completed | - | 37 |  |  |  | Mon 19/11/07 | Mon 19/11/07
4382 | 370023 | Service and Capability for Core IMS - inclusion of TISPAN requirements | TISCAPR8 | 3 | Rel-8 | S1 | 2007-09-03 08:00 | 2007-12-14 17:00 | 100% | SP-070691 | - | Ericsson | Susana Sabater | SP#39 completed | 22.228, 22.115, 22.101 | 37 |  |  |  | Tue 02/10/07 | Thu 20/03/08
4383 | 380001 | Documentation of TISPAN R1 and R2 in CT1 | REDOC_TIS-C1 | 3 | Rel-8 | C1 | 2007-11-28 08:00 | 2008-09-12 17:00 | 100% | CP-080213 | - | Nokia Siemens Networks | peter.leis@nsn.com | CP#41 completed | 24.141, 24.147, 24.173, 24.229, 24.247, 24.341, 24.604, 24.605, 24.606, 24.607, 24.608, 24.610, 24.611, 24.616, 24.623, 24.628, 24.629, 24.647, 24.654 | 38 | 21 |  |  | Wed 28/11/07 | Fri 01/08/08
4384 | 380002 | Documentation of TISPAN R1 and R2 in CT3 | REDOC_TIS-C3 | 3 | Rel-8 | C3 | 2007-11-28 08:00 | 2009-03-06 17:00 | 100% | CP-080213 | - | Nokia Siemens Networks | peter.leis@nsn.com | CP#43 completed | 29.162, 29.163, 29.658 | 38 | 21 |  |  | Wed 28/11/07 | Mon 07/12/09
4385 | 380003 | Documentation of TISPAN R1 and R2 in CT4 | REDOC_TIS-C4 | 3 | Rel-8 | C4 | 2007-11-28 08:00 | 2008-09-12 17:00 | 100% | CP-080213 | - | Nokia Siemens Networks | peter.leis@nsn.com | CP#41 completed | 29.228, 29.229 | 38 | 21 |  |  | Wed 28/11/07 | Mon 01/09/08
4386 | 370062 | IMS Multimedia Telephony Service | IMS-MMTel | 2 | Rel-8 | S1,S5 | 2007-09-10 08:00 | 2009-03-12 17:00 | 100% | - | - | - | - | SP#43 completed | - | 37 |  |  |  | Mon 19/11/07 | Mon 19/11/07
4387 | 370024 | Merging TISPAN MMTel [requirements] for Common IMS | TMMTEL | 3 | Rel-8 | S1 | 2007-09-10 08:00 | 2007-12-07 17:00 | 100% | SP-070569 | - | Nokia Siemens Networks | - | SP#38 completed | 22.173 | 37 |  |  |  | Tue 02/10/07 | Mon 19/11/07
4388 | 380041 | Multimedia Telephony Service and Supplementary Services (MMTel) offline Charging | MMTel-CH | 3 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | SP-080848 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | CP#43 completed | 32.275, 32.298/299 | 38 | 21 |  |  | Fri 17/06/05 | Mon 23/02/09
4389 | 380006 | Call Completion on Busy Subscriber (CCBS)/Call Completion on Non-Reachable (CCNR) on IMS | CCBS_CCNR | 2 | Rel-8 | C1,C3,IETF | 2007-05-02 08:00 | 2013-06-14 17:00 | 100% | CP-080215 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | - | 38 | 21 |  |  | Wed 14/11/07 | Thu 29/11/07
4390 | 380007 | CT1 part of Stage 3 CCBS_CCNR | CCBS_CCNR | 3 | Rel-8 | C1 | 2007-05-02 08:00 | 2009-03-06 17:00 | 100% | CP-080215 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | 24.642, 24.229, 24.173 | 38 | 21 |  |  | Wed 14/11/07 | Wed 11/01/12
4391 | 380008 | CT3 part of Stage 3 CCBS_CCNR | CCBS_CCNR | 3 | Rel-8 | C3 | 2007-05-02 08:00 | 2008-12-05 17:00 | 100% | CP-080215 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#42 completed | 29.163 | 38 | 21 |  |  | Wed 14/11/07 | Wed 11/01/12
4392 | 521019 | (IETF) Stage 3 CCBS_CCNR [RFC 6910 (was draft-ietf-bliss-call-completion)] | CCBS_CCNR | 3 | Rel-8 | C1-IETF,C3-IETF | 2007-05-02 08:00 | 2013-06-14 17:00 | 100% | CP-080215 | - | Roland Jesske | - | CP#60 completed | RFC 6910 (was draft-ietf-bliss-call-completion) | 52 | 27 |  |  | Mon 20/06/11 | Mon 10/06/13
4393 | 390058 | Flexible Alerting | FA | 2 | Rel-8 | S1,C1 | 2008-01-30 08:00 | 2009-03-06 17:00 | 100% | CP-080219 | - | Nortel | milanpa@nortel.com | CP#43 completed | - | 39 | 21 |  |  | Mon 03/03/08 | Tue 15/04/08
4394 | 390059 | Stage 1 FA | FA | 3 | Rel-8 | S1 | 2008-01-30 08:00 | 2008-06-05 17:00 | 100% | - | - | Telecom Italia | - | SP#40 completed | 22.173 | 39 | 21 |  |  | Mon 03/03/08 | Thu 18/09/08
4395 | 390015 | Stage 3 FA | FA | 3 | Rel-8 | C1 | 2008-01-30 08:00 | 2009-03-06 17:00 | 100% | CP-080219 | - | Nortel | milanpa@nortel.com | CP#43 completed | 24.239, 24.173 | 39 | 21 |  |  | Mon 03/03/08 | Fri 20/02/09
4396 | 380009 | Communication Wait on IMS | CW_IMS | 2 | Rel-8 | C1,C3,IETF | 2007-06-22 08:00 | 2014-12-09 17:00 | 100% | CP-080214 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | - | 38 | 21 |  |  | Wed 14/11/07 | Tue 15/04/08
4397 | 380010 | CT1 part of Stage 3 CW-IMS | CW_IMS | 3 | Rel-8 | C1 | 2007-11-30 08:00 | 2009-03-06 17:00 | 100% | CP-080214 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#43 completed | 24.615, 24.229, 24.173 | 38 | 21 |  |  | Wed 14/11/07 | Fri 20/02/09
4398 | 521020 | (IETF) Stage 3 CW-IMS (salud-alert-info-urns) | CW_IMS | 3 | Rel-8 | C1-IETF | 2007-06-22 08:00 | 2014-12-09 17:00 | 100% | CP-080214 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Dec.14: 75->90; 7/3/16: 90%->100 | draft-ietf-salud-alert-info-urns | 52 | 27 |  |  | Mon 20/06/11 | Mon 07/03/16
4399 | 380011 | CT3 part of Stage 3 CW-IMS | CW_IMS | 3 | Rel-8 | C3 | 2007-11-30 08:00 | 2008-12-04 17:00 | 100% | CP-080214 | - | Deutsche Telekom | martin.huelsemann@telekom.de | CP#42 completed | 29.163 | 38 | 21 |  |  | Wed 14/11/07 | Fri 21/11/08
4400 | 370103 | IMS Charging | CH8_IMS | 2 | Rel-8 | S5 | 2007-09-17 08:00 | 2009-03-12 17:00 | 100% | SP-070621 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#39 completed | 32.260, 32.298 | 37 |  |  |  | Sat 15/09/07 | Sun 23/03/08
4401 | 370003 | Add Interconnection Border Control Function (IBCF) to IMS Charging | CH8_IMS | 3 | Rel-8 | S5 | 2007-09-17 08:00 | 2008-03-12 17:00 | 100% | SP-070621 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#39 completed | 32.260, 32.298 | 37 |  |  |  | Sat 15/09/07 | Sun 23/03/08
4402 | 380042 | Advice of Charge (AoC) support in IMS Charging | CH8_IMS | 3 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | SP-070739 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#43 completed | 32.240, 32.260, 32.296, 32.298, 32.299, new 32.280 | 38 | 21 |  |  | Fri 17/06/05 | Mon 23/02/09
4403 | 390035 | 3GPP2 Input to Common IMS | CIMS_3GPP2 | 1 | Rel-8 | S1,S2,S3,C1,C3,C4 | 2008-03-07 08:00 | 2008-12-11 17:00 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | TSG#42 completed. Acronym changed from "CIMS_3GPP2, IMS_Common" | - | 39 | 21 |  |  | Tue 02/10/07 | Tue 24/03/15
4404 | 390050 | Stage 1 CIMS_3GPP2 | CIMS_3GPP2 | 2 | Rel-8 | S1 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#40 completed. Acronym changed from "CIMS_3GPP2, IMS_Common" | 22.228, 22.173, 22.101, 22.153 | 39 | 21 |  |  | Mon 03/03/08 | Tue 24/03/15
4405 | 390051 | Stage 2 CIMS_3GPP2 | CIMS_3GPP2 | 2 | Rel-8 | S2 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#40 completed. Acronym changed from "CIMS_3GPP2, IMS_Common" | 23.002, 23.141, 23.203, 23.167, 23.228 | 39 | 21 |  |  | Mon 03/03/08 | Tue 24/03/15
4406 | 390052 | Security CIMS_3GPP2 | CIMS_3GPP2 | 2 | Rel-8 | S3 | 2008-03-12 08:00 | 2008-12-11 17:00 | 100% | SP-080220 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#42 completed [issues addressed under UID_370078 (IMS-Sec)]. Acronym changed from "CIMS_3GPP2, IMS_Common" | 33.141, 33.203, 33.210 | 39 | 21 |  |  | Mon 03/03/08 | Tue 24/03/15
4407 | 390113 | Stage 3 CIMS_3GPP2 | REDOC_3GPP2 | 2 | Rel-8 | C1,C3,C4 | 2008-03-07 08:00 | 2008-12-11 17:00 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | - | - | 39 | 21 |  |  | Mon 03/03/08 | Thu 04/12/08
4408 | 390013 | Stage 3 CIMS_3GPP2 (CT1) | REDOC_3GPP2 | 3 | Rel-8 | C1 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | CP#42 completed | 23.218, 24.141, 24.147, 24.173, 24.229, 24.238, 24.247, 24.604, 24.605, 24.606, 24.607, 24.608, 24.610, 24.611, 24.629, 24.930 | 39 | 21 |  |  | Mon 03/03/08 | Thu 04/12/08
4409 | 390026 | Stage 3 CIMS_3GPP2 (CT3) | REDOC_3GPP2 | 3 | Rel-8 | C3 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | CP#42 completed | 29.163, 29.212, 29.213, 29.214 | 39 | 21 |  |  | Mon 03/03/08 | Thu 26/03/09
4410 | 390027 | Stage 3 CIMS_3GPP2 (CT4) | REDOC_3GPP2 | 3 | Rel-8 | C4 | 2008-03-07 08:00 | 2008-12-11 17:00 | 100% | CP-080795 | - | Alcatel-Lucent | orsic@alcatel-lucent.com | CP#42 completed | 29.228, 29.229, 29.328, 29.329 | 39 | 21 |  |  | Mon 03/03/08 | Thu 26/03/09
4411 | 350005 | IMS Enhancements for support of Packet Cable access | PktCbl | 1 | Rel-8 | S2,S3,C1,C3,C4 | 2006-12-06 08:00 | 2008-05-30 17:00 | 100% | - | - | Cablelabs | Bernie McKibben (b.mckibben@cablelabs.com) | CP#40 completed | - | 35 |  |  |  | Thu 29/03/07 | Thu 29/03/07
4412 | 350008 | IMS Enhancements for Cable Client Types and Deployment Models | PktCbl-Deploy | 2 | Rel-8 | S2,C1 | 2007-02-05 08:00 | 2008-05-30 17:00 | 100% | SP-070105 | - | Cablelabs | Bernie McKibben (b.mckibben@cablelabs.com) | CP#40 completed | - | 35 |  |  |  | Thu 29/03/07 | Thu 29/03/07
4413 | 350009 | Architecture aspects of PktCbl-Deploy | PktCbl-Deploy | 3 | Rel-8 | S2 | 2007-02-05 08:00 | 2007-12-06 17:00 | 100% | SP-070105 | - | Cablelabs | Bernie McKibben (b.mckibben@cablelabs.com) | SP#38 completed | 23.228 | 35 |  |  |  | Thu 29/03/07 | Tue 27/05/08
4414 | 350010 | CT1 aspects of PktCbl-Deploy | PktCbl-Deploy | 3 | Rel-8 | C1 | 2007-03-26 08:00 | 2008-05-30 17:00 | 100% | CP-070122 | - | Cablelabs | D.Hancock@CableLabs.com | CP#40 completed | - | 35 |  |  |  | Thu 29/03/07 | Tue 13/05/08
4415 | 350011 | IMS Inter-working aspects in Support of Cable Regulatory requirements | PktCbl-Intw | 2 | Rel-8 | S2,C1,C3 | 2007-02-05 08:00 | 2008-03-14 17:00 | 100% | SP-070107 | - | Cablelabs | B.McKibben@CableLabs.com | CP#39 completed | - | 35 |  |  |  | Thu 29/03/07 | Thu 29/03/07
4416 | 350012 | Architecture aspects of PktCbl-Interwork | PktCbl-Intw | 3 | Rel-8 | S2 | 2007-02-05 08:00 | 2007-09-14 17:00 | 100% | SP-070107 | - | Cablelabs | B.McKibben@CableLabs.com | SP#37 completed | 23.228 | 35 |  |  |  | Thu 29/03/07 | Tue 29/05/07
4417 | 350013 | CT1,CT3 aspects of PktCbl-Interwork | PktCbl-Intw | 3 | Rel-8 | C1,C3 | 2007-03-26 08:00 | 2008-03-14 17:00 | 100% | CP-070575 | - | Cablelabs | D.Hancock@CableLabs.com | CP#39 completed | 24.229 | 35 |  |  |  | Thu 29/03/07 | Mon 03/03/08
4418 | 340008 | IMS Enhancements for Security Requirements in Support of Cable Deployments | PktCbl-Sec | 2 | Rel-8 | S3,C1,C3,C4 | 2006-12-06 08:00 | 2008-05-30 17:00 | 100% | SP-060933 | - | Cablelabs | s.dotson@cablelabs.com | CP#40 completed | - | 34 |  |  |  | Fri 04/11/05 | Tue 29/05/07
4419 | 350033 | SA3 aspects of PktCbl-Sec | PktCbl-Sec | 3 | Rel-8 | S3 | 2006-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-060933 | - | Cablelabs | s.dotson@cablelabs.com | SP#39 completed | 33.203, 33.210, 33.220 | 35 |  |  |  | Fri 04/11/05 | Sun 23/03/08
4420 | 350006 | CT1 aspects of PktCbl-Sec | PktCbl-Sec | 3 | Rel-8 | C1 | 2007-03-26 08:00 | 2008-05-30 17:00 | 100% | CP-070124 | - | Cablelabs | D.Hancock@CableLabs.com | CP#40 completed | 24.229 | 35 |  |  |  | Thu 29/03/07 | Tue 27/05/08
4421 | 380029 | CT3 aspects of PktCbl-Sec | PktCbl-Sec | 3 | Rel-8 | C3 | 2007-03-26 08:00 | 2007-11-30 17:00 | 100% | CP-070124 | - | Cablelabs | D.Hancock@CableLabs.com | CP#38 completed | 29.163 | 38 | 21 |  |  | Thu 29/03/07 | Fri 07/03/08
4422 | 350007 | CT4 aspects of PktCbl-Sec | PktCbl-Sec | 3 | Rel-8 | C4 | 2007-03-26 08:00 | 2008-03-14 17:00 | 100% | CP-070124 | - | Cablelabs | D.Hancock@CableLabs.com | CP#39 completed | 29.228, 29.229, 23.008 | 35 |  |  |  | Thu 29/03/07 | Tue 27/05/08
4423 | 360012 | IMS System enhancements for corporate network access | IMS_Corp | 1 | Rel-8 | S2,S1,C1,C4,IETF | 2007-06-22 08:00 | 2014-09-12 17:00 | 100% | SP-080095 | - | Orange | Delphin Barankanira | CP#47 completed | - | 36 |  |  |  | Fri 22/06/07 | Thu 29/07/10
4424 | 390049 | SA1 aspects of IMS_Corp | IMS_Corp | 2 | Rel-8 | S1 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080095 | - | Telecom Italia | - | SP#40 completed | - | 39 | 21 |  |  | Fri 22/06/07 | Mon 19/05/08
4425 | 360014 | SA2 aspects of IMS_Corp | IMS_Corp | 2 | Rel-8 | S2 | 2007-06-22 08:00 | 2008-09-18 17:00 | 100% | SP-080095 | - | Orange | Delphin Barankanira | no Stage 2 impacts | 23.228 | 36 |  |  |  | Fri 22/06/07 | Thu 29/07/10
4426 | 390022 | CT1 aspects of IMS_Corp | IMS_Corp | 2 | Rel-8 | C1 | 2008-03-07 08:00 | 2010-03-19 17:00 | 100% | CP-080220 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#47 completed | 24.229, 24.503 | 39 | 21 |  |  | Fri 07/03/08 | Wed 03/03/10
4427 | 531002 | (IETF) CT1 aspects of IMS_Corp (RFC 7316) | IMS_Corp | 2 | Rel-8 | C1-IETF | 2011-06-29 13:00 | 2014-09-12 17:00 | 100% | CP-080220 | - | Keith Drage | Keith Drage (drage@alcatel-lucent.com) | CP#65 completed | RFC 7316 (was draft-vanelburg-dispatch-private-network-ind) | 53 | 27 |  |  | Fri 29/07/11 | Wed 03/09/14
4428 | 390023 | CT4 aspects of IMS_Corp | IMS_Corp | 2 | Rel-8 | C4 | 2008-02-26 16:36 | 2008-12-05 17:00 | 100% | CP-080220 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#42 completed | 29.228, 29.229, 23.003, 23.008, 29.433 | 39 | 21 |  |  | Fri 07/03/08 | Sat 22/11/08
4429 | 380069 | Maintenance of TISPAN documentation | MAINTISP | 1 | Rel-8 | S2,C1,C3,C4,IETF | 2007-07-02 08:00 | 2014-06-13 17:00 | 100% | - | - | - | - | SP#40 completed | - | 38 | 21 |  |  | Thu 13/12/07 | Thu 29/07/10
4430 | 380005 | Maintenance of TISPAN R2 | MAINT_R2 | 2 | Rel-8 | C1,C3,C4 | 2007-11-09 08:00 | 2008-03-07 17:00 | 100% | CP-080229 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#39 completed | 24.406, 24.407, 24.410, 24.411, 24.423, 24.430, 24.447, 24.451, 24.454, 24.503, 24.505, 24.508, 24.516, 24.528, 24.529, 29.412, 29.421, 29.433, 29.458, 29.527, 29.624 | 38 | 21 |  |  | Mon 19/11/07 | Mon 07/12/09
4431 | 521021 | Deleted - (IETF) Maintenance of TISPAN R2 (avasarala-dispatch-comm-div-notification) | MAINT_R2_IETF | 2 | Rel-8 | C1-IETF | 2007-11-09 08:00 | 2014-06-13 17:00 | 100% | CP-080229 | - | Andrew Allen | - | CP#64 Draft removed from 3GPP documentation | draft-avasarala-dispatch-comm-div-notification | 52 | 27 | SP-69 |  | Mon 20/06/11 | Fri 06/06/14
4432 | 380043 | Documentation of TISPAN NGN R1 and R2 in 3GPP SA2 | IMS_Comm_Doc | 2 | Rel-8 | S2 | 2008-01-14 08:00 | 2008-06-05 17:00 | 100% | SP-070823 | - | Nokia Siemens Networks | jozsef.varga@nsn.com | SP#40 completed | 23.228, 23.204, 23.167 | 38 | 21 |  |  | Tue 02/10/07 | Tue 27/05/08
4433 | 380044 | Maintenance of TISPAN release 2 common IMS | IMS_Comm_Mtce8 | 2 | Rel-8 | S2 | 2007-07-02 08:00 | 2007-12-06 17:00 | 100% | SP-070916 | - | Telecom Italia | antonio.ascolese@telecomitalia.it | SP#38 completed | 23.506, 23.507,23.517, 23.521 | 38 | 21 |  |  | Tue 02/10/07 | Thu 29/07/10
4434 | 390056 | IMS Service Continuity | IMS-Cont | 1 | Rel-8 | S2,S1,C1 | 2008-03-12 08:00 | 2009-05-29 17:00 | 100% | SP-080092 | - | LG Electronics | JaeSeung SONG (anthonys@lge.com) | CP#44 completed | - | 39 | 21 |  |  | Tue 02/10/07 | Thu 29/07/10
4435 | 390072 | Stage 1 IMS Service Continuity | IMS-Cont | 2 | Rel-8 | S1 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080092 | - | LG Electronics | JaeSeung SONG (anthonys@lge.com) | SP#40 completed | - | 39 | 21 |  |  | Tue 02/10/07 | Tue 27/05/08
4436 | 390057 | Stage 2 IMS Service Continuity | IMS-Cont | 2 | Rel-8 | S2 | 2008-03-12 08:00 | 2008-06-05 17:00 | 100% | SP-080092 | - | LG Electronics | JaeSeung SONG (anthonys@lge.com) | SP#40 completed | 23.237, 23.292 | 39 | 21 |  |  | Tue 02/10/07 | Tue 27/05/08
4437 | 400011 | Stage 3 IMS Service Continuity | IMS-Cont | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-05-29 17:00 | 100% | CP-080491 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#44 completed | 24.237, 24.229, 24.216 | 40 | 21 |  |  | Tue 02/10/07 | Wed 13/05/09
4438 | 370078 | Security Enhancements for IMS | IMS-Sec | 1 | Rel-8 | S3,C1,C4 | 2006-09-19 14:36 | 2009-03-06 17:00 | 100% | SP-070496 | - | Ericsson | Bengt.Sahlin@ericsson.com | CP#43 completed | - | 37 |  |  |  | Fri 04/11/05 | Fri 20/02/09
4439 | 360017 | Stage 2 for IMS-Sec | IMS-Sec | 2 | Rel-8 | S3 | 2007-03-01 08:00 | 2008-12-11 17:00 | 100% | SP-070496 | - | Ericsson | Bengt.Sahlin@ericsson.com | SP#42 completed. SP#46 withdrawn draft 33.178-100 and 33.978 from Rel-8 onwards | 33.203, 33.141, 33.803 | 36 |  |  |  | Wed 21/11/07 | Mon 06/04/09
4440 | 390054 | CT1 part of Stage 3 for IMS-Sec | IMS-Sec | 2 | Rel-8 | C1 | 2006-09-19 14:36 | 2008-12-05 17:00 | 100% | - | - | Ericsson | - | CP#42 completed | - | 39 | 21 |  |  | Wed 21/11/07 | Thu 04/12/08
4441 | 390154 | CT4 part of Stage 3 for IMS-Sec | IMS-Sec | 2 | Rel-8 | C4 | 2007-06-07 08:00 | 2009-03-06 17:00 | 100% | - | - | Ericsson | - | CP#43 completed | - | 39 | 21 |  |  | Wed 21/11/07 | Fri 20/02/09
4442 | 380012 | CT1 part of Network Attachment Subsystem (NASS) Bundled Authentication | NBA | 2 | Rel-8 | C1 | 2007-11-14 08:00 | 2009-03-06 17:00 | 100% | CP-070781 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | 24.229 | 39 | 21 |  |  | Mon 19/11/07 | Fri 20/02/09
4443 | 380013 | CT4 part of Network Attachment Subsystem (NASS) Bundled Authentication | NBA-CT4 | 2 | Rel-8 | C4 | 2007-11-14 08:00 | 2008-05-30 17:00 | 100% | CP-070781 | - | Alcatel-Lucent | - | CP#40 completed | 29.229, 29.228, 23.008 | 39 | 21 |  |  | Mon 19/11/07 | Wed 14/05/08
4444 | 34046 | IMS initiated and controlled PSS and MBMS User Service | IMS_PSS_MBMS_US | 1 | Rel-8 | S4,S3,IETF | 2008-03-12 08:00 | 2011-09-21 17:00 | 100% | SP-080201 | - | FT, Ericsson | olle.franceschi@ericsson.com | SP#39 WID approved | - | 34 |  |  |  | Tue 18/03/08 | Thu 30/06/11
4445 | 34146 | SA4, SA3 part of IMS initiated and controlled PSS and MBMS User Service | IMS_PSS_MBMS_US | 2 | Rel-8 | S4,S3 | 2008-03-12 08:00 | 2008-03-12 08:00 | 100% | SP-080201 | - | FT, Ericsson | olle.franceschi@ericsson.com | SP#43 completed | 26.234, 26.346, 33.246, New 26.237 | 34 |  |  |  | Tue 18/03/08 | Thu 30/06/11
4446 | 521022 | (IETF) IMS initiated and controlled PSS and MBMS User Service (RFC 6080) | IMS_PSS_MBMS_US | 2 | Rel-8 | S4-IETF | 2008-03-12 08:00 | 2011-09-21 17:00 | 100% | SP-080201 | - | Ericsson | - | SP#53/IETF#81 completed | RFC 6080 (was draft-ietf-sipping-config-framework) | 52 | 27 |  |  | Mon 20/06/11 | Fri 23/08/13
4447 | 713024 | Multimedia interworking between IMS and CS networks | MIW-IMS | 1 | Rel-8 | C3,C4 | 2005-09-23 08:00 | 2008-12-05 17:00 | 100% | CP-070729 | - | Vodafone | nico.gabriele@vodafone.com | CP#42 completed | - | 71 | 36 |  |  | Mon 03/10/05 | Wed 10/12/08
4448 | 7013 | Stage 1 and 2 defined in earlier Releases | MIW-IMS | 2 | Rel-8 | S2 | 2005-09-23 08:00 | 2005-11-30 17:00 | 100% | - | - | Vodafone | nico.gabriele@vodafone.com | SP#31 Moved from FS section Feb 2006 | - |  |  |  |  | Thu 16/02/06 | Fri 30/07/10
4449 | 7014 | Stage 3 of MW-IMS | MIW-IMS-St3C3 | 2 | Rel-8 | C3 | 2005-09-23 08:00 | 2007-11-30 17:00 | 100% | CP-070096 | - | Vodafone | nico.gabriele@vodafone.com | Moved from Rel-7. Feature extended in Rel-8 by including Stage 3 covering MONA UID_380021 | 29.863, 29.163 |  |  |  |  | Thu 16/02/06 | Tue 05/08/08
4450 | 380021 | Stage 3 for MW-IMS, MONA extension | MIW-IMS-St3C3_MONA | 2 | Rel-8 | C3 | 2007-11-05 08:00 | 2008-12-05 17:00 | 100% | CP-070729 | - | Vodafone | Christer.Holmberg@ericsson.com | CP#42 completed | 29.863, 29.163 | 38 | 21 |  |  | Tue 13/11/07 | Mon 01/09/08
4451 | 380022 | Mn interface (MGCF – IM MGW) | MIW-IMS-St3C4 | 2 | Rel-8 | C4 | 2007-11-21 08:00 | 2008-12-05 17:00 | 100% | CP-070729 | - | Vodafone | Christer.Holmberg@ericsson.com | CP#42 completed | 29.332 | 38 | 21 |  |  | Wed 21/11/07 | Sat 22/11/08
4452 | 360029 | IMS Stage 3 IETF Protocol Alignment - phase 2 | IMSProtoc2 | 1 | Rel-8 | C1,IETF | 2007-06-22 08:00 | 2014-12-09 17:00 | 100% | CP-080794 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | - | 36 |  |  |  | Wed 05/09/07 | Fri 20/02/09
4453 | 360129 | CT1 aspects of IMS Stage 3 IETF Protocol Alignment - phase 2 | IMSProtoc2 | 2 | Rel-8 | C1 | 2007-06-22 08:00 | 2009-03-06 17:00 | 100% | CP-080794 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | 23.218, 24.229, 24.930 | 36 |  |  |  | Wed 05/09/07 | Fri 20/02/09
4454 | 521023 | (IETF) IMS Stage 3 IETF Protocol Alignment (draft-bakker-sipping-3gpp-ims-xml-body-handling) | IMSProtoc2 | 2 | Rel-8 | C1-IETF | 2007-06-22 08:00 | 2012-12-07 17:00 | 100% | CP-080794 | - | Andrew Allen | - | CP#58 completed. ietf-draft discontinued. Documented within 3GPP | draft-bakker-sipping-3gpp-ims-xml-body-handling | 52 | 27 |  |  | Mon 20/06/11 | Sat 24/11/12
4455 | 521024 | (IETF) IMS Stage 3 IETF Protocol Alignment (RFC 6544) | IMSProtoc2 | 2 | Rel-8 | C1-IETF | 2007-06-22 08:00 | 2012-06-15 17:00 | 100% | CP-080794 | - | Keith Drage | - | CP#56 completed | RFC 6544 (was draft-ietf-mmusic-ice-tcp) | 52 | 27 |  |  | Mon 20/06/11 | Fri 20/04/12
4456 | 521025 | (IETF) IMS Stage 3 IETF Protocol Alignment (draft-ietf-salud-alert-info-urns) | IMSProtoc2 | 2 | Rel-8 | C1-IETF | 2007-06-22 08:00 | 2014-12-09 17:00 | 100% | CP-080794 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Dec.14: 75->90; 7/3/16: 90%->100 | draft-ietf-salud-alert-info-urns | 52 | 27 |  |  | Mon 20/06/11 | Mon 07/03/16
4457 | 380014 | Interworking between User-to-User Signalling (UUS) and SIP | UUSIW | 1 | Rel-8 | C1,C3,IETF | 2007-11-30 08:00 | 2014-12-09 17:00 | 100% | CP-070782 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#43 completed | - | 38 | 21 |  |  | Tue 13/11/07 | Wed 11/03/09
4458 | 380015 | CT1 part of Stage 3 MGCF UUSIW | UUSIW | 2 | Rel-8 | C1 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-070782 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#42 completed | 24.279, 24.229 | 38 | 21 |  |  | Tue 13/11/07 | Fri 21/11/08
4459 | 521026 | (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui) | UUSIW | 2 | Rel-8 | C1-IETF,C3-IETF | 2007-11-30 08:00 | 2014-12-09 17:00 | 100% | CP-070782 | - | Roland Jesske | Roland Jesske | In RFC Editors Queue. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui). June 2015: RFC 7433 (was draft-ietf-cuss-sip-uui) | RFC 7433 | 52 | 27 |  |  | Mon 20/06/11 | Tue 10/03/15
4460 | 551001 | (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui-isdn) | UUSIW | 2 | Rel-8 | C1-IETF,C3-IETF | 2011-03-17 13:00 | 2014-12-09 17:00 | 100% | CP-070782 | - | Keith Drage | Keith Drage (drage@alcatel-lucent.com) | In RFC Editors Queue. Dec.14: 75->90. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui-isdn). June 2015: RFC 7434 (was draft-ietf-cuss-sip-uui-isdn) | RFC 7434 | 55 | 28 |  |  | Sat 03/03/12 | Tue 10/03/15
4461 | 380016 | CT3 part of Stage 3 MGCF UUSIW | UUSIW | 2 | Rel-8 | C3 | 2007-11-30 08:00 | 2009-03-12 17:00 | 100% | CP-070782 | - | Huawei | Lili Yang (kadyyang@huawei.com) | CP#43 completed | 29.163 | 38 | 21 |  |  | Tue 13/11/07 | Thu 19/02/09
4462 | 380018 | Support of Overlap signalling | Overlap | 1 | Rel-8 | C3,C1,C4 | 2007-11-30 08:00 | 2009-03-06 17:00 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#43 completed | - | 38 | 21 |  |  | Tue 13/11/07 | Fri 20/02/09
4463 | 380019 | Stage 3 Overlap (CT1) | Overlap | 2 | Rel-8 | C1 | 2007-11-30 08:00 | 2009-03-06 17:00 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#43 completed | 24.229 | 38 | 21 |  |  | Tue 13/11/07 | Fri 20/02/09
4464 | 380020 | Stage 3 Overlap (CT3) | Overlap | 2 | Rel-8 | C3 | 2007-11-30 08:00 | 2009-03-06 17:00 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#43 completed | 29.163 | 38 | 21 |  |  | Tue 13/11/07 | Tue 25/11/08
4465 | 380120 | Stage 3 Overlap (CT4) | Overlap | 2 | Rel-8 | C4 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-070731 | - | Deutsche Telekom | r.jesske@telekom.de | CP#42 completed | 29.228, 29.229 | 38 | 21 |  |  | Tue 13/11/07 | Sat 22/11/08
4466 | 380035 | AS/MRFC Stage 2 and 3 | MRFC_TS | 1 | Rel-8 | C1,IETF | 2007-11-14 08:00 | 2012-06-15 17:00 | 100% | CP-070784 | - | Hewlett-Packard | mark.syrett@hp.com | Triggered by Study UID_7048 (MRFC) | - | 38 | 21 |  |  | Wed 14/11/07 | Fri 30/07/10
4467 | 380135 | AS/MRFC Stage 2 | MRFC_TS | 2 | Rel-8 | C1 | 2007-11-14 08:00 | 2008-12-05 17:00 | 100% | CP-070784 | - | Hewlett-Packard | mark.syrett@hp.com | CP#42 completed | 23.218 | 38 | 21 |  |  | Wed 14/11/07 | Tue 10/01/12
4468 | 380235 | AS/MRFC Stage 3 | MRFC_TS | 2 | Rel-8 | C1 | 2007-11-14 08:00 | 2008-12-05 17:00 | 100% | CP-070784 | - | Hewlett-Packard | mark.syrett@hp.com | CP#42 completed | 24.229, 24.147, 24.247 | 38 | 21 |  |  | Wed 14/11/07 | Tue 10/01/12
4469 | 521027 | (IETF) AS/MRFC Stage 2 and 3 (RFC 6505) | MRFC_TS | 2 | Rel-8 | C1-IETF | 2007-11-14 08:00 | 2012-06-15 17:00 | 100% | CP-070784 | - | Keith Drage | - | CP#56 completed | RFC 6505 (was draft-ietf-mediactrl-mixer-control-package) | 52 | 27 |  |  | Mon 20/06/11 | Fri 20/04/12
4470 | 400012 | IMS Restoration Procedures | IMS_RP | 1 | Rel-8 | C4,C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080447 | - | Ericsson | german.blanco@ericsson.com | CP#43 completed. Triggered by Study TR 23.820 (FS_IMS_RP) UID_350018 | - | 40 | 21 |  |  | Thu 29/03/07 | Fri 30/07/10
4471 | 400026 | IMS Restoration Procedures (CT4) | IMS_RP | 2 | Rel-8 | C4 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080447 | - | Ericsson | german.blanco@ericsson.com | CP#43 completed | 23.380, 29.228, 29.229, 29.230, 23.008 | 40 | 21 |  |  | Thu 29/03/07 | Fri 30/07/10
4472 | 400027 | IMS Restoration Procedures (CT1) | IMS_RP | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080447 | - | Ericsson | german.blanco@ericsson.com | CP#43 completed | 24.229 | 40 | 21 |  |  | Thu 29/03/07 | Fri 30/07/10
4473 | 410003 | IMS Application Server Service Data Descriptions for AS interoperability | IMS_ASIO | 1 | Rel-8 | C4 | 2008-09-12 17:00 | 2009-03-06 17:00 | 100% | CP-080451 | - | Alcatel-Lucent | nhberry@alcatel-lucent.com | CP#43 completed. Triggered by UID_360030 (FS_IMS_ASIO) | 29.328, 29.329, 29.364 | 41 | 21 |  |  | Wed 05/09/07 | Fri 20/02/09
4474 | 340030 | I-WLAN Network Selection Principle (NSP) | IWLANNSP | 1 | Rel-8 | S1,C1,C6 | 2007-06-14 17:00 | 2009-03-06 17:00 | 100% | SP-060932 | - | Telefónica O2 | chris.friel@O2.com | CP#43 completed | - | 34 |  |  |  | Fri 04/11/05 | Wed 25/02/09
4475 | 390024 | Stage 1 for I-WLAN NSP | IWLANNSP | 2 | Rel-8 | S1 | 2007-06-14 17:00 | 2007-06-14 17:00 | 100% | SP-060932 | - | Telefónica O2 | chris.friel@O2.com | SP#36 completed | 22.234 | 39 | 21 |  |  | Fri 04/11/05 | Tue 25/03/08
4476 | 390025 | CT1 part of Stage 3 for I-WLAN NSP | IWLANNSP | 2 | Rel-8 | C1 | 2008-03-07 08:00 | 2009-03-06 17:00 | 100% | CP-080217 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | CP#43 completed | 24.234 | 39 | 21 |  |  | Fri 07/03/08 | Wed 25/03/09
4477 | 390125 | CT6 part of Stage 3 for I-WLAN NSP | IWLANNSP | 2 | Rel-8 | C6 | 2008-03-07 08:00 | 2008-12-11 17:00 | 100% | CP-080217 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | CP#42 completed | 31.102, 31.111 | 39 | 21 |  |  | Fri 07/03/08 | Wed 25/02/09
4478 | 370049 | Mobility between 3GPP-WLAN Interworking and 3GPP Systems | IWLAN_Mob | 1 | Rel-8 | S2,C1 | 2007-09-14 08:00 | 2009-03-06 17:00 | 100% | SP-070701 | - | Orange | xiaobao.chen@orange-ftgroup.com | CP#43 completed | - | 37 |  |  |  | Fri 04/11/05 | Tue 27/05/08
4479 | 380045 | Stage 2 for Mobility between 3GPP-WLAN Interworking and 3GPP Systems | IWLAN_Mob | 2 | Rel-8 | S2 | 2007-09-14 08:00 | 2008-06-05 17:00 | 100% | SP-070701 | - | Orange | xiaobao.chen@orange-ftgroup.com | SP#40 completed | new 23.327 | 38 | 21 |  |  | Wed 21/11/07 | Fri 30/07/10
4480 | 400013 | CT1 aspects of Mobility between 3GPP-WLAN Interworking and 3GPP Systems | IWLAN_Mob | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080320 | - | Orange | reina.nader@orange-ftgroup.com | CP#43 completed | 24.303, new 24.327 | 40 | 21 |  |  | Wed 21/11/07 | Fri 30/07/10
4481 | 460006 | Conformance Test Aspects – Mobility between 3GPP WLAN Interworking and 3GPP Systems | IWLAN_Mob_UEConTest | 1 | Rel-8 | R5 | 2009-12-04 08:00 | 2010-09-17 17:00 | 100% | RP-091349 | RP-100740 | Qualcomm | Patrick Stupar (pstupar@qualcomm.com) | RP#49 completed. Testing for Rel-8 UID_400013 CT1 aspects of mobility between 3GPP WLAN Interworking and 3GPP Systems (24.327) | 34.108, 34.123-1, 34.123-2, 34.123-3 | 46 | 24 |  |  | Mon 30/11/09 | Thu 09/09/10
4482 | 7042 | Enhancements for Voice Group Call Service (VGCS) Applications (EVA) | EVA | 1 | Rel-8 | S1,C1,C4,G2 | 2006-03-15 08:00 | 2009-09-18 17:00 | 100% | SP-070904 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | CP#45 completed | - | 32 |  |  |  | Tue 21/03/06 | Fri 30/07/10
4483 | 320021 | SA1 aspects of EVA | EVA | 2 | Rel-8 | S1 | 2006-03-15 08:00 | 2006-12-06 17:00 | 100% | SP-070904 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | SP#38 completed | 42.068 | 32 |  |  |  | Tue 21/03/06 | Fri 16/05/08
4484 | 370019 | VGCS/VBS and GPRS Interactions | EVA | 2 | Rel-8 | S1 | 2007-09-03 08:00 | 2008-03-21 17:00 | 100% | SP-070653 | - | Huawei | Ling Liu | SP#39 completed | 42.068, 42.069 | 37 |  |  |  | Tue 02/10/07 | Fri 16/05/08
4485 | 320019 | CT1 aspects of EVA | EVA | 2 | Rel-8 | C1 | 2006-06-02 08:00 | 2009-09-18 17:00 | 100% | CP-060260 | - | Nortel | milanpa@nortel.com | CP#45 completed | 43.068, 44.068 | 32 |  |  |  | Wed 21/06/06 | Wed 09/09/09
4486 | 320020 | CT4 aspects of EVA | EVA | 2 | Rel-8 | C4 | 2006-06-02 08:00 | 2007-11-30 17:00 | 100% | CP-060260 | - | Nortel | - | CP#38 completed | 29.002 | 32 |  |  |  | Wed 21/06/06 | Fri 16/05/08
4487 | 52148 | GERAN2 aspects of EVA | EVA | 2 | Rel-8 | G2 | 2006-06-30 08:00 | 2008-02-22 17:00 | 100% | GP-071855 | - | Nortel | frank.billenkamp@nortel.com | GP#37 completed | 44.018, 48.008 |  |  |  |  | Wed 05/07/06 | Fri 16/05/08
4488 | 31081 | Personal Network Management | PNM | 1 | Rel-8 | S1,C1,S3 | 2005-07-11 08:00 | 2009-03-06 17:00 | 100% | SP-080327 | - | Vodafone | armin.toepfer@vodafone.com | CP#43 completed | - | 35 |  |  |  | Thu 21/04/05 | Tue 24/03/09
4489 | 7012 | Stage 1 for PNM | PNM | 2 | Rel-8 | S1 | 2005-07-11 08:00 | 2006-07-31 17:00 | 100% | SP-080327 | - | Vodafone | armin.toepfer@vodafone.com | SP#31 completed | 22.259 |  |  |  |  | Thu 16/02/06 | Wed 04/06/08
4490 | 350050 | Stage 2 for PNM | PNM | 2 | Rel-8 | C1 | 2007-03-26 08:00 | 2008-12-05 17:00 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#42 completed | 23.259 | 35 |  |  |  | Fri 04/05/07 | Fri 21/11/08
4491 | 350041 | Stage 3 for PNM | PNM | 2 | Rel-8 | C1,C4 | 2007-03-26 08:00 | 2009-03-06 17:00 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#43 completed | - | 35 |  |  |  | Thu 16/02/06 | Mon 19/11/07
4492 | 350001 | CT1 aspects of Stage 3 PNM | PNM | 3 | Rel-8 | C1 | 2007-03-26 08:00 | 2009-03-06 17:00 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#43 completed | 24.259, 24.229 | 35 |  |  |  | Thu 29/03/07 | Fri 20/02/09
4493 | 350002 | Deleted - CT4 aspects of Stage 3 PNM | PNM | 3 | Rel-8 | C4 | 2007-03-26 08:00 | 2008-12-05 17:00 | 100% | CP-080065 | - | Vodafone | yang.lu@vodafone.com | CP#42 no impact on CT4 specs | - | 35 |  | CP-42 |  | Thu 29/03/07 | Fri 30/07/10
4494 | 340010 | Key establishment between a UICC hosting device and a remote device | PNM | 2 | Rel-8 | S3 | 2006-12-06 08:00 | 2007-10-30 17:00 | 100% | SP-060839 | - | Ericsson | Vesa.Lehtovirta@ericsson.com | SP#37 completed | 33.259 |  |  |  |  | Thu 16/02/06 | Thu 26/03/09
4495 | 350049 | Deleted - Actual Requirements of PNM | PNM | 2 | Rel-8 | C1 | 2007-03-26 08:00 | 2007-03-26 08:00 | 100% | - | - | Ericsson | - | SP#37 stopped | - | 35 |  | SP-37 |  | Fri 04/05/07 | Tue 24/03/09
4496 | 330005 | eCall Data Transfer | EData | 1 | Rel-8 | S1,C1 | 2006-09-28 08:00 | 2009-03-06 17:00 | 100% | SP-060678 | - | Airbiquity | rrobinson@airbiquity.com | SP#39 completed. Linked to SA4 Feature UID_34042 (eCall_Phase2) | - |  |  |  |  | Fri 06/10/06 | Mon 02/08/10
4497 | 370081 | eData Requirements | EData | 2 | Rel-8 | S1 | 2006-09-28 08:00 | 2008-03-12 17:00 | 100% | SP-060678 | - | Airbiquity | rrobinson@airbiquity.com | SP#39 completed | 22.101, 22.105 | 37 |  |  |  | Fri 06/10/06 | Mon 02/08/10
4498 | 400014 | Transfer of data during an emergency call | EData | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080316 | - | T-Mobile | Dieter Jacobsohn | CP#43 completed | 24.008 | 40 | 21 |  |  | Fri 06/10/06 | Mon 02/08/10
4499 | 34042 | eCall data transfer Phase 2: Comparison of alternative in-band modem solutions and standardization of one in-band modem solution | eCall_Phase2 | 1 | Rel-8 | S4 | 2007-12-06 08:00 | 2009-09-24 17:00 | 100% | SP-070756 | - | Airbiquity | lhong@airbiquity.com & rrobinson@airbiquity.com | SP#45 completed. Triggered by Study UID_360015 (eCALLIBMS). Linked to SA1 Feature UID_330005 (EData) | 26.267, 26.268, 26.269, 26.967, 26.969 |  |  |  |  | Sun 09/12/07 | Mon 02/08/10
4500 | 450001 | eCall Conformance Testing | eCall_MSTest | 1 | Rel-8 | G3new | 2009-09-04 08:00 | 2010-09-03 17:00 | 100% | GP-091098 | - | Ericsson, Qualcomm | Vikrant Jain (vikrantj@qualcomm.com) | GP#47 completed. GP#43 WID approved. Testing for Rel-8 eCall_Phase2 (UID_34042) and EData (UID_330005) | 51.010-1, 51.010-2 | 45 | 23 |  |  | Mon 07/09/09 | Sat 04/09/10
4501 | 450023 | Conformance Test Aspects – non-modem procedures of eCall sessions in UTRA | UMTS_eCall_UEConTest | 1 | Rel-8 | R5 | 2009-09-18 08:00 | 2010-06-04 17:00 | 100% | RP-090952 | RP-100489 | Ericsson, Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#48 completed. Testing for Rel-8 eCall_Phase2 (UID_34042) and Edata (UID_330005) | 34.108, 34.123-1, 34.123-2, 34.123-3 | 45 | 23 |  |  | Tue 15/09/09 | Tue 01/06/10
4502 | 380060 | IP Interconnection of Services | IPinterc | 1 | Rel-8 | S1,S2,S5,C3 | 2006-08-16 08:00 | 2009-03-06 17:00 | 100% | SP-080565 | - | Telefónica O2 | chris.friel@O2.com | SP#43 completed | - | 38 | 21 |  |  | Thu 13/12/07 | Mon 02/08/10
4503 | 380061 | Stage 1 for IPinterc | IPinterc | 2 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-080565 | - | Telefónica O2 | chris.friel@O2.com | SP#39 completed. | 22.101, 22.228 | 38 | 21 |  |  | Thu 13/12/07 | Mon 02/08/10
4504 | 7005 | System enhancements for interconnection interfaces between two IMSs | IMS_NNI | 2 | Rel-8 | S2,S5,C3 | 2006-08-16 08:00 | 2009-03-06 17:00 | 100% | SP-080554 | - | Telecom Italia | Mario Madella (mario.madella@telecomitalia.it) | CP#43 completed | - | 36 |  |  |  | Thu 16/02/06 | Mon 02/08/10
4505 | 360024 | Stage 2 for IMS_NNI | IMS_NNI | 3 | Rel-8 | S2 | 2007-06-22 08:00 | 2007-12-06 17:00 | 100% | SP-080554 | - | Telecom Italia | Mario Madella (mario.madella@telecomitalia.it) | SP#38 completed | 23.002, 23.228 | 36 |  |  |  | Fri 22/06/07 | Mon 02/08/10
4506 | 360011 | IMS inter-operator service interconnection interface | FBI2-IOPSI | 3 | Rel-8 | C3 | 2007-06-01 08:00 | 2009-03-06 17:00 | 100% | CP-080578 | - | Telecom Italia | antonio.ascolese@telecomitalia.it | CP#43 completed | 29.865, 29.165 | 36 |  |  |  | Wed 20/06/07 | Mon 02/08/10
4507 | 330011 | Charging harmonization for NGN between 3GPP and ATIS-TMOC | FBI2-TISP2-CH | 3 | Rel-8 | S5 | 2006-09-28 08:00 | 2006-12-07 17:00 | 100% | SP-060545 | - | Amdocs | yishai.brown@amdocs.com | SP#34 completed | 32.297 |  |  |  |  | Mon 09/10/06 | Mon 03/03/08
4508 | 7007 | Deleted - Protocol impact of FBI for TISPAN R2 | FBI2-TISP2-c1 | 3 | Rel-8 | C1 | 2006-08-16 08:00 | 2007-03-15 17:00 | 100% | - | - | Ericsson | - | SP#38 stopped | - |  |  | SP-38 |  | Thu 16/02/06 | Tue 24/03/09
4509 | 7006 | Deleted (never approved) - Stage 2 of FBI for TISPAN R2 - Rel 8 | FBI2-TISP2-s2 | 3 | Rel-8 | S2 | 2007-11-30 17:00 | 2007-11-30 17:00 | 100% | - | - | Nokia Siemens Networks | - | SP#36 stopped | - |  |  | SP-36 |  | Thu 16/02/06 | Tue 24/03/09
4510 | 360025 | Support of (G)MSC-S – (G)MSC-S Nc Interface based on the SIP-I protocol | SIP_Nc | 1 | Rel-8 | C4,C3 | 2007-09-14 08:00 | 2009-03-06 17:00 | 100% | CP-080282 | - | Vodafone | David.Hutton@vodafone.com | CP#43 completed. Stage 1 in Feature UID_380060 (IPinterc). CP#40 updated WID CP-070517=>CP-080282 | - | 36 |  |  |  | Wed 05/09/07 | Wed 28/05/08
4511 | 410002 | Stage 1 for SIP_Nc (covered by Feature IPinterc) | SIP_Nc | 2 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-070871 | - | Telefónica O2 | chris.friel@O2.com | 22/07/08 Created. Stage 1 for SIP_Nc (covered by SA1 Feature UID_380060 Ipinterc) | 22.101, 22.228 | 41 | 21 |  |  | Thu 13/12/07 | Thu 20/03/08
4512 | 360026 | SIP-I based circuit-switched core network; Stage 2 | SIP_Nc-St2 | 2 | Rel-8 | C4 | 2007-09-14 08:00 | 2008-12-05 17:00 | 100% | CP-080282 | - | Vodafone | David.Hutton@vodafone.com | CP#42 completed | 23.231, 23.153, 23.205 | 36 |  |  |  | Wed 05/09/07 | Sat 22/11/08
4513 | 360027 | Application of SIP-I Protocols to Circuit Switched (CS) core network architecture; Stage 3 | SIP_Nc-St3C4 | 2 | Rel-8 | C4 | 2007-09-14 08:00 | 2008-12-05 17:00 | 100% | CP-080282 | - | Vodafone | David.Hutton@vodafone.com | CP#42 completed | 29.231, 29.232, 29.332 | 36 |  |  |  | Wed 05/09/07 | Sat 22/11/08
4514 | 360028 | Interworking between the 3GPP CS domain with SIP-I as signalling protocol and other networks | SIP_Nc-St3C3 | 2 | Rel-8 | C3 | 2007-09-14 08:00 | 2009-03-06 17:00 | 100% | CP-080282 | - | Nokia Siemens Networks | Thomas.Belling@nsn.com | CP#43 completed. CP#42 target 12/08=>03/09 | 29.235, 23.172, 23.202, 29.007, 29.163, 29.414 | 36 |  |  |  | Wed 05/09/07 | Thu 19/02/09
4515 | 370051 | Earthquake and Tsunami Warning System | ETWS | 1 | Rel-8 | S1,S2,C1,C4,G2 | 2007-09-10 08:00 | 2009-05-15 17:00 | 100% | SP-070815 | - | NTT DoCoMo | kitaharar@nttdocomo.co.jp | SP#43 Larger scope Feature UID_380057 (PWS) moved to Rel-9 | - | 37 |  |  |  | Mon 19/11/07 | Mon 02/08/10
4516 | 370052 | Stage 1 for ETWS | ETWS | 2 | Rel-8 | S1 | 2007-09-10 08:00 | 2008-03-12 17:00 | 100% | SP-070815 | - | NTT DoCoMo | kitaharar@nttdocomo.co.jp | SP#39 completed | 22.168 | 37 |  |  |  | Mon 19/11/07 | Thu 20/03/08
4517 | 380056 | SA2 aspects of ETWS | ETWS | 2 | Rel-8 | S2 | 2008-01-14 08:00 | 2008-09-18 17:00 | 100% | SP-070815 | - | NTT DoCoMo | tanakai@nttdocomo.co.jp | SP#41 completed | 23.828, 23.401 | 38 | 21 |  |  | Thu 13/12/07 | Sun 14/09/08
4518 | 400015 | CT1 aspects of ETWS | ETWS | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080951 | - | NTT DoCoMo | yamashitahi@s1.nttdocomo.co.jp | CP#42 completed | 23.041 | 40 | 21 |  |  | Thu 13/12/07 | Mon 02/08/10
4519 | 410021 | CT4 aspects of ETWS | ETWS | 2 | Rel-8 | C4 | 2008-09-26 13:00 | 2008-12-05 17:00 | 100% | CP-080951 | - | NTT DoCoMo | yamashitahi@s1.nttdocomo.co.jp | CP#42 completed | 29.168 | 40 | 21 |  |  | Thu 13/12/07 | Mon 02/08/10
4520 | 430045 | ETWS primary notification message definition in GERAN | ETWS | 2 | Rel-8 | G2 | 2009-03-12 08:00 | 2009-05-15 17:00 | 100% | SP-090154 | - | Ericsson | claes-goran.persson@ericsson.com | SP#44 completed with CT1 help (GERAN2 LS_in SP-090154) | 44.018, 44.060 | 43 | 22 |  |  | Tue 10/03/09 | Sat 30/05/09
4521 | 440011 | Conformance Test Aspects – UMTS Earthquake and Tsunami Warning System (ETWS) FDD | ETWS_UMTS_UEConTestFDD | 1 | Rel-8 | R5 | 2009-05-29 08:00 | 2010-03-12 17:00 | 100% | RP-090467 | RP-100068 | NTT DoCoMo | Makoto Ito (itohm@nttdocomo.co.jp) | RP#47 completed. Testing for Rel-8 ETWS UID_370051 | 34.108, 34.123-1, 34.123-2 | 44 | 23 |  |  | Thu 28/05/09 | Mon 08/03/10
4522 | 380059 | In Case of Emergency numbers storage and easy access on UICC | ICE | 1 | Rel-8 | S1,C6 | 2007-03-13 08:00 | 2009-03-06 17:00 | 100% | SP-070944 | - | Vodafone | armin.toepfer@vodafone.com | CP#43 completed (ICE Graphics not included in Rel-8) | - | 38 | 21 |  |  | Thu 13/12/07 | Wed 04/03/09
4523 | 380159 | Stage 1 for ICE | ICE | 2 | Rel-8 | S1 | 2007-03-13 08:00 | 2008-03-12 17:00 | 100% | SP-070944 | - | Vodafone | armin.toepfer@vodafone.com | SP#39 Stage 1 completed | 22.030, 22.101 | 38 | 21 |  |  | Thu 13/12/07 | Tue 17/06/08
4524 | 380259 | CT6 aspects of ICE | ICE | 2 | Rel-8 | C6 | 2007-03-13 08:00 | 2009-03-06 17:00 | 100% | SP-070944 | - | Vodafone | armin.toepfer@vodafone.com | CP#43 completed (ICE Graphics not in Rel-8 / not explicitly in SA1 WID either) | 31.102 | 38 | 21 |  |  | Thu 13/12/07 | Mon 06/09/10
4525 | 330006 | Local Charging Zone Requirements | LCZR | 1 | Rel-8 | S1 | 2006-09-28 08:00 | 2008-03-12 17:00 | 100% | SP-060482 | - | China Mobile | liuhongyfw@chinamobile.com | SP#39 Stage 1 completed | 22.115 |  |  |  |  | Fri 06/10/06 | Tue 25/03/08
4526 | 340029 | Customized Alerting Tone (CAT) service | CAT | 1 | Rel-8 | S1,C1,C3,C4 | 2006-12-06 08:00 | 2009-09-18 17:00 | 100% | SP-070122 | - | China Mobile | fenglingjuan@chinamobile.com | CP#45 completed | - | 34 |  |  |  | Fri 04/11/05 | Mon 02/08/10
4527 | 370028 | Stage 1 for CAT | CAT | 2 | Rel-8 | S1 | 2006-12-06 08:00 | 2007-09-20 17:00 | 100% | SP-070122 | - | China Mobile | fenglingjuan@chinamobile.com | - | 22.182 | 37 |  |  |  | Tue 02/10/07 | Wed 10/09/08
4528 | 370029 | TISPAN requirements for customized multimedia information services | TISCMI | 2 | Rel-8 | S1 | 2007-09-03 08:00 | 2007-12-10 17:00 | 100% | SP-070880 | - | China Mobile | fenglingjuan@chinamobile.com | SP#38 completed | 22.182 | 37 |  |  |  | Tue 02/10/07 | Thu 24/07/08
4529 | 390014 | IMS CAT Supplementary Service | CAT-SS | 2 | Rel-8 | C1,C3 | 2008-03-12 08:00 | 2009-09-18 17:00 | 100% | CP-080496 | - | Nortel | milanpa@nortel.com | - | - | 39 | 21 |  |  | Mon 03/03/08 | Fri 21/11/08
4530 | 390114 | IMS CAT SS | CAT-SS | 3 | Rel-8 | C1 | 2008-04-21 08:00 | 2008-12-04 17:00 | 100% | CP-080496 | - | Nortel | milanpa@nortel.com | CP#42 completed | 24.182 | 39 | 21 |  |  | Mon 03/03/08 | Fri 21/11/08
4531 | 390071 | CAT solution for voice and video call in CS domain | CAT-SS | 3 | Rel-8 | C3 | 2008-03-12 08:00 | 2009-09-18 17:00 | 100% | CP-080496 | - | Nortel | milanpa@nortel.com | CP#45 completed. Triggered by Study UID_360031 (TR 29.882) | 29.163 | 39 | 21 |  |  | Mon 03/03/08 | Mon 02/08/10
4532 | 410010 | CAT Service in 3GPP CS domain | CAT-3G_CS | 2 | Rel-8 | C4,C1 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080445 | - | China Mobile | zhaoyuyi@chinamobile.com | - | 23.205, 23.231, 29.002 | 41 | 21 |  |  | Thu 11/09/08 | Wed 11/01/12
4533 | 410110 | CT4 part of CAT Service in 3GPP CS domain | CAT-3G_CS | 3 | Rel-8 | C4 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080445 | - | China Mobile | zhaoyuyi@chinamobile.com | CP#43 completed. Triggered by Study UID_360031 (TR 29.882) | 23.205, 23.231, 29.002 | 41 | 21 |  |  | Thu 11/09/08 | Wed 11/01/12
4534 | 410015 | CT1 part of CAT Service in 3GPP CS domain | CAT-3G_CS | 3 | Rel-8 | C1 | 2008-09-12 08:00 | 2008-12-05 17:00 | 100% | CP-080445 | - | China Mobile | zhaoyuyi@chinamobile.com | CP#42 completed. Triggered by Study UID_360031 (TR 29.882) | 24.008, 23.014 | 41 | 21 |  |  | Thu 11/09/08 | Wed 11/01/12
4535 | 340031 | Service-Level Interworking for Messaging Services | MESSIW | 1 | Rel-8 | S1,S2,C3,C1 | 2007-03-26 17:00 | 2009-03-06 17:00 | 100% | SP-070816 | - | Huawei | ling.liu@huawei.com; duanxiaoqin@huawei.com | CP#43 completed | - | 34 |  |  |  | Fri 04/11/05 | Mon 02/08/10
4536 | 350047 | Stage 1 for MESSIW | MESSIW | 2 | Rel-8 | S1 | 2007-03-26 17:00 | 2007-03-26 17:00 | 100% | SP-070816 | - | Huawei | ling.liu@huawei.com | SP#35 completed | 22.105, 22.340 | 35 |  |  |  | Fri 04/11/05 | Sat 22/03/08
4537 | 350048 | Stage 2 for MESSIW | MESSIW | 2 | Rel-8 | S2 | 2007-04-26 08:00 | 2008-03-07 17:00 | 100% | SP-070816 | - | Huawei | patrice.hede@huawei.com | SP#39 completed | 23.811, 23.204 | 35 |  |  |  | Fri 04/11/05 | Sat 22/03/08
4538 | 400016 | CT3 part of Stage 3 for MESSIW | MESSIW | 2 | Rel-8 | C3 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080773 | - | Huawei | xupeili@huawei.com | CP#43 completed | 29.311 | 40 | 21 |  |  | Wed 19/07/06 | Thu 19/02/09
4539 | 400017 | CT1 part of Stage 3 for MESSIW | MESSIW | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080773 | - | Huawei | xupeili@huawei.com | CP#42 completed | 24.229 | 40 | 21 |  |  | Wed 19/07/06 | Mon 02/08/10
4540 | 340044 | Multimedia Priority Service | PRIOR_EMR | 1 | Rel-8 | S1,C1,C3,C4 | 2006-06-08 08:00 | 2009-09-18 17:00 | 100% | SP-060780 | - | Telcordia | jgarraha@telcordia.com | CP#45 completed | - | 34 |  |  |  | Fri 28/03/03 | Wed 09/09/09
4541 | 320023 | Service Requirements for PRIOR | PRIOR_EMR | 2 | Rel-8 | S1 | 2006-06-08 08:00 | 2007-12-06 17:00 | 100% | SP-060780 | - | Telcordia | jgarraha@telcordia.com | SP#38 completed | New 22.153 | 32 |  |  |  | Fri 28/03/03 | Tue 03/06/08
4542 | 340012 | CT1 part of Stage 3 for PRIOR | PRIOR_EMR | 2 | Rel-8 | C1 | 2006-12-01 08:00 | 2009-09-18 17:00 | 100% | CP-070576 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#45 completed | 24.229 | 34 |  |  |  | Mon 18/12/06 | Wed 09/09/09
4543 | 370021 | CT4 part of Stage 3 for PRIOR | PRIOR_EMR | 2 | Rel-8 | C4 | 2007-09-21 08:00 | 2009-03-06 17:00 | 100% | CP-070576 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#43 completed | 23.008, 29.228, 29.229 | 37 |  |  |  | Tue 25/09/07 | Wed 11/03/09
4544 | 370020 | Deleted - Stage 3 for PRIOR | PRIOR-EMR | 2 | Rel-8 | C3 | 2007-09-21 08:00 | 2009-05-29 17:00 | 100% | CP-070576 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#44 stopped (Reason: No Rel-8 solution expected (LS sent to SA2, but not prioritized in SA2) | 29.212, 29.213, 29.214, 29.163 | 37 |  | CP-44 | PCG-23 | Tue 25/09/07 | Fri 29/05/09
4545 | 360010 | Open Service Access (OSA) Rel-8 | OSA8 | 1 | Rel-8 | S1,C5 | 2007-08-23 08:00 | 2008-05-30 17:00 | 100% | SP-070692 | - | Orange | Song Dong | SP#40 maintenance & new OSA work moved to OMA. Rel-9 onwards 3GPP references to 22.127 changed to OMA Parlay Service Access Requirements (OMA-RD-Parlay_Service_Access-V1_0-20100427-A). | - | 36 |  |  |  | Tue 22/03/05 | Mon 30/08/10
4546 | 360004 | OSA Stage 1 - Service Requirements | OSA8 | 2 | Rel-8 | S1 | 2007-08-23 08:00 | 2008-03-12 17:00 | 100% | - | - | Orange, AePONA | Song Dong | SP#40 maintenance & new OSA work moved to OMA. Rel-9 onwards 3GPP references to 22.127 changed to OMA Parlay Service Access Requirements (OMA-RD-Parlay_Service_Access-V1_0-20100427-A). | 22.127 | 36 |  |  |  | Tue 22/03/05 | Mon 30/08/10
4547 | 370034 | OSA Stage 1 - NGN Service Requirement | OSA8-IMSReq | 2 | Rel-8 | S1 | 2007-09-03 08:00 | 2008-03-14 17:00 | 100% | SP-070692 | - | Orange | Song Dong | SP#40 maintenance & new OSA work moved to OMA | 22.127 | 37 |  |  |  | Tue 02/10/07 | Mon 02/08/10
4548 | 360005 | Rel-8 OSA Stage 2/3 enhancements | OSA8-IMS | 2 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | SP#40 maintenance & new OSA work moved to OMA | 23.198, 29.198, 29.199 | 36 |  |  |  | Wed 14/12/05 | Mon 02/08/10
4549 | 370012 | Deleted - Ensure Parlay-X composable with identity management frameworks, in particular Liberty Alliance | - | 3 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Ericsson | catherine.mulligan@ericsson.com | CP#40: Work moved to OMA | existing 29.199-xy | 37 | 21 | CP-40 | PCG-21 | Thu 13/09/07 | Tue 24/03/09
4550 | 370013 | Parlay-X Content Management web service (store/manage meta-data) | OSA8-IMS | 3 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-21 | 37 |  |  |  | Thu 13/09/07 | Mon 19/01/09
4551 | 370014 | Parlay-X Policy web service | OSA8-IMS | 3 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-22 | 37 |  |  |  | Thu 13/09/07 | Mon 19/01/09
4552 | 370015 | Parlay-X Terminal status web service | OSA8-IMS | 3 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-08 | 37 |  |  |  | Thu 13/09/07 | Mon 19/01/09
4553 | 370016 | Deleted - Identify communication format used by a particular application | - | 3 | Rel-8 | C5 | 2007-10-25 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Ericsson | catherine.mulligan@ericsson.com | CP#40: Work moved to OMA | existing 29.199-xy | 37 | 21 | CP-40 | PCG-21 | Thu 13/09/07 | Tue 24/03/09
4554 | 380047 | Deleted - Security on User Profile Management - reuse GUP API (22.127 CR 0084 S1-071794) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
4555 | 380048 | Deleted - Privacy on Subscriber Identity (Liberty Alliance, OASIS) (22.127 CR 0085 S1-071835) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
4556 | 380049 | Deleted - Topology Hiding (22.127 CR 0086 S1-071838) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
4557 | 380050 | Deleted - Subscriber event notification (22.127 CR 0087 S1-071836) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
4558 | 380051 | Deleted - Event notification (22.127 CR 0088 S1-071762) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
4559 | 380052 | Deleted - Access policy (22.127 CR 0089 S1-071763) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
4560 | 380053 | Deleted - API usage accounting (22.127 CR 0090 S1-071792) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Telecom Italia | vincenzo.amorino@telecomitalia.it | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | PXWS Framework | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
4561 | 380054 | Presence alignment with OMA and IETF (22.127 CR 0092 S1-071764) | OSA8-IMS | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.199-14/13 | 38 | 21 |  |  | Wed 05/12/07 | Mon 19/01/09
4562 | 380055 | Deleted - Service identification (22.127 CR 0095 S1-071837) | - | 3 | Rel-8 | C5 | 2007-12-05 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Ericsson | catherine.mulligan@ericsson.com | SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA | existing 29.199-xy | 38 | 21 | CP-40 | PCG-21 | Wed 05/12/07 | Tue 24/03/09
4563 | 390067 | Framework Enterprise Operator (Service Subscription function) | OSA8-IMS | 3 | Rel-8 | C5 | 2008-01-10 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-03 | 39 | 21 |  |  | Wed 26/03/08 | Mon 19/01/09
4564 | 390068 | Mobility Emergency Location | OSA8-IMS | 3 | Rel-8 | C5 | 2008-01-10 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-06 | 39 | 21 |  |  | Wed 26/03/08 | Mon 19/01/09
4565 | 390069 | Connectivity Manager SCF | OSA8-IMS | 3 | Rel-8 | C5 | 2008-01-10 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-10 | 39 | 21 |  |  | Wed 26/03/08 | Mon 19/01/09
4566 | 390070 | PAM Presence Agent | OSA8-IMS | 3 | Rel-8 | C5 | 2008-01-10 08:00 | 2008-05-30 17:00 | 100% | CP-080429 | - | Alcatel-Lucent | unmehopa@alcatel-lucent.com | CP#40 completed | 29.198-14 | 39 | 21 |  |  | Wed 26/03/08 | Mon 19/01/09
4567 | 360032 | Paging Permission with Access Control (PPACR) | PPACR | 1 | Rel-8 | S1,C1 | 2007-06-12 08:00 | 2008-12-05 17:00 | 100% | SP-070501 | - | NTT DoCoMo | Morita Takashi | CP#42 completed. Triggered by Study UID_330016 (PPAC). | - | 36 |  |  |  | Tue 16/10/07 | Wed 10/12/08
4568 | 370084 | Stage 1 for PPACR | PPACR-S1 | 2 | Rel-8 | S1 | 2007-06-12 08:00 | 2007-09-14 17:00 | 100% | SP-070501 | - | NTT DoCoMo | Morita Takashi | SP#37 completed | 22.011 | 37 |  |  |  | Tue 16/10/07 | Fri 16/05/08
4569 | 380017 | Stage 3 for PPACR (CT1) | PPACR-CT1 | 2 | Rel-8 | C1 | 2007-11-14 08:00 | 2008-12-05 17:00 | 100% | CP-070783 | - | NTT DoCoMo | - | CP#42 completed | 24.008, 23.122, 24.301 | 38 | 21 |  |  | Wed 14/11/07 | Fri 21/11/08
4570 | 490017 | Conformance Test Aspects – Paging Permission with Access Control (PPAC) | PPAC_UEConTest | 1 | Rel-8 | R5 | 2010-09-17 08:00 | 2010-12-10 17:00 | 100% | RP-100806 | RP-101074 | NTT DoCoMo | Takao.Shimizu.rp@nttdocomo.com | RP#50 completed | UTRA 34.108, 34.123-1, 34.123-2, 34.123-3 | 49 | 25 |  |  | Fri 10/09/10 | Wed 08/12/10
4571 | 380063 | Charging for multi-phases services | CHRGMPH | 1 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 99% | SP-080053 | - | Telecom Italia | Marco.DeLuca1@telecomitalia.it | SP#39 Stage 1 completed | 22.115 | 38 | 21 |  |  | Thu 13/12/07 | Wed 10/12/08
4572 | 380070 | Stage 1 for CHRGMPH | CHRGMPH-s1 | 2 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-080053 | - | Telecom Italia | Marco.DeLuca1@telecomitalia.it | SP#39 completed | 22.115 | 38 | 21 |  |  | Thu 13/12/07 | Thu 20/03/08
4573 | 380065 | Home NodeB / eNodeB | HomeNB | 1 | Rel-8 | S1,C1,C4 | 2007-12-06 08:00 | 2009-03-06 17:00 | 100% | SP-070952 | - | Vodafone | John Watson | CP#43 completed | - | 38 | 21 |  |  | Thu 13/12/07 | Wed 11/03/09
4574 | 380066 | Stage 1 for Home NodeB / eNodeB | HomeNB-S1 | 2 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-070952 | - | Vodafone | John Watson | SP#39 completed | 22.011, 22.115 | 38 | 21 |  |  | Thu 13/12/07 | Thu 24/07/08
4575 | 420019 | Support of Closed Subscriber Group (CSG) | - | 2 | Rel-8 | C4 | 2008-12-05 08:00 | 2009-03-06 17:00 | 100% | - | - | CT#42 | Hannu Hietalahti | CP#43 completed. SP#42 SP-080874 22.011CR0141 confirmed Requirement to support roaming subscribers with CSG home network subscription but did NOT confirmed requirement for home network independent support of roamers in CSG | 29.002, 29.272, 23.008, 23.003 | 42 | 22 |  |  | Thu 04/12/08 | Mon 23/02/09
4576 | 410012 | CSG and Idle Mode Mobility for LTE Home eNodeB | HomeNB-LTE | 2 | Rel-8 | C1 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080498 | - | Huawei | zhang.peng@huawei.com | CP#43 completed | 23.122, new (24.285, 24.301, 24.801) | 41 | 21 |  |  | Wed 03/09/08 | Wed 11/03/09
4577 | 410013 | CSG and Idle Mode Mobility for 3G Home NodeB | HomeNB-3G | 2 | Rel-8 | C1 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | CP-080792 | - | Qualcomm | Osok Song | CP#43 completed | 23.122, 24.008, new 24.285 | 41 | 21 |  |  | Wed 03/09/08 | Wed 11/03/09
4578 | 390033 | UTRA HNB | HNB | 1 | Rel-8 | RP,S5 | 2008-03-07 08:00 | 2009-06-04 17:00 | 100% | - | - | - | - | SP#44 completed | - | 39 | 21 |  |  | Tue 04/01/05 | Tue 03/06/08
4579 | 400053 | Support of UTRA HNB | HNB-supp | 2 | Rel-8 | R2 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | RP-080752 | RP-090040 | Huawei | Yang Xudong (yangxudong@huawei.com) | RP#43 completed | 25.304, 25.306, 25.331, new 25.367 | 40 | 21 |  |  | Tue 03/06/08 | Fri 27/02/09
4580 | 400054 | UTRAN Architecture for 3G HNB | HNB-arch | 2 | Rel-8 | R3 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | RP-080487 | RP-090042 | Alcatel-Lucent | Martin Warner (mw15@alcatel-lucent.com) | RP#42 completed | 25.401, 25.410, 25.412, 25.413, 25.414, 25.415, new (25.467, 25.468, 25.469) | 40 | 21 |  |  | Tue 03/06/08 | Fri 06/03/09
4581 | 390034 | FDD Home NodeB RF requirements | HNB-RF | 2 | Rel-8 | R4 | 2008-03-07 08:00 | 2009-03-06 17:00 | 100% | RP-080971 | RP-090041 | Motorola | Ying Cai (yingcai@motorola.com) | RP#43 completed | 25.104, 25.141, new 25.967 | 39 | 21 |  |  | Mon 27/09/04 | Fri 27/02/09
4582 | 420037 | 3G Home NodeB OAM&P Type 1 Management Interface | HNB-3G_OAM | 2 | Rel-8 | S5 | 2008-12-11 08:00 | 2009-06-04 17:00 | 100% | SP-080708 | - | Huawei | Zou Lan (zlan@huawei.com) | SP#44 completed. Complements work in BroadBand Forum | new (32.581, 32.582, 32.583, 32.584) | 42 | 22 |  |  | Wed 03/12/08 | Mon 18/05/09
4583 | 430022 | UTRA HNB – UE Conformance Testing | HNB-UEConTest | 1 | Rel-8 | R5 | 2009-03-06 08:00 | 2010-06-04 17:00 | 100% | - | - | - | - | RP#48 FDD completed. Testing for Feature UID_390033 UTRA HNB | - | 43 | 22 |  |  | Fri 27/02/09 | Tue 01/06/10
4584 | 430023 | Conformance Test Aspects – UTRA HNB (FDD) | HNB-UEConTestFDD | 2 | Rel-8 | R5 | 2009-03-06 08:00 | 2010-06-04 17:00 | 100% | RP-090023 | RP-100482 | Huawei | Trica Li (trica_li@huawei.com) | RP#48 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 | 43 | 22 |  |  | Fri 27/02/09 | Tue 01/06/10
4585 | 350015 | Lawful Interception in the 3GPP Rel-8 | LI8 | 1 | Rel-8 | S3 | 2007-03-12 08:00 | 2009-03-12 17:00 | 100% | SP-070238 | - | BMWI, Verizon | berthold.wilhelm@bnetza.de, ron_ryan@verizon.net | SP#43 completed | 33.106, 33.107, 33.108 | 35 |  |  |  | Thu 29/03/07 | Wed 11/03/09
4586 | 390046 | Generic Bootstrapping Architecture Push Function | GBAPush | 1 | Rel-8 | S3,C1,C4 | 2008-03-12 08:00 | 2009-03-06 17:00 | 100% | SP-080133 | - | Ericsson | Rolf Blom | CP#43 completed | - | 39 | 21 |  |  | Sat 22/03/08 | Fri 20/02/09
4587 | 390146 | SA3 part of GBAPush (33.223) | GBAPush | 2 | Rel-8 | S3 | 2008-03-12 08:00 | 2008-12-05 17:00 | 100% | SP-080133 | - | Ericsson | Rolf Blom | SP#42 completed 33.223 as Rel-8. TS 33.224 moved to Rel-9 under new UID_420039 | 33.223 | 39 | 21 |  |  | Sat 22/03/08 | Mon 09/03/09
4588 | 390246 | CT1 part of GBAPush | GBAPush | 2 | Rel-8 | C1 | 2008-03-12 08:00 | 2009-03-06 17:00 | 100% | CP-090112 | - | Ericsson | Rolf Blom | CP#43 completed | 24.109 | 39 | 21 |  |  | Sat 22/03/08 | Wed 04/03/09
4589 | 390346 | CT4 part of GBAPush | GBAPush | 2 | Rel-8 | C4 | 2008-03-12 08:00 | 2009-03-06 17:00 | 100% | CP-090112 | - | Ericsson | Rolf Blom | CP#43 completed | 29.109 | 39 | 21 |  |  | Sat 22/03/08 | Wed 04/03/09
4590 | 34045 | Requirements and Test methods for Wideband Terminals | RETEM_WB_T | 1 | Rel-8 | S4 | 2008-03-12 08:00 | 2008-12-11 17:00 | 100% | SP-080004 | - | FT, Ericsson | stephane.ragot@orange-ftgroup.com, wanqing.shi@sonyericsson.com | SP#42 completed. SP#39 WID approved. | 26.131, 26.132 |  |  |  |  | Tue 18/03/08 | Fri 21/11/08
4591 | 34043 | Extending PSS and MBMS User Services for optimized Mobile TV | PSS_MBMS_OMTV | 1 | Rel-8 | S4 | 2007-12-06 08:00 | 2008-12-11 17:00 | 100% | SP-070757 | - | Ericsson | thorsten.lohmar@ericsson.com | SP#42 completed. SP#38 WID approved. | 26.234, 26.346, 26.946 |  |  |  |  | Sun 09/12/07 | Fri 21/11/08
4592 | 400028 | Encoding formats, transport formats and media description signalling for interworking, QoE, and other enhancements to MTSI-MHI | MTSI_eMHI | 1 | Rel-8 | S4,C3,C4 | 2007-12-06 08:00 | 2009-03-12 17:00 | 100% | SP-080443 | - | Ericsson, Qualcomm | olle.franceschi@ericsson.com, nleung@qualcomm.com | TSG#43 completed | - | 40 | 21 |  |  | Sun 09/12/07 | Sat 21/02/09
4593 | 34041 | MTSI Video - Dynamic Rate Adaptation/Signalling of Image Size | MTSI_eMHI-DRASIS | 2 | Rel-8 | S4 | 2007-12-06 08:00 | 2009-03-12 17:00 | 100% | SP-080246 | - | Qualcomm, Samsung | nleung@qualcomm.com & kyunghun.jung@samsung.com | SP#43 completed | 26.114 |  |  |  |  | Sun 09/12/07 | Mon 02/08/10
4594 | 400018 | CT3 part of Enhancement of interworking between MTSI and CS networks | MTSI_eMHI | 2 | Rel-8 | C3 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080774 | - | Huawei | Tingfang Tang (tagna_online@huawei.com) | CP#43 completed | 29.163 | 40 | 21 |  |  | Sun 09/12/07 | Fri 20/02/09
4595 | 400020 | CT4 part of Enhancement of interworking between MTSI and CS networks | MTSI_eMHI | 2 | Rel-8 | C4 | 2008-05-30 08:00 | 2009-03-06 17:00 | 100% | CP-080774 | - | Huawei | Tingfang Tang (tagna_online@huawei.com) | CP#43 completed | 29.332 | 40 | 21 |  |  | Sun 09/12/07 | Fri 20/02/09
4596 | 400019 | Deleted - CT1 part of Enhancement of interworking between MTSI and CS networks | MTSI_eMHI | 2 | Rel-8 | C1 | 2008-05-30 08:00 | 2008-12-12 17:00 | 100% | CP-080774 | - | Huawei | Tingfang Tang (tagna_online@huawei.com) | CP#42 stopped (No CT1-impact). WID updated CP-080422=>CP-080774 | - | 40 | 21 | CP-42 |  | Sun 09/12/07 | Mon 02/08/10
4597 | 340063 | Rel-8 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM8 | 1 | Rel-8 | S5,C1,C4,IETF | 2007-06-07 08:00 | 2012-12-07 17:00 | 100% | - | - | - | - | OAM8 is an umbrella Feature also for OAM&P related TEI8 type of changes that are not part of any other dedicated feature/WI | TR 30.818 | 34 |  |  |  | Thu 08/03/07 | Mon 02/08/10
4598 | 340064 | Rel-8 Network Infrastructure Management | OAM8-NIM | 2 | Rel-8 | S5 | 2007-06-07 08:00 | 2009-12-04 17:00 | 100% | - | - | - | - | - | - | 34 |  |  |  | Fri 13/07/07 | Tue 24/03/09
4599 | 35051 | Telecom Management Methodology | OAM8-NIM | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2009-03-12 17:00 | 100% | SP-070296 | - | Ericsson | thomas.tovinger@ericsson.com | SP#43 completed | 32.155, 32.153 |  |  |  |  | Fri 17/06/05 | Mon 23/02/09
4600 | 35053 | Advanced Alarming on Itf-N | OAM8-NIM | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2008-06-12 17:00 | 100% | SP-070492 | - | Nokia Siemens Networks | SUERBAUM, Clemens | SP#40 completed | 32.121, 32.122, 32.123 |  |  |  |  | Fri 17/06/05 | Wed 04/06/08
4601 | 35056 | CN CS Bearer Transport Network (BTN) relative NRM | OAM8-NIM | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2008-06-12 17:00 | 100% | SP-070300 | - | China Mobile | Li Jian (lijian@chinamobile.com) | SP#40 completed | 32.632, 32.633, 32.635 |  |  |  |  | Fri 17/06/05 | Mon 28/04/08
4602 | 390016 | Alignment with eTOM and M.3060 architectural concepts | OAM8-NIM | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2008-12-11 17:00 | 100% | SP-080068 | - | TeliaSonera | tommy.berggren@teliasonera.com | SP#42 completed | 32.101/2, 32-series | 39 | 21 |  |  | Sat 15/09/07 | Tue 25/11/08
4603 | 400030 | IRP SOAP Solution Sets | OAM8-NIM | 3 | Rel-8 | S5 | 2008-06-05 08:00 | 2009-03-12 17:00 | 100% | SP-090148 | - | Ericsson | edwin.tse@ericsson.com | SP#43 completed | 32.111-7, 32.617, 32.417, 32.367, 32.347, 32.111-1, 32.111-2, 32.111-3, 32.111-5, 32.307, 32.317, 32.341, 32.342, 32.343, 32.345, 32.361, 32.362, 32.363, 32.365, 32.411, 32.412, 32.413, 32.415, 32.611, 32.612, 32.613, 32.615, 32.625 | 40 | 21 |  |  | Sat 15/09/07 | Tue 11/08/09
4604 | 450052 | Create missing specifications for IRP XML definitions | OAM8-NIM | 3 | Rel-8 | S5 | 2009-09-24 08:00 | 2009-12-04 17:00 | 100% | SP-090553 | - | ZTE | Shuqiang Huang (huangsq@zte.com.cn) | SP#46 completed. Create missing XML definitions specs for IRPs (Advanced Alarm Management, Communication Surveillance, Self-Configuration of Network Elements, Software Management) needed for implementation of Rel-8 Notification Log IRP (TS 32.33x) | new (32.125, 32.355, 32.505, 32.535), 32.150, 32.153, 32.335 | 45 | 23 |  |  | Fri 11/09/09 | Tue 01/12/09
4605 | 370002 | Deleted - End point modelling for reference point | OAM8-NIM | 3 | Rel-8 | S5 | 2007-09-17 08:00 | 2008-12-11 17:00 | 100% | SP-070618 | - | Motorola | Yizhi Yao (yzyao@motorola.com) | SP#41 Work stopped. Contributions related to E-UTRAN/EPC to be submitted to UID_380036 E-UTRAN NRM IRP/ UID_380037 EPC NRM IRP | 32.152, 32.62/3/4x, 32.73x | 37 |  | SP-41 | PCG-21 | Sat 15/09/07 | Tue 24/03/09
4606 | 340065 | Rel-8 Performance Management | OAM8-PM | 2 | Rel-8 | S5 | 2007-06-07 08:00 | 2009-03-12 17:00 | 100% | - | - | - | Li Jian (lijian@chinamobile.com) | - | - | 34 |  |  |  | Fri 13/07/07 | Thu 26/06/08
4607 | 35061 | IP bearer network Performance measurement definitions | OAM8-PM | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2008-12-11 17:00 | 100% | SP-070301 | - | China Mobile | lilianyuan@chinamobile.com | SP#42 completed | 32.321, 32.322, 32.323, 32.325 |  |  |  |  | Fri 17/06/05 | Mon 02/08/10
4608 | 360001 | HSUPA performance measurements | OAM8-PM | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2008-12-11 17:00 | 100% | SP-070835 | - | China Mobile | Li Jian (lijian@chinamobile.com) | SP#42 completed | 32.405 | 36 |  |  |  | Mon 28/05/07 | Tue 25/11/08
4609 | 360002 | Key Performance Indicators (KPIs) for UMTS and GSM | OAM8-PM | 3 | Rel-8 | S5 | 2007-06-07 08:00 | 2009-03-12 17:00 | 100% | SP-070299 | - | China Mobile | Li Jian (lijian@chinamobile.com), Liang Shuangchun (liangshuangchun@cmdi.chinamobile.com) | SP#43 completed | 32.410 | 36 |  |  |  | Mon 28/05/07 | Mon 23/02/09
4610 | 340066 | Rel-8 Trace Management | OAM8-Trace | 2 | Rel-8 | C1,C4,IETF | 2008-03-07 08:00 | 2012-12-07 17:00 | 100% | - | - | - | - | - | - | 34 |  |  |  | Fri 22/06/07 | Wed 10/12/08
4611 | 11067 | CT1 part of Service Level Tracing in IMS | OAM8-Trace | 3 | Rel-8 | C1 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | CP-080315 | - | Vodafone | peter.dawes@vodafone.com | CP#42 completed | 24.323, 24.229 |  |  |  |  | Mon 17/03/08 | Mon 02/08/10
4612 | 521028 | (IETF) Service Level Tracing in IMS (RFC8497) | OAM8-Trace | 3 | Rel-8 | C1-IETF | 2008-03-07 08:00 | 2012-12-07 17:00 | 100% | CP-080315 | - | Peter Dawes | peter.dawes@vodafone.com | CP#58 Removed from Rel-8, Rel-9 and Rel-10 (Not completed internet-draft) | Rel-11 remains draft-dawes-dispatch-debug | 52 | 27 |  |  | Mon 20/06/11 | Wed 20/03/13
4613 | 531003 | (IETF) Service Level Tracing in IMS (draft-dawes-sipping-debug-event) | OAM8-Trace | 3 | Rel-8 | C1-IETF | 2008-03-07 08:00 | 2011-12-09 17:00 | 100% | CP-080315 | - | Peter Dawes | peter.dawes@vodafone.com | CP#54 Draft removed from 3GPP documentation, covered by draft-dawes-sipping-debug | draft-dawes-sipping-debug-event | 53 | 27 |  |  | Fri 29/07/11 | Tue 13/12/11
4614 | 400022 | CT4 part of Service Level Tracing in IMS | OAM8-Trace | 3 | Rel-8 | C4 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | CP-080315 | - | Vodafone | peter.dawes@vodafone.com | CP#42 completed | 29.228, 29.229 | 40 | 21 |  |  | Mon 17/03/08 | Mon 02/08/10
4615 | 400021 | Deleted - CT3 part of Service Level Tracing in IMS | OAM8-Trace | 3 | Rel-8 | C3 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | CP-080315 | - | Vodafone | peter.dawes@vodafone.com | CP#42 stopped (No CT3-impact) | - | 40 | 21 | CP-42 | PCG-22 | Mon 17/03/08 | Mon 02/08/10
4616 | 350016 | Rel-8 Charging Management small Enhancements | CH8 | 1 | Rel-8 | S5 | 2006-03-16 08:00 | 2008-12-11 17:00 | 100% | - | - | - | - | CH8 is an umbrella Feature also for OAM&P related TEI8 type of changes that are not part of any other dedicated feature/WI | TR 30.818 | 35 |  |  |  | Mon 22/05/06 | Tue 24/03/09
4617 | 350038 | Online charging correlation | CH8 | 2 | Rel-8 | S5 | 2006-03-16 08:00 | 2007-12-14 17:00 | 100% | SP-070077 | - | Orange | Chahine, Rony | SP#38 completed | 32.296 | 35 |  |  |  | Mon 17/03/08 | Mon 17/03/08
4618 | 360003 | SMS online charging | CH8 | 2 | Rel-8 | S5 | 2007-06-07 08:00 | 2007-12-14 17:00 | 100% | SP-070293 | - | Vodafone | Gavin.Wong@vodafone.com | SP#38 completed | 32.240, 32.299, new 32.274 | 36 |  |  |  | Tue 29/05/07 | Mon 17/03/08
4619 | 410045 | Introduce Online Charging from SMS-SC into the SMS Charging Specifications | CH8 | 2 | Rel-8 | S5 | 2008-09-18 08:00 | 2008-12-11 17:00 | 100% | SP-080463 | - | Acision | erik.gebler@acision.com | SP#42 completed. Linked to SA2 UID 32081 (Support of SMS over IP networks) and CT4 UID 340016 (Routeing of MT-SMS via the HPLMN). | 32.274, 32.299 | 41 | 21 |  |  | Mon 15/09/08 | Tue 25/11/08
4620 | 380046 | Deleted - WLAN Offline Charging | CH8 | 2 | Rel-8 | S5 | 2008-01-07 08:00 | 2008-12-11 17:00 | 100% | SP-070750 | - | Alcatel-Lucent | maryse.gardella@alcatel-lucent.com | SP#42 stopped | 32.252, 32.298, 32.299 | 38 | 21 | SP-42 | PCG-22 | Fri 17/06/05 | Tue 24/03/09
4621 | 380024 | Conferencing enhancements for Mp interface | eMp | 1 | Rel-8 | C4 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-080725 | - | Huawei | Chencheng@huawei.com | CP#42 completed | - |  | 21 |  |  | Mon 19/11/07 | Mon 02/08/10
4622 | 380025 | Stage 2 for eMp | eMp | 2 | Rel-8 | C4 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-080725 | - | Huawei | Chencheng@huawei.com | CP#42 completed | 23.333 | 38 | 21 |  |  | Mon 19/11/07 | Mon 02/08/10
4623 | 380026 | Stage 3 for eMp | eMp | 2 | Rel-8 | C4 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-080725 | - | Huawei | Chencheng@huawei.com | CP#42 completed | 29.333 | 38 | 21 |  |  | Mon 19/11/07 | Mon 02/08/10
4624 | 320014 | Contact Manager for 3GPP UICC applications | eUPHBOOK | 1 | Rel-8 | C6 | 2006-06-22 08:00 | 2008-12-05 17:00 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#42 completed. CP#40: WID updated CP-070622=>CP-080382. aka Enhanced USIM phonebook | - | 32 |  |  |  | Tue 24/01/06 | Tue 24/03/09
4625 | 320015 | Requirements for Contact Manager | eUPHBOOK-St1 | 2 | Rel-8 | C6 | 2006-06-22 08:00 | 2007-12-21 17:00 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#38 completed | 21.111 | 32 |  |  |  | Tue 24/01/06 | Thu 29/05/08
4626 | 350046 | External interface for eUPHBOOK | eUPHBOOK-Ext_Spec | 2 | Rel-8 | C6 | 2007-05-07 08:00 | 2008-03-07 17:00 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#39 completed | new 31.220 | 35 |  |  |  | Tue 24/01/06 | Thu 29/05/08
4627 | 370004 | Internal interface for eUPHBOOK | eUPHBOOK-Int_Spec | 2 | Rel-8 | C6 | 2007-05-07 08:00 | 2008-12-05 17:00 | 100% | CP-080382 | - | Gemalto | Jacques.seif@gemalto.com | CP#42 completed | new 31.221 | 37 |  |  |  | Tue 24/01/06 | Tue 25/11/08
4628 | 320016 | Deleted - Implementation of eUPHBOOK | eUPHBOOK-St23 | 2 | Rel-8 | C6 | 2007-06-21 17:00 | 2007-06-21 17:00 | 100% | CP-060355 | - | Giesecke & Devrient | Claus Dietze | SP#33 stopped | 31.102 | 32 |  | SP-33 |  | Tue 24/01/06 | Tue 24/03/09
4629 | 20068 | Rel-8 LTE – 3G Long Term Evolution - Evolved Packet System RAN part | LTE | 1 | Rel-8 | RP,S5 | 2006-09-25 08:00 | 2009-03-12 17:00 | 100% | RP-080747 | RP-080741 | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | RP#43 completed. Role model for SAE/LTE system wide project management by SA2 in SP-060166 | LTE 36.300, 36.938 |  |  |  |  | Wed 21/06/06 | Fri 18/12/09
4630 | 330018 | LTE – Physical Layer | LTE-Phys | 2 | Rel-8 | R1 | 2006-09-25 08:00 | 2008-03-07 17:00 | 100% | RP-080747 | RP-080741 | NTT DoCoMo | Sadayuki Abeta | RP#39 completed | 36.201, 36.211, 36.212, 36.213, 36.214, 25.215, 25.225 |  |  |  |  | Tue 21/03/06 | Fri 18/12/09
4631 | 330019 | LTE – Radio Interface Layer 2 and 3 Protocol Aspect | LTE-L23 | 2 | Rel-8 | R2 | 2006-09-25 08:00 | 2008-12-05 17:00 | 100% | RP-080747 | RP-080741 | Nokia Siemens Networks | benoist.sebire@nokia.com | RP#42 completed | 36.302, 36.304, 36.306, 36.314, 36.321, 36.322, 36.323, 36.331, 25.302, 25.304, 25.331 |  |  |  |  | Tue 21/03/06 | Fri 18/12/09
4632 | 330020 | LTE – eUTRAN Interfaces | LTE-interfaces | 2 | Rel-8 | R3 | 2006-09-25 08:00 | 2008-12-05 17:00 | 100% | RP-080747 | RP-080741 | Ericsson | Martin Israelsson | RP#42 completed | 36.401, 36.410, 36.411, 36.412, 36.413, 36.414, 36.420, 36.421, 36.422, 36.423, 36.424, 25.413 |  |  |  |  | Tue 21/03/06 | Fri 18/12/09
4633 | 330021 | LTE – Evolved UTRA and UTRAN RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing | LTE-RF | 2 | Rel-8 | R4 | 2006-09-25 08:00 | 2008-12-05 17:00 | 100% | RP-080747 | RP-080741 | Nokia Siemens Networks | Tuomo Saynajakangas | RP#42 completed. RP#47 abandoned draft 36.801, 36.803, 36.804 | 36.101, 36.104, 36.113, 36.124, 36.133, 36.141, 36.942, 25.123, 25.133 |  |  |  |  | Tue 21/03/06 | Tue 16/03/10
4634 | 370046 | LTE – FDD repeaters | LTE-Repeaters | 2 | Rel-8 | R4 | 2007-09-14 08:00 | 2009-03-06 17:00 | 100% | RP-070749 | RP-090037 | Powerwave Technologies, Andrew Wireless | ralf.michanikl@andrew.com, Alf.Ahlstrom@pwav.com | RP#43 completed. RP#47 create Rel-9 TR 36.956 (see R4-100386, RP-100320_RAN4 Report) | 36.106, 36.143, 25.113 | 37 |  |  |  | Mon 01/10/07 | Tue 16/03/10
4635 | 390001 | E-UTRAN Data Definitions | E-UTRAN-OAM | 2 | Rel-8 | S5 | 2007-09-17 08:00 | 2009-03-12 17:00 | 100% | - | - | - | - | SP#43 completed | - | 39 | 21 |  |  | Fri 17/06/05 | Mon 03/03/08
4636 | 370001 | Subscriber and Equipment Trace for E-UTRAN and EPC | E-UTRAN-OAM | 3 | Rel-8 | S5 | 2007-09-17 08:00 | 2009-03-12 17:00 | 100% | SP-070617 | - | Ericsson | robert.petersen@ericsson.com | SP#43 completed | 32.421, 2.422, 32.423, 2.441, 32.442, 32.443, 32.445 | 37 |  |  |  | Sat 15/09/07 | Thu 29/07/10
4637 | 380036 | E-UTRAN Network Resource Model (NRM) Integration Reference Point (IRP) | E-UTRAN-OAM | 3 | Rel-8 | S5 | 2008-01-07 08:00 | 2009-03-12 17:00 | 100% | SP-070738 | - | Ericsson | ELMDAHL, Per | SP#43 completed | new (32.761, 32.762, 32.763, 32.765) | 38 | 21 |  |  | Fri 17/06/05 | Thu 29/07/10
4638 | 390002 | Performance measurements for E-UTRAN | E-UTRAN-OAM | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2009-03-12 17:00 | 100% | SP-080062 | - | Motorola, Huawei | Yizhi Yao (yzyao@motorola.com) | SP#43 completed | new 32.425 | 39 | 21 |  |  | Fri 17/06/05 | Thu 29/07/10
4639 | 390003 | Key Performance Indicators (KPIs) for E-UTRAN | E-UTRAN-OAM | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2009-03-12 17:00 | 100% | SP-080063 | - | Ericsson | ulf.hubinette@ericsson.com | SP#43 completed | new (32.450, 32.451) | 39 | 21 |  |  | Fri 17/06/05 | Mon 23/02/09
4640 | 390004 | Self-Organizing Networks (SON) | LTE_SON-OAM | 2 | Rel-8 | S5 | 2008-02-22 08:00 | 2008-12-11 17:00 | 100% | SP-080275 | - | Vodafone | GOMPAKIS, Panagiotis | SP#42 completed (WT UID_390007 moved to Rel-9) | - | 39 | 21 |  |  | Fri 17/06/05 | Mon 01/12/08
4641 | 390104 | SON Concepts and requirements | LTE_SON-OAM | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2008-12-11 17:00 | 100% | SP-080275 | - | Vodafone | GOMPAKIS, Panagiotis | SP#42 completed | new 32.500 | 39 | 21 |  |  | Fri 17/06/05 | Tue 25/11/08
4642 | 390005 | Self-Establishment of eNBs, including automated Software Management | LTE_SON-OAM | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2008-12-11 17:00 | 100% | SP-080849 | - | Nokia Siemens Networks | SUERBAUM, Clemens | SP#42 completed | new (32.501, 32.502, 32.503, 32.531, 32.532, 32.533) | 39 | 21 |  |  | Fri 17/06/05 | Mon 22/03/10
4643 | 390006 | SON Automatic Neighbour Relations (ANR) List Management | LTE_SON-OAM | 3 | Rel-8 | S5 | 2008-02-22 08:00 | 2008-12-11 17:00 | 100% | SP-080066 | - | Ericsson | edwin.tse@ericsson.com | SP#42 completed | 32.761, 32.762, 32.763, 32.765, new 32.511 | 39 | 21 |  |  | Fri 17/06/05 | Mon 01/12/08
4644 | 25029 | Rel-8 LTE – Terminal Conformance Test Specification | LTE-UEConTest | 1 | Rel-8 | R5 | 2007-06-01 08:00 | 2009-12-04 17:00 | 100% | - | - | - | - | Testing for Feature UID_20068 (LTE) | - |  |  |  |  | Tue 21/03/06 | Sun 01/06/08
4645 | 25041 | 3G LTE – Terminal Protocol Conformance Test Specifications | LTE-UEConTest_SIG | 2 | Rel-8 | R5 | 2007-06-01 08:00 | 2009-12-04 17:00 | 100% | RP-080647 | RP-091060 | NEC, Motorola | david.lecompte@nectech.fr, Jacob.John@motorola.com | RP#46 completed | 36.521-1, 36.521-2, 36.508, 36.509, 36.523-1, 36.523-2, 36.523-3 |  |  |  |  | Tue 21/03/06 | Fri 27/11/09
4646 | 25042 | LTE – Terminal Radio Transmission and Reception Conformance Test Specifications | LTE-UEConTest_RF | 2 | Rel-8 | R5 | 2007-06-01 08:00 | 2009-12-04 17:00 | 100% | RP-080601 | RP-091059 | Agilent | andrea_leonardi@agilent.com | RP#46 completed. RP#50 TR 36.903 v100 for Approval | 36.521-1, 36.521-2, 36.521-3, new TR 36.903 |  |  |  |  | Tue 02/06/09 | Fri 10/12/10
4647 | 350040 | Rel-8 Improvements of the Radio Interface | RInImp8 | 1 | Rel-8 | RP | 2007-03-05 08:00 | 2009-03-06 17:00 | 100% | - | - | - | - | - | - | 35 |  |  |  | Tue 04/01/05 | Tue 24/03/09
4648 | 350034 | UMTS 1500 MHz | RInImp8-UMTS1500 | 2 | Rel-8 | R4 | 2007-03-05 08:00 | 2007-09-14 17:00 | 100% | RP-070078 | RP-070526 | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | RP#37 completed | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 | 35 |  |  |  | Mon 27/09/04 | Thu 09/07/09
4649 | 350035 | UMTS 700 MHz FDD | RInImp8-UMTS700 | 2 | Rel-8 | R4 | 2007-03-05 08:00 | 2008-05-30 17:00 | 100% | RP-070127 | RP-080260 | Nokia | Tuomo Saynajakangas | RP#40 completed | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 | 35 |  |  |  | Mon 27/09/04 | Tue 16/03/10
4650 | 410018 | UMTS 1880 MHz TDD | RInImp9-UMTS1880TDD | 2 | Rel-8 | R4 | 2008-09-12 08:00 | 2009-03-06 17:00 | 100% | RP-080757 | RP-090044 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#43 completed | 25.102, 25.105, 25.113, 25.123, 25.142, 34.124, 25.307 | 41 | 21 |  |  | Thu 11/09/08 | Tue 10/03/09
4651 | 380074 | UMTS 2300 MHz TDD LCR | RInImp8-UMTS2300TDD | 2 | Rel-8 | R4 | 2007-12-17 08:00 | 2008-09-12 17:00 | 100% | RP-071016 | RP-080517 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#41 completed. RP#47 abandoned draft 25.828 | 25.102, 25.105, 25.113, 25.123, 25.142, 34.124, 25.306, 25.331, 34.122 | 38 | 21 |  |  | Mon 17/12/07 | Mon 02/08/10
4652 | 350037 | Further Improved Minimum Performance Requirements for HSDPA UE (FDD) - Two-Branch Interference Cancellation | RInImp8-2BIC | 2 | Rel-8 | R4 | 2007-03-05 08:00 | 2008-03-07 17:00 | 100% | RP-070254 | RP-080041 | AT&T | Marc Grant | RP#39 completed | 25.101 | 35 |  |  |  | Thu 15/12/05 | Mon 02/08/10
4653 | 370032 | CS Voice Service over HSPA | RInImp8-CsHspa | 2 | Rel-8 | R2 | 2007-07-19 08:00 | 2008-03-07 17:00 | 100% | RP-070765 | RP-080042 | Nokia Siemens Networks | woonhee.hwang@nsn.com | RP#39 completed | 25.323, 25.331, 25.322 | 37 |  |  |  | Tue 02/10/07 | Mon 02/08/10
4654 | 370033 | Performance requirements for 15 code reception with 16QAM/QPSK (FDD) | RInImp8-Hsdpa15codes | 2 | Rel-8 | R4 | 2007-06-11 15:00 | 2008-03-07 17:00 | 100% | RP-070745 | RP-080043 | Vodafone | tim.frost@vodafone.com | RP#39 completed | 25.101 | 37 |  |  |  | Tue 02/10/07 | Mon 02/08/10
4655 | 350036 | Deleted - UMTS 2300 MHz FDD/TDD | RInImp8-UMTS2300 | 2 | Rel-8 | R4 | 2007-03-05 08:00 | 2008-09-12 17:00 | 100% | RP-070128 | RP-080515 | AT&T | Marc Grant | RP#41 stopped | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 | 35 |  | RP-41 | PCG-21 | Mon 27/09/04 | Mon 02/08/10
4656 | 25125 | Rel-8 Improvements of the Radio Interface - UE Conformance Testing | - | 1 | Rel-8 | R5 | 2007-06-01 08:00 | 2008-12-05 17:00 | 100% | - | - | - | - | 05/08: Linked to Feature UID_20028 (RInImp) | - |  |  |  |  | Fri 22/09/06 | Sun 01/06/08
4657 | 25050 | Conformance Test Aspects – CS Voice Service over HSPA | RInImp8-CsHspa_UEConTest | 2 | Rel-8 | R5 | 2007-06-01 08:00 | 2008-09-12 17:00 | 100% | RP-080160 | RP-080542 | Huawei | baoyi@huawei.com | RP#41 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Tue 11/03/08 | Tue 09/09/08
4658 | 400055 | Conformance Test Aspects – Performance requirements for 15 code reception with 16QAM/QPSK (FDD) | RInImp8-UEConTest_Hsdpa15codes | 2 | Rel-8 | R5 | 2008-03-07 17:00 | 2008-12-05 17:00 | 100% | RP-080311 | RP-080818 | Ericsson | Mikael.Ziren@Ericsson.com | RP#42 completed | 34.121-1, 34.121-2 | 40 | 21 |  |  | Tue 03/06/08 | Tue 09/12/08
4659 | 370035 | Rel-8 RAN improvements | - | 1 | Rel-8 | RP | 2007-06-04 08:00 | 2009-05-29 17:00 | 100% | - | - | - | - | - | - | 36 |  |  |  | Mon 01/10/07 | Tue 09/02/10
4660 | 360013 | Combination of 64QAM and MIMO for HSDPA (FDD) | RANimp-64QamMimoHsdpa | 2 | Rel-8 | R1 | 2007-06-04 08:00 | 2008-09-12 17:00 | 100% | RP-070500 | RP-080518 | Ericsson | Johan.Bergman@ericsson.com | RP#41 completed | 25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141 | 36 |  |  |  | Thu 21/06/07 | Tue 03/08/10
4661 | 370036 | Improved L2 for uplink | RANimp-UplinkL2dataRates | 2 | Rel-8 | R2 | 2007-09-14 08:00 | 2008-05-30 17:00 | 100% | RP-070717 | RP-080265 | Ericsson | Janne.Peisa@ericsson.com | RP#40 completed. Linked to UID_370037 Enhanced Uplink for CELL_FACH State in FDD | 25.319, 25.301, 25.306, 25.321, 25.331, 25.433, 25.435, 25.423, 25.425, 25.427 | 37 |  |  |  | Tue 02/10/07 | Tue 03/08/10
4662 | 370037 | Enhanced Uplink for CELL_FACH State in FDD | RANimp-UplinkEnhState | 2 | Rel-8 | R2 | 2007-09-14 08:00 | 2008-12-05 17:00 | 100% | RP-070677 | RP-080804 | Nokia Siemens Networks | markus.wimmer@nsn.com | RP#42 completed. Linked to UID_370036 Improved L2 for uplink | 25.309, 25.211, 25.214, 25.321, 25.331, 25.423, 25.433 | 37 |  |  |  | Tue 02/10/07 | Tue 03/08/10
4663 | 370038 | Enhanced UE Discontinuous Reception (DRX) for FDD | RANimp-DRX | 2 | Rel-8 | R2 | 2007-09-14 08:00 | 2008-09-12 17:00 | 100% | RP-070679 | RP-080520 | Nokia | luis.barreto@nokia.com | RP#41 completed. Continuation of Rel-7 work item "Continuous connectivity for packet data users" UID_20046. | 25.306, 25.308, 25.321, 25.331, 25.423 | 37 |  |  |  | Mon 01/10/07 | Tue 03/08/10
4664 | 370039 | Enhancements for Serving Radio Network Subsystem (SRNS) Relocation Procedure | RANimp-SrnsReloc | 2 | Rel-8 | R3 | 2007-09-14 08:00 | 2008-09-12 17:00 | 100% | RP-070759 | RP-080521 | Nokia Siemens Networks | masatoshi.nakamata@nsn.com | RP#41 completed. Linked to UID_370040 Enhancements for FDD HSPA Evolution | 25.306, 25.308, 25.321, 25.331, 25.423, 25.433, 25.214, 25.133 | 37 |  |  |  | Mon 01/10/07 | Tue 03/08/10
4665 | 370040 | Enhancements for FDD HSPA Evolution | RANimp-HSPAEvo | 2 | Rel-8 | R3,R2 | 2007-09-14 08:00 | 2008-12-05 17:00 | 100% | RP-080830 | RP-080805 | Nokia Siemens Networks | masatoshi.nakamata@nsn.com | RP#42 completed. Triggered by Rel-7 Study on Scope of future FDD HSPA Evolution (UID_20065) TR 25.999 | 25.401, 25.413, 25.420, 25.423, 25.427, 25.433, 25.446, 25.301, 25.346 | 37 |  |  |  | Mon 01/10/07 | Tue 03/08/10
4666 | 380075 | 64QAM for 1.28 Mcps TDD HSDPA | RANimp-64Qam1.28TDD | 2 | Rel-8 | R1 | 2007-12-04 08:00 | 2008-12-05 17:00 | 100% | RP-070924 | RP-080806 | ZTE | zfmail@zte.com.cn | RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | 25.102, 25.105, 25.123, 25.142, 25.201, 25.221, 25.222, 25.223, 25.224, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433 | 38 | 21 |  |  | Mon 17/12/07 | Tue 03/08/10
4667 | 380076 | Enhanced CELL_FACH state in 1.28 Mcps TDD | RANimp-EnhState1.28TDD | 2 | Rel-8 | R2 | 2007-12-04 08:00 | 2008-12-05 17:00 | 100% | RP-071038 | RP-080807 | ZTE | zhang.yincheng@zte.com.cn | RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | 25.123, 25.221, 25.222, 25.224, 25.301, 25.302, 25.304, 25.306, 25.308, 25.319, 25.321, 25.331, 25.401, 25.423, 25.425, 25.433, 25.435 | 38 | 21 |  |  | Mon 17/12/07 | Tue 03/08/10
4668 | 390028 | Continuous Connectivity for packet data users for 1.28 Mcps TDD | RANimp-LCRCPC | 2 | Rel-8 | R1 | 2008-03-07 08:00 | 2009-05-29 17:00 | 100% | RP-080085 | RP-090394 | TD Tech | chenying@td-tech.com | RP#44 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | 25.929, 25.308, 25.319 | 39 | 21 |  |  | Mon 17/03/08 | Tue 03/08/10
4669 | 390029 | HSPA VoIP to WCDMA/GSM CS continuity | RANimp-HSPAVoIP | 2 | Rel-8 | R2 | 2008-03-07 08:00 | 2009-03-06 17:00 | 100% | RP-080749 | RP-090050 | Nokia | Simone.Provvedi@nokia.com | RP#43 completed | 25.331, 25.413 | 39 | 21 |  |  | Mon 17/03/08 | Tue 03/08/10
4670 | 390030 | HS-DSCH Serving Cell Change Enhancements | RANimp-HSDSCH | 2 | Rel-8 | R2 | 2008-03-07 08:00 | 2008-12-05 17:00 | 100% | RP-080227 | RP-080811 | Ericsson | henrik.enbuske@ericsson.com | RP#42 completed | 25.101, 25.104, 25.133, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433 | 39 | 21 |  |  | Mon 17/03/08 | Tue 03/08/10
4671 | 400050 | MIMO for 1.28 Mcps TDD. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824 | RANimp-MIMOLCR | 2 | Rel-8 | R1,R4 | 2008-01-24 11:12 | 2009-05-29 17:00 | 100% | RP-080485 | RP-090313 | CATT | wangke@datangmobile.cn | RP#43 completed | 25.201, 25.221, 25.222, 25.223, 25.224, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433, 25.102, 25.105, 25.142 | 40 | 21 |  |  | Mon 17/03/08 | Tue 03/08/10
4672 | 400052 | Dual-Cell HSDPA operation on adjacent carriers | RANimp-DCHSDPA | 2 | Rel-8 | R1,R4 | 2008-11-17 08:00 | 2009-05-29 17:00 | 100% | RP-080490 | RP-080814 | Ericsson | johan.bergman@ericsson.com | RP#42 completed. Triggered by UID_390032 Study on Dual-Cell HSDPA (withdrawn TR 25.825 v100). | 25.101, 25.104, 25.133, 25.141, 25.211, 25.212, 25.213, 25.214, 25.215, 25.306, 25.308, 25.321, 25.331, 25.423, 25.433 | 40 | 21 |  |  | Mon 17/03/08 | Tue 03/08/10
4673 | 25126 | Rel-8 RAN improvements - UE Conformance Testing | - | 1 | Rel-8 | R5 | 2008-05-30 08:00 | 2010-09-17 17:00 | 100% | - | - | - | - | Linked to Feature UID_20029 (RANimp) | - |  |  |  |  | Fri 22/09/06 | Sun 01/06/08
4674 | 410020 | Conformance Test Aspects – Combination of 64QAM and MIMO for HSDPA (FDD) | RANimp-UEConTest_64QamMimoHsdpa | 2 | Rel-8 | R5 | 2008-09-12 08:00 | 2009-12-04 17:00 | 100% | RP-080759 | RP-091058 | Ericsson | leif.mattisson@ericsson.com | RP#46 completed. Testing for UID_360013 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2 | 41 | 21 |  |  | Tue 03/06/08 | Tue 03/08/10
4675 | 400056 | Conformance Test Aspects – Improved L2 for uplink | RANimp-UEConTest_UplinkL2dataRates | 2 | Rel-8 | R5 | 2008-05-30 08:00 | 2009-09-18 17:00 | 100% | RP-080606 | RP-090712 | Ericsson | leif.mattisson@ericsson.com | RP#45 completed. Testing for UID_370036 | 34.108, 34.123-1, 34.123-2, 34.123-3 | 40 | 21 |  |  | Tue 03/06/08 | Tue 03/08/10
4676 | 440010 | Conformance Test Aspects – 1.28 Mcps TDD Improved L2 support for high data rates | RANimp-UEConTest_ImprovedL2LCRTDD | 2 | Rel-8 | R5 | 2009-05-29 08:00 | 2010-09-17 17:00 | 100% | RP-090491 | RP-100737 | CATT | Xiaozhong Chen (chenxiaozhong@datangmobile.cn) | RP#49 completed. Testing for Rel-7 UID_340039 Improved L2 support for high data rates and Rel-8 UID_370036 Improved L2 for uplink | 34.108, 34.123-1, 34.123-2, 34.123-3 | 44 | 23 |  |  | Wed 20/05/09 | Thu 09/09/10
4677 | 400057 | Conformance Test Aspects – 64QAM for 1.28 Mcps TDD HSDPA | RANimp-UEConTest_64Qam1.28TDD | 2 | Rel-8 | R5 | 2008-05-30 08:00 | 2009-05-29 17:00 | 100% | RP-080334 | RP-090415 | ZTE | ma.zijiang@zte.com.cn | RP#44 completed. Testing for UID_380075 | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 | 40 | 21 |  |  | Tue 03/06/08 | Tue 03/08/10
4678 | 420015 | Conformance Test Aspects – Dual-Cell HSDPA operation on adjacent carriers | RANimp-UEConTest_DCHSDPA | 2 | Rel-8 | R5 | 2008-12-05 08:00 | 2010-06-04 17:00 | 100% | RP-080996 | RP-100479 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#48 completed. Testing for UID_400052 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 42 | 22 |  |  | Thu 04/12/08 | Tue 03/08/10
4679 | 430024 | Conformance Test Aspects – Enhanced Uplink for CELL_FACH State in FDD | RANimp-UEConTest_EnhancedRACHCellFACHState | 2 | Rel-8 | R5 | 2009-03-06 08:00 | 2010-06-04 17:00 | 100% | RP-090152 | RP-100483 | Nokia | jarkko.hellsten@nokia.com | RP#48 completed. Testing for UID_370037 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 43 | 22 |  |  | Fri 27/02/09 | Tue 03/08/10
4680 | 430028 | Conformance Test Aspects – Receiver Type3i | RANimp-UEConTest_ReceiverType3i | 2 | Rel-8 | R5 | 2009-03-06 08:00 | 2009-12-04 17:00 | 100% | RP-090010 | RP-091066 | Qualcomm | Ashok Kumar Narayanaswamy (anarayan@qualcomm.com) | RP#46 completed. Testing for Receiver Type3i in 25.101 UE radio Tx and Rx FDD | 34.108, 34.121-1, 34.121-2 | 43 | 22 |  |  | Tue 10/03/09 | Tue 03/08/10
4681 | 440009 | Conformance Test Aspects – Enhanced CELL_FACH State in LCR TDD | RANimp-UEConTest_EnhancedCellFACHStateLCRTDD | 2 | Rel-8 | R5 | 2009-05-30 08:00 | 2010-09-17 17:00 | 100% | RP-090490 | RP-100735 | CATT | Xiaozhong Chen (chenxiaozhong@datangmobile.cn) | RP#49 completed. Testing for UID_380076 | 34.108, 34.123-1, 34.123-2, 34.123-3 | 44 | 23 |  |  | Wed 20/05/09 | Thu 09/09/10
4682 | 450024 | Conformance Test Aspects – Continuous Connectivity for packet data users for 1.28 Mcps TDD | RANimp-UEConTest_CPCLCRTDD | 2 | Rel-8 | R5 | 2009-09-18 08:00 | 2010-09-17 17:00 | 100% | RP-090751 | RP-100739 | ZTE | huang.he4@zte.com.cn | RP#49 completed. Testing for UID_390028 | 34.108, 34.123-1, 34.123-2, 34.123-3 | 45 | 23 |  |  | Tue 15/09/09 | Thu 09/09/10
4683 | 450025 | Conformance Test Aspects – MIMO for 1.28 Mcps TDD | RANimp-UEConTest_MIMOLCRTDD | 2 | Rel-8 | R5 | 2009-09-18 08:00 | 2010-06-04 17:00 | 100% | RP-100120 | RP-100660 | ZTE | huang.chun2@zte.com.cn | PR#48 completed. Testing for UID_400050 | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 | 45 | 23 |  |  | Tue 15/09/09 | Tue 03/08/10
4684 | 450026 | Conformance Test Aspects – HS-DSCH Serving Cell Change Enhancements | HSDSCH_UEConTest | 2 | Rel-8 | R5 | 2009-09-18 08:00 | 2010-03-19 17:00 | 100% | RP-090756 | RP-100077 | Qualcomm | Shubhang Vora (svora@qualcomm.com) | RP#47 completed. Testing for UID_390030 | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 45 | 23 |  |  | Tue 15/09/09 | Tue 03/08/10
4685 | 360008 | 3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast | MBSFN-DOB | 1 | Rel-8 | R1 | 2007-06-04 08:00 | 2008-12-05 17:00 | 100% | RP-081124 | RP-080218 | Ericsson | Lars.Lindbom@ericsson.com | RP#42 completed. WID updated RP-070493=>RP-081124 (changed WI title "MBSFN Downlink Optimized Broadcast (DOB) 3.84 Mcps TDD" => "3.84Mcps TDD MBSFN Integrated Mobile Broadcast"). | 25.102, 25.105, 25.123, 25.201, 25.221, 25.222, 25.223, 25.224, 25.304, 25.306, 25.331, 25.346, 25.402, 25.433 | 36 |  |  |  | Thu 21/06/07 | Tue 09/12/08
4686 | 440008 | Conformance Test Aspects – 3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast | MBSFN_IMB_UEConTest | 1 | Rel-8 | R5 | 2009-05-30 08:00 | 2010-03-19 17:00 | 100% | RP-090583 | RP-100070 | IPwireless | Phil Young (pyoung@ipwireless.com) | RP#47 completed. Testing for Rel-8 MBSFN-DOB UID_360008 | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 | 44 | 23 |  |  | Thu 21/05/09 | Tue 16/03/10
4687 | 50583 | GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 1 | Rel-8 | GP,G1,C1,G3new | 2006-09-08 08:00 | 2011-11-25 17:00 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | GP#41 completed. GP#52 completed MS conformance testing | 44.018, 44.060, 45.002, 45.008, 45.010, 48.008, 48.018, 51.010 |  |  |  |  | Wed 13/09/06 | Fri 25/11/11
4688 | 51583 | G1 part of GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 2 | Rel-8 | G1 | 2006-09-08 08:00 | 2009-02-20 17:00 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | GP#41 completed | 43.055, 43.129, 43.246, 45.002, 45.008, 45.010 |  |  |  |  | Wed 13/09/06 | Thu 09/09/10
4689 | 52583 | G2 part of GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 2 | Rel-8 | G2 | 2006-09-08 08:00 | 2009-02-20 17:00 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | GP#41 completed | 44.018, 44.060, 48.008, 48.018 |  |  |  |  | Wed 13/09/06 | Thu 09/09/10
4690 | 53583 | CT1 part of GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 2 | Rel-8 | C1 | 2006-09-08 08:00 | 2009-02-20 17:00 | 100% | GP-061757 | - | Nokia, Nokia Siemens Networks | sergio.parolari@nsn.com, vlora.rexhepi@nokia.com | - | 24.008 |  |  |  |  | Wed 13/09/06 | Thu 09/09/10
4691 | 54583 | Testing for GERAN support for GERAN - 3G Long Term Evolution interworking | GELTE | 2 | Rel-8 | G3new | 2006-09-08 08:00 | 2011-11-25 17:00 | 100% | GP-061757 | - | Renesas Mobile | deepa.kamath@renesasmobile.com | GP#52 completed | 51.010 |  |  |  |  | Wed 13/09/06 | Fri 25/11/11
4692 | 55586 | U-TDOA Enhancement | GUTEN | 1 | Rel-8 | GP | 2007-05-18 08:00 | 2007-11-16 17:00 | 100% | GP-070865 | - | TruePosition | Terry Brooks (terri.brooks@trueposition.com) | GP#36 completed U-TDOA (Uplink Time Difference of Arrival) | 43.059, 45.008, 48.071 |  |  |  |  | Mon 21/05/07 | Sat 30/05/09
4693 | 50587 | GAN Enhancements | GANENH | 1 | Rel-8 | GP | 2007-05-15 15:24 | 2009-09-04 17:00 | 100% | GP-071484 | - | T-Mobile | mohammed.versi@t-mobile.com | GP#37 completed. GP#43 completed Testing | - |  |  |  |  | Thu 06/09/07 | Mon 28/09/09
4694 | 50588 | Update to GAN specifications | GANENH-SPEC | 2 | Rel-8 | GP | 2007-08-31 08:00 | 2008-02-22 17:00 | 100% | GP-071560 | - | T-Mobile | mohammed.versi@t-mobile.com | GP#37 completed | 43.318, 44.318 |  |  |  |  | Thu 06/09/07 | Mon 19/05/08
4695 | 53089 | Update TS 51.010 Mobile Station (MS) Conformance Specification for GAN Enhancements | GANENH-MStest | 2 | Rel-8 | G3new | 2007-05-15 15:24 | 2009-09-04 17:00 | 100% | GP-071563 | - | T-Mobile | mohammed.versi@t-mobile.com | GP#43 completed | 51.010 |  |  |  |  | Thu 06/09/07 | Mon 07/09/09
4696 | 50591 | AoIP (A-interface over IP) | AoIP | 1 | Rel-8 | GP,S4,C4,C1,C3 | 2000-01-03 08:00 | 2008-12-11 17:00 | 100% | GP-081361 | - | China Mobile, Ericsson | wangshuaiyu@chinamobile.com, paul.schliwa-bertling@ericsson.com | GP#40/TSG#42 completed . Triggered by TR 43.903 Study on A-interface over IP (AINTIP) UID_50589. | - |  | 21 |  |  | Tue 26/02/08 | Wed 03/12/08
4697 | 400041 | GERAN aspects of AoIP | AoIP | 2 | Rel-8 | GP | 2000-01-03 08:00 | 2008-11-21 17:00 | 100% | GP-081362 | - | China Mobile, Ericsson | wangshuaiyu@chinamobile.com, paul.schliwa-bertling@ericsson.com | GP#40 completed. GP#39 updated WID GP-080901=>GP-081362. | 48.001, 48.002, 48.008, 48.020, 49.008, 48.103 | 40 | 21 |  |  | Wed 28/05/08 | Wed 03/12/08
4698 | 400042 | Media Requirements for CS over IP based User Plane | AoIP-CSoIP | 2 | Rel-8 | S4 | 2007-12-05 08:00 | 2008-12-11 17:00 | 100% | SP-080444 | - | China Mobile, Ericsson | Karl.Hellwig@Ericsson.com | SP#42 completed | 26.102, 26.103, 26.202 | 40 | 21 |  |  | Sun 09/12/07 | Fri 21/11/08
4699 | 400024 | Core Network Impacts for A-Interface User Plane over IP | AoIP-CN | 2 | Rel-8 | C4,C1,C3 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | - | 40 | 21 |  |  | Wed 19/09/07 | Wed 11/01/12
4700 | 400324 | CT4 part of Core Network Impacts for A-Interface User Plane over IP | AoIP-CN | 3 | Rel-8 | C4 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | 23.205, 23.153, 23.231, 29.232 | 40 | 21 |  |  | Wed 19/09/07 | Wed 11/01/12
4701 | 400124 | CT1 part of Core Network Impacts for A-Interface User Plane over IP | AoIP-CN | 3 | Rel-8 | C1 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | 23.009 | 40 | 21 |  |  | Wed 19/09/07 | Wed 11/01/12
4702 | 400224 | CT3 part of Core Network Impacts for A-Interface User Plane over IP | AoIP-CN | 3 | Rel-8 | C3 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | CP-080722 | - | Ericsson | philip.hodges@ericsson.com | CP#42 completed. Updated WID CP-080278=>CP-080722 | 29.007 | 40 | 21 |  |  | Wed 19/09/07 | Wed 11/01/12
4703 | 51147 | New multicarrier BTS class | MCBTS | 1 | Rel-8 | G1 | 2007-08-31 08:00 | 2008-08-29 17:00 | 100% | GP-071542 | - | Alcatel-Lucent | thomas.bitzer@alcatel-lucent.de | GP#39 completed | 45.005, 45.050, 51.021 |  |  |  |  | Thu 06/09/07 | Sun 31/08/08
4704 | 38001 | Support for Additional Navigation Satellite Systems (ANSS) for LCS | ANSS | 1 | Rel-8 | S1,G2,R2 | 2008-05-16 08:00 | 2008-12-11 17:00 | 100% | GP-081784 | - | Qualcomm | Mungal Dhanda | GP#40 completed | - |  |  |  |  | Mon 19/05/08 | Thu 19/02/09
4705 | 420038 | Stage 1 for ANSS for LCS | ANSS | 2 | Rel-8 | S1 | 2008-12-11 08:00 | 2008-12-11 17:00 | 100% | - | - | - | - | SP#42 completed by 22.071 CR0077 | 22.071 | 42 | 22 |  |  | Mon 08/12/08 | Tue 09/02/10
4706 | 38101 | GERAN2 part of Support for Additional Navigation Satellite Systems (ANSS) for LCS | ANSS | 2 | Rel-8 | G2 | 2008-05-16 08:00 | 2008-11-21 17:00 | 100% | GP-081784 | - | Qualcomm | Mungal Dhanda | GP#40 completed | 43.059, 44.031, 49.031, 44.071, 48.031, 51.010 |  |  |  |  | Mon 19/05/08 | Wed 03/12/08
4707 | 400051 | RAN2 part of Support for Additional Navigation Satellite Systems (ANSS) for LCS | RANimp-ANSS | 2 | Rel-8 | R2 | 2008-05-30 08:00 | 2008-12-05 17:00 | 100% | RP-080346 | RP-080813 | Qualcomm | Etienne Chaponniere (echaponn@qualcomm.com) | RP#42 WI closed at 95%. Considers Rel-9 performance requirements | 25.305, 25.306, 25.331, 25.413, 25.423, 25.433, 25.453 | 40 | 21 |  |  | Mon 17/03/08 | Thu 04/12/08
4708 | 51149 | Conformance testing for the Latency Reductions feature | CTLATRED | 1 | Rel-8 | G1,G3new | 2008-02-22 08:00 | 2010-03-05 17:00 | 100% | GP-080367 | - | Ericsson | mats.y.samuelsson@ericsson.com, hakan.e.grunditz@ericsson.com | GP#45 completed | - |  | 21 |  |  | Tue 26/02/08 | Fri 05/03/10
4709 | 53090 | MS conformance testing for the Latency Reductions feature | CTLATRED-MStest | 2 | Rel-8 | G3new | 2008-02-22 08:00 | 2010-03-05 17:00 | 100% | GP-080368 | - | Ericsson | hakan.e.grunditz@ericsson.com | GP#45 completed | 51.010 |  | 21 |  |  | Tue 26/02/08 | Fri 05/03/10
4710 | 51150 | BTS conformance testing for the Latency Reductions feature | CTLATRED-BTStest | 2 | Rel-8 | G1 | 2008-02-22 08:00 | 2009-02-20 17:00 | 100% | GP-080369 | - | Ericsson | mats.y.samuelsson@ericsson.com | GP#41 completed | 51.021 |  | 21 |  |  | Tue 26/02/08 | Fri 20/02/09
4711 | 53091 | MS conformance testing of changes introduced by WI "Support of Packet-switched Handover for GERAN A/Gb mode" | PSHCT-MStest | 1 | Rel-8 | G3new | 2008-02-22 08:00 | 2008-11-21 17:00 | 100% | GP-080411 | - | Rohde & Schwarz | Franz.Segerer@ROHDE-SCHWARZ.COM | GP#40 completed | 51.010 |  | 21 |  |  | Tue 26/02/08 | Sat 22/11/08
4712 | 320001 | (Small) Technical Enhancements and Improvements for Rel-8 | TEI8 | 1 | Rel-8 | SP,CP,RP,GP | 2007-01-01 08:00 | 2008-12-11 17:00 | 100% | - | - | - | - | SP#42 completed | - | 32 |  |  |  | Fri 04/11/05 | Fri 20/02/09
4713 | 521029 | (IETF) (Small) Technical Enhancements and Improvements for Rel-8 | TEI8_IETF | 1 | Rel-8 | C1-IETF | 2007-01-01 08:00 | 2012-09-07 17:00 | 100% | - | - | christer.holmberg@ericsson.com | christer.holmberg@ericsson.com | CP#57 completed | RFC 6714 (was draft-ietf-simple-msrp-cema) | 52 | 27 |  |  | Mon 20/06/11 | Mon 03/09/12
4714 | 400025 | Test - (Small) Technical Enhancements and Improvements for Rel-8 | TEI8_Test | 1 | Rel-8 | R5,G3new | 2007-03-07 11:12 | 2010-12-24 17:00 | 100% | - | - | - | - | - | - | 40 | 21 |  |  | Fri 04/11/05 | Tue 07/12/10
4715 | 31067 | Deleted - All-IP Network | AIPN | 1 | Rel-8 | S1 | 2004-06-28 08:00 | 2006-03-15 17:00 | 100% | SP-050181 | - | NTT DoCoMo | c.masyu@nttdocomo.co.jp | SP#38 stopped. 25/07/08 Moved UID_31059 Study on All-IP Network (FS_AIPN/was AIPFS) to Rel-7 out of the stopped Rel-8 Feature UID_31067 Deleted - All-IP Network (AIPN) | - |  |  | SP-38 |  | Mon 30/08/04 | Tue 24/03/09
4716 | 31068 | Deleted - Stage 1 | AIPN | 2 | Rel-8 | S1 | 2004-06-28 08:00 | 2006-03-15 17:00 | 100% | SP-050181 | - | NTT DoCoMo | c.masyu@nttdocomo.co.jp | 22.258 withdrawn, superseded by 22.278 (UID 320022). SP#38 stopped | 22.258 |  |  | SP-38 |  | Mon 30/08/04 | Tue 24/03/09
4717 | 340032 | Deleted - was Rel-7 - LCS for 3GPP Interworking WLAN | LCS4_IWLAN | 1 | Rel-8 | S2 | 2007-09-28 17:00 | 2007-09-28 17:00 | 100% | SP-060818 | - | LG Electronics | dhshim@lge.com | SP#35 stopped | 23.234, 23.271, 23.167 | 34 |  | SP-35 |  | Wed 22/03/06 | Tue 24/03/09
4718 | 330010 | Deleted - never approved- FBI Phase 2 | FBI2 | 1 | Rel-8 | S2 | 2007-09-28 17:00 | 2007-09-28 17:00 | 100% | - | - | Nokia Siemens Networks | - | SP#38 stopped | - |  |  | SP-38 |  | Mon 09/06/03 | Tue 24/03/09
4719 | 330007 | Deleted -Enhancements to BS30 Bearer service for Videotelephony | BS30 | 1 | Rel-8 | S1 | 2007-03-15 17:00 | 2007-03-15 17:00 | 100% | SP-060484 | - | 3 | andre.jarvis@three.co.uk | SP#38 stopped (no support) | 22.002, 22.004, 22.101, 22.105, 24.008 |  |  | SP-38 |  | Fri 06/10/06 | Tue 24/03/09
4720 | 370055 | Deleted - IMS Enhancements Rel-8 | IMS8 | 1 | Rel-8 | S1 | 2007-09-03 08:00 | 2007-12-14 17:00 | 100% | - | - | Telecom Italia | - | SP#38 stopped | - | 37 |  | SP-38 |  | Tue 30/10/07 | Tue 24/03/09
4721 | 400023 | Deleted - Contact Manager Conformance Test specifications | eUPHBOOK-Test | 1 | Rel-8 | C6 | 2008-06-02 08:00 | 2010-03-19 17:00 | 100% | CP-080430 | - | Comprion, Gemalto | Udo Willenbrink, Jacques Seif | CP#47 work stopped/abandoned | - | 40 | 21 | CP-47 | PCG-24 | Tue 24/01/06 | Tue 09/03/10
4722 | 400123 | Deleted - Contact Manager for 3GPP UICC applications test specifications | eUPHBOOK-Test | 2 | Rel-8 | C6 | 2008-06-02 08:00 | 2010-03-19 17:00 | 100% | CP-080430 | - | Comprion | Udo Willenbrink (uwillenbrink@comprion.com ) | CP#47 work stopped/abandoned | 31.320 (external interface for communication with the ME) | 40 | 21 | CP-47 | PCG-24 | Mon 24/11/08 | Mon 06/09/10
4723 | 400223 | Deleted - Contact Manager API for Java™ Card test specification | eUPHBOOK-Test | 2 | Rel-8 | C6 | 2008-06-02 08:00 | 2010-03-19 17:00 | 100% | CP-080430 | - | Gemalto | jacques.seif@gemalto.com | CP#47 work stopped/abandoned | 31.321 (internal interface (API)) | 40 | 21 | CP-47 | PCG-24 | Mon 24/11/08 | Tue 09/03/10
4724 | 53092 | Deleted - MS conformance testing of Support of Conversational Services in A/Gb mode via the PS domain | SCSAGBCT-MStest | 1 | Rel-8 | G3new | 2008-02-25 08:00 | 2009-09-04 17:00 | 100% | GP-080330 | - | Nokia | arsi.heino@nokia.com | GP#43 work stopped/abandoned (completion 0%) | 51.010 |  | 21 | GP-43 | PCG-23 | Tue 26/02/08 | Mon 07/09/09
4725 | 0 | Release 8 Studies | - | 1 | Rel-8 | CP,GP,RP,SP | 2005-10-07 08:00 | 2005-10-07 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 09/02/10
4726 | 7026 | Study on Customised Alerting Tone (CAT) Requirements | FS_CAT | 1 | Rel-8 | S1 | 2005-10-07 08:00 | 2006-09-14 17:00 | 100% | SP-060474 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | Spin-off Rel-8 Feature Customized Alerting Tone (CAT) Service UID_340029 | 22.982 |  |  |  |  | Fri 04/11/05 | Tue 31/08/10
4727 | 7027 | Study on Facilitating Machine to Machine Communication in GSM and UMTS (M2M) | FS_M2M | 1 | Rel-8 | S1 | 2005-11-04 08:00 | 2007-03-08 17:00 | 100% | SP-050527 | - | Siemens | Juergen Merkel | SP#35 completed. Spin-off SA3 Study on Security Aspects of Remote Provisioning and Change of Subscription for M2M (UID_370053). SP#40 Spin-off new Feature UID_410030 (NIMTC) | 22.868 |  |  |  |  | Fri 04/11/05 | Mon 24/03/08
4728 | 31089 | Study on Network Composition | FS_NetComp | 1 | Rel-8 | S1 | 2005-12-07 08:00 | 2007-12-12 17:00 | 100% | SP-060478 | - | Nokia Siemens Networks | joerg.swetina@neclab.eu | SP#38 completed | 22.980 |  |  |  |  | Mon 12/12/05 | Mon 24/03/08
4729 | 320024 | Study on Requirements of IMS Multimedia Conferencing | FS_IMSconf | 1 | Rel-8 | S1 | 2006-06-08 08:00 | 2007-09-12 17:00 | 100% | SP-060479 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | SP#37 completed. Spin-off New Feature UID_370026 Value-Added Services for Short Message Service (VAS4SMS) | 22.948 | 32 |  |  |  | Fri 23/06/06 | Tue 31/08/10
4730 | 320025 | Study on support of a Public Warning System | FS_PWS | 1 | Rel-8 | S1 | 2007-09-03 08:00 | 2008-03-14 17:00 | 100% | SP-080054 | - | T-Mobile | mark.younge@t-mobile.com | SP#39 completed. Spin-off Rel-9 Feature UID_380057 (PWS) | 22.968 | 32 |  |  |  | Fri 23/06/06 | Thu 20/03/08
4731 | 330016 | Study on Paging Permission with Access Control | FS_PPAC | 1 | Rel-8 | S1 | 2006-09-28 08:00 | 2007-09-20 17:00 | 100% | SP-060785 | - | NTT DoCoMo | Katsuhiro NOGUCHI (noguchi@nttdocomo.co.jp) | SP#37 completed. Spin-off new Feature UID_370084 (PPACR) | 22.908 |  |  |  |  | Fri 06/10/06 | Tue 31/08/10
4732 | 340033 | Study on Non-3GPP access Network Selection Principles (NSP) | FS_N3GtoNSP | 1 | Rel-8 | S1 | 2006-12-06 08:00 | 2008-06-05 17:00 | 100% | SP-080318 | - | Telefónica O2 | chris.friel@O2.com | SP#38 completed. Spin-off New Feature UID_380062 (N3GTONSP). SP#40 WID updated SP-060930=>SP-080318. TR re-approved with new # 22.812=>22.912 | 22.912 | 34 |  |  |  | Fri 06/10/06 | Tue 03/06/08
4733 | 340034 | Study on Value Added Services for Short Message Service | FS_VAS4SMS | 1 | Rel-8 | S1 | 2006-12-06 08:00 | 2007-12-07 17:00 | 100% | SP-060786 | - | China Mobile | Qing Huang (huangqing@chinamobile.com) | SP#38 completed. Spin-off New Feature UID_370026 (VAS4SM) | 22.942 | 34 |  |  |  | Fri 06/10/06 | Tue 31/08/10
4734 | 340035 | Study on Service continuity between mobile and WLAN networks | FS_SMLSWLAN | 1 | Rel-8 | S1 | 2006-12-06 08:00 | 2007-12-06 17:00 | 100% | SP-060936 | - | NEC | joerg.swetina@neclab.eu | SP#38 completed | 22.937 | 34 |  |  |  | Fri 06/10/06 | Tue 31/08/10
4735 | 370086 | Study on Services Alignment and Migration | FS_ServAl | 1 | Rel-8 | S1 | 2006-12-06 08:00 | 2008-03-12 17:00 | 100% | SP-070126 | - | Telefónica O2 | chris.friel@O2.com | SP#39 completed. Spin-off Rel-9 Feature UID_330017 Services Alignment and Migration (ServAl) | 22.983 | 37 |  |  |  | Fri 06/10/06 | Thu 05/08/10
4736 | 32085 | Study on 3GPP System Architecture Evolution | FS_SAE | 1 | Rel-8 | S2,S3 | 2004-12-03 08:00 | 2009-03-12 17:00 | 100% | SP-070163 | - | Vodafone | chris.pudney@vodafone.com | SP#43 completed | - |  |  |  |  | Mon 31/01/05 | Fri 20/02/09
4737 | 32086 | Stage 2 Interim conclusion for RAN Work to start | FS_SAE | 2 | Rel-8 | S2 | 2004-12-03 08:00 | 2008-09-18 17:00 | 100% | SP-070163 | - | Vodafone | chris.pudney@vodafone.com | SP#41 completed | 23.882 |  |  |  |  | Mon 31/01/05 | Sun 14/09/08
4738 | 32087 | Stage 2 study on 3GPP architectural development | FS_SAE | 2 | Rel-8 | S2 | 2006-01-09 08:00 | 2008-09-18 17:00 | 100% | SP-070163 | - | Vodafone | chris.pudney@vodafone.com | SP#41 completed | 23.882 |  |  |  |  | Mon 31/01/05 | Sun 14/09/08
4739 | 7024 | Security study for Inter-access mobility between non-3GPP and 3GPP system | FS_SAE | 2 | Rel-8 | S3 | 2007-09-03 08:00 | 2009-03-12 17:00 | 100% | SP-070163 | - | Nokia | dajiang.zhang@nokia.com | SP#43 completed | 33.821, 33.822 |  |  |  |  | Tue 21/02/06 | Fri 20/02/09
4740 | 320028 | Study on Stage 2 aspects of IMS Service Brokering | FS_ISB_ST2 | 1 | Rel-8 | S2 | 2006-06-19 08:00 | 2008-09-18 17:00 | 100% | SP-060443 | - | Telcordia | raquel@research.telcordia.com | SP#41 completed. No spin-off activity proposed. [Note: IMS Service Brokering enhancements UID_31088 moved back from R8 to R7 to give a home to 22228CR0036_(Rel-7)_S1-051232. Hence, Rel-7 ISB has Stage 1 only (and is misaligned with Rel-7 Stages 2/3.] | 23.810 | 32 |  |  |  | Mon 17/07/06 | Sun 14/09/08
4741 | 7049 | Study on IMS utilizing multicast bearer services | FS_MLTICAST-IMS | 1 | Rel-8 | S2 | 2006-03-22 08:00 | 2007-12-06 17:00 | 100% | SP-060148 | - | Nokia Siemens Networks | - | SP#38 completed | 23.847 |  |  |  |  | Wed 22/03/06 | Mon 24/03/08
4742 | 350051 | Study on Multimedia Session Continuity | FS_MMSC | 1 | Rel-8 | S2 | 2007-04-26 08:00 | 2008-06-05 17:00 | 100% | SP-070818 | - | LG Electronics | - | SP#40 completed | 23.893 | 35 |  |  |  | Thu 29/03/07 | Mon 24/03/08
4743 | 380034 | Study on centralized IMS service control | FS_ICS | 1 | Rel-8 | S2,S1 | 2006-10-23 08:00 | 2008-03-12 17:00 | 100% | SP-070494 | - | Ericsson | peter.bleckert@ericsson.com | SP#39 completed | - | 38 | 21 |  |  | Wed 31/10/07 | Thu 20/03/08
4744 | 370087 | Study on centralized IMS services requirements | FS_ICS-S1 | 2 | Rel-8 | S1 | 2007-03-05 08:00 | 2008-03-12 17:00 | 100% | SP-070494 | - | NEC | joerg.swetina@neclab.eu | SP#39 completed | 22.892 | 37 |  |  |  | Wed 21/11/07 | Tue 31/08/10
4745 | 330012 | Study on centralized IMS services control | FS_IMS_CSC | 2 | Rel-8 | S2 | 2006-10-23 08:00 | 2008-03-12 17:00 | 100% | SP-070494 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | SP#39 completed | 23.892 |  |  |  |  | Thu 16/02/06 | Sat 22/03/08
4746 | 380078 | Study on Architecture of IMS based Customized Alerting Tone (CAT) | FS_CAT-St2 | 1 | Rel-8 | S2 | 2007-12-04 08:00 | 2008-09-18 17:00 | 100% | SP-070905 | - | China Mobile | WANG, Jing (wangjing@chinamobilecom) | SP#41 completed as Rel-8 | 23.872 | 38 | 21 |  |  | Thu 20/12/07 | Tue 23/09/08
4747 | 380085 | Study on Home (e)NodeB Security | FS_HNB_Sec | 1 | Rel-8 | S3 | 2007-12-20 08:00 | 2009-03-12 17:00 | 100% | SP-070783 | - | Huawei | yangyanmei@huawei.com | SP#43 completed. Linked to RAN4 Study on 3G Home NodeB/eNodeB (UID_350039) and to SA5 Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB (UID_360007) | 33.820 | 38 | 21 |  |  | Thu 20/12/07 | Wed 11/03/09
4748 | 360015 | Study on Transferring of emergency call data – in-band modem solution | eCALLIBMS | 1 | Rel-8 | S4 | 2006-12-07 08:00 | 2007-12-12 17:00 | 100% | SP-060935 | - | Airbiquity | lhong@airbiquity.com | SP#38 completed. Spin-off WID UID_34042 (eCall_Phase2) | 26.967 | 36 |  |  |  | Sun 10/12/06 | Fri 16/05/08
4749 | 35065 | Study on Element Operations Systems Function (EOSF) definition | OAM7-NIM-EOSF | 1 | Rel-8 | S5 | 2007-06-07 08:00 | 2008-06-12 17:00 | 100% | SP-070307 | - | China Mobile | Li Jian (lijian@chinamobile.com) | SP#40 completed. WID updated SP-050608=>SP-070307 | 32.819 |  |  |  |  | Fri 16/09/05 | Mon 28/04/08
4750 | 35074 | Study on SA5 MTOSI XML Harmonization | OAM8-NIM-XML | 1 | Rel-8 | S5 | 2006-05-10 08:00 | 2007-09-12 17:00 | 100% | SP-070305 | - | Nortel | jduguay@nortel.com | SP#37 completed. WID updated SP-050295=>SP-070305 | 32.818 |  |  |  |  | Thu 24/11/05 | Thu 15/10/09
4751 | 320006 | Study on Common Profile Storage (CPS) Framework of User Data for network services and management | OAM7-CPS | 1 | Rel-8 | S5 | 2006-07-03 08:00 | 2007-06-07 17:00 | 100% | SP-060263 | - | T-Mobile | istvan.aba@t-mobile.at | SP#36 completed. Spin-off New Feature UID_400034 User Data Convergence (UDC) | 32.808 | 32 |  |  |  | Mon 22/05/06 | Mon 17/03/08
4752 | 340036 | Study on Management for LTE and SAE | FS_OAM_LTE_SAE | 1 | Rel-8 | S5 | 2006-12-07 08:00 | 2008-12-11 17:00 | 100% | SP-060753 | - | Ericsson | robert.petersen@ericsson.com | SP#42 completed | 32.816 | 34 |  |  |  | Fri 15/12/06 | Tue 25/11/08
4753 | 350004 | Study on Charging Aspects of 3GPP System Evolution | FS_SAEcharg | 1 | Rel-8 | S5 | 2007-04-02 08:00 | 2007-12-06 17:00 | 100% | SP-070174 | - | Nokia Siemens Networks | Gerald.Goermer@nsn.com | SP#38 completed | 32.820 | 35 |  |  |  | Thu 24/11/05 | Mon 17/03/08
4754 | 7048 | Study on AS-MRFC media server control protocol | MRFC | 1 | Rel-8 | C1 | 2006-03-22 08:00 | 2008-06-13 17:00 | 100% | CP-060180 | - | Hewlett-Packard | mark.syrett@hp.com | CP#40 completed. Spin-off New Feature UID_380035 (MRFC_TS) | 24.880 |  |  |  |  | Wed 22/03/06 | Tue 13/05/08
4755 | 350018 | Study on IMS Restoration Procedures | FS_IMS_RP | 1 | Rel-8 | C4 | 2007-03-26 08:00 | 2008-05-30 17:00 | 100% | CP-070031 | - | Ericsson | german.blanco@ericsson.com | CP#40 completed. Spin-off WID UID_400012 (IMS_RP) | 23.820 | 35 |  |  |  | Thu 29/03/07 | Thu 29/05/08
4756 | 360030 | Study on IMS Application Server Service Data Descriptions for AS interoperability | FS_IMS_ASIO | 1 | Rel-8 | C4 | 2007-09-14 08:00 | 2008-09-12 17:00 | 100% | CP-070685 | - | Alcatel-Lucent | Jean-Jacques Trottin | CP#41 completed. Linked to SA5 Study on Common Profile Storage framework UID_320006. Spin-off WID UID_410003 (IMS_ASIO) | 29.864 | 36 |  |  |  | Wed 05/09/07 | Thu 11/09/08
4757 | 360031 | Study on Customized Alerting Tone (CAT) solution for voice and video call in CS domain | FS_CAT_VVC_CS | 1 | Rel-8 | C4 | 2007-09-14 08:00 | 2008-09-12 17:00 | 100% | CP-070518 | - | China Mobile | zhanghao@chinamobile.com | CP#41 completed. Spin-off WID under Feature CAT UID_340029 | 29.882 | 36 |  |  |  | Wed 05/09/07 | Mon 01/09/08
4758 | 380023 | Study on InterWorking Function between MAP based and Diameter based interfaces | FS_MAP2Diam | 1 | Rel-8 | C4 | 2007-11-30 08:00 | 2008-12-05 17:00 | 100% | CP-070760 | - | Huawei | liming49985@huawei.com | CP#42 completed. Spin-off implementation Building Block UID_410007 (MAP2Diam) under the SAES Feature UID_320005 | 29.805 | 38 | 21 |  |  | Mon 19/11/07 | Sat 22/11/08
4759 | 370041 | Study on Scope of future HSPA Evolution for 1.28 Mcps TDD | FS_RAN-LCRTDDHSPAEvo | 1 | Rel-8 | R1 | 2007-09-14 08:00 | 2008-05-30 17:00 | 100% | RP-070748 | RP-080290 | RITT | Xu Fei | RP#40 completed | 25.824 | 37 |  |  |  | Thu 21/06/07 | Thu 12/06/08
4760 | 370042 | Study on Synchronized E-DCH for UTRA FDD | FS_RAN-UplinkSync | 1 | Rel-8 | R1 | 2007-09-14 08:00 | 2008-03-07 17:00 | 100% | RP-070678 | RP-080068 | Nokia Siemens Networks | Karri.Ranta-aho@nsn.com | RP#39 completed | 25.823 | 37 |  |  |  | Thu 21/06/07 | Thu 26/06/08
4761 | 360016 | Study on Improved network controlled mobility between LTE and 3GPP2/mobile WiMAX radio technologies | FS_RAN-LTEmob | 1 | Rel-8 | R4 | 2007-06-04 08:00 | 2007-12-03 17:00 | 100% | RP-070511 | RP-070827 | Motorola | hao.bi@Motorola.com | RP#38 completed | 36.938 | 36 |  |  |  | Thu 21/06/07 | Thu 26/06/08
4762 | 350039 | Study on 3G Home NodeB/eNodeB | FS_RAN-HNBeNB | 1 | Rel-8 | R4 | 2007-03-05 08:00 | 2008-05-30 17:00 | 100% | RP-070257 | RP-080289 | Motorola | howard.thomas@motorola.com | RP#40 completed | 25.820 | 35 |  |  |  | Thu 29/03/07 | Thu 26/06/08
4763 | 50589 | Study on A-interface over IP | AINTIP | 1 | Rel-8 | GP | 2007-08-31 08:00 | 2008-02-22 17:00 | 100% | GP-071562 | - | China Mobile, Ericsson | paul.schliwa-bertling@ericsson.com | GP#37 completed. Spin-off implementation Feature AoIP (A-interface over IP) UID_50591 | 43.903 |  |  |  |  | Sat 03/11/07 | Mon 03/03/08
4764 | 50590 | Study on Multi-User Reusing-One-Slot | MUROS | 1 | Rel-8 | GP | 2007-11-16 08:00 | 2010-11-12 17:00 | 100% | GP-072033 | - | Nokia Siemens Networks | juergen.hofmann@nsn.com | GP#48 completed as Rel-8. Spin-off implementation WI UID_420002 VAMOS (Voice services over Adaptive Multi-user channels on One Slot) | 45.914 |  |  |  |  | Mon 19/11/07 | Tue 30/11/10
4765 | 51148 | Study on Optimized Transmit Pulse Shape for Downlink EGPRS2-B | WIDER | 1 | Rel-8 | G1 | 2007-11-16 08:00 | 2010-05-21 17:00 | 100% | GP-072026 | - | Research In Motion, Nokia Siemens Networks | jdwyer@RIM.COM and eddie.riddington@nsn.com | GP#46 completed | 45.913 |  |  |  |  | Tue 26/02/08 | Thu 27/05/10
4766 | 350017 | Deleted - Study on Mobility between 3GPP-WLAN Interworking and 3GPP Systems | FS_SM3GWLAN | 1 | Rel-8 | S2 | 2007-03-20 08:00 | 2008-09-18 17:00 | 100% | SP-070106 | - | Orange | - | SP#41 stopped. Draft TR 23.827 content implemented in TS 23.327. | withdrawn 23.827 | 35 |  | SP-41 | PCG-21 | Thu 29/03/07 | Wed 17/09/08
4767 | 370044 | Deleted - equals 340035 -FS on Service continuity between mobile and WLAN networks | FSSCMobToW | 1 | Rel-8 | S1 | 2007-09-03 08:00 | 2007-12-14 17:00 | 100% | SP-070557 | - | BT | mike.meyerstein@bt.com | SP#39 stopped | 22.937 | 37 |  | SP-39 | PCG-21 | Tue 02/10/07 | Tue 24/03/09
4768 | 380068 | Deleted - Study on Evaluation of LCS Control Plane Solution for EPS | FS_LCS_EPS | 1 | Rel-8 | S2 | 2008-01-14 08:00 | 2008-05-30 17:00 | 100% | SP-070819 | - | SiRF | - | SP#40 spin-off Feature UID_400038 (LCS_CPS_EPS). SP#40 FS stopped | 23.891 | 38 |  | SP-40 | PCG-21 | Tue 02/10/07 | Tue 24/03/09
4769 | 380080 | Deleted - Study on HS-PDSCH serving cell change enhancements | FS_RAN-HSPDSCH | 1 | Rel-8 | R4 | 2007-12-17 08:00 | 2008-03-07 17:00 | 100% | RP-071044 | RP-080070 | Qualcomm | - | RP#39 stopped (no TR produced). Spin-off HS-DSCH Serving Cell Change Enhancements (UID_39003) | none | 38 | 21 | RP-39 | PCG-21 | Mon 17/12/07 | Thu 26/06/08
4770 | 390032 | Deleted - Study on Dual-Cell HSDPA operation | FS_RAN-DCHS | 1 | Rel-8 | R1 | 2007-08-15 08:00 | 2009-03-06 17:00 | 100% | RP-080228 | RP-090066 | Qualcomm | Josef Blanz | RP#43 stopped (draft TR 25.825 v100 withdrawn). Conclusions in RP-090318 (RAN1 findings of the UTRA Multi-Carrier Evolution study). RP#42 New WI approved on Dual-Cell HSDPA operation on adjacent carriers (UID_400052) | withdrawn 25.825 v100 | 39 | 21 | RP-43 | PCG-22 | Mon 17/12/07 | Tue 17/03/09
4771 | 0 | Release 7 Features | - | 1 | Rel-7 | CP,GP,RP,SP | 2005-05-02 08:00 | 2007-12-06 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 09/02/10
4772 | 732097 | Identification of Communication Services in IMS | ServID | 1 | Rel-7 | S2,S1,C1,S5 | 2005-05-02 08:00 | 2007-09-14 17:00 | 100% | SP-060293 | - | Ericsson | stephen.terrill@ericsson.com | WID approved SP#28. WID updated SP#32 | - | 32 |  |  |  | Wed 22/06/05 | Tue 01/07/08
4773 | 32106 | TR on ServID | ServID | 2 | Rel-7 | S2 | 2005-05-02 08:00 | 2006-03-21 17:00 | 100% | SP-060293 | - | Ericsson | stephen.terrill@ericsson.com | - | 23.816 |  |  |  |  | Fri 01/07/05 | Tue 01/07/08
4774 | 32107 | Stage 1,2 of ServID | ServID | 2 | Rel-7 | S1,S2 | 2005-11-11 08:00 | 2006-05-31 17:00 | 100% | SP-060293 | - | Ericsson | stephen.terrill@ericsson.com | - | 22.228, 23.228, 23.203 |  |  |  |  | Fri 01/07/05 | Tue 01/07/08
4775 | 320010 | Stage 3 of ServID | ServID | 2 | Rel-7 | C1 | 2006-03-31 08:00 | 2007-03-15 17:00 | 100% | CP-060259 | - | Ericsson | christer.holmberg@ericsson.com | CP#32 approved WID | 23.218, 24.229 | 32 |  |  |  | Mon 20/03/06 | Tue 01/07/08
4776 | 7035 | Charging of ServID | ServID | 2 | Rel-7 | S5 | 2006-03-31 08:00 | 2007-09-14 17:00 | 100% | SP-060293 | - | Orange | alain.bibas@orange-ft.com | - | 32.260, 32.298, 32.299 |  |  |  |  | Mon 20/03/06 | Tue 01/07/08
4777 | 32116 | Supporting Globally Routable User Agent URIs in IMS | GRUU | 1 | Rel-7 | S2,S1,C1 | 2005-11-14 08:00 | 2007-06-15 17:00 | 100% | SP-050633 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | SP#29 approved WID | - | 32 |  |  |  | Fri 28/03/03 | Tue 01/07/08
4778 | 7009 | Deleted - TR on GRUU | GRUU | 2 | Rel-7 | S2 | 2005-11-14 08:00 | 2006-09-14 17:00 | 100% | SP-050633 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | Abandoned | - |  |  | SP-32 |  | Thu 16/02/06 | Tue 01/07/08
4779 | 7010 | Stage 1,2 of GRUU | GRUU | 2 | Rel-7 | S1,S2 | 2006-07-03 08:00 | 2006-09-29 17:00 | 100% | SP-050633 | - | Research In Motion | Adrian Buckley (abuckley@rim.com) | SP#29 approved WID | 22.228, 23.228, 23.218, 24.229 |  |  |  |  | Thu 16/02/06 | Tue 01/07/08
4780 | 320011 | Stage 3 of GRUU | GRUU | 2 | Rel-7 | C1 | 2006-06-02 08:00 | 2007-06-15 17:00 | 100% | CP-060358 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | CP#32 approved WID | 24.229 | 32 |  |  |  | Thu 16/02/06 | Tue 01/07/08
4781 | 7038 | Multimedia Telephony Service for IMS | MTSI | 1 | Rel-7 | S1,C1,S4 | 2006-02-01 08:00 | 2017-03-15 17:00 | 100% | SP-060224 | - | Ericsson | peter.bleckert@ericsson.com | - | - | 69 | 35 |  |  | Thu 02/03/06 | Wed 25/06/08
4782 | 7039 | Stage 1 of MTSI | MTSI-REQ | 2 | Rel-7 | S1 | 2006-02-01 08:00 | 2006-09-29 17:00 | 100% | SP-060224 | - | Ericsson | peter.bleckert@ericsson.com | - | 22.173 |  |  |  |  | Tue 21/03/06 | Wed 25/06/08
4783 | 7037 | Stage 3 of MTSI | MTSI | 2 | Rel-7 | C1 | 2006-03-10 08:00 | 2007-06-14 17:00 | 100% | CP-060257 | - | Ericsson | christer.holmberg@ericsson.com | - | 24.173 |  |  |  |  | Wed 22/03/06 | Wed 25/06/08
4784 | 7040 | Media handling and interaction in MTSI | MTSI-MHI | 2 | Rel-7 | S4 | 2006-03-15 08:00 | 2007-03-15 17:00 | 100% | SP-060225 | - | Ericsson | olle.franceschi@ericsson.com | - | 26.114 |  |  |  |  | Tue 21/03/06 | Wed 25/06/08
4785 | 690069 | UE Conformance Test Aspects - Multimedia Telephony Services for IMS (MTSI) over fixed access | MTSI_FIXED_ACCESS-UEConTest | 2 | Rel-7 | R5 | 2015-09-15 08:00 | 2017-03-15 17:00 | 100% | RP-151257 |  | Telecom Italia |  | tested: REL-7 SA/CT WI MTSI;1/1/16: Compl:0%->5%; 22/3/16: Compl:5%->15%1/7/16: Compl:15%->30% ; 21/ |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 21/03/17
4786 | 690071 | UE Conformance Test Aspects – Multimedia Telephony Services for IMS (MTSI) over WLAN | MTSI_WLAN-UEConTest | 2 | Rel-7 | R5 | 2015-09-15 08:00 | 2016-12-15 17:00 | 100% | RP-151770 |  | Ericsson |  | tested: REL-7 WI MTSI; 1/1/16: Compl:0%->5%1/1/16: WID: RP-151334->RP-15177022/3/16: Compl:5%->10% |  | 69 | 35 |  |  | Tue 29/09/15 | Tue 20/12/16
4787 | 7023 | Deleted - duplicates UID7039 - IMS Multimedia Telephony Service | MMTEL | 2 | Rel-7 | S1 | 2007-06-15 | 2007-06-15 | 100% | SP-050387 | - | Ericsson | peter.bleckert@ericsson.com | - | 22.173 |  |  | SP-32 |  | Thu 02/03/06 | Wed 25/06/08
4788 | 350147 | Multimedia Telephony Service for IMS (MTSI) - UE Conformance Testing | MTSI-UEConTest | 1 | Rel-7 | R5 | 2007-09-19 08:00 | 2009-03-12 17:00 | 100% | RP-080605 | RP-090056 | Ericsson, Motorola | Leif.Mattisson@ericsson.com, Jacob.John@motorola.com | RP#43 completed. Linked UID_7038 (MTSI) | 34.123-1, 34.123-2, 34.123-3, 34.229-1, 34.229-2 | 35 |  |  |  | Tue 21/03/06 | Tue 24/02/09
4789 | 377001 | TISPAN requirements for Multimedia Telephony with PSTN/ISDN simulation services | TMMTEL7 | 1 | Rel-7 | S1 | 2007-09-18 08:00 | 2007-12-06 17:00 | 100% | SP-070568 | - | - | - | - | 22.273 (EI 181 002 maintenance) | 37 |  |  |  | Thu 10/01/08 | Thu 10/01/08
4790 | 387001 | Maintenance of TISPAN release 1 common IMS | MCIMSTR1 | 1 | Rel-7 | S2 | 2007-07-02 08:00 | 2008-03-07 17:00 | 100% | SP-070915 | - | Ericsson | Raymond Forbes | - | http://www.3gpp.org/specs/TISPAN-IMS-ansfer.htm | 38 | 21 |  |  | Thu 10/01/08 | Mon 21/07/08
4791 | 387002 | SA1 aspects of MCIMSTR1 | MCIMSTR1-S1 | 2 | Rel-7 | S1 | 2007-09-18 08:00 | 2007-12-06 17:00 | 100% | SP-070915 | - | Telecom Italia | Marco.DeLuca1@telecomitalia.it | - | 22.173, 22.273 | 38 | 21 |  |  | Thu 10/01/08 | Tue 04/11/08
4792 | 387003 | SA2 aspects of MCIMSTR1 | MCIMSTR1-S2 | 2 | Rel-7 | S2 | 2007-09-18 08:00 | 2007-12-06 17:00 | 100% | SP-070915 | - | Ericsson | Raymond Forbes | - | 23.406, 23.417, 23.508,23.509, 23.511 | 38 | 21 |  |  | Thu 10/01/08 | Mon 21/07/08
4793 | 380072 | SA1,SA2 part of Maintenance of TISPAN release 1 common IMS | IMS_Comm_Mtce7 | 2 | Rel-7 | S2,S1 | 2007-07-02 08:00 | 2007-12-06 17:00 | 100% | SP-080501 | - | BT, Ericsson | Dick Knight, Raymond Forbes | SP#38 completed | 22.173, 22.273, 22.401, 23.406, 23.417, 23.508, 23.509, 23.511 | 38 | 21 |  |  | Tue 02/10/07 | Thu 29/07/10
4794 | 380004 | Maintenance of TISPAN R1 | MAINT_R1 | 2 | Rel-7 | C1,C3,C4 | 2007-11-09 08:00 | 2008-03-07 17:00 | 100% | CP-080211 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#39 completed | 24.404, 24.405, 24.406, 24.407, 24.408, 24.410, 24.411, 24.416, 29.421, 24.423, 24.428, 24.429, 29.433, 24.441, 24.403, 29.427, 24.430, 29.412 | 38 | 21 |  |  | Mon 19/11/07 | Tue 15/04/08
4795 | 32045 | PS domain and IMS impacts for supporting IMS Emergency calls (EMC1) | EMC1 | 1 | Rel-7 | S2,S1,C1,C4,IETF | 2000-09-18 08:00 | 2011-12-09 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | EMC1 |  |  |  |  | Thu 27/03/03 | Fri 28/03/03
4796 | 1314 | Service Requirements for IP-based emergency calls | EMC1 | 2 | Rel-7 | S1 | 2000-09-18 08:00 | 2004-06-25 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 22.101 |  |  |  |  | Wed 19/04/00 | Tue 08/06/04
4797 | 32046 | Study on Stage 2 for IMS-level solution | EMC1 | 2 | Rel-7 | S2 | 2003-02-26 08:00 | 2005-09-16 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 23.867 |  |  |  |  | Thu 27/03/03 | Thu 22/12/05
4798 | 32080 | Study on Stage 2 for GPRS-level solution | EMC1 | 2 | Rel-7 | S2 | 2004-10-14 08:00 | 2005-12-08 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 23.867 |  |  |  |  | Thu 14/10/04 | Thu 22/12/05
4799 | 32100 | Stage 2 Specification Phase - IMS-level | EMC1 | 2 | Rel-7 | S2 | 2005-09-05 08:00 | 2006-06-09 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | 23.060, 23.167, 23.203, 23.221, 23.228, 23.234, 23.271, 23.406 |  |  |  |  | Thu 14/10/04 | Tue 19/09/06
4800 | 32101 | Deleted - Stage 2 Specification Phase - GPRS-level | EMC1 | 2 | Rel-7 | S2 | 2007-03-02 17:00 | 2007-03-02 17:00 | 100% | SP-050604 | - | Siemens | Rainer Liebhart | - | - |  |  | SP-32 |  | Thu 14/10/04 | Fri 22/06/07
4801 | 1653 | Emergency Call Enhancements for IP& PS Based Calls – stage 3 | EMC1 | 2 | Rel-7 | C1,C4,IETF | 2006-01-09 08:00 | 2011-12-09 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | - |  |  |  |  | Tue 08/08/00 | Thu 22/12/05
4802 | 1315 | CT1 IMS aspects to support IMS Emergency sessions | EMC1 | 3 | Rel-7 | C1 | 2006-01-09 08:00 | 2007-06-15 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | 24.229 |  |  |  |  | Wed 19/04/00 | Wed 12/09/07
4803 | 521030 | (IETF) CT1 IMS aspects to support IMS Emergency sessions | EMC1 | 3 | Rel-7 | C1-IETF | 2006-01-09 08:00 | 2011-12-09 17:00 | 100% | CP-050529 | - | Keith Drage | - | CP#54 completed | RFC 6442 (was draft-ietf-sipcore-location-conveyance) | 52 | 27 |  |  | Mon 20/06/11 | Tue 13/12/11
4804 | 13028 | Deleted - CT3 IMS aspects to support IMS Emergency sessions | EMC1 | 3 | Rel-7 | C3 | 2006-05-08 08:00 | 2006-09-15 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | Cancelled for Rel-7 and there is no corresponding Rel-8 WI | 29.163 |  |  | CP-33 |  | Wed 19/04/00 | Tue 01/07/08
4805 | 13031 | Deleted - CT3 PS domain aspects to support IMS Emergency sessions | EMC1 | 3 | Rel-7 | C3 | 2006-05-08 08:00 | 2006-09-15 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | Cancelled for Rel-7 and there is no corresponding Rel-8 WI | 29.061 |  |  | CP-33 |  | Tue 08/08/00 | Tue 01/07/08
4806 | 1646 | CT1 PS domain aspects to support IMS Emergency sessions | EMC1 | 3 | Rel-7 | C1 | 2006-01-09 08:00 | 2007-06-15 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | 24.008, 24.234 |  |  |  |  | Tue 08/08/00 | Wed 12/09/07
4807 | 14026 | CT4 PS domain aspects to support IMS Emergency sessions | EMC1-GPRSc4 | 3 | Rel-7 | C4 | 2006-01-09 08:00 | 2007-06-01 17:00 | 100% | CP-050529 | - | Ericsson | alf.heidermark@ericsson.com | - | 29.060 |  |  |  |  | Tue 08/08/00 | Tue 29/05/07
4808 | 11065 | IMS Support of Conferencing | IMSconf | 1 | Rel-7 | C1 | 2005-11-04 08:00 | 2007-03-15 17:00 | 100% | CP-070120 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | CP#35 revised WID | 24.147, 24.229 |  |  |  |  | Thu 22/12/05 | Tue 01/07/08
4809 | 34033 | Performance Characterization of VoIMS over HSDPA\EUL channels | VoIMS-PCVoIMS | 1 | Rel-7 | S4 | 2005-03-15 08:00 | 2007-12-06 17:00 | 100% | SP-050089 | - | Alcatel-Lucent | mcgowan@alcatel-lucent.com | - | 26.935 |  |  |  |  | Mon 21/03/05 | Thu 10/01/08
4810 | 31062 | WLAN-UMTS Interworking Phase 2 | WLAN2 | 1 | Rel-7 | S1,S2 | 2004-01-05 08:00 | 2005-06-07 08:00 | 100% | SP-030712 | - | Telenor | frederic.paint@telenor.com | Created at SP#27 because of WLAN items belonging to Rel-7. Acronym changed from "WLAN2, WLAN-SC" | 33.234 (SP-36 SA3 CRs approved) |  |  |  |  | Wed 09/03/05 | Tue 24/03/15
4811 | 31057 | Stage 1 on Session Continuity | WLAN2 | 2 | Rel-7 | S1 | 2004-01-05 08:00 | 2004-06-11 17:00 | 100% | - | - | - | - | Acronym changed from "WLAN2, WLAN-SC" | 22.234 |  |  |  |  | Thu 17/06/04 | Tue 24/03/15
4812 | 32096 | Stage 2 on Session Continuity: covered by SAE | WLAN2 | 2 | Rel-7 | S2 | 2005-06-07 08:00 | 2005-06-07 08:00 | 100% | - | - | - | - | Acronym changed from "WLAN2, WLAN-SC" | - |  |  |  |  | Tue 07/06/05 | Tue 24/03/15
4813 | 32110 | WLAN Interworking – Private Network access from WLAN 3GPP IP Access | WLANPNA | 1 | Rel-7 | S2,C1,C3,C4 | 2005-10-10 08:00 | 2006-09-26 17:00 | 100% | SP-050489 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | - | - |  |  |  |  | Fri 28/03/03 | Fri 07/10/05
4814 | 32111 | WLAN-PNA - Stage 2 | WLANPNA-st2 | 2 | Rel-7 | S2 | 2005-10-10 08:00 | 2006-06-23 17:00 | 100% | SP-050489 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | Approved at SP#29 | 23.234, 33.234 |  |  |  |  | Tue 20/12/05 | Wed 31/05/06
4815 | 11059 | WLAN-PNA - Stage 3 | WLANPNA-st3 | 2 | Rel-7 | C1,C3,C4 | 2006-02-01 08:00 | 2006-09-26 17:00 | 100% | CP-060256 | - | NEC | - | Approved at CP#29 | - |  |  |  |  | Tue 22/03/05 | Fri 23/06/06
4816 | 11064 | CT1 aspets for WLAN-PNA | WLANPNA-st3 | 3 | Rel-7 | C1 | 2006-02-01 08:00 | 2006-09-26 17:00 | 100% | CP-060256 | - | NEC | - | Approved at CP#29 | 24.234 |  |  |  |  | Thu 22/12/05 | Wed 31/05/06
4817 | 13027 | CT3 aspets for WLAN-PNA | WLANPNA-st3 | 3 | Rel-7 | C3 | 2006-02-01 08:00 | 2006-09-26 17:00 | 100% | CP-060256 | - | NEC | - | Approved at CP#29 | 29.161 |  |  |  |  | Thu 22/12/05 | Fri 23/06/06
4818 | 14024 | Deleted - CT4 aspets for WLAN-PNA | WLANPNA-st3 | 3 | Rel-7 | C4 | 2006-02-01 08:00 | 2006-09-26 17:00 | 100% | CP-060256 | - | NEC | - | CT4#31; no impacts identified, therefore completed. CP-32 stopped | 29.234 |  |  | CP-32 |  | Thu 22/12/05 | Thu 08/03/07
4819 | 32092 | Enhancements to support QoS provisioning over 3GPP/WLAN Interworking | WLANQOS | 1 | Rel-7 | S2,C4,C1 | 2005-03-14 08:00 | 2007-03-09 17:00 | 100% | SP-050682 | - | Samsung | - | Moved from FS section Feb 06. SP-30 updated WID | - |  |  |  |  | Tue 07/06/05 | Fri 18/07/08
4820 | 7015 | Deleted - TR on support of QoS on WLAN | WLANQOS | 2 | Rel-7 | S2 | 2005-03-14 08:00 | 2006-01-31 17:00 | 100% | SP-050682 | - | Samsung | - | SP#32 stopped | 23.836 |  |  | SP-32 |  | Thu 16/02/06 | Fri 18/07/08
4821 | 7016 | Stage 2 on support of QoS over 3GPP/WLAN interworking | WLANQOS | 2 | Rel-7 | S2 | 2006-02-01 08:00 | 2006-06-30 17:00 | 100% | SP-050682 | - | Samsung | - | SP#30 updated WID | 23.234 |  |  |  |  | Thu 16/02/06 | Fri 18/07/08
4822 | 14028 | Stage 3 CT4 on support of QoS over 3GPP/WLAN Interworking | WLANQOS | 2 | Rel-7 | C4 | 2006-09-22 08:00 | 2007-03-09 17:00 | 100% | CP-060418 | - | Huawei | zhang.peng@huawei.com | CP#33 approved WID | 29.234, 23.008 |  |  |  |  | Wed 11/10/06 | Fri 18/07/08
4823 | 340005 | Stage 3 CT1 on support of QoS over 3GPP/WLAN Interworking | WLANQOS | 2 | Rel-7 | C1 | 2006-09-04 08:00 | 2006-11-30 17:00 | 100% | CP-060418 | - | Huawei | zhang.peng@huawei.com | CP#33 approved WID | 24.234 | 34 |  |  |  | Wed 29/11/06 | Fri 18/07/08
4824 | 32079 | Location Services enhancements | LCS3 | 1 | Rel-7 | S1,S2,GP,C4,R2 | 2004-06-28 08:00 | 2007-12-17 17:00 | 100% | SP-040682 | - | - | - | - | - |  |  |  |  | Fri 21/06/02 | Wed 02/07/08
4825 | 32093 | Stage 2 for LCS3 (including IMS emergency location aspects) | LCS3 | 2 | Rel-7 | S2 | 2004-12-31 08:00 | 2006-09-15 17:00 | 100% | SP-050119 | - | SiRF | brodilitz@sirf.com | SP#27 approved WID | 23.271 |  |  |  |  | Tue 22/03/05 | Wed 02/07/08
4826 | 50558 | LCS Enhancements related to Location-Based Services | LCS3-LBS | 2 | Rel-7 | GP | 2005-01-03 08:00 | 2007-08-31 17:00 | 100% | GP-050265 | - | SiRF | kjudge@sirf.com | - | 43.059, 44.031, 48.008, 49.031 |  |  |  |  | Tue 01/02/05 | Wed 02/07/08
4827 | 14025 | CT4 aspects for LCS UEPos-LBS | LCS3-UEPos-LBS | 2 | Rel-7 | C4 | 2006-01-02 08:00 | 2006-12-01 17:00 | 100% | CP-050240 | - | SiRF | brodilitz@sirf.com | - | 24.030, 24.080, 29.002 |  |  |  |  | Mon 20/06/05 | Wed 02/07/08
4828 | 20042 | UE positioning - Velocity | LCS3-UEPos-Velocity | 2 | Rel-7 | R2 | 2005-03-15 08:00 | 2006-09-15 17:00 | 100% | RP-050300 | RP-060459 | SiRF | BRodilitz@SiRF.com | - | 25.305, 25.331, 25.410, 25.413, 25.453 |  |  |  |  | Mon 20/06/05 | Wed 02/07/08
4829 | 20012 | Inclusion of Uplink TDOA UE positioning method in the UTRAN specifications | LCS3-UEPos-UTDOA | 2 | Rel-7 | R2 | 2004-09-15 08:00 | 2007-12-17 17:00 | 100% | RP-040387 | RP-070797 | TruePosition | Robert Gross (rgross@polariswireless.com) | - | 25.305, 25.453, new TS 25.111 |  |  |  |  | Mon 27/09/04 | Wed 02/07/08
4830 | 31052 | LCS for 3GPP Interworking WLAN | LCS3-IWLAN | 2 | Rel-7 | S1,S2 | 2004-06-28 08:00 | 2007-03-02 17:00 | 100% | SP-060291 | - | Telcordia | Mike Loushine | - | - |  |  |  |  | Mon 30/08/04 | Tue 31/08/10
4831 | 32077 | FS on 3GPP system to WLAN Interworking with LCS | LCS3-IWLAN-FSs1 | 3 | Rel-7 | S1 | 2004-06-28 08:00 | 2006-06-30 17:00 | 100% | SP-060291 | - | Telcordia | Mike Loushine | - | new TR 22.935 |  |  |  |  | Mon 30/08/04 | Tue 31/08/10
4832 | 32108 | Deleted - Study of work on an LCS architecture for I-WLAN. | LCS3-IWLAN-FSs2 | 3 | Rel-7 | S2 | 2006-06-26 08:00 | 2007-03-02 17:00 | 100% | SP-060291 | - | LG Electronics | dhshim@lge.com ; phede@lge.com | SP#41 TR withdrawn. All work transferred to specs | 23.837 |  |  | SP-35 |  | Thu 16/02/06 | Wed 02/07/08
4833 | 340007 | Stage 2 for LCS architecture for I-WLAN | LCS3-IWLAN | 3 | Rel-7 | S2 | 2006-10-23 08:00 | 2007-03-02 17:00 | 100% | SP-060818 | - | LG Electronics | dhshim@lge.com ; phede@lge.com | - | 23.234, 23.271, 23.167 | 34 |  |  |  | Thu 16/02/06 | Mon 15/08/11
4834 | 20030 | Deleted - UE positioning Rel-7 | LCS3-UEpos | 2 | Rel-7 | RP | 2004-09-15 08:00 | 2007-12-17 17:00 | 100% | - | - | - | - | - | - |  |  | RP-38 |  | Tue 04/01/05 | Wed 25/06/08
4835 | 31084 | MBMS Enhancements | MBMSE | 1 | Rel-7 | S1,R1,C3 | 2005-07-11 08:00 | 2007-11-30 17:00 | 100% | SP-050389 | - | China Mobile | liuhongyfw@chinamobile.com | - | - | 35 |  |  |  | Mon 20/06/05 | Wed 25/06/08
4836 | 340041 | Stage 1 of MBMSE | MBMSE | 2 | Rel-7 | S1 | 2005-07-11 08:00 | 2005-12-08 17:00 | 100% | SP-050389 | - | China Mobile | liuhongyfw@chinamobile.com | - | 22.146, 22.246, 22.228 | 34 |  |  |  | Mon 20/06/05 | Tue 15/04/08
4837 | 340042 | MBMS FDD Physical layer Enhancements | MBMSE-RANPhysFDD | 2 | Rel-7 | R1 | 2006-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-070226 | RP-070290 | Ericsson | Lars.Lindbom@ericsson.com | - | 25.211, 25.212, 25.213, 25.101, 25.104, 25.331, 25.433, 25.346, 25.306 | 34 |  |  |  | Mon 21/11/05 | Wed 25/06/08
4838 | 340043 | MBMS TDD Physical layer Enhancements | MBMSE-RANPhysTDD | 2 | Rel-7 | R1 | 2006-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-070241 | RP-070291 | IPWireless | Nicholas Anderson | - | 25.346, 25.221, 25.222, 25.223, 25.224, 25.306, 25.331, 25.402, 25.433, 25.102, 25.105, 25.123 | 34 |  |  |  | Mon 21/11/05 | Wed 25/06/08
4839 | 350022 | MBMS Low Chip Rate TDD Physical Layer Enhancement | MBMSE-RANPhysLCRTDD | 2 | Rel-7 | R1 | 2007-03-16 08:00 | 2007-09-10 17:00 | 100% | RP-070253 | RP-070292 | RITT | Lin Hui | - | 25.346, 25.221, 25.222, 25.223, 25.224, 25.306, 25.331, 25.402, 25.433, 25.102, 25.105, 25.123 | 35 |  |  |  | Mon 02/04/07 | Wed 25/06/08
4840 | 340046 | MBMS Mz interface | MBMSMz | 2 | Rel-7 | C3 | 2006-12-04 08:00 | 2007-11-30 17:00 | 100% | CP-070109 | - | Huawei | Deng Tingting (ttdeng@huawei.com) | - | 29.061 | 34 |  |  |  | Thu 08/03/07 | Mon 21/07/08
4841 | 400058 | MBMS - UE Conformance Testing | MBMSE_UEConTest | 1 | Rel-7 | R5 | 2007-06-01 08:00 | 2009-12-04 17:00 | 100% | - | - | - | - | Linked to Rel-7 Feature UID_31084 (MBMSE) | - | 40 | 21 |  |  | Tue 11/03/08 | Wed 01/04/09
4842 | 25049 | Conformance Test Aspects – MBMS TDD Physical layer Enhancements – MBSFN for HCR and VHCR TDD | MBMSE-RANPhysTDD_UEConTest | 2 | Rel-7 | R5 | 2007-06-01 08:00 | 2008-09-12 17:00 | 100% | RP-080155 | RP-080541 | IPWireless | tspeight@ipwireless.com | RP#41 completed | 34.108, 34.122, 34.123-1/2/3 |  |  |  |  | Tue 11/03/08 | Tue 09/09/08
4843 | 400059 | Conformance Test Aspects – MBMS LCR TDD Physical Layer Enhancement | MBMSE-RANPhysLCRTDD_UEConTest | 2 | Rel-7 | R5 | 2008-05-30 08:00 | 2009-09-18 17:00 | 100% | RP-080318 | RP-090715 | CATT | chenxiaozhong@datangmobile.cn | RP#45 completed | 34.108, 34.123-1 | 40 | 21 |  |  | Tue 03/06/08 | Fri 11/09/09
4844 | 400060 | Conformance Test Aspects – MBSFN for FDD | MBMSE-UEConTest_RANPhysFDD | 2 | Rel-7 | R5 | 2008-05-30 08:00 | 2009-12-04 17:00 | 100% | RP-080336 | RP-091214 | Huawei | Xiang Li (trica_li@huawei.com) | RP#46 completed | 34.108, 34.109, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 | 40 | 21 |  |  | Tue 03/06/08 | Thu 26/11/09
4845 | 34038 | MBMS User Service Extensions | MBMSUSE | 1 | Rel-7 | S4 | 2005-12-07 08:00 | 2007-06-07 17:00 | 100% | SP-050838 | - | Ericsson | Thorsten.Lohmar@ericsson.com | - | 26.346, 26.946 |  |  |  |  | Tue 13/12/05 | Tue 29/05/07
4846 | 31051 | Advanced Global Navigation Satellite System (AGNSS) concept | LCS3-AGNSS | 1 | Rel-7 | S1,S2,GP,R2 | 2004-06-28 08:00 | 2007-08-31 17:00 | 100% | SP-040681 | - | Alcatel | Michel.monnerat@thalesaleniaspace.com | - | - |  |  |  |  | Mon 30/08/04 | Wed 25/06/08
4847 | 50551 | Stage 1/2 for Towards AGNSS Concept | AGNSS | 2 | Rel-7 | S1,S2 | 2007-02-16 08:00 | 2007-02-16 17:00 | 100% | SP-040681 | - | Alcatel | richard.couty@space.alcatel.fr | - | 22.071, 23.271 |  |  |  |  | Mon 21/05/12 | Mon 21/05/12
4848 | 50548 | Towards AGNSS Concept | AGNSS-GP | 2 | Rel-7 | GP | 2004-06-28 08:00 | 2007-08-31 17:00 | 100% | GP-042677 | - | Alcatel | richard.couty@space.alcatel.fr | GP#36 completed | 43.030, 43.059, 44.031, 44.035, 44.071, 48.008, 48.018, 48.031, 49.031 |  |  |  |  | Mon 30/08/04 | Mon 21/05/12
4849 | 20050 | Global Navigation Satellite System (GNSS) in UTRAN | LCS3-GNSS-UTRAN | 2 | Rel-7 | R2 | 2005-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-060211 | RP-070482 | France Telecom | alain.abinakhoul@francetelecom.com | - | 25.305, 25.331, 25.306, 25.413, 25.423, 25.433, 25.453, 25.302, 25.215, 25.401, 25.402, 25.450, 25.452 |  |  |  |  | Thu 15/12/05 | Wed 25/06/08
4850 | 50581 | A-GPS Minimum Performance | GAGR | 1 | Rel-7 | G1,G3 | 2006-04-28 08:00 | 2007-08-31 17:00 | 100% | GP-060834 | - | Spirent | richard.catmur@spirentcom.com | - | 45.005, 51.010 |  |  |  |  | Wed 03/05/06 | Wed 12/09/07
4851 | 31048 | Unstructured Supplementary Service Data (USSD) message delivery and transfer to USIM | USSD-USIM | 1 | Rel-7 | S1,C6 | 2004-03-05 08:00 | 2005-08-12 17:00 | 100% | SP-040104 | - | Axalto | Christophe Dubois (cdubois@axalto.com) | - | - |  |  |  |  | Tue 08/06/04 | Wed 10/09/08
4852 | 31060 | Stage 1 for USSD message delivery and transfer to USIM | USSD-USIM | 2 | Rel-7 | S1 | 2004-03-18 08:00 | 2004-10-15 17:00 | 100% | SP-040104 | - | Axalto | Christophe Dubois (cdubois@axalto.com) | - | 22.090 |  |  |  |  | Tue 08/06/04 | Wed 10/09/08
4853 | 43008 | Alignment with requirements regarding USSD usage | USSD-USIM | 2 | Rel-7 | C6 | 2004-03-05 08:00 | 2005-08-12 17:00 | 100% | TP-040069 | - | Axalto | Christophe Dubois (cdubois@axalto.com) | - | 31.111, 31.115, 31.130 |  |  |  |  | Thu 02/09/04 | Thu 01/09/11
4854 | 31063 | Combinational Services | CSICS | 1 | Rel-7 | S1,S2,C1,S4 | 2005-01-17 08:00 | 2006-03-06 17:00 | 100% | SP-050228 | - | TeliaSonera | Robert.Frank@teliasonera.com | - | - |  |  |  |  | Fri 17/12/04 | Wed 02/07/08
4855 | 31064 | Stage 1 for CSICS | CSICS | 2 | Rel-7 | S1 | 2005-01-17 08:00 | 2005-06-09 17:00 | 100% | SP-050228 | - | TeliaSonera | Robert.Frank@teliasonera.com | - | 22.279 |  |  |  |  | Mon 28/02/05 | Wed 02/07/08
4856 | 32084 | Stage 2 for CSICS | CSICS | 2 | Rel-7 | S2 | 2005-01-17 08:00 | 2005-07-15 17:00 | 100% | SP-050228 | - | TeliaSonera | Robert.Frank@teliasonera.com | - | 23.279 |  |  |  |  | Tue 07/06/05 | Wed 02/07/08
4857 | 11054 | Stage 3 for CSICS CN aspects | CSICS | 2 | Rel-7 | C1 | 2005-05-02 08:00 | 2006-03-06 17:00 | 100% | CP-060105 | - | Vodafone | peter.dawes@vodafone.com | - | 24.879, 24.279, 24.229, 24.008 |  |  |  |  | Tue 22/03/05 | Wed 02/07/08
4858 | 34031 | Stage 3 for codec aspects | CSICS-Codec | 2 | Rel-7 | S4 | 2005-03-15 08:00 | 2005-12-07 17:00 | 100% | SP-050091 | - | Ericsson | Per.Frojdh@ericsson.com | - | 26.141, 26.235 |  |  |  |  | Tue 22/03/05 | Wed 02/07/08
4859 | 31065 | CAMEL Trunk Triggers | TTCAMEL | 1 | Rel-7 | S1,C4 | 2004-12-17 13:00 | 2005-12-05 12:00 | 100% | SP-040743 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | - | - |  |  |  |  | Fri 17/12/04 | Fri 18/07/08
4860 | 31066 | Stage 1 for CAMEL Trunk Triggers | TTCAMEL | 2 | Rel-7 | S1 | 2004-12-17 13:00 | 2005-12-05 12:00 | 100% | SP-040743 | - | Nortel | Amar Deol (deola@nortelnetworks.com) | - | 22.078 |  |  |  |  | Fri 17/12/04 | Fri 18/07/08
4861 | 14017 | CAMEL Trunk Originated Trigger Detection Points | CamelR7 | 2 | Rel-7 | C4 | 2004-12-17 13:00 | 2005-12-05 12:00 | 100% | NP-040550 | - | Nortel | David Hutton (dhutton@nortel.com) | - | - |  |  |  |  | Fri 17/12/04 | Fri 18/07/08
4862 | 31088 | IMS Service Brokering enhancements | ISB | 1 | Rel-7 | S1 | 2005-12-07 08:00 | 2006-03-13 17:00 | 100% | SP-050830 | - | Telcordia | jbakker@telcordia.com | No CR submitted in rel-8 (according to CR database). | 22.228 | 32 |  |  |  | Fri 04/11/05 | Tue 25/03/08
4863 | 320027 | Stage 1 for ISB | ISB-s1 | 2 | Rel-7 | S1 | 2005-12-07 08:00 | 2006-03-13 17:00 | 100% | SP-050830 | - | Telcordia | jbakker@telcordia.com | No Rel-8 changes | 22.228 | 32 |  |  |  | Fri 04/11/05 | Tue 25/03/08
4864 | 11045 | Enhancements of VGCS for public authority officials | EVGCS | 1 | Rel-7 | S1,C1,C4,G2 | 2004-08-27 08:00 | 2007-06-15 17:00 | 100% | SP-040304 | - | - | - | Moved from Rel-6 UID_50563 Enhancements of VGCS in public networks for communication of public authority officials | 43.068, 44.068, 24.008, 29.002 | 75 | 38 |  |  | Fri 03/09/04 | Mon 17/07/06
4865 | 31061 | Stage 1 for Enhancements of VGCS for public authority officials | EVGCS | 2 | Rel-7 | S1 | 2004-08-27 08:00 | 2004-08-27 08:00 | 100% | SP-040304 | - | Siemens | joerg.swetina@neclab.eu | Voice Group Call Service | 42.068, 43.068 |  |  |  |  | Mon 30/08/04 | Tue 19/09/06
4866 | 11056 | Architecture and protocol aspects | EVGCS | 2 | Rel-7 | C1,C4 | 2004-08-27 08:00 | 2007-06-15 17:00 | 100% | CP-050528 | - | Siemens | robert.zaus@nsn.com | - | 43.068, 44.068 |  |  |  |  | Wed 14/09/05 | Thu 09/03/06
4867 | 11062 | CT1 aspects of EVGCS | EVGCS | 3 | Rel-7 | C1 | 2004-08-27 08:00 | 2007-06-15 17:00 | 100% | CP-050528 | - | Siemens | robert.zaus@nsn.com | - | 43.068, 44.068, 24.008 |  |  |  |  | Wed 14/09/05 | Wed 12/09/07
4868 | 14022 | CT4 aspects of EVGCS | EVGCS | 3 | Rel-7 | C4 | 2004-08-27 08:00 | 2006-03-10 17:00 | 100% | CP-050528 | - | Siemens | robert.zaus@nsn.com | - | 29.002 |  |  |  |  | Wed 14/09/05 | Thu 08/03/07
4869 | 752076 | GERAN2 aspects of EVGCS | EVGCS | 2 | Rel-7 | G2 | 2004-08-27 08:00 | 2007-02-16 17:00 | 100% | GP-071855 | - | Siemens | kenneth.isaacs@roke.co.uk | - | - | 75 | 38 |  |  | Fri 15/10/04 | Thu 08/03/07
4870 | 11055 | Improvements of VGCS for parallel use of services | IVGCS | 1 | Rel-7 | S1 | 2005-03-15 08:00 | 2007-03-15 17:00 | 100% | SP-070167 | - | - | - | Voice Group Call Service | - |  |  |  |  | Wed 02/03/05 | Mon 26/03/07
4871 | 31070 | Service Requirements for VGCS improvements | IVGCS | 2 | Rel-7 | S1 | 2005-03-15 08:00 | 2005-06-08 17:00 | 100% | SP-070167 | - | T-Mobile | kurt.bischinger@t-mobile.at | - | 42.068 |  |  |  |  | Tue 22/03/05 | Thu 29/03/07
4872 | 32090 | Stage 2 modifications for VGCS improvements | IVGCS | 2 | Rel-7 | C1 | 2005-12-01 08:00 | 2007-03-14 17:00 | 100% | NP-050141 | - | T-Mobile | kurt.bischinger@t-mobile.at | - | 43.068 |  |  |  |  | Tue 22/03/05 | Thu 08/03/07
4873 | 11057 | Protocol aspects | IVGCS | 2 | Rel-7 | C1 | 2005-12-01 08:00 | 2007-03-15 17:00 | 100% | NP-050141 | - | T-Mobile | Dieter Jacobsohn | Previous name (before CT32) was Architecture and protocol aspects | 44.068 |  |  |  |  | Wed 14/09/05 | Wed 31/05/06
4874 | 11063 | CT1 aspects of IVGCS | IVGCS | 3 | Rel-7 | C1 | 2005-12-01 08:00 | 2007-03-15 17:00 | 100% | CP-070118 | - | T-Mobile | - | - | 43.068, 44.068 |  |  |  |  | Wed 14/09/05 | Wed 12/09/07
4875 | 14023 | Deleted - CT4 aspects of IVGCS | IVGCS-St3-c4 | 3 | Rel-7 | C4 | 2007-03-09 17:00 | 2007-03-09 17:00 | 100% | NP-050141 | - | T-mobile | - | CT4#33 stage 2 solution is still open. | 29.002 |  |  | CP-35 |  | Wed 14/09/05 | Thu 29/03/07
4876 | 31071 | Open Service Access (OSA) Rel-7 | OSA7 | 1 | Rel-7 | S1,C5 | 2005-03-15 08:00 | 2007-06-08 17:00 | 100% | SP-050183 | - | AePONA | eamonn.murray@aepona.com | - | - |  |  |  |  | Tue 22/03/05 | Thu 15/09/05
4877 | 31172 | OSA Service Broker | OSA7-SB | 2 | Rel-7 | S1,C5 | 2005-03-15 08:00 | 2006-12-01 17:00 | 100% | SP-050183 | - | AePONA | eamonn.murray@aepona.com | - | - |  |  |  |  | Tue 22/03/05 | Thu 16/02/06
4878 | 31072 | Service Requirements for OSA Service Broker | OSA7 | 3 | Rel-7 | S1 | 2005-03-15 08:00 | 2005-06-08 17:00 | 100% | SP-050183 | - | AePONA | eamonn.murray@aepona.com | - | 22.127 |  |  |  |  | Tue 22/03/05 | Thu 16/02/06
4879 | 43011 | Stage 2 OSA API Service Brokering | OSA7 | 3 | Rel-7 | C5 | 2006-04-28 08:00 | 2006-12-01 17:00 | 100% | CP-070200 | - | AePONA | damian.oneill@aepona.com | - | 23.198 |  |  |  |  | Tue 22/03/05 | Thu 26/07/12
4880 | 7017 | Stage 3 OSA API Service Brokering | OSA7 | 3 | Rel-7 | C5 | 2006-04-28 08:00 | 2006-12-01 17:00 | 100% | CP-070200 | - | AePONA | damian.oneill@aepona.com | - | 29.198-16 |  |  |  |  | Wed 01/03/06 | Thu 26/07/12
4881 | 15039 | Rel-7 OSA Stage 2/3 enhancements | OSA7 | 2 | Rel-7 | C5 | 2006-04-28 08:00 | 2007-06-08 17:00 | 100% | CP-070200 | - | AePONA | damian.oneill@aepona.com | CP#34 updated WID CP-060607=>CP-070200 | 29.198/9, 23.198 |  |  |  |  | Wed 14/12/05 | Thu 26/07/12
4882 | 7018 | Parlay X Message Broadcast Web Service | OSA7 | 3 | Rel-7 | C5 | 2006-04-28 08:00 | 2006-12-01 17:00 | 100% | CP-070200 | - | ETRI | - | - | 29.199-15, 23.198 |  |  |  |  | Wed 01/03/06 | Thu 26/07/12
4883 | 7019 | Parlay X Geocoding Web Service | OSA7 | 3 | Rel-7 | C5 | 2006-04-28 08:00 | 2006-12-01 17:00 | 100% | CP-070200 | - | ETRI | - | - | 29.199-16, 23.198 |  |  |  |  | Wed 01/03/06 | Thu 26/07/12
4884 | 7020 | Parlay X Application driven QoS Web Service | OSA7 | 3 | Rel-7 | C5 | 2006-04-28 08:00 | 2007-03-09 17:00 | 100% | CP-070200 | - | BT | - | - | 29.199-17, 23.198 |  |  |  |  | Wed 01/03/06 | Thu 26/07/12
4885 | 340001 | Parlay-X Device Capabilities and Configuration | OSA7 | 3 | Rel-7 | C5 | 2006-10-26 08:00 | 2007-06-08 17:00 | 100% | CP-070200 | - | Telenor | - | - | 29.199-18, 23.198 | 34 |  |  |  | Thu 26/10/06 | Thu 26/07/12
4886 | 340002 | Parlay-X Multimedia Streaming Session Management Web Service | OSA7 | 3 | Rel-7 | C5 | 2006-10-26 08:00 | 2007-03-09 17:00 | 100% | CP-070200 | - | Telenor | - | - | 29.199-19, 23.198 | 34 |  |  |  | Thu 26/10/06 | Thu 26/07/12
4887 | 340003 | Parlay-X Multimedia Multicast Control Web Service | OSA7 | 3 | Rel-7 | C5 | 2006-10-26 08:00 | 2007-03-09 17:00 | 100% | CP-070200 | - | ETRI | - | - | 29.199-20, 23.198 | 34 |  |  |  | Thu 26/10/06 | Thu 26/07/12
4888 | 340004 | OSA API Conference Call Control SCF | OSA7 | 3 | Rel-7 | C5 | 2006-10-26 08:00 | 2007-03-09 17:00 | 100% | CP-070200 | - | Ericsson | - | - | 29.198-04-5, 23.198 | 34 |  |  |  | Thu 26/10/06 | Thu 26/07/12
4889 | 31053 | Selective Disabling of UE Capabilities | SDoUE | 1 | Rel-7 | S1,S2,C1 | 2005-01-24 14:07 | 2007-06-15 17:00 | 100% | SP-050182 | - | Motorola | - | Moved from FS section Feb 06 | - |  |  |  |  | Mon 30/08/04 | Thu 17/07/08
4890 | 32088 | Stage 1 of SDoUE | SDoUE-CR | 2 | Rel-7 | S1 | 2005-01-24 14:07 | 2006-12-08 17:00 | 100% | SP-050182 | - | Motorola | - | Moved from FS section Feb 06 | 22.011 |  |  |  |  | Mon 30/08/04 | Thu 17/07/08
4891 | 32089 | Deleted - TR on different possible architectures | SDoUE-FS | 2 | Rel-7 | S2 | 2005-03-21 08:00 | 2005-12-16 17:00 | 100% | SP-050182 | - | Vodafone | Gavin.Wong@vodafone.com | Moved from FS section Feb 06. Abandoned at SP-30 | 23.805 abandonned at SP-30; descendant C1 24.305 |  |  | SP-30 |  | Tue 07/06/05 | Thu 17/07/08
4892 | 7036 | Stage 3 of SDoUE | SDoUE | 2 | Rel-7 | C1 | 2006-03-10 08:00 | 2007-06-15 17:00 | 100% | CP-070121 | - | Ericsson | christian.herrero@ericsson.com | - | 24.305 |  |  |  |  | Wed 22/03/06 | Thu 17/07/08
4893 | 7041 | Network selection enhancements (NSP) | NSP | 1 | Rel-7 | S1 | 2006-03-15 08:00 | 2007-06-15 17:00 | 100% | SP-060220 | - | O2 | chris.friel@O2.com | - | - | 32 |  |  |  | Fri 04/11/05 | Wed 22/03/06
4894 | 320012 | Stage 1 of NSP | NSP-TS | 2 | Rel-7 | S1 | 2006-03-15 08:00 | 2006-12-06 17:00 | 100% | SP-060220 | - | O2 | chris.friel@O2.com | - | 22.101, 22.011, 23.122, 24.008, 25.304, 31.102, 45.008 | 32 |  |  |  | Mon 17/07/06 | Tue 15/04/08
4895 | 320013 | Procedural aspects of NSP | NSP-CR | 2 | Rel-7 | C1 | 2006-06-02 08:00 | 2007-06-15 17:00 | 100% | CP-060357 | - | Motorola | Andrew Howell | - | 23.122, 24.008, 31.102 | 32 |  |  |  | Wed 21/06/06 | Fri 04/05/07
4896 | 25048 | Network selection enhancements (NSP) - UE Conformance Testing | NSP-CR_UEConTest | 1 | Rel-7 | R5 | 2007-06-01 08:00 | 2008-12-05 17:00 | 100% | RP-080135 | RP-080819 | Nokia | jarkko.hellsten@nokia.com | RP#42 completed. Testing for Feature UID_7041 (NSP-CR) | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Tue 21/03/06 | Tue 09/12/08
4897 | 32064 | Access Class Barring and Overload Protection | ACBOP | 1 | Rel-7 | S2,C1 | 2004-03-15 08:00 | 2006-09-08 17:00 | 100% | SP-040338 | - | Vodafone | chris.pudney@vodafone.com | - | 23.898 |  |  |  |  | Wed 14/04/04 | Tue 15/07/08
4898 | 32065 | TR on Stage 2 | ACBOP | 2 | Rel-7 | S2 | 2004-03-15 08:00 | 2005-03-31 17:00 | 100% | SP-040338 | - | NTT DoCoMo | Jean-Jacques Davidian (davidian@docomo.fr) | - | 23.898 |  |  |  |  | Wed 14/04/04 | Tue 15/07/08
4899 | 11048 | Stage 3 CN aspects of ACBOP | ACBOP | 2 | Rel-7 | C1 | 2005-06-06 08:00 | 2006-01-31 17:00 | 100% | - | - | - | - | - | 24.008 |  |  |  |  | Thu 02/09/04 | Tue 15/07/08
4900 | 20010 | Deleted - Potential impact on Iu interface Overload functionality | ACBOP | 2 | Rel-7 | RP | 2004-03-15 08:00 | 2004-03-15 08:00 | 100% | - | - | - | - | - | 25.413 |  |  | RP-25 |  | Wed 14/04/04 | Wed 13/10/04
4901 | 20009 | Deleted - Extra ACBOP information in RAN | ACBOP | 2 | Rel-7 | RP | 2004-03-15 08:00 | 2004-03-15 08:00 | 100% | - | - | - | - | - | 25.331 |  |  | RP-25 |  | Wed 14/04/04 | Wed 13/10/04
4902 | 50117 | Deleted - Extra ACBOP information in GERAN | ACBOP | 2 | Rel-7 | GP | 2006-09-08 17:00 | 2006-09-08 17:00 | 100% | - | - | - | - | - | 44.018 |  |  | RP-33 |  | Wed 14/04/04 | Thu 20/07/06
4903 | 32074 | System enhancements for Fixed Broadband access to IMS | FBI | 1 | Rel-7 | S2,S3,S5,C1,C3,C4,IETF | 2003-11-05 08:00 | 2011-12-09 17:00 | 100% | SP-060145 | - | - | - | - | - |  |  |  |  | Mon 09/06/03 | Thu 21/10/04
4904 | 7001 | TISPAN Rel 1 related aspects | FBI-TIS1 | 2 | Rel-7 | S2,S3,C1,C3,C4,IETF | 2003-11-05 08:00 | 2011-12-09 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/02/06 | Thu 16/02/06
4905 | 32075 | Stage 2 of FBI for TISPAN R1 | - | 3 | Rel-7 | S2 | 2004-10-14 08:00 | 2006-03-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/02/06 | Wed 31/05/06
4906 | 11050 | Protocol impact of FBI for TISPAN R1 | - | 3 | Rel-7 | S3,C1,C3,C4,IETF | 2003-11-05 08:00 | 2011-12-09 17:00 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | - | - |  |  |  |  | Fri 03/09/04 | Thu 16/02/06
4907 | 521031 | (IETF) CT aspects of FBI for TISPAN R1 | - | 4 | Rel-7 | C1-IETF,C3-IETF | 2003-11-05 08:00 | 2011-12-09 17:00 | 100% | NP-040618 | - | Roland Jesske | - | CP#54 completed | RFC 6432 (was draft-jesske-dispatch-update3326-reason-responses) | 52 | 27 |  |  | Mon 20/06/11 | Tue 13/12/11
4908 | 11060 | CT1 aspects of FBI for TISPAN R1 | - | 4 | Rel-7 | C1 | 2003-11-05 08:00 | 2006-11-30 17:00 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | - | 24.819, 24.229 |  |  |  |  | Fri 03/09/04 | Fri 05/01/07
4909 | 13025 | CT3 aspects of FBI for TISPAN R1 | - | 4 | Rel-7 | C3 | 2003-11-05 08:00 | 2006-12-08 17:00 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | - | 29.163, 29.209 |  |  |  |  | Fri 03/09/04 | Thu 12/10/06
4910 | 14020 | CT4 aspects of FBI for TISPAN R1 | FBI-TIS1-st3-c4 | 4 | Rel-7 | C4 | 2006-01-13 08:00 | 2007-03-09 17:00 | 100% | NP-040618 | - | Siemens | peter.leis@nsn.com | CT4#32: a set of CRs on FBI for cable labs | 29.229 |  |  |  |  | Fri 03/09/04 | Thu 08/03/07
4911 | 33027 | Security Enhancements for FBI | FBI-ISE | 3 | Rel-7 | S3 | 2005-06-28 08:00 | 2005-12-08 17:00 | 100% | SP-050395 | - | Ericsson | Bengt.Sahlin@ericsson.com | Duplicated entry ("ACCSEC2", "Access Security Enhancements", SP-040865) deleted by A.Sultan | 33.203 |  |  |  |  | Mon 20/06/05 | Tue 29/05/07
4912 | 7002 | PacketCable Related aspects | FBI-PCBL | 2 | Rel-7 | S2,S5,C1 | 2006-02-01 08:00 | 2007-03-14 17:00 | 100% | SP-060145 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | - | - |  |  |  |  | Thu 16/02/06 | Thu 16/02/06
4913 | 7003 | Stage 1,2 of FBI for PacketCable | - | 3 | Rel-7 | S2 | 2006-02-01 08:00 | 2006-12-15 17:00 | 100% | SP-060145 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | - | 22.228, 23.228 |  |  |  |  | Thu 16/02/06 | Tue 19/09/06
4914 | 7004 | Protocol impact of FBI for PacketCable | - | 3 | Rel-7 | C1 | 2006-05-01 08:00 | 2007-03-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/02/06 | Thu 08/03/07
4915 | 7032 | SA5 Charging aspects of FBI for PacketCable | FBI-PCBL-CH | 3 | Rel-7 | S5 | 2006-03-31 08:00 | 2006-12-07 17:00 | 100% | SP-060145 | - | CableLabs | Bernie McKibben (b.mckibben@cablelabs.com) | 03/2006 SP#31 WID approved | 32.240, 32.260, 32.298, 32.299 |  |  |  |  | Mon 20/03/06 | Thu 29/03/07
4916 | 32081 | Support of SMS over generic 3GPP IP access | SMSIP | 1 | Rel-7 | S2,C4,C1 | 2004-10-14 08:00 | 2007-06-14 17:00 | 100% | SP-060658 | - | Huawei | zhangwenlin@huawei.com | SP#33 updated WID (removed MMS) | - |  |  |  |  | Thu 14/10/04 | Fri 18/07/08
4917 | 32094 | FS on SMSIP | - | 2 | Rel-7 | S2 | 2004-10-14 08:00 | 2005-06-13 17:00 | 100% | SP-060658 | - | Huawei | zhangwenlin@huawei.com | SP#33 updated WID | 23.804 |  |  |  |  | Tue 07/06/05 | Tue 15/07/08
4918 | 32095 | Stage 2 for SMSIP | - | 2 | Rel-7 | S2 | 2005-06-08 08:00 | 2006-09-15 17:00 | 100% | SP-060658 | - | Huawei | zhangwenlin@huawei.com | SP#33 updated WID | 23.204 |  |  |  |  | Tue 07/06/05 | Tue 15/07/08
4919 | 310001 | Stage 3 for SMSIP | SMSIP-St3 | 2 | Rel-7 | C4,C1 | 2005-06-08 08:00 | 2007-06-14 17:00 | 100% | CP-060697 | - | Nokia | jari.jansson@nokia.com | CP#34 updated WID | - |  |  |  |  | Thu 13/04/06 | Tue 15/07/08
4920 | 310002 | CT1 aspects for SMSIP | - | 3 | Rel-7 | C1 | 2005-06-08 08:00 | 2007-06-14 17:00 | 100% | CP-060697 | - | Nokia | jari.jansson@nokia.com | CP#34 updated WID | 23.040, 24.229 |  |  |  |  | Thu 13/04/06 | Tue 15/07/08
4921 | 310003 | CT4 aspects for SMSIP | SMSIP-St3-c4 | 3 | Rel-7 | C4 | 2005-06-08 08:00 | 2007-06-01 17:00 | 100% | CP-060697 | - | Nokia | jari.jansson@nokia.com | CP#34 updated WID | 23.008, 29.002 |  |  |  |  | Thu 13/04/06 | Tue 15/07/08
4922 | 32082 | Evolution of Policy Control and Charging | PCC | 1 | Rel-7 | S2,S5,C3,C1 | 2004-10-14 08:00 | 2007-11-30 17:00 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-29 approved WID. SP-31 updated WID adding SA5 charging. 23.125 will be discontinued from Rel-7. | - |  |  |  |  | Thu 14/10/04 | Fri 18/07/08
4923 | 32102 | Deleted - TR for PCC | - | 2 | Rel-7 | S2 | 2004-10-14 08:00 | 2005-12-29 17:00 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-30: S2 has no intention for TR completion | 23.803 |  |  | SP-33 |  | Fri 01/07/05 | Fri 18/07/08
4924 | 32103 | Stage 2 for PCC | - | 2 | Rel-7 | S2 | 2005-07-04 08:00 | 2006-09-15 17:00 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7. | 23.203 |  |  |  |  | Fri 01/07/05 | Fri 18/07/08
4925 | 32109 | Evolution of policy control and flow based bearer level charging | - | 2 | Rel-7 | S2 | 2006-08-01 08:00 | 2006-12-29 17:00 | 100% | SP-060217 | - | Nokia | balazs.bertenyi@nsn.com | SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7. | 23.207, 23.002, 23.228 |  |  |  |  | Fri 01/07/05 | Fri 18/07/08
4926 | 7033 | SA5 Charging aspects of PCC | PCC-CH | 2 | Rel-7 | S5 | 2006-03-31 08:00 | 2007-06-15 17:00 | 100% | SP-060217 | - | Orange | alain.bibas@orange-ft.com | SP-31 updated WID with SA5 charging. | 32.250, 32.251, 32.298, 32.299 |  |  |  |  | Mon 20/03/06 | Fri 18/07/08
4927 | 13029 | Gx reference point for Policy and Charging Control | PCC-Gx | 2 | Rel-7 | C3 | 2005-12-02 08:00 | 2007-11-30 17:00 | 100% | CP-060434 | - | Siemens | Thomas.Belling@nsn.com | - | 29.212 (not progressed to Rel-7: 29.210, 29.207, 29.208) |  |  |  |  | Tue 13/12/05 | Fri 18/07/08
4928 | 13030 | Rx reference point for PCC CT3 aspects | PCC-Rx | 2 | Rel-7 | C3,C1 | 2005-12-02 08:00 | 2007-11-30 17:00 | 100% | CP-060435 | - | Ericsson | j.javier.pastor@ericsson.com | WID approved at CP#30, Revised at CP#31, Revised at CP#33 | - |  |  |  |  | Tue 13/12/05 | Fri 18/07/08
4929 | 310006 | PCC-Rx CT3 aspects | PCC-Rx-c3 | 3 | Rel-7 | C3 | 2005-12-02 08:00 | 2007-11-30 17:00 | 100% | CP-060435 | - | Ericsson | j.javier.pastor@ericsson.com | - | 29.213, 29.214 (not progressed to Rel-7: 29.209, 29.211) |  |  |  |  | Tue 13/12/05 | Fri 18/07/08
4930 | 7008 | PCC-Rx CT1 aspects | PCC-Rx-Gx-c1 | 3 | Rel-7 | C1 | 2005-12-02 08:00 | 2007-06-15 17:00 | 100% | CP-060435 | - | Ericsson | j.javier.pastor@ericsson.com | - | 24.229 |  |  |  |  | Tue 13/12/05 | Fri 18/07/08
4931 | 32091 | Voice Call Continuity between CS and IMS (incl. I-WLAN) | VCC | 1 | Rel-7 | S2,S1,S5,C1,C4 | 2004-12-31 08:00 | 2007-06-15 17:00 | 100% | SP-060292 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | WID approved SP#27; updated SP#28; updated SP#32 | - |  |  |  |  | Tue 07/06/05 | Mon 21/07/08
4932 | 32104 | TR for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | S2 | 2004-12-31 08:00 | 2005-12-08 17:00 | 100% | SP-060292 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | 23.806 |  |  |  |  | Fri 01/07/05 | Mon 21/07/08
4933 | 31085 | Stage 1 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | S1 | 2005-03-17 08:00 | 2005-09-28 17:00 | 100% | SP-060292 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | 22.101 |  |  |  |  | Mon 19/09/05 | Mon 21/07/08
4934 | 32105 | Stage 2 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | S2 | 2005-09-06 08:00 | 2006-09-08 17:00 | 100% | SP-060292 | - | Alcatel-Lucent | andy.bennett@alcatel-lucent.com | - | 23.206 |  |  |  |  | Fri 01/07/05 | Mon 21/07/08
4935 | 35079 | SA5 Charging for Voice Call Continuity between CS and IMS (incl. I-WLAN) | VCC-CH | 2 | Rel-7 | S5 | 2006-03-17 08:00 | 2007-06-14 17:00 | 100% | SP-060292 | - | Orange | alain.bibas@orange-ft.com | 03/2006 SP#31 WID approved | 32.250, 32.260 |  |  |  |  | Mon 20/03/06 | Mon 21/07/08
4936 | 11058 | Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 2 | Rel-7 | C1,C4 | 2006-02-01 08:00 | 2007-06-15 17:00 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  |  |  | Tue 04/10/05 | Mon 21/07/08
4937 | 11066 | CT1 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 3 | Rel-7 | C1 | 2006-02-01 08:00 | 2007-06-15 17:00 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 24.206, 24.216 |  |  |  |  | Tue 04/10/05 | Mon 21/07/08
4938 | 14027 | CT4 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | VCC-St3-c4 | 3 | Rel-7 | C4 | 2006-06-09 08:00 | 2007-03-09 17:00 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 23.003 |  |  |  |  | Tue 04/10/05 | Mon 21/07/08
4939 | 13032 | Deleted - CT3 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN) | - | 3 | Rel-7 | C3 | 2006-11-02 08:00 | 2006-11-02 08:00 | 100% | CP-070186 | - | Alcatel-Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 29.163 |  |  | CP-33 |  | Tue 04/10/05 | Mon 21/07/08
4940 | 7046 | One Tunnel solution for optimization of Packet Data Traffic | OPTUNEL | 1 | Rel-7 | S2 | 2006-03-27 08:00 | 2007-10-31 17:00 | 100% | SP-060819 | - | Nokia | antti.j.pasanen@nokia.com | - | - | 32 |  |  |  | Wed 22/03/06 | Tue 15/07/08
4941 | 320002 | Deleted - Study on Stage 2 for One Tunnel solution | OPTUNEL-Study | 2 | Rel-7 | S2 | 2006-03-27 08:00 | 2006-09-15 17:00 | 100% | SP-060819 | - | Nokia | antti.j.pasanen@nokia.com | TR for Info SP-33. SP-34: S2 Report intention to discontinue TR | 23.809 | 32 |  | SP-34 |  | Mon 30/08/04 | Tue 15/07/08
4942 | 340013 | One Tunnel Deployment Guideline | OPTUNEL-Guide | 2 | Rel-7 | S2 | 2006-10-23 08:00 | 2007-10-31 17:00 | 100% | SP-060819 | - | Huawei | lan.liu@huawei.com | - | 23.919 | 34 |  |  |  | Mon 30/08/04 | Tue 15/07/08
4943 | 320003 | Stage 2 specification for One Tunnel solution | OPTUNEL-Stage2 | 2 | Rel-7 | S2 | 2006-09-11 08:00 | 2006-12-15 17:00 | 100% | SP-060819 | - | Nokia | antti.j.pasanen@nokia.com | - | 23.060 | 32 |  |  |  | Mon 30/08/04 | Tue 15/07/08
4944 | 320029 | CSI Terminating Session handling | CSItermS | 1 | Rel-7 | S2,C1 | 2006-06-08 08:00 | 2007-06-15 17:00 | 100% | SP-060437 | - | Samsung | Osok Song | Triggered by the abandoned Study UID_32117 | - | 32 |  |  |  | Wed 19/07/06 | Thu 17/07/08
4945 | 340014 | Stage 2 of CStermS | - | 2 | Rel-7 | S2 | 2006-06-08 08:00 | 2007-03-02 17:00 | 100% | SP-060437 | - | Samsung | Osok Song | - | 23.279 | 34 |  |  |  | Fri 05/01/07 | Thu 17/07/08
4946 | 340015 | Stage 3 of CStermS | - | 2 | Rel-7 | C1 | 2006-12-14 08:00 | 2007-06-15 17:00 | 100% | CP-070239 | - | Samsung | chenho.chin@samsung.com | CP-34 approved WID. CP-35 updated WID | 24.229, 24.279 | 34 |  |  |  | Fri 05/01/07 | Thu 17/07/08
4947 | 340011 | Deleted - duplicated with UID 340015 -Stage 3 CSI Terminating Session handling | - | 2 | Rel-7 | C1 | 2007-03-09 17:00 | 2007-03-09 17:00 | 100% | CP-060647 | - | Samsung | chenho.chin@samsung.com | CP-34 approved WID | 24.229, 24.179, 24.279 | 34 |  | CP-34 |  | Mon 18/12/06 | Thu 17/07/08
4948 | 33022 | Liberty Alliance and 3GPP Security Interworking | LibSec | 1 | Rel-7 | S3 | 2005-03-10 08:00 | 2006-11-30 17:00 | 100% | SP-050145 | - | Nokia | Silke.Holtmanns@nokia.com | WID approved SP#27. | 33.980 |  |  |  |  | Thu 24/03/05 | Wed 16/07/08
4949 | 33023 | Trust Requirements for Open Platforms in 3GPP | TrustOP | 1 | Rel-7 | S3 | 2005-01-03 08:00 | 2006-11-30 17:00 | 100% | SP-040863 | - | Nokia | Silke.Holtmanns@nokia.com | WID approved SP#26. | 33.905 |  |  |  |  | Thu 24/03/05 | Wed 16/07/08
4950 | 33024 | Development of UEA2 and UIA2 | AlgUEA2 | 1 | Rel-7 | S3 | 2004-12-01 08:00 | 2005-12-09 17:00 | 100% | SP-040864 | - | TeliaSonera | per.christoffersson@teliasonera.com | WID approved SP#26, Dependant on Funding Availability. | 35.919, 35.215, 35.216, 35.217, 35.218 |  |  |  |  | Thu 24/03/05 | Wed 16/07/08
4951 | 33026 | Lawful Interception in the 3GPP Rel-7 architecture | LI-7A | 1 | Rel-7 | S3 | 2005-06-28 08:00 | 2005-12-08 17:00 | 100% | SP-050237 | - | BMWI | berthold.wilhelm@regtp.de | - | 33.106, 33.107, 33.108 |  |  |  |  | Mon 20/06/05 | Wed 16/07/08
4952 | 33028 | Key establishment between a UICC and a terminal | KeyEstUTerm | 1 | Rel-7 | S3 | 2005-12-07 08:00 | 2006-09-28 17:00 | 100% | SP-050780 | - | Gemalto | mireille.pauliac@gemplus.com | - | 33.110 |  |  |  |  | Mon 12/12/05 | Thu 10/01/08
4953 | 330008 | NDS Authentication Framework Extension for Transport Layer Security | NDSAFTLS | 1 | Rel-7 | S3 | 2006-09-28 08:00 | 2006-12-06 17:00 | 100% | SP-060507 | - | Nokia | tiina.s.koskinen@nokia.com | TLS profile is moved to Rel-8 | 33.310 |  |  |  |  | Fri 06/10/06 | Wed 16/07/08
4954 | 732030 | Security enhancements | SEC7 | 1 | Rel-7 | S3,C1,C4 | 2005-09-12 08:00 | 2006-11-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
4955 | 732031 | HTTPS connection between a UICC and a NAF | SEC7-HSUN | 2 | Rel-7 | S3,C1 | 2005-09-12 08:00 | 2005-09-12 17:00 | 100% | SP-050573 | - | Gemalto | JSeif@axalto.com, mireille.pauliac@gemplus.com | - | 33.918, 33.222, 24.109 |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
4956 | 732032 | 2G GBA: 2G SIM usage in 3GPP GAA framework | SEC7-2GGBA | 2 | Rel-7 | S3 | 2005-09-12 08:00 | 2005-12-05 17:00 | 100% | SP-050576 | - | Nokia | Silke.Holtmanns@nokia.com | - | 33.920, 33.220 |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
4957 | 732033 | Generic Authentication Architecture usage extensions and optimizations | SEC7-GAA2 | 2 | Rel-7 | S3 | 2005-09-12 08:00 | 2006-11-30 17:00 | 100% | SP-060429 | - | Nokia | Silke.Holtmanns@nokia.com | 33.223 goes to R8 | 33.220, 29.109, 24.109, (33.223 goes to R8) |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
4958 | 32034 | SS7 TCAP security Gateway | SEC7-NDS-TCAPsec | 2 | Rel-7 | S3,C4 | 2005-09-12 08:00 | 2006-08-14 17:00 | 100% | SP-050579 | - | Siemens | marc.blommaert.ext@nsn.com | - | - |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
4959 | 310004 | SA3 aspects of SEC7-NDS-TCAPsec | SEC7-NDS-TCAPsec-SA3 | 3 | Rel-7 | S3 | 2005-09-12 08:00 | 2006-03-10 17:00 | 100% | SP-050579 | - | Siemens | marc.blommaert.ext@nsn.com | - | 33.204 |  |  |  |  | Fri 04/11/05 | Wed 16/07/08
4960 | 310005 | TCAPsec Gateway | SEC7-TCAP | 3 | Rel-7 | C4 | 2006-04-03 08:00 | 2006-08-14 17:00 | 100% | CP-060170 | - | Siemens | Ulrich.wiehe@gksag.de | - | 29.204, 29.002 |  |  |  |  | Fri 07/10/05 | Wed 16/07/08
4961 | 711052 | IMS Stage 3 IETF Protocol Alignment | IMSProtoc | 1 | Rel-7 | C1 | 2004-12-10 08:00 | 2007-03-14 17:00 | 100% | CP-060101 | - | - | - | TR 24.930: Signalling flows for the session setup in the IM CN subsystem based on Session Initiation Protocol (SIP) | 24.930 | 71 | 36 |  |  | Wed 05/01/05 | Tue 29/05/07
4962 | 7043 | Interoperability between VGCS/VBS and A/Gb flexibility | VGCSFlex | 1 | Rel-7 | C1,C4 | 2006-03-22 08:00 | 2007-03-09 17:00 | 100% | CP-060102 | - | Siemens | robert.zaus@nsn.com | Voice Group Call Service | - |  |  |  |  | Wed 22/03/06 | Mon 21/07/08
4963 | 7044 | CT1 aspects of VGCSFlex | - | 2 | Rel-7 | C1 | 2006-03-22 08:00 | 2006-10-30 17:00 | 100% | CP-060102 | - | Siemens | robert.zaus@nsn.com | - | 43.068, 43.069 |  |  |  |  | Wed 22/03/06 | Mon 21/07/08
4964 | 7045 | CT4 aspects of VGCSFlex | VGCSFlex-c4 | 2 | Rel-7 | C4 | 2006-03-22 08:00 | 2007-03-09 17:00 | 100% | CP-060102 | - | Siemens | robert.zaus@nsn.com | - | 29.002 |  |  |  |  | Wed 22/03/06 | Mon 21/07/08
4965 | 13023 | DIAMETER on the GGSN Gi interface | DIAMGi | 1 | Rel-7 | C3 | 2004-09-10 08:00 | 2006-12-08 17:00 | 100% | CP-060431 | - | Vodafone | Nico.Gabriele@vodafone.com | - | 29.061 |  |  |  |  | Tue 18/01/05 | Tue 15/07/08
4966 | 13022 | DIAMETER on the PDG Wi interface | DIAMWi | 1 | Rel-7 | C3 | 2004-09-10 08:00 | 2006-12-08 17:00 | 100% | CP-060432 | - | Vodafone | Nico.Gabriele@vodafone.com | - | 29.161 |  |  |  |  | Tue 18/01/05 | Tue 15/07/08
4967 | 13033 | Interworking between the 3GPP CS domain with BICC or ISUP as signalling protocol and external SIP-I networks | ExtSIPI | 1 | Rel-7 | C3 | 2006-09-22 08:00 | 2008-07-22 17:00 | 100% | CP-070101 | - | Siemens | Thomas.Belling@nsn.com | - | 29.164 |  |  |  |  | Fri 06/10/06 | Thu 17/04/08
4968 | 340047 | PDU multiplexing at Nb Interface with IP transport | NbIPMux | 1 | Rel-7 | C3 | 2006-12-04 08:00 | 2008-07-22 17:00 | 100% | CP-070105 | - | Alcatel-Lucent | Jean.Rzeznik@alcatel-lucent.fr | - | 29.414 | 34 |  |  |  | Thu 08/03/07 | Fri 04/05/07
4969 | 14012 | Mp (MRFC - MRFP) interface | Mp | 1 | Rel-7 | C4,C1 | 2006-02-13 08:00 | 2007-06-08 17:00 | 100% | CP-070246 | - | Ericsson | philip.hodges@ericsson.com | - | - | 32 |  |  |  | Mon 13/01/03 | Tue 15/07/08
4970 | 11061 | CT1 aspects of Mp | - | 2 | Rel-7 | C1 | 2006-02-13 08:00 | 2006-02-13 17:00 | 100% | CP-070246 | - | Ericsson | philip.hodges@ericsson.com | - | 24.229 |  |  |  |  | Mon 13/01/03 | Tue 15/07/08
4971 | 13026 | Deleted - CT3 aspects of Mp | - | 2 | Rel-7 | C3 | 2006-09-22 08:00 | 2006-09-22 17:00 | 100% | - | - | Ericsson | philip.hodges@ericsson.com | CP#34: CT3 not involved in Mp interface definition | 29.162 |  |  | CP-33 |  | Mon 13/01/03 | Tue 15/07/08
4972 | 320009 | Procedures description | Mp-PROCc4 | 2 | Rel-7 | C4 | 2006-06-02 08:00 | 2007-03-09 17:00 | 100% | CP-070246 | - | Huawei | Chencheng@huawei.com | - | 23.333 | 32 |  |  |  | Wed 21/06/06 | Tue 15/07/08
4973 | 14021 | Stage 3 for Mp (MRFC - MRFP) interface | Mp-St3c4 | 2 | Rel-7 | C4 | 2006-02-13 08:00 | 2007-06-08 17:00 | 100% | CP-070246 | - | Ericsson | philip.hodges@ericsson.com | - | 29.333 |  |  |  |  | Mon 13/01/03 | Tue 15/07/08
4974 | 340016 | Routeing of MT-SMS via the HPLMN | SMSviaH | 1 | Rel-7 | C4,C1 | 2006-12-01 08:00 | 2007-03-09 17:00 | 100% | CP-070032 | - | Vodafone | Nick.Russell@vodafone.com | WID approved in CP#34 | 23.040, 29.002 | 34 |  |  |  | Fri 07/10/05 | Wed 12/09/07
4975 | 350003 | Mobile Termination whilst the MS is moving to another MSC | MTmovMS | 1 | Rel-7 | C4 | 2007-03-09 08:00 | 2007-05-31 17:00 | 100% | CP-070334 | - | Alcatel-Lucent | bruno.landais@alcatel-lucent.fr | - | 23.008, 23.012, 23.018, 23.078, 23.079, 29.002 | 35 |  |  |  | Thu 29/03/07 | Tue 29/05/07
4976 | 743009 | ISIM API for Java Card | APIJAVA | 1 | Rel-7 | C6 | 2005-03-14 08:00 | 2007-07-27 17:00 | 100% | CP-050145 | - | Sun | Sebastian Hans | - | 31.103, 102 241 | 74 | 38 |  |  | Fri 04/11/05 | Wed 12/09/07
4977 | 440042 | Rel-7 (U)SIM API Testing (TS 31.213) | USIM_API_Test | 1 | Rel-7 | C6 | 2009-05-30 08:00 | 2010-03-19 17:00 | 100% | CP-090450 | - | Sagem Orga | gerrit.hartbrod@sagem-orga.com | CP#47 completed. Update of Rel-6 (U)SIM API for Java Card Testing UID_43007 under Rel-6 UICC/USIM enhancements and interworking UID_1800 | 31.213 | 44 | 23 |  |  | Fri 29/05/09 | Tue 09/03/10
4978 | 330001 | High speed interface between the UICC and the ME | HSI | 1 | Rel-7 | C6 | 2006-09-22 08:00 | 2007-11-30 17:00 | 100% | CP-070259 | - | Gemalto | jacques.seif@GEMALTO.COM | Following ETSI publication of TS 102 600, expected to be completed at CT6 meeting 45 | 31.101 |  |  |  |  | Thu 21/09/06 | Fri 11/01/08
4979 | 34030 | Video Codec Performance Requirements | VICPer | 1 | Rel-7 | S4 | 2005-01-03 08:00 | 2007-06-07 17:00 | 100% | SP-040836 | - | Siemens | juergen.pandel@siemens.com | - | 26.234, 26.235, 26.346, 26.140, 26.902 |  |  |  |  | Thu 13/01/05 | Tue 29/05/07
4980 | 34032 | Dynamic and Interactive Multimedia Scenes | DIMS | 1 | Rel-7 | S4 | 2005-03-15 08:00 | 2007-06-07 17:00 | 100% | SP-050195 | - | Streamezzo | gaelle.martin-cocher@streamezzo.com | - | 26.140, 26.142, 26.234, 26.244, 23.346 |  |  |  |  | Mon 21/03/05 | Tue 29/05/07
4981 | 34034 | 3G-324M Video Telephony Call Setup Times Improvements | VTCSTI | 1 | Rel-7 | S4 | 2005-06-08 08:00 | 2006-09-27 17:00 | 100% | SP-050404 | - | Vodafone | edward.hall@vodafone.co.uk | - | 26.911 |  |  |  |  | Thu 16/06/05 | Wed 29/11/06
4982 | 34035 | Optimizations for Multimedia Telephony over IMS | OMTIMS | 1 | Rel-7 | S4 | 2005-09-28 08:00 | 2005-09-29 17:00 | 100% | SP-060226 | - | Ericsson | olle.franceschi@ericsson.com | Aug2015: 99%->100 | 26.235, 26.236 |  |  |  |  | Tue 04/10/05 | Wed 12/08/15
4983 | 34037 | Deleted - Characterisation of Adaptive Jitter Management Performance for VoIP Services | OMTIMS-CAJMP | 2 | Rel-7 | S4 | 2005-09-28 08:00 | 2005-09-29 17:00 | 100% | SP-050432 | - | Lucent | dhuo@lucent.com | SP-35 stopped | - |  |  | SP-35 |  | Tue 04/10/05 | Thu 29/03/07
4984 | 34036 | End-to-End Multimedia Services Performance Metrics | E2EMSPM | 1 | Rel-7 | S4 | 2005-09-28 08:00 | 2007-03-15 17:00 | 100% | SP-050433 | - | China Mobile | zhangyanyf@chinamobile.com | - | 26.944 |  |  |  |  | Tue 04/10/05 | Thu 08/03/07
4985 | 34039 | Packet Switched Streaming Enhancements | PSSe | 1 | Rel-7 | S4 | 2006-06-08 08:00 | 2007-06-07 17:00 | 100% | SP-060361 | - | Ericsson | olle.franceschi@ericsson.com | - | 26.234, 26.244 |  |  |  |  | Tue 24/01/06 | Tue 29/05/07
4986 | 35041 | Rel-7 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM7 | 1 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-15 17:00 | 100% | - | - | Huawei | Christian.Toche@huawei.com | OAM7 is an umbrella Feature also for OAM&P related TEI7 type of changes that are not part of any other dedicated feature/WI | TR 30.817 |  |  |  |  | Wed 09/03/05 | Thu 29/03/07
4987 | 35042 | Rel-7 Network Infrastructure Management | OAM7-NIM | 2 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
4988 | 35044 | Enhance NRM to accommodate NGN (IMS as basis of the Next Generation Network) | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050302 | - | Motorola | - | - | 32.731/2/3/5, 32.631/2/3/5 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
4989 | 35046 | Co-operative Element Management interface (CO-OP) (Study + Implementation) | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050304 | - | Motorola | - | - | 32.806, 32.814, 32.101 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
4990 | 35047 | Network Management (NM) Itf-N performance criteria | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050305 | - | China Mobile | - | - | 32.811 |  |  |  |  | Fri 17/06/05 | Fri 22/06/07
4991 | 35048 | Delta synchronization between IRP Manager and IRP Agent (Study + Implementation) | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050306 | - | Siemens | - | - | 32.391/2/3/5 |  |  |  |  | Fri 17/06/05 | Fri 22/06/07
4992 | 35049 | Subscription Management (SuM) IRP Solution Sets | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-07 17:00 | 100% | SP-060739 | - | Ericsson | - | - | 32.307/317/607/667/665, 32.101, 32.175 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
4993 | 35050 | Integration Reference Point (IRP) Security Management | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050308 | - | Huawei | Christian.Toche@huawei.com | - | 32.372/3/5, 32.111,32.30x,32.32x,32.33x,32.34x,32.35x,32.36x,32.41x,32.60x,32.61x,32.66x |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
4994 | 35052 | Partial suspension of Itf-N during maintenance/testing (Study + Implementation) | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050310 | - | Siemens | - | - | 32.381/2/3/5 |  |  |  |  | Fri 17/06/05 | Fri 22/06/07
4995 | 35054 | Deleted - Management of Legacy Equipment | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-15 17:00 | 100% | SP-050312 | - | Siemens | - | Request to TSG#35 to STOP the WI | new 32.xxx |  |  | SP-35 |  | Fri 17/06/05 | Thu 29/03/07
4996 | 35055 | Deleted - Rules for Vendor Specific Extensions | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050313 | - | Siemens | - | Request to TSG#35 to STOP the WI | 32.62n; For n = 1 to 5 |  |  | SP-35 |  | Fri 17/06/05 | Thu 29/03/07
4997 | 35064 | Backward and Forward Compatibility of IRP systems | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050630 | - | Ericsson | - | - | 32.154 |  |  |  |  | Fri 16/09/05 | Fri 22/06/07
4998 | 35071 | Repeater Network Resource Model (NRM) definition | - | 3 | Rel-7 | S5 | 2006-02-13 08:00 | 2006-12-07 17:00 | 100% | SP-050731 | - | China Mobile | - | - | 32.721/2/3/5 |  |  |  |  | Thu 24/11/05 | Thu 29/03/07
4999 | 35072 | UTRAN radio channel power monitoring | - | 3 | Rel-7 | S5 | 2006-02-13 08:00 | 2007-03-15 17:00 | 100% | SP-050733 | - | China Mobile | - | - | 32.405, 32.64n; For n = 1 to 5 |  |  |  |  | Thu 24/11/05 | Thu 29/03/07
5000 | 340009 | Notification XML Schema | - | 3 | Rel-7 | S5 | 2006-12-07 08:00 | 2007-03-15 17:00 | 100% | SP-060754 | - | Huawei | Christian.Toche@huawei.com | 12/2006 SP#34 WID approved | New 32.325/345/365/415, CR to 32.335/615/665 |  |  |  |  | Fri 15/12/06 | Thu 29/03/07
5001 | 35043 | Rel-7 Performance Management | OAM7-PM | 2 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
5002 | 35057 | Performance measurements definition for CN CS | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050315 | - | China Mobile | - | - | 32.407, 32.408 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
5003 | 35058 | Enhancement UTRAN performance measurements definition | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050316 | - | China Mobile | - | - | 32.405 |  |  |  |  | Fri 17/06/05 | Fri 22/06/07
5004 | 35059 | Add TDD specific counters in Performance measurement | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-07 17:00 | 100% | SP-050317 | - | CATT | - | - | 32.405 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
5005 | 35060 | ATM bearer network Performance measurements | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050318 | - | ZTE | - | - | No impact on 32.404, 32.405, 32.406, 32.407 |  |  |  |  | Fri 17/06/05 | Thu 29/03/07
5006 | 35069 | Performance measurements definition for IMS | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050631 | - | China Mobile | - | - | 32.404,32.409,32.437, 32.632/3/4/5 |  |  |  |  | Fri 17/06/05 | Fri 22/06/07
5007 | 35073 | HSDPA performance measurements | - | 3 | Rel-7 | S5 | 2006-02-13 08:00 | 2007-06-14 17:00 | 100% | SP-060379 | - | China Mobile | - | - | 32.405 |  |  |  |  | Thu 24/11/05 | Fri 22/06/07
5008 | 35039 | Rel-7 Trace Management | OAM7-Trace | 2 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-15 17:00 | 100% | SP-050628 | - | Vodafone | - | - | - |  |  |  |  | Fri 08/11/02 | Thu 29/03/07
5009 | 35040 | End-to-end Service Level tracing for IMS | - | 3 | Rel-7 | S5 | 2005-11-11 08:00 | 2007-03-15 17:00 | 100% | SP-050627 | - | Vodafone | - | 07/2005: OMA (Stage 1), Stage 2/3 SA5, CT1/3/4 | 32.101, 32.421, 32.422, 32.423 |  |  | SP-31 |  | Wed 02/03/05 | Thu 29/03/07
5010 | 35062 | Trace record content for UTRAN TDD | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-07 17:00 | 100% | SP-050628 | - | Nokia | - | - | 32.421, 32.422, 32.423 |  |  |  |  | Wed 02/03/05 | Thu 29/03/07
5011 | 35063 | IRP for Subscriber and Equipment Trace Management | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-06-14 17:00 | 100% | SP-050629 | - | Nokia | - | - | 32.441, 32.442, 32.443, 32.445, 32.632, 32.633, 32.635 |  |  |  |  | Wed 02/03/05 | Fri 22/06/07
5012 | 11046 | Deleted - SIP enhancements for trace | - | 3 | Rel-7 | C1 | 2007-06-15 17:00 | 2007-06-15 17:00 | 100% | - | - | - | - | combined with UID 11067 | - |  |  | CP-32 |  | Mon 01/03/04 | Wed 29/11/06
5013 | 35070 | Deleted - duplicated with UID 35063 - IRP for Subscriber and Equipment Trace Management | - | 3 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-15 17:00 | 100% | SP-050629 | - | Nokia | - | - | 32.421,32.422,32.423. 3 new 32.4x1,2,3 |  |  | SP-33 |  | Wed 02/03/05 | Thu 29/03/07
5014 | 320007 | Rel-7 Charging Management small Enhancements | CH7 | 1 | Rel-7 | S5 | 2006-05-22 08:00 | 2007-06-14 17:00 | 100% | - | - | Orange | alain.bibas@orange-ft.com | CH7 is an umbrella Feature also for OAM&P related TEI7 type of changes that are not part of any other dedicated feature/WI | TR 30.817 | 32 |  |  |  | Mon 22/05/06 | Mon 09/03/09
5015 | 320008 | Alternate Charged Party (ACP) for IMS | CH7-IMS-ACP | 2 | Rel-7 | S5 | 2006-05-22 08:00 | 2007-06-14 17:00 | 100% | SP-060442 | - | Lucent | njmazzarella@alcatel-lucent.com | - | 32.240, 32.260, 32.298, 32.299 | 32 |  |  |  | Mon 22/05/06 | Fri 22/06/07
5016 | 330004 | Align 3GPP Charging with OMA PoC Enabler Release 2.0 | CH7-PoC | 2 | Rel-7 | S5 | 2006-09-28 08:00 | 2007-06-14 17:00 | 100% | SP-060546 | - | Siemens | Gerald.Goermer@nsn.com | 09/2006 SP#33 WID approved | 32.240, 32.272, 32.299, 32.298 |  |  |  |  | Mon 09/10/06 | Fri 22/06/07
5017 | 2468 | Multiple-Input Multiple-Output (MIMO) antennas | MIMO | 1 | Rel-7 | R1,R5 | 2003-03-14 08:00 | 2008-03-07 17:00 | 100% | RP-030192 | - | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007; SR in RP-070037and RP-070531 | 25.876, 25.996 |  |  |  |  | Tue 20/03/01 | Wed 25/06/08
5018 | 21006 | MIMO - Physical layer | MIMO-Phys | 2 | Rel-7 | R1 | 2003-09-12 08:00 | 2007-03-15 17:00 | 100% | RP-030192 | RP-070037 | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007; SR in RP-070037 | 25.211, 25.212, 25.213, 25.214, 25.215, 25.221 |  |  |  |  | Thu 27/03/03 | Tue 24/06/08
5019 | 22003 | MIMO - Layer 2,3 aspects | MIMO-L23 | 2 | Rel-7 | R2 | 2003-09-12 08:00 | 2007-03-15 17:00 | 100% | RP-030192 | RP-070037 | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007; SR in RP-070037 | 25.876 |  |  |  |  | Thu 27/03/03 | Tue 24/06/08
5020 | 23008 | MIMO - Iub/Iur Protocol Aspects | MIMO-IurIub | 2 | Rel-7 | R3 | 2003-03-14 08:00 | 2007-03-15 17:00 | 100% | RP-030192 | RP-070037 | Alcatel-Lucent | hchuang@Alcatel-Lucent.com | Completed Sep 2007; SR in RP-070037 | - |  |  |  |  | Thu 27/03/03 | Tue 24/06/08
5021 | 24008 | MIMO - RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing | MIMO-RF | 2 | Rel-7 | R4 | 2003-12-12 08:00 | 2007-09-17 17:00 | 100% | RP-030192 | RP-070531 | Alcatel-Lucent | ngm@Alcatel-Lucent.com | Completed Sep 2007; SR in RP-070531 | - |  |  |  |  | Thu 27/03/03 | Tue 24/06/08
5022 | 25036 | UE Conformance Testing for Multiple Input Multiple Output antennas (MIMO) | MIMO-UEConTest | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-03-07 17:00 | 100% | - | - | Qualcomm | svora@qualcomm.com | BB place holder for a number of RAN5 Tasks | - |  |  |  |  | Mon 19/03/07 | Wed 16/06/10
5023 | 25037 | Conformance Test Aspects – Multiple Input Multiple Output Antennas (MIMO) for FDD | MIMO-UEConTest_FDD | 3 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-03-07 17:00 | 100% | - | - | Qualcomm | svora@qualcomm.com | - | TS 34.108, TS 34.109, TS 34.121-1, TS 34.121-2, TS 34.123-1, TS 34.123-2, TS 34.123-3 |  |  |  |  | Wed 20/09/06 | Wed 16/06/10
5024 | 20028 | Rel-7 Improvements of the Radio Interface | - | 1 | Rel-7 | RP,GP | 2004-09-15 08:00 | 2007-06-04 17:00 | 100% | - | - | - | - | Generic feature | - |  |  |  |  | Tue 04/01/05 | Wed 25/06/08
5025 | 20060 | Extended UMTS 1.7/2.1 GHz | RInImp-UMTS1721Ext | 2 | Rel-7 | R4 | 2006-03-15 08:00 | 2006-12-15 17:00 | 100% | RP-060180 | RP-060681 | Ericsson | johan.skold@ericsson.com | RP#34 completed. Introduction of Band X (Extended UMTS 1.7/2.1 GHz) in 25.307 | 25.806, 25.101, 25.104, 25.133, 24.141, 25.331, 25.306, 25.307, 25.423, 25.461, 25.463, 34.121 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
5026 | 20067 | UMTS 2.6 GHz 7.68 Mcps TDD | RInImp-UMTS26VHCRTDD | 2 | Rel-7 | R4 | 2006-06-15 08:00 | 2006-09-15 17:00 | 100% | RP-060349 | RP-060451 | IPWireless | Shin Horng Wong (shwong@ipwireless.com) | RP#33 completed | 25.102, 25.105, 25.123, 25.113, 25.142, 34.124 |  |  |  |  | Wed 21/06/06 | Tue 27/07/10
5027 | 20021 | UMTS 2.6 GHz | RInImp-UMTS2600 | 2 | Rel-7 | R4 | 2004-09-15 08:00 | 2005-06-14 17:00 | 100% | RP-040397 | RP-050184 | Nokia | jussi.numminen@nokia.com | RP#28 completed | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
5028 | 20025 | UMTS 2.6 GHz TDD | RInImp-UMTS2600TDD | 2 | Rel-7 | R4 | 2004-12-15 08:00 | 2005-12-14 17:00 | 100% | RP-040553 | RP-050661 | IPWireless | Shin Horng Wong (shwong@ipwireless.com) | RP#30 completed | 25.102, 25.105, 25.113, 25.123, 25.142, 25.331, 25.942, 25.306, 25.307, 34.122, 34.124 |  |  |  |  | Tue 04/01/05 | Tue 27/07/10
5029 | 20027 | UMTS 900 MHz | RInImp-UMTS900 | 2 | Rel-7 | R4 | 2004-12-15 08:00 | 2005-12-14 17:00 | 100% | RP-040541 | RP-050662 | Nortel | Yannick Li (yli@nortelnetworks.com) | RP#30 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 |  |  |  |  | Tue 04/01/05 | Tue 27/07/10
5030 | 20043 | UMTS 1700 MHz | RInImp-UMTS1700 | 2 | Rel-7 | R4 | 2005-03-15 08:00 | 2005-12-14 17:00 | 100% | RP-050385 | RP-050824 | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | RP#30 completed | 25.101, 25.104, 25.113, 25.133, 25.141, 25.306, 25.307, 25.331, 34.121 |  |  |  |  | Mon 20/06/05 | Tue 27/07/10
5031 | 20024 | UE Antenna Performance Evaluation Method and Requirements | RInImp-UEAnt | 2 | Rel-7 | R4,GP | 2004-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-050122 | RP-070281 | TeliaSonera | Christian.Bergljung@TeliaSonera.com | RP#36 completed | 25.101, new TR (25.914, 25.963) |  |  |  |  | Tue 04/01/05 | Tue 27/07/10
5032 | 20045 | Improved Performance Requirements for HSDPA UE based on Rx Diversity (type 1) & LMMSE equalizer (type 2) | RInImp-HSPerf-Type3 | 2 | Rel-7 | R4 | 2005-03-15 | 2005-03-15 | 100% | RP-050362 | RP-060015 | Cingular | Marc Grant | RP#27 completed | 25.101 |  |  |  |  | Mon 20/06/05 | Tue 27/07/10
5033 | 20062 | Additional minimum UE performance requirement for non-HSDPA channels based on type 1 enhanced receiver (Rx Diversity) | RInImp-RxDiv | 2 | Rel-7 | R4 | 2005-09-15 08:00 | 2006-12-15 17:00 | 100% | - | - | Qualcomm | Serge Willenegger (sergew@qualcomm.com) | - | 25.101 |  |  |  |  | Tue 21/03/06 | Tue 24/06/08
5034 | 20048 | Additional minimum UE performance requirement for DL physical channels in support of DCH/HS-DSCH operation based on type 1 enhanced receiver (RX-Diversity) | RInImp-RxDiv-DCH | 3 | Rel-7 | R4 | 2005-09-15 08:00 | 2006-06-14 17:00 | 100% | RP-060185 | RP-060235 | Cingular | Marc Grant | RP#32 completed | 25.101 |  |  |  |  | Wed 05/10/05 | Tue 27/07/10
5035 | 7028 | Additional minimum UE performance requirement for downlink physical channels in support of MTCH and MCCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-RxDiv-MBMS | 3 | Rel-7 | R4 | 2006-03-15 08:00 | 2006-12-15 17:00 | 100% | RP-060183 | RP-060678 | Qualcomm | Serge Willenegger (sergew@qualcomm.com) | RP#34 completed | 25.101 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
5036 | 7029 | Additional minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-RxDiv-EDCH | 3 | Rel-7 | R4 | 2006-03-15 08:00 | 2006-12-15 17:00 | 100% | RP-060184 | RP-060679 | Qualcomm | Serge Willenegger (sergew@qualcomm.com) | RP#34 completed | 25.101 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
5037 | 20049 | Deleted Improved support of gaming over HSDPA/EDCH | RInImp-Gaming | 2 | Rel-7 | R2 | 2005-12-15 08:00 | 2006-12-15 17:00 | 100% | - | RP-060680 | Cingular | Don Zelmer (dz1069@att.com) | RP#34 stopped. SR in RP-060680 | - |  |  | RP-34 |  | Thu 15/12/05 | Tue 27/07/10
5038 | 20047 | Deleted (not approved at PCG) - UMTS 2.6 GHz FDD DL External | RInImp-UMTS2600Ext | 2 | Rel-7 | R4 | 2005-09-15 08:00 | 2005-09-15 08:00 | 100% | - | - | T-mobile | han.van.bussel@t-mobile.de | This item was conditionnaly approved pending decision of PCG#16 who decided not to approve it | 25.101, 25.104, 25.133, 25.141, 25.331, 25.942, 25.306, 25.307, 34.121 |  |  | RP-31 | PCG-16 | Wed 05/10/05 | Thu 22/12/05
5039 | 25025 | Rel-7 Improvements of the Radio Interface - UE Conformance Testing | - | 1 | Rel-7 | R5 | 2005-11-11 08:00 | 2008-09-12 17:00 | 100% | - | - | - | - | Linked to Feature UID_20028 (RInImp) | - |  |  |  |  | Fri 22/09/06 | Sun 01/06/08
5040 | 25007 | UE Conformance Test for UMTS 2600 MHz | RInImp-UMTS2600_Test | 2 | Rel-7 | R5 | 2005-11-11 08:00 | 2006-06-02 17:00 | 100% | - | - | Nokia | Aleksi.Heino@nokia.com | RP#32 completed | 34.108, 34.121 |  |  |  |  | Thu 28/02/02 | Tue 21/03/06
5041 | 25008 | UE Conformance Test for UMTS 900 MHz (band VIII) | RInImp-UMTS900_Test | 2 | Rel-7 | R5 | 2005-11-11 08:00 | 2006-06-02 17:00 | 100% | - | - | Qualcomm | hanye@qualcomm.com | RP#32 completed | 34.108, 34.121 |  |  |  |  | Thu 28/02/02 | Tue 21/03/06
5042 | 25013 | Conformance Test Aspects – Improved Performance of HSDPA Receiver type 3 | RInImp-HSPerf-Type3_Test | 2 | Rel-7 | R5 | 2006-03-10 08:00 | 2006-12-01 17:00 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | RP#34 completed | 34.121, 34.108 |  |  |  |  | Tue 21/03/06 | Tue 21/03/06
5043 | 25020 | UE antenna Over The Air (OTA) conformance testing | RInImp-UEAnt_Test | 2 | Rel-7 | R5 | 2006-09-20 08:00 | 2008-09-12 17:00 | 100% | RP-060486 | RP-080535 | Nokia | Aleksi.Heino@nokia.com | RP#41 completed (GERAN aspects might need to be included later) | 34.114 |  |  |  |  | Wed 20/09/06 | Sun 14/09/08
5044 | 25015 | UE conformance testing for FDD Inter-Band Operation | RInImp-InterBand_Test | 2 | Rel-7 | R5 | 2006-06-02 08:00 | 2006-12-01 17:00 | 100% | - | - | NEC, Motorola | Jacob.John@motorola.com | RP#34 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Tue 21/03/06 | Fri 01/12/06
5045 | 25028 | Conformance Test Aspects – Extended UMTS 1.7/2.1 GHz | RInImp-UEConTest_UMTS1721Ext | 2 | Rel-7 | R5 | 2006-12-01 08:00 | 2007-06-01 17:00 | 100% | RP-060676 | RP-070312 | Motorola | carolyn.taylor@motorola.com | RP#36 completed | 34.108, 34.121-1, 34.121-2 |  |  |  |  | Wed 20/09/06 | Mon 11/06/07
5046 | 25039 | Conformance Test Aspects – Minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-UEConTest_RxDivEDCH | 2 | Rel-7 | R5 | 2007-06-01 08:00 | 2007-12-07 17:00 | 100% | RP-070414 | RP-070810 | Motorola | carolyn.taylor@motorola.com | RP#38 completed | - |  |  |  |  | Wed 20/09/06 | Tue 11/09/07
5047 | 25040 | Conformance Test Aspects – Minimum UE performance requirement for downlink physical channels in support of MTCGH and MCCH operation based on type 1 enhanced receiver (Rx-Diversity) | RInImp-UEConTest_RxDivMBMS | 2 | Rel-7 | R5 | 2007-06-01 08:00 | 2008-03-07 17:00 | 100% | RP-070381 | RP-080056 | Ericsson | leif.mattisson@ericsson.com | RP#39 completed | 34.121-1, 34.121-2 |  |  |  |  | Wed 20/09/06 | Mon 10/03/08
5048 | 20029 | Rel-7 RAN improvements | - | 1 | Rel-7 | RP,S5 | 2004-12-15 | 2007-06-15 17:00 | 100% | - | - | - | - | Generic feature | - |  |  |  |  | Tue 04/01/05 | Wed 25/06/08
5049 | 20026 | Optimization of channelisation code utilisation for 1.28 Mcps TDD | RANimp-RABSE-CodOptLCRTDD | 2 | Rel-7 | R1 | 2004-12-15 | 2006-12-15 17:00 | 100% | RP-040552 | RP-060682 | UTStarcom | Ka Leong Lo (kaleong.lo@UTSTAR.COM) | RP#34 completed | - |  |  |  |  | Tue 04/01/05 | Tue 27/07/10
5050 | 20031 | Delay optimization for procedures applicable to CS and PS Connections | RANimp-DelayOpt | 2 | Rel-7 | R2 | 2005-03-15 08:00 | 2006-09-15 17:00 | 100% | RP-050386 | RP-060453 | Nokia | juho.pirskanen@nokia.com | RP#33 completed | 25.815, 25.321, 25.322, 25.331 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
5051 | 20132 | Improved support of IMS Realtime Services using HSDPA/HSUPA | RANimp-IMSRealTime | 2 | Rel-7 | R2 | 2005-03-15 | 2005-12-14 17:00 | 100% | RP-050160 | RP-050667 | Cingular | Don Zelmer (dz1069@att.com) | RP#30 completed | - |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
5052 | 20033 | UE Performance Requirements for MBMS (TDD) | MBMS-RAN-RF-TDD | 2 | Rel-7 | R4 | 2005-03-15 08:00 | 2006-06-15 17:00 | 100% | RP-050156 | RP-060477 | IPwireless | shwong@ipwireless.com | RP#32 completed | 25.102, 25.123 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
5053 | 20046 | Continuous connectivity for packet data users | RANimp-CPC | 2 | Rel-7 | R1 | 2005-03-14 08:00 | 2007-03-15 17:00 | 100% | RP-050870 | RP-070033 | Siemens | Joern.Krause@siemens.com | RP#35 completed | 25.903, 25.201, 25.211, 25.212, 25.214, 25.308, 25.321, 25.331, 25.423, 25.433, 25.101, 25.133 |  |  |  |  | Wed 05/10/05 | Tue 27/07/10
5054 | 7030 | Extended WCDMA Cell Range | RANimp-ExtCell | 2 | Rel-7 | R3 | 2006-03-15 08:00 | 2006-12-15 17:00 | 100% | RP-060212 | RP-060685 | Ericsson | Muhammad Kazmi | RP#34 completed | 25.133, 25.423, 25.425, 25.433, 25.435, 25.453, 25.331 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
5055 | 7031 | 7.68 Mcps TDD Enhanced Uplink | RANimp-VHCRTDD-EDCH | 2 | Rel-7 | R1 | 2006-03-15 08:00 | 2006-12-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | nanderson@ipwireless.com | RP#34 completed | 25.201, 25.202, 25.221, 25.222, 25.223, 25.224, 25.225, 25.331, 23.321, 25.306, 25.302, 25.401, 25.420, 25.423, 25.427, 25.433, 25.102, 25.105, 25.142 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
5056 | 330009 | Enhanced CELL_FACH State in FDD | RANimp-EnhState | 2 | Rel-7 | R2 | 2006-09-25 08:00 | 2007-06-04 17:00 | 100% | RP-070245 | RP-070286 | Nokia | juho.pirskanen@nokia.com | RP#36 completed | 25.308, 25.304, 25.306, 25.321, 25.331, 25.433, 25.435, 25.423, 25.425, |  |  |  |  | Fri 06/10/06 | Tue 27/07/10
5057 | 340038 | 64QAM for HSDPA (FDD) | RANimp-64QamDownlink | 2 | Rel-7 | R1 | 2006-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-070223 | RP-070287 | Ericsson | Johan.Bergman@ericsson.com | RP#36 completed | 25.308, 25.211, 25.212, 25.213, 25.306, 25.331, 25.433, 25.435, 25.423, 25.425, 25.101, 25.104, 25.141 |  |  |  |  | Fri 06/10/06 | Tue 27/07/10
5058 | 340039 | Improved L2 support for high data rates | RANimp-L2DataRates | 2 | Rel-7 | R2 | 2006-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-070242 | RP-070289 | Ericsson | Janne.Peisa@ericsson.com | RP#36 completed | 25.301, 25.308,25.306, 25.321, 25.322, 25.331, 25.433, 25.435, 25.423, 25.425, 25.999 |  |  |  |  | Fri 06/10/06 | Tue 27/07/10
5059 | 340040 | Introduction of 16QAM in HSUPA (FDD) | RANimp-16QamUplink | 2 | Rel-7 | R1 | 2006-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-060844 | RP-070288 | Nokia | Karri.Ranta-aho@nsn.com | RP#36 completed | 25.319, 25.101, 25.104, 25.133, 25.141, 25.211, 25.212, 25.213, 25.214, 25.306, 25.321, 25.331, 25.423, 25.433 |  |  |  |  | Fri 06/10/06 | Tue 27/07/10
5060 | 20066 | Interface to control Tower Mounted Amplifiers (TMAs) | RANImp-TMA | 2 | Rel-7 | R3,S5 | 2006-06-02 08:00 | 2007-06-15 17:00 | 100% | RP-060418 | RP-070140 | Vodafone | alexej.kulakov@vodafone.com | RP#35 completed | - |  |  |  |  | Wed 21/06/06 | Tue 27/07/10
5061 | 20166 | RAN3 part of Interface to control Tower Mounted Amplifiers (TMAs) | - | 3 | Rel-7 | R3 | 2006-06-02 08:00 | 2007-03-16 17:00 | 100% | RP-060418 | RP-070140 | Vodafone | alexej.kulakov@vodafone.com | RP#35 completed | - |  |  |  |  | Wed 21/06/06 | Tue 27/07/10
5062 | 340045 | OAM aspects to Interface to control TMAs | RANImp-TMA-OAM | 3 | Rel-7 | S5 | 2007-01-26 08:00 | 2007-06-15 17:00 | 100% | - | - | Vodafone | Adrian.Neal@vodafone.com | SP#36 completed | 32.642, 32.643, 32.645 – Align with RAN 25.466 |  |  |  |  | Thu 08/03/07 | Tue 27/07/10
5063 | 25026 | Rel-7 RAN improvements - UE Conformance Testing | - | 1 | Rel-7 | R5 | 2006-09-20 08:00 | 2009-09-18 17:00 | 100% | - | - | - | - | Linked to Feature UID_20029 (RANimp) | - |  |  |  |  | Fri 22/09/06 | Tue 27/07/10
5064 | 25021 | Conformance Test Aspects - 3.84 Mcps and 7.68 Mcps TDD Enhanced Uplink | RANimp-UEConTest_EDCHTDH | 2 | Rel-7 | R5 | 2006-09-20 08:00 | 2008-09-12 17:00 | 100% | RP-060484 | RP-080536 | IPWireless | tspeight@ipwireless.com | RP#41 completed | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
5065 | 25031 | Conformance Test Aspects – 64QAM for HSDPA (FDD) | RANimp-UEConTest_64QamDownlink | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-03-03 17:00 | 100% | RP-071319 | RP-080059 | Ericsson | leif.mattisson@ericsson.com | RP#39 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
5066 | 25032 | Conformance Test Aspects – 16QAM for HSUPA (FDD) | RANimp-UEConTest_16QamUplink | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-05-30 17:00 | 100% | RP-070022 | RP-080281 | Motorola | carolyn.taylor@motorola.com | RP#40 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
5067 | 25033 | Conformance Test Aspects – Improved L2 support for high data rates | RANimp-UEConTest_L2DataRates | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-05-30 17:00 | 100% | RP-070020 | RP-080256 | Ericsson | leif.mattisson@ericsson.com | RP#40 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
5068 | 25034 | Conformance Test Aspects – Continuous connectivity for packet data users | RANimp-UEConTest_CPC | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2008-05-30 17:00 | 100% | RP-070023 | RP-080282 | Nokia | jarkko.hellsten@nokia.com | RP#40 completed | 34.108, 34.121-1, 34.121-2, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
5069 | 25035 | Conformance Test Aspects – Enhanced CELL_FACH state in FDD | RANimp-UEConTest_EnhancedCellFACHState | 2 | Rel-7 | R5 | 2007-03-09 08:00 | 2009-09-18 17:00 | 100% | RP-080730 | RP-090711 | Nokia | jarkko.hellsten@nokia.com | RP#45 completed | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
5070 | 20014 | 7.68 Mcps TDD option | VHCRTDD | 1 | Rel-7 | R1,R2,R3,R4,R5 | 2004-09-15 08:00 | 2007-09-14 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | Martin Beale (mbeale@ipwireless.com) | RP#31 completed | - |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
5071 | 20015 | VHCRTDD: Stage 2 | VHCRTDD-Stage2 | 2 | Rel-7 | R1 | 2004-09-15 08:00 | 2006-03-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | Martin Beale (mbeale@ipwireless.com) | RP#31 completed | 25.202 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
5072 | 20016 | VHCRTDD: Physical Layer | VHCRTDD-Phys | 2 | Rel-7 | R1 | 2004-09-15 08:00 | 2006-03-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | Martin Beale (mbeale@ipwireless.com) | RP#31 completed | 25.221, 25.222, 25.223, 25.224,25.225 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
5073 | 20017 | VHCRTDD: Layer 2 and layer 3 protocol aspects | VHCRTDD-L23 | 2 | Rel-7 | R2 | 2004-09-15 08:00 | 2006-03-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | drichards@ipwireless.com | RP#31 completed | 25.301, 25.302, 25.305, 25.306, 25.321, 25.331 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
5074 | 20018 | VHCRTDD: UTRAN Iub/Iur Protocol Aspects | VHCRTDD-IurIub | 2 | Rel-7 | R3 | 2004-09-15 08:00 | 2006-03-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | Peter Legg (plegg@ipwireless.com) | RP#31 completed | 25.401, 25.420, 25.423, 25.425, 25.427, 25.430, 25.433, 25.435 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
5075 | 20019 | VHCRTDD: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | VHCRTDD-RF | 2 | Rel-7 | R4 | 2004-09-15 08:00 | 2006-06-15 17:00 | 100% | RP-060119 | RP-060684 | IPwireless | Shin Horng Wong (shwong@ipwireless.com) | RP#32 completed | 25.102, 25.105, 25.123, 25.133, 25.142 |  |  |  |  | Mon 27/09/04 | Tue 27/07/10
5076 | 25027 | Conformance Test Aspects - 7.68 Mcps TDD | VHCRTDD-UEConTest | 2 | Rel-7 | R5 | 2006-09-20 08:00 | 2007-09-14 17:00 | 100% | RP-060482 | RP-070307 | IPWireless | tspeight@ipwireless.com | RP#37 completed | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Tue 27/07/10
5077 | 20035 | 3.84 Mcps TDD Enhanced Uplink | EDCHTDD | 1 | Rel-7 | RP | 2005-03-15 | 2006-09-15 17:00 | 100% | RP-050100 | RP-060462 | IPwireless | nanderson@ipwireless.com | RP#33 completed | - |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
5078 | 20036 | EDCHTDD: Stage 2 | EDCHTDD-Stage2 | 2 | Rel-7 | R2 | 2005-03-15 | 2006-06-15 17:00 | 100% | - | RP-060462 | IPwireless | nanderson@ipwireless.com | RP#33 completed | - |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
5079 | 20037 | EDCHTDD: Physical Layer | EDCHTDD-Phys | 2 | Rel-7 | R1 | 2005-03-15 | 2006-09-15 17:00 | 100% | - | RP-060462 | IPwireless | nanderson@ipwireless.com | RP#33 completed | 25.201, 25.221,25.222, 25.223, 25.224, 25.225 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
5080 | 20038 | EDCHTDD: Layer 2 and 3 Protocol Aspects | EDCHTDD-L23 | 2 | Rel-7 | R2 | 2005-03-15 | 2006-09-15 17:00 | 100% | - | RP-060462 | IPwireless | drichards@ipwireless.com | RP#33 completed | 25.301, 25.302, 25.306, 25.321, 25.331 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
5081 | 20039 | EDCHTDD: UTRAN Iub/Iur Protocol Aspects | EDCHTDD-IurIub | 2 | Rel-7 | R3 | 2005-03-15 | 2006-09-15 17:00 | 100% | - | RP-060462 | Interdigital | jim.miller@interdigital.com | RP#33 completed | 25.401, 25.420, 25.423, 25.427, 25.430, 25.433, 25.435 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
5082 | 20040 | EDCHTDD: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | EDCHTDD-RF | 2 | Rel-7 | R4 | 2005-03-15 08:00 | 2006-09-15 17:00 | 100% | - | RP-060462 | IPwireless | Shin Horng Wong (shwong@ipwireless.com) | RP#33 completed | 25.102, 25.105, 25.123, 25.142 |  |  |  |  | Tue 15/03/05 | Tue 27/07/10
5083 | 20055 | 1.28 Mcps TDD Enhanced Uplink | LCRTDD-EDCH | 1 | Rel-7 | R1,R2,R3,R4,R5 | 2006-03-15 08:00 | 2008-09-12 17:00 | 100% | RP-060202 | RP-070296 | CATT | Haijing Hu | RP#35 completed | - | 35 |  |  |  | Tue 21/03/06 | Tue 27/07/10
5084 | 20056 | 1.28 Mcps TDD Enhanced Uplink: Physical Layer | LCRTDD-EDCH-Phys | 2 | Rel-7 | R1 | 2006-03-15 08:00 | 2007-03-15 17:00 | 100% | - | RP-070038 | CATT | Ke Wang | RP#35 completed | 25.201, 25.221, 25.222, 25.223, 25.224, 25.225 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
5085 | 20057 | 1.28 Mcps TDD Enhanced Uplink: Layer 2 and 3 Protocol Aspects | LCRTDD-EDCH-L23 | 2 | Rel-7 | R2 | 2006-03-15 08:00 | 2007-03-15 17:00 | 100% | - | RP-070038 | CATT | Haiyang Quan | RP#35 completed | 25.301, 25.302, 25.306, 25.321, 25.331 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
5086 | 20058 | 1.28 Mcps TDD Enhanced Uplink: UTRAN Iub/Iur Protocol Aspects | LCRTDD-EDCH-IubIur | 2 | Rel-7 | R3 | 2006-03-15 08:00 | 2007-03-15 17:00 | 100% | - | RP-070038 | CATT | Yincheng Zhang | RP#35 completed | 25.401, 25.420, 25.423, 25.425, 25.427, 25.430, 25.433, 25.435 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
5087 | 20059 | 1.28 Mcps TDD Enhanced Uplink: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | LCRTDD-EDCH-RF | 2 | Rel-7 | R4 | 2006-03-15 08:00 | 2007-06-15 17:00 | 100% | - | RP-070296 | CATT | Yuexia Song (songyuexia@catt.cn) | RP#36 completed | 25.102, 25.105, 25.123, 25.142 |  |  |  |  | Tue 21/03/06 | Tue 27/07/10
5088 | 350146 | 1.28 Mcps TDD Enhanced Uplink - UE Conformance Testing | LCRTDD-EDCH-UEConTest | 2 | Rel-7 | R5 | 2007-09-20 08:00 | 2008-09-12 17:00 | 100% | RP-070724 | RP-080539 | CATT | chenxiaozhong@datangmobile.cn | RP#41 completed | 34.108, 34.122, 34.123-1/2/3 | 35 |  |  |  | Tue 21/03/06 | Tue 27/07/10
5089 | 490016 | Conformance Test Aspects – Multiple Band and Multiple Frequency operation for LCR TDD | LCRTDD_MB_MF_UEConTest | 1 | Rel-7 | R5 | 2010-09-17 08:00 | 2011-09-16 17:00 | 100% | RP-100805 | RP-110968 | CATR | Ms Jun Chen (chenjun@catr.cn) | RP#53 completed. Core specification was introduced via Rel-7 CR under TEI7 (RP#37 RP-070650) and via 2 Rel-8 work items: RInImp9-UMTS1880TDD and RInImp8-UMTS2300TDD. | UTRA 34.108, 34.123-1, 34.123-2, 34.123-3 | 49 | 25 |  |  | Wed 08/09/10 | Tue 06/09/11
5090 | 50118 | MS Antenna Performance Evaluation Method and Requirements | APEMR | 1 | Rel-7 | GP | 2005-01-28 08:00 | 2007-11-16 17:00 | 100% | GP-050284 | - | TeliaSonera | Ulf.Tegth@teliasonera.com | GP#36 completed for R7 | 25.914, 25.144, 45.005 |  |  |  |  | Wed 05/09/07 | Mon 19/05/08
5091 | 50119 | Lower 700 MHz Inclusion in the GERAN Specifications | GSM710 | 1 | Rel-7 | GP | 2005-01-03 08:00 | 2006-06-30 17:00 | 100% | GP-050543 | - | UTC | dcotton@mtview.union-tel.com | - | - |  |  |  |  | Tue 01/02/05 | Tue 19/09/06
5092 | 51138 | Inclusion of the 698 – 746 MHz band into GERAN core specifications | GSM710-core | 2 | Rel-7 | G1 | 2005-01-03 08:00 | 2005-06-30 17:00 | 100% | - | - | - | - | Completed | 24.008, 43.022, 44.018, 44.118, 45, 001, 45.005, |  |  |  |  | Mon 12/09/05 | Thu 15/09/05
5093 | 53184 | Aspects of GSM710 | GSM-710-test | 2 | Rel-7 | G1,G3new | 2005-08-31 13:00 | 2006-06-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 12/09/05 | Thu 20/07/06
5094 | 53084 | G1 aspects of GSM710 | - | 3 | Rel-7 | G1 | 2005-08-31 13:00 | 2006-06-30 17:00 | 100% | - | - | - | - | - | 51.021 |  |  |  |  | Mon 12/09/05 | Thu 20/07/06
5095 | 55094 | G3 aspects of GSM710 | - | 3 | Rel-7 | G3new | 2005-08-31 13:00 | 2006-06-30 17:00 | 100% | - | - | - | - | - | 51.010 |  |  |  |  | Tue 20/12/05 | Mon 17/07/06
5096 | 50564 | Support of Conversational Services in A/Gb mode via the PS domain | SCSAGB | 1 | Rel-7 | GP | 2005-04-08 08:00 | 2007-08-31 17:00 | 100% | GP-061501 | - | Ericsson | gunnar.hedby@ericsson.com | Originally started Nov. 2003 as GP-030443 | - |  |  |  |  | Thu 21/04/05 | Tue 29/05/07
5097 | 52143 | Minimise the transfer delay between the SGSN and the MS | SCSAGB-MTD | 2 | Rel-7 | GP | 2005-04-08 08:00 | 2007-08-31 17:00 | 100% | GP-061501 | - | Ericsson | gunnar.hedby@ericsson.com | - | - |  |  |  |  | Wed 03/05/06 | Thu 10/01/08
5098 | 51137 | Definition of radio resource management functionality for Support of Conversational Services in A/Gb mode via the PS domain | SCSAGB-RRM | 2 | Rel-7 | G1 | 2005-04-08 08:00 | 2007-08-31 17:00 | 100% | GP-061502 | - | Ericsson | gunnar.hedby@ericsson.com | - | - |  |  |  |  | Thu 21/04/05 | Thu 10/01/08
5099 | 52144 | Support of Conversational Services in A/Gb mode via the PS domain – RLC Non-Persistent mode | SCSAGB-RLCNP | 2 | Rel-7 | G2 | 2006-06-30 08:00 | 2006-11-17 17:00 | 100% | GP-061503 | - | Ericsson | gunnar.hedby@ericsson.com | - | 43.955, 43.064, 44.060, 45.001, 45.002, 45.003, 45.005, 45.010, 51.010, 51.021 |  |  |  |  | Wed 05/07/06 | Thu 10/01/08
5100 | 52138 | Deleted- Radio Channel Support | SCSAGB-RCHS | 2 | Rel-7 | G2 | 2006-07-17 17:00 | 2006-07-17 17:00 | 100% | GP-051166 | - | Ericsson | gunnar.hedby@ericsson.com | - | - |  |  | SP-32 |  | Thu 21/04/05 | Thu 11/05/06
5101 | 52139 | Deleted- Modifications to FLO | SCSAGB-FLO | 2 | Rel-7 | G2 | 2006-07-17 17:00 | 2006-07-17 17:00 | 100% | GP-051165 | - | Ericsson | gunnar.hedby@ericsson.com | - | - |  |  | SP-32 |  | Thu 21/04/05 | Thu 09/03/06
5102 | 50565 | Addition of new frequency band to GSM (T-GSM810) | TGSM810 | 1 | Rel-7 | GP | 2005-04-08 08:00 | 2007-08-31 17:00 | 100% | GP-050945 | - | Huawei | chende@huawei.com | - | 45.005, 45.050, 24.008, 45.008, 45.001, 43.022, 43.030, 44.018, 44.060, 51.010-1, 51.021 |  |  |  |  | Thu 21/04/05 | Tue 29/05/07
5103 | 50566 | Changes to core specification | TGSM810-Core | 2 | Rel-7 | GP | 2005-04-08 08:00 | 2005-09-02 17:00 | 100% | GP-050946 | - | Huawei | chende@huawei.com | - | 45.005, 45.050, 24.008, 45.008, 45.001, 43.022, 43.030, 44.018, 44.060 |  |  |  |  | Thu 21/04/05 | Thu 15/09/05
5104 | 55092 | Changes to MS testing specification | TGSM810-MStest | 2 | Rel-7 | G3new | 2005-04-08 08:00 | 2007-08-31 17:00 | 100% | GP-050947 | - | Huawei | chende@huawei.com | - | 51010-1 |  |  |  |  | Thu 21/04/05 | Wed 12/09/07
5105 | 53082 | Changes to BTS testing specification | TGSM810-BTStest | 2 | Rel-7 | G1 | 2005-04-08 08:00 | 2005-11-11 17:00 | 100% | GP-050948 | - | Huawei | chende@huawei.com | - | 51021 |  |  |  |  | Thu 21/04/05 | Thu 22/12/05
5106 | 50567 | Handover of dedicated and shared resources while in Dual Transfer Mode | HODSRDTM | 1 | Rel-7 | GP | 2005-04-08 08:00 | 2006-11-17 17:00 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | GP#30 completed. Started at GP#24 | - |  |  |  |  | Thu 21/04/05 | Tue 19/09/06
5107 | 55093 | GERAN2 part of Handover of dedicated and shared resources while in Dual Transfer Mode | HODSRDTM-G2 | 2 | Rel-7 | G2 | 2005-04-08 08:00 | 2006-06-30 17:00 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | GP#30 completed | 43.055, 44.018, 44.060 |  |  |  |  | Thu 21/04/05 | Mon 17/07/06
5108 | 55095 | Deleted - MS Conformance Testing | HODSRDTM-MStest | 2 | Rel-7 | G3new | 2005-04-08 08:00 | 2006-11-17 17:00 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | Stopped, no work done. 12/2008 Marked as stopped ("deleted") | 51-010 |  |  | GP-32 |  | Mon 21/11/05 | Mon 15/12/08
5109 | 53083 | Deleted - BTS conformance testing | HODSRDTM-BTStest | 2 | Rel-7 | G1 | 2005-04-08 08:00 | 2006-11-17 17:00 | 100% | GP-050979 | - | Nokia | rami.vaittinen@nokia.com | Stopped, no work done. 12/2008 Marked as stopped ("deleted") | 51.026 |  |  | GP-32 |  | Thu 21/04/05 | Mon 15/12/08
5110 | 50569 | Mobile Station Receive Diversity (DARP Phase II) | MSRD2 | 1 | Rel-7 | GP | 2005-11-11 08:00 | 2007-11-16 17:00 | 100% | GP-061491 | - | Nokia | kent.pedersen@nokia.com | GP#36 completed | - |  |  |  |  | Mon 21/11/05 | Mon 19/05/08
5111 | 50571 | Performance Requirements for Mobile Station Receive Diversity, DARP Phase II | MSRD2-PerfReq | 2 | Rel-7 | GP | 2005-11-11 08:00 | 2007-02-16 17:00 | 100% | GP-060115 | - | Nokia | kent.pedersen@nokia.com | GP#33 completed | 45.005 |  |  |  |  | Mon 21/11/05 | Thu 08/03/07
5112 | 50572 | Capability signalling of Mobile Station Receive Diversity, DARP Phase II | MSRD2-CapSig | 2 | Rel-7 | GP | 2005-11-11 08:00 | 2007-02-16 17:00 | 100% | GP-060116 | - | Nokia | kent.pedersen@nokia.com | GP#33 completed | 24.008 |  |  |  |  | Mon 21/11/05 | Thu 08/03/07
5113 | 50573 | Test Scenarios for Mobile Station Receive Diversity, DARP Phase II | MSRD2-TestSc | 2 | Rel-7 | GP | 2005-11-11 08:00 | 2007-02-16 17:00 | 100% | GP-060117 | - | Nokia | kent.pedersen@nokia.com | GP#33 completed | 45.005 |  |  |  |  | Mon 21/11/05 | Thu 08/03/07
5114 | 50570 | MS conformance test of DARP Phase II (MSRD) | MSRD2-Msconf | 2 | Rel-7 | GP | 2005-11-11 08:00 | 2007-11-16 17:00 | 100% | GP-060114 | - | Nokia | kent.pedersen@nokia.com | GP#36 completed | 51.010 |  |  |  |  | Mon 21/11/05 | Wed 12/09/07
5115 | 50579 | Downlink Dual Carrier | GDCDL | 1 | Rel-7 | GP | 2006-01-20 08:00 | 2009-09-04 17:00 | 100% | GP-061331 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#35 completed | - |  |  |  |  | Tue 24/01/06 | Wed 01/04/09
5116 | 51139 | Downlink Dual Carrier Stage 2 | GDCDL-Stage2 | 2 | Rel-7 | G1 | 2006-01-20 08:00 | 2006-06-30 17:00 | 100% | GP-060484 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#30 completed | 43.055, 43.064 |  |  |  |  | Tue 24/01/06 | Wed 01/04/09
5117 | 52142 | Downlink Dual Carrier Stage 3 | GDCDL-Stage3 | 2 | Rel-7 | G1 | 2006-01-20 08:00 | 2007-08-31 17:00 | 100% | GP-060485 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#35 completed | 24.008, 44.018, 44.060, 45.001, 45.002, 45.005, 45.008 |  |  |  |  | Tue 24/01/06 | Wed 01/04/09
5118 | 53086 | Downlink Dual Carrier – MS Conformance Test | GDCDL-MStest | 2 | Rel-7 | G3new | 2006-01-20 08:00 | 2009-09-04 17:00 | 100% | GP-060486 | - | Nokia Siemens Networks | leonardo.provvedi@roke.co.uk | GP#43 completed | 51.010 |  |  |  |  | Tue 24/01/06 | Mon 07/09/09
5119 | 50580 | Support of SIGTRAN in GERAN | GSIGT | 1 | Rel-7 | GP | 2006-01-20 08:00 | 2006-06-30 17:00 | 100% | GP-060450 | - | Ericsson | peter.ostrup@ericsson.com | GP#30 completed | 48.001, 48.006, 43.059, 49.031 |  |  |  |  | Tue 24/01/06 | Thu 02/04/09
5120 | 50582 | Latency Reductions | LATRED | 1 | Rel-7 | GP | 2006-06-30 08:00 | 2007-08-31 17:00 | 100% | GP-061519 | - | Ericsson | Hakan.Persson@Ericsson.com | GP#35 completed | 45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021 |  |  |  |  | Wed 05/07/06 | Wed 12/09/07
5121 | 52145 | Improved Ack/Nack reporting | LATRED-ACKNAR | 2 | Rel-7 | G2 | 2006-06-30 08:00 | 2007-08-31 17:00 | 100% | GP-061520 | - | Ericsson | Hakan.Persson@Ericsson.com | GP#35 completed | 45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021 |  |  |  |  | Wed 05/07/06 | Mon 15/12/08
5122 | 52146 | Reduced TTI | LATRED-REDTTI | 2 | Rel-7 | G2 | 2006-06-30 08:00 | 2007-08-31 17:00 | 100% | GP-061521 | - | Ericsson | Hakan.Persson@Ericsson.com | GP#35 completed | 45.001, 45.002, 45.003, 45.005, 45.010, 43.055, 43.064, 44.060, 51.010-1, 51.021 |  |  |  |  | Wed 05/07/06 | Mon 15/12/08
5123 | 52147 | PS Handover between GERAN/UTRAN mode and GAN Mode | GUGAN | 1 | Rel-7 | G2 | 2006-06-30 08:00 | 2007-02-16 17:00 | 100% | GP-061349 | - | Ericsson | John.Diachina@Ericsson.com | GP#33 completed | 43.318, 44.318, 43.129, 25.306, 24.008, 44.060, 25.331, 51.010 |  |  |  |  | Wed 05/07/06 | Mon 15/12/08
5124 | 50584 | Higher Uplink performance for GERAN Evolution | HUGE | 1 | Rel-7 | GP | 2006-09-08 08:00 | 2011-05-20 17:00 | 100% | GP-071083 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#39 completed | - |  |  |  |  | Wed 13/09/06 | Mon 26/07/10
5125 | 51140 | Stage 2 for HUGE | HUGE-Stage2 | 2 | Rel-7 | G1 | 2006-09-08 08:00 | 2007-09-07 17:00 | 100% | GP-061902 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#35 completed | 43.055, 43.064 |  |  |  |  | Wed 13/09/06 | Mon 15/12/08
5126 | 51141 | Layer 1 Support for HUGE | HUGE-Layer1 | 2 | Rel-7 | G1 | 2006-09-08 08:00 | 2008-02-22 17:00 | 100% | GP-061903 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#37 completed | 45.001, 45.002, 45.003, 45.004, 45.008 |  |  |  |  | Wed 13/09/06 | Mon 15/12/08
5127 | 52149 | Layer 2/3 Support for HUGE | HUGE-Layer23 | 2 | Rel-7 | G2 | 2006-09-08 08:00 | 2007-08-31 17:00 | 100% | GP-061904 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#35 completed | 24.008, 44.018, 44.060 |  |  |  |  | Wed 13/09/06 | Mon 15/12/08
5128 | 51142 | Performance requirements for HUGE | HUGE-Perfreq | 2 | Rel-7 | G1 | 2006-09-08 08:00 | 2008-08-29 17:00 | 100% | GP-061905 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#39 completed | 45.005 |  |  |  |  | Wed 13/09/06 | Mon 15/12/08
5129 | 51143 | BTS Conformance Test for HUGE | HUGE-BTStest | 2 | Rel-7 | G1 | 2006-09-08 08:00 | 2009-09-04 17:00 | 100% | GP-061907 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#43 completed | 51.021 |  |  |  |  | Wed 13/09/06 | Mon 07/09/09
5130 | 53087 | MS Conformance Test for HUGE | HUGE-Mstest | 2 | Rel-7 | G3new | 2006-09-08 08:00 | 2011-05-20 17:00 | 100% | GP-061906 | - | Nokia Siemens Networks, Ericsson | eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com | GP#50 completed | 51.010 |  |  |  |  | Wed 13/09/06 | Sat 21/05/11
5131 | 50121 | REduced symbol Duration, Higher Order modulation and Turbo coding (RED HOT) for downlink | REDHOT | 1 | Rel-7 | GP | 2006-11-17 08:00 | 2011-05-20 17:00 | 100% | GP-071080 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#38 completed | - |  |  |  |  | Mon 20/11/06 | Mon 15/12/08
5132 | 51144 | Stage 2 for REDHOT | REDHOT-Stage2 | 2 | Rel-7 | G1 | 2006-11-17 08:00 | 2007-08-31 17:00 | 100% | GP-062489 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#35 completed | 43.055, 43.064 |  |  |  |  | Mon 20/11/06 | Mon 15/12/08
5133 | 51145 | Stage 3 for REDHOT | REDHOT-Stage3 | 2 | Rel-7 | G1 | 2006-11-17 08:00 | 2008-05-16 17:00 | 100% | GP-062490 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#38 completed | 24.008, 44.018, 44.060, 45.001, 45.002, 45.003, 45.004, 45.005, 45.008 |  |  |  |  | Mon 20/11/06 | Mon 15/12/08
5134 | 51146 | BTS Conformance Tests for REDHOT | REDHOT-BTStest | 2 | Rel-7 | G1 | 2006-11-17 08:00 | 2009-05-15 17:00 | 100% | GP-062492 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#42 completed | 51.021 |  |  |  |  | Mon 20/11/06 | Mon 18/05/09
5135 | 53088 | MS Conformance Tests for REDHOT | REDHOT-Mstest | 2 | Rel-7 | G3new | 2006-11-17 08:00 | 2011-05-20 17:00 | 100% | GP-062491 | - | Ericsson, Nokia Siemens Networks, Marvell | stefan.g.eriksson@ericsson.com | GP#50 completed | 51.010 |  |  |  |  | Mon 20/11/06 | Sat 21/05/11
5136 | 60110 | (Small) Technical Enhancements and Improvements for Rel-7 | TEI7 | 1 | Rel-7 | SP,CP,RP,GP | 2007-03-26 17:00 | 2007-03-26 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 04/11/05 | Thu 20/04/06
5137 | 25030 | Test - (Small) Technical Enhancements and Improvements for Rel-7 | TEI7_Test | 1 | Rel-7 | R5 | 2006-06-02 08:00 | 2007-11-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 26/05/10 | Wed 26/05/10
5138 | 32113 | Deleted - PS domain and IMS support for IMS Emergency sessions | IMS-EMER | 1 | Rel-7 | S2 | 2006-06-23 17:00 | 2006-06-23 17:00 | 100% | SP-050604 | - | Nokia | curt.c.wong@nokia.com | Approved at SP#29 | 23.867, 23.abc, 23.060, 23.002, 23.271 |  |  | SP-30 |  | Fri 28/03/03 | Thu 22/12/05
5139 | 32114 | Deleted - IMS aspects to support IMS Emergency sessions | - | 2 | Rel-7 | S2 | 2006-06-23 17:00 | 2006-06-23 17:00 | 100% | SP-050604 | - | Nokia | curt.c.wong@nokia.com | Approved at SP#29 | 23.867, 23.abc, 23.060, 23.002, 23.271 |  |  | SP-30 |  | Tue 22/03/05 | Thu 22/12/05
5140 | 32115 | Deleted - PS domain aspects to support IMS Emergency sessions | - | 2 | Rel-7 | S2 | 2006-06-23 17:00 | 2006-06-23 17:00 | 100% | SP-050604 | - | Nokia | curt.c.wong@nokia.com | Approved at SP#29 | 23.867, 23.abc, 23.060, 23.002, 23.271 |  |  | SP-30 |  | Tue 22/03/05 | Thu 22/12/05
5141 | 32005 | Deleted - IMS Local services | IMSLocal | 1 | Rel-7 | S2 | 2006-01-06 08:00 | 2006-01-06 08:00 | 99% | - | - | - | - | - | 23.228 |  |  | SP-28 |  | Mon 08/10/01 | Thu 30/05/02
5142 | 32019 | Deleted - Stage 2 | - | 2 | Rel-7 | S2 | 2006-01-06 08:00 | 2006-01-06 08:00 | 100% | - | - | - | - | DAB - Not yet required in SA2 as it exists in previous releases | - |  |  | SP-26 |  | Mon 25/03/02 | Mon 06/12/04
5143 | 11035 | Deleted - Stage 3 for IMS Local services | - | 2 | Rel-7 | C1 | 2006-01-06 08:00 | 2006-01-06 08:00 | 100% | - | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  | SP-25 |  | Mon 13/01/03 | Thu 09/09/04
5144 | 32078 | Deleted - IMS Phase 3 | - | 1 | Rel-7 | S2 | 2006-01-06 08:00 | 2006-01-06 08:00 | 100% | - | - | - | - | - | - |  |  | SP-25 |  | Wed 08/09/04 | Thu 09/09/04
5145 | 701216 | Deleted - Improvements of Radio Interface | - | 1 | Rel-7 | RP | 2004-09-15 08:00 | 2004-09-15 08:00 | 100% | - | - | - | - | Stage 2 description of Interim conclusion | - | 70 | 36 | SP-24 |  | Fri 31/03/00 | Thu 08/07/04
5146 | 14018 | Deleted: Generic User Profile Phase 2 | - | 1 | Rel-7 | C4 | 2005-08-08 13:48 | 2006-06-30 17:00 | 100% | - | - | - | - | Created at TSG#27 by A. Sultan because of the move to Rel-7 of "Common Objects". | - |  |  | SP-27 |  | Wed 09/03/05 | Wed 09/03/05
5147 | 42003 | Deleted - Stage 3 - Common objects | - | 1 | Rel-7 | C4 | 2005-08-08 13:48 | 2005-08-08 13:48 | 100% | TP-020275 | - | - | - | No progress in CN4#26. This have to be moved to Rel-7. It was deleted from WID | 24.241 |  |  | SP-27 |  | Tue 09/10/01 | Wed 09/03/05
5148 | 0 | Release 7 Studies | - | 1 | Rel-7 | CP,GP,RP,SP | 2004-06-28 08:00 | 2007-09-17 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 08/09/04 | Tue 09/02/10
5149 | 31082 | Study on Multimedia Telephony Capabilities for IMS | MITE | 1 | Rel-7 | S1 | 2005-07-11 08:00 | 2006-07-31 17:00 | 100% | SP-050387 | - | Ericsson | peter.bleckert@ericsson.com | Spin-off Feature UID_7038 (MTSI) | 22.973 |  |  |  |  | Thu 21/04/05 | Tue 01/07/08
5150 | 31050 | Study on Behaviour of Multi system UEs | BMSU | 1 | Rel-7 | S1 | 2004-06-28 08:00 | 2005-12-15 17:00 | 100% | SP-050502 | - | Qualcomm | dwilliams@qualcomm.com | - | 22.936 |  |  |  |  | Mon 30/08/04 | Fri 27/06/08
5151 | 31055 | Study on Combining CS calls and IMS sessions | IRTSD-CS_IMS | 1 | Rel-7 | S1 | 2004-06-28 08:00 | 2005-03-17 17:00 | 100% | SP-040467 | - | TeliaSonera | robert.frank@teliasonera.com | - | 22.979 |  |  |  |  | Mon 30/08/04 | Tue 27/07/10
5152 | 31059 | Study on All-IP Network | FS_AIPN | 1 | Rel-7 | S1 | 2004-06-28 08:00 | 2005-03-16 17:00 | 100% | SP-040303 | - | NTT DoCoMo | Shin-ichi Isobe (isobes@nttdocomo.co.jp) | 07/08 Moved to Rel-7 as Study out of stopped Rel-8 Feature UID_31067 All-IP Network (AIPN) | 22.978 |  |  |  |  | Mon 30/08/04 | Tue 31/08/10
5153 | 31075 | Study on Videotelephony teleservice | VidTel | 1 | Rel-7 | S1 | 2005-03-01 08:00 | 2006-01-17 17:00 | 100% | SP-050506 | - | T-Mobile | michael.kurz@t-mobile.at | - | 22.903 |  |  |  |  | Tue 22/03/05 | Fri 27/06/08
5154 | 31073 | Study on Network Selection Principles | NetSel | 1 | Rel-7 | S1 | 2005-03-15 08:00 | 2005-12-08 17:00 | 100% | SP-050227 | - | O2 | chris.friel@O2.com | Spin-off Feature Network selection enhancements (NSP-CR) UID_7041 | 22.811 |  |  |  |  | Tue 22/03/05 | Fri 27/06/08
5155 | 31041 | Study on Multimedia Priority Service | PRIOR-MM | 1 | Rel-7 | S1 | 2003-03-28 08:00 | 2006-06-30 17:00 | 100% | SP-060329 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | Spin-off Feature PRIOR UID_340044 | 22.953 |  |  |  |  | Fri 28/03/03 | Tue 31/08/10
5156 | 31083 | Study on Transferring of emergency Call data | eCALL | 1 | Rel-7 | S1 | 2005-07-11 08:00 | 2006-03-31 17:00 | 100% | SP-050388 | - | Motorola | jian.j.wu@motorola.com | - | 22.967 |  |  |  |  | Mon 20/06/05 | Tue 31/08/10
5157 | 32073 | Study on Enhancement of E2E QoS | QoS7 | 1 | Rel-7 | S2 | 2004-06-28 08:00 | 2005-09-15 17:00 | 100% | SP-040326 | - | Huawei | Robert Jaksa | - | 23.802 |  |  |  |  | Mon 30/08/04 | Mon 30/06/08
5158 | 35066 | Study on SOAP/HTTP IRP Solution Sets | OAM7-NIM-XML | 1 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-07 17:00 | 100% | SP-050610 | - | Nortel | Suzèle Lariven (lariven@nortel.com) | SP#34 completed | 32.809 |  |  |  |  | Fri 16/09/05 | Tue 27/07/10
5159 | 35067 | Study on Itf-N Implementation Conformance Statement (ICS) template | OAM7-NIM-ICS | 1 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050609 | - | China Mobile | Li Yewen (liyewen@chinamobile.com) | SP#35 completed | 32.812 |  |  |  |  | Fri 16/09/05 | Thu 29/03/07
5160 | 35068 | Study on IRP Information Model | OAM7-NIM-IM | 1 | Rel-7 | S5 | 2005-09-02 08:00 | 2007-03-15 17:00 | 100% | SP-050611 | - | Motorola | trevor.pirt@motorola.com | SP#35 completed | 32.810 |  |  |  |  | Fri 16/09/05 | Tue 27/07/10
5161 | 7034 | Study on Bandwidth Saving at Nb Interface with IP transport | BSNbIP | 1 | Rel-7 | C3 | 2006-03-10 08:00 | 2007-03-09 17:00 | 100% | CP-060438 | - | Siemens | Thomas.Belling@siemens.com | Moved to FS at CT32 (in line with slides) | 29.814 |  |  |  |  | Mon 20/03/06 | Tue 27/07/10
5162 | 14019 | Study on Routeing of MT-SMS via the HPLMN | SMS7 | 1 | Rel-7 | C4 | 2005-10-07 08:00 | 2006-12-01 17:00 | 100% | CP-060701 | - | Vodafone | Nick.Russell@vodafone.com | Previously known as "Study of a SMS Centre for MT SMS" | 23.840 |  |  |  |  | Fri 07/10/05 | Mon 30/06/08
5163 | 7025 | Feasibility Study on the TCAPsec Gateway concept | FS_SEC7-TCAP | 1 | Rel-7 | C4 | 2005-10-28 08:00 | 2006-03-10 17:00 | 100% | CP-050687 | - | Siemens | Ulrich.wiehe@gksag.de | TR 29.800 content moved to TS 29.204 under implementation WI UID_310005 TCAPsec Gateway | 29.800 |  |  |  |  | Fri 07/10/05 | Tue 01/07/08
5164 | 7050 | Study on using M2PA in 3GPP network | FS-M2PA | 1 | Rel-7 | C4 | 2006-03-22 08:00 | 2007-06-08 17:00 | 100% | CP-060698 | - | China Mobile | zhaoyuyi@chinamobile.com | - | 29.801 |  |  |  |  | Wed 22/03/06 | Tue 01/07/08
5165 | 320018 | Study on Support of (G)MSC-S - (G)MSC-S Nc Interface based on the SIP-I protocol | NcSIP | 1 | Rel-7 | C4,C3 | 2006-05-15 08:00 | 2007-09-14 17:00 | 100% | CP-070034 | - | Vodafone | david.hutton@vodafone.com | - | 29.802 | 32 |  |  |  | Wed 21/06/06 | Tue 01/07/08
5166 | 330002 | CT4 aspects of NcSIP | - | 2 | Rel-7 | C4 | 2006-05-15 08:00 | 2007-06-01 17:00 | 100% | CP-070034 | - | Vodafone | david.hutton@vodafone.com | - | 29.802 |  |  |  |  | Thu 21/09/06 | Tue 01/07/08
5167 | 330003 | CT3 aspects of NcSIP | - | 2 | Rel-7 | C3 | 2006-05-15 08:00 | 2007-09-14 17:00 | 100% | CP-070034 | - | Ericsson | ragnar.huslende@ericsson.com | - | 29.802 |  |  |  |  | Thu 21/09/06 | Tue 01/07/08
5168 | 20023 | Study on Evolved UTRA and UTRAN | RANFS-Evo | 1 | Rel-7 | RP | 2004-12-15 08:00 | 2006-09-15 17:00 | 100% | RP-040461 | RP-060472 | NTT DoCoMo | nakamurata@NTTDOCOMO.CO.JP | RP#33 (Sep 2006) completed. SR in RP-060472 | 25.912 |  |  |  |  | Tue 04/01/05 | Mon 23/06/08
5169 | 20034 | Study on Performance Evaluation of the UE behaviour in high speed trains with speeds up to 350 kmph | RANFS-HSTrains | 1 | Rel-7 | R4 | 2005-03-15 | 2006-06-15 17:00 | 100% | RP-050146 | RP-060412 | Vodafone | Mike.vogel@vodafone.com,tim.frost@vodafone.com | RP#32 (Jun 2006) completed. SR in RP-060412 | none |  |  |  |  | Tue 15/03/05 | Mon 23/06/08
5170 | 20041 | Study on UTRA Tower Mounted Amplifier (FDD) | RANFS-TMA | 1 | Rel-7 | R4 | 2005-06-15 08:00 | 2006-03-14 17:00 | 100% | RP-050387 | RP-060035 | Ericsson | Klas.Sjerling@ericsson.com | RP#31 (Mar 2006) completed. SR in RP-060035 | 25.818 |  |  |  |  | Mon 20/06/05 | Tue 27/07/10
5171 | 20044 | Study on Continuous connectivity for packet data users | RANFS-cont-packet | 1 | Rel-7 | R1 | 2005-03-15 08:00 | 2005-09-14 17:00 | 100% | RP-050391 | RP-050427 | Siemens | joerg.gustrau@siemens.com | RP#29 (Sep 2006) completed. SR in RP-050427 | none |  |  |  |  | Mon 20/06/05 | Mon 23/06/08
5172 | 20051 | Study on Improvement of the Multimedia Broadcast Multicast Service (MBMS) in UTRAN | RANFS-MBMSImp | 1 | Rel-7 | R2 | 2005-12-15 08:00 | 2006-12-15 17:00 | 100% | RP-050746 | RP-060692 | LG Electronics | leego@lge.com | RP#34 completed | 25.905 |  |  |  |  | Thu 15/12/05 | Thu 26/07/12
5173 | 20052 | Deleted - Study on Performance Improvements in Small Cells using HSDPA/EDCH | SMALLCELLS | 1 | Rel-7 | R1,R4 | 2005-12-15 08:00 | 2006-06-15 17:00 | 100% | RP-050782 | RP-060263 | Cingular | Marc Grant | RP#32 (Jun 2006) stopped at 0% completion | none |  |  | SP-69 |  | Thu 15/12/05 | Mon 23/06/08
5174 | 20053 | Study on Further Improved Performance Requirements for UMTS/HSDPA UE (FDD) | RANFS-IC | 1 | Rel-7 | R4 | 2005-12-15 08:00 | 2007-06-04 17:00 | 100% | RP-050880 | RP-070499 | Cingular | Marc Grant | RP#36 (May 2007) completed. SR in RP-070499 | 25.963 |  |  |  |  | Thu 15/12/05 | Mon 23/06/08
5175 | 20065 | Study on Scope of future FDD HSPA Evolution | RANFS-HSPAEvo | 1 | Rel-7 | RP | 2006-03-15 08:00 | 2007-09-17 17:00 | 100% | RP-060217 | RP-070533 | Cingular | Don Zelmer (dz1069@att.com) | RP#37 (Sep 2007) completed. SR in RP-070533 | 25.999 |  |  |  |  | Tue 21/03/06 | Mon 23/06/08
5176 | 330013 | Study on Dynamically reconfiguring a FDD UE receiver to reduce power consumption when desired Quality of Service is met | FSUEPow | 1 | Rel-7 | R4 | 2007-06-22 17:00 | 2007-06-22 17:00 | 100% | RP-060641 | RP-070534 | Nokia | Chris.callender@nokia.com, tiina.s.koskinen@nokia.com | RP#37 (Sep 2007) completed. SR in RP-070534 | 25.906 |  |  |  |  | Fri 06/10/06 | Mon 23/06/08
5177 | 50568 | Study on Future GERAN Evolution | FGE | 1 | Rel-7 | GP | 2005-04-08 08:00 | 2007-02-16 17:00 | 100% | GP-051052 | - | Nokia | eddie.riddington@nokia.com | GP#33 completed | 45.912 |  |  |  |  | Thu 21/04/05 | Thu 08/03/07
5178 | 50120 | Study on GAN Enhancements | EGAN | 1 | Rel-7 | GP | 2007-08-31 17:00 | 2007-08-31 17:00 | 100% | GP-062298 | - | T-Mobile | janne.linkola@t-mobile.com | GP#35 completed | 43.902 |  |  |  |  | Mon 20/11/06 | Tue 29/05/07
5179 | 31054 | Deleted - Study on IMS with real time services deployment | IRTSD | 1 | Rel-7 | S1 | 2004-06-28 08:00 | 2005-09-12 17:00 | 100% | SP-040465 | - | - | - | - | - |  |  | SP-30 |  | Mon 30/08/04 | Fri 27/06/08
5180 | 31077 | Deleted - Covered by SI - Personal Network (PN) and Personal Area Network (PAN) | PNPAN | 1 | Rel-7 | S1 | 2005-12-08 17:00 | 2005-12-08 17:00 | 100% | SP-050386 | - | Vodafone | armin.toepfer@vodafone.com | - | - |  |  | SP-30 |  | Thu 21/04/05 | Thu 22/12/05
5181 | 31087 | Deleted - Study on Customised Alerting Tone (CAT) Requirements (was duplicated) | - | 1 | Rel-7 | S1 | 2006-06-30 17:00 | 2006-06-30 17:00 | 100% | SP-050607 | - | - | - | Awaiting MCC SA3 input | - |  |  | SP-31 |  | Fri 04/11/05 | Wed 22/03/06
5182 | 732028 | Deleted - IMS security extensions (covered by UID33027) | IMS-SE | 1 | Rel-7 | S3 | 2005-12-08 17:00 | 2005-12-08 17:00 | 100% | SP-050395 | - | Ericsson | Bengt.Sahlin@ericsson.com | - | - |  |  | SP-30 |  | Mon 20/06/05 | Thu 22/12/05
5183 | 32029 | Deleted - Study on applicability of GALILEO for LCS | Galileo | 1 | Rel-7 | S2 | 2005-06-30 17:00 | 2005-06-30 17:00 | 100% | SP-020541 | - | - | - | - | - |  |  | SP-25 |  | Fri 08/11/02 | Wed 08/09/04
5184 | 32058 | Deleted - TR on Stage 2 | - | 2 | Rel-7 | S2 | 2005-06-30 17:00 | 2005-06-30 17:00 | 100% | - | - | - | - | - | - |  |  | SP-25 |  | Wed 23/07/03 | Thu 21/10/04
5185 | 50095 | Deleted - GERAN review of the TR | - | 2 | Rel-7 | GP | 2005-06-30 17:00 | 2005-06-30 17:00 | 100% | - | - | - | - | - | - |  |  | SP-26 |  | Wed 23/07/03 | Mon 06/12/04
5186 | 32076 | Deleted - Study on Stage 2 (IMS services using CS bearers) | IRTSD-IMSCS | 1 | Rel-7 | S2 | 2004-06-28 08:00 | 2005-09-12 17:00 | 100% | SP-040479 | - | Nortel | Mark Watson | SP-30: S2 has no intention for TR completion | 23.899 |  |  | SP-30 |  | Mon 30/08/04 | Thu 26/06/08
5187 | 32099 | Deleted - VoIMS bearer related enhancements | VoIMS | 1 | Rel-7 | S2 | 2006-07-21 17:00 | 2006-07-21 17:00 | 100% | - | - | - | - | Created by MCC to group all VoIMS related items, after consultation of chairs | - |  |  | SP-32 |  | Thu 15/09/05 | Wed 25/06/08
5188 | 32098 | Deleted - Study on enhancement of radio performance for VoIMS | - | 2 | Rel-7 | S2 | 2006-07-21 17:00 | 2006-07-21 17:00 | 100% | SP-050351 | - | Nortel | Laurence Lautier (lautierl@nortel.com) | WID approved SP#28. SA2#52 stopped | 23.807 |  |  | SP-32 |  | Wed 22/06/05 | Wed 31/05/06
5189 | 32112 | Deleted - Study on IMS enhancements and optimizations for real time communication. | IMS-RT | 1 | Rel-7 | S2 | 2005-10-10 08:00 | 2007-06-01 17:00 | 100% | SP-050492 | - | Ericsson | stephen.terrill@ericsson.com | abandoned at 65% | 23.818 |  |  | SP-35 |  | Thu 16/02/06 | Fri 22/06/07
5190 | 32117 | Deleted - Study on Terminating Session handling | CSIterm | 1 | Rel-7 | S2 | 2006-01-09 08:00 | 2006-12-29 17:00 | 100% | SP-050811 | - | Samsung | - | SP#32 Jun 2006 Study abandoned => spin-off Implementation work UID_320029 | 23.819 |  |  | SP-32 |  | Tue 20/12/05 | Mon 30/06/08
5191 | 34040 | Deleted eCALLIBMS - Study on Transferring of emergency call data – in-band modem solution (moved to Rel-8) | - | 1 | Rel-7 | S4 | 2007-06-22 17:00 | 2007-06-22 17:00 | 100% | SP-060935 | - | Airbiquity | lhong@airbiquity.com | SP-38 stopped | 26.967 |  |  | SP-38 |  | Sun 10/12/06 | Fri 22/06/07
5192 | 35045 | Deleted - Study on IRP usage scenarios | OAM-Study | 1 | Rel-7 | S5 | 2005-09-02 08:00 | 2006-12-07 17:00 | 100% | SP-050303 | - | Lucent | - | - | 32.8xy |  |  | SP-32 |  | Fri 17/06/05 | Thu 29/03/07
5193 | 360009 | Deleted - Study on Interference Cancellation for UTRA FDD UE (covered by UID 20053) | RANFS-InterfCanc | 1 | Rel-7 | R4 | 2007-03-28 08:00 | 2007-03-28 17:00 | 100% | - | - | - | - | Deleted. Same as FS on Further Improved Performance Requirements for UMTS/HSDPA UE (FDD) | - | 36 |  | SP-38 |  | Thu 21/06/07 | Thu 10/01/08
5194 | 50552 | Deleted - Study on enhanced support of Video Telephony | VIDGER | 1 | Rel-7 | GP | 2006-06-30 17:00 | 2006-06-30 17:00 | 100% | GP-042221 | - | Ericsson | stefan.g.eriksson@ericsson.com | FS CLOSED at G#28 (no input) | - |  |  | SP-32 |  | Fri 15/10/04 | Thu 09/03/06
5195 | 0 | Release 6 Features | - | 1 | Rel-6 | NP,GP,RP,SP,TP | 2002-06-28 17:00 | 2005-12-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 11/07/08 | Tue 09/02/10
5196 | 1216 | Rel-6 Improvements of Radio Interface | - | 1 | Rel-6 | R2,R4,R5 | 2000-08-14 08:00 | 2006-12-01 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Thu 08/07/04
5197 | 20032 | Improved support of IMS Realtime Services using HSDPA/EDCH | RInImp-IMSRealTime | 2 | Rel-6 | R2 | 2005-03-15 | 2005-12-14 17:00 | 100% | - | - | Cingular | Don Zelmer (dz1069@att.com) | - | - |  |  |  |  | Mon 20/06/05 | Fri 13/01/06
5198 | 24006 | Improving Receiver Performance Requirements for the FDD UE | RInImp-UERecPerf | 2 | Rel-6 | R4 | 2002-03-08 08:00 | 2003-09-19 17:00 | 100% | - | - | Intel | shimon.moshavi@INTEL.COM | - | 25.101 |  |  |  |  | Thu 02/10/03 | Thu 08/07/04
5199 | 24004 | Base station classification for FDD | RInImp-BSClass-FDD | 2 | Rel-6 | R4 | 2000-08-14 08:00 | 2002-12-04 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 16/09/02 | Thu 08/07/04
5200 | 1476 | FDD Base station classification | - | 3 | Rel-6 | R4 | 2000-08-14 08:00 | 2002-12-04 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | 25.104, 25.141 |  |  |  |  | Wed 26/07/00 | Thu 08/07/04
5201 | 24007 | UMTS-850 | RInImp-UMTS850 | 2 | Rel-6 | R4 | 2002-12-06 08:00 | 2003-12-12 17:00 | 100% | - | - | Cingular | Don Zelmer (dz1069@att.com) | Introduction of UMTS850 (Band V) in 25.307 | 25.101, 25.104, 25.133, 25.141, 25.307, 25.331, 25.942 |  |  |  |  | Thu 02/10/03 | Thu 09/07/09
5202 | 24009 | DS-CDMA introduction in the 800 MHz band | RInImp-UMTS800 | 2 | Rel-6 | R4 | 2003-03-14 08:00 | 2003-12-12 17:00 | 100% | - | - | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | Introduction of UMTS800 in 25.307 | 25.101, 25.104, 25.133, 25.141, 25.307, 25.331 |  |  |  |  | Thu 02/10/03 | Thu 09/07/09
5203 | 24010 | UMTS 1.7/2.1 GHz | RInImp-UMTS1721 | 2 | Rel-6 | R4 | 2003-03-14 08:00 | 2003-03-14 08:00 | 100% | - | - | Nokia | jussi.numminen@NOKIA.COM | Introduction of UMTS1700/2100 (Band IV) | 25.101, 25.104, 25.133, 25.141, 25.307, 25.331 |  |  |  |  | Thu 02/10/03 | Thu 09/07/09
5204 | 25010 | Conformance Test Aspects – UMTS 1.7/2.1 GHz Band | RInImp-UMTS1721_Test | 2 | Rel-6 | R5 | 2006-03-10 08:00 | 2006-12-01 17:00 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | TS34.121, TS34.108 |  |  |  |  | Tue 21/03/06 | Wed 16/06/10
5205 | 24013 | Improved Receiver Performance Requirements for HSDPA | RInImp-HSPerf | 2 | Rel-6 | R4,R5 | 2003-09-19 08:00 | 2006-06-09 17:00 | 100% | - | - | Nokia | jussi.numminen@NOKIA.COM | - | - |  |  |  |  | Tue 13/01/04 | Thu 08/07/04
5206 | 20011 | Improved Minimum Performance Requirements for HSDPA UE categories 7 and 8 | RInImp-HSPerf-10code | 3 | Rel-6 | R4 | 2004-09-15 | 2006-06-09 17:00 | 100% | - | - | Nokia | jussi.numminen@nokia.com | Approved at RP#25 as RP-040375 | 25.101 |  |  |  |  | Mon 27/09/04 | Fri 13/01/06
5207 | 25001 | Testing of Improved Minimum Performance for HSDPA | RInImp-HSPerf-10Code_Test | 3 | Rel-6 | R5 | 2003-09-19 08:00 | 2006-03-16 17:00 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Mon 27/09/04 | Wed 16/06/10
5208 | 24014 | Performance Requirements of Receive Diversity for HSDPA | RInImp-HSPerf-RxDiv | 3 | Rel-6 | R4 | 2003-12-15 | 2005-06-07 17:00 | 100% | - | - | NTT DoCoMo | Takehiro Nakamura (nakamurata@nttdocomo.co.jp) | - | 25.101 |  |  |  |  | Tue 13/01/04 | Fri 25/03/05
5209 | 25002 | Testing of Performance of Receiver diversity for HSDPA | RInImp-HSPerf-RxDiv_Test | 3 | Rel-6 | R5 | 2003-09-19 08:00 | 2006-03-16 17:00 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Mon 27/09/04 | Wed 16/06/10
5210 | 3 | Rel-6 RAN Feasibility Studies | - | 1 | Rel-6 | RP | 2000-08-14 08:00 | 2005-03-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 07/12/03 | Sun 07/12/03
5211 | 23007 | FS of the improved access to UE measurement data for CRNC to support TDD RRM | RANimp-RRMopt-FSUEMsD | 2 | Rel-6 | R3 | 2002-12-06 08:00 | 2003-12-18 17:00 | 100% | - | - | Interdigital | jim.miller@interdigital.com | - | 25.801, 25.423 |  |  |  |  | Thu 13/02/03 | Thu 21/10/04
5212 | 1506 | FS on Radio link performance enhancements | RInImp-Rlperf | 2 | Rel-6 | R1 | 2000-08-14 08:00 | 2004-09-14 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | Study finished at RP#25 | 25.899 |  |  |  |  | Thu 02/10/03 | Wed 13/10/04
5213 | 21000 | FS on Improvement of inter-frequency and inter-system measurements for 1.28 Mcps TDD | RInImp-IfIsMLCR | 2 | Rel-6 | R1 | 2001-12-14 08:00 | 2003-09-19 17:00 | 100% | - | - | Samsung | Li Xiao Qiang (xqli@samsung.co.kr) | - | 25.888 |  |  |  |  | Thu 02/10/03 | Thu 08/07/04
5214 | 21003 | FS for the analysis of OFDM for UTRAN enhancement | RInImp-FSOFDM | 2 | Rel-6 | R1 | 2002-06-10 08:00 | 2004-06-14 17:00 | 100% | - | - | Nortel | Sarah Boumendil | - | 25.892 |  |  |  |  | Thu 02/10/03 | Thu 08/07/04
5215 | 21004 | FS on Uplink Enhancements for Dedicated Transport Channels | RInImp-FSUpDTrCh | 2 | Rel-6 | R1 | 2002-09-06 08:00 | 2004-03-12 17:00 | 100% | - | - | Nokia | Karri.Ranta-aho@nsn.com | - | 25.896 |  |  |  |  | Thu 02/10/03 | Thu 08/07/04
5216 | 21005 | FS on Analysis on Higher Chip Rates for UTRA TDD evolutions | RInImp-FSVHCRTDD | 2 | Rel-6 | R1 | 2002-09-06 08:00 | 2004-09-14 17:00 | 100% | - | - | IPWireless | mbeale@ipwireless.com | Study finished at RP#25 | 25.895 |  |  |  |  | Thu 02/10/03 | Wed 13/10/04
5217 | 24011 | FS on Low Output Powers for general purpose FDD BSs | RInImp-FSLoPw | 2 | Rel-6 | R3 | 2003-06-13 08:00 | 2004-03-12 17:00 | 100% | - | - | Telefónica | Ana Burgos (burgos_a@tsm.es) | - | 25.807 |  |  |  |  | Thu 02/10/03 | Thu 08/07/04
5218 | 21007 | FS on Uplink enhancements for UTRA TDD | RInImp-FSUpEnhTDD | 2 | Rel-6 | R1 | 2003-06-06 08:00 | 2005-03-14 17:00 | 100% | - | - | Interdigital | Marian.Rudolf@InterDigital.com | - | 25.804 |  |  |  |  | Thu 02/10/03 | Fri 25/03/05
5219 | 24005 | FS on UE antenna efficiency test methods performance requirements (2) | RInImp-UEAnTM2 | 2 | Rel-6 | R4 | 2002-03-08 08:00 | 2002-09-06 17:00 | 100% | - | - | Allgon | Alf Ahlström (alf.ahlstrom@pwav.com) | The RInImp-UEAnTM FS was re-opened at TSG RP#15 upon request from WG4 | - |  |  |  |  | Thu 30/05/02 | Thu 08/07/04
5220 | 23006 | Deleted - FS on the evolution of the UTRAN architecture | RANimp-FSEvo | 2 | Rel-6 | R3 | 2002-09-09 08:00 | 2004-12-14 17:00 | 100% | - | - | Nokia | woonhee.hwang@nsn.com, Antti.Toskala@nokia.com | Study Closed, work will continue within the FS on evolved UTRA and UTRAN | - |  |  | RP-26 |  | Mon 16/09/02 | Thu 13/01/05
5221 | 20003 | FDD Enhanced Uplink | EDCH | 1 | Rel-6 | R2,R1,R3,R4,R5 | 2004-03-15 | 2007-09-14 17:00 | 100% | - | - | Ericsson | Joakim Bergström | - | - |  |  |  |  | Thu 18/03/04 | Thu 08/07/04
5222 | 20004 | FDD Enhanced Uplink - Stage 2 | EDCH-Stage2 | 2 | Rel-6 | R2 | 2004-03-15 08:00 | 2004-12-14 17:00 | 100% | - | - | - | - | - | 25.309 |  |  |  |  | Sun 21/03/04 | Thu 13/01/05
5223 | 20005 | FDD Enhanced Uplink - Physical Layer | EDCH-Phys | 2 | Rel-6 | R1 | 2004-03-15 08:00 | 2005-03-14 17:00 | 100% | - | - | Nokia | Karri.Ranta-aho@nsn.com | - | 25.211, 25.212, 25.213, 25.214, 25.215 |  |  |  |  | Thu 18/03/04 | Fri 25/03/05
5224 | 20006 | FDD Enhanced Uplink - Layer 2 and 3 Protocol Aspects | EDCH-L23 | 2 | Rel-6 | R2 | 2004-03-15 08:00 | 2005-03-14 17:00 | 100% | - | - | Ericsson | Joakim Bergström | - | 25.301, 25.302, 25.306, 25.321, 25.331 |  |  |  |  | Thu 18/03/04 | Fri 25/03/05
5225 | 20007 | FDD Enhanced Uplink - UTRAN Iub/Iur Protocol Aspects | EDCH-IurIub | 2 | Rel-6 | R3 | 2004-03-15 08:00 | 2005-03-14 17:00 | 100% | - | - | Nortel | Saso Stojanovski | - | 25.401, 25.420, 25.423, 25.430, 25.433 |  |  |  |  | Thu 18/03/04 | Fri 25/03/05
5226 | 20008 | FDD Enhanced Uplink - RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | EDCH-RF | 2 | Rel-6 | R4 | 2004-03-15 | 2004-06-24 17:00 | 100% | - | - | Ericsson | thomas.unshelm@ericsson.com | - | 25.101, 25.104, 25.133, 25.141 |  |  |  |  | Thu 18/03/04 | Fri 13/01/06
5227 | 25003 | Conformance Test Aspects – FDD Enhanced Uplink | EDCH_Test | 2 | Rel-6 | R5 | 2005-06-03 08:00 | 2007-09-14 17:00 | 100% | - | - | Ericsson | Leif.Mattisson@ericsson.com | - | 34.108, 34.109, 34.121, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 18/03/04 | Wed 16/06/10
5228 | 9 | Rel-6 RAN improvements | - | 1 | Rel-6 | RP,S5 | 2002-09-09 08:00 | 2005-03-14 17:00 | 100% | - | - | - | - | Generic feature | - |  |  |  |  | Fri 31/03/00 | Thu 08/07/04
5229 | 624 | RAB support enhancement | - | 2 | Rel-6 | R2 | 2003-03-14 08:00 | 2005-03-14 17:00 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | building block without particular end date | 25.862 |  |  |  |  | Fri 31/03/00 | Thu 13/01/05
5230 | 21008 | Optimization of downlink channelisation code utilisation | RANimp-RABSE-CodeOptFDD | 3 | Rel-6 | R1 | 2004-03-12 08:00 | 2005-03-14 17:00 | 100% | - | - | Nortel | Sarah Boumendil | - | - |  |  |  |  | Thu 18/03/04 | Fri 25/03/05
5231 | 21009 | optimization of channelisation code utilisation for 3.84 Mcps TDD | RANimp-RABSE-CodOptTDD | 3 | Rel-6 | R1 | 2004-03-15 08:00 | 2005-03-14 17:00 | 100% | - | - | IPWireless | Nicholas Anderson | WIDS modified in RP#26, RP-040551 | - |  |  |  |  | Thu 18/03/04 | Fri 13/01/06
5232 | 20013 | HS-DPCCH ACK/NACK Enhancement | RANimp-RABSE-ACKNACK | 3 | Rel-6 | R1 | 2004-09-15 08:00 | 2004-12-14 17:00 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | Approved at RP#25 as RP-040390 | 25.212, 25.214, 24.331, 25.433 |  |  |  |  | Mon 27/09/04 | Fri 25/03/05
5233 | 23009 | Deleted - Iu enhancements for IMS support in RAN | RANimp-RABSE-IuEnhIMS | 3 | Rel-6 | R3 | 2003-03-14 08:00 | 2004-06-03 17:00 | 100% | - | - | Nortel | Philippe.Godin@nortelnetworks.com | Closed RP#24 due to the lack of progress | - |  |  | RP-24 |  | Thu 27/03/03 | Fri 13/01/06
5234 | 23005 | Deleted - Improvement of RRM across RNS and RNS/BSS | RANimp-RRM1 | 3 | Rel-6 | R3 | 2003-12-05 17:00 | 2003-12-05 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | abandoned RP-23 | - |  |  | RP-23 |  | Tue 19/10/04 | Thu 21/10/04
5235 | 20999 | Beamforming Enhancements | RANimp-BFE | 2 | Rel-6 | R1 | 2003-09-19 | 2003-12-19 17:00 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | - | 24.215, 25.423, 25.425, 25.433, 25.435 |  |  |  |  | Thu 29/11/01 | Thu 08/07/04
5236 | 23012 | Rel-6 RRM optimization for Iur and Iub | RANimp-RRMopt-UEMsD | 2 | Rel-6 | R3 | 2003-09-19 | 2004-03-12 17:00 | 100% | - | - | Ericsson | Gert-Jan.van.Lieshout@eln.ericsson.se | - | - |  |  |  |  | Thu 27/03/03 | Thu 08/07/04
5237 | 23014 | Improved access to UE measurement data for CRNC to support TDD RRM | - | 3 | Rel-6 | R3 | 2003-09-19 | 2004-03-12 17:00 | 100% | - | - | Interdigital | jim.miller@interdigital.com | - | 25.423 |  |  | RP-22 |  | Thu 02/10/03 | Thu 13/01/05
5238 | 23010 | Remote Control of Electrical Tilting Antennas | RANimp-TiltAnt | 2 | Rel-6 | R3,S5 | 2003-03-14 08:00 | 2004-09-16 17:00 | 100% | - | - | Vodafone | Andreas.Hauser@vodafone.com | - | - |  |  |  |  | Thu 27/03/03 | Wed 14/04/04
5239 | 23015 | Tilting Antenna - RAN aspects | - | 3 | Rel-6 | R3 | 2003-03-14 08:00 | 2004-09-14 17:00 | 100% | - | - | Vodafone | Andreas.Hauser@vodafone.com | Finished at RP#25 | 25.460, 25.461, 25.462, 25.463 |  |  |  |  | Thu 27/03/03 | Wed 13/10/04
5240 | 35023 | OAM&P impacts | RANimp-TiltAnt-OAM | 3 | Rel-6 | S5 | 2004-02-27 08:00 | 2004-09-16 17:00 | 100% | S5-048270 | - | Vodafone | Adrian.Neal@vodafone.com | SP#25 09/2004 completed | 32.804, 32.64x |  |  |  |  | Tue 30/03/04 | Fri 13/01/06
5241 | 23011 | Network Assisted Cell Change (NACC) from UTRAN to GERAN - network-side aspects | RANimp-NACC | 2 | Rel-6 | R3 | 2002-09-09 08:00 | 2004-06-15 17:00 | 100% | - | - | Vodafone | Brendan.McWilliams@gb.vodafone.co.uk | - | - |  |  |  |  | Thu 27/03/03 | Thu 08/07/04
5242 | 32023 | Location Services enhancements 2 | LCS2 | 1 | Rel-6 | S2,S5,N4,R2,R4,R5,OMA | 2001-01-15 08:00 | 2004-12-16 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Fri 21/06/02 | Sat 02/06/12
5243 | 32024 | Improvement on Le interface | - | 2 | Rel-6 | S2,OMA | 2002-06-17 08:00 | 2004-12-15 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Fri 21/06/02 | Mon 21/05/12
5244 | 32051 | Stage 2 for Improvement on Le interface | - | 3 | Rel-6 | S2 | 2002-06-17 08:00 | 2003-09-22 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271 |  |  |  |  | Thu 27/03/03 | Mon 21/05/12
5245 | 32053 | Stage 3 - impacts MLP (Mobile Location Protocol) | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-12-15 17:00 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
5246 | 32001 | Enhanced support for anonymity and user privacy | - | 2 | Rel-6 | S2,OMA | 2002-07-08 08:00 | 2004-12-15 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Wed 19/09/01 | Mon 21/05/12
5247 | 32047 | Stage 2 for Enhanced support for anonymity and user privacy | - | 3 | Rel-6 | S2 | 2002-07-08 08:00 | 2003-06-27 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271 |  |  |  |  | Thu 27/03/03 | Mon 21/05/12
5248 | 32054 | Stage 3 - impacts MLP and RLP | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-12-15 17:00 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
5249 | 32025 | Enhanced inter-GMLC interface | - | 2 | Rel-6 | S2,OMA | 2002-06-24 08:00 | 2004-12-15 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Wed 19/09/01 | Mon 21/05/12
5250 | 32048 | Stage 2 for Enhanced inter-GMLC interface | - | 3 | Rel-6 | S2 | 2002-06-24 08:00 | 2003-09-05 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271 |  |  |  |  | Thu 27/03/03 | Mon 21/05/12
5251 | 32055 | Stage 3 - definition of RLP and PCP | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-12-15 17:00 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
5252 | 32012 | Location Services support for IMS public identities | - | 2 | Rel-6 | S2,OMA | 2003-02-24 08:00 | 2004-12-15 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Thu 24/01/02 | Mon 21/05/12
5253 | 32049 | Stage 2 for Location Services support for IMS public identities | - | 3 | Rel-6 | S2 | 2003-02-24 08:00 | 2004-01-23 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271 |  |  |  |  | Thu 27/03/03 | Mon 21/05/12
5254 | 32056 | OMA Stage 3 for Location Services support for IMS public identities - impacts MLP, RLP and PCP | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-12-15 17:00 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
5255 | 32026 | New area event for location service triggering reports | - | 2 | Rel-6 | S2,N4,OMA | 2002-06-03 08:00 | 2004-12-15 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | - |  |  |  |  | Fri 21/06/02 | Mon 21/05/12
5256 | 32050 | Stage 2 for New area event for location service triggering reports | - | 3 | Rel-6 | S2 | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | SP-030127 | - | Nokia | Jan Kåll | - | 23.002,23.271 |  |  |  |  | Thu 27/03/03 | Mon 21/05/12
5257 | 14015 | Stage 3 for UE-CN signalling | - | 3 | Rel-6 | N4 | 2003-10-09 08:00 | 2004-08-31 17:00 | 100% | SP-030127 | - | Nokia | - | Current stage 3 fullfills stage 2 | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
5258 | 32057 | Stage 3 for New area event for location service triggering reports - impacts MLP, RLP and PCP | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-12-15 17:00 | 100% | SP-040232 | - | OMA | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Wed 23/07/03 | Mon 21/05/12
5259 | 20001 | UE positioning for Location Services enhancements 2 | LCS2-UEpos | 2 | Rel-6 | R2,R4,R5 | 2001-01-15 08:00 | 2004-09-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 16/09/02 | Mon 21/05/12
5260 | 2475 | Open SMLC-SRNC Interface within the UTRAN to support UTRAN Rel-4 positioning methods | LCS-Rel4Pos | 3 | Rel-6 | R2 | 2001-01-15 08:00 | 2003-09-19 17:00 | 100% | - | - | Siemens | Meik.Kottkamp@siemens.com | - | 25.305, 25.401, 25.450, 25.452, 25.453 |  |  |  |  | Tue 20/03/01 | Mon 21/05/12
5261 | 24012 | A-GPS minimum performance specification | LCS-UEPos-AGPSPerf | 3 | Rel-6 | R4,R5 | 2003-06-06 08:00 | 2004-09-14 17:00 | 100% | - | - | AT&T Wireless | donglin.shen@attws.com | RP#25 completed (FDD) | new 25.171, 34.171 (testing) |  |  |  |  | Fri 04/07/03 | Mon 21/05/12
5262 | 22002 | Deleted - FS on Enhancements to OTDOA Positioning using advanced blanking methods | LCS2-UEpos-FSBlank | 3 | Rel-6 | R2 | 2002-07-01 08:00 | 2003-09-19 17:00 | 100% | - | - | Cambridge Positioning Systems | david.bartlett@cursor-system.com | RP#38 Work stopped | new TR 25.894 |  |  | RP-38 |  | Fri 21/06/02 | Mon 21/05/12
5263 | 2457 | Deleted - UE positioning enhancements - other methods | LCS2-UEpos-enh | 3 | Rel-6 | R2 | 2003-09-26 17:00 | 2003-09-26 17:00 | 100% | - | - | Siemens | Meik.Kottkamp@siemens.com | RP#24 Work stopped | - |  |  | RP-24 |  | Tue 19/10/04 | Mon 21/05/12
5264 | 35035 | LCS charging | LCS2-CH | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-12-16 17:00 | 100% | SP-040778 | - | France Telecom | alain.bibas@orange-ft.com | SP#26 completed | new TS 32.271 |  |  |  |  | Fri 29/10/04 | Mon 21/05/12
5265 | 1571 | Rel-6 Security enhancements | SEC16 | 1 | Rel-6 | S3 | 2001-01-03 08:00 | 2004-11-26 17:00 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | SP#9 approved WID. Acronym changed from "SEC1, Rel-6" | - |  |  |  |  | Sun 09/04/00 | Tue 24/03/15
5266 | 2026 | Enhanced HE control of security (including positive authentication reporting) | - | 2 | Rel-6 | S3 | 2001-01-03 08:00 | 2003-09-25 17:00 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | SP#9 approved WID S3-000490 (Enhanced home control of security by HE) | 33.102 |  |  |  |  | Fri 22/09/00 | Mon 08/08/11
5267 | 2027 | Deleted - SEC1 Stage 2 (Enhanced HE control of security) | - | 3 | Rel-6 | S3 | 2001-01-03 08:00 | 2002-06-14 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | SP-16 |  | Fri 22/09/00 | Mon 12/03/01
5268 | 33006 | Rel-6 Network Domain Security | SEC1-NDS | 3 | Rel-6 | S3 | 2002-06-17 08:00 | 2003-09-25 17:00 | 100% | SP-000420 | - | Telenor | Geir-myrdahl.koien@telenor.com | SP#9 approved WID S3-000606 (Network Domain Security) | 33.102, 33.103, 33.105 |  |  |  |  | Fri 08/11/02 | Mon 08/08/11
5269 | 33007 | Rel-6 IP network layer security (NDS/IP) | SEC1-NDS-IP | 4 | Rel-6 | S3 | 2002-06-17 08:00 | 2003-09-25 17:00 | 100% | SP-000420 | - | - | - | SP#9 approved WID S3-000626 (Access security for IP-based services) | 33.210 |  |  |  |  | Fri 08/11/02 | Mon 08/08/11
5270 | 33017 | Network Domain Security; Authentication Framework (NDS/AF) | SEC1-NDS-AF | 2 | Rel-6 | S3 | 2002-02-15 08:00 | 2004-02-13 17:00 | 100% | SP-030108 | - | Nokia | tommi.viitanen@nokia.com | SP#19 approved WID | 33.810 |  |  |  |  | Thu 27/03/03 | Mon 08/08/11
5271 | 33019 | Key Management of group keys for Voice Group Call Services | SECGKYV | 2 | Rel-6 | S3 | 2003-09-26 08:00 | 2004-11-26 17:00 | 100% | SP-030491 | - | Vodafone | benno.tietz@vodafone.com | - | 42.068, 43.068, 44.068, 42.069, 43.069, 44.069, 31.102, 24.008, 48.008, 42.009, 43.020, New TSs (55.236, 55.205) MILENAGE algorithms |  |  |  |  | Tue 14/10/03 | Thu 13/01/05
5272 | 33020 | Network Domain Security; MAP application layer security (NDS/MAPsec) | MAPSEC | 1 | Rel-6 | S3 | 2004-07-06 08:00 | 2004-12-29 17:00 | 100% | SP-040280 | - | Vodafone | Peter.Howard@vodafone.com | SP#19 approved WID. Marked as closed 12/2008 (was marked 20% complete) | 33.200 |  |  |  |  | Fri 25/07/03 | Mon 08/08/11
5273 | 32021 | IMS Phase 2 | IMS2 | 1 | Rel-6 | S1,S2,S3,S5,NP,R5 | 2000-08-28 08:00 | 2007-09-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 25/03/02 | Thu 08/07/04
5274 | 14014 | Enhancements to the Cx and Sh interfaces | IMS2-CCR | 2 | Rel-6 | N4 | 2003-06-06 08:00 | 2004-08-31 17:00 | 100% | NP-030229 | - | - | - | Shared public user identities need to be solved. If email approval CR is accepted. Work 100% done. | - |  |  |  |  | Mon 09/06/03 | Fri 25/03/05
5275 | 25009 | Conformance Test Aspects – IMS Call Control Rel-6 enhancements | IMS2_CCR_Test | 2 | Rel-6 | R5 | 2006-03-10 08:00 | 2007-09-14 17:00 | 100% | - | - | Ericsson | Jacob.John@motorola.com, Leif.Mattisson@ericsson.com | - | 34.229-1, 34.229-2, 34.229-3, 34.108 |  |  |  |  | Tue 21/03/06 | Wed 16/06/10
5276 | 31025 | IMS Group Management | IMSGM | 2 | Rel-6 | S1 | 2002-03-14 08:00 | 2004-12-08 17:00 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | - |  |  |  |  | Thu 21/03/02 | Wed 08/09/04
5277 | 31026 | Stage 1 - TS on IMS group management | - | 3 | Rel-6 | S1 | 2002-03-14 08:00 | 2002-12-09 17:00 | 100% | - | - | Nokia | juha.kalliokulju@nokia.com | - | - |  |  |  |  | Thu 21/03/02 | Sun 07/12/03
5278 | 32036 | Stage 2 for IMS Group Management | - | 3 | Rel-6 | S2 | 2003-05-26 08:00 | 2003-12-31 17:00 | 100% | - | - | - | - | - | 23.228 |  |  |  |  | Thu 27/02/03 | Tue 08/06/04
5279 | 11036 | Stage 3 for IMS Group management (e.g. chat) | - | 3 | Rel-6 | N1 | 2002-12-13 08:00 | 2004-12-08 17:00 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Depends on CN decision on CPCP in Rel-6. Complete, if unresolved IETF dependencies are dropped (-> LS to CN plenary) | - |  |  |  |  | Mon 13/01/03 | Fri 25/03/05
5280 | 11037 | IMS Conferencing | - | 2 | Rel-6 | N1 | 2002-11-04 08:00 | 2004-12-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 13/01/03 | Mon 13/01/03
5281 | 32037 | Stage 2 for IMS Conferencing | - | 3 | Rel-6 | S2 | 2002-11-04 08:00 | 2003-12-31 17:00 | 100% | - | - | - | - | - | 23.228 |  |  |  |  | Thu 27/02/03 | Fri 12/03/04
5282 | 32038 | Stage 3 for IMS Conferencing | - | 3 | Rel-6 | N1 | 2002-12-13 08:00 | 2004-12-08 17:00 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Depends on CN decision on IETF dependenciES in CP-150Rel-6. Higher figure if CPCP is dropped (-> LS to CN plenary) | - |  |  |  |  | Fri 28/02/03 | Fri 25/03/05
5283 | 31022 | IMS Messaging | IMSM | 2 | Rel-6 | S1 | 2002-03-14 08:00 | 2005-12-30 17:00 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | - |  |  |  |  | Thu 21/03/02 | Wed 08/09/04
5284 | 31023 | TR on support of messaging in the IMS | IMSM-TR | 3 | Rel-6 | S1 | 2002-03-14 08:00 | 2002-12-09 17:00 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | New 22.940 |  |  |  |  | Thu 21/03/02 | Tue 07/09/10
5285 | 31034 | Stage 1 22.340 | IMSM-TS | 3 | Rel-6 | S1 | 2002-11-11 08:00 | 2002-12-11 17:00 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | 22.340 |  |  |  |  | Mon 13/01/03 | Tue 07/09/10
5286 | 31033 | CRs to 22.140 & 22.228 | IMSM-CR | 3 | Rel-6 | S1 | 2002-03-14 08:00 | 2003-03-17 17:00 | 100% | SP-020065 | - | Nokia | juha.kalliokulju@nokia.com | - | 22.140,22.228 |  |  |  |  | Mon 13/01/03 | Tue 07/09/10
5287 | 32700 | Stage 2 for IMS Messaging | - | 3 | Rel-6 | S2 | 2002-11-04 08:00 | 2004-08-31 17:00 | 100% | - | - | - | - | - | 23.228 |  |  |  |  | Thu 26/09/02 | Wed 08/09/04
5288 | 11039 | Stage 3 for IMS Messaging | - | 3 | Rel-6 | N1 | 2002-12-13 08:00 | 2004-12-08 17:00 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  |  |  | Mon 13/01/03 | Fri 25/03/05
5289 | 60001 | SIP/SIMPLE Instant messaging | - | 3 | Rel-6 | OMA | 2004-01-01 08:00 | 2005-12-30 17:00 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | Updated according to SP-040232 | - |  |  |  |  | Tue 08/06/04 | Fri 25/03/05
5290 | 11040 | Additional SIP Capabilities support not covered by Rel-5 | - | 2 | Rel-6 | N1 | 2002-11-11 08:00 | 2005-06-17 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 13/01/03 | Mon 13/01/03
5291 | 32041 | Stage 2 for add SIP cap (e.g. forking) | - | 3 | Rel-6 | S2 | 2002-11-11 08:00 | 2004-02-20 17:00 | 100% | - | - | - | - | - | 23.228 |  |  |  |  | Thu 27/02/03 | Fri 12/03/04
5292 | 32042 | Stage 3 for Additional SIP Capabilities | - | 3 | Rel-6 | N1 | 2002-12-13 08:00 | 2004-09-08 17:00 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  |  |  | Mon 13/01/03 | Thu 02/06/05
5293 | 11052 | Procedured associated with IMS-ALG | - | 3 | Rel-6 | N1 | 2004-09-06 08:00 | 2005-06-17 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 20/04/05 | Thu 02/06/05
5294 | 11041 | Review additional SIP Capabilities against IMS | - | 2 | Rel-6 | N1 | 2002-12-13 08:00 | 2004-09-08 17:00 | 100% | NP-040494 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  |  |  | Mon 13/01/03 | Fri 25/03/05
5295 | 2048 | Interworking between IMS and IP networks | IMS-CCR-IWIP | 2 | Rel-6 | N3 | 2000-08-28 08:00 | 2004-12-08 17:00 | 100% | NP-020091 | - | BT | nigel.holland@bt.com | [DAB 14.02.02] - end date pushed back to March 2003 | 23.821, 29.061, 29.162 |  |  |  |  | Mon 09/10/00 | Mon 13/01/03
5296 | 13004 | Interworking for 3GPP_SIP and IETF_SIP | - | 3 | Rel-6 | N3 | 2000-08-28 08:00 | 2003-06-13 17:00 | 100% | - | - | Siemens | Thomas.Belling@nsn.com | [DAB - 20.08.03] - CN Part of TR Complete @ CN#20 | New 29.962 |  |  |  |  | Thu 28/02/02 | Mon 15/09/03
5297 | 13005 | Interworking for IPv6 to IPv4 | - | 3 | Rel-6 | N3 | 2000-08-28 08:00 | 2004-12-08 17:00 | 100% | - | - | - | - | - | 29.163 |  |  |  |  | Thu 28/02/02 | Wed 09/03/05
5298 | 11044 | Interworking for IPv6 to IPv4 (SIP / SDP aspects) | - | 3 | Rel-6 | N1 | 2004-05-11 08:00 | 2004-09-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/03/04 | Wed 08/09/04
5299 | 11017 | stage 3 of interworking with non-IMS IP networks | - | 3 | Rel-6 | N1 | 2001-03-14 08:00 | 2004-09-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Wed 08/09/04
5300 | 2047 | Interworking between IMS and CS networks | IMS-CCR-IWCS | 2 | Rel-6 | N3 | 2000-08-28 08:00 | 2004-03-18 17:00 | 100% | NP-030292 | - | Vodafone | Brendan.McWilliams@gb.vodafone.co.uk | [DAB - 25.05.04] - CN3 consider this work to be complete | 29.163, 29.061, 24.228, and New CN4 specification |  |  |  |  | Thu 24/01/02 | Thu 09/09/04
5301 | 14001 | Mn interface (IM-MGW to MGCF) enhancements (CN4 Part) | IMS-CCR-Mn | 2 | Rel-6 | N4 | 2001-08-07 10:24 | 2004-09-01 17:00 | 100% | - | - | - | - | TISPAN issue is open | - |  |  |  |  | Mon 08/10/01 | Wed 09/03/05
5302 | 31036 | Study of subscriber and operators relationship in IMS and related ISIM requirements for Rel 6” | - | 2 | Rel-6 | S1 | 2002-11-15 08:00 | 2002-12-12 17:00 | 100% | - | - | Nokia | juha.kalliokulju@nokia.com | - | - |  |  |  |  | Mon 13/01/03 | Fri 04/07/03
5303 | 33012 | Lawful Interception in Rel-6 architecture | SEC1-LI | 2 | Rel-6 | S3 | 2002-12-09 08:00 | 2003-12-18 17:00 | 100% | SP-030106 | - | Reg TP, Nortel | berthold.wilhelm@regtp.de, Ron Ryan | Acronym changed from "SEC1-LI, Rel6" | 33.106, 33.107, 33.108 |  |  |  |  | Wed 15/01/03 | Tue 24/03/15
5304 | 31042 | IMS Subscription and access scenarios | - | 2 | Rel-6 | S1 | 2002-12-16 08:00 | 2003-06-13 17:00 | 100% | - | - | TeliaSonera | FRANK, Robert | - | 22.800 |  |  |  |  | Fri 28/03/03 | Tue 31/08/10
5305 | 35032 | IMS charging | IMS2-CH | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-12-16 17:00 | 100% | SP-030049 | - | Ericsson | Patrik TEPPO | SP#26 12/2004 completed | 32.260 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5306 | 11051 | IMS Management objects | - | 2 | Rel-6 | N1 | 2004-09-03 08:00 | 2005-11-04 17:00 | 100% | NP-040494 | - | - | - | - | 24.167 |  |  |  |  | Mon 06/12/04 | Wed 09/03/05
5307 | 32027 | Deleted - Stage 2 of IMS Phase 2 | - | 2 | Rel-6 | S2 | 2003-09-19 17:00 | 2003-09-19 17:00 | 100% | SP-020544 | - | - | - | - | - |  |  | SP-21 |  | Tue 19/10/04 | Thu 21/10/04
5308 | 32063 | 3GPP Enablers for services like Push to Talk over Cellular (PoC) | PoC | 1 | Rel-6 | S2,S4,S5 | 2003-09-08 08:00 | 2005-06-09 17:00 | 100% | SP-030384 | - | Ericsson | Shabnam Sultana | - | - |  |  |  |  | Wed 15/10/03 | Thu 08/07/04
5309 | 32068 | Feasibility Study on 3GPP Enablers for services like Push to Talk over Cellular (PoC) | - | 2 | Rel-6 | S2 | 2003-09-08 08:00 | 2004-11-30 17:00 | 100% | SP-030384 | - | Ericsson | Shabnam Sultana | - | 23.979 |  |  |  |  | Wed 15/10/03 | Mon 06/12/04
5310 | 60002 | Dependencies on OMA PoC | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2005-02-28 17:00 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | Updated according to SP-040232 | - |  |  |  |  | Wed 15/10/03 | Fri 25/03/05
5311 | 34029 | Selection of one or more PoC codec(s) for PoC | - | 2 | Rel-6 | S4 | 2004-09-13 08:00 | 2004-12-16 17:00 | 100% | - | - | - | - | Completed | 26.235, 26.236 |  |  |  |  | Fri 01/10/04 | Mon 06/12/04
5312 | 35036 | PoC charging | PoC-CH | 2 | Rel-6 | S5 | 2004-09-27 08:00 | 2005-06-09 17:00 | 100% | SP-050032 | - | Siemens | Gerald.Goermer@nsn.com | SP#28 06/2005 completed | 32.272 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5313 | 32062 | Study on Interworking aspects and migration scenarios for IPv4 based IMS Implementations | IPv4IMS | 1 | Rel-6 | S2 | 2003-09-08 08:00 | 2004-06-25 17:00 | 100% | SP-040327 | - | Siemens | Alexander Milinski | - | 23.981 |  |  |  |  | Wed 15/10/03 | Wed 18/11/09
5314 | 11032 | Interoperability and Commonality between IMS using different IP-connectivity Networks | IMSCOOP | 1 | Rel-6 | S2 | 2002-09-16 08:00 | 2003-12-12 17:00 | 100% | - | - | - | - | - | 23.864 |  |  |  |  | Thu 26/09/02 | Thu 08/07/04
5315 | 32028 | Stage 2 for Interoperability | - | 2 | Rel-6 | S2 | 2002-09-16 08:00 | 2003-09-30 17:00 | 100% | SP-020543 | - | Nokia | balazs.bertenyi@nsn.com | No contributions assumed that no more will be done in 3GPP hence work may need to be done in 3GPP2 | 23.864 |  |  |  |  | Fri 08/11/02 | Thu 08/07/04
5316 | 32061 | Stage 2 for commonality | - | 2 | Rel-6 | S2 | 2002-09-16 08:00 | 2003-09-19 17:00 | 100% | SP-020543 | - | Nokia | balazs.bertenyi@nsn.com | - | 23.864 |  |  |  |  | Mon 15/09/03 | Thu 08/07/04
5317 | 11033 | Stage 3 for Interoperability and Commonality between IMS using different IP-connectivity Networks | - | 2 | Rel-6 | N1 | 2002-10-14 08:00 | 2003-12-12 17:00 | 100% | NP-020572 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | - |  |  |  |  | Fri 08/11/02 | Fri 12/03/04
5318 | 1365 | Support of Push Services | PUSH | 1 | Rel-6 | S1 | 2001-01-03 08:00 | 2004-02-27 17:00 | 100% | SP-000669 | - | NTT Comware | Yoshinori Kitada | Changed from FS to actual support of Push | 23.976 |  |  |  |  | Wed 19/04/00 | Wed 19/01/05
5319 | 31004 | Stage 1 for Support of Push Services | - | 2 | Rel-6 | S1 | 2001-01-03 08:00 | 2002-06-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Fri 04/07/03
5320 | 32701 | TR 23.976 on Push Architecture | - | 2 | Rel-6 | S2 | 2002-11-11 08:00 | 2004-02-27 17:00 | 100% | SP-030126 | - | Research In Motion | Nick Alfano | - | 23.976 |  |  |  |  | Thu 26/09/02 | Thu 08/07/04
5321 | 42009 | Rel-6 Multimedia Messaging (MMS) enhancements | MMS6 | 1 | Rel-6 | T2,S1,S4,S5,OMA | 2002-08-15 08:00 | 2005-12-07 17:00 | 100% | TP-030175 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | - |  |  |  |  | Thu 26/09/02 | Mon 06/12/04
5322 | 42010 | Definition of service requirements for MMS6 | MMS6-SR | 2 | Rel-6 | S1 | 2002-11-15 08:00 | 2003-12-19 17:00 | 100% | - | - | - | - | - | 22.140 |  |  |  |  | Thu 26/09/02 | Fri 12/03/04
5323 | 31031 | Definition of service requirements charging | - | 3 | Rel-6 | S1 | 2002-11-15 08:00 | 2003-12-19 17:00 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140 |  |  |  |  | Mon 13/01/03 | Fri 12/03/04
5324 | 42011 | Technical realization of MMS6 | - | 2 | Rel-6 | T2 | 2002-09-06 08:00 | 2004-12-10 17:00 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 23.140 |  |  |  |  | Thu 26/09/02 | Mon 06/12/04
5325 | 42012 | OMA dependencies | - | 2 | Rel-6 | OMA | 2003-08-15 08:00 | 2005-04-29 17:00 | 100% | - | - | - | - | - | OMA specs |  |  |  |  | Thu 26/09/02 | Fri 25/03/05
5326 | 42013 | MMS formats and codecs for MMS6 | MMS6-Codec | 2 | Rel-6 | S4 | 2002-08-15 08:00 | 2005-12-07 17:00 | 100% | - | - | Nokia | roberto.castagno@nokia.com | - | 26.140, 26.936 |  |  |  |  | Thu 26/09/02 | Fri 13/01/06
5327 | 42014 | Handling of private addressing schemes in MMS | - | 2 | Rel-6 | T2 | 2003-12-10 08:00 | 2004-12-10 17:00 | 100% | TP-030299 | - | T-Mobile | Steffen.Habermann@T-MOBILE.DE | - | 23.140 |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
5328 | 35034 | MMS charging | MMS6-CH | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | SP-040778 | - | - | - | SP#25 09/2004 completed | 32.270 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5329 | 42015 | Deleted - FS Multiple MMS Relay/Server Architecture | - | 2 | Rel-6 | T2 | 2004-12-10 17:00 | 2004-12-10 17:00 | 100% | TP-030301 | - | Telefónica Móviles | Juan Gorospe (gorospe_j@tsm.es) | originally it was intended to create a FS TR but most likely the work will become an Annex of 23.140 | probably Annex to 23.140 |  |  | TP-26 |  | Mon 01/12/03 | Wed 08/09/04
5330 | 42005 | Rel-6 MExE enhancements | MEXE6 | 1 | Rel-6 | T2 | 2002-03-08 08:00 | 2003-06-06 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 21/03/02 | Thu 21/03/02
5331 | 42006 | MExE Rel-6 Improvements and Investigations | MEXE6-ENHANC | 2 | Rel-6 | T2 | 2002-03-08 08:00 | 2003-03-12 17:00 | 100% | TP-020017 | - | TTPCom | Lars Brenk ( (lsb_ttpcom@HOTMAIL.COM) | - | - |  |  |  |  | Thu 21/03/02 | Wed 18/11/09
5332 | 42007 | MExE Run-Time Independent Framework Feasibility Study | MEXE6-RTIF | 2 | Rel-6 | T2 | 2002-03-08 08:00 | 2003-06-06 17:00 | 100% | TP-020086 | - | Nokia Siemens Networks | balazs.bertenyi@nokia.com | - | 22.857 |  |  |  |  | Thu 21/03/02 | Tue 31/08/10
5333 | 2062 | Subscription Management | SuM | 1 | Rel-6 | S5 | 2002-09-20 08:00 | 2005-03-17 17:00 | 100% | SP-040763 | - | T-Mobile | istvan.aba@t-mobile.at | SP#27 03/2005 completed | 32.140/1, 32.171/2/5, 32.803 |  |  |  |  | Mon 09/10/00 | Fri 13/01/06
5334 | 2499 | Presence Capability | PRESNC | 1 | Rel-6 | S1,S2,S3,S4,N1,N3,N4,OMA | 2001-03-19 08:00 | 2005-12-07 17:00 | 100% | SP-010064 | - | Motorola | Mark Cataldo | merged "Presence Service Enhancements" (UID31028, PRES1) to this feature as no answer was provided on why Presence and Presence Encmts had same target completion date | - |  |  |  |  | Fri 30/03/01 | Wed 08/09/04
5335 | 2501 | Stage 1 for Presence Capability | - | 2 | Rel-6 | S1 | 2001-03-19 08:00 | 2003-07-18 17:00 | 100% | SP-010064 | - | Motorola | Mark Cataldo | TP#16 moved Stage 1 to Rel-6 TS 22.141 (existed already in Rel-5) | 22.141 |  |  |  |  | Fri 30/03/01 | Tue 09/08/11
5336 | 2502 | Stage 2 for Presence Capability | - | 2 | Rel-6 | S2 | 2001-09-12 08:00 | 2002-09-20 17:00 | 100% | SP-010517 | - | Nokia | balazs.bertenyi@nsn.com | - | 23.002, 24.229, New 23.141 |  |  |  |  | Fri 30/03/01 | Tue 09/08/11
5337 | 2503 | Stage 3 for Presence Capability | - | 2 | Rel-6 | N1,N4 | 2002-04-01 08:00 | 2004-12-08 17:00 | 100% | NP-040492 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Dependency to 2 IETF drafts, no known work at the moment | New N1 (24.141, 24.841), N4 (29.002, 29.228, 29.230, 29.328) |  |  |  |  | Fri 30/03/01 | Tue 09/08/11
5338 | 13018 | Stage 3 (CN3 Part Pk interface) | - | 2 | Rel-6 | N3 | 2002-04-01 08:00 | 2005-03-11 17:00 | 100% | NP-040492 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | - | 29.061, 29.161 |  |  |  |  | Tue 08/06/04 | Tue 09/08/11
5339 | 34025 | Media Codecs and Formats for IMS Messaging and Presence | PRESNC-COFIMP | 2 | Rel-6 | S4 | 2003-06-12 08:00 | 2005-12-07 17:00 | 100% | SP-030212 | - | Nokia | harri.honko@nokia.com | - | 26.141, 26.936 |  |  |  |  | Fri 04/07/03 | Fri 13/01/06
5340 | 2504 | Security aspects of Presence Capability | - | 2 | Rel-6 | S3 | 2002-08-26 08:00 | 2002-12-12 17:00 | 100% | SP-020514 | - | Ericsson | krister.boman@erv.ericsson.se | SP#17 approved WID S3-020429 | - |  |  |  |  | Fri 30/03/01 | Tue 09/08/11
5341 | 60003 | SIMPLE Presence | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2005-03-31 17:00 | 100% | SP-040232 | - | - | OMA-LIAISON@mail.openmobilealliance.org | SP#24 OMA LS_in update in SP-040232 OMA dependencies on 3GPP deliverables | - |  |  |  |  | Tue 08/06/04 | Tue 09/08/11
5342 | 50056 | Enhanced A/Gb feasibility study | AGbEnFS | 1 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | GP-022565 | - | Vodafone | jose-luis.carrizo@vodafone.co.uk | - | None |  |  |  |  | Thu 23/05/02 | Wed 18/11/09
5343 | 50057 | Feasibility study on A/Gb enhancements | AGbEnFS-FS | 2 | Rel-6 | G2 | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | GP-022565 | - | Vodafone | jose-luis.carrizo@vodafone.co.uk | - | None |  |  |  |  | Thu 23/05/02 | Wed 18/11/09
5344 | 50080 | Requirements for the support of conversational services | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None |  |  |  |  | Thu 26/09/02 | Wed 18/11/09
5345 | 50084 | Identification of the different building blocks for the provision of conversational services on the existing A/Gb protocol stack | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None |  |  |  |  | Mon 13/01/03 | Wed 18/11/09
5346 | 50093 | Outline of impact and feasibility of these building blocks and their different solutions | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None |  |  |  |  | Mon 13/01/03 | Wed 18/11/09
5347 | 50081 | Impact on 3GPP architecture and requirement to co-ordinatge with other TSGs (CN, SA) | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None |  |  |  |  | Thu 26/09/02 | Wed 18/11/09
5348 | 50082 | Standardisation effort | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None |  |  |  |  | Thu 26/09/02 | Wed 18/11/09
5349 | 50083 | Dependency to other features of Enhanced A/Gb feasibility study | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2002-11-08 17:00 | 100% | - | - | - | - | - | None |  |  |  |  | Thu 26/09/02 | Wed 18/11/09
5350 | 50063 | Flexible Layer One for GERAN | FLOGER | 1 | Rel-6 | GP,S3 | 2000-01-03 08:00 | 2004-06-25 17:00 | 100% | GP-021018 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Tue 16/09/03
5351 | 50064 | Realisation of a Flexible Layer One | FLOGER-Real | 2 | Rel-6 | GP | 2000-01-03 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Thu 08/07/04
5352 | 50065 | Technical Report on Realisation of a Flexible Layer One | - | 3 | Rel-6 | GP | 2002-04-19 08:00 | 2004-02-06 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
5353 | 51002 | Architecture in 45.001 and 43.051 | - | 3 | Rel-6 | G1 | 2002-04-19 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
5354 | 51003 | Multiplexing in 45.002 | - | 3 | Rel-6 | G1 | 2002-04-19 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
5355 | 51004 | Channel Coding in 45.003 for Realisation of a Flexible Layer One | - | 3 | Rel-6 | G1 | 2002-04-19 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
5356 | 51005 | Performance Requirements in 45.005 for Realisation of a Flexible Layer One | - | 3 | Rel-6 | G1 | 2000-01-03 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
5357 | 51006 | Radio subsystem link control in 45.008 for Realisation of a Flexible Layer One | - | 3 | Rel-6 | G1 | 2002-04-19 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
5358 | 52071 | Requirements in 44.004 | - | 3 | Rel-6 | G2 | 2002-04-19 08:00 | 2004-04-23 17:00 | 100% | GP-021019 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Fri 12/03/04
5359 | 52072 | Signalling and protocol support for a Flexible Layer One | FLOGER-SigPro | 2 | Rel-6 | G2 | 2002-04-19 08:00 | 2004-06-25 17:00 | 100% | GP-021020 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Mon 06/12/04
5360 | 52073 | Modifications to RLC/MAC in 44.060 and 44.160 | - | 3 | Rel-6 | G2 | 2002-04-19 08:00 | 2004-06-25 17:00 | 100% | GP-021020 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Thu 08/07/04
5361 | 52074 | Modifications to RRC in 44.118 and 44.018 | - | 3 | Rel-6 | G2 | 2002-04-19 08:00 | 2004-06-25 17:00 | 100% | GP-021020 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Thu 08/07/04
5362 | 52075 | Security for a Flexible Layer One | FLOGER-SecFLO | 2 | Rel-6 | S3,G2 | 2002-04-19 08:00 | 2003-08-29 17:00 | 100% | GP-021021 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  |  |  | Thu 23/05/02 | Wed 14/01/04
5363 | 52076 | Ciphering in 44.060, 44.160, 44.018, 44.118 | - | 3 | Rel-6 | S3,G2 | 2002-04-19 08:00 | 2003-08-29 17:00 | 100% | GP-021021 | - | Nokia | benoist.sebire@nokia.com | - | 44.060, 44.160, 44.018, 44.118 |  |  |  |  | Thu 23/05/02 | Tue 16/09/03
5364 | 55077 | Deleted - GERAN MS Conformance test for the Flexible Layer One - DELETE | FLOGER-Msconf | 2 | Rel-6 | G4,G5 | 2004-02-06 08:00 | 2004-02-06 08:00 | 100% | GP-021022 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  | GP-27 |  | Thu 23/05/02 | Wed 09/03/05
5365 | 55078 | Deleted at TSG #27 - MS Test in 51.010 | - | 3 | Rel-6 | G4,G5 | 2004-02-06 08:00 | 2004-02-06 08:00 | 100% | - | - | Nokia | benoist.sebire@nokia.com | - | - |  |  | GP-22 |  | Thu 23/05/02 | Wed 09/03/05
5366 | 55079 | Deleted - GERAN BTS Conformance test for the Flexible Layer One - DELETE | FLOGER-BTSconf | 2 | Rel-6 | G3new | 2004-02-06 08:00 | 2004-02-06 08:00 | 100% | GP-021023 | - | Nokia | benoist.sebire@nokia.com | - | - |  |  | GP-27 |  | Thu 23/05/02 | Wed 09/03/05
5367 | 53080 | Deleted at TGS #27 - BTS Test in 51.021 - DELETE | - | 3 | Rel-6 | G3new | 2004-02-06 08:00 | 2004-02-06 08:00 | 100% | - | - | Nokia | benoist.sebire@nokia.com | - | - |  |  | GP-22 |  | Thu 26/09/02 | Wed 09/03/05
5368 | 50041 | Uplink TDOA feasibility study | TDOAF | 1 | Rel-6 | GP | 2001-11-30 08:00 | 2002-06-28 17:00 | 100% | GP-012794 | - | TruePosition | Bob Gross (rlgross@trueposition.com) | - | 45.811 |  |  |  |  | Mon 10/12/01 | Thu 24/04/03
5369 | 2544 | Multimedia Broadcast and Multicast Service | MBMS | 1 | Rel-6 | S1,S2,S3,S4,S5,N1,N3,R2,R4,R5,T1,GP,G2,G3new | 2001-05-11 08:00 | 2008-03-07 17:00 | 100% | - | - | - | - | SP#13 Title renamed | - |  |  |  |  | Mon 28/05/01 | Thu 26/07/12
5370 | 2545 | Stage 1 for Multimedia Broadcast and Multicast Service | - | 2 | Rel-6 | S1 | 2001-05-11 08:00 | 2002-04-01 17:00 | 100% | - | - | - | - | - | 22.146, 22.101 |  |  |  |  | Fri 30/03/01 | Thu 26/07/12
5371 | 32002 | Stage 2 for Multimedia Broadcast and Multicast Service | - | 2 | Rel-6 | S2 | 2001-09-24 08:00 | 2004-03-17 17:00 | 100% | SP-010516 | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Thu 26/07/12
5372 | 32702 | TR on MBMS Architectural Study | - | 3 | Rel-6 | S2 | 2001-09-24 08:00 | 2002-08-23 17:00 | 100% | - | - | - | - | - | 23.846 |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5373 | 32703 | Stage 2 MBMS Specification Work | - | 3 | Rel-6 | S2 | 2002-08-19 08:00 | 2004-03-17 17:00 | 100% | - | - | - | - | - | 23.246 |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5374 | 11030 | Support of the MBMS in CN protocols | - | 2 | Rel-6 | N1 | 2002-06-18 08:00 | 2004-12-08 17:00 | 100% | NP-040493 | - | - | - | - | - |  |  |  |  | Fri 21/06/02 | Thu 26/07/12
5375 | 13015 | Gmb interface for MBMS (CN3 part) | - | 2 | Rel-6 | N3 | 2003-08-29 08:00 | 2004-12-08 17:00 | 100% | - | - | - | - | - | 29.061 |  |  |  |  | Mon 13/10/03 | Thu 26/07/12
5376 | 33008 | Security aspects of MBMS | - | 2 | Rel-6 | S3 | 2002-07-01 08:00 | 2005-03-18 17:00 | 100% | SP-020514 | - | 3 | adrian.escott@three.co.uk | SP#17 approved WID S3-020433 | New 33.246 |  |  |  |  | Fri 08/11/02 | Thu 26/07/12
5377 | 35038 | MBMS Charging | MBMS-CH | 2 | Rel-6 | S5 | 2005-01-11 08:00 | 2005-06-09 17:00 | 100% | SP-040779 | - | - | - | SP#28 completed | 32.273 |  |  |  |  | Fri 29/10/04 | Thu 26/07/12
5378 | 31045 | MBMS User Services | - | 2 | Rel-6 | S1,S4 | 2003-05-13 08:00 | 2006-03-16 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 30/03/01 | Thu 26/07/12
5379 | 31044 | Stage 1 for MBMS User Services | - | 3 | Rel-6 | S1 | 2003-05-13 08:00 | 2004-04-01 17:00 | 100% | - | - | - | - | - | 22.246 |  |  |  |  | Fri 30/03/01 | Thu 26/07/12
5380 | 34026 | Definition of MBMS user services, media codecs, formats and transport/application protocols using MBMS | MBMS-TSMBMS | 3 | Rel-6 | S4 | 2003-06-12 08:00 | 2006-03-16 17:00 | 100% | SP-030674 | - | Nokia | igor.curcio@nokia.com | - | 26.346, 26.936, 26.946 |  |  |  |  | Fri 04/07/03 | Thu 26/07/12
5381 | 2481 | Introduction of MBMS in RAN | MBMS-RAN | 2 | Rel-6 | R2,R4 | 2002-01-01 | 2005-09-14 17:00 | 100% | - | - | Nokia | juho.pirskanen@nokia.com | - | - |  |  |  |  | Tue 20/03/01 | Thu 26/07/12
5382 | 20022 | Introduction of MBMS in RAN (physical & upper layers, access network interfaces) | - | 3 | Rel-6 | R2 | 2002-01-01 | 2004-12-14 17:00 | 100% | - | - | Nokia | juho.pirskanen@nokia.com | - | 25.346, 25.304, 25.321, 25.322, 25.323 |  |  |  |  | Mon 27/09/04 | Thu 26/07/12
5383 | 20020 | UE Performance Requirements for MBMS | MBMS-RAN-RF | 3 | Rel-6 | R4 | 2004-09-15 | 2005-09-14 17:00 | 100% | RP-040370 | - | Ericsson | Torgny.Palenius@ericsson.com | RP#25 approved WID RP-040370 | 25.101, 25.133 |  |  |  |  | Mon 27/09/04 | Thu 26/07/12
5384 | 25024 | MBMS UE Conformance Testing | MBMS-UEConTest | 2 | Rel-6 | R5,T1 | 2006-03-10 08:00 | 2008-03-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 22/09/06 | Thu 26/07/12
5385 | 25014 | RF/RRM Conformance Test Aspects – MBMS (FDD) | MBMS-RAN-RF_Test | 3 | Rel-6 | R5,T1 | 2006-06-02 08:00 | 2008-03-07 17:00 | 100% | - | - | Ericsson | leif.mattisson@ericsson.com | - | 34.108, 34.109, 34.121-1, 34.121-2 |  |  |  |  | Thu 28/02/02 | Thu 26/07/12
5386 | 25022 | Conformance Test Aspects - MBMS for 3.84 Mcps and 7.68 Mcps TDD | MBMS-UEConTest_TDH | 3 | Rel-6 | R5,T1 | 2006-09-20 08:00 | 2007-12-07 17:00 | 100% | - | - | IPWireless | Timothy Speight (tspeight@ipwireless.com) | - | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Thu 26/07/12
5387 | 25023 | Signalling Conformance Test Aspects – MBMS for LCR TDD | MBMS-UEConTest_SIGTDL | 3 | Rel-6 | R5,T1 | 2006-09-20 08:00 | 2007-12-07 17:00 | 100% | - | - | Datang | zhaojian@datangmobile.cn | - | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 21/09/06 | Thu 26/07/12
5388 | 25011 | Conformance Test Aspects – MBMS | MBMS_Test | 3 | Rel-6 | R5,T1 | 2006-03-10 08:00 | 2007-09-14 17:00 | 100% | - | - | Qualcomm | Shubhang Vora (svora@qualcomm.com) | - | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Tue 21/03/06 | Thu 26/07/12
5389 | 25038 | Conformance Test Aspects - 1.28 Mcps TDD MBMS RF/RRM | MBMS-UEConTest_RFTDL | 3 | Rel-6 | R5,T1 | 2007-06-01 08:00 | 2007-12-07 17:00 | 100% | - | - | Datang | chenxiaozhong@datangmobile.cn | - | 34.108, 34.109, 34.122 |  |  |  |  | Thu 28/02/02 | Thu 26/07/12
5390 | 50085 | Support of MBMS in GERAN | MBMS-GERAN | 2 | Rel-6 | GP,G2,G3new | 2001-08-30 08:00 | 2005-01-28 17:00 | 100% | GP-022566 | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5391 | 50086 | MBMS Impact on the logical and physical channels | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5392 | 52085 | MBMS Re-synchronisation at cell change | - | 3 | Rel-6 | G2 | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5393 | 50098 | Simultaneous support of MBMS services | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Thu 26/07/12
5394 | 50099 | Simultaneous support of MBMS and non-MBMS services | - | 3 | Rel-6 | GP | 2001-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Thu 26/07/12
5395 | 50100 | MBMS Resynchronization at cell change | - | 3 | Rel-6 | GP | 2001-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Thu 26/07/12
5396 | 50087 | MBMS Decision making process between point-to-point or point-to-multipoint configurations | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5397 | 50088 | MBMS channel allocations procedures to multiple MSs | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5398 | 50089 | MBMS Changes to the Gb interface | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5399 | 50090 | GERAN specific changes to the Iu-ps interface for MBMS | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5400 | 50091 | Interaction between MBMS and Iu-flex | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5401 | 50092 | MBMS Security aspects | - | 3 | Rel-6 | GP | 2002-08-30 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 26/09/02 | Thu 26/07/12
5402 | 53081 | MBMS-GERAN - MS conformance tests | - | 3 | Rel-6 | G3new | 2002-01-25 08:00 | 2005-01-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Thu 26/07/12
5403 | 55091 | Deleted - MS conformance tests - G5 | - | 3 | Rel-6 | G5 | 2003-06-27 17:00 | 2003-06-27 17:00 | 100% | - | - | - | - | - | - |  |  | GP-19 |  | Wed 20/10/04 | Thu 26/07/12
5404 | 31006 | Speech Recognition and Speech Enabled Services | SRSES | 1 | Rel-6 | S1,S2,S4,OMA | 2001-10-08 08:00 | 2005-12-30 17:00 | 100% | SP-010572 | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Wed 08/09/04
5405 | 31007 | Speech Enabled Services Based on Distributed Speech Recognition (DSR) | DSR | 2 | Rel-6 | S1 | 2001-10-08 08:00 | 2002-03-15 17:00 | 100% | SP-010581 | - | Qualcomm | Dwilliams@qualcomm.com | - | 22.977, 22.941, 23.207, 22.243 |  |  |  |  | Tue 09/10/01 | Fri 12/03/04
5406 | 32999 | TR on Architectural impacts | - | 2 | Rel-6 | S2 | 2003-05-12 08:00 | 2004-03-02 17:00 | 100% | - | - | - | - | - | 23.877 |  |  |  |  | Thu 29/11/01 | Thu 08/07/04
5407 | 34700 | Codec Work to Support Speech Recognition Framework for Automated Voice Services | SRSES-Codec | 2 | Rel-6 | S4 | 2002-10-15 08:00 | 2004-12-16 17:00 | 100% | SP-020687 | - | Motorola | David Pearce (bdp003@motorola.com) | - | 26.235, 26.236, 26.243, 26.177, 26.943 |  |  |  |  | Mon 13/01/03 | Mon 06/12/04
5408 | 60004 | Multimodal support | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2005-12-30 17:00 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Tue 08/06/04 | Fri 25/03/05
5409 | 11021 | Deleted - SES codec negotiation at Session Description Protocol (SDP) | - | 2 | Rel-6 | N1 | 2003-06-04 17:00 | 2003-06-04 17:00 | 100% | - | - | - | - | Abandoned NP-23 | - |  |  | NP-23 |  | Wed 20/10/04 | Thu 21/10/04
5410 | 31008 | Generic User Profile Rel-6 | GUP | 1 | Rel-6 | S1,S3,N4 | 2001-10-08 08:00 | 2005-03-03 17:00 | 100% | SP-040515 | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Fri 28/03/03
5411 | 31009 | Stage 1 - Requirements for Generic User Profile | - | 2 | Rel-6 | S1 | 2001-10-08 08:00 | 2003-05-30 17:00 | 100% | - | - | T-Mobile | kurt.bischinger@t-mobile.at | - | 22.240, 22.228 |  |  |  |  | Tue 09/10/01 | Fri 25/03/05
5412 | 32008 | Stage 2 - Architecture | - | 2 | Rel-6 | S2 | 2002-01-28 08:00 | 2003-06-06 17:00 | 100% | SP-020539 | - | Nokia | harri.o.koskinen@nokia.com | - | 23.240 |  |  |  |  | Tue 09/10/01 | Fri 12/03/04
5413 | 42002 | Stage 2 - Data Description Method | - | 2 | Rel-6 | N4 | 2002-12-05 08:00 | 2005-03-03 17:00 | 100% | TP-020275 | - | T-Mobile | kurt.bischinger@t-mobile.at | TR approved in CN#26 | 23.241 |  |  |  |  | Tue 09/10/01 | Wed 09/03/05
5414 | 14008 | Stage 3 - Network | - | 2 | Rel-6 | N4 | 2003-05-19 08:00 | 2005-03-03 17:00 | 100% | - | - | - | - | - | 29.240 |  |  |  |  | Thu 21/03/02 | Wed 09/03/05
5415 | 33009 | Security aspects of GUP | - | 2 | Rel-6 | S3 | 2002-07-16 08:00 | 2003-09-18 17:00 | 100% | SP-030109 | - | Lucent | Bradley Owen (bvowen@lucent.com) | SP#19 approved WID | 33.102, 33.203, 33.210 |  |  |  |  | Fri 08/11/02 | Mon 08/08/11
5416 | 31010 | Digital Rights Management | DRM | 1 | Rel-6 | S1,OMA | 2001-10-08 08:00 | 2004-05-28 17:00 | 100% | SP-010577 | - | - | - | Foreseen start and completion dates introduced by MCC (no indication at all on the WID) | - |  |  |  |  | Thu 11/10/01 | Thu 11/10/01
5417 | 31011 | Requirements for Digital Rights Management | - | 2 | Rel-6 | S1 | 2001-10-08 08:00 | 2002-06-13 17:00 | 100% | - | - | Openwave | nicholas.wood@openwave.com | - | - |  |  |  |  | Thu 11/10/01 | Fri 04/07/03
5418 | 60005 | Stage 2 for Digital Rights Management | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-05-28 17:00 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Tue 08/06/04 | Fri 25/03/05
5419 | 60006 | Stage 3 for Digital Rights Management | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-05-28 17:00 | 100% | - | - | - | OMA-LIAISON@mail.openmobilealliance.org | - | - |  |  |  |  | Tue 08/06/04 | Fri 25/03/05
5420 | 33001 | Security for Digital Rights Management | - | 2 | Rel-6 | OMA | 2002-06-17 08:00 | 2003-03-03 17:00 | 100% | - | - | - | - | SA3 acknowledge role in WI at SA3#20. Active contribution S3#24, S3#25. S3 WID approved SP#17 | - |  |  |  |  | Thu 11/10/01 | Fri 25/03/05
5421 | 31037 | Deleted - Monitoring of Stages 2 and 3 progress (actual work to be done by OMA) | - | 2 | Rel-6 | S1 | 2003-03-21 17:00 | 2003-03-21 17:00 | 100% | - | - | - | - | Replaced by UID 60005 and 60006 | - |  |  | SP-19 |  | Wed 15/01/03 | Wed 08/09/04
5422 | 31012 | WLAN-UMTS Interworking Rel-6 | WLAN | 1 | Rel-6 | S1,S2,S3,S5,N1,N3,N4,T3 | 2000-01-03 08:00 | 2005-09-22 17:00 | 100% | SP-030712 | - | Telenor | frederic.paint@telenor.com | - | - |  |  |  |  | Thu 11/10/01 | Fri 12/03/04
5423 | 31020 | Technical Report on WLAN-UMTS Interworking | WLAN-TR | 2 | Rel-6 | S1 | 2000-01-03 08:00 | 2003-06-13 17:00 | 100% | SP-030712 | - | T-mobile | Mark.Younge@t-mobile.com | - | 22.934 |  |  |  |  | Thu 28/02/02 | Tue 08/06/04
5424 | 31035 | Stage 1 for WLAN-UMTS Interworking Rel-6 | WLAN-TS | 2 | Rel-6 | S1 | 2003-01-06 08:00 | 2004-06-11 17:00 | 100% | SP-030712 | - | Telenor | frederic.paint@telenor.com | - | 22.101, 22.105 |  |  |  |  | Mon 13/01/03 | Tue 08/06/04
5425 | 32018 | Architecture Definition for scenarii 2 and 3 | - | 2 | Rel-6 | S2 | 2002-03-25 08:00 | 2004-05-31 17:00 | 100% | SP-020542 | - | - | - | - | 23.234 |  |  |  |  | Mon 25/03/02 | Thu 08/07/04
5426 | 32704 | Security aspects of WLAN-UMTS Interworking | - | 2 | Rel-6 | S3 | 2002-09-30 08:00 | 2003-03-21 17:00 | 100% | SP-020514 | - | Ericsson, BT | luis.lopez-soria@ece.ericsson.se, colin.blanchard@bt.com | SP#17 approved WID S3-020451 | 21.133, 33.106, 33.107, 33.108, 33.200, 33.203, 33.210, New 33.234 |  |  |  |  | Thu 26/09/02 | Tue 09/08/11
5427 | 14013 | Stage 3 - CN4 aspects | WLAN-IW | 2 | Rel-6 | N4 | 2003-05-23 08:00 | 2004-09-01 17:00 | 100% | NP-030490 | - | Nokia | raquel.rodriguez@nokia.com | WID approved at CN#19 | 29.234, 29.061 |  |  |  |  | Thu 27/03/03 | Wed 09/03/05
5428 | 13019 | Stage 3 - CN3 aspects (Wi Interface for Scenario 3) | - | 2 | Rel-6 | N3 | 2003-05-23 08:00 | 2004-09-30 17:00 | 100% | - | - | - | - | - | 29.161 |  |  |  |  | Tue 08/06/04 | Wed 09/03/05
5429 | 11042 | Stage 3 for scenario 2 | - | 2 | Rel-6 | N1 | 2003-05-23 08:00 | 2004-09-08 17:00 | 100% | NP-030490 | - | - | - | - | - |  |  |  |  | Mon 09/06/03 | Wed 09/03/05
5430 | 11047 | Stage 3 for scenario 3 | - | 2 | Rel-6 | N1 | 2003-05-23 08:00 | 2004-12-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 08/06/04 | Wed 09/03/05
5431 | 35033 | WLAN charging | WLAN-CH | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2005-09-22 17:00 | 100% | SP-030048 | - | Nokia | Benni ALEXANDER | - | 32.252 |  |  |  |  | Fri 29/10/04 | Mon 15/08/11
5432 | 43010 | USIM enhancements for WLAN Interworking | - | 2 | Rel-6 | T3 | 2003-09-05 08:00 | 2005-03-04 17:00 | 100% | TP-030185 | - | Axalto | Jabellan@axalto.com | - | 31.102 |  |  |  |  | Mon 06/12/04 | Thu 01/09/11
5433 | 31015 | Priority Service | PRIOR1 | 1 | Rel-6 | S1 | 2002-05-30 08:00 | 2003-09-26 17:00 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | - |  |  |  |  | Wed 27/02/02 | Tue 31/08/10
5434 | 31016 | Feasibility Study on Priority Service | PRIOR-FS | 2 | Rel-6 | S1 | 2002-06-14 08:00 | 2002-06-14 17:00 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | 22.950 |  |  |  |  | Wed 27/02/02 | Tue 31/08/10
5435 | 31017 | Stage 1 - Requirements for Priority Service | PRIOR-SR | 2 | Rel-6 | S1 | 2002-05-30 08:00 | 2003-09-17 17:00 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | - |  |  |  |  | Wed 27/02/02 | Tue 31/08/10
5436 | 31043 | Priority service implementation guide | - | 2 | Rel-6 | S1 | 2003-03-28 08:00 | 2003-09-26 17:00 | 100% | SP-010523 | - | Telcordia | James Garrahan (jgarraha@telcordia.com) | - | 22.952 |  |  |  |  | Fri 04/07/03 | Tue 31/08/10
5437 | 31018 | Network Sharing | NTShar | 1 | Rel-6 | S1,S2,N1,R2,R5 | 2003-01-20 08:00 | 2006-03-10 17:00 | 100% | SP-010739 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | - |  |  |  |  | Wed 27/02/02 | Tue 10/11/09
5438 | 31019 | Technical Report on Network Sharing | NTShar-TR | 2 | Rel-6 | S1 | 2003-01-20 08:00 | 2003-12-19 17:00 | 100% | SP-010739 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 22.951 |  |  |  |  | Wed 27/02/02 | Tue 10/11/09
5439 | 31038 | Stage 1 - CRs to implement Network Sharing | NTSharCR | 2 | Rel-6 | S1 | 2003-01-20 08:00 | 2003-12-19 17:00 | 100% | SP-010739 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 22.011, 22.101, 22.115, 22.129 |  |  |  |  | Fri 14/03/03 | Tue 10/11/09
5440 | 32044 | Stage 2 for Network Sharing | - | 2 | Rel-6 | S2 | 2003-02-27 08:00 | 2004-07-30 17:00 | 100% | SP-030123 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 23.002, 23.060, 23.221, 23.236, new TS 23.251, TR 23.851 |  |  |  |  | Thu 27/03/03 | Tue 10/11/09
5441 | 11043 | Network sharing - stage 3 | - | 2 | Rel-6 | N1 | 2003-05-23 08:00 | 2004-12-08 17:00 | 100% | NP-040429 | - | T-Mobile | michele.zarri@t-mobile.co.uk | - | 23.008, 23.122, 24.007, 24.008, 29.018 |  |  |  |  | Mon 09/06/03 | Tue 10/11/09
5442 | 22004 | Enhancement of the support of network sharing in the UTRAN | NTShar-UTRANEnh | 2 | Rel-6 | R2 | 2003-09-19 | 2003-09-19 | 100% | - | - | TeliaSonera | Anders.Dahlen@TeliaSonera.com | - | 25.401, 25.413, 25.331, 25.304 |  |  |  |  | Thu 02/10/03 | Thu 13/01/05
5443 | 25004 | Conformance Test Aspects – Network Sharing | NTShar-UTRANEnh_Test | 2 | Rel-6 | R5 | 2005-03-11 08:00 | 2006-03-10 17:00 | 100% | - | - | TeliaSonera | Niklas.Wiren@TeliaSonera.com | - | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 28/02/02 | Wed 16/06/10
5444 | 32016 | QoS Improvements | QoS1 | 1 | Rel-6 | S2,N3 | 2002-07-15 08:00 | 2004-12-08 17:00 | 100% | SP-010719 | - | Nokia | - | - | 23.107, 23.207, 23.221 |  |  |  |  | Thu 24/01/02 | Thu 24/01/02
5445 | 32017 | FS on Dynamic Policy control enhancements for end-to-end QoS | - | 2 | Rel-6 | S2 | 2002-07-15 08:00 | 2004-04-23 17:00 | 100% | SP-020540 | - | Nortel | Claire Mousset | - | 23.917 withdrawn (Contents all in 23.207) |  |  |  |  | Thu 24/01/02 | Thu 08/07/04
5446 | 32059 | Definition of the Gq interface | - | 2 | Rel-6 | S2 | 2003-07-01 08:00 | 2004-04-23 17:00 | 100% | SP-030306 | - | - | Janne Rinne | - | 23.207 |  |  |  |  | Wed 23/07/03 | Thu 08/07/04
5447 | 13016 | Gq interface specification for Dynamic Policy control enhancements – Stage 3 | - | 2 | Rel-6 | N3 | 2003-08-29 08:00 | 2004-12-08 17:00 | 100% | NP-030198 | - | Nokia | Anna.Sillanpaai@nokia.com | [DAB - 25.05.04] - Delayed to Sept - possibly Dec 2004 | 29.207, 29.208, 29.209 |  |  |  |  | Mon 13/10/03 | Wed 09/03/05
5448 | 33002 | Subscriber certificates | SEC1-SC | 1 | Rel-6 | S3,S2,N1,N4,T3,OMA | 2002-02-25 08:00 | 2004-12-08 17:00 | 100% | SP-010622 | - | Nokia | valtteri.niemi@nokia.com | SP#14 approved WID | - |  |  |  |  | Thu 24/01/02 | Mon 08/08/11
5449 | 32705 | Stage 1 of Subscriber certificates | - | 2 | Rel-6 | S3 | 2002-02-25 08:00 | 2002-09-12 17:00 | 100% | SP-010622 | - | Nokia | valtteri.niemi@nokia.com | - | New (33.220, 33.221, 33.222, 33.246, 33.919) |  |  |  |  | Thu 26/09/02 | Mon 07/06/10
5450 | 32706 | Architecture review | - | 2 | Rel-6 | S2 | 2002-10-14 08:00 | 2002-11-14 17:00 | 100% | - | - | Nokia | - | - | - |  |  |  |  | Thu 26/09/02 | Tue 10/11/09
5451 | 14504 | Stage 3 for Subscriber certificates | - | 2 | Rel-6 | N4,T3 | 2003-09-19 08:00 | 2004-11-30 17:00 | 100% | NP-030399 | - | Nokia | Lauri Laitinen | Finished in CN4#26 | 23.003, 23.008, 29.109, 29.230, T3 31.102, 31.103, 31.111 |  |  |  |  | Wed 15/10/03 | Tue 10/11/09
5452 | 11049 | Stage 3 Ua & Ub interfaces | - | 2 | Rel-6 | N1 | 2003-11-03 08:00 | 2004-12-08 17:00 | 100% | - | - | Nokia | - | - | 24.109 |  |  |  |  | Mon 01/03/04 | Tue 10/11/09
5453 | 60007 | OMA dependencies on Subscriber certificates | - | 2 | Rel-6 | OMA | 2004-01-01 08:00 | 2004-06-08 17:00 | 100% | - | - | Nokia | OMA-LIAISON@mail.openmobilealliance.org | Updated according to SP-040420 | - |  |  |  |  | Tue 08/06/04 | Tue 10/11/09
5454 | 15010 | Rel-6 Open Service Access (OSA) enhancements | OSA3 | 1 | Rel-6 | N5 | 2002-10-31 08:00 | 2005-03-10 17:00 | 100% | NP-040351 | - | Alcatel | Chelo.Abarca@alcatel.fr | CN#25: Updated WID NP-040351 replaces NP-040144. | 22.127, 23.198, 29.198, 29.199, 29.998 |  |  |  |  | Wed 20/03/02 | Thu 13/01/05
5455 | 31040 | Scope of the Open Service Access Release 6 | - | 2 | Rel-6 | S1 | 2003-03-28 08:00 | 2003-06-27 17:00 | 100% | SP-030038 | - | - | - | - | - |  |  |  |  | Fri 28/03/03 | Fri 12/03/04
5456 | 15038 | OSA Stage 2 | - | 2 | Rel-6 | N5 | 2004-08-13 08:00 | 2005-03-10 17:00 | 100% | - | - | - | - | Inherited by CN5 from SA2 at TSG#25 Sep 2004. SA2's 23.127 (OSA/VHE Stage 2) replaced from Rel-6 onwards by a new CN5 TS 23.198 (Stage 2 OSA-only). | 23.198 OSA Stage 2-ONLY replaces 23.127 (OSA/VHE) from Rel-6 onwards |  |  |  |  | Fri 03/09/04 | Fri 25/03/05
5457 | 15026 | Multi Media Messaging function | - | 2 | Rel-6 | N5 | 2002-10-31 08:00 | 2004-09-10 17:00 | 100% | - | - | - | - | - | 29.198-15 |  |  |  |  | Mon 13/01/03 | Thu 13/01/05
5458 | 15028 | Policy management extensions | - | 2 | Rel-6 | N5 | 2002-10-31 08:00 | 2003-12-12 17:00 | 100% | - | - | - | - | - | 29.198, 29.998 |  |  |  |  | Mon 13/01/03 | Thu 13/01/05
5459 | 15029 | TS on Presence and Availability Management (from the PRESNC WI) | - | 2 | Rel-6 | N5 | 2002-10-31 08:00 | 2004-03-26 17:00 | 100% | - | - | - | - | N5#26: Split WI into TS & TR. | 29.198-14 |  |  |  |  | Mon 13/01/03 | Thu 13/01/05
5460 | 15032 | OSA interfaces at different levels of abstractions (Parlay X, Web services) | - | 2 | Rel-6 | N5 | 2003-07-14 08:00 | 2004-09-10 17:00 | 100% | - | - | - | - | - | 29.199 |  |  |  |  | Thu 27/03/03 | Thu 13/01/05
5461 | 15033 | Introduction of migration support mechanism | - | 2 | Rel-6 | N5 | 2002-10-31 08:00 | 2003-12-10 17:00 | 100% | - | - | - | - | - | 29.198, 29.998 |  |  |  |  | Thu 27/03/03 | Thu 13/01/05
5462 | 15036 | Framework Function for Federation | - | 2 | Rel-6 | N5 | 2003-02-03 08:00 | 2003-12-12 17:00 | 100% | - | - | - | - | - | 29.198, 29.998 |  |  |  |  | Thu 27/03/03 | Thu 13/01/05
5463 | 60008 | OMA potential overlaps with 3GPP OSA Stage 3 (Web services) | - | 2 | Rel-6 | OMA | 2003-12-18 08:00 | 2004-09-16 17:00 | 100% | - | - | - | - | TSG#25 Approved CN5 29.199 Parlay X Web services. Ongoing 3GPP/OMA co-ordination to avoid OMA producing conflicting/OVERLAPING specs (NP-040283/SP-040493). | - |  |  |  |  | Tue 08/06/04 | Fri 25/03/05
5464 | 15037 | Deleted - TR on Presence and Availability Management (from the PRESNC WI) | - | 2 | Rel-6 | N5 | 2004-09-17 17:00 | 2004-09-17 17:00 | 100% | - | - | - | - | N5#26:TR Completion 09/04; consistent with CN1 delayed Rel-6 completion. | - |  |  | NP-24 |  | Wed 20/10/04 | Thu 21/10/04
5465 | 50401 | Addition of frequency bands to GSM (TAPS) | TAPS | 1 | Rel-6 | GP | 2002-06-28 08:00 | 2005-01-28 17:00 | 100% | GP-022072 | - | Nokia | Torben Themsen | - | - |  |  |  |  | Wed 31/07/02 | Wed 09/03/05
5466 | 50094 | Addition of frequency bands to GSM – Changes to core specs | TAPS-Specs | 2 | Rel-6 | G1 | 2002-11-15 08:00 | 2002-12-20 17:00 | 100% | GP-022073 | - | Nokia | Torben Themsen | - | - |  |  |  |  | Wed 31/07/02 | Thu 13/02/03
5467 | 51102 | Changes to core specs | - | 3 | Rel-6 | G1 | 2002-11-15 08:00 | 2002-12-20 17:00 | 100% | GP-022073 | - | Nokia | Torben Themsen | - | - |  |  |  |  | Wed 31/07/02 | Thu 13/02/03
5468 | 54102 | Deleted - Addition of frequency bands to GSM – Changes for conformance tests | TAPS-Conf | 2 | Rel-6 | G4 | 2002-06-28 08:00 | 2005-01-28 17:00 | 100% | GP-022074 | - | Nokia | Torben Themsen | - | - |  |  | GP-23 |  | Wed 31/07/02 | Wed 09/03/05
5469 | 54103 | Deleted - 51.010-1 Add testing | - | 3 | Rel-6 | G4 | 2002-06-28 08:00 | 2005-01-28 17:00 | 100% | GP-022074 | - | Nokia | Torben Themsen | - | - |  |  | GP-23 |  | Wed 31/07/02 | Wed 09/03/05
5470 | 50130 | Seamless support of streaming services in A/Gb mode | SSStrea | 1 | Rel-6 | GP,S3 | 2000-01-03 08:00 | 2005-06-17 17:00 | 100% | GP-022561 | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 26/09/02 | Wed 14/01/04
5471 | 51131 | Identification of requirements for streaming | - | 2 | Rel-6 | G1 | 2003-06-27 08:00 | 2003-08-29 17:00 | 100% | GP-022564 | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 26/09/02 | Tue 16/09/03
5472 | 51133 | Requirements for streaming | - | 3 | Rel-6 | G1 | 2003-06-27 08:00 | 2003-08-29 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
5473 | 51132 | Performance study of cell change mechanisms | - | 2 | Rel-6 | G1 | 2000-01-03 08:00 | 2003-08-29 17:00 | 100% | GP-022562 | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 26/09/02 | Tue 16/09/03
5474 | 51134 | Performance of NACC | - | 3 | Rel-6 | G1 | 2000-01-03 08:00 | 2003-08-29 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
5475 | 51135 | Performance of cell change in DTM for the PS domain | - | 3 | Rel-6 | G1 | 2000-01-03 08:00 | 2003-08-29 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
5476 | 51136 | Handover for Seamless support of streaming services in A/Gb mode | - | 3 | Rel-6 | G1 | 2000-01-03 08:00 | 2003-08-29 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
5477 | 52131 | Reduction of service interruption times and packet loss during mobility procedures | - | 2 | Rel-6 | G2 | 2003-06-27 08:00 | 2005-06-17 17:00 | 100% | GP-022563 | - | Vodafone | José Luis Carrizo Martínez | Completed at GERP#17 | - |  |  |  |  | Thu 26/09/02 | Tue 16/09/03
5478 | 52133 | optimizations of existing mechanisms/procedures | - | 3 | Rel-6 | G2 | 2003-06-27 08:00 | 2003-11-21 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
5479 | 52134 | Inter-system NACC | - | 3 | Rel-6 | G2 | 2003-06-27 08:00 | 2003-11-21 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
5480 | 52135 | PS Handover (within GERAN and between GERAN and UTRAN) | - | 3 | Rel-6 | G2 | 2003-06-27 08:00 | 2005-06-17 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
5481 | 52136 | Dependency to other features of Reduction of service interruption times and packet loss during mobility procedures | - | 3 | Rel-6 | G2 | 2003-06-27 08:00 | 2003-11-21 17:00 | 100% | - | - | Vodafone | José Luis Carrizo Martínez | - | - |  |  |  |  | Thu 13/02/03 | Tue 16/09/03
5482 | 54131 | Deleted - MS conformance testing for Seamless support of streaming services in A/Gb mode | - | 2 | Rel-6 | G3new | 2003-12-19 08:00 | 2004-01-30 17:00 | 100% | GP-023424 | - | Vodafone | José Luis Carrizo Martínez | Marked as stopped 10/2009 | - |  |  | GP-27 |  | Thu 26/09/02 | Tue 13/10/09
5483 | 54132 | Deleted - MS conformance tests for Seamless support of streaming services in A/Gb mode | - | 3 | Rel-6 | G4,G5 | 2003-12-19 08:00 | 2004-01-30 17:00 | 100% | GP-023424 | - | Vodafone | José Luis Carrizo Martínez | Marked as stopped 10/2009 | - |  |  | GP-27 |  | Thu 13/02/03 | Tue 13/10/09
5484 | 33013 | GERAN A/Gb mode security enhancements | - | 2 | Rel-6 | S3 | 2002-09-26 08:00 | 2005-01-28 17:00 | 100% | SP-030107 | - | Vodafone | peter.howard@vodafone.com | SP#19 approved WID | 33.102 |  |  |  |  | Wed 15/01/03 | Mon 08/08/11
5485 | 34300 | Performance characterisation of default codecs for PS conversational multimedia application | CODCAR | 1 | Rel-6 | S4 | 2002-09-13 08:00 | 2004-06-10 17:00 | 100% | SP-020433 | - | Nokia | pasi.s.ojala@nokia.com | - | 26.935 |  |  |  |  | Thu 26/09/02 | Wed 08/09/04
5486 | 31030 | Study on Privacy Capability | PrivCap | 1 | Rel-6 | S1 | 2003-11-10 08:00 | 2004-03-03 17:00 | 100% | SP-020579 | - | Lucent | Michael Boote (mboote@alcatel-lucent.com) | - | 22.949 |  |  |  |  | Fri 08/11/02 | Tue 31/08/10
5487 | 35010 | Rel-6 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM6 | 1 | Rel-6 | S5 | 2002-09-12 08:00 | 2005-03-11 17:00 | 100% | SP-040766 | - | - | - | SP#26: Updated WID SP-040766 was SP-020445. Completion delayed 12/04->03/05 due to OAM-Trace in CN1/4. | - |  |  |  |  | Fri 08/11/02 | Thu 13/01/05
5488 | 35011 | Principles, high level Requirements and Architecture | - | 2 | Rel-6 | S5 | 2002-09-12 08:00 | 2004-09-16 17:00 | 100% | SP-040767 | - | Motorola | - | SP#25 09/2004 completed | 32.101, 32.102 |  |  |  |  | Fri 08/11/02 | Fri 13/01/06
5489 | 35012 | Performance Management | - | 2 | Rel-6 | S5 | 2002-09-12 08:00 | 2004-12-16 17:00 | 100% | SP-040782 | - | Nortel | - | SP#26 12/2004 completed | 32.401, 32.403, 52.402, 32.411, 32.412, 32.413, 32.432, 32.435, 32.436 |  |  |  |  | Fri 08/11/02 | Fri 13/01/06
5490 | 35014 | Network Infrastructure Management | - | 2 | Rel-6 | S5 | 2002-09-12 08:00 | 2004-12-16 17:00 | 100% | SP-040789 | - | Ericsson | thomas.tovinger@ericsson.com | SP#26 12/2004 completed | 32.150/1/2, 32.805, 32.111-5, 32.313/4, 32.331/2/3/4/5, 32.341/2/3/4, 32.351/2/3/4, 32.361/2/3/4, 32.371/2/3/4, 32.804, 32.675, 32.690, 32.695, 32.71/2/3/4/5, 32.741/2/3/4/5 |  |  |  |  | Fri 08/11/02 | Mon 21/02/11
5491 | 35015 | Rel-6 Trace Management | OAM-Trace | 2 | Rel-6 | S5,N4,R3 | 2002-09-20 08:00 | 2005-03-11 17:00 | 100% | SP-040782 | - | Nokia | kari.t.ronka@nokia.com | SP#26 12/2004 SA5 completed 12/04. Signalling Based Trace Activation for IMS (SIP) moved to Rel-7. Reason: CN1 cannot complete 24.229 trace without IETF dependency => estimate 05/2005. | - |  |  |  |  | Fri 08/11/02 | Wed 09/03/05
5492 | 35022 | Subscriber and UE trace management | - | 3 | Rel-6 | S5 | 2002-09-20 08:00 | 2004-12-16 17:00 | 100% | - | - | Nokia | kari.t.ronka@nokia.com | SP#26 12/2004 completed | 32.421, 32.422, 32.423, 52.008 |  |  |  |  | Fri 03/10/03 | Fri 13/01/06
5493 | 23013 | Subscriber and equipment trace in UTRAN | OAM-Trace-RAN | 3 | Rel-6 | R3 | 2003-06-06 08:00 | 2004-06-15 17:00 | 100% | - | - | Nortel | Yann Sehedi (sehedic@nortelnetworks.com) | - | 25.413, 25.420, 25.423 |  |  |  |  | Fri 04/07/03 | Thu 13/01/05
5494 | 14016 | Trace Management, Stage3 | - | 3 | Rel-6 | N4 | 2004-06-09 08:00 | 2005-03-11 17:00 | 100% | NP-040411 | - | Nokia | seppo.kauntola@nokia.com | - | 23.205, 29.232, 29.060, 29.002, 29.228 |  |  |  |  | Mon 01/03/04 | Wed 09/03/05
5495 | 35016 | Rel-6 Charging Management | CH | 1 | Rel-6 | S5,S2,N3 | 2002-11-21 08:00 | 2005-06-09 17:00 | 100% | SP-040773 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | SP#28 Target 09/2005 for WLAN Charging 32.252 | - |  |  |  |  | Mon 13/01/03 | Fri 13/01/06
5496 | 35037 | Charging architecture and principles | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.240 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5497 | 35024 | Charging Data Record (CDR) file format and transfer | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-03-18 17:00 | 100% | - | - | - | - | SP#23 03/2004 completed | 32.297 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5498 | 35025 | CDR parameter description | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2005-06-09 17:00 | 100% | - | - | - | - | SP#28 06/2005 completed | 32.298 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5499 | 35026 | Diameter charging applications | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.299 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5500 | 35027 | Online Charging System (OCS) architecture study | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2003-09-18 17:00 | 100% | - | - | - | - | SP#21 09/2003 completed | 32.815 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5501 | 35028 | OCS: Applications and interfaces | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-12-16 17:00 | 100% | - | - | - | - | SP#26 12/2004 completed | 32.296 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5502 | 35017 | Charging Management for Bearer level | CH-BC | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | SP-030048 | - | Nokia | Benni ALEXANDER | SP#28 Target 09/2005 for WLAN Charging 32.252 | - |  |  |  |  | Mon 13/01/03 | Fri 13/01/06
5503 | 35029 | CS domain charging | - | 3 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-03-18 17:00 | 100% | - | - | - | - | SP#23 03/2004 completed | 32.250 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5504 | 35030 | PS domain charging | - | 3 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.251 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5505 | 35031 | CDR transfer | - | 3 | Rel-6 | S5 | 2003-03-21 08:00 | 2004-09-16 17:00 | 100% | - | - | - | - | SP#25 09/2004 completed | 32.295 |  |  |  |  | Fri 29/10/04 | Fri 13/01/06
5506 | 35019 | Charging Management for the Service domain | - | 2 | Rel-6 | S5 | 2003-03-21 08:00 | 2005-06-09 17:00 | 100% | SP-040778 | - | Siemens | Gerald.Goermer@nsn.com | SP#26: Updated WID SP-040778 was SP-030050. Target completion 06/2005. Consisting of MMS-CH, LCS-CH, WLAN-CH, POC-CH, MBMS-CH | 32.252, 32.270, 32.271, 32.272 |  |  |  |  | Mon 13/01/03 | Fri 13/01/06
5507 | 32030 | Overall architectural aspects of IP flow based bearer level charging | CH-FBC | 2 | Rel-6 | S2,N3 | 2002-11-21 08:00 | 2005-03-11 17:00 | 100% | SP-040041 | - | - | - | - | 23.125 |  |  |  |  | Wed 15/01/03 | Thu 08/07/04
5508 | 32069 | Overall definition of FBC architecture | - | 3 | Rel-6 | S2 | 2002-11-21 08:00 | 2004-03-02 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 20/05/04 | Wed 09/03/05
5509 | 32070 | Study on providing policy control with FBC | - | 3 | Rel-6 | S2 | 2004-02-02 08:00 | 2004-07-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 20/05/04 | Thu 21/10/04
5510 | 13020 | Gx interface for flow based charging | - | 3 | Rel-6 | N3 | 2004-02-02 08:00 | 2004-12-08 17:00 | 100% | NP-040245 | - | Nokia | juha.a.rasanen@nokia.com | - | 29.210 |  |  |  |  | Thu 20/05/04 | Wed 09/03/05
5511 | 13021 | Rx interface for flow based charging | - | 3 | Rel-6 | N3 | 2004-02-02 08:00 | 2005-03-11 17:00 | 100% | NP-040339 | - | Nortel | Javier Gonzalez Gallego | - | 29.209 |  |  |  |  | Thu 20/05/04 | Fri 25/03/05
5512 | 1800 | Rel-6 UICC/USIM enhancements and interworking | USAT1 | 1 | Rel-6 | T3 | 2000-09-25 08:00 | 2005-03-10 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 14/09/00 | Fri 01/12/00
5513 | 1802 | UICC API | USAT1-API | 2 | Rel-6 | T3 | 2002-03-20 08:00 | 2005-03-10 17:00 | 100% | - | - | - | - | 8/3/2001: test spec is based on R99 core spec, so deleted from Workplan | - |  |  |  |  | Thu 14/09/00 | Mon 12/03/01
5514 | 43001 | Rel-6 Java API Test specification | - | 3 | Rel-6 | T3 | 2002-03-20 08:00 | 2002-06-10 17:00 | 100% | TP-020029 | - | Microelectrónica Española | Mario Pérez | - | - |  |  |  |  | Thu 30/05/02 | Tue 09/02/10
5515 | 43006 | 2G/3G Java Card™ API based applet interworking | - | 3 | Rel-6 | T3 | 2003-03-17 08:00 | 2004-03-05 17:00 | 100% | TP-030031 | - | Oberthur Card Systems | Stéphane Andrau | - | - |  |  |  |  | Mon 08/09/03 | Wed 19/01/05
5516 | 43007 | (U)SIM API for Java Card Testing | - | 3 | Rel-6 | T3 | 2003-03-17 08:00 | 2005-03-10 17:00 | 100% | TP-040186 | - | Axalto | Christophe Begassat (cbegassat@axalto.com) | - | 31.213 |  |  |  |  | Mon 08/09/03 | Thu 02/06/05
5517 | 43003 | Deleted - Java API Test specification (TS 43.019 Rel-5) | - | 3 | Rel-6 | T3 | 2002-05-30 08:00 | 2003-06-09 17:00 | 100% | TP-020122 | - | Microelectrónica Española | Mario Pérez | MOVED to Rel-5 WP | - |  |  | TP-20 |  | Thu 26/09/02 | Tue 09/02/10
5518 | 43004 | Rel-6 USIM toolkit enhancements | USAT1-API-MULTOS | 2 | Rel-6 | T3 | 2000-09-25 08:00 | 2005-03-04 17:00 | 100% | - | - | Aspects Software | Neil Livingston | - | - |  |  |  |  | Fri 29/11/02 | Wed 19/01/05
5519 | 502031 | C SIM API | - | 3 | Rel-6 | T3 | 2000-09-25 08:00 | 2002-09-27 17:00 | 100% | TP-000155 | - | Aspects Software | Neil Livingston | - | 31.101, 31.102, 31.103, 31.111, 31.113, new 31.115, 31.116 |  |  |  |  | Wed 27/09/00 | Tue 09/02/10
5520 | 502032 | Specification of C SIM API | - | 4 | Rel-6 | T3 | 2000-09-25 08:00 | 2002-09-27 17:00 | 100% | TP-000155 | - | Aspects Software | Neil Livingston | - | - |  |  |  |  | Sun 09/04/00 | Tue 09/02/10
5521 | 502033 | Test specification for C SIM API | - | 4 | Rel-6 | T3 | 2001-01-01 08:00 | 2001-09-28 17:00 | 100% | TP-000155 | - | Aspects Software | Neil Livingston | - | - |  |  |  |  | Thu 14/09/00 | Tue 09/02/10
5522 | 43009 | USIM application toolkit Conformance Test Specification for Mobile Equipments | - | 3 | Rel-6 | T3 | 2003-12-05 08:00 | 2005-03-04 17:00 | 100% | TP-030259 | - | Gemplus | Eric.laffont@gemplus.com | - | 31.124 |  |  |  |  | Mon 06/12/04 | Thu 02/06/05
5523 | 34022 | Packet Switched Streaming Services Rel-6 | PSSrel6 | 1 | Rel-6 | S4,S1 | 2002-11-18 08:00 | 2005-12-07 17:00 | 100% | SP-020685 | - | Ericsson | olle.franceschi@ericsson.com | - | - |  |  |  |  | Thu 28/11/02 | Fri 13/11/09
5524 | 31039 | Stage 1 for Packet Switched Streaming Services Rel-6 | - | 2 | Rel-6 | S1 | 2002-11-18 08:00 | 2003-03-17 17:00 | 100% | SP-020685 | - | Ericsson | - | 2nd resp SA4 | 22.233 |  |  |  |  | Fri 14/03/03 | Fri 13/11/09
5525 | 34024 | Stage 3 for Packet Switched Streaming Services Rel-6 | PSSrel6-Stage3 | 2 | Rel-6 | S4 | 2002-12-13 08:00 | 2005-12-07 17:00 | 100% | SP-020685 | - | Ericsson | olle.franceschi@ericsson.com | TR tbc by Sept. 05 | 26.233, 26.234, 26.244, 26.245, 26.246, 26.401, 26.402, 26.403, 26.404, 26.405, 26.406, 26.410, 26.411, 26.412, 26.273, 26.290, 26.304, 26.412, 26.274, 26.936 |  |  |  |  | Thu 27/03/03 | Fri 13/11/09
5526 | 34023 | AMR-WB extension for high audio quality | AMRWB+ | 1 | Rel-6 | S4 | 2002-12-13 08:00 | 2005-12-07 17:00 | 100% | SP-030083 | - | Nokia | janne.m.vainio@nokia.com | TR tbc by Sept. 05 | 26.290, 26.304, 26.273, 26.274, 26.412, 26.936 |  |  |  |  | Thu 28/11/02 | Fri 13/01/06
5527 | 34027 | Codec Enhancements for Packet Switched Conversational Multimedia Applications | CEPSCM | 1 | Rel-6 | S4 | 2004-03-16 08:00 | 2004-12-16 17:00 | 100% | SP-040066 | - | Nokia | miska.hannuksela@nokia.com | - | 26.235, 26.236 |  |  |  |  | Tue 02/03/04 | Mon 06/12/04
5528 | 34028 | 3G-324M Improvements | 3G-324MI | 1 | Rel-6 | S4 | 2004-03-16 08:00 | 2004-12-16 17:00 | 100% | SP-040067 | - | Ericsson | bo.burman@ericsson.com | - | 26.111, 26.911 |  |  |  |  | Tue 02/03/04 | Mon 06/12/04
5529 | 51101 | Single Antenna Receiver Interference Cancellation (SAIC) | SAIC | 1 | Rel-6 | GP,G1 | 2002-11-15 08:00 | 2004-06-25 16:22 | 100% | GP-023400 | - | Cingular | Marc Grant | - | 45.903 |  |  |  |  | Thu 13/02/03 | Wed 18/11/09
5530 | 12006 | Enhancement of dialled service for CAMEL | EDCAMEL | 1 | Rel-6 | S1,N2,N4 | 2003-03-28 08:00 | 2003-12-31 17:00 | 100% | SP-020818 | - | Samsung | craig.bishop@samsung.com | - | 22.078 |  |  |  |  | Fri 14/03/03 | Fri 13/11/09
5531 | 12007 | Stages 2 and 3 for Enhancement of dialled service for CAMEL | - | 2 | Rel-6 | N2,N4 | 2003-03-28 08:00 | 2003-12-31 17:00 | 100% | NP-030153 | - | Samsung | Richard Brook | - | 23.008, 23.016, 23.018, 23.078, 29.002, 29.078 |  |  |  |  | Thu 27/03/03 | Fri 13/11/09
5532 | 32060 | Study on Bandwidth and resource savings in CS networks | BARS | 1 | Rel-6 | S2 | 2003-06-01 08:00 | 2004-06-16 17:00 | 100% | SP-030308 | - | - | - | - | 23.977 |  |  |  |  | Wed 23/07/03 | Thu 08/07/04
5533 | 50600 | Multiple TBF in A/Gb mode | MULTBF | 1 | Rel-6 | GP,G2 | 2002-04-05 08:00 | 2005-01-28 17:00 | 100% | GP-021263 | - | Ericsson | gunnar.mildh@era.ericsson.se | GP#17 Nov 2003 Moved from Rel-5 UID_50058 MULTBF (Only Multiple TBF Concept paper produced in Rel-5) | - |  |  |  |  | Thu 31/07/03 | Fri 13/01/06
5534 | 50601 | Multiple TBF in A/Gb mode - Core | MULTBF-Agbmode | 2 | Rel-6 | GP,G2 | 2002-04-05 08:00 | 2003-08-29 17:00 | 100% | GP-021263 | - | Ericsson | gunnar.mildh@era.ericsson.se | - | - |  |  |  |  | Thu 31/07/03 | Tue 16/09/03
5535 | 50602 | Multiple TBF Concept paper | - | 3 | Rel-6 | GP,G2 | 2002-04-05 08:00 | 2003-08-29 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 31/07/03 | Tue 16/09/03
5536 | 50603 | Multiple TBF Stage 2 (43.064) CRs | - | 3 | Rel-6 | GP,G2 | 2002-04-05 08:00 | 2003-08-29 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 31/07/03 | Tue 16/09/03
5537 | 50604 | Multiple TBF Stage 3 (44.060) CRs | - | 3 | Rel-6 | GP,G2 | 2002-04-05 08:00 | 2003-08-29 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 31/07/03 | Mon 06/12/04
5538 | 50605 | Deleted - Multiple TBF in A/Gb mode – MS testing | MULTBF-Testing | 2 | Rel-6 | G3new | 2005-01-28 17:00 | 2005-01-28 17:00 | 100% | GP-022098 | - | Ericsson | gunnar.mildh@era.ericsson.se | - | - |  |  | GP-27 |  | Thu 31/07/03 | Wed 09/03/05
5539 | 50096 | Alignment between the test-regimes for GERAN capable MS | ALTERE | 1 | Rel-6 | G3new | 2003-08-29 08:00 | 2005-09-02 17:00 | 99% | GP-032236 | - | Ericsson | anthony.toubassi@sonyericsson.com | - | - |  |  |  |  | Tue 16/09/03 | Fri 13/01/06
5540 | 50097 | Determine the controversial test cases in the different test regimes and align them with 3GPP GERAN test specifications. Such test cases to be added to TS 51.010. | ALTERE-TC | 2 | Rel-6 | G3new | 2003-08-29 08:00 | 2005-09-02 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 16/09/03 | Fri 13/01/06
5541 | 50444 | Addition of U-TDOA in the CS domain | UTDOACS | 1 | Rel-6 | GP | 2003-11-21 08:00 | 2004-04-23 17:00 | 100% | GP-032773 | - | TruePosition | Bob Gross, Rhys Robinson (rlgross@trueposition.com) | Completed, except for potential LMU performance specs | - |  |  |  |  | Mon 01/12/03 | Fri 12/03/04
5542 | 50445 | Addition of U-TDOA in the PS domain | UTDOAPS | 1 | Rel-6 | GP | 2003-06-27 08:00 | 2004-11-12 17:00 | 100% | GP-032774 | - | TruePosition | Bob Gross, Rhys Robinson (rlgross@trueposition.com) | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
5543 | 50101 | Downlink Advanced Receiver Performance | DARP | 1 | Rel-6 | GP | 2003-11-21 08:00 | 2005-09-02 17:00 | 100% | GP-041966 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
5544 | 50102 | DARP test scenarios | DARP-TS | 2 | Rel-6 | GP | 2003-11-21 08:00 | 2004-08-27 17:00 | 100% | GP-041967 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
5545 | 50103 | DARP for GMSK modulated voice services | DARP-GMSK | 2 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | GP-041968 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
5546 | 50104 | Performance requirements in 45.005 for DARP for GMSK modulated voice services | DARP-GMSK-Perf | 3 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
5547 | 50105 | Radio subsystem link control in 45.008 for DARP for GMSK modulated voice services | DARP-GMSK-LC | 3 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
5548 | 50106 | DARP for GPRS and EGPRS MCS1-MCS4 | DARP-GPRSE | 2 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | GP-041969 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Wed 09/03/05
5549 | 50107 | Performance requirements in 45.005 for DARP for GPRS and EGPRS MCS1-MCS4 | DARP-GPRSE-Perf | 3 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
5550 | 50108 | Radio subsystem link control in 45.008 for DARP for GPRS and EGPRS MCS1-MCS4 | DARP-GPRSE-LC | 3 | Rel-6 | GP | 2004-02-06 08:00 | 2004-11-12 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
5551 | 50115 | DARP Capability signalling | DARP-CAPSIG | 2 | Rel-6 | GP | 2003-11-21 08:00 | 2004-11-12 17:00 | 100% | GP-041970 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Mon 06/12/04
5552 | 50116 | GERAN MS Conformance test for DARP | ARP-ConfTest | 2 | Rel-6 | G3new | 2004-08-27 08:00 | 2005-09-02 17:00 | 100% | GP-041971 | - | Nokia | tommy.bysted@nokia.com | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
5553 | 50109 | Reduction of PS service interruption in Dual Transfer Mode | PSintDTM | 1 | Rel-6 | G2 | 2003-11-21 08:00 | 2005-06-24 17:00 | 100% | GP-032548 | - | Siemens | toby.proctor@roke.co.uk | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
5554 | 50110 | Use case and requirement definition | PSintDTM-Req | 2 | Rel-6 | G2 | 2003-11-21 08:00 | 2004-04-23 17:00 | 100% | GP-032549 | - | Siemens | toby.proctor@roke.co.uk | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
5555 | 50111 | Performance Study of Current Procedures | PSintDTM-Perf | 2 | Rel-6 | G2 | 2003-11-21 08:00 | 2004-04-23 17:00 | 100% | GP-032550 | - | Siemens | toby.proctor@roke.co.uk | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
5556 | 50112 | Reduction of service interruption times and packet loss during Dual Transfer Mode and mobility procedures | PSintDTM-Reduct | 2 | Rel-6 | G2 | 2004-04-23 08:00 | 2004-11-12 17:00 | 100% | GP-032551 | - | Siemens | toby.proctor@roke.co.uk | - | - |  |  |  |  | Mon 01/12/03 | Fri 13/01/06
5557 | 50113 | Deleted - MS Conformance testing - Reduction of PS service interruption in DTM | PSintDTM-ConfMS | 2 | Rel-6 | G3new | 2004-06-25 08:00 | 2005-06-24 17:00 | 100% | - | - | - | - | - | - |  |  | GP-25 |  | Mon 01/12/03 | Fri 12/12/08
5558 | 50114 | Deleted - BTS Conformance testing - Reduction of PS service interruption in DTM | PSintDTM-ConfBTS | 2 | Rel-6 | G3new | 2005-06-24 17:00 | 2005-06-24 17:00 | 100% | - | - | - | - | - | - |  |  | GP-25 |  | Mon 01/12/03 | Fri 13/01/06
5559 | 12008 | CAMEL prepay interworking with SCUDIF | SCCAMEL | 1 | Rel-6 | N4,N3,S1 | 2003-12-08 08:00 | 2004-10-05 10:24 | 100% | NP-030584 | - | Nokia | Keijo.Palviainen@Nokia.Com | - | 22.078, 23.078, 29.078, 29.002, 23.172 |  |  |  |  | Wed 03/03/04 | Fri 13/11/09
5560 | 31046 | Circuit Switched Video and Voice Service Improvements | CS_VSS | 1 | Rel-6 | S2,N1 | 2004-01-12 08:00 | 2005-09-02 17:00 | 100% | SP-040331 | - | Vodafone | John Watson | - | - |  |  |  |  | Fri 14/03/03 | Thu 08/07/04
5561 | 31047 | Deleted - Stage 1 - Requirements | - | 2 | Rel-6 | S1 | 2004-01-12 08:00 | 2004-10-14 17:00 | 100% | SP-040331 | - | Vodafone | John Watson | - | 22.101 |  |  | SP-26 |  | Tue 27/01/04 | Tue 08/06/04
5562 | 32071 | Stage 2 Study on architecture alternatives | - | 2 | Rel-6 | S2 | 2004-01-12 08:00 | 2004-12-16 17:00 | 100% | SP-040331 | - | Vodafone | chris.pudney@vodafone.com | - | 23.903 |  |  |  |  | Thu 20/05/04 | Mon 06/12/04
5563 | 32072 | Deleted - Stage 2 description on Redial | - | 2 | Rel-6 | S2 | 2004-05-03 08:00 | 2004-12-16 17:00 | 100% | SP-040331 | - | Vodafone | chris.pudney@vodafone.com | - | - |  |  | SP-26 |  | Thu 20/05/04 | Wed 09/03/05
5564 | 11053 | Switching between voice and video call - Redial solution | - | 2 | Rel-6 | N1 | 2005-01-03 08:00 | 2005-06-17 17:00 | 100% | SP-040331 | - | Vodafone | - | - | 23.009, 24.008 |  |  |  |  | Wed 20/04/05 | Thu 02/06/05
5565 | 52137 | Deleted - CS_VSS - GERAN2 Part | - | 2 | Rel-6 | G2 | 2005-09-02 17:00 | 2005-09-02 17:00 | 100% | SP-040331 | - | Vodafone | - | - | - |  |  | GP-26 |  | Wed 28/01/04 | Thu 21/04/05
5566 | 13017 | Deleted - CS_VSS - CN3 Part | - | 2 | Rel-6 | N3 | 2004-10-14 17:00 | 2004-10-14 17:00 | 100% | SP-040331 | - | Vodafone | - | - | - |  |  | TP-26 |  | Wed 20/10/04 | Thu 21/10/04
5567 | 13024 | Reorganisation of CS Data Specifications | CSData | 1 | Rel-6 | N3 | 2004-11-19 08:00 | 2004-12-08 17:00 | 100% | NP-040563 | - | Siemens | Thomas.Belling@nsn.com | Created at TSG#27 as 100 % complete | 23.910, 29.007, New 23.202 |  |  |  |  | Wed 02/03/05 | Wed 09/03/05
5568 | 50553 | Generic Access to A/Gb Interface (GAAI) | GAAI | 1 | Rel-6 | GP | 2004-06-25 08:00 | 2006-01-20 17:00 | 100% | GP-042247 | - | Motorola | - | - | - |  |  |  |  | Fri 15/10/04 | Fri 13/01/06
5569 | 50544 | FS on GAAI | GAAG | 2 | Rel-6 | GP | 2004-06-25 08:00 | 2004-08-27 17:00 | 100% | GP-041592 | - | Motorola | - | Feasibility Study | 43.901 |  |  |  |  | Wed 30/06/04 | Fri 25/03/05
5570 | 50554 | GAAI – Stage 2 | GAAI-Stage2 | 2 | Rel-6 | GP | 2004-08-27 08:00 | 2005-04-08 17:00 | 100% | - | - | Ericsson | jari.vikberg@ericsson.com | - | 43.318 |  |  |  |  | Fri 15/10/04 | Fri 25/03/05
5571 | 50555 | GAAI – Stage 3 | GAAI-Stage3 | 2 | Rel-6 | GP | 2004-08-27 08:00 | 2005-04-08 17:00 | 100% | - | - | - | - | - | 44.318 |  |  |  |  | Fri 15/10/04 | Fri 13/01/06
5572 | 50556 | MS Conformance Test for GAAI | GAAI-CT | 2 | Rel-6 | GP | 2004-08-27 08:00 | 2006-01-20 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 90% complete) | - |  |  |  |  | Fri 15/10/04 | Fri 12/12/08
5573 | 50559 | Support of PS Handover for GERAN A/Gb mode | SPSHAGB | 1 | Rel-6 | GP,G2 | 2003-11-03 08:00 | 2005-08-24 17:00 | 100% | GP-051160 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB- Originally Started Nov 2003 as GP-030443 | - |  |  |  |  | Wed 20/04/05 | Fri 13/01/06
5574 | 50560 | Stage 2 for Support of PS Handover for GERAN A/Gb mode | SPSHAGB-Stage2 | 2 | Rel-6 | GP,G2 | 2003-11-03 08:00 | 2005-08-24 17:00 | 100% | GP-051161 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB-Stage2 | 43.129 |  |  |  |  | Wed 20/04/05 | Fri 13/01/06
5575 | 50561 | PS handover for Support of PS Handover for GERAN A/Gb mode | SPSHAGB-PSHO | 2 | Rel-6 | GP,G2 | 2003-11-03 08:00 | 2005-08-24 17:00 | 100% | GP-051162 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB-PSH | - |  |  |  |  | Wed 20/04/05 | Fri 13/01/06
5576 | 50562 | Definition of radio resource management functionality for Support of PS Handover for GERAN A/Gb mode | SPSHAGB-RRM | 2 | Rel-6 | GP,G2 | 2003-11-03 08:00 | 2005-08-24 17:00 | 100% | GP-051163 | - | Ericsson | gunnar.hedby@ericsson.com | Replaces SCSAGB-RRM | - |  |  |  |  | Wed 20/04/05 | Fri 13/01/06
5577 | 33018 | Study on (U)SIM Security Reuse by Peripheral Devices on Local Interfaces | - | 1 | Rel-6 | S3 | 2003-07-03 08:00 | 2003-12-26 17:00 | 100% | SP-030341 | - | Toshiba | Raziq Yaqub (ryaqub@tari.toshiba.com) | SP#20 approved WID | 33.817 |  |  |  |  | Fri 25/07/03 | Tue 09/08/11
5578 | 33021 | Study on Security for early IMS | SEC-IMS | 1 | Rel-6 | S3 | 2004-10-01 08:00 | 2005-03-28 17:00 | 100% | SP-040691 | - | Vodafone | Peter.Howard@vodafone.com | SP#24 approved WID. SP#46 withdrawn TR 33.978 from Rel-8 onwards | 33.978 |  |  |  |  | Fri 25/07/03 | Tue 09/08/11
5579 | 60111 | (Small) Technical Enhancements and Improvements for Rel-6 | TEI6 | 1 | Rel-6 | SP,CP,RP,GP | 2006-06-02 08:00 | 2006-06-02 08:00 | 100% | - | - | - | - | "Joker" WI, to be used for a Rel 6 CR not related to any feature and with very limited impact on the system. Moved in from Stoyan/Testing WP | - |  |  |  |  | Thu 21/09/06 | Tue 06/05/08
5580 | 25019 | Test - (Small) Technical Enhancements and Improvements for Rel-6 | TEI6_Test | 1 | Rel-6 | R5,T1 | 2006-06-02 08:00 | 2008-05-06 17:00 | 100% | - | - | - | - | "Joker" WI, to be used for small modifications applicable to Rel 4 conformance testing | 34.108,34.121-1/2,34.122,34.123-1/2/3 |  |  |  |  | Thu 21/09/06 | Tue 06/05/08
5581 | 31029 | Deleted - Study of Feature Interactions Requirements | FINTER | 1 | Rel-6 | S1 | 2004-09-16 17:00 | 2004-09-16 17:00 | 100% | SP-020578 | - | - | - | SP#25 stopped | - |  |  | SP-25 |  | Wed 20/10/04 | Tue 02/03/10
5582 | 50563 | Deleted EVGCS - Enhancements of VGCS in public networks for communication of public authority officials | - | 1 | Rel-6 | GP,G2 | 2005-08-25 08:00 | 2005-09-02 17:00 | 100% | GP-041837 | - | Siemens | kenneth.isaacs@roke.co.uk | GP#26 moved to Rel-7 as UID_11045 Enhancements of VGCS in public networks for communication of public authority officials | 44.018, 44.068, 48.008 |  |  | GP-26 |  | Wed 20/04/05 | Thu 21/04/05
5583 | 50500 | Deleted SCSAGB - Support of Conversational Services in A/Gb mode via the PS domain | - | 1 | Rel-6 | GP,N1 | 2003-11-21 17:00 | 2004-02-19 17:00 | 100% | GP-030443 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | - | - |  |  | GP-18 |  | Thu 13/02/03 | Tue 02/03/10
5584 | 50501 | Deleted - Creation of a TR | SCSAGB-TR | 2 | Rel-6 | GP | 2003-11-21 17:00 | 2003-11-21 17:00 | 100% | GP-030444 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | - | - |  |  | GP-17 |  | Thu 13/02/03 | Tue 02/03/10
5585 | 50502 | Deleted - Stage 2 | SCSAGB-Stage2 | 2 | Rel-6 | GP | 2003-11-21 17:00 | 2003-11-21 17:00 | 100% | GP-030445 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Started | - |  |  | GP-17 |  | Thu 13/02/03 | Tue 02/03/10
5586 | 50503 | Deleted - Radio Channel Support | SCSAGB-RCS | 2 | Rel-6 | GP | 2003-11-21 17:00 | 2003-11-21 17:00 | 100% | GP-030446 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Not started | - |  |  | GP-17 |  | Thu 13/02/03 | Tue 02/03/10
5587 | 50504 | Deleted SCSAGB-RRM - Definition of radio resource management functionality | - | 2 | Rel-6 | GP | 2003-11-21 17:00 | 2003-11-21 17:00 | 100% | GP-030447 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Not started | - |  |  | GP-17 |  | Thu 13/02/03 | Tue 02/03/10
5588 | 50505 | Deleted - replaced by 50561 - PS Handover | SCSAGB-PSH | 2 | Rel-6 | GP,N1 | 2003-11-24 08:00 | 2004-02-19 17:00 | 100% | GP-030448 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Started | - |  |  | GP-18 |  | Thu 13/02/03 | Tue 02/03/10
5589 | 50506 | Deleted SCSAGB-FLO - Modifications to FLO | - | 2 | Rel-6 | GP | 2003-11-21 17:00 | 2003-11-21 17:00 | 100% | GP-030449 | - | Ericsson | David Bladsjö (david.bladsjo@ericsson.com) | Not started | - |  |  | RP-29 |  | Thu 13/02/03 | Tue 02/03/10
5590 | 2 | Deleted - Rel-6 Evolutions of the transport in the UTRAN (ETRAN) | - | 1 | Rel-6 | RP | 2003-12-31 17:00 | 2003-12-31 17:00 | 100% | - | - | Alcatel | Francois Courau | Generic feature ETRAN | - |  |  | RP-22 |  | Thu 02/10/03 | Thu 08/07/04
5591 | 0 | Release 5 Features | - | 1 | Rel-5 | NP,GP,RP,SP,TP | 2000-01-03 08:00 | 2001-03-29 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 11/07/08 | Tue 09/02/10
5592 | 625 | IP transport in the UTRAN | ETRAN-IPtrans | 1 | Rel-5 | R3 | 2000-07-17 08:00 | 2002-03-29 17:00 | 100% | - | - | Alcatel | Nicolas Drevon | - | - |  |  |  |  | Fri 31/03/00 | Wed 12/12/01
5593 | 2455 | Feasibility study on SS7 signalling transportation in the core network with SCCP-User Adaptation (SUA) | FS_SS7IP | 1 | Rel-5 | N4 | 2001-03-12 08:00 | 2001-12-21 17:00 | 100% | NP-010460 | - | - | - | - | 29.903 |  |  |  |  | Mon 12/03/01 | Wed 12/12/01
5594 | 2476 | High Speed Downlink Packet Access | HSDPA | 1 | Rel-5 | R2,R5 | 2001-04-02 08:00 | 2007-03-09 17:00 | 100% | - | - | Motorola | Ravi Kuchibhotla | - | - |  |  |  |  | Tue 20/03/01 | Mon 10/12/01
5595 | 2477 | Physical Layer for High Speed Downlink Packet Access | HSDPA-Phys | 2 | Rel-5 | R1 | 2001-04-05 08:00 | 2002-03-29 17:00 | 100% | RP-010262 | - | Motorola | Amitabha Ghosh (qa0047@email.mot.com) | - | - |  |  |  |  | Tue 20/03/01 | Mon 25/03/02
5596 | 2478 | Layer 2 and 3 aspects | HSDPA-L23 | 2 | Rel-5 | R2 | 2001-04-05 08:00 | 2002-03-29 17:00 | 100% | - | - | Motorola | Ravi Kuchibhotla | - | - |  |  |  |  | Tue 20/03/01 | Thu 28/02/02
5597 | 2479 | Iub/Iur protocol aspects - for High Speed Downlink Packet Access | HSDPA-IubIur | 2 | Rel-5 | R3 | 2001-04-02 08:00 | 2002-03-29 17:00 | 100% | RP-010262 | - | Motorola | Mike Diesen | - | - |  |  |  |  | Tue 20/03/01 | Fri 01/03/02
5598 | 2480 | RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing | HSDPA-RF | 2 | Rel-5 | R4 | 2001-04-09 08:00 | 2003-06-06 17:00 | 100% | RP-010262 | - | Motorola | Howard Benn | - | - |  |  |  |  | Tue 20/03/01 | Thu 27/03/03
5599 | 25000 | Conformance Testing of HSDPA | HSDPA_Test | 2 | Rel-5 | R5 | 2003-09-19 08:00 | 2006-09-22 17:00 | 100% | - | - | Motorola | carolyn.taylor@motorola.com | - | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Mon 27/09/04 | Wed 16/06/10
5600 | 25012 | Conformance Testing of HCR TDD HSDPA | HSDPA_HCRTDD_Test | 2 | Rel-5 | R5 | 2006-03-10 08:00 | 2007-03-09 17:00 | 100% | - | - | IPWireless | drichards@ipwireless.com | - | 34.108, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Tue 21/03/06 | Wed 16/06/10
5601 | 501216 | Rel-5 Improvements of Radio Interface | - | 1 | Rel-5 | RP | 2000-08-14 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Thu 11/10/01
5602 | 1471 | Base station classification for TDD | RInImp-BSClass | 2 | Rel-5 | R4 | 2000-08-14 08:00 | 2002-06-14 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | - |  |  |  |  | Wed 26/04/00 | Wed 03/10/01
5603 | 1477 | TDD Base station classification | RInImp-BSClass-TDD | 3 | Rel-5 | R4 | 2000-08-14 08:00 | 2002-03-08 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | - |  |  |  |  | Wed 26/07/00 | Fri 21/06/02
5604 | 24002 | Base Station Classification for 1.28 Mcps TDD option | RInImp-BSClass-LCRTDD | 3 | Rel-5 | R4 | 2001-06-15 08:00 | 2002-06-14 17:00 | 100% | - | - | Siemens | Meik.Kottkamp@siemens.com | - | - |  |  |  |  | Thu 05/07/01 | Fri 21/06/02
5605 | 2469 | Enhancement on the DSCH hard split mode | RInImp-DSCHhsp | 2 | Rel-5 | R1 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Samsung | Jaeyoel KIM | - | - |  |  |  |  | Tue 20/03/01 | Mon 25/03/02
5606 | 1217 | Hybrid ARQ II/III | RInImp-HARQ | 2 | Rel-5 | R2 | 2000-08-21 08:00 | 2001-12-28 17:00 | 100% | - | - | Siemens | armin.sitte@siemens.com | Stopped at RP#14; work on this task was performed as part of High Speed Downlink Packet Access feature | - |  |  | RP-14 |  | Wed 26/04/00 | Thu 24/01/02
5607 | 1221 | FS on USTS | RInImp-USTS | 2 | Rel-5 | R1 | 2000-08-14 08:00 | 2001-12-21 17:00 | 100% | - | - | SK Telecom | D. Kim | - | - |  |  |  |  | Wed 26/04/00 | Thu 28/02/02
5608 | 1997 | FS on UE antenna efficiency test method performance requirements | RInImp-UEAnTM | 2 | Rel-5 | R4 | 2000-09-25 08:00 | 2001-09-14 17:00 | 100% | - | - | Allgon | O. Edvardsson | - | - |  |  |  |  | Tue 26/09/00 | Wed 03/10/01
5609 | 2494 | FS on the re-introduction of the downlink SIR measurement | RInImp-SIR | 2 | Rel-5 | R4 | 2001-03-12 08:00 | 2001-12-14 17:00 | 100% | - | - | Ericsson | Torgny.Palenius@ericsson.com | - | - |  |  |  |  | Tue 27/03/01 | Thu 29/11/01
5610 | 2493 | FS on mitigating the effect of CPICH interference at the UE | RInImp-CPICH_Intf | 2 | Rel-5 | R4 | 2001-03-19 08:00 | 2002-03-08 17:00 | 100% | - | - | Intel | shimon.moshavi@INTEL.COM | - | - |  |  |  |  | Tue 27/03/01 | Fri 01/03/02
5611 | 1839 | Deleted - Conformance Test Spec. improvements in Radio Interface | - | 2 | Rel-5 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 14/09/00 | Thu 11/10/01
5612 | 2210 | Deleted - Testing improvement of inter-frequency and inter-system measurement | - | 3 | Rel-5 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Thu 28/02/02
5613 | 2211 | Deleted - Testing Hybrid ARQ II/III | - | 3 | Rel-5 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Thu 28/02/02
5614 | 500009 | Rel-5 RAN improvements | - | 1 | Rel-5 | RP | 2001-03-16 08:00 | 2007-03-09 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Fri 21/06/02
5615 | 656 | RRM optimization for Iur and Iub | RANimp-RRMopt | 2 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-06-04 17:00 | 100% | - | - | Ericsson | Gert-Jan.van.Lieshout@eln.ericsson.se | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
5616 | 23000 | Iur common transport channel efficiency optimization | RANimp-RRMopt-ctc | 3 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Ericsson | Shahrokh Amirijoo | - | - |  |  |  |  | Wed 19/09/01 | Thu 21/03/02
5617 | 23001 | Iur neighbouring cell reporting efficiency optimization | RANimp-RRMopt-ncr | 3 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Ericsson | Shahrokh Amirijoo | - | - |  |  |  |  | Wed 19/09/01 | Fri 01/03/02
5618 | 23002 | FS Introduction of direct transport bearers between SRNC and Node-B | RAN-imp-RRMopt-DTB | 3 | Rel-5 | R3 | 2001-06-15 08:00 | 2002-06-04 17:00 | 100% | - | - | Ericsson | Risto Sepponen | FS was closed and introduction of WI not agreed at RAN #16 | - |  |  |  |  | Wed 19/09/01 | Fri 08/11/02
5619 | 2488 | RL Timing Adjustment | RANimp-RLTA | 2 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Ericsson | Elena Voltolina | - | - |  |  |  |  | Tue 20/03/01 | Fri 01/03/02
5620 | 2489 | Separation of resource reservation and radio link activation | RANimp-SepRR | 2 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Ericsson | Gert-Jan.van.Lieshout@eln.ericsson.se | - | - |  |  |  |  | Tue 20/03/01 | Fri 01/03/02
5621 | 23003 | FS SRNS Relocation Procedure Enhancement | RANimp-SRNS | 2 | Rel-5 | R3 | 2001-06-15 08:00 | 2002-09-03 17:00 | 100% | - | - | Nokia | Olivier Guyot | - | - |  |  |  |  | Wed 19/09/01 | Fri 08/11/02
5622 | 2490 | FS Improvement of Radio Resource Management across RNS and RNS/PSS | RANimp-ImpRRM | 2 | Rel-5 | R3 | 2001-03-16 08:00 | 2001-12-21 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | FS was closed and WI was introduced at RAN #14 | - |  |  |  |  | Tue 20/03/01 | Fri 08/11/02
5623 | 2491 | Re-arrangements of Iub transport bearers | RANimp-TTPS | 2 | Rel-5 | R3 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | - |  |  |  |  | Tue 20/03/01 | Fri 01/03/02
5624 | 22000 | RAB support enhancement for Rel-5 | RANimp-RABSE5 | 2 | Rel-5 | R2 | 2001-04-02 08:00 | 2002-06-28 17:00 | 100% | - | - | Nokia | Juha Mikola | RFC 3095 context relocation | - |  |  |  |  | Thu 30/05/02 | Fri 21/06/02
5625 | 25005 | Testing of ROHC performance | RANimp-RABSE5_Test | 2 | Rel-5 | R5 | 2005-09-09 08:00 | 2007-03-09 17:00 | 100% | - | - | Nokia | jarkko.hellsten@nokia.com | - | 34.108, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Thu 28/02/02 | Wed 16/06/10
5626 | 21001 | Beamforming requirements for UE | RANimp-BFR-UE | 2 | Rel-5 | R1 | 2001-09-21 08:00 | 2001-12-14 17:00 | 100% | - | - | Nokia | Jussi Kähtävä (juha.mikola@nokia.com) | - | - |  |  |  |  | Thu 28/02/02 | Thu 28/02/02
5627 | 21002 | Support of Site Selection Diversity Transmission in UTRAN | RANimp-SSDT | 2 | Rel-5 | R1 | 2001-12-14 08:00 | 2002-06-04 17:00 | 100% | - | - | NEC | - | RP-020356 | - |  |  |  |  | Thu 28/02/02 | Fri 21/06/02
5628 | 2472 | Node B Synchronisation for 1.28 Mcps TDD | RANimp-NBSLCR | 2 | Rel-5 | R1 | 2001-03-16 08:00 | 2002-03-29 17:00 | 100% | - | - | CATT | Jinling HU | - | - |  |  |  |  | Tue 20/03/01 | Mon 25/03/02
5629 | 2102 | Deleted - Conformance Test Aspects - RAN Improvements | - | 2 | Rel-5 | T1 | 2002-01-01 08:00 | 2004-03-01 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-23 |  | Wed 01/11/00 | Sat 01/04/00
5630 | 2222 | Deleted - Testing Radio access bearer support enhancements | - | 3 | Rel-5 | T1 | 2002-01-01 08:00 | 2002-09-02 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Mon 10/12/01
5631 | 41010 | Deleted - General changes to TS34.121 and TS34.122 corresponding to release 5 | RANimp-test,TEI5 | 3 | Rel-5 | T1 | 2003-03-03 08:00 | 2004-03-01 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.108, 34.121, 34.122 |  |  | TP-23 |  | Fri 14/03/03 | Fri 14/03/03
5632 | 23004 | UTRAN Sharing in Connected Mode | NETSHARE | 1 | Rel-5 | R3 | 2001-12-03 08:00 | 2002-09-03 17:00 | 100% | - | - | Ericsson | Martin Israelsson | Formerly 'Shared Network support in connected mode', renamed at RAN #16. | - |  |  |  |  | Thu 21/03/02 | Fri 08/11/02
5633 | 1273 | Provisioning of IP-based multimedia services | IMS | 1 | Rel-5 | S1,S2,S3,S5,NP,T3,T1,R5 | 2000-01-03 08:00 | 2006-12-01 17:00 | 100% | SP-000216 | - | Openwave | Mark Cataldo | - | - |  |  |  |  | Sun 09/04/00 | Thu 28/02/02
5634 | 1274 | Call control and roaming to support IMS in UMTS | IMS-CCR | 2 | Rel-5 | S2,R5 | 2000-01-03 08:00 | 2006-12-01 17:00 | 100% | SP-010339 | - | Lucent | Liz Daniel | - | - |  |  |  |  | Sun 09/04/00 | Thu 24/01/02
5635 | 1633 | Stage 1 for Call control and roaming to support IMS in UMTS | - | 3 | Rel-5 | S1 | 2000-02-21 08:00 | 2000-12-15 17:00 | 100% | - | - | Motorola | Mark Cataldo | Issues include e.g.: Roaming requirements, Requirements on supplementary services, Interworking requirements | 22.228 |  |  |  |  | Tue 08/08/00 | Fri 30/03/01
5636 | 1514 | Stage 2 (Architecture and Main flows) | - | 3 | Rel-5 | S2 | 2000-04-14 08:00 | 2001-03-23 17:00 | 100% | SP-000289 | - | Lucent | Liz Daniel | Issues include e.g.: Mobile IP, RAB selection principles, Optimized VoIP bearer mechanisms, SIP multimedia protocol | 23.228 |  |  |  |  | Fri 28/07/00 | Thu 08/02/01
5637 | 1296 | Impact on MM/CC/SM | IMS-CCR-IWMM | 3 | Rel-5 | N1 | 2000-08-28 08:00 | 2002-03-08 17:00 | 100% | NP-010434 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | Per 26/2-02: This is understood to be the PCO & TFT CRs which CN1 provides to TSGN #15 for approval. If this is correct understanding, then the task is 100 % complete. | - |  |  |  |  | Wed 19/04/00 | Mon 25/03/02
5638 | 2233 | SIP Call Control protocol for the IMS | - | 3 | Rel-5 | N1 | 2000-10-02 08:00 | 2002-03-22 17:00 | 100% | NP-010643 | - | Lucent | Keith Drage (drage@alcatel-lucent.com) | TSGN_10 approved the change:CN1 - SA2 SIP joint meeting spotted one more place for improvement: work tasks with ID 1998 and 1278 are actually subtasks under of single CN1 WT. One WI has been approved for the CN1 WT with title "SIP Call Control protocol | 24.228, 24.229, 23.218 |  |  |  |  | Mon 11/12/00 | Thu 24/01/02
5639 | 1998 | IMS signalling flows | - | 4 | Rel-5 | N1 | 2000-10-02 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | 24.228 | 24.228 |  |  |  |  | Fri 25/08/00 | Fri 14/03/03
5640 | 1278 | IMS stage 3 | - | 4 | Rel-5 | N1 | 2000-10-02 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | 24.229 | 24.229 |  |  |  |  | Wed 19/04/00 | Fri 14/03/03
5641 | 2255 | IMS Session Handling; stage 2 | - | 4 | Rel-5 | N1 | 2000-10-02 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | 23.218 | 23.218 |  |  |  |  | Thu 08/02/01 | Thu 28/02/02
5642 | 25006 | Conformance Test Aspects – IMS Call Control | IMS-CCR_Test | 3 | Rel-5 | R5 | 2005-03-11 08:00 | 2006-12-01 17:00 | 100% | - | - | Motorola | Jacob.John@motorola.com | - | 34.108, 34.229-1, 34.229-2, 34.229-3 |  |  |  |  | Thu 28/02/02 | Wed 16/06/10
5643 | 10004 | Main IETF dependencies | - | 3 | Rel-5 | NP | 2000-01-03 08:00 | 2002-06-14 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Fri 25/01/02 | Fri 28/03/03
5644 | 2521 | IETF: RFC 3261 (Session Initiation Protocol) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-03-22 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Sun 06/05/01 | Fri 14/03/03
5645 | 2523 | IETF: RFC 3262 (Reliability of provisional responses) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-03-22 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 25/03/02 | Fri 14/03/03
5646 | 2522 | IETF: RFC 3312 (Without COMET)(Integration of resource management and SIP) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Sun 06/05/01 | Fri 14/03/03
5647 | 2524 | IETF: RFC 3323 (SIP extensions for caller identity and privacy) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Sun 06/05/01 | Fri 14/03/03
5648 | 2525 | IETF: RFC 3313 (SIP extensions for media authorization) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Sun 06/05/01 | Fri 14/03/03
5649 | 11000 | IETF: RFC 3265 (specific event notification) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-03-22 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
5650 | 11001 | IETF: RFC editor Queue (refer method) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-06-07 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
5651 | 11002 | IETF: RFC editor Queue (DHCP options for SIP servers) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
5652 | 11004 | IETF: RFC 3267 (AMR and AMR WB RTP and SDP) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-03-22 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
5653 | 11005 | IETF: RFC 3266 (IPv6 support within SDP) | - | 4 | Rel-5 | N1 | 2000-01-03 08:00 | 2002-03-22 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
5654 | 11022 | IETF: RFC 3311 (The Update method) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Fri 21/06/02 | Fri 14/03/03
5655 | 11023 | IETF: RFC 3324 (Network Asserted Identity) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Fri 21/06/02 | Fri 14/03/03
5656 | 11024 | IETF: RFC editor Queue (Various 3GPP Private Extensions) | - | 4 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | Lucent | - | - | - |  |  |  |  | Fri 21/06/02 | Fri 14/03/03
5657 | 1290 | Addressing | - | 4 | Rel-5 | S2 | 2000-10-09 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Sat 01/04/00
5658 | 1291 | Architectural issues | - | 5 | Rel-5 | S2 | 2000-10-09 08:00 | 2001-08-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Thu 08/02/01
5659 | 1292 | Impact on HSS | - | 5 | Rel-5 | N4 | 2000-11-15 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | Covered by 29.228 & 29228 | - |  |  |  |  | Wed 19/04/00 | Thu 30/05/02
5660 | 2530 | Service Examples (Work stopped) | IMS-Sex | 4 | Rel-5 | S1 | 2001-04-17 08:00 | 2002-06-14 17:00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.928 |  |  |  |  | Mon 28/05/01 | Fri 25/07/03
5661 | 2531 | IMS Framework Report (work stopped) | IMS-FrWk | 5 | Rel-5 | S1 | 2001-04-17 08:00 | 2002-06-14 17:00 | 100% | - | - | SBC | Randolph Wohlert (rwohlert@tri.sbc.com) | - | 22.941 |  |  |  |  | Mon 28/05/01 | Fri 25/07/03
5662 | 1298 | Access Security for IMS | IMS-ASEC | 2 | Rel-5 | S3,T3 | 2001-10-08 08:00 | 2002-06-28 17:00 | 100% | SP-010323 | - | Ericsson | krister.boman@emw.ericsson.se | - | - |  |  |  |  | Tue 18/04/00 | Mon 08/08/11
5663 | 43000 | IMS impacts on UICC (ISIM application) | - | 3 | Rel-5 | T3 | 2001-10-08 08:00 | 2002-06-21 17:00 | 100% | TP-010251 | - | Vodafone | Jeremy Norris | - | 33.102, New TS 31.103 |  |  |  |  | Mon 08/10/01 | Thu 26/09/02
5664 | 11014 | Deleted - SIP extensions for Integrity protection | - | 3 | Rel-5 | N1 | 2001-12-17 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | CN1 is not aware of any requirements and is not doing anything on this task | - |  |  | SP-69 |  | Fri 05/10/01 | Fri 21/06/02
5665 | 2574 | Security Aspects of Requirement for Network Configuration Independence | SEC1-NCI | 2 | Rel-5 | S3 | 2001-07-02 08:00 | 2001-12-28 17:00 | 100% | SP-010324 | - | AT&T Wireless | hugh.shieh@attws.com | Consider security aspects in SA2 TS 23.228 clause 4.4 & annex C | 33.203 |  |  |  |  | Sat 09/06/01 | Mon 08/08/11
5666 | 1299 | IMS Lawful Interception | IMS-LI | 2 | Rel-5 | S3 | 2000-09-04 08:00 | 2002-03-29 17:00 | 100% | SP-010621 | - | Reg TP | berthold.wilhelm@regtp.de | SP#17 completed | 33.106, 33.107, New 33.108 |  |  |  |  | Sun 09/04/00 | Mon 08/08/11
5667 | 35007 | Charging and OAM&P for IMS | IMS-OAM | 2 | Rel-5 | S5 | 2000-12-25 08:00 | 2002-06-12 17:00 | 100% | SP-010461 | - | - | - | - | 32-series |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
5668 | 2036 | Multimedia codecs and protocols for conversational PS services | IMS-CODEC | 2 | Rel-5 | S4 | 2000-07-26 08:00 | 2002-09-27 17:00 | 100% | SP-000398 | - | Toshiba, Nokia | B. Aronson (Toshiba), pasi.s.ojala@nokia.com | - | 26.235, 26.236 |  |  |  |  | Wed 27/09/00 | Thu 27/03/03
5669 | 2039 | Codecs | - | 3 | Rel-5 | S4 | 2000-07-26 08:00 | 2002-03-14 17:00 | 100% | SP-000398 | - | - | - | - | 26.235, 26.236 |  |  |  |  | Thu 28/09/00 | Mon 25/03/02
5670 | 34020 | Transport protocols | - | 3 | Rel-5 | S4 | 2002-03-12 08:00 | 2002-03-12 17:00 | 100% | - | - | Nokia | P. Ojala | - | 26.236 |  |  |  |  | Mon 25/03/02 | Mon 25/03/02
5671 | 34006 | recommendation for QoS parameter values for various media types | - | 3 | Rel-5 | S4 | 2001-12-31 08:00 | 2002-09-27 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 28/09/00 | Mon 13/01/03
5672 | 11025 | IETF: RFC 3310 (HTTP Digest Authentication using AKA) | - | 3 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 21/06/02 | Fri 14/03/03
5673 | 11026 | IETF: RFC 3329 (Security mechanism agreement for SIP connections) | - | 3 | Rel-5 | N1 | 2000-11-24 08:00 | 2002-05-13 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 21/06/02 | Fri 14/03/03
5674 | 32003 | SIP message compression | - | 2 | Rel-5 | S2 | 2001-09-24 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Mon 25/03/02
5675 | 32004 | Stage 2 for SIP message compression | - | 3 | Rel-5 | S2 | 2001-09-24 08:00 | 2001-10-26 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Sat 24/11/01
5676 | 11015 | Compression signalling | - | 3 | Rel-5 | N1 | 2001-09-28 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
5677 | 10001 | Stage 3 description of IMS interfaces | - | 2 | Rel-5 | NP | 2001-03-14 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Thu 24/01/02
5678 | 1286 | Cx interface (HSS to CSCF) | - | 3 | Rel-5 | N4 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | NP-010626 | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Thu 30/05/02
5679 | 14997 | Mp interface (MRFC - MRFP) enhancements | - | 3 | Rel-5 | N4 | 2001-03-14 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | [DAB 08-03-02] - No work required in CN4 | - |  |  |  |  | Mon 08/10/01 | Thu 30/05/02
5680 | 11016 | Mw interface (CSCF to P-CSCF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Fri 14/03/03
5681 | 11018 | Mr interface (CSCF to MRF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-03-29 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Thu 28/02/02
5682 | 14003 | Dx interface (I-CSCF to SLF) | - | 3 | Rel-5 | N4 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | CN4#11 30/11/01: No inputs received in CN4 | - |  |  |  |  | Mon 08/10/01 | Thu 30/05/02
5683 | 13001 | Go interface (GGSN to PCF) | - | 3 | Rel-5 | N3 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | [DAB - 23/05/03] - 100 % complete | - |  |  |  |  | Mon 08/10/01 | Fri 25/07/03
5684 | 11019 | ISC (IMS Service Control) Interface | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Thu 30/05/02
5685 | 14006 | Sh interface (HSS to AS) | - | 3 | Rel-5 | N4 | 2002-02-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | CN4#11 30/11/01: No inputs received in CN4 | - |  |  |  |  | Thu 11/10/01 | Thu 30/05/02
5686 | 14998 | Si interface (HSS to IM-SSF) | - | 3 | Rel-5 | N4 | 2002-01-16 13:00 | 2002-08-30 17:00 | 100% | - | - | - | - | SA16: Part of Rel5 only if completed in September 02. Marked as closed 12/2008 (was marked 72% complete) | - |  |  |  |  | Mon 25/03/02 | Thu 30/05/02
5687 | 11020 | Gm interface (UE to CSCF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 11/10/01 | Fri 14/03/03
5688 | 11027 | Mi interface (CSCF to BGCF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 11/10/01 | Fri 14/03/03
5689 | 11028 | Mj interface (BGCF to MGCF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 11/10/01 | Fri 14/03/03
5690 | 11029 | Mk interface (BGCF to BGCF) | - | 3 | Rel-5 | N1 | 2001-03-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 11/10/01 | Fri 14/03/03
5691 | 1310 | Support of VHE/OSA by entities and protocols of the IMS (e.g. CSCF) | IMS-ONOSA | 2 | Rel-5 | N5 | 2001-09-21 08:00 | 2002-06-07 17:00 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998 |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
5692 | 12000 | CAMEL control of IMS services | IMS-CAMEL | 2 | Rel-5 | N2 | 2001-04-16 08:00 | 2002-09-06 17:00 | 100% | NP-020305 | - | Lucent | Angelica Remoquillo | - | - |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
5693 | 12001 | Stage2 work 'general' | - | 3 | Rel-5 | N2 | 2001-04-16 08:00 | 2002-09-06 17:00 | 100% | - | - | - | - | DAB 12.12.01 split into cn4 and cn2 parts | - |  |  |  |  | Mon 08/10/01 | Mon 13/01/03
5694 | 12002 | Stage3 work 'CAP' | - | 3 | Rel-5 | N2 | 2002-01-07 08:00 | 2002-09-06 17:00 | 100% | - | - | - | - | DAB 12.12.01 split into cn4 and cn2 parts | - |  |  |  |  | Thu 24/01/02 | Mon 13/01/03
5695 | 12003 | Stage2 work 'Si interface' | - | 3 | Rel-5 | N2 | 2002-01-07 08:00 | 2002-09-06 17:00 | 100% | - | - | - | - | DAB 12.12.01 split into cn4 and cn2 parts | - |  |  |  |  | Thu 24/01/02 | Mon 13/01/03
5696 | 12004 | Stage3 work 'Si interface' | - | 3 | Rel-5 | N4 | 2002-02-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | [DAB 08-03-02] - UID 12004 is MASTER of UID 14998 | - |  |  |  |  | Thu 24/01/02 | Thu 30/05/02
5697 | 14004 | Deleted - SDM issues for CAMEL control of IMS | - | 3 | Rel-5 | N4 | 2002-02-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | NP-17 |  | Mon 08/10/01 | Fri 12/12/08
5698 | 31002 | Pre-pay/real-time charging in IMS | - | 2 | Rel-5 | S1 | 2001-06-15 08:00 | 2002-03-15 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | - |  |  |  |  | Wed 11/07/01 | Thu 28/02/02
5699 | 35005 | IMS Charging | OAM-CH | 2 | Rel-5 | S2,S5 | 2001-08-06 08:00 | 2002-09-12 17:00 | 100% | SP-010631 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | - | 32.225 |  |  |  |  | Mon 08/10/01 | Mon 13/01/03
5700 | 32006 | Charging Implications of IMS architecture | - | 3 | Rel-5 | S2 | 2001-08-06 08:00 | 2001-11-16 17:00 | 100% | SP-010519 | - | - | - | - | - |  |  |  |  | Mon 08/10/01 | Thu 28/02/02
5701 | 35006 | Charging management for IMS (off-line & on-line) | - | 3 | Rel-5 | S5 | 2001-11-19 08:00 | 2002-09-12 17:00 | 100% | - | - | - | - | - | 32.225 |  |  |  |  | Mon 08/10/01 | Fri 08/11/02
5702 | 34012 | Billing, accounting and call detail record aspects | - | 3 | Rel-5 | S5 | 2001-09-27 08:00 | 2002-09-12 17:00 | 100% | SP-010631 | - | T-Mobile | Karl-Heinz.Nenner@T-MOBILE.DE | - | 32.225 |  |  |  |  | Tue 09/10/01 | Fri 08/11/02
5703 | 10002 | Other IETF dependencies | - | 2 | Rel-5 | NP | 2000-11-24 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Was introduced at SP#13 by Ileana Leuca (exact position in the WP and related WG have to be defined) | - |  |  |  |  | Thu 11/10/01 | Mon 25/03/02
5704 | 11011 | IETF: draft-ietf-aaa-diameter - should be CN4 | - | 3 | Rel-5 | NP | 2000-11-24 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 90% complete) | - |  |  |  |  | Mon 08/10/01 | Fri 12/12/08
5705 | 11999 | IETF: draft-johansson-aaa-diameter-mm-app - should be CN4 | - | 3 | Rel-5 | NP | 2000-11-24 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | - |  |  |  |  | Mon 08/10/01 | Fri 12/12/08
5706 | 1844 | Conformance Test Aspects - Provisioning of IMS | IMS-TEST | 2 | Rel-5 | T1 | 2002-03-18 08:00 | 2002-12-27 17:00 | 100% | - | - | - | - | The task is a BB, individual work items were considered but are constrained by lack of supporting companies. Marked as stopped 12/2008 | - |  |  |  |  | Thu 14/09/00 | Fri 12/12/08
5707 | 41004 | Testing of support for IMS - prose | - | 2 | Rel-5 | T1 | 2002-09-18 08:00 | 2003-09-30 17:00 | 100% | TP-030052 | - | Anritsu | dan.fox@eu.anritsu.com | Marked as stopped 12/2008 | 34.108, 34.123 |  |  |  |  | Thu 26/09/02 | Fri 12/12/08
5708 | 41005 | Testing of support for IMS - TTCN | - | 2 | Rel-5 | T1 | 2002-09-18 08:00 | 2004-03-03 17:00 | 100% | TP-030052 | - | Anritsu | dan.fox@eu.anritsu.com | Marked as stopped 12/2008 | 34.108, 34.123 |  |  |  |  | Thu 26/09/02 | Fri 12/12/08
5709 | 740068 | UE Conformance Test Aspects – IMS for Converged IP Communications | IMS_CONV_IP_COM-UEConTest | 1 | Rel-5 | R5 | 2016-12-14 08:00 | 2017-12-15 17:00 | 100% | RP-171635 |  | Rohnert, Hans | Hans.Rohnert.ext@rohde-schwarz.com | UID: 740999->740068; Rel-14->Rel-519/9/17: Compl:0%->75%; 8/1/18: Compl:75%->100% | TS 34.229-1, TS 34.229-2, TS 34.229-3 | 74 | 38 |  |  | Wed 01/02/17 | Mon 08/01/18
5710 | 34001 | Extended Transparent End-to-End PS Streaming Service | PSS-E | 1 | Rel-5 | S4 | 2002-01-03 08:00 | 2003-03-17 17:00 | 100% | SP-010392 | - | Ericsson | olle.franceschi@ericsson.com | - | 26.233, 26.234 |  |  |  |  | Thu 28/06/01 | Thu 28/02/02
5711 | 34002 | Stage 1 for Extended Transparent End-to-End PS Streaming Service | - | 2 | Rel-5 | S1 | 2002-11-18 08:00 | 2003-03-17 17:00 | 100% | SP-010392 | - | Vodafone | stephen.wolak@vodafone.com | 2nd resp SA4 | 22.233 |  |  |  |  | Thu 28/06/01 | Mon 25/03/02
5712 | 31032 | Interaction with other services | - | 3 | Rel-5 | S1 | 2002-11-18 08:00 | 2003-03-17 17:00 | 100% | - | - | Vodafone | stephen.wolak@vodafone.com | 2nd resp SA4. Marked as closed 12/2008 (was marked 65% complete) | 22.233 |  |  |  |  | Mon 13/01/03 | Fri 12/12/08
5713 | 34003 | Stage 2 (version Rel-5 of TS 26.234) | - | 2 | Rel-5 | S4 | 2002-01-03 08:00 | 2002-03-14 17:00 | 100% | SP-010392 | - | - | - | 2nd resp SA2 | 26.234 |  |  |  |  | Thu 28/06/01 | Mon 25/03/02
5714 | 34019 | RTP usage model | - | 2 | Rel-5 | S4 | 2002-01-03 08:00 | 2002-12-06 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 90% complete) | 26.937 |  |  |  |  | Mon 25/03/02 | Fri 12/12/08
5715 | 501637 | Rel-5 Open Service Access (OSA) enhancements | OSA1 | 1 | Rel-5 | S1,S3 | 1999-04-27 08:00 | 2002-12-20 17:00 | 100% | SP-000216 | - | Siemens | joerg.swetina@neclab.eu | - | 22.127, 23.127, 29.198-x, 29.998-x |  |  |  |  | Tue 08/08/00 | Fri 25/07/03
5716 | 32010 | General Stage 2 for Rel-5 | - | 2 | Rel-5 | S2 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 47% complete) | - |  |  |  |  | Tue 21/11/00 | Fri 12/12/08
5717 | 1429 | OSA APIs for Multimedia Call Control | OSA1-CSCF | 2 | Rel-5 | S2 | 2000-07-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | For Rel5 even if completed by March | - |  |  |  |  | Wed 19/04/00 | Thu 24/01/02
5718 | 1430 | Stage 1 for OSA APIs for Multimedia Call Control | - | 3 | Rel-5 | S1 | 2000-07-11 08:00 | 2002-03-14 17:00 | 100% | - | - | Siemens | Manfred.leitgeb@siemens.at | - | 22.127 |  |  |  |  | Wed 19/04/00 | Thu 30/05/02
5719 | 15002 | Stages 2 and 3 for Multimedia Call Control | - | 3 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198-04 |  |  |  |  | Thu 28/02/02 | Fri 21/06/02
5720 | 15003 | Generic user interaction - Stage 3 | - | 2 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198-05 |  |  |  |  | Thu 28/02/02 | Fri 21/06/02
5721 | 15004 | OSA Charging - Stage 3 | - | 2 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198-12 |  |  |  |  | Thu 28/02/02 | Fri 21/06/02
5722 | 15007 | Call Control Service Mapping; Multiparty Call Control SIP - Stage 3 | - | 2 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.998-04-4 |  |  |  |  | Thu 28/02/02 | Fri 21/06/02
5723 | 15999 | WSDL APIs for SOAP/HTTP - Stage 3 | - | 2 | Rel-5 | N5 | 2000-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198, 29.998 |  |  |  |  | Mon 25/03/02 | Fri 21/06/02
5724 | 1419 | OSA Security | OSA1-SEC | 2 | Rel-5 | S3 | 2000-07-11 08:00 | 2002-12-20 17:00 | 100% | SP-000302 | - | Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102 |  |  |  |  | Wed 19/04/00 | Mon 08/08/11
5725 | 2121 | Stage 1 for OSA Security | - | 3 | Rel-5 | S1 | 2000-07-11 08:00 | 2001-11-09 17:00 | 100% | - | - | Siemens | Manfred.leitgeb@siemens.at | - | 22.127 |  |  |  |  | Wed 22/11/00 | Thu 28/02/02
5726 | 1421 | OSA Stage 3 | - | 3 | Rel-5 | S3 | 2000-10-23 08:00 | 2002-06-14 17:00 | 100% | SP-000302 | - | BT, Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102 |  |  |  |  | Wed 19/04/00 | Sun 07/08/11
5727 | 1422 | security related SCF(s) definition | - | 3 | Rel-5 | N5 | 2001-09-21 08:00 | 2002-06-07 17:00 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998 |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
5728 | 1423 | OSA changes required from supporting platforms, e.g. gsmSCF, HLR | - | 3 | Rel-5 | S3 | 2000-09-11 08:00 | 2000-12-14 17:00 | 100% | SP-000302 | - | BT, Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102 |  |  |  |  | Wed 19/04/00 | Mon 08/08/11
5729 | 15017 | OSA Security (moved from Rel-6) | - | 3 | Rel-5 | S3 | 2002-03-14 08:00 | 2002-12-20 17:00 | 100% | SP-000302 | - | BT, Ericsson | colin.blanchard@bt.com | SP#8 approved WID | 33.102 |  |  |  |  | Wed 20/03/02 | Mon 08/08/11
5730 | 401424 | Interactions OSA - e-commerce | OSA1-ECOM | 2 | Rel-5 | S2 | 1999-04-27 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
5731 | 1425 | Stage 1 for Interactions OSA - e-commerce | - | 3 | Rel-5 | S1 | 1999-04-27 08:00 | 2000-12-28 17:00 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | Marked as closed 12/2008 (was marked 95% complete) | 22.127 |  |  |  |  | Wed 19/04/00 | Fri 12/12/08
5732 | 1529 | Stages 2 and 3 for Interactions OSA - e-commerce | - | 3 | Rel-5 | N5 | 2001-09-21 08:00 | 2002-06-07 17:00 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998 |  |  |  |  | Fri 28/07/00 | Fri 21/06/02
5733 | 15005 | Policy Management - Stage 3 | - | 2 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198-13 |  |  |  |  | Thu 28/02/02 | Thu 26/09/02
5734 | 15006 | Presence and Availability Management (PAM) - Stage 3 | - | 2 | Rel-5 | N5 | 2001-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | 29.198-14 |  |  |  |  | Thu 28/02/02 | Thu 26/09/02
5735 | 1786 | LCS - OSA interfaces | OSA1-LCSI | 2 | Rel-5 | S1 | 2000-09-11 08:00 | 2002-06-07 17:00 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | az: CN#13 - changed to Rel5 | - |  |  |  |  | Wed 19/04/00 | Mon 08/10/01
5736 | 1787 | Stage 1 for LCS - OSA interfaces | - | 3 | Rel-5 | S1 | 2000-09-11 08:00 | 2000-12-08 17:00 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | - | 22.127 |  |  |  |  | Wed 19/04/00 | Thu 30/05/02
5737 | 2124 | Stage 2 for LCS - OSA interfaces | - | 3 | Rel-5 | S2 | 2000-12-11 08:00 | 2000-12-11 17:00 | 100% | - | - | Ericsson | Christophe GOURRAUD | az 24/05/01: Rel4 completion 90->100%. | 23.127 |  |  |  |  | Wed 22/11/00 | Wed 06/06/01
5738 | 1788 | Stage 3 for LCS - OSA interfaces | - | 3 | Rel-5 | N5 | 2001-09-21 08:00 | 2002-06-07 17:00 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998 |  |  |  |  | Wed 19/04/00 | Fri 21/06/02
5739 | 2540 | Access to User Profile | OSA2-UP | 2 | Rel-5 | S1 | 2001-06-01 08:00 | 2001-12-20 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 28/05/01 | Fri 25/07/03
5740 | 1433 | Retrieval of Terminal capabilities | OSA2-TC | 2 | Rel-5 | S2 | 2000-07-11 08:00 | 2002-12-13 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Fri 25/07/03
5741 | 1434 | Stage 1 for Retrieval of Terminal capabilities | - | 3 | Rel-5 | S1 | 2000-07-11 08:00 | 2001-01-10 17:00 | 100% | - | - | Siemens | joerg.swetina@neclab.eu | - | 22.127 |  |  |  |  | Wed 19/04/00 | Fri 25/07/03
5742 | 1436 | Stages 2 and 3 for Retrieval of Terminal capabilities | - | 3 | Rel-5 | N5 | 2001-09-21 08:00 | 2002-12-13 17:00 | 100% | NP-010692 | - | Ericsson | Ard.Jan.Moerdijk@eln.ericsson.se | - | 29.198, 29.998 |  |  |  |  | Wed 19/04/00 | Fri 25/07/03
5743 | 2122 | Provisioning of the terminal capabilities | - | 3 | Rel-5 | T2 | 2001-04-02 08:00 | 2002-12-13 17:00 | 100% | - | - | - | - | According to T2 SWG1 M. Cataldo this is automatically supported by the MExE support of UAProf therefore 100% complete | 23.057 |  |  |  |  | Wed 22/11/00 | Fri 25/07/03
5744 | 1638 | CAMEL phase 4 | CAMEL4 | 1 | Rel-5 | S1 | 2000-04-17 08:00 | 2002-09-06 17:00 | 100% | NP-020486 | - | Nokia | keijo.palviainen@nokia.com | - | - |  |  |  |  | Tue 08/08/00 | Thu 28/02/02
5745 | 1461 | Service requirements | - | 2 | Rel-5 | S1 | 2000-04-17 08:00 | 2002-06-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Thu 28/02/02
5746 | 2012 | Call Party Handling | CAMEL4-CPH | 2 | Rel-5 | N2 | 2000-07-10 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 15/09/00 | Thu 30/05/02
5747 | 2013 | Mid call procedure for MO and MT calls | CAMEL4-MCP | 2 | Rel-5 | N2 | 2000-07-17 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Thu 30/05/02
5748 | 2014 | Interactions with Optimal Routing | CAMEL4-IOR | 2 | Rel-5 | N2 | 2000-07-17 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Thu 28/02/02
5749 | 2015 | Inclusion of flexible tone injection | CAMEL4-IFTI | 2 | Rel-5 | N2 | 2000-07-17 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Thu 28/02/02
5750 | 2016 | CSE control over MT SMS | CAMEL4-CCSMS | 2 | Rel-5 | N2 | 2000-07-17 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Thu 28/02/02
5751 | 2460 | Notification of GPRS mobility management to CSE | CAMEL4-NMM | 2 | Rel-5 | N2 | 2001-03-02 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 13/03/01 | Thu 30/05/02
5752 | 2458 | Provision of location information of called subscriber | CAMEL4-LOCB | 2 | Rel-5 | N2 | 2001-03-02 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 13/03/01 | Thu 28/02/02
5753 | 2514 | Inclusion of ODB data in the CSE_HLR interface | CAMEL4-ODB | 2 | Rel-5 | N2 | 2001-07-09 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | Added on May 29, 2001 | - |  |  |  |  | Tue 29/05/01 | Thu 28/02/02
5754 | 2515 | Location information during an ongoing call (Handover DP) | CAMEL4-HODP | 2 | Rel-5 | N2 | 2001-05-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 29/05/01 | Thu 30/05/02
5755 | 2516 | GPRS Any Time Interrogation | CAMEL4-ATI | 2 | Rel-5 | N2 | 2001-07-09 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 29/05/01 | Thu 30/05/02
5756 | 2599 | Transfer of IMEI (with SW version) to CSE (CAMEL4-ATI) | - | 2 | Rel-5 | N2 | 2001-07-09 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 25/03/02 | Thu 30/05/02
5757 | 12005 | Handling of partial implementations of CAMEL4 | CAMEL4-SUB | 2 | Rel-5 | N2 | 2002-03-08 08:00 | 2002-09-06 17:00 | 100% | - | - | - | - | stage2 and stage3 CRs for approval at CN#17 | - |  |  |  |  | Thu 30/05/02 | Thu 26/09/02
5758 | 2464 | Rel-5 MExE enhancements | MEXE5 | 1 | Rel-5 | T2 | 2001-03-26 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Tue 13/03/01
5759 | 2466 | MExE Rel-5 Improvements and Investigations | MEXE5-ENHANC | 2 | Rel-5 | T2 | 2001-03-26 08:00 | 2002-03-08 17:00 | 100% | TP-010071 | - | Motorola | Mark Cataldo | - | 22.057, 23.057 |  |  |  |  | Thu 14/09/00 | Thu 21/03/02
5760 | 1625 | Wideband Telephony Service - AMR | AMRWB | 1 | Rel-5 | S4 | 2000-01-01 08:00 | 2003-12-19 17:00 | 100% | SP-99354 | - | Siemens | Imre.Varga@mch.siemens.de | - | - |  |  |  |  | Tue 08/08/00 | Thu 27/03/03
5761 | 62 | Specification | - | 2 | Rel-5 | S4 | 2000-01-01 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 27/03/03
5762 | 31005 | Stage 1 for Wideband Telephony Service - AMR | - | 3 | Rel-5 | S1 | 2001-10-01 08:00 | 2002-03-22 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 05/10/01 | Fri 01/03/02
5763 | 32007 | Stage 2 for Wideband Telephony Service - AMR | - | 3 | Rel-5 | S4 | 2000-01-03 08:00 | 2000-04-17 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 05/10/01 | Thu 28/02/02
5764 | 1459 | Design Constraints for Wideband Telephony Service - AMR | - | 4 | Rel-5 | S4 | 2000-01-03 08:00 | 2000-02-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 28/02/02
5765 | 1460 | General Description for Wideband Telephony Service - AMR | - | 4 | Rel-5 | S4 | 2000-02-07 08:00 | 2000-04-17 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 28/02/02
5766 | 1626 | Feasibility Study for Wideband Telephony Service - AMR | - | 3 | Rel-5 | S4 | 2000-04-28 08:00 | 2000-06-02 17:00 | 100% | SP-000024 | - | - | - | S4,TD SP-000024: TR 26.901 v.4.0.0 | 26.901 |  |  |  |  | Tue 08/08/00 | Thu 28/02/02
5767 | 1656 | N1 Aspects for Wideband Telephony Service - AMR | - | 3 | Rel-5 | N1 | 2001-09-21 08:00 | 2001-12-21 17:00 | 100% | - | - | - | - | Some of N1 tasks: Indication of supported codecs by the MS, Bearer cap negociation, codec indication to MS | - |  |  |  |  | Tue 08/08/00 | Thu 26/09/02
5768 | 14005 | N4 work for Wideband Telephony Service - AMR | - | 3 | Rel-5 | N4 | 2002-02-13 08:00 | 2002-06-07 17:00 | 100% | N4-010538 | - | - | - | CN4#11 30/11/01: No inputs to CN4 at this meeting | - |  |  |  |  | Tue 08/08/00 | Thu 30/05/02
5769 | 67 | Codec issues | - | 3 | Rel-5 | S4 | 2000-01-03 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 28/02/02
5770 | 1627 | Codec qualification | - | 4 | Rel-5 | S4 | 2000-02-02 08:00 | 2000-05-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 08/08/00 | Thu 28/02/02
5771 | 74 | Codec selection tests | - | 4 | Rel-5 | S4 | 2000-06-01 08:00 | 2000-10-20 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 28/02/02
5772 | 891 | Codec selection | - | 4 | Rel-5 | S4 | 2000-10-23 08:00 | 2000-10-27 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Thu 28/02/02
5773 | 34007 | TFO AMR-WB | AMRWB-TFO | 4 | Rel-5 | S4 | 2001-12-18 08:00 | 2002-03-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Thu 26/09/02
5774 | 890 | Other codec issues (verif., characterization) | - | 4 | Rel-5 | S4 | 2000-09-29 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | ANSI C-Code , Test Sequences, Speech Transcoding Functions, Error Concealment of lost frames, Source Controlled Bit-Rate Operation, Voice Activity Detector, Frame Structure | 26.976 |  |  |  |  | Wed 05/04/00 | Mon 13/01/03
5775 | 34008 | AMR-WB and narrrowband interworking | AMRWB-IWG | 4 | Rel-5 | S4 | 2001-09-27 08:00 | 2002-03-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Thu 28/02/02
5776 | 34009 | Interworking with fixed broadband networks | - | 4 | Rel-5 | S4 | 2001-09-27 08:00 | 2002-03-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Thu 28/02/02
5777 | 34010 | Tones and announcements | - | 4 | Rel-5 | S4 | 2001-09-27 08:00 | 2002-03-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Thu 28/02/02
5778 | 34011 | Deleted - WB Conferencing and WB Voice Group calls | - | 4 | Rel-5 | S1 | 2000-01-03 08:00 | 2000-01-03 17:00 | 100% | - | - | - | - | - | - |  |  | SP-07 |  | Tue 09/10/01 | Fri 25/07/03
5779 | 1855 | Conformance tests (CRs to 34 series) | - | 3 | Rel-5 | T1 | 2000-01-01 08:00 | 2000-04-12 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 14/09/00 | Mon 13/01/03
5780 | 76 | Terminal Acoustic Characteristics | - | 4 | Rel-5 | S4 | 2000-01-01 08:00 | 2000-04-12 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Sat 01/04/00
5781 | 1628 | Definition for Terminal Acoustic Characteristics | - | 5 | Rel-5 | S4 | 2000-01-01 08:00 | 2000-01-31 17:00 | 100% | - | - | - | - | - | 26.131 |  |  |  |  | Tue 08/08/00 | Thu 28/02/02
5782 | 1629 | Test specification for Terminal Acoustic Characteristics | - | 5 | Rel-5 | S4 | 2000-02-01 08:00 | 2000-04-12 17:00 | 100% | - | - | - | - | - | 26.132 |  |  |  |  | Tue 08/08/00 | Tue 20/03/01
5783 | 34004 | Floating-point ANSI-C code for the AMR-WB speech codec | AMRWB-FP | 2 | Rel-5 | S4 | 2001-09-25 08:00 | 2002-03-14 17:00 | 100% | SP-010459 | - | Nokia | janne.m.vainio@nokia.com | - | 26.204 |  |  |  |  | Mon 08/10/01 | Thu 28/02/02
5784 | 80 | Support of AMR-WB in GERAN: GMSK and 8PSK WB FR / HR | GAMRWB | 2 | Rel-5 | GP | 2000-01-03 08:00 | 2002-06-28 17:00 | 100% | GP-000453 | - | - | - | - | - |  |  |  |  | Wed 05/04/00 | Wed 31/07/02
5785 | 50298 | Channel coding in 45.003 for Support of AMR-WB in GERAN: GMSK and 8PSK WB FR / HR | - | 3 | Rel-5 | GP | 2000-01-03 08:00 | 2002-04-05 17:00 | 100% | - | - | - | - | 50098 -> 50298 | - |  |  |  |  | Thu 01/02/01 | Tue 06/05/08
5786 | 2266 | Signalling for the A interface | - | 3 | Rel-5 | GP | 2000-01-03 08:00 | 2001-06-29 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
5787 | 2267 | Signalling for Iu | - | 3 | Rel-5 | GP | 2000-01-03 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5788 | 2268 | Receiver performance in TS 45.005 | - | 3 | Rel-5 | GP | 2001-04-02 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5789 | 50000 | Link Adaptation in 45.009 | - | 3 | Rel-5 | GP | 2001-03-26 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 09/10/01 | Wed 31/07/02
5790 | 2269 | Deleted - GERAN MS conformance test for AMR-WB | - | 2 | Rel-5 | GP | 2000-01-03 08:00 | 2003-12-19 17:00 | 100% | GP-000454 | - | - | - | Not started 02/2003. Marked as stopped 12/2008 | - |  |  | SP-69 |  | Thu 01/02/01 | Fri 12/12/08
5791 | 2270 | Deleted - MS test for AMR-WB | - | 3 | Rel-5 | GP | 2000-01-03 08:00 | 2003-12-19 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-17 |  | Thu 01/02/01 | Fri 12/12/08
5792 | 2271 | GERAN BTS conformance test for AMR-WB | - | 2 | Rel-5 | GP | 2000-01-03 08:00 | 2002-12-02 17:00 | 100% | GP-000455 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Thu 13/02/03
5793 | 1826 | Rel-5 Terminal interfaces | TLM5 | 1 | Rel-5 | T2 | 2001-05-14 08:00 | 2002-03-20 17:00 | 100% | - | - | - | - | Acronym changed from "TI, TLMN5" | - |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
5794 | 2573 | Terminal local model enhancements | TLM5 | 2 | Rel-5 | T2 | 2001-05-14 08:00 | 2002-03-20 17:00 | 100% | TP-010224 | - | - | - | - | 23.227 |  |  |  |  | Thu 14/09/00 | Thu 27/03/03
5795 | 1536 | Rel-5 Location Services enhancements | LCS1 | 1 | Rel-5 | S2,S1,S3,S5,N4,R2,R3,GP | 2000-04-03 08:00 | 2003-06-27 17:00 | 100% | SP-010518 | - | Nokia | Jan Kall | . Acronym changed from "LCS1, Rel-5" | - |  |  |  |  | Fri 28/07/00 | Tue 24/03/15
5796 | 1600 | UE positioning for Rel-5 Location Services enhancements | LCS1-Uepos | 2 | Rel-5 | R2 | 2001-01-15 08:00 | 2002-03-29 17:00 | 100% | - | - | - | - | Acronym changed from "LCS1-Uepos, Rel-5" | - |  |  |  |  | Wed 26/07/00 | Tue 24/03/15
5797 | 2474 | UE positioning enhancements for 1.28 Mcps TDD | LCS-128Pos | 3 | Rel-5 | R2 | 2001-04-09 08:00 | 2002-03-29 17:00 | 100% | RP-010215 | - | CATT | Xiaohua Mei | - | 25.123, 25.224, 25.225, 25.302, 25.303, 25.304, 25.305, 25.331, 25.420, 25.423, 25.430, 25.433, New TR 25.859 |  |  |  |  | Tue 20/03/01 | Thu 28/02/02
5798 | 2125 | Open SMLC-SRNC Interface within the UTRAN to support A-GPS Positioning | LCS-INTF | 3 | Rel-5 | R2 | 2001-01-15 08:00 | 2001-10-12 17:00 | 100% | RP-010414 | - | Qualcomm | Kirk Burroughs | RP#13 completed | - |  |  |  |  | Mon 27/11/00 | Thu 24/01/02
5799 | 1171 | Event Based and Periodic LCS | LCS1-EBP | 2 | Rel-5 | S1,S2,N4 | 2000-05-22 | 2002-06-07 17:00 | 100% | - | - | Pacific Bell Wireless | Randolph Wohlert (rwohlert@tri.sbc.com) | - | - |  |  |  |  | Wed 19/04/00 | Mon 21/05/12
5800 | 1641 | Stage 1 for Event based and Periodic LCS | - | 3 | Rel-5 | S1 | 2000-05-22 | 2000-11-17 17:00 | 100% | - | - | Pacific Bell Wireless | Randolph Wohlert (rwohlert@tri.sbc.com) | Evaluate Event based and Periodic LCS to be included in R00, corresponding Stage 1 description | 22.071 |  |  |  |  | Tue 08/08/00 | Sat 01/04/00
5801 | 1538 | Stage 2 for Event based and Periodic LCS | - | 3 | Rel-5 | S2 | 2000-11-06 08:00 | 2001-01-26 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 51% complete) | - |  |  |  |  | Fri 28/07/00 | Fri 12/12/08
5802 | 1179 | Impact on MAP | - | 3 | Rel-5 | N4 | 2002-03-15 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Possible impact on UTRAN of LCS quality level request | - |  |  |  |  | Wed 19/04/00 | Thu 30/05/02
5803 | 2436 | Location Services for GERAN in A/Gb Mode | LCS-GERAN | 2 | Rel-5 | GP | 2000-04-03 08:00 | 2002-02-08 17:00 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Mon 21/05/12
5804 | 2437 | GERAN LCS Stage 2 (first release) | - | 3 | Rel-5 | GP,S2,G1,G2 | 2000-04-03 08:00 | 2002-02-08 17:00 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Mon 21/05/12
5805 | 2438 | Gb interface support for LCS | - | 3 | Rel-5 | GP | 2000-04-03 08:00 | 2001-08-31 17:00 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Mon 21/05/12
5806 | 2440 | L3 protocol support for LCS | - | 3 | Rel-5 | GP | 2000-04-03 08:00 | 2001-06-01 17:00 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Mon 21/05/12
5807 | 2441 | Stage 3 for Location Services for GERAN in A/Gb Mode | - | 3 | Rel-5 | GP | 2000-04-03 08:00 | 2001-06-01 17:00 | 100% | GP-011925 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Mon 21/05/12
5808 | 2442 | Location Services for GERAN in Iu Mode | - | 2 | Rel-5 | S2,G1,G2,R2,R3 | 2000-04-03 08:00 | 2002-06-28 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5809 | 2443 | GERAN LCS Stage 2 | - | 3 | Rel-5 | S2,G1,G2 | 2000-04-03 08:00 | 2002-06-28 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5810 | 2444 | Iu-ps interface support for LCS | - | 3 | Rel-5 | R2,R3 | 2000-04-03 08:00 | 2002-06-28 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5811 | 2445 | Iu-cs interface support for LCS | - | 3 | Rel-5 | R2,R3 | 2000-04-03 08:00 | 2002-06-28 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5812 | 2446 | Iur-g interface support for LCS | - | 3 | Rel-5 | G1,G2 | 2002-01-23 13:00 | 2002-04-19 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | FFS | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5813 | 2447 | RRC protocol support for LCS | - | 3 | Rel-5 | G1,G2,R2,R3 | 2001-08-20 08:00 | 2001-11-30 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5814 | 2448 | Additional impacts on Broadcast of LCS data on packet channels | - | 3 | Rel-5 | G1,G2,R2,R3 | 2001-08-20 08:00 | 2001-12-05 12:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5815 | 2449 | Stage 3 for Location Services for GERAN in Iu Mode | - | 3 | Rel-5 | G1,G2,R2,R3 | 2002-03-25 13:00 | 2002-06-28 17:00 | 100% | GP-011926 | - | Nokia | Margaret Livingston | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5816 | 50068 | GERAN MS Conformance test for LCS | LCS-GERAN-MSconf | 2 | Rel-5 | GP | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | GP-000458 | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Mon 21/05/12
5817 | 55069 | LCS MS test case work plan (Release 98/99/4) | - | 3 | Rel-5 | G4,G5 | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | GP-000458 | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | - |  |  |  |  | Thu 23/05/02 | Mon 21/05/12
5818 | 55070 | LCS MS test cases | - | 3 | Rel-5 | G4,G5 | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | GP-000458 | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | - |  |  |  |  | Thu 23/05/02 | Mon 21/05/12
5819 | 50069 | Deleted - GERAN BTS Conformance test for LCS | LCS-GERAN-BTSconf | 2 | Rel-5 | GP | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | GP-000459 | - | - | - | Not started 02/3003. Marked as stopped 12/2008 | - |  |  | GP-15 |  | Thu 23/05/02 | Mon 21/05/12
5820 | 55071 | Deleted - LCS BTS test case work plan (Release 98/99/4) | - | 3 | Rel-5 | G4,G5 | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-15 |  | Thu 23/05/02 | Fri 12/12/08
5821 | 55072 | Deleted - LCS BTS test cases | - | 3 | Rel-5 | G4,G5 | 2002-06-03 08:00 | 2003-06-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-15 |  | Thu 23/05/02 | Fri 12/12/08
5822 | 544 | LCS interoperation stage 2 aspects | - | 2 | Rel-5 | S2 | 2000-08-28 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 17% complete) | - |  |  |  |  | Wed 19/04/00 | Fri 12/12/08
5823 | 2434 | LCS interoperability aspects to GERAN (LCS-GERAN) | - | 2 | Rel-5 | GP,S5 | 2000-08-28 08:00 | 2002-06-28 17:00 | 100% | GP-000456 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 21/05/12
5824 | 2435 | Co-ordinated development of GSM LCS Phase 2 and UMTS LCS, S2 and GERAN | - | 3 | Rel-5 | GP,S2,S5,R2,R3,G2,G1 | 2000-08-28 08:00 | 2002-06-28 17:00 | 100% | GP-000456 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 21/05/12
5825 | 1183 | FS on LCS support in the IMS | - | 2 | Rel-5 | S1 | 2001-02-12 08:00 | 2002-01-18 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 75% complete) | - |  |  |  |  | Wed 19/04/00 | Fri 12/12/08
5826 | 35008 | Charging and OAM&P for LCS enhancements | LCS1-OAM | 2 | Rel-5 | S5 | 2001-09-21 08:00 | 2002-06-28 17:00 | 100% | SP-010461 | - | - | - | - | 32.200-series |  |  |  |  | Wed 19/04/00 | Mon 21/05/12
5827 | 521 | New security aspects of LCS | LCS1-SEC | 2 | Rel-5 | S3,S2 | 2000-04-14 08:00 | 2001-12-28 17:00 | 100% | SP-000421 | - | Nokia | valtteri.niemi@nokia.com | SP#9 updated WID S3-000609 (Location services security) | 23.271, 43.059 |  |  |  |  | Wed 19/04/00 | Mon 21/05/12
5828 | 32011 | Specification for the Le interface | LCS1-Le | 2 | Rel-5 | S2 | 2002-01-14 08:00 | 2002-03-15 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 24/01/02 | Mon 21/05/12
5829 | 32022 | Deleted - CHECK STATUS - Inter-GMLC interface | - | 2 | Rel-5 | S2 | 2002-05-30 08:00 | 2002-12-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | SP-10 |  | Thu 30/05/02 | Fri 12/12/08
5830 | 501571 | Rel-5 Security enhancements (SEC1) | - | 1 | Rel-5 | S3 | 2000-02-21 08:00 | 2002-06-28 17:00 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | Added BB UE authentication and rapporteur added. TO BE DELETED | - |  |  |  |  | Sun 09/04/00 | Mon 08/08/11
5831 | 1576 | Rel-5 Network Domain Security (SEC1-NDS) | - | 2 | Rel-5 | S3 | 2000-02-21 08:00 | 2002-06-28 17:00 | 100% | SP-000420 | - | Telenor | Geir-myrdahl.koien@telenor.com | SP#9 approved WID SP-000420 (S3-000606 Network domain security). S3#17: All due in Rel5. (WI Update at S3#18). Replaced by NDS-IP and NDS-MAP. TO BE DELETED OR MOVED TO HISTORY FILE | New 33.200 (exists also for Rel-4) |  |  |  |  | Tue 18/04/00 | Mon 08/08/11
5832 | 2576 | Rel-5 IP network layer security (NDS/IP) (SEC1-NDS-IP) | - | 3 | Rel-5 | S3 | 2000-06-15 08:00 | 2002-03-15 17:00 | 100% | SP-010326 | - | Telenor | Geir-myrdahl.koien@telenor.com | SP#12 WID updated SP-000420 (S3-000606) =>SP-010326 (S3-010286) | New 33.210 |  |  |  |  | Sat 09/06/01 | Mon 08/08/11
5833 | 1577 | Deleted - Control plane protection in core network (e.g., GTP, CAP, MAP/IP, provided by IPsec) | - | 3 | Rel-5 | S3 | 2000-05-12 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | SP-16 |  | Tue 18/04/00 | Fri 12/12/08
5834 | 1578 | Deleted - Main aspects of User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | S3 | 2000-05-12 08:00 | 2001-06-21 17:00 | 100% | - | - | - | - | TO BE DELETED. Marked as stopped 12/2008 | - |  |  | SP-12 |  | Sun 09/04/00 | Fri 12/12/08
5835 | 1579 | Deleted - Integration of GTP signalling security architecture - for User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | N4 | 2001-09-14 08:00 | 2002-06-07 17:00 | 100% | - | - | - | - | Waiting for input from SA3!. Marked as stopped 12/2008 | - |  |  | NP-16 |  | Sun 09/04/00 | Fri 12/12/08
5836 | 1580 | Deleted - User plane protection in core network (e.g., provided by IPsec) | - | 3 | Rel-5 | S3 | 2000-02-21 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | TO BE DELETED. Marked as stopped 12/2008 | - |  |  | SP-16 |  | Tue 18/04/00 | Fri 12/12/08
5837 | 1581 | Deleted -Main aspects of User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | S3 | 2000-02-21 08:00 | 2001-06-21 17:00 | 100% | - | - | - | - | - | - |  |  | SP-12 |  | Sun 09/04/00 | Fri 08/11/02
5838 | 1582 | Deleted - Integration of GTP signalling security architecture - for User plane protection in core network (e.g., provided by IPsec) | - | 4 | Rel-5 | N4 | 2001-09-14 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | 14/02/2002 requirements are not clear/not receivedMarked as closed 12/2008 (was marked 95 complete) | - |  |  | NP-16 |  | Sun 09/04/00 | Fri 12/12/08
5839 | 2243 | Intra Domain Connection of RAN Nodes to Multiple CN Nodes | IUFLEX | 1 | Rel-5 | S2,N1,N4,R3,GP | 2000-10-02 08:00 | 2002-06-28 17:00 | 100% | SP-000619 | - | Ericsson | stephen.terrill@ericsson.com | No clear indication on the end date. Put to Rel5 by AS. | 23.236 |  |  |  |  | Wed 13/12/00 | Thu 24/01/02
5840 | 2244 | Overall System Architecture for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | - | 2 | Rel-5 | S2 | 2001-01-03 08:00 | 2001-09-21 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 13/12/00 | Wed 19/09/01
5841 | 20000 | Stage 3: RAN node selecting CN node | - | 2 | Rel-5 | R3 | 2001-09-24 08:00 | 2002-03-22 17:00 | 100% | - | - | Vodafone | Brendan.McWilliams@gb.vodafone.co.uk | Not identified | - |  |  |  |  | Wed 19/09/01 | Fri 01/03/02
5842 | 2248 | N1 work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | - | 2 | Rel-5 | N1 | 2001-09-17 08:00 | 2002-06-28 17:00 | 100% | NP-010693 | - | - | - | - | 24.008 and check 29.018 |  |  |  |  | Wed 13/12/00 | Thu 26/09/02
5843 | 2249 | N4 work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | - | 2 | Rel-5 | N4 | 2000-10-02 08:00 | 2002-03-08 17:00 | 100% | NP-000737 | - | - | - | DAB 12.12.01 - % complete to 66% | - |  |  |  |  | Wed 13/12/00 | Mon 25/03/02
5844 | 50067 | GERAN work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes | IDCRAN-GERAN | 2 | Rel-5 | GP | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | GP-020492 | - | Ericsson | ingemar.backlund@era.ericsson.se | Accept changes Gb over IP | - |  |  |  |  | Thu 23/05/02 | Thu 26/09/02
5845 | 51068 | Stage 2 (changes to ) | - | 3 | Rel-5 | G1 | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5846 | 51069 | 43.051 Introduction of support for IDNNS in GERAN Iu mode | - | 3 | Rel-5 | G1 | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5847 | 52070 | Stage 3 (changes to ) | - | 3 | Rel-5 | G2 | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5848 | 52077 | 48.016 Use of Gb interface concepts when a network applies IDNNS | - | 3 | Rel-5 | G2 | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | Closed, accept changes for Gb over IP | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5849 | 52078 | 48.018 Include MSC/VLR identity in CS IMSI paging | - | 3 | Rel-5 | G2 | 2002-02-08 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5850 | 2320 | Deleted - GERAN improvements 3 (new transport layer on interface A) | GEIMP3 | 1 | Rel-5 | GP | 2001-04-06 08:00 | 2002-12-20 17:00 | 100% | GP-010909 | - | - | - | Terminated - not standardized. Marked as stopped 12/2008 | - |  |  | SP-69 |  | Thu 01/02/01 | Fri 12/12/08
5851 | 2321 | Deleted - Evolution of the transport for A | GEIMP3-EtA | 2 | Rel-5 | GP | 2001-04-06 08:00 | 2002-12-20 17:00 | 100% | GP-010910 | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
5852 | 2322 | Deleted - Definition of a new A/Ater interface Transport Layer option based on the Iu Interface Transport Layer | - | 3 | Rel-5 | GP | 2001-04-06 08:00 | 2002-12-20 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
5853 | 2323 | Deleted - Adaptation of the Layer 3 BSSMAP procedures as required | - | 3 | Rel-5 | GP | 2001-04-06 08:00 | 2002-12-20 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
5854 | 501142 | Rel-5 Charging Management & Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM5 | 1 | Rel-5 | S5 | 2001-09-10 08:00 | 2002-09-12 17:00 | 100% | SP-010461 | - | - | - | - | - |  |  |  |  | Wed 26/04/00 | Fri 21/06/02
5855 | 35002 | Rel-5 Principles, high level Requirements and Architecture | - | 2 | Rel-5 | S5 | 2001-09-17 08:00 | 2002-06-28 17:00 | 100% | SP-010461 | - | Motorola | - | - | 32.101, 32.102 |  |  |  |  | Wed 26/04/00 | Fri 21/06/02
5856 | 35003 | Rel-5 Performance Management | - | 2 | Rel-5 | S5 | 2001-09-17 08:00 | 2002-09-12 17:00 | 100% | SP-010631 | - | Nortel | - | - | 32.4xy, 52.402 |  |  |  |  | Wed 26/04/00 | Fri 08/11/02
5857 | 35004 | Rel-5 Charging Management | - | 2 | Rel-5 | S5 | 2001-09-10 08:00 | 2002-09-12 17:00 | 100% | SP-010631 | - | T-Mobile | Karl-Heinz.Nenner@T-MOBILE.DE | - | 32.200, 32.205, 32.215, 32.225, 32.235 |  |  |  |  | Wed 26/04/00 | Fri 08/11/02
5858 | 35001 | Rel-5 Network Infrastructure Management | - | 2 | Rel-5 | S5 | 2001-09-21 08:00 | 2002-09-12 17:00 | 100% | SP-010461 | - | Ericsson | thomas.tovinger@ericsson.com | - | 32.6xy, 32.3xy |  |  |  |  | Mon 08/10/01 | Fri 08/11/02
5859 | 2392 | GERAN enhancements for streaming services 1 (RLC enhancements) | - | 1 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | GP-010429 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5860 | 2394 | Concept for GERAN enhancements for streaming services 1 (RLC enhancements) | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2001-10-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5861 | 2395 | RLC protocol enhancement (SDU Discard) | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5862 | 2396 | GERAN enhancements for streaming services 2 (usage of ECSD) | - | 1 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | GP-010430 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Motorola, Vodafone | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5863 | 2398 | Usage of ECSD Concept | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5864 | 2399 | Stage 2 for GERAN enhancements for streaming services 2 (usage of ECSD) | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5865 | 2400 | Stage 3 for GERAN enhancements for streaming services 2 (usage of ECSD) | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5866 | 2401 | RLC PDU formats | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5867 | 2402 | MAC header | - | 2 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5868 | 2412 | GERAN/UTRAN interface evolution 1 (evolution of Iu PS) | GERUEV1 | 1 | Rel-5 | GP,R3 | 2000-09-01 08:00 | 2002-06-28 17:00 | 100% | GP-010481 | - | SBC | Marc Grant | SBC, Motorola, Nokia, Ericsson, Nortel | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5869 | 2413 | Evolution of Iu ps | GERUEV1-IuPS | 2 | Rel-5 | GP,R3 | 2000-09-01 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5870 | 2414 | Identification of GERAN requirements on Iu ps | - | 3 | Rel-5 | GP,R3 | 2000-09-01 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Tue 21/05/02
5871 | 2415 | Update of Evolution of Iu ps specifications | - | 3 | Rel-5 | GP,R3 | 2001-12-03 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5872 | 2416 | GERAN/UTRAN interface evolution 2 (evolution of Iu CS) | GERUEV2 | 1 | Rel-5 | GP,R3 | 2000-06-29 08:00 | 2002-06-28 17:00 | 100% | GP-010417 | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5873 | 2417 | Evolution of Iu cs | GERUEV2-IuCS | 2 | Rel-5 | GP,R3 | 2000-06-29 08:00 | 2002-06-28 17:00 | 100% | GP-000430 | - | Lucent | Krishna Balachandran | Lucent, Ericsson, AWS, Nortel | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5874 | 2418 | Identification of GERAN requirements on Iu cs | - | 3 | Rel-5 | GP,R3 | 2000-06-29 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5875 | 2419 | Update of Evolution of Iu cs specifications | - | 3 | Rel-5 | GP,R3 | 2000-09-01 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 02/02/01 | Wed 31/07/02
5876 | 2556 | End to End QoS for PS Domain including IMS | E2EQoS | 1 | Rel-5 | S2,S5,N3 | 2000-08-28 08:00 | 2002-06-28 17:00 | 100% | SP-010343 | - | Ericsson | Johnson.oyama@era.ericcson.se | Acronym changed from "E2EQoS, Rel-5" | - |  |  |  |  | Fri 08/06/01 | Tue 24/03/15
5877 | 2557 | E2E QoSConcept and Architecture | - | 2 | Rel-5 | S2 | 2001-01-03 08:00 | 2001-09-07 17:00 | 100% | - | - | - | - | - | 23.207 |  |  |  |  | Fri 08/06/01 | Sat 24/11/01
5878 | 2558 | E2E QoS interworking | E2EQoS-IW | 2 | Rel-5 | N3 | 2000-08-28 08:00 | 2002-06-07 17:00 | 100% | NP-010528 | - | Lucent | Daisuke Yokota (yokota@lucent.com) | [DAB - 30/07/02] - % complete to 95% (if we exclude Diffserv). Marked as closed 12/2008 (was marked 95% complete) | 29.208, 29.207, 27.060, 29.061, 24.008, 24.228, , 24.229, 29.060, 29.163 |  |  |  |  | Fri 08/06/01 | Fri 12/12/08
5879 | 2559 | QoS Management (Provisioning and Monitoring) | E2EQoS-OAM | 2 | Rel-5 | S5 | 2001-09-21 08:00 | 2002-06-28 17:00 | 100% | SP-010461 | - | - | - | - | 32-series |  |  |  |  | Fri 08/06/01 | Fri 08/11/02
5880 | 2569 | Rel-5 Messaging enhancements | MESS5 | 1 | Rel-5 | T2 | 2001-06-15 08:00 | 2003-03-31 17:00 | 100% | - | - | - | - | support of UAProf, so this in my opinion is 100% complete | - |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
5881 | 2571 | Rel-5 Multimedia Messaging (MMS) enhancements | MESS5-MMS | 2 | Rel-5 | T2 | 2001-06-15 08:00 | 2003-03-31 17:00 | 100% | TP-010130 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | - |  |  |  |  | Thu 14/09/00 | Thu 27/03/03
5882 | 31000 | Definition of service requirements for MESS5-MMS | MESS5-SR | 3 | Rel-5 | S1 | 2001-06-15 08:00 | 2002-03-15 17:00 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140 |  |  |  |  | Wed 04/07/01 | Fri 25/07/03
5883 | 42000 | Technical realization of MESS5-MMS | - | 3 | Rel-5 | T2 | 2001-06-15 08:00 | 2002-06-07 17:00 | 100% | - | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | stage 3 MM7 is missing | 23.140 |  |  |  |  | Wed 04/07/01 | Thu 27/03/03
5884 | 42008 | WAP Forum dependency: MM1 stage 3 | - | 3 | Rel-5 | T2 | 2001-06-15 08:00 | 2003-03-31 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 80% complete) | - |  |  |  |  | Thu 30/05/02 | Fri 12/12/08
5885 | 34018 | MMS formats and codecs for MESS5-MMS | - | 3 | Rel-5 | S4 | 2001-12-03 08:00 | 2002-03-15 17:00 | 100% | - | - | - | - | - | 26.140 |  |  |  |  | Thu 24/01/02 | Thu 28/02/02
5886 | 2572 | Enhanced Messaging Service (EMS) enhancements | MESS5-EMS | 2 | Rel-5 | T2 | 2001-06-15 08:00 | 2002-03-08 17:00 | 100% | TP-010153 | - | Ericsson | Alan.Baldwin@EML.ERICSSON.SE | - | 23.040 |  |  |  |  | Thu 14/09/00 | Thu 27/03/03
5887 | 31001 | Definition of service requirements for Enhanced Messaging Service (EMS) enhancements | - | 3 | Rel-5 | S1 | 2001-06-15 08:00 | 2001-09-14 17:00 | 100% | - | - | Ericsson | Alan.Baldwin@EML.ERICSSON.SE | - | - |  |  |  |  | Wed 04/07/01 | Thu 28/02/02
5888 | 42001 | Technical realization of Enhanced Messaging Service (EMS) enhancements | - | 3 | Rel-5 | T2 | 2001-06-15 08:00 | 2002-03-08 17:00 | 100% | - | - | Ericsson | Alan.Baldwin@EML.ERICSSON.SE | - | 23.040 |  |  |  |  | Wed 04/07/01 | Thu 28/02/02
5889 | 50001 | GERAN Inter BSC NACC improvements over the Gb Interface | GERNACC | 1 | Rel-5 | GP | 2001-09-03 08:00 | 2002-06-28 17:00 | 100% | GP-012313 | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
5890 | 14501 | Modification of core network protocols for GERAN Inter BSC NACC over Gb Interface | GERNACC-Cnmod | 2 | Rel-5 | N4,S2 | 2001-09-03 08:00 | 2002-04-19 17:00 | 100% | GP-011877 | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
5891 | 32502 | Stage 2 - Concept | - | 3 | Rel-5 | N4,S2 | 2001-09-03 08:00 | 2001-10-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
5892 | 14502 | Stage 2 - 23.060 change - Definition of Inter BSC NACC | - | 3 | Rel-5 | N4,S2 | 2001-09-03 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
5893 | 14503 | Stage 3 (changes to TS 29.060) | - | 3 | Rel-5 | N4 | 2001-09-03 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | IP 30/11/01: Input awaited from GERAN2 to CN4 | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
5894 | 50002 | Modification of Gb protocols for GERAN Inter BSC NACC over Gb Interface | GERNACC-Gbmod | 2 | Rel-5 | GP | 2001-11-30 08:00 | 2002-06-28 17:00 | 100% | GP-012314 | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
5895 | 50003 | Stage 3 (changes to TS 48.018) | - | 3 | Rel-5 | GP | 2001-11-30 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 31/07/02
5896 | 50033 | Enhanced Power Control | EPC | 1 | Rel-5 | GP | 2001-11-26 08:00 | 2003-12-19 17:00 | 100% | GP-012748 | - | - | - | - | - |  |  |  |  | Mon 10/12/01 | Thu 13/02/03
5897 | 50034 | Realization of Enhanced power control and signalling support | - | 2 | Rel-5 | GP | 2001-11-26 08:00 | 2001-11-30 17:00 | 100% | GP-012749 | - | - | - | Completed 11/2001 | - |  |  |  |  | Mon 10/12/01 | Thu 13/02/03
5898 | 50035 | Deleted - GERAN MS Conformance test for Enhanced Power Control | - | 2 | Rel-5 | GP | 2001-12-10 08:00 | 2003-12-19 17:00 | 100% | GP-012750 | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Mon 10/12/01 | Thu 13/02/03
5899 | 50036 | Deleted - GERAN BTS Conformance test for Enhanced Power Control | - | 2 | Rel-5 | GP | 2001-12-10 08:00 | 2003-12-19 17:00 | 100% | GP-012751 | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Mon 10/12/01 | Thu 13/02/03
5900 | 50037 | 8PSK AMR HR | 8PSK-AH | 1 | Rel-5 | GP | 2001-12-10 08:00 | 2003-12-19 17:00 | 100% | GP-012752 | - | - | - | Completed for Rel-5 | - |  |  |  |  | Mon 10/12/01 | Mon 13/01/03
5901 | 50038 | Definition of channel coding, performance requirements and signalling support | - | 2 | Rel-5 | GP | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | GP-012753 | - | - | - | - | - |  |  |  |  | Mon 10/12/01 | Wed 31/07/02
5902 | 50061 | Concept | - | 3 | Rel-5 | GP | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5903 | 52004 | Changes to 44.018 | - | 3 | Rel-5 | G2 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5904 | 51025 | Changes to 45.001 | - | 3 | Rel-5 | G1 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5905 | 51026 | Changes to 45.002 | - | 3 | Rel-5 | G1 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5906 | 51027 | Changes to 45.003 | - | 3 | Rel-5 | G1 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5907 | 51028 | Changes to 45.005 | - | 3 | Rel-5 | G1 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5908 | 52005 | Changes to 24.008 | - | 3 | Rel-5 | G2 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5909 | 52006 | Changes to 48.058 | - | 3 | Rel-5 | G2 | 2001-12-10 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5910 | 50039 | Deleted - GERAN MS Conformance test for 8PSK HR | - | 2 | Rel-5 | GP | 2001-12-10 08:00 | 2003-12-19 17:00 | 100% | GP-012754 | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-17 |  | Mon 10/12/01 | Fri 12/12/08
5911 | 50040 | GERAN BTS Conformance test for 8PSK HR | - | 2 | Rel-5 | GP | 2001-12-10 08:00 | 2002-12-20 17:00 | 100% | GP-012755 | - | - | - | - | - |  |  |  |  | Mon 10/12/01 | Mon 13/01/03
5912 | 13000 | Service Change and UDI Fallback | SCUDIF | 1 | Rel-5 | N3 | 2001-10-08 08:00 | 2002-06-07 17:00 | 100% | NP-020164 | - | Ericsson | Rune.Werner.Wiik@ericsson.no | - | 29.007, 27.001, 24.008 |  |  |  |  | Wed 19/09/01 | Fri 25/07/03
5913 | 501800 | Rel-5 USIM toolkit enhancements | USAT5 | 1 | Rel-5 | T3,S1 | 2000-06-05 08:00 | 2003-09-26 17:00 | 100% | - | - | G & D | Michael Meyer | Acronym changed from USAT1, USAT1-Interpr, USAT1LocLnk | 22.038, 31.111 (USAT1), 22.038, 03.19, 03.48 (USAT1LocLnk), 23.048 (USAT1SM), 43.019 (USAT1APIJAVA) |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
5914 | 43002 | Deleted - Test specification for USIM toolkit security mechanisms | - | 2 | Rel-5 | T3 | 2002-05-28 08:00 | 2003-09-26 17:00 | 100% | TP-020028 | - | Gemplus | Sophie Viallet | Marked as stopped 12/2008 | - |  |  | TP-21 |  | Thu 30/05/02 | Mon 13/01/03
5915 | 1801 | Protocol Standardisation of a SIM Toolkit Interpreter | - | 2 | Rel-5 | T3,T2 | 2000-06-05 08:00 | 2003-01-22 17:00 | 100% | TP-000116 | - | G & D | Michael Meyer | 28/5/2001: T3-19 proposed that since the stage 2 and 3 will not be presented to TP-12 for approval as expected, the WI will be moved to rel-5, with completion expected at TP-13. | T2 27.103 |  |  |  |  | Thu 14/09/00 | Mon 28/05/01
5916 | 2497 | Stage 1 for Protocol Standardisation of a SIM Toolkit Interpreter | - | 3 | Rel-5 | T3 | 2000-06-05 08:00 | 2001-03-16 17:00 | 100% | - | - | - | - | 5/10/2001: Stage one comepeted at TP-12. | 31.112, 31.113, 31.114 |  |  |  |  | Fri 30/03/01 | Fri 05/10/01
5917 | 2496 | Stage 2 and 3 | - | 3 | Rel-5 | T3 | 2001-01-03 08:00 | 2002-03-08 17:00 | 100% | - | - | - | - | 5/10/2001: TS 31.112 and 31.113 approved at TP-13. TS 31.114 to be presented to TP-14. | 31.112, 31.113, 31.114 |  |  |  |  | Fri 30/03/01 | Tue 04/06/02
5918 | 2518 | Test specification for Protocol Standardisation of a SIM Toolkit Interpreter | - | 3 | Rel-5 | T3 | 2001-09-03 08:00 | 2003-01-22 17:00 | 100% | TP-010111 | - | Gemplus | Gérald MAUNIER | 5/10/2001: Work started on test specification. Marked as closed 12/2008 (was marked 12% complete) | - |  |  |  |  | Fri 30/03/01 | Fri 12/12/08
5919 | 501802 | (U)SIM API | USAT5-API | 2 | Rel-5 | T3 | 2002-03-20 08:00 | 2002-09-20 17:00 | 100% | TP-020029 | - | Microelectrónica Española | Mario Pérez | 8/3/2001: test spec is based on R99 core spec, so deleted from Workplan. Acronym changed from USAT1-API, TEI4 | - |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
5920 | 504301 | Rel-5 Java API Test specification | - | 3 | Rel-5 | T3 | 2002-03-20 08:00 | 2002-09-20 17:00 | 100% | TP-020029 | - | Microelectrónica Española | Mario Pérez | - | 51.013 |  |  |  |  | Thu 30/05/02 | Thu 26/09/02
5921 | 30001 | (Small) Technical Enhancements and Improvements for Rel-5 | TEI5 | 1 | Rel-5 | SP,CP,RP,GP | 2000-01-03 08:00 | 2000-01-03 08:00 | 100% | - | - | - | - | "Joker" WI, to be used for a Rel 5 CR not related to any feature and with very limited impact on the system | - |  |  |  |  | Tue 26/09/00 | Sat 01/04/00
5922 | 25018 | Test - (Small) Technical Enhancements and Improvements for Rel-5 | TEI5_Test | 1 | Rel-5 | R5,T1 | 2000-01-03 08:00 | 2008-12-31 17:00 | 100% | - | - | - | - | "Joker" WI, to be used for small modifications applicable to Rel 5 conformance testing. Moved in from Stoyan/testing WP. | 34.108, 34.109, 34.121-1, 34.121-2, 34.122, 34.123-1, 34.123-2, 34.123-3, 34.171, 34.229-1, 34.229-2, 34.229-3 |  |  |  |  | Tue 21/03/06 | Tue 06/05/08
5923 | 31013 | Technical Report on UE Functionality Split | UESPLIT | 1 | Rel-5 | S1 | 2000-01-03 08:00 | 2000-05-01 17:00 | 100% | SP-010484 | - | Motorola | jian.j.wu@motorola.com | - | New TR 22.944 |  |  |  |  | Thu 11/10/01 | Tue 14/09/10
5924 | 2520 | User Equipment Management | UEM | 1 | Rel-5 | S5 | 2001-06-21 08:00 | 2002-06-28 17:00 | 100% | SP-010286 | - | Vodafone | john.mudge@vf.vodafone.co.uk | - | 32.802 |  |  |  |  | Wed 06/06/01 | Fri 21/06/02
5925 | 35000 | FS on User Equipment (UE) Management | OAM-UEM | 2 | Rel-5 | S5 | 2001-06-21 08:00 | 2002-06-28 17:00 | 100% | SP-010286 | - | Vodafone | john.mudge@vf.vodafone.co.uk | - | 32.802 |  |  |  |  | Tue 03/07/01 | Fri 21/06/02
5926 | 50201 | Flow control supporting an MS with multiple data flows with different QoS over the Gb interface | FlowCon | 1 | Rel-5 | GP | 2002-06-24 08:00 | 2002-08-30 17:00 | 100% | GP-021767 | - | Ericsson | ingemar.backlund@era.ericsson.se | 50101 -> 50201 | - |  |  |  |  | Wed 31/07/02 | Tue 06/05/08
5927 | 50202 | Update of stage 2 specifications | - | 2 | Rel-5 | GP | 2002-06-24 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | 50102 -> 50202 | - |  |  |  |  | Wed 31/07/02 | Tue 06/05/08
5928 | 32097 | Concept document 23.060 (changes to) | - | 3 | Rel-5 | S2 | 2002-06-28 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/07/02 | Thu 26/09/02
5929 | 50203 | Flow Control | - | 3 | Rel-5 | GP | 2002-06-24 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | 50103 -> 50203 | - |  |  |  |  | Wed 31/07/02 | Tue 06/05/08
5930 | 50204 | Modification of BSSGP protocol | - | 2 | Rel-5 | GP | 2002-06-24 08:00 | 2002-06-28 17:00 | 100% | GP-021508 | - | Ericsson | ingemar.backlund@era.ericsson.se | 50104 -> 50204 | - |  |  |  |  | Wed 31/07/02 | Fri 26/10/12
5931 | 52095 | Stage 3 (changes to 48.018) | - | 3 | Rel-5 | G2 | 2002-06-24 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/07/02 | Thu 26/09/02
5932 | 50058 | Deleted - Multiple TBF in A/Gb mode - Phase 1 (MULTBF) | - | 1 | Rel-5 | GP | 2002-04-19 08:00 | 2003-11-28 17:00 | 100% | GP-021263 | - | Ericsson | gunnar.mildh@era.ericsson.se | GP#17 Nov 2003 Moved to Rel-6 as UID_50600 MULTBF (Only Multiple TBF Concept paper produced in Rel-5) | - |  |  | GP-17 |  | Thu 23/05/02 | Thu 12/11/09
5933 | 50059 | Deleted - Multiple TBF in A/Gb mode - Core (MULTBF-Agbmode) | - | 2 | Rel-5 | GP | 2002-04-19 08:00 | 2003-08-22 17:00 | 100% | GP-021263 | - | - | - | Marked as closed 12/2008 (was marked 26% complete) | - |  |  | GP-17 |  | Thu 23/05/02 | Thu 12/11/09
5934 | 50060 | Deleted - Multiple TBF Concept paper | - | 3 | Rel-5 | GP | 2002-04-19 08:00 | 2003-08-22 17:00 | 100% | - | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | - |  |  | GP-17 |  | Thu 23/05/02 | Thu 12/11/09
5935 | 51001 | Deleted - Multiple TBF Stage 2 (43.064) CRs | - | 3 | Rel-5 | G1 | 2002-04-19 08:00 | 2002-11-22 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 23/05/02 | Thu 12/11/09
5936 | 50062 | Deleted - Multiple TBF Stage 3 (44.060) CRs | - | 3 | Rel-5 | G2 | 2002-04-19 08:00 | 2002-11-22 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 23/05/02 | Thu 12/11/09
5937 | 50206 | Deleted - Multiple TBF in A/Gb mode - Phase 1 – MS testing | - | 2 | Rel-5 | GP | 2002-06-24 08:00 | 2003-11-28 17:00 | 100% | GP-022098 | - | Ericsson | ingemar.backlund@era.ericsson.se | 08/08: duplicate UID_50106=-> 50206. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Wed 31/07/02 | Thu 12/11/09
5938 | 54101 | Deleted - MS conformance tests for Multiple TBF in A/Gb mode | - | 3 | Rel-5 | G4 | 2002-06-24 08:00 | 2003-11-28 17:00 | 100% | - | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Wed 31/07/02 | Thu 12/11/09
5939 | 2345 | Alignment of 3G functional split and Iu | GER3GAL | 1 | Rel-5 | GP | 2000-06-08 08:00 | 2003-12-19 17:00 | 100% | GP-021256 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone | - |  |  |  |  | Thu 01/02/01 | Thu 26/09/02
5940 | 2346 | GERAN user / control plane | GER3GAL-GUCOPL | 2 | Rel-5 | GP | 2000-08-07 08:00 | 2002-08-30 17:00 | 100% | GP-021255 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone | - |  |  |  |  | Thu 01/02/01 | Thu 13/02/03
5941 | 2347 | Alignment with UMTS bearer concept | - | 3 | Rel-5 | GP | 2000-08-07 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Thu 13/02/03
5942 | 50300 | Enhanced power control - for Alignment with UMTS bearer concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2001-08-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/09/01 | Wed 12/09/01
5943 | 2423 | Stage 2 - for Alignment with UMTS bearer concept | - | 4 | Rel-5 | GP | 2000-08-07 08:00 | 2001-06-29 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
5944 | 2348 | Adoption of the UTRAN PDCP | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2001-12-21 17:00 | 100% | - | - | - | - | Responsible is GERAN; RAN WG2 help may be needed. | - |  |  |  |  | Thu 01/02/01 | Fri 01/03/02
5945 | 50043 | Development of RLC / MAC | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Mon 13/01/03
5946 | 50044 | Development of GERAN RRC | - | 4 | Rel-5 | GP | 2001-06-22 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Wed 31/07/02
5947 | 50045 | Ciphering and integrity protection concept paper | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
5948 | 50046 | Multiple TBF or equivalent Concept paper | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-02-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
5949 | 50047 | Paging concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
5950 | 50048 | Dedicated Physical subchannels, includes traffic and control channels | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
5951 | 50049 | Iu support and broadcast concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
5952 | 50050 | Impact of using RLC instead of LAPDm concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-02-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
5953 | 50051 | Contention resolution, mobile station identity, and access concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
5954 | 50052 | PDCP concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-04-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
5955 | 50053 | Downlink delayed TBF release | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Thu 26/09/02
5956 | 50054 | Add transparent RLC Concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-02-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
5957 | 50055 | Handover concept | - | 4 | Rel-5 | GP | 2001-08-31 08:00 | 2002-02-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 23/05/02 | Tue 21/05/02
5958 | 2424 | Physical layer alignment with UMTS bearer concept | - | 3 | Rel-5 | GP | 2000-11-06 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
5959 | 2356 | PDTCH/TCH in 45.003 | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
5960 | 2357 | Control channels in 45.003 | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
5961 | 2358 | Receiver performance in 45.005 for PDTCH/TCH and control channels | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
5962 | 2359 | Iu rg interface | GER3GAL-Iurg | 2 | Rel-5 | GP,RP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | GP-010428 | - | Ericsson | Frank Muller | AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone | - |  |  |  |  | Thu 01/02/01 | Thu 13/02/03
5963 | 2425 | Inter BSS interface | - | 3 | Rel-5 | GP,RP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5964 | 2360 | Identification of requirements for Inter BSS interface | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5965 | 2361 | Stage 2 for Inter BSS interface | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5966 | 2362 | Adoption of relevant parts from Iur - for Inter BSS interface | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5967 | 2363 | Complementation with GERAN specifics - for Inter BSS interface | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5968 | 2364 | Stage 3 for Inter BSS interface | - | 4 | Rel-5 | GP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5969 | 2426 | Inter BSS-RNS interface | - | 3 | Rel-5 | GP,RP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5970 | 2365 | Identification of requirements for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5971 | 2366 | Stage 2 for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5972 | 2367 | Adoption of relevant parts from Iur - for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5973 | 2368 | Complementation with GERAN specifics - for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | 2002-01-30 13:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5974 | 2369 | Stage 3 for Inter BSS-RNS interface | - | 4 | Rel-5 | GP,R3 | 2002-01-30 13:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5975 | 2370 | Voice over GERAN PS and CS concept | - | 2 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | GP-011252 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
5976 | 2371 | Architecture for A, Iu cs and Iu ps | - | 3 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5977 | 2372 | Transcoder position/operation | - | 3 | Rel-5 | GP | 2000-11-06 08:00 | 2001-04-13 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5978 | 2373 | Handover for Voice over GERAN PS and CS | - | 3 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5979 | 2374 | RTP payload | - | 3 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 08/11/02
5980 | 2375 | Codec renegotiation concept | - | 3 | Rel-5 | GP,R3 | 2000-11-06 08:00 | 2002-03-29 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 08/11/02 | Fri 08/11/02
5981 | 2376 | LA | - | 3 | Rel-5 | GP | 2000-11-06 08:00 | 2001-04-13 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 08/11/02 | Fri 08/11/02
5982 | 2388 | Deleted - GERAN MS Conformance test for GERAN interface evolution | - | 2 | Rel-5 | GP | 2001-06-11 08:00 | 2003-12-19 17:00 | 100% | GP-021253 | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Thu 01/02/01 | Fri 12/12/08
5983 | 2389 | Deleted - MS test for GERAN interface evolution | - | 3 | Rel-5 | GP | 2001-06-11 08:00 | 2003-12-19 17:00 | 100% | - | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Thu 01/02/01 | Fri 12/12/08
5984 | 2390 | GERAN BSS Conformance test for GERAN interface evolution | - | 2 | Rel-5 | GP | 2000-06-08 08:00 | 2003-12-19 17:00 | 100% | GP-021254 | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  |  |  | Thu 01/02/01 | Fri 12/12/08
5985 | 2391 | Deleted - BSS test | - | 3 | Rel-5 | GP | 2000-06-08 08:00 | 2003-12-19 17:00 | 100% | - | - | - | - | Not started. Marked as stopped 12/2008 | - |  |  | GP-17 |  | Thu 01/02/01 | Fri 12/12/08
5986 | 2330 | GERAN support for IMS | GERIMS | 1 | Rel-5 | GP | 2000-05-01 08:00 | 2002-12-20 17:00 | 100% | GP-010420 | - | Nokia | Shkumbin Hamiti | AWS, Nokia, Ericsson, Nortel, Siemens, Motorola | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
5987 | 2331 | GERAN Header adaptation | GERIMS-HEADAPT | 2 | Rel-5 | GP,S2,RP | 2000-05-01 08:00 | 2002-12-20 17:00 | 100% | GP-010421 | - | Nokia | Shkumbin Hamiti | AWS, Nokia, Ericsson, Nortel, Siemens, Motorola | - |  |  |  |  | Thu 01/02/01 | Mon 13/01/03
5988 | 2332 | Definition of compression and removal modes for PDCP protocol | - | 3 | Rel-5 | GP,S2,RP | 2000-07-24 15:48 | 2000-09-01 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
5989 | 2333 | Conceptual description in stage 2 | - | 3 | Rel-5 | GP,S2,RP | 2000-05-01 08:00 | 2001-10-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
5990 | 2334 | Necessary changes on stage 3 regarding header removal | - | 3 | Rel-5 | GP,S2,RP | 2000-11-06 08:00 | 2002-12-20 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 13/01/03
5991 | 2335 | Deleted - GERAN Radio access bearer design for IMS | GERIMS-RABDES | 2 | Rel-5 | GP,S2,RP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | GP-010422 | - | Nokia | Shkumbin Hamiti | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-10 |  | Thu 01/02/01 | Fri 12/12/08
5992 | 2422 | Deleted - MuM control signalling for conversational multimedia services | - | 3 | Rel-5 | GP,S2,RP | 2000-11-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-10 |  | Thu 01/02/01 | Fri 12/12/08
5993 | 2431 | Deleted - Identification of requirements for MuM control signalling for conversational multimedia services | - | 4 | Rel-5 | GP,S2,RP | 2000-11-06 08:00 | 2002-02-08 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED | - |  |  | GP-08 |  | Tue 13/02/01 | Mon 13/01/03
5994 | 2337 | Deleted - Necessary modifications due to SIP | - | 4 | Rel-5 | GP,S2,RP | 2002-05-06 08:00 | 2002-06-28 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED | - |  |  | GP-10 |  | Thu 01/02/01 | Mon 13/01/03
5995 | 2341 | Deleted - GERAN MS Conformance test for support of IMS | GERIMS-MSconf | 2 | Rel-5 | GP | 2001-06-11 08:00 | 2002-12-20 17:00 | 100% | GP-010424 | - | Nokia | Shkumbin Hamiti | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
5996 | 2342 | Deleted - MS test for support of IMS | - | 3 | Rel-5 | G4 | 2001-06-11 08:00 | 2002-12-20 17:00 | 100% | - | - | - | - | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
5997 | 2343 | Deleted - GERAN BTS Conformance test for support of IMS | GERIMS-BTSconf | 2 | Rel-5 | GP | 2001-06-11 08:00 | 2002-12-20 17:00 | 100% | GP-010425 | - | Nokia | Shkumbin Hamiti | TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Thu 01/02/01 | Fri 12/12/08
5998 | 54001 | MS Conformance Testing of Dual Transfer Mode | MSCTDTM | 1 | Rel-5 | G4,G5 | 2002-11-11 08:00 | 2003-02-07 17:00 | 100% | GP-023236 | - | Vodafone | Dave Fox | Needed to complete DTM (R99) | - |  |  |  |  | Mon 13/01/03 | Thu 13/02/03
5999 | 32033 | Handling of early Ues | LATE_UE | 1 | Rel-5 | S2 | 2000-01-03 08:00 | 2003-06-27 17:00 | 100% | SP-030125 | - | - | - | - | - |  |  |  |  | Wed 15/01/03 | Wed 15/01/03
6000 | 32031 | Feasibility Study on Handling of early Ues | - | 2 | Rel-5 | S2 | 2002-10-07 08:00 | 2002-12-13 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 15/01/03 | Wed 15/01/03
6001 | 32032 | Stage 2 for Handling of early Ues | - | 2 | Rel-5 | S2 | 2003-01-06 08:00 | 2003-06-27 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 15/01/03 | Wed 23/07/03
6002 | 22001 | FS for the Early Mobile Handling in UTRAN | FSEarlyUE | 2 | Rel-5 | R2 | 2002-09-09 08:00 | 2003-06-06 17:00 | 100% | - | - | Vodafone | alan.law@vodafone.com | - | - |  |  |  |  | Mon 16/09/02 | Fri 04/07/03
6003 | 96 | Note: Stage 3 RAN part not shown | - | 2 | Rel-5 | RP | 2000-01-03 08:00 | 2000-01-03 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 09/10/00 | Thu 11/10/01
6004 | 0 | Release 4 Features | - | 1 | Rel-4 | NP,GP,RP,SP,TP | 2000-01-03 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 11/07/08 | Tue 09/02/10
6005 | 1861 | Miscellaneous UE Conformance Testing Activities | MISTST1 | 1 | Rel-4 | T1 | 2001-04-02 08:00 | 2004-12-01 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 14/09/00 | Mon 13/01/03
6006 | 1862 | Optimization of Test Time, RF Aspects (FDD) | MISTST1-OpFDD | 2 | Rel-4 | T1 | 2001-09-24 08:00 | 2003-09-03 17:00 | 100% | TP-030052 | - | - | - | It is believed that the current R99 test spec. can be optimised for faster overall test times. Marked as stopped 12/2008 (was 70% complete) | 34.121 |  |  |  |  | Thu 14/09/00 | Fri 12/12/08
6007 | 1863 | Optimization of Test Time, RF Aspects (TDD) | MISTST1-OpTDD | 2 | Rel-4 | T1 | 2001-09-24 08:00 | 2003-09-03 17:00 | 100% | TP-030052 | - | - | - | It is believed that the current R99 test spec. can be optimised for faster overall test times | 34.122 |  |  |  |  | Thu 14/09/00 | Fri 12/12/08
6008 | 1907 | Extensions to R99 Test cases | MISTST1-Ext | 2 | Rel-4 | T1 | 2001-04-02 08:00 | 2003-12-02 17:00 | 100% | TP-030052 | - | - | - | Further test coverage of the R99 specification to cover supplementry services. Marked as stopped 12/2008 (was 70% complete) | 34.123 p 1,2 |  |  |  |  | Thu 24/08/00 | Fri 12/12/08
6009 | 2564 | Extension to R99 Test cases - TTCN | - | 2 | Rel-4 | T1 | 2002-06-28 08:00 | 2004-03-03 17:00 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | - |  |  |  |  | Fri 01/06/01 | Fri 12/12/08
6010 | 2565 | Creation of R99 TCs for TDD - prose | MISTST1-TDD | 2 | Rel-4 | T1 | 2001-10-01 08:00 | 2004-07-01 17:00 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 50% complete) | 34.123-1 |  |  |  |  | Fri 01/06/01 | Fri 12/12/08
6011 | 2566 | Deleted - Creation of R99 TCs for TDD - TTCN | - | 2 | Rel-4 | T1 | 2002-09-03 08:00 | 2004-12-01 17:00 | 100% | TP-030052 | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-26 |  | Fri 01/06/01 | Fri 12/12/08
6012 | 1908 | Deleted - Review all other work items for impact on new or exiting 34 series specs. | - | 2 | Rel-4 | T1 | 2002-07-02 08:00 | 2002-12-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.121,122,123,125 |  |  | TP-18 |  | Wed 06/09/00 | Fri 12/12/08
6013 | 1340 | Real Time Facsimile | FAX-RT | 1 | Rel-4 | S1 | 2000-02-22 08:00 | 2000-06-23 17:00 | 100% | SP-000169 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Sat 01/04/00
6014 | 1341 | Real Time Fax | - | 2 | Rel-4 | S2 | 2000-02-22 08:00 | 2000-06-23 17:00 | 100% | SP-000169 | - | - | - | postponed from R99 to R00, SP-000169 | - |  |  |  |  | Sun 09/04/00 | Wed 15/11/00
6015 | 1808 | Terminal capabilities, AT commands | - | 3 | Rel-4 | T2 | 2000-02-22 08:00 | 2000-06-23 17:00 | 100% | - | - | - | - | - | 21.904, 27.007 |  |  |  |  | Thu 14/09/00 | Sat 01/04/00
6016 | 1343 | Signalling aspects (e.g. ICM) | - | 3 | Rel-4 | N1 | 2000-02-22 08:00 | 2000-06-23 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Wed 15/11/00
6017 | 1648 | Service provision | - | 3 | Rel-4 | N3 | 2000-02-22 08:00 | 2000-06-23 17:00 | 100% | - | - | - | - | - | 23.146 |  |  |  |  | Tue 08/08/00 | Wed 15/11/00
6018 | 1345 | Review whether service/stage 1 aspects need to be aligned | - | 3 | Rel-4 | S1 | 2000-04-14 08:00 | 2000-06-23 17:00 | 100% | SP-000169 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Sat 01/04/00
6019 | 1346 | Review whether architecture/stage 2 aspects need to be aligned | - | 3 | Rel-4 | S2 | 2000-04-14 08:00 | 2000-06-23 17:00 | 100% | SP-000169 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Sat 01/04/00
6020 | 1539 | Transparent End-to-End PS mobile streaming application | PSTREAM | 1 | Rel-4 | S4 | 2000-04-03 08:00 | 2001-03-21 17:00 | 100% | SP-000345 | - | - | - | - | 26.233, 26.234 |  |  |  |  | Fri 28/07/00 | Tue 20/03/01
6021 | 1818 | Multimedia Messaging | MMS4 | 1 | Rel-4 | T2,S1 | 2000-02-22 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | Acronym changed from "MMS, Rel-4" | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
6022 | 136 | Definition of service requirements for Multimedia Messaging | - | 2 | Rel-4 | S1 | 2000-02-22 08:00 | 2000-05-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 06/04/00 | Sat 01/04/00
6023 | 1819 | Review of definition of service requirements | - | 2 | Rel-4 | T2 | 2000-06-01 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | - | - | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Wed 08/07/09
6024 | 1820 | Technical Realisation | - | 2 | Rel-4 | T2 | 2000-04-10 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Wed 08/07/09
6025 | 1821 | Review of definition of reference Achitecture model | - | 3 | Rel-4 | T2 | 2000-04-10 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Wed 08/07/09
6026 | 1822 | Fulfill Requirements of Stage 1 | - | 3 | Rel-4 | T2 | 2000-04-10 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | e.g. minimum set of media formats, media format conversion, personalization of MMS. | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Wed 08/07/09
6027 | 1823 | Definition of MMS primitives in Stage 2 | - | 3 | Rel-4 | T2 | 2000-04-10 08:00 | 2001-03-14 17:00 | 100% | TP-000078 | - | Siemens | Josef.Laumen@SAL.SIEMENS.DE | - | 22.140, 23.140 |  |  |  |  | Thu 14/09/00 | Wed 08/07/09
6028 | 1541 | Transcoder-Free Operation | TrFO | 1 | Rel-4 | N4,S2,N1 | 2000-01-03 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | Lead given to CN4 from CN | - |  |  |  |  | Fri 28/07/00 | Mon 25/03/02
6029 | 112 | Out-of-Band Transcoder Control solution | TrFO-OoBTC | 2 | Rel-4 | N4 | 2000-01-03 08:00 | 2001-03-30 17:00 | 100% | N4-000531 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | - | - |  |  |  |  | Thu 06/04/00 | Wed 08/07/09
6030 | 1512 | implementation in UTRAN | TrFO-OoBTC-UTRAN | 3 | Rel-4 | R3 | 2000-09-11 08:00 | 2001-03-30 17:00 | 100% | - | - | Siemens | Alexander Vesely | moved according to NP-000575 | 25.401, 25.410, 25.413, 25.415, 23.153 |  |  |  |  | Wed 26/07/00 | Tue 20/03/01
6031 | 896 | Impact on architecture, Principles and Terminology | - | 3 | Rel-4 | S2 | 2000-01-03 08:00 | 2000-10-20 17:00 | 100% | - | - | - | - | e.g. study cascading TrFO/TFO/TrFO | - |  |  |  |  | Thu 06/04/00 | Wed 13/12/00
6032 | 1657 | Codec Negotiation between UE and MSC | - | 3 | Rel-4 | N1 | 2000-08-14 08:00 | 2001-02-02 17:00 | 100% | - | - | Motorola | Andrew Howell | the link to NP-000085has been deleted because refering to a R99 status sheet | 24.008, 23.009, 23.108, (29.002) |  |  |  |  | Tue 08/08/00 | Mon 04/12/00
6033 | 115 | Codec Negotiation inter MSC | - | 3 | Rel-4 | N4 | 2000-07-03 08:00 | 2000-12-22 17:00 | 100% | - | - | - | - | Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex + list of open issues | - |  |  |  |  | Thu 06/04/00 | Mon 12/03/01
6034 | 894 | Bearer establishment inter MSC | - | 3 | Rel-4 | N4 | 2000-07-03 08:00 | 2000-12-22 17:00 | 100% | NP-000127 | - | - | - | Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex. | 23.153 |  |  |  |  | Thu 06/04/00 | Mon 12/03/01
6035 | 905 | Speech Transcoder: Location and Control at the UMTS Core Network Border | TrFO-STLC | 2 | Rel-4 | S2 | 2000-04-10 08:00 | 2000-09-29 17:00 | 100% | - | - | - | - | WI description and Tdoc S2-99352 | - |  |  |  |  | Thu 06/04/00 | Sat 01/04/00
6036 | 124 | Transcoder at Edge | - | 3 | Rel-4 | NP | 2000-04-10 08:00 | 2000-09-29 17:00 | 100% | - | - | - | - | WI description and Tdoc S2-99352 | - |  |  |  |  | Thu 06/04/00 | Mon 12/03/01
6037 | 2310 | GERAN improvements 1 (Gb over IP) | GEIMP1 | 1 | Rel-4 | GP | 2000-05-09 08:00 | 2001-03-19 17:00 | 100% | GP-000433 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
6038 | 2311 | Gb over IP (Ip-fication of Gb) | GbIP | 2 | Rel-4 | GP | 2000-05-09 08:00 | 2001-03-19 17:00 | 100% | GP-000434 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
6039 | 2312 | Concept of Gb over IP (Ip-fication of Gb) | - | 3 | Rel-4 | GP | 2000-05-09 08:00 | 2000-11-10 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
6040 | 2313 | Changes to 08.16, 08.18 | - | 3 | Rel-4 | GP | 2000-05-09 08:00 | 2001-03-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
6041 | 2314 | GERAN improvements 2 (NACC) | GEIMP2 | 1 | Rel-4 | GP | 2000-11-06 08:00 | 2003-06-10 17:00 | 100% | GP-012812 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 10/12/01
6042 | 2315 | Gb enhancements | Gben | 2 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | GP-000436 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
6043 | 2316 | Intra BSC NACC (Network Assisted Cell Change) | - | 3 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
6044 | 2420 | Concept | - | 4 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
6045 | 2317 | Changes in 03.64 | - | 4 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
6046 | 2318 | Changes in 04.60 | - | 4 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
6047 | 2319 | Changes in 44.008 | - | 4 | Rel-4 | GP | 2000-11-06 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 12/09/01
6048 | 50030 | MS conformance test for Intra BSC NACC | GEIMP2-Msconf | 2 | Rel-4 | GP | 2001-11-30 08:00 | 2003-06-10 17:00 | 100% | GP-012811 | - | - | - | - | - |  |  |  |  | Mon 10/12/01 | Thu 13/02/03
6049 | 50299 | Changes in 51.010 | - | 3 | Rel-4 | G5,G4 | 2001-11-30 08:00 | 2003-06-10 17:00 | 100% | - | - | - | - | az 05/08: duplicated UID_50099 => 50299. Marked as closed 12/2008 (was marked 50% complete) | - |  |  |  |  | Thu 23/05/02 | Tue 06/05/08
6050 | 2324 | GERAN improvements 4 (Delayed TBF) | GEIMP4 | 1 | Rel-4 | GP | 2001-01-15 08:00 | 2001-06-08 17:00 | 100% | GP-010363 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
6051 | 2325 | Gb enhancements 2 | GEIMP4-Gben2 | 2 | Rel-4 | GP | 2001-01-15 08:00 | 2001-06-08 17:00 | 100% | GP-010363 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 21/05/02
6052 | 2429 | Stage 2 for Gb enhancements 2 | - | 3 | Rel-4 | GP | 2001-01-15 08:00 | 2001-06-08 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 13/02/01 | Fri 01/03/02
6053 | 2421 | Stage 3 (changes in 44.060) | - | 3 | Rel-4 | G2 | 2001-01-15 08:00 | 2001-04-06 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 01/03/02
6054 | 2327 | Definition of enhanced countdown procedure | - | 4 | Rel-4 | G2 | 2001-01-15 08:00 | 2001-04-06 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 01/03/02
6055 | 2328 | Definition of enhanced TBF release procedure | - | 4 | Rel-4 | G2 | 2001-01-15 08:00 | 2001-04-06 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 01/03/02
6056 | 2329 | Definition of USF=FREE type polling mechanism on PDCH | - | 4 | Rel-4 | G2 | 2001-01-15 08:00 | 2001-04-06 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Fri 01/03/02
6057 | 1222 | Low Chip Rate TDD option | LCRTDD | 1 | Rel-4 | R1 | 2000-07-19 08:00 | 2003-12-02 17:00 | 100% | - | - | CWTS | G. Yang | - | - |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
6058 | 1223 | Physical layer for Low Chip Rate TDD option | LCRTDD-Phys | 2 | Rel-4 | R1 | 2000-07-19 08:00 | 2001-03-30 17:00 | 100% | - | - | CWTS | G. Yang | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
6059 | 1224 | Layer 2 and layer 3 protocol aspects | LCRTDD-L23 | 2 | Rel-4 | R2 | 2000-07-19 08:00 | 2001-03-30 17:00 | 100% | - | - | CWTS | Y. Liu | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
6060 | 1225 | RF radio transmission/reception, system performance requirements and conformance testing | LCRTDD-RF | 2 | Rel-4 | R4 | 2000-08-14 08:00 | 2001-03-30 17:00 | 100% | - | - | CWTS | D. Zhang | - | - |  |  |  |  | Wed 26/04/00 | Fri 30/03/01
6061 | 1227 | UE radio access capability | LCRTDD-UErac | 2 | Rel-4 | R2 | 2000-08-14 08:00 | 2001-03-30 17:00 | 100% | - | - | CWTS | Y. Liu | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
6062 | 1228 | Iub/Iur protocol aspects - for Low Chip Rate TDD option | LCRTDD-IubIur | 2 | Rel-4 | R3 | 2000-08-14 08:00 | 2001-03-30 17:00 | 100% | - | - | CWTS | Y. Liu | - | - |  |  |  |  | Wed 26/04/00 | Tue 20/03/01
6063 | 2262 | Low chiprate TDD interworking with GERAN | - | 2 | Rel-4 | GP | 2000-09-01 08:00 | 2001-01-19 17:00 | 100% | GP-000432 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
6064 | 2263 | Handover and Cell Selection / Reselection to UTRA 1.28 Mcps TDD | - | 3 | Rel-4 | GP | 2000-09-01 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
6065 | 2103 | Conformance Test Aspects - Low Chip Rate TDD | - | 2 | Rel-4 | T1 | 2001-09-17 08:00 | 2003-12-02 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 01/11/00 | Sat 01/04/00
6066 | 2217 | Testing Layer 2 and layer 3 protocol aspects | - | 3 | Rel-4 | T1 | 2001-09-17 08:00 | 2003-07-02 17:00 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 60% complete) | 34.123-1, 34.123-2 |  |  |  |  | Thu 16/11/00 | Fri 14/03/03
6067 | 2562 | Deleted - Testing Layer 2 and layer 3 protocol aspects - TTCN | - | 3 | Rel-4 | T1 | 2002-12-03 08:00 | 2003-12-02 17:00 | 100% | TP-030052 | - | - | - | Marked as stopped 12/2008 | 34.123-3 |  |  | TP-22 |  | Thu 31/05/01 | Fri 14/03/03
6068 | 2218 | Testing RF Radio Transmission and Reception | - | 3 | Rel-4 | T1 | 2001-09-17 08:00 | 2002-06-28 17:00 | 100% | TP-030052 | - | - | - | duration set to 6 months (was 0), finish date set | - |  |  |  |  | Thu 16/11/00 | Mon 13/01/03
6069 | 1322 | Enable bearer independent CS architecture | CSSPLIT | 1 | Rel-4 | S2,N3,N4 | 2000-01-03 08:00 | 2002-03-01 17:00 | 100% | SP-000288 | - | Siemens | Alexander Milinski | - | - |  |  |  |  | Sun 09/04/00 | Sat 06/08/11
6070 | 1323 | Enable bearer-independent call control | - | 2 | Rel-4 | N4 | 2000-01-03 08:00 | 2001-08-16 17:00 | 100% | N4-000512 | - | Ericsson | Heinz-Peter.Keutmann@eed.ericsson.se | DAB 12.12.01 should be 100% hence closed | - |  |  |  |  | Sun 09/04/00 | Thu 24/01/02
6071 | 1516 | Architecture and Stage 2 description | - | 3 | Rel-4 | S2 | 2000-01-03 08:00 | 2000-09-08 17:00 | 100% | - | - | - | - | R00 stage 2 at least 80 % complete in TSGS #8 21.-23.6.2000 | 23.002 |  |  |  |  | Fri 28/07/00 | Sat 01/04/00
6072 | 1325 | Standardisation of protocols (control & user planes) over Nb interface | - | 3 | Rel-4 | N3 | 2001-01-02 08:00 | 2001-03-30 17:00 | 100% | N4-000512 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Wed 30/05/01
6073 | 1326 | Standardisation of protocols over reference points between MSC server and Gateway MSC server | - | 3 | Rel-4 | N4 | 2000-09-25 08:00 | 2001-03-23 17:00 | 100% | N4-000512 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Mon 12/03/01
6074 | 1616 | Standardisation of detailed stage 2 description | - | 3 | Rel-4 | N4 | 2000-07-17 08:00 | 2001-03-23 17:00 | 100% | N4-000512 | - | - | - | - | - |  |  |  |  | Tue 08/08/00 | Mon 12/03/01
6075 | 1327 | Bearer control between MSC server and MGW | - | 3 | Rel-4 | N4 | 2000-09-01 08:00 | 2001-08-16 17:00 | 100% | N4-000512 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Mon 12/03/01
6076 | 1328 | stage 3 - protocol issues | - | 4 | Rel-4 | N4 | 2000-09-01 08:00 | 2001-08-16 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Mon 12/03/01
6077 | 1329 | stage 3 - parameter value issues | - | 4 | Rel-4 | N3 | 2001-01-02 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Wed 30/05/01
6078 | 2052 | Deleted - Conformance Test Aspects - Enable bearer independent CS architecture | CSSPLIT-TEST | 2 | Rel-4 | T1 | 2001-03-05 08:00 | 2002-03-01 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-15 |  | Mon 09/10/00 | Sat 01/04/00
6079 | 1445 | MExE enhancements Rel-4 | MEXE | 1 | Rel-4 | T2,S3 | 2000-01-03 08:00 | 2001-12-14 17:00 | 100% | TP-030052 | - | - | - | - | - |  |  |  |  | Sun 09/04/00 | Fri 14/09/01
6080 | 1447 | MExE Security Analysis Activity | MEXE-SEC | 2 | Rel-4 | S3,T2 | 2000-02-22 08:00 | 2001-12-14 17:00 | 100% | SP-010327 | - | BT | Andrew.Myers@bt.com | SP#12 updated WID | - |  |  |  |  | Tue 18/04/00 | Sat 06/08/11
6081 | 2045 | Stage 3 for MExE Security | - | 3 | Rel-4 | S3 | 2000-07-17 08:00 | 2001-12-14 17:00 | 100% | SP-010327 | - | BT | Andrew.Myers@bt.com | - | 21.133, 33.102 |  |  |  |  | Mon 09/10/00 | Sat 06/08/11
6082 | 1448 | Terminal aspects for MExE Security | - | 3 | Rel-4 | T2 | 2000-02-22 08:00 | 2000-12-15 17:00 | 100% | SP-010327 | - | BT | Andrew.Myers@bt.com | - | 23.057 |  |  |  |  | Sun 09/04/00 | Tue 13/03/01
6083 | 1810 | MExE Rel-4 Improvements and Investigations | MEXE-ENHANC | 2 | Rel-4 | T2 | 2000-01-03 08:00 | 2000-12-15 17:00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.057, 23.057 |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
6084 | 1812 | 3rd MExE classmark | - | 3 | Rel-4 | T2 | 2000-01-03 08:00 | 2000-12-15 17:00 | 100% | - | - | Motorola | Mark Cataldo | Additional features for MExE R2000 | 22.057, 23.057 |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
6085 | 1814 | FS on Secure download mechanism and capabilities to support SDR concepts | - | 3 | Rel-4 | T2 | 2000-02-07 08:00 | 2000-12-15 17:00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.057, 23.057 |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
6086 | 1815 | FS on Support of MP3/MPEG4 content | - | 3 | Rel-4 | T2 | 2000-02-07 08:00 | 2000-12-15 17:00 | 100% | - | - | Motorola | Mark Cataldo | - | 22.057, 23.057 |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
6087 | 1631 | Tandem Free aspects for 3G and between 2G and 3G systems | TFO | 1 | Rel-4 | S4 | 2000-02-22 08:00 | 2001-06-15 17:00 | 100% | - | - | - | - | RAN and CN to verify no problems for GSM terminals roaming in 3G R99 | - |  |  |  |  | Tue 08/08/00 | Fri 30/03/01
6088 | 1632 | Tandem Free AMR | TFO-AMR | 2 | Rel-4 | S4 | 2000-02-22 08:00 | 2001-06-15 17:00 | 100% | - | - | - | - | RAN and CN to verify UMTS_AMR_2 support | - |  |  |  |  | Tue 08/08/00 | Fri 30/03/01
6089 | 130 | Specification of Tandem Free AMR | - | 3 | Rel-4 | S4 | 2000-02-22 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | 28.062 |  |  |  |  | Thu 06/04/00 | Tue 20/03/01
6090 | 907 | Impact of Tandem Free AMR on: | - | 3 | Rel-4 | NP | 2001-01-08 08:00 | 2001-06-15 17:00 | 100% | - | - | - | - | "Implementation" changed to "Impact on:" by A. Sultan (for better wording) | - |  |  |  |  | Thu 06/04/00 | Sat 01/04/00
6091 | 131 | CN | - | 4 | Rel-4 | NP | 2001-03-26 08:00 | 2001-06-15 17:00 | 100% | - | - | - | - | RAN and CN to verify UMTS_AMR_2 support | - |  |  |  |  | Thu 06/04/00 | Fri 30/03/01
6092 | 132 | GERAN | - | 4 | Rel-4 | GP | 2001-01-08 08:00 | 2001-04-06 17:00 | 100% | - | - | - | - | End date Modified from June to March to have it in Rel4 | - |  |  |  |  | Thu 06/04/00 | Thu 28/02/02
6093 | 2230 | Advanced Speech Call Items enhancements_Rel-4 | ASCI4 | 1 | Rel-4 | N1 | 2000-12-03 08:00 | 2002-03-14 17:00 | 100% | NP-000730 | - | Nortel | sonia.garapaty@nortelnetworks.com | Approved at CN#10. Acronym changed from ASCI, Rel-4 | - |  |  |  |  | Mon 11/12/00 | Tue 24/03/15
6094 | 2232 | Stage 2 for Advanced Speech Call Items enhancements_Rel-4 (ASCI) | - | 2 | Rel-4 | N4 | 2000-12-03 08:00 | 2002-03-14 17:00 | 100% | - | - | Sagem | Vivien Perlic | CN4#11 30/11/02: no inputs received in CN4 | 23.067, 24.067 |  |  |  |  | Mon 11/12/00 | Wed 12/12/01
6095 | 2231 | Stages 2 and 3 on A interface | - | 2 | Rel-4 | N1 | 2000-12-03 08:00 | 2001-03-23 17:00 | 100% | - | - | Nortel | sonia.garapaty@nortelnetworks.com | - | 44.068, 44.069, 24.008 |  |  |  |  | Mon 11/12/00 | Wed 30/05/01
6096 | 2403 | 700 MHz spectrum support | 700SS | 1 | Rel-4 | GP | 2000-01-03 08:00 | 2002-12-20 17:00 | 100% | GP-000449 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 13/01/03
6097 | 2404 | GERAN support for the 700 MHz band | - | 2 | Rel-4 | GP | 2000-01-03 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
6098 | 2405 | Signalling support | - | 3 | Rel-4 | GP | 2000-01-03 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
6099 | 2406 | Physical layer definitions - for GERAN support for the 700 MHz band | - | 3 | Rel-4 | GP | 2000-01-03 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
6100 | 2407 | Receiver performance and RF budget | - | 3 | Rel-4 | GP | 2000-01-03 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Tue 13/02/01
6101 | 2408 | GERAN MS Conformance test for 700 MHz band | - | 2 | Rel-4 | GP | 2001-04-02 08:00 | 2001-11-30 17:00 | 100% | GP-000451 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Wed 31/07/02
6102 | 2410 | GERAN BTS Conformance test for 700 MHz band | - | 2 | Rel-4 | GP | 2001-04-02 08:00 | 2002-12-20 17:00 | 100% | GP-000452 | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 13/01/03
6103 | 2463 | Operator Determined Barring for Packet Oriented Services | ODB | 1 | Rel-4 | NP | 2000-06-01 08:00 | 2001-03-19 17:00 | 100% | NP-010089 | - | NEC | Toshiyuki Tamura (tamurato@aj.jp.nec.com) | Completed WI missing from the P-plan Added for tracking | - |  |  |  |  | Tue 20/03/01 | Tue 20/03/01
6104 | 2546 | UMTS QoS Architecture for PS Domain | QoSPS | 1 | Rel-4 | S2,S5,R3,GP | 2000-01-03 08:00 | 2002-11-27 17:00 | 100% | SP-010342 | - | Ericsson | Ina.widegren@era.ericsson.se | - | - |  |  |  |  | Fri 08/06/01 | Thu 24/01/02
6105 | 2548 | Architecture | - | 2 | Rel-4 | S2 | 2000-06-05 08:00 | 2001-01-03 17:00 | 100% | - | - | - | - | - | 23.107 |  |  |  |  | Fri 08/06/01 | Thu 24/01/02
6106 | 2550 | Charging and OAM&P for QoS Management | QoSPS-OAM | 2 | Rel-4 | S5 | 2001-09-21 08:00 | 2002-06-28 17:00 | 100% | SP-010461 | - | - | - | - | 32-series |  |  |  |  | Fri 08/06/01 | Fri 21/06/02
6107 | 1681 | RAB Quality of Service (re)Negotiation over Iu | QoSPS-MAPEND-RABQoS | 2 | Rel-4 | R3 | 2000-08-21 08:00 | 2001-03-23 17:00 | 100% | - | - | Ericsson | anders.molander@ericsson.com | - | 25.413 |  |  |  |  | Wed 26/07/00 | Fri 16/02/01
6108 | 1991 | RAB Quality of Service Negotiation over Iu | QoSPS-MAPEND-RABQoS-Negot | 3 | Rel-4 | R3 | 2000-08-21 08:00 | 2001-03-23 17:00 | 100% | - | - | Ericsson | anders.molander@ericsson.com | - | - |  |  |  |  | Tue 26/09/00 | Mon 12/03/01
6109 | 2456 | RAB Quality of Service Negotiation over Iu during relocation | QoSPS-MAPEND-RABQoS-NegotReloc | 3 | Rel-4 | R3 | 2001-03-02 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 09/03/01 | Mon 12/03/01
6110 | 1992 | RAB Quality of Service Re-Negotiation over Iu | QoSPS-MAPEND-RABQoS-ReNegot | 3 | Rel-4 | R3 | 2000-09-25 08:00 | 2001-03-23 17:00 | 100% | - | - | Motorola | S. Irwin | - | - |  |  |  |  | Tue 26/09/00 | Mon 12/03/01
6111 | 1553 | GERAN QoS Aspects - Handovers: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN and SRNS relocation or possibly other mechanisms | GERQoS | 2 | Rel-4 | GP | 2000-01-03 08:00 | 2001-11-30 17:00 | 100% | GP-010431 | - | - | - | - | - |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
6112 | 2306 | Handover Concept for the PS domain | - | 3 | Rel-4 | GP | 2000-01-03 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 10/12/01
6113 | 2309 | Stable RT handover report 25.936 including header removal | - | 4 | Rel-4 | GP | 2000-01-03 08:00 | 2000-01-19 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 08/02/01 | Thu 24/01/02
6114 | 2307 | Update of stage 2 | - | 4 | Rel-4 | GP | 2000-01-03 08:00 | 2001-02-13 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Thu 24/01/02
6115 | 2308 | Update of relevant stage 3 specs -> RRC | - | 4 | Rel-4 | G2 | 2000-01-03 08:00 | 2001-11-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 01/02/01 | Mon 10/12/01
6116 | 50010 | Deleted - GERAN MS Conformance test for inter-system and intra-system Packet data real-time Handover | GERQoS-Mstest | 2 | Rel-4 | G4,R3 | 2001-08-31 08:00 | 2002-11-27 17:00 | 100% | GP-012287 | - | - | - | Still exist? To be clarified by GERAN4/5. Marked as stopped 12/2008 | - |  |  | GP-12 |  | Wed 19/09/01 | Fri 12/12/08
6117 | 50011 | Deleted - Handover for the PS domain | - | 3 | Rel-4 | G4,R3 | 2001-08-31 08:00 | 2002-11-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Wed 19/09/01 | Fri 12/12/08
6118 | 50012 | Deleted - Stable RT handover report 25.936 including header removal | - | 4 | Rel-4 | G4,R3 | 2001-08-31 08:00 | 2002-11-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Wed 19/09/01 | Fri 12/12/08
6119 | 50013 | Deleted - Update of stage 2 | - | 4 | Rel-4 | G4,R3 | 2001-08-31 08:00 | 2002-11-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Wed 19/09/01 | Fri 12/12/08
6120 | 50014 | Deleted - Update of relevant stage 3 specs | - | 4 | Rel-4 | G4,R3 | 2001-08-31 08:00 | 2002-11-27 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | GP-12 |  | Wed 19/09/01 | Fri 12/12/08
6121 | 1685 | PS-domain handover for real-time services | QoSPS-PSdoRTS | 2 | Rel-4 | R3 | 2000-08-28 08:00 | 2001-03-30 17:00 | 100% | - | - | Nokia | atte.lansisalmi@nokia.com | - | - |  |  |  |  | Wed 19/04/00 | Mon 12/03/01
6122 | 2554 | Deleted - RAB QoS Renegotiation at Relocation | - | 2 | Rel-4 | R3 | 2001-01-03 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | 25.851, 25.946 |  |  | RP-11 |  | Fri 08/06/01 | Fri 12/12/08
6123 | 1993 | (Small) Technical Enhancements and Improvements for Rel-4 | TEI4 | 1 | Rel-4 | SP,CP,RP,GP | 2000-01-03 08:00 | 2000-01-03 08:00 | 100% | - | - | - | - | "Joker" WI, to be used for a Rel 4 CR not related to any feature and with very limited impact on the system | - |  |  |  |  | Tue 26/09/00 | Sat 01/04/00
6124 | 25017 | Test - (Small) Technical Enhancements and Improvements for Rel-4 | TEI4_Test | 1 | Rel-4 | R5,T1 | 2000-01-03 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | "Joker" WI, to be used for small modifications applicable to Rel 4 conformance testing. Moved in from the Stoyan/Testing WP | - |  |  |  |  | Tue 21/03/06 | Tue 06/05/08
6125 | 400002 | Rel-4 Evolutions of the transport in the UTRAN | ETRAN | 1 | Rel-4 | RP | 2000-08-21 08:00 | 2002-08-23 17:00 | 100% | - | - | Alcatel | Francois Courau | - | - |  |  |  |  | Fri 31/03/00 | Fri 17/11/00
6126 | 12 | QoS optimization for AAL2 connections over Iub and Iur interfaces | ETRAN-QoSAAL2 | 2 | Rel-4 | R3 | 2000-08-21 08:00 | 2001-03-30 17:00 | 100% | - | - | Japan Telecom | T. Yoshimura | - | - |  |  |  |  | Fri 31/03/00 | Tue 20/03/01
6127 | 1995 | Transport bearer modification procedure on Iub, Iur, and Iu | ETRAN-MigrMod | 2 | Rel-4 | R3 | 2000-10-02 08:00 | 2001-03-30 17:00 | 100% | - | - | Japan Telecom | T. Yoshimura | - | - |  |  |  |  | Tue 26/09/00 | Tue 20/03/01
6128 | 401834 | Deleted - Conformance Test Aspects of Rel-4 evolutions of the transport in UTRAN | - | 2 | Rel-4 | T1 | 2002-02-25 08:00 | 2002-08-23 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 14/09/00 | Tue 13/10/09
6129 | 2208 | Deleted - Testing RAB support enhancements | CT-RABS? | 3 | Rel-4 | T1 | 2002-02-25 08:00 | 2002-08-23 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.108, 34. 121, 34.122, 34.123 p 1,2, 34.123 pt 3 |  |  | TP-17 |  | Thu 16/11/00 | Tue 13/10/09
6130 | 400004 | Rel-4 Evolutions of the transport in the CN | CNTRSP | 1 | Rel-4 | N4,N1,N2,S2 | 2000-05-29 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Tue 20/03/01
6131 | 859 | IP Transport of CN protocols (e.g. CAP, MAP) | SS7IP | 2 | Rel-4 | N4 | 2000-12-07 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 26/04/00 | Tue 20/03/01
6132 | 1679 | Stage 3 for IP Transport of CN protocols (e.g. CAP, MAP) | - | 3 | Rel-4 | N4 | 2000-12-07 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 25/08/00 | Tue 13/03/01
6133 | 2018 | CAP | - | 4 | Rel-4 | N2 | 2000-12-07 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 25/08/00 | Tue 13/03/01
6134 | 2019 | MAP | - | 4 | Rel-4 | N4 | 2000-12-07 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | 29.202 |  |  |  |  | Fri 25/08/00 | Mon 12/03/01
6135 | 2253 | BSSAP+ | SS7IP-BSSAP+ | 4 | Rel-4 | N1 | 2001-01-15 08:00 | 2001-03-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 08/02/01 | Mon 12/03/01
6136 | 1513 | FS on Transport and control separation in the PS CN domain | - | 2 | Rel-4 | S2 | 2000-05-29 08:00 | 2001-03-23 17:00 | 100% | SP-000293 | - | Ericsson | Juan-Antonio.Ibanez@eed.ericsson.se | - | - |  |  |  |  | Fri 28/07/00 | Wed 19/09/01
6137 | 1615 | Architectural impacts | - | 3 | Rel-4 | S2 | 2000-05-29 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 08/08/00 | Thu 08/02/01
6138 | 401216 | Rel-4 Improvements of Radio Interface | - | 1 | Rel-4 | RP | 2000-07-10 08:00 | 2003-03-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Thu 11/10/01
6139 | 1509 | UTRA repeater specification (master) | RInImp-REP | 2 | Rel-4 | R4 | 2000-07-10 08:00 | 2001-03-21 17:00 | 100% | - | - | Mikom, Allgon | T. Kummetz, Mikom; Alf Ahlström, Allgon | - | - |  |  |  |  | Wed 26/07/00 | Fri 30/03/01
6140 | 1994 | DSCH power control improvement in soft handover | RInImp-DSCHsho | 2 | Rel-4 | R1 | 2000-09-11 08:00 | 2001-03-23 17:00 | 100% | - | - | Nokia | antti.toskala@nokia.com | - | - |  |  |  |  | Tue 26/09/00 | Mon 12/03/01
6141 | 1996 | UMTS 1800 | RInImp-UMTS18 | 2 | Rel-4 | R4 | 2000-09-25 08:00 | 2001-12-14 17:00 | 100% | - | - | Motorola | Howard Benn | - | - |  |  |  |  | Tue 26/09/00 | Thu 29/11/01
6142 | 2467 | UMTS 1900 | RInImp-UMTS19 | 2 | Rel-4 | R4 | 2001-03-19 08:00 | 2001-12-14 17:00 | 100% | - | - | Motorola | Howard Benn | - | 25.101 |  |  |  |  | Mon 19/03/01 | Thu 09/07/09
6143 | 1219 | FS on High Speed downlink packet access | RInImp-HSDPA | 2 | Rel-4 | R2 | 2000-08-21 08:00 | 2001-03-23 17:00 | 100% | - | - | Motorola | Amitabha Ghosh (qa0047@email.mot.com) | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
6144 | 1510 | Deleted - FS on improved common DL channel for Cell-FACH state | RInImp-DLCFACH | 2 | Rel-4 | R2 | 2000-09-11 08:00 | 2001-12-28 17:00 | 100% | - | - | GBT | J. Kwak | Stopped at RP#14 | - |  |  | RP-14 |  | Wed 26/04/00 | Tue 13/10/09
6145 | 401839 | Conformance Test Spec. Rel-4 improvements in Radio Interface | - | 2 | Rel-4 | T1 | 2001-10-08 08:00 | 2003-03-14 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 14/09/00 | Thu 11/10/01
6146 | 2212 | Deleted - Testing Improved usage of downlink resource in FDD for CCTrCHs of dedicated type | - | 3 | Rel-4 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Mon 10/12/01
6147 | 2213 | Deleted - Testing Terminal Power saving features | - | 3 | Rel-4 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Mon 10/12/01
6148 | 2214 | Deleted - Testing DSCH power control improvement in soft handover | - | 3 | Rel-4 | T1 | 2002-02-18 08:00 | 2002-08-30 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Thu 28/02/02
6149 | 2215 | Testing UMTS 1800 | - | 3 | Rel-4 | T1 | 2001-10-08 08:00 | 2002-06-14 17:00 | 100% | TP-030052 | - | - | - | - | 34.108, 34,121, 34.122, 34.123-1 |  |  |  |  | Thu 16/11/00 | Mon 13/01/03
6150 | 41000 | Testing UMTS 1900 | - | 3 | Rel-4 | T1 | 2001-10-08 08:00 | 2002-06-14 17:00 | 100% | TP-030052 | - | - | - | - | 34.108, 34,121, 34.122, 34.123-1 |  |  |  |  | Thu 16/11/00 | Mon 13/01/03
6151 | 2561 | Testing UMTS 1800 - TTCN | - | 3 | Rel-4 | T1 | 2002-06-17 08:00 | 2003-03-14 17:00 | 100% | TP-030052 | - | - | - | - | 34.123-3 |  |  |  |  | Thu 31/05/01 | Mon 13/01/03
6152 | 41001 | Testing UMTS 1900 - TTCN | - | 3 | Rel-4 | T1 | 2002-06-17 08:00 | 2003-03-14 17:00 | 100% | TP-030052 | - | - | - | - | 34.123-3 |  |  |  |  | Thu 31/05/01 | Mon 13/01/03
6153 | 400009 | Rel-4 RAN improvements | - | 1 | Rel-4 | RP | 2000-08-14 08:00 | 2004-03-17 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 31/03/00 | Fri 17/11/00
6154 | 655 | Node B synchronization for TDD | RANimp-NBsync | 2 | Rel-4 | R1 | 2000-08-14 08:00 | 2001-03-23 17:00 | 100% | - | - | Siemens | S. Oestreich | - | - |  |  |  |  | Wed 26/04/00 | Mon 12/03/01
6155 | 2206 | RAB support enhancement for Rel-4 | RANimp-RABSE | 2 | Rel-4 | R2 | 2000-08-21 08:00 | 2001-03-23 17:00 | 100% | - | - | Ericsson | M. Israelsson, A. Krishnarajah | 29 Nov 2000: split into ROHC and non-ROHC part; 5 Mar 2001: splitting off of ROHC for Rel-4 agreed by R2 | - |  |  |  |  | Mon 04/12/00 | Thu 28/02/02
6156 | 402102 | Deleted - Conformance Test Aspects - Rel-4 RAN Improvements | - | 2 | Rel-4 | T1 | 2002-01-01 08:00 | 2004-03-17 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-23 |  | Wed 01/11/00 | Sat 01/04/00
6157 | 402222 | Deleted - Testing Radio access bearer support enhancments | - | 3 | Rel-4 | T1 | 2002-01-01 08:00 | 2002-09-02 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | - |  |  | TP-17 |  | Thu 16/11/00 | Tue 09/04/02
6158 | 402461 | Deleted - Testing RAB support enhancements-Robust Header Compression | RABimp-RoCH | 3 | Rel-4 | T1 | 2002-05-28 08:00 | 2003-09-03 17:00 | 100% | TP-030052 | - | - | - | UID changed. Marked as stopped 12/2008 | 34.123-1, -2 |  |  | TP-21 |  | Tue 20/03/01 | Fri 14/03/03
6159 | 41006 | Deleted - Testing RAB support enhancements-Robust Header Compression - TTCN | - | 3 | Rel-4 | T1 | 2002-05-28 08:00 | 2004-03-17 17:00 | 100% | TP-030052 | - | - | - | UID changed. Marked as stopped 12/2008 | 34.123-3 |  |  | TP-23 |  | Thu 26/09/02 | Fri 14/03/03
6160 | 41007 | Testing of Extended Robut Header Compression | Ext-RoHC | 3 | Rel-4 | T1 | 2002-09-18 08:00 | 2003-09-30 17:00 | 100% | TP-030052 | - | - | - | Marked as closed 12/2008 (was marked 15% complete) | 34.123-1, -2 |  |  |  |  | Thu 26/09/02 | Fri 14/03/03
6161 | 41008 | Deleted - Testing of Extended Robut Header Compression - TTCN | - | 3 | Rel-4 | T1 | 2002-09-18 08:00 | 2003-12-16 17:00 | 100% | TP-030052 | - | - | - | Marked as stopped 12/2008 | 34.123-3 |  |  | TP-22 |  | Thu 26/09/02 | Fri 14/03/03
6162 | 41009 | Deleted - General changes to TS34.121 corresponding to release 4 | RANimp-test,TEI4 | 3 | Rel-4 | T1 | 2003-03-03 08:00 | 2004-03-03 17:00 | 100% | - | - | - | - | Marked as stopped 12/2008 | 34.108, 34.121 |  |  | TP-23 |  | Fri 14/03/03 | Fri 14/03/03
6163 | 401652 | Rel-4 Emergency call enhancements | EMC1-CS | 1 | Rel-4 | N1,S1,T1 | 2000-01-03 08:00 | 2002-05-28 17:00 | 100% | - | - | Ericsson | - | Acronym changed from EMC1, EMC1-CS | - |  |  |  |  | Tue 08/08/00 | Tue 24/03/15
6164 | 1654 | For CS based calls | EMC1-CS | 2 | Rel-4 | N1 | 2000-01-03 08:00 | 2002-05-28 17:00 | 100% | NP-010136 | - | Ericsson | - | WI approved in TSG_10 | - |  |  |  |  | Tue 08/08/00 | Wed 30/05/01
6165 | 1320 | Distinction in CS domain of emergency call types to different emergency services | - | 3 | Rel-4 | S1 | 2000-05-01 08:00 | 2000-06-23 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Mon 21/07/08
6166 | 1999 | Distinction in CS domain of emergency calls to different emergency types | - | 3 | Rel-4 | N1 | 2000-08-24 08:00 | 2000-09-22 17:00 | 100% | NP-010136 | - | - | - | Calls to different emergency services such as ambulance, fire brigade, police, etc. can be routed to respective different emergency centres. | 24.008 |  |  |  |  | Sat 23/09/00 | Mon 21/07/08
6167 | 402224 | Deleted - Conformance Test Aspects - Emergency call enhancements | - | 3 | Rel-4 | T1 | 2000-01-03 08:00 | 2000-07-28 17:00 | 100% | - | - | - | - | UID changed. Marked as stopped 12/2008 | - |  |  | TP-08 |  | Thu 16/11/00 | Fri 12/12/08
6168 | 2226 | Testing CS based emergency calls | - | 3 | Rel-4 | T1 | 2002-02-25 08:00 | 2002-05-28 17:00 | 100% | TP-030052 | - | - | - | - | 34.123-1 |  |  |  |  | Tue 28/11/00 | Mon 13/01/03
6169 | 2563 | Testing CS based emergency calls - TTCN | - | 3 | Rel-4 | T1 | 2001-11-22 08:00 | 2002-05-28 17:00 | 100% | TP-030052 | - | - | - | - | 34.123-3 |  |  |  |  | Thu 31/05/01 | Mon 13/01/03
6170 | 401826 | Rel-4 Terminal interfaces | TI | 1 | Rel-4 | T2 | 2000-01-03 08:00 | 2001-03-15 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
6171 | 1827 | AT commands enhancements | TI-ATC | 2 | Rel-4 | T2 | 2000-01-03 08:00 | 2001-03-14 17:00 | 100% | - | - | - | - | - | 27.007 |  |  |  |  | Thu 14/09/00 | Tue 13/03/01
6172 | 1828 | Specification of AT commands for new services | - | 3 | Rel-4 | T2 | 2000-01-03 08:00 | 2001-03-14 17:00 | 100% | - | - | - | - | goal not completely achieved because of missing input | 27.007 |  |  |  |  | Thu 14/09/00 | Tue 20/03/01
6173 | 1829 | Wide Area Data Synchronization | TI-WADS | 2 | Rel-4 | T2 | 2000-01-03 08:00 | 2001-03-14 17:00 | 100% | - | - | - | - | AS: Rel5 changed to Rel4 according to SP#10 decision, milestone on testing added | - |  |  |  |  | Thu 14/09/00 | Tue 19/12/00
6174 | 1830 | Continues evolution of Synchronization protocol | TI-SYNC-EVOL | 3 | Rel-4 | T2 | 2000-01-03 08:00 | 2001-03-14 17:00 | 100% | - | - | - | - | - | 27.903, 27.103 |  |  |  |  | Thu 14/09/00 | Tue 20/03/01
6175 | 1832 | Terminal local model | TLM | 2 | Rel-4 | T2 | 2000-05-16 08:00 | 2001-03-15 17:00 | 100% | TP-000080 | - | Ericsson | Olga.Tome@ECS.ERICSSON.SE | - | 23.227 |  |  |  |  | Thu 14/09/00 | Fri 14/09/01
6176 | 401536 | Rel-4 Location Services enhancements | LCS4 | 1 | Rel-4 | S2,S1,T2,N1,N4,R3,R2 | 2000-04-03 08:00 | 2001-12-28 17:00 | 100% | SP-010518 | - | Nokia | Jan Kall | Acronym changed form LCS1 | - |  |  |  |  | Fri 28/07/00 | Tue 24/03/15
6177 | 2229 | CBS interactions | LCS4-CBS | 2 | Rel-4 | T2 | 2000-04-03 08:00 | 2001-12-28 17:00 | 100% | - | - | - | - | - | 23.041 |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
6178 | 523 | LCS support in the CS domain | LCS4-CS | 2 | Rel-4 | S2 | 2000-05-15 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | Only MAP impact foreseen so far. To be further split if needed. | - |  |  |  |  | Wed 19/04/00 | Tue 24/03/15
6179 | 525 | LCS support in the PS domain | LCS4-PS | 2 | Rel-4 | S2,S1,N1,N4 | 2000-05-01 08:00 | 2001-12-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Tue 24/03/15
6180 | 1642 | Stage 1 for LCS support in the PS domain | - | 3 | Rel-4 | S1 | 2000-07-03 08:00 | 2000-08-25 17:00 | 100% | - | - | Pacific Bell Wireless | Randolph Wohlert (rwohlert@tri.sbc.com) | To be also considered: External LCS client identity, and Privacy options when PDP-context and when no PDP-context is established | 22.071 |  |  |  |  | Tue 08/08/00 | Sat 01/04/00
6181 | 1181 | Stage 2 for LCS support in the PS domain | - | 3 | Rel-4 | S2,R2,G1 | 2000-05-01 08:00 | 2001-01-19 17:00 | 100% | - | - | - | - | SP#10 completed | 25.305 (UTRAN part), new 23.271 (CN part by S2, 43.059 (GERAN part) |  |  |  |  | Wed 19/04/00 | Wed 13/12/00
6182 | 1180 | Stage 3 for LCS support in the PS domain | - | 3 | Rel-4 | N1,N4 | 2000-08-21 08:00 | 2001-12-28 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Wed 10/10/01
6183 | 526 | Layer 3 LCS signalling UE (MS) -SGSN (UMTS PS and and GSM-GPRS) | - | 4 | Rel-4 | N1 | 2000-08-21 08:00 | 2001-12-28 17:00 | 100% | - | - | Nokia | Janne Muhonen | - | - |  |  |  |  | Wed 19/04/00 | Mon 25/03/02
6184 | 2462 | MAP impacts of LCS | - | 4 | Rel-4 | N4 | 2000-08-21 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Tue 20/03/01 | Tue 20/03/01
6185 | 527 | GTP signalling for LCS | - | 4 | Rel-4 | N4 | 2000-08-21 08:00 | 2001-03-30 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 19/04/00 | Mon 12/03/01
6186 | 401600 | UE positioning Rel-4 | LCS1-UEpos | 2 | Rel-4 | R3,R2 | 2000-04-03 08:00 | 2001-03-30 17:00 | 100% | RP-000509 | RP-010045 | - | - | - | - |  |  |  |  | Wed 26/07/00 | Tue 09/04/02
6187 | 1601 | Iub/Iur interfaces for methods Rel 99 | LCS1-UEpos-IubIur | 3 | Rel-4 | R3 | 2000-04-03 08:00 | 2001-03-30 17:00 | 100% | RP-000509 | RP-010045 | Ericsson | Yun-Chao Hu | - | 25.401, 25.420, 25.423, 25.430, 25.433, new TR 25.850 |  |  |  |  | Wed 26/07/00 | Tue 20/03/01
6188 | 1602 | UE positioning enhancements - IPDL for TDD | LCS1-UEpos-enh | 3 | Rel-4 | R2 | 2000-08-28 08:00 | 2001-03-23 17:00 | 100% | RP-000509 | RP-010045 | Siemens | Armin Sitte | 5 Mar 2001: split of IPDL for TDD agreed by R2 | new TR 25.847 |  |  |  |  | Wed 26/07/00 | Tue 22/05/12
6189 | 401560 | Rel-4 UICC/(U)SIM enhancements and interworking | UICC1 | 1 | Rel-4 | T3 | 2000-07-24 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | Acronym changed from UICC1, Rel-4 | - |  |  |  |  | Sun 09/04/00 | Tue 24/03/15
6190 | 1799 | Common PCN Handset Specification (CPHS) | UICC1-CPHS | 2 | Rel-4 | T3 | 2000-07-24 08:00 | 2001-03-23 17:00 | 100% | TP-000116 | - | One2One | - | 28/5/2001: CRs approved at TP-11. WI complete. | 27.103 |  |  |  |  | Thu 14/09/00 | Mon 28/05/01
6191 | 401800 | Rel-4 (U)SIM toolkit enhancements | USAT4 | 1 | Rel-4 | T3,S1 | 2000-06-05 08:00 | 2001-03-23 17:00 | 100% | - | - | Gemplus | Jean-Francois Rubon | Acronym changed from USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM | 23.048 (USAT1SM), 43.019 (USAT1APIJAVA) |  |  |  |  | Thu 14/09/00 | Tue 24/03/15
6192 | 2034 | USAT local link | USAT1-LocLnk | 2 | Rel-4 | T3,S1 | 2000-06-05 08:00 | 2001-03-23 17:00 | 100% | TP-000116 | - | Gemplus | Jean-Francois Rubon | 25/5/2001:CR was approved at TP-11. WI is complete | 22.038, 31.111 |  |  |  |  | Wed 27/09/00 | Mon 28/05/01
6193 | 401571 | Rel-4 Security enhancements | SEC4 | 1 | Rel-4 | S3,N4,N1 | 2000-01-03 08:00 | 2002-03-15 17:00 | 100% | SP-000421 | - | Vodafone | Peter.Howard@vodafone.com | acronym changed from SEC1 | - |  |  |  |  | Sun 09/04/00 | Tue 24/03/15
6194 | 1331 | Rel-4 Lawful Interception | SEC4-LI | 2 | Rel-4 | S3 | 2000-08-21 08:00 | 2001-03-23 17:00 | 100% | - | - | - | - | Requirements capture: S3#14 (Aug 00), Feature specification: S3#15 (Sep 00), Definition of architecture. Should be included in general LI work mentioned above.. Acronym changed from SEC1-LI | 33.107 |  |  |  |  | Sun 09/04/00 | Tue 24/03/15
6195 | 1587 | Evolution of GSM CS algorithms (e.g. A5/3 development and deployment) | SEC1-CSALGO1 | 2 | Rel-4 | S3 | 2000-01-03 08:00 | 2001-01-15 17:00 | 100% | SP-000306 | - | DTI, BIS | cbrookson@iee.org | SP#8 approved WID | 33.102, 33.103, 33.105 |  |  |  |  | Sun 09/04/00 | Tue 17/11/09
6196 | 1588 | Evolution of GSM PS algorithms (e.g. GEA 2 deployment) | SEC1-PSALGO1 | 2 | Rel-4 | S3,N4,N1 | 2000-02-22 08:00 | 2000-12-22 17:00 | 100% | SP-000307 | - | DTI, BIS | cbrookson@iee.org | SP#8 approved WID | 33.102, 33.103, 33.105 |  |  |  |  | Sun 09/04/00 | Tue 17/11/09
6197 | 1589 | Deleted - Main aspects of Evolution of GSM PS algorithms (e.g. GEA 2 deployment) | - | 3 | Rel-4 | S3 | 2000-02-22 08:00 | 2000-11-24 17:00 | 100% | - | - | DTI, BIS | cbrookson@iee.org | Complete TSG#09 (09/2000). S3#17: Proposed for deletion. TO BE DELETED | - |  |  | SP-69 |  | Sun 09/04/00 | Sat 06/08/11
6198 | 1618 | Impact on GTP | - | 3 | Rel-4 | N4 | 2000-03-20 08:00 | 2000-12-22 17:00 | 100% | - | - | DTI, BIS | cbrookson@iee.org | - | - |  |  |  |  | Tue 08/08/00 | Wed 13/12/00
6199 | 1661 | GEA capability indication in MS CM | SEC1-PSALGO1-GEACAP | 3 | Rel-4 | N1 | 2000-06-19 08:00 | 2000-12-22 17:00 | 100% | - | - | Vodafone Airtouch | Duncan Mills | - | - |  |  |  |  | Tue 08/08/00 | Wed 15/11/00
6200 | 401583 | Deleted - MAP application layer security | SEC1-MAPAL | 2 | Rel-4 | S3 | 2000-01-03 08:00 | 2002-03-15 17:00 | 100% | - | - | - | - | REPLACED BY NDS-MAP and NDS-IP. Completed Auto Key Management -> Rel-6. Marked as stopped 12/2008 | - |  |  | SP-15 |  | Sun 09/04/00 | Tue 17/11/09
6201 | 401584 | Deleted - Main aspects of MAP application layer security | - | 3 | Rel-4 | S3 | 2000-02-21 08:00 | 2001-03-29 17:00 | 100% | - | - | - | - | UID changed. Marked as stopped 12/2008 | - |  |  | SP-11 |  | Sun 09/04/00 | Tue 09/04/02
6202 | 402025 | Deleted - Other stage 3 aspects | - | 3 | Rel-4 | N4 | 2000-02-22 08:00 | 2000-11-24 17:00 | 100% | - | - | - | - | UID changed. Marked as stopped 12/2008 | - |  |  | CP-10 |  | Sun 09/04/00 | Tue 09/04/02
6203 | 401594 | Deleted - Visibility and Configurability of security | SEC1-VCS | 3 | Rel-4 | S3 | 2000-01-03 08:00 | 2002-03-15 17:00 | 100% | SP-000305 | - | France Telecom | Sebastien.nguyenngoc@rd.francetelecom.com | CR approved at SA3#21 awaiting comments from CN1. Marked as stopped 12/2008 | - |  |  | SP-15 |  | Sun 09/04/00 | Tue 17/11/09
6204 | 401142 | Rel-4 Charging and OAM&P | OAM4 | 1 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-10-05 17:00 | 100% | SP-010461 | - | - | - | SP#13 approved WID | - |  |  |  |  | Wed 26/04/00 | Thu 24/01/02
6205 | 2089 | Rel-4 Principles, high level Requirements and Architecture | - | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-06-21 17:00 | 100% | SP-010461 | - | Motorola, Telia | Michael.Truss@motorola.com, Tommy.R.Berggren@TELIA.SE | - | 32.101, 32.102 |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
6206 | 2088 | Rel-4 Performance Management | - | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-09-28 17:00 | 100% | SP-010238 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | - | 32.4xy, 52.402 |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
6207 | 2081 | Fault Management | - | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-10-05 17:00 | 100% | SP-000524 | - | Lucent | - | - | 32.111-1/4 |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
6208 | 2082 | Configuration Management | - | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-06-21 17:00 | 100% | SP-000524 | - | Ericsson | thomas.tovinger@ericsson.com | - | 32.106-1/8 |  |  |  |  | Wed 26/04/00 | Mon 13/01/03
6209 | 2083 | Rel-4 Charging Management | - | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-09-28 17:00 | 100% | SP-000524 | - | T-Mobile | karl-heinz.nenner@t-mobile.de | - | 32.200, 32.205, 32.215, 32.235 |  |  |  |  | Wed 26/04/00 | Tue 07/07/09
6210 | 2071 | UTRAN Operations and Maintenance procedures | UOAM | 2 | Rel-4 | S5 | 2000-12-01 08:00 | 2001-06-21 17:00 | 100% | SP-000524 | - | Mannesmann Mobilfunk | bert.boden@d2mannesmann.de | - | 32.800 |  |  |  |  | Mon 09/10/00 | Mon 13/01/03
6211 | 1517 | Global Text Telephony | GTT | 1 | Rel-4 | S1,S2,S4,T1,R5 | 2000-01-03 08:00 | 2001-03-19 17:00 | 100% | SP-010340 | - | Ericsson | gunnar.hellstrom@omnitor.se | SP#12 updated WID SP-000162=>SP-010340 | - |  |  |  |  | Fri 28/07/00 | Wed 14/10/09
6212 | 1634 | Stage 1 for Global Text Telephony | - | 2 | Rel-4 | S1 | 2000-04-05 08:00 | 2000-12-22 17:00 | 100% | SP-010340 | - | - | - | - | 22.226 |  |  |  |  | Tue 08/08/00 | Wed 09/05/12
6213 | 1519 | Stage 2 for Global Text Telephony | - | 2 | Rel-4 | S2 | 2000-01-03 08:00 | 2000-10-13 17:00 | 100% | SP-010340 | - | - | - | - | 23.226 |  |  |  |  | Fri 28/07/00 | Thu 24/01/02
6214 | 2234 | Specification of Cellular Text telephone Modem | GTT-CTM | 2 | Rel-4 | S4 | 2000-09-11 08:00 | 2001-03-19 17:00 | 100% | SP-010340 | - | - | - | - | - |  |  |  |  | Wed 13/12/00 | Thu 28/02/02
6215 | 2238 | General description and C-code | - | 3 | Rel-4 | S4 | 2000-09-11 08:00 | 2000-12-11 17:00 | 100% | - | - | - | - | - | 26.226, 26.230 |  |  |  |  | Wed 13/12/00 | Thu 28/02/02
6216 | 2237 | Minimum Performance requirements | - | 3 | Rel-4 | S4 | 2000-09-11 08:00 | 2001-03-19 17:00 | 100% | - | - | - | - | - | 26.231 |  |  |  |  | Wed 13/12/00 | Thu 28/02/02
6217 | 1852 | Deleted - Conformance Test Aspects - Global Text Telephony | GTT_Test | 2 | Rel-4 | R5,T1 | 2000-09-21 08:00 | 2000-09-21 08:00 | 100% | - | - | - | - | RP#45 work item abandoned/closed (it was never really started) | - |  |  | RP-45 | PCG-23 | Thu 14/09/00 | Tue 15/09/09
6218 | 0 | Release 1999 Features | - | 1 | R99 | NP,SP,TP,SMG | 2000-01-03 08:00 | 2000-12-29 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 31/05/06 | Tue 09/02/10
6219 | 60150 | UMTS Features | - | 1 | R99 | S1,S2,S4,SMG,N3,N4,RP | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 11/08/09
6220 | 60102 | UMTS_SERVICES | UMTS_SERVICES | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.101 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6221 | 60103 | UMTS phase 1 | UMTS1 | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.100 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6222 | 60119 | UMTS Capabilities | UMTS_Capabil | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Requirement for high quality speech in UMTS Phase 1 but not in R99 | 22.105 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6223 | 60164 | Architecture of the GSM-UMTS platform | - | 2 | R99 | S2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | wid “Architecture overview of the GSM-UMTS System”, “Architecture the GSM-UMTS Platform” and “New Access Network to Core Network (BSS-NSS) interface” | 23.002, 23.008, 23.060, 23.101, 23.110 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6224 | 60165 | UMTS Terrestrial Radio Access Network | UTRAN | 2 | R99 | RP | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.011, 22.038, 22.060, 22.078, 22.100, 22.101, 22.105, 22.115, 22.129, 23.002, 23.060, 24.007, 24.008, 25.101, 25.102, 25.104, 25.105, 25.113, 25.123, 25.133, 25.141, 25.142, 25.201, 25.211, 25.212, 25.213, 25.214, 25.215, 25.221, 25.222, 25.223, 25.224, |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6225 | 60083 | UMTS 1800, UMTS 1900 | Rlnlmp19,Rlnlmp18 | 2 | R99 | R2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 25.307 CR#0002, 0003 Inclusion of release independent RF related information |  |  |  |  | Thu 30/07/09 | Tue 09/02/10
6226 | 60149 | Mandatory speech codec for narrowband telephony service | Mandatory_Speech_Codec,AMR-NB,AMR | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99060 | - | - | - | Define the default speech codec for UMTS (both for FDD and TDD). Definition limited to selection of one codec among several existing ones/proposed codecs: GSM AMR, IS127 EVRC, ITU G.729 and MPEG-4 speech codec. | 04.08, 05.01, 05.02, 05.03, 05.05, 05.08, 05.09, 05.09, 05.50, 08.60, 08.61, 11.21, 26.071, 26.073, 26.074, 26.090, 26.091, 26.092, 26.093, 26.094, 26.101, 26.102, 26.103, 26.104, 26.975 |  |  |  |  | Thu 16/07/09 | Tue 11/08/09
6227 | 60055 | Codec for low bitrate multimedia telephony service | Low_bit_rate_codec_for_MM_Tel.,H.324M | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99060 | - | - | - | - | 26.104, 26.110, 26.111, 26.911, 26.912, 26.915 |  |  |  |  | Thu 16/07/09 | Tue 11/08/09
6228 | 60109 | 3G Audio-Visual Terminal characteristics | WI5TAC,3G-AVT,Terminal_Acoustic_Characteristics | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99129 | - | - | - | - | 26.131, 26.132 |  |  |  |  | Thu 16/07/09 | Tue 11/08/09
6229 | 60104 | Updates_for_UMTS | Updates_for_UMTS | 2 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 24.022, 27.001, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6230 | 60124 | UMTS | UMTS | 2 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 27.060, 29.061 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
6231 | 60151 | UMTS and GSM Features | - | 1 | R99 | S1,S2,SMG,T2,N1,N2,N3,N4,R2,R3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6232 | 60147 | Multimedia Messaging Service | MMS | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | MMS allows users to send/receive messages e.g. almost unlimited text length, images, audio and video clips and new content types. R99 only includes the concept. MMS stage 3 is not included in 23.140. Rel-4 adds detailed architecture and protocols. | 22.140, 23.040, 23.140 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6233 | 60121 | Location Services | LCS | 2 | R99 | S1,S2,S3,SMG1,SMG2,SMG12,N1,N2,N4,R2,R3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99327 | - | - | - | LCS provide ability to localize a terminal | 02.07, 03.71, 04.31, 04.35, 04.71, 05.05, 08.08, 08.31, 08.71, 09.31, 22.071, 23.002, 23.003, 23.007, 23.008, 23.016, 23.018, 23.032, 23.171, 24.007, 24.008, 24.030, 24.080, 25.305, 25.306, 25.331, 25.413, 25.423, 29.002, 29.010 |  |  |  |  | Thu 16/07/09 | Sat 06/08/11
6234 | 60118 | Customised Application for Mobile network Enhanced Logic Phase 3 | CAMEL3 | 2 | R99 | S1,S2,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99368 | - | - | - | CAMEL is a network feature providing mechanisms to support services of operators which are not covered by standardised services, even when roaming outside the HPLMN. | 22.101, 23.008, 23.012, 23.016, 23.018, 23.060, 23.072, 23.078, 23.079, 23.082, 23.093, 29.002, 29.078 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6235 | 60218 | Global view | - | 3 | R99 | S1,S2,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.078, 23.078, 29.078 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6236 | 60318 | Multiple Subscriber Profile (MSP) based on CAMEL phase 3 | - | 3 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | MSP is an optional service enabling mobile subscribers to have several profiles associated with a single IMSI, with each profile being a subscription option. Each profile may be used for mobile originated and mobile terminated calls. | 22.097 (Advanced Addressing) |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6237 | 60038 | Short Message Service enhancements / Enhanced Messaging Service (EMS) | EMS | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | SMS for 3G terminals compatible with GSM SMS. Added Enhanced Messaging Service (EMS) allowing small pictures, sounds, animations to be transferred via SMS. | 23.038, 23.039, 23.040, 23.042 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6238 | 60122 | Mobile Station Execution Environment | MExE | 2 | R99 | S1,SMG1,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | MExE provides a standardized MS execution environment and ability to negotiate its supported capabilities with a MExE SP. R99 enhances SIM MExE certificate management, security clarifications, QoS and defines two MExE classmarks WAP/Personal-Java based. | 02.57, 22.057, 22.101, 23.057 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6239 | 60123 | MS_Classmark | MS_Classmark | 2 | R99 | N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | MExE classmark identifies a category of MExE UE supporting MExE functionality with a minimum level of processing, memory, display, and interactive capabilities. Several MExE classmarks may be defined. | 24.008 |  |  |  |  | Wed 08/07/09 | Tue 07/07/09
6240 | 60057 | MultiCall | Multicall | 2 | R99 | S1,N1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | NP-000348 | - | - | - | Multicall allows several simultaneous CS calls with dedicated bearers of independent traffic and performance characteristics. R99 Multicall was defined as a supplementary service limited to one CS bearer to be used for speech at any time. | 22.030, 22.083, 22.087, 23.008, 23.009, 23.016, 23.018, 23.108, 23.135, 24.008, 24.080, 24.135, 29.002, 29.010 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6241 | 60058 | Stage 1 for Multicall | - | 3 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.030, 22.083, 22.087 |  |  |  |  | Thu 30/07/09 | Tue 09/02/10
6242 | 60105 | Virtual Home Environment | VHE | 2 | R99 | S1,SMG1,S2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Information exists in SP#5-8 reports & in SP-99416,SP-000095,SP 000155. OSA allows service development by operators and 3rd parties by making use of network functionality through open, standardised, secure, extensible and scalable interfaces. | 02.01, 22.105, 22.121,23.127 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6243 | 60067 | Open Service Access | OSA | 2 | R99 | S1,S2,N5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Open Service Architecture became in later Releases Open Service Access. Produced by Parlay, ETSI SPAN (TISPAN), 3GPP SA1 (Stage 1), SA2 (Stage 2) and CN5 (Stage 3), resulting in a single set of standard OSA APIs for the whole development community. | 22.121, 23.127, 29.198, 29.998 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6244 | 60091 | Super Charger mechanism for signalling traffic associated with mobility | Super_Charger | 2 | R99 | N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Super Charger reduces mobility management cost by reducing the volume of location update signalling. It changes subscriber data management associated with inter-VLR and SGSN location updates. It also applies to packet services (SGSN replaces VLR and | 21.905, 23.007, 23.008, 23.012, 23.016, 23.018, 23.040, 23.060, 23.116, 23.912, 29.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6245 | 60039 | Follow_Me service | Follow_Me | 2 | R99 | S1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Follow Me enables a mobile subscriber A to manipulate the Follow Me data of a party B in such a way that - under certain conditions - subsequent calls directed to party B will be forwarded to subscriber A. It is PLMN-specific and control based on USSD | 21.905, 22.004, 22.030, 22.082, 22.090, 22.094, 23.090, 24.090, 22.094, 23.011, 23.015, 23.082, 29.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6246 | 60093 | Wide area network Synchronization and object exchange | SYNC | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Allows data stored in ME/USIM to be synchronized with the outside world. TS 27.103 defines protocols based upon IrMC level 4 and will evaluate new technologies (XML) for inclusion. From Rel-4 IrMC was replaced by SyncML in 27.103. | 27.103, 27.903 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
6247 | 60145 | R99 Terminal Interfaces | - | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
6248 | 60166 | AT commands for 3GPP | - | 3 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | AT commands to control a 3G ME via an external Terminal Equipment (TE), fully compatible with GSM AT commands. R99 adds new AT commands e.g. to control Advanced Speech Call Items (ASCI) services. | 27.005, 27.007 |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
6249 | 60167 | Physical interfaces | - | 3 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Conclusion: 3GPP should not produce any technical specification for terminal interfaces other than radio interface and USIM interface. SDOs could develop own optional physical connector specification based on market requirements | 27.901 |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
6250 | 60168 | Multiplexer | MUXMS-TE | 3 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Multiplexing protocol allowing a number of simultaneous sessions between a MS and a terminal; used to send any data (voice, SMS, USSD, fax etc.). 27.010 describes the protocol, but not the commands or data transported with it. | 27.010 |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
6251 | 60169 | Bearer Services | - | 2 | R99 | S1,T2,N1,N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
6252 | 60012 | Circuit Switched Bearer Services | Circuit_switched_Bearer_Services | 3 | R99 | S1,N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | NP-99285 | - | - | - | CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported | 22.002, 23.910, 27.001, 29.007 |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
6253 | 60021 | Stage 1 for Circuit Switched Bearer Services | CS_Bearerss_in_UMTS | 4 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | NP-99285 | - | - | - | CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported | 22.002 |  |  |  |  | Thu 16/07/09 | Mon 20/07/09
6254 | 60019 | CS_Bearers | CS_Bearers | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6255 | 60020 | CS_Bearerss | CS_Bearerss | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 04.21, 23.910, 27.001, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6256 | 60022 | CS_Data | CS_Data | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 27.001, 27.002, 27.003, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6257 | 60023 | CS_Data_Bearers | CS_Data_Bearers | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.910, 27.001, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6258 | 60024 | Deleted - CN3 poart of Circuit Switched Bearer Services | CSBS | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 23.910, 27.001, 29.007 |  |  | NP-06 |  | Thu 30/07/09 | Tue 09/02/10
6259 | 60040 | Frame Tunnelling Mode | FTM | 3 | R99 | T2,N1,N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | NP-99285 | - | - | - | FTM is a type of async non-transparent CS bearer service (22.002). Generic term for HDLC and HDLC-related transmission protocols. Converts async non-transp data stream towards mobile side & sync data stream using X.31 flag stuffing on fixed network side. | 22.002, 27.001, 27.007, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6260 | 60171 | Access to ISPs and Intranets – Wireless/Remote access to LANs | InterworkingwithPDN(DHCP) | 3 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | N3-99069 | - | - | - | Access to an Intranet or ISP by running DHCP between the TE and a server in the Intranet/ISP domain. | 29.061 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
6261 | 60070 | PHS Internet Access Forum Specification | PIAFS | 3 | R99 | S1,N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | NP-99285 | - | - | - | PIAFS is one type of CS bearer data service (22.002). It refers to async CS tx protocol over ISDN 64 kbit/s unrestricted digital line. Facilitates interworking between PHS-MS and UMTS-UE & UMTS-UE and existing PIAFS TA (Terminal Adapter). | 22.002, 27.001, 27.007, 29.007 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
6262 | 60170 | Personal Handyphone System Internet Access Forum Standard (PIAFS) | - | 4 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | PIAFS was originally standardised by the PHS Internet Access Forum in Japan. More information can be found at: http://www.infopro.or.jp/piaf | 22.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6263 | 60092 | Support_of_PIAFS_in_UMTS | Support_of_PIAFS_in_UMTS | 4 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 27.001, 27.007, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6264 | 60172 | Universal Integrated Circuit Card (UICC) and Universal Subscriber Identity Module (USIM) | UICC,USIM | 2 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99084 | - | - | - | For 3G, GSM 11.11 was divided into two parts: a platform comprised of basic physical, electrical and logical specification (31.101) and an application specification (31.102) | - |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6265 | 60173 | UICC / Terminal interface; Physical and logical characteristics | UICC | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99084 | - | - | - | Defines a generic Terminal/Integrated Circuit Card (ICC) interface. Is independent of 3G USIM application => platform for any IC card application. Ensures interoperability between ICC and terminal independently of manufacturer, card issuer or operator. | 31.101 (Since 10/2000, ETSI EP SCP is responsible for the generic Terminal/Integrated Circuit Card (ICC) interface TS 102 221) |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6266 | 60142 | UICC/(U)SIM enhancements and interworking | UICC99 | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Acronym changed from UICC1 | 31.102, 31.900 |  |  |  |  | Wed 08/07/09 | Tue 24/03/15
6267 | 60174 | Characteristics of the USIM application | USIM | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99084 | - | - | - | Defines Universal Subscriber Identity Module (USIM) application for 3G telecom network operation & resides on UICC, an IC card specified in 31.101. UICC can be used as a multi-application card: several USIMs and/or other applications can co-exist | 31.102 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6268 | 60114 | UICC Application Identifiers | AID,Application_Identifiers | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99184 | - | - | - | Defines and administers Application IDentifiers (AID) for UICC. AID is used to address an application in the card. Consists of Registered application provider ID (RID) & Proprietary application ID exception (PIX - according to ISO/IEC 7816-5). | 21.111, 31.110 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6269 | 60139 | SIM Application Toolkit | SAT | 3 | R99 | S1,T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 11.14, 22.030, 22.100, 22.101 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
6270 | 60141 | USIM Application Toolkit | USAT | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99184 | - | - | - | Defines UICC - ME interface, and mandatory ME procedures for USAT. Based on GSM 11.14 (SIM Application Toolkit). Commands and procedures defined in USIM and 3G Terminal for using USAT. Service and security requirements defined in 22.100 and 22.101. | 31.111 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6271 | 60175 | Bearer Independent Protocol for SAT applications to exchange data over the GSM network | BIP | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Defines at SIM-ME interface a basic protocol allowing SIM Toolkit applications to determine available bearers and to exchange data by selecting using the most appropriate bearer available (CS data, GPRS, SMS, Unstructured Supplementary Service Data (USSD) | 03.48, 11.10, 11.14 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6272 | 60176 | Administrative commands and functions for IC cards | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Defines function and syntax of administrative commands for telecommunication IC Card used during installation, activation and de-activation of applications. Compliant to ISO/IEC 7816 series. Handed over to ETSI Project Smart Card Platform (SCP) in 2000. | ETSI TS 102 222 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6273 | 60177 | USIM and UICC requirements | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99084 | - | - | - | High level requirements for 3GPP IC card and its interface to 3GPP terminal (USIM&UICC reqs). Service&security reqs in 322.01,22.00. USIM is a 3GPP application on an IC card. Inter-operates with 3GPP terminals and provides access to 3GPP services | 21.111 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6274 | 60140 | SIM_API | SIM_API | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.19 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
6275 | 60086 | SIM_toolkit_API | SIM_toolkit | 3 | R99 | SMG9,T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.48, 11.11, 11.14 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6276 | 60087 | Deleted - 1.8 Volt SIM ME interface | SMIME_1.8V | 3 | R99 | SMG9 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 11.18 |  |  | TP-06 |  | Thu 30/07/09 | Tue 09/02/10
6277 | 60178 | USIM/UICC Testing | - | 2 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6278 | 60179 | Terminal tests for the UICC Interface | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99184 | - | - | - | Test spec for the interface between UICC and terminal (originally based GSM 11.10-1 clause 27). Ensures UICC - terminal interoperability independently of manufacturer, card issuer or operator. Tests for applications residing on UICC are in 31.121 | 31.120 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6279 | 60180 | USIM application test specification | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-99184 | - | - | - | Application test spec originally based on GSM 11.17. Aspects related to UICC administrative management phase are not defined. Any internal technical realisation of either UICC or terminal is only specified where these are reflected over the interface. | 31.121 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6280 | 60181 | USIM conformance test specification | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Conformance Test specification for UICC defined in 31.101 with USIM defined in 31.102. | 31.122 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6281 | 60182 | SIM toolkit test specification | - | 3 | R99 | T3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | SIM Application Toolkit (SAT) has major impact on ME design and enhances SIM/ME interface. Contains tests for SIM/ME interface optional features (no network related signalling issues involved). Doesn't form basis for any type approval or regulatory tests. | 11.10-4 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6282 | 60137 | Security for UMTS and GSM Features | Security | 2 | R99 | S3,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.09, 03.20, 21.133, 22.022, 23.003, 23.007, 23.008, 23.012, 23.018, 24.007, 24.008, 24.010, 24.011, 29.002, 29.060, New (33.102, 33.103, 33.105, 33.107, 35.201) |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6283 | 60183 | Fraud Information Gathering Service (for connection-orientated services) | FIGS | 3 | R99 | S3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | HPLMN can monitor its subscribers in VPLMN, which collects info on a defined set of monitored subscribers activities & sends it to HPLMN, which can perform service limitation control eg Operator Determined Barring (ODB) and IST to limit financial exposure | New 22.031, 23.031 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6284 | 60085 | Immediate Service Termination / SECurity Immediate Service Termination | IST,SECIST | 3 | R99 | S3,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | HPLMN can terminate all activities of its subscriber in VPLMN, if decides (based on info via eg FIGS) that a roaming subscriber is behaving in fraudulent/suspicious way. HPLMN can terminate all subscriber activities including calls in progress. | 03.35, 22.032, 23.008, 23.016, 23.035, 29.002 |  |  |  |  | Wed 08/07/09 | Tue 21/07/09
6285 | 60018 | Core_Network_Security | Core_Network_Security | 3 | R99 | N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 29.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6286 | 60152 | GSM Features | - | 1 | R99 | S1,S2,SMG,T2,N1,N2,N3,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6287 | 60184 | Dual Transfer Mode within GSM and GPRS | DTM | 2 | R99 | SMG,N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | 2-99-1780 (2-99-H80 from SMG2#32) WID on “BSS co-ordination of Radio Resource allocation for class A GPRS services - GSM Radio Access (R99)” | 03.55, 03.64, 04.18, 04.60, 05.01, 05.02, 05.08, 08.08, 23.060, 24.007, 24.008 |  |  |  |  | Thu 16/07/09 | Tue 21/07/09
6288 | 60013 | Class A Dual Transfer Mode | Class_A_Dual_Transfer_Mode_(DTM) | 3 | R99 | SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 05.10 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6289 | 60027 | Dual Transfer Mode | - | 3 | R99 | SMG,N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.55, 03.64, 04.18, 05.01, 05.02, 05.08, 24.008 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6290 | 60185 | General Packet Radio Service enahancements | GPRSenhancements | 2 | R99 | S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | GPRS was introduced in Release 97. Release 99 brings a number of essential corrections e.g. on Downlink Power Control, Timing Advance procedure, Cell reselection delay time, PBCCH scheduling, PTCCH mapping, etc. | 05.02, 05.05, 05.08, 05.10, 05.50, 11.21, 23.064, 24.008, 24.060 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
6291 | 60132 | General Packet Radio Service | GPRS | 3 | R99 | S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.60, 03.22, 03.64, 04.18, 04.60, 04.64, 04.65, 05.01, 05.02, 05.05, 05.08, 05.10, 08.08, 08.18, 11.10-1, 11.21, 22.041, 22.060, 23.003, 23.007, 23.060, 23.107, 23.122, 24.007, 24.008, 27.007, 27.060, 29.002, 29.016, 29.018, 29.060, 29.061 |  |  |  |  | Tue 07/07/09 | Mon 06/07/09
6292 | 60133 | GPRS2 | GPRS2 | 3 | R99 | SMG1,N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Introduction of EGPRS (S1) + Introduction of Reserved Service Labels in the APN (N2) | 02.60, 23.003 |  |  |  |  | Thu 09/07/09 | Mon 06/07/09
6293 | 60134 | GPRS Tunnelling Protocol enhancement | GTP_enhancement | 3 | R99 | N4,N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.003, 23.008, 29.060 |  |  |  |  | Tue 07/07/09 | Mon 06/07/09
6294 | 60186 | Enhanced Data rates for GSM Evolution - Phase 1 | EDGE-Phase1 | 2 | R99 | SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | EDGE is independent of the frequency bands, so it can be deployed e.g. in 900 and 1900 MHz bands. The new physical layer based on 8-PSK modulation is introduced and EGPRS and ECSD facilitate the new modulation in single and multi slot constellation. | 10.59, 02.34, 02.60, 03.30, 05.10, 05.50, 11.26 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
6295 | 60030 | Enhanced Data rates for GSM Evolution | EDGE | 3 | R99 | SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | WID in SMG2 331/97, SMG 1147/97, SMG 1148/97 | 02.34, 03.10, 03.20, 03.64, 04.03, 04.04, 04.06, 04.08, 04.18, 04.21, 04.22, 04.60, 04.64, 05.01, 05.02, 05.03, 05.04, 05.05, 05.08, 05.10, 05.50, 07.01, 07.02, 07.03, 08.08, 08.20, 08.58, 08.60, 09.07, 09.18, 11.10-1, 11.11, 11.21, 11.26, 23.034, 24.008, |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6296 | 60034 | EDGE-Layer1 | EDGE-Layer1 | 3 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | WID in SMG2 331/97, SMG 1147/97, SMG 1148/97 | 05.05, 05.10, 05.50 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6297 | 60135 | High Speed Circuit Switched Data | HSCSD | 3 | R99 | SMG1,SMG2,SMG7 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No additional features for R99. | 02.34, 04.18, 11.10-1 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
6298 | 60029 | Enhanced Circuit Switched Data - Phase 1 | ECSD | 3 | R99 | S1,SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | ECSD supports both transparent and non-transparent services, up to 64 kbit/s and 57.6 kbit/s respectively. See Tdoc SMG2 670/99 “ECSD Concept Evaluation” for more info | 05.02, 08.58, 22.034 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6299 | 60032 | EDGE-Enhanced Circuit Switched Data | EDGE-ECSD | 3 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 05.03 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6300 | 60035 | Enhanced GPRS - Phase 1 | EGPRS | 3 | R99 | SMG,N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.07, 03.64, 04.14, 04.18, 04.60, 05.05, 05.08, 24.008 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6301 | 60033 | EDGE-EGPRS | EDGE-EGPRS | 3 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 05.03, 05.05, 05.08 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6302 | 60069 | Packet Flow Context (PFC) | PFC | 3 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 04.18 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6303 | 60031 | Support for EGPRS in ANSI-136 networks and EDGE COMPACT | EDGE-Compact | 3 | R99 | SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Support for EGPRS in ANSI-136 networks” and “EDGE Compact” (for ANSI-136 networks only). COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz | 03.22, 03.30, 03.64, 05.01, 05.02, 05.03, 05.05, 05.08, 05.10 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6304 | 60036 | EGPRS COMPACT | EGPRS-Compact | 3 | R99 | SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz | 04.18, 05.02 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6305 | 60136 | COMPACT | COMPACT | 3 | R99 | SMG,N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz | 03.22, 04.18, 04.60, 05.08, 23.122, 24.008 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
6306 | 60047 | GSM_400 | GSM_400 | 2 | R99 | SMG2,SMG7,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | GSM in the 400 MHz bands allows to deploy GSM within frequency bands in the range 450 to 500 MHz, previously used for analogue cellular systems. See Tdoc SMG2 190/99 and 595/99 for further info. | 02.17, 03.22, 03.30, 04.04, 04.18, 04.60, 05.01, 05.02, 05.05, 05.08, 05.10, 05.50, 08.18, 08.58, 11.21, 24.008, 27.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6307 | 60048 | GSM_450 | GSM_450 | 2 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.22, 03.30, 05.01, 05.05, 05.08 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6308 | 60131 | GSM_700 | GSM_700 | 2 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 05.05 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6309 | 60041 | Deleted - GERAN | GERAN | 2 | R99 | SMG2,S2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | G2: 04.18 CR#A248 , 04.60 CR#B090 |  |  | SP-06 |  | Thu 30/07/09 | Tue 09/02/10
6310 | 60153 | GSM Features transposed to UMTS | - | 1 | R99 | S1,S3,T2,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
6311 | 60187 | Cell Broadcast Service | CBS | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Moved to CT1 at TSG-T closure. Applicability of the Cell Broadcast Service (as defined for GSM network) to 3G networks | 23.041 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
6312 | 60188 | GSM mobile number portability euro MNP / North American MNP | MNP | 2 | R99 | S1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | R98 MNP: mobile subscriber ability to change PLMN operator within the same country whilst retaining its original MS ISDN number (MSISDN). IMSI is changed, only MSISDN is kept. R99 adds requirements for North American Service Provider Number Portability. | 22.066 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
6313 | 60144 | Mobile Number Portability | - | 3 | R99 | N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.018, 23.066, 29.002 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
6314 | 60189 | Automatic establishment of roaming relations | - | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | Telecom Italia | enrico.scarrone@telecomitalia.it | framework for commercial and technical interworking between UMTS Home Environments and Serving Networks who have no direct prior commercial agreements with each other. | 22.101, 22.971 |  |  |  |  | Thu 16/07/09 | Tue 31/08/10
6315 | 60190 | Advanced addressing | - | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.101, 22.75U, 22.975 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
6316 | 60191 | UMTS numbering, addressing and identities | - | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Also new requirements for Single and Multiple Numbering scheme was added (CR#20 and 21). Deleted the term International Mobile User Identifier (IMUI) and changed IMSI (International Mobile Station Identifier=>International Mobile Subscriber Identity. | 22.101 |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
6317 | 60192 | Lawful Interception for GSM Features transposed to UMTS | LI | 2 | R99 | S3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Defines an interception system in UMTS that supports a number of regional interception regulations. Regional interception requirements shall be met in using specific (regional) mediation functions allowing only required information to be transported. | New 33.106, 33.107 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
6318 | 60154 | Charging | - | 1 | R99 | S1,S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
6319 | 60011 | R99 Charging | Charging | 2 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.115, 23.121 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6320 | 60215 | R99 OAM Charging Management | OAMCH,CH | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99271 | - | - | - | - | 32.005, 32.015 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6321 | 60155 | Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM1999 | 1 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99581 | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Tue 09/02/10
6322 | 60073 | OAM Principles and High-level Requirements | PR,Princs_&_Reqs_(PR) | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99581 | - | - | - | - | 32.101 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6323 | 60062 | OAM Architecture | OAMAR,AR,Telecom_Management_Arch_(AR) | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99581 | - | - | - | - | 32.101, 32.102 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6324 | 60014 | OAM Configuration Management | OAMCM,CM | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99273 | - | - | - | - | 32.106, 32.106-1, 32.106-2, 32.106-3, 32.106-4, 32.106-5, 32.106-6, 32.106-7, 32.106-8 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6325 | 60063 | OAM Fault Management | OAMFM | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99272 | - | - | - | - | 32.111, 32.111-1, 32.111-2, 32.111-3, 32.111-4 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6326 | 60064 | OAM Performance Management | OAMPM,PM | 2 | R99 | S5 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99274 | - | - | - | - | 12.04, 32.104 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6327 | 60106 | Vocabulary | Vocabulary | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 21.905 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6328 | 60037 | Emergency | Emergency | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.101 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6329 | 60049 | GSM General Bearer Services (GBS) and interworking scenarios support in UMTS | GSM_to_UMTS_Evol | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | UMTS shall support GSM General Bearer Services (GBS) and interworking scenarios as specified in 02.02 | 22.105 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6330 | 60043 | GPRS_Mobile_IP_interworking | GPRS_Mobile_IP_interworking | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 29.061 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6331 | 60046 | GSM/UMTS interworking | 2G3Ginterworking | 1 | R99 | N1,N2,N4,R3,S1,SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.22, 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 08.18, 08.58, 09.08, 22.011, 23.003, 23.009, 23.014, 23.034, 23.122, 24.007, 24.008, 24.011, 24.080, 29.108 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6332 | 60050 | Handover | Handover | 1 | R99 | S1,SMG2,N1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 04.18, 08.08, 08.58, 22.129, 23.009, 29.002, 29.010 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6333 | 60120 | 2G3Ghandover | 2G3Ghandover | 1 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 29.010 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6334 | 60088 | Service Provider Name Indication | SPANME | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Service Provider Name Indication included in R98 (02.07) was not carried into R99 (22.101), but is in the SIM/USIM specification for R99 | 22.101 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6335 | 60026 | Data & Data_CleanUp | Data,Data_CleanUp | 1 | R99 | SMG1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.01, 02.02, 02.04, 02.34 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6336 | 60125 | Unstructured Supplementary Service Data (USSD) | USSD | 1 | R99 | SMG1,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No additional features for R99. | 02.04, 02.90, 23.090, 29.002 |  |  |  |  | Tue 07/07/09 | Tue 07/07/09
6337 | 60126 | Man-Machine Interface (MMI) of the User Equipment (UE) | MMI | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Data services streamlining + Support for Anonymous Call Rejection | 22.030 |  |  |  |  | Wed 08/07/09 | Tue 07/07/09
6338 | 60127 | Network Identity and Timezone (NITZ) | NITZ | 1 | R99 | SMG1,SMG3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.42, 04.08 |  |  |  |  | Wed 08/07/09 | Tue 07/07/09
6339 | 60128 | Deleted - Operator Determined Barring for Packet Oriented Services | ODB_Enh. | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Remove ODB for Packet Oriented Services from R99 | 22.041 |  |  | SP-69 |  | Thu 09/07/09 | Tue 07/07/09
6340 | 60068 | Packet Flow Management | Packet_Flow_Management | 1 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 08.18 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6341 | 60044 | GPRS_Point-To-Multipoint Group call | GPRS_PTMG | 1 | R99 | SMG1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.60 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6342 | 60156 | Call Forwarding | - | 1 | R99 | SMG1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Wed 22/07/09 | Tue 09/02/10
6343 | 60010 | Call Forwarding enhancements | CF_enhancements | 2 | R99 | N4,N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No additional features for R99. | 23.078, 23.079, 23.082, 29.002, 29.078 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6344 | 60116 | Call_Forwarding | Call_Forwarding | 2 | R99 | SMG1,N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.82, 29.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6345 | 60117 | Call_Forwarding_Enhancements | Call_Forwarding_Enhancements | 2 | R99 | N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.082 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6346 | 60157 | Quality of Service | - | 1 | R99 | S2,T2,N1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | WID SMG 98-0781 End To End UMTS QoS Management | - |  |  |  |  | Thu 16/07/09 | Tue 09/02/10
6347 | 60076 | End-to-end UMTS Quality of Service management | QoS | 2 | R99 | S2,T2,N1,N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | WID SMG 98-0781 End To End UMTS QoS Management | 23.107, 23.907, 24.008 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6348 | 60130 | End-to-end QoS for PS Domain including IMS | E2EQoS99 | 2 | R99 | S2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Acronym changed from E2EQos | 23.060, 23.170 |  |  |  |  | Wed 08/07/09 | Tue 24/03/15
6349 | 60045 | GPRS-enhanced_QoS | GPRS-enhanced_QoS | 2 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | AT-commands for Enhanced QoS Support management | 27.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6350 | 60077 | QoS_enhancements | QoS_enhancements | 2 | R99 | N2,N1,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.008, 23.016, 24.008, 29.002, 29.060 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6351 | 60129 | Support of Localised Service Area | SoLSA | 1 | R99 | SMG2,SMG3,SMG7,N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Mechanism which can be used as a platform for providing special tariffs and/or special set of service features for certain subscribers within a regionally restricted area or areas. No additional features for R99. | 04.08, 04.18, 08.08, 11.10-1, 29.002 |  |  |  |  | Tue 07/07/09 | Mon 06/07/09
6352 | 60100 | Transcoder_location | Transcoder_location | 1 | R99 | S2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | UE location identification: background information and associated primitives 2. Transcoder location at the core network and source depending coding belonging to the non-access stratum. | 23.110 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6353 | 60113 | Antenna_test_methods | Antenna_test_methods | 1 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.30 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6354 | 60107 | WBAMR / high quality speech in UMTS Phase 1 but not in R99 | WBAMR | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Add requirement for high quality speech in UMTS Phase 1 but not in R99 | 22.105 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6355 | 60138 | Codec | - | 1 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6356 | 60015 | Codecs for Multimedia Telephony Service | Codec_for_Multimedia_Telephony | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6357 | 60415 | Codecs for Multimedia Telephony Service | Multimedia_Codec | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6358 | 60515 | Codecs for Multimedia Telephony Service | CSM | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6359 | 60615 | Codecs for Multimedia Telephony Service | WI2MMC | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6360 | 60715 | Codecs for Multimedia Telephony Service | Codec(s)_for_CS_MM_Tel._Serv | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6361 | 60815 | Codecs for Multimedia Telephony Service | Codec(s)_for_MM_Tel_Service | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6362 | 60915 | Codecs for Multimedia Telephony Service | - | 3 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 26.911, 26.104, 26.111 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6363 | 60078 | QoS for Speech and Multimedia Codec | QoS_for_Speech_&_MM_Codecs_/_AMR | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | SP-99060 | - | - | - | - | 26.102, 26.912 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6364 | 60099 | Tandem Free Operation - Adaptive Multi-Rate codec types | TFOAMR | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | UMTS_AMR2 is default Codec Type in R99 dual_mode terminals | 26.103 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6365 | 60112 | Noise Suppression for AMR | AMRNS | 2 | R99 | S4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Combination of the AMR speech codec and the Noise Suppression function. TS 06.77 and TR 06.78 only apply to GSM. They apply to UMTS from Rel-4 onwards, when they were converted to TS 26.077 and TR 26.078. | 06.77, 06.78 |  |  |  |  | Mon 06/07/09 | Tue 11/08/09
6366 | 60065 | Out-of-Band Transcoder | OoBT | 2 | R99 | N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Transcoder handling in the CN at inter-system handover and relocation + Introduction of UMTS AMR | 23.009, 24.008 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6367 | 60066 | Out-of-Band Transcoder Control | OoBTC | 2 | R99 | N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | 24.008 CR#0572 in NP-020220 was approved under this WI | 24.008 CR#0572 in NP-020220 |  |  |  |  | Thu 30/07/09 | Tue 09/02/10
6368 | 60143 | Advanced Speech Call Items enhancements | ASCI | 1 | R99 | SMG1,SMG2,SMG3,SMG7,SMG9,N1,N4,S1,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 02.30, 02.68, 03.68, 03.69, 04.18, 08.08, 11.10-1, 11.11, 23.067, 23.094, 24.008, 24.067, 27.007, 29.002 |  |  |  |  | Tue 07/07/09 | Mon 06/07/09
6369 | 60009 | Call Control improvements | CC_Related_items | 1 | R99 | N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Minor improvements to 24.007 and 24.008 to increase the number of simultaneous calls/sessions from the present 7: the TI value is increased (NP-99441). | 24.007, 24.008 |  |  |  |  | Mon 06/07/09 | Thu 23/07/09
6370 | 60059 | Multimedia | Multimedia | 1 | R99 | N1,N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 24.008, 27.001, 29.007 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6371 | 60089 | Sub-System Number allocation for RANAP, RNSAP | SSN_allocation | 1 | R99 | N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Sub-System Number allocation for Radio Access Network Application Part, Radio Network Subsystem Application Part | 23.003 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6372 | 60053 | Intranet / ISP access with DHCP end-to-end | ISPaccess | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Access to an Intranet/ISP with DHCP end to end | 29.061 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6373 | 60072 | Point_to_Multipoint_Services | Point_to_Multipoint_Services | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Support for the IP-Multicast protocol | 29.061 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6374 | 60146 | Facsimile | FAX | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.003, 22.100 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
6375 | 60081 | Realtime_NT_FAX_in_UMTS | Realtime_NT_FAX_in_UMTS | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Asynchronous Interface for real-time NT Fax + Introduction of Asynchronous interface for Real-time non-transparent FAX | 27.001, 27.003 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6376 | 60042 | Gateway Location Register (GLR) - Mobile Application Part (MAP) specification | GLR | 1 | R99 | N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 29.120 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6377 | 60056 | Multiple Subscriber Profile phase 2 | MSP2 | 1 | R99 | S1,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 22.097, 23.072, 23.083, 23.084, 23.091, 23.093, 23.097 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6378 | 60074 | Prepaging | Prepaging | 1 | R99 | N2,N4 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.018, 23.082, 29.002 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6379 | 60148 | Re-definition of channel quality measure used for AMR link adaptation for Downlink Advanced Receiver Performance (DARP) MS | - | 1 | R99 | SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Re-definition of channel quality measure used for AMR link adaptation for DARP MS | 05.09 |  |  |  |  | Wed 08/07/09 | Mon 06/07/09
6380 | 60051 | Harmonized Standard | HS | 1 | R99 | SMG2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 13.21 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6381 | 60090 | Streamlining of specifications | Streamlining | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 27.060, 29.061 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6382 | 60079 | R99_Service_Clean_up | R99_Service_Clean_up | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 03.10, 27.001, 27.002, 27.003, 27.060, 29.007, 29.061 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6383 | 60094 | (Small) Technical Enhancements and Improvements for R99 | TEI | 1 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6384 | 60095 | TEI_[CS_Data] | TEI_[CS_Data] | 2 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6385 | 60096 | TEI_[GPRS] | TEI_[GPRS] | 2 | R99 | N3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6386 | 25016 | R99 UE Conformance Testing | TEI_Test | 1 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | Specifies Conformance Tests for a 3G UE to be recognised as “3GPP-standard compliant”. A 3GPP-external body, GCF (Global Certification Forum), delivers certificates to prove that a UE has correctly passed tests and is then conform to the 3GPP standard. | 34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6387 | 60084 | Deleted - RTEI | RTEI | 2 | R99 | T1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 34.123-1 CR#0650, 0651, 34.123-3 CR#0148, 0149, 0150 |  |  | TP-06 |  | Thu 30/07/09 | Tue 09/02/10
6388 | 60193 | Common test environments for User Equipment (UE); Conformance testing | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | - | 34.108 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
6389 | 60194 | Terminal conformance specification, Radio transmission and reception (FDD) | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in FDD mode. | 34.121 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
6390 | 60195 | Terminal conformance specification, Radio transmission and reception (TDD) | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in TDD mode. | 34.122 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
6391 | 60196 | UE conformance specification; Part 1: Protocol conformance specification | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | TS 34.123, composed of three parts, actually specifies the protocol conformance testing for the 3G UE. Part 1 describes the overall test structure. | 34.123-1 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
6392 | 60197 | UE conformance specification; Part 2: Implementation Conformance Statement (ICS) specification | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | Part 2 contains the applicability of each test case defined as the “Implementation Conformance Statement (ICS) proforma”, in compliance with the relevant requirements, and in accordance with the relevant guidance given in ISO/IEC 9646-7 and ETS 300 406. | 34.123-2 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
6393 | 60198 | UE conformance specification; Part 3: Abstract test suites (ATSs) | - | 2 | R99 | R5,T1 | 1999-01-01 08:00 | 1999-01-01 08:00 | 100% | - | - | - | - | Part 3 specifies the protocol conformance testing in TTCN for the 3G UE at the Uu interface. It defines the TTCN test specification and design considerations in Abstract Test Suites based on the test cases specified in prose in part 1. | 34.123-3 |  |  |  |  | Wed 22/07/09 | Wed 22/07/09
6394 | 60028 | Deleted - Dual Tone Multi-Frequency signalling : Support in the whole 3GPP system | DTMF | 1 | R99 | N1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 23.014 CR#0004 |  |  | NP-06 |  | Thu 30/07/09 | Tue 09/02/10
6395 | 60052 | Deleted - Intersystem_Change | Intersystem_Change | 1 | R99 | SMG | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 04.18 CR#A243 |  |  | SMG |  | Thu 30/07/09 | Tue 09/02/10
6396 | 60054 | Deleted - Long_Forwardedto_Numbers | Long_Forwardedto_Numbers | 1 | R99 | N2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 29.002 |  |  | NP-06 |  | Mon 06/07/09 | Mon 06/07/09
6397 | 60080 | Deleted - RANimp-FSEarlyUE | RANimp-FSEarlyUE | 1 | R99 | R3 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | No CR or new TS/TR approved under this WI | 25.413 CR#0520, 0538, 0565, 0563, 0541, 0540, 0539, 0547 |  |  | RP-06 |  | Thu 30/07/09 | Tue 09/02/10
6398 | 0 | Release 1999 Studies | - | 1 | R99 | S1,T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | - |  |  |  |  | Thu 16/07/09 | Mon 14/06/10
6399 | 60061 | Advanced Addressing/Numbering | Numbering | 1 | R99 | S1 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | Vodafone | mona.mustapha@vodafone.com | Study on requirements for numbering and addressing for UMTS | 22.975 |  |  |  |  | Mon 06/07/09 | Tue 31/08/10
6400 | 60161 | Combined GSM and Mobile IP mobility handling in UMTS IP CN | - | 1 | R99 | S2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | - | 23.923 |  |  |  |  | Thu 23/07/09 | Tue 09/02/10
6401 | 60101 | UE Capabilities Requirements | UCR | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Moved to CT1 at TSG-T closure | 21.904 |  |  |  |  | Mon 06/07/09 | Mon 06/07/09
6402 | 60158 | Electrical safety requirements and regulations | - | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Moved to RAN4 at TSG-T closure. TR summarizes differences between international and national standards relevant to IEC60950 and refers to regulations for conformity assessment due to different regulatory environments in different countries / regions. | 34.907 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
6403 | 60159 | Specific Absorbtion Rate (SAR) requirements and regulations in different regions | - | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Moved to RAN4 at TSG-T closure. | 34.925 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
6404 | 60160 | Multi-mode UE issues | - | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | TP-000022 | - | - | - | Moved to CT1 at TSG-T closure. Consequences on roaming capabilities and service availability (e.g. handover) of multi-mode UEs while roaming in various regions with various network configurations. Case studies for each of the possible scenarios in specs | 21.810, 21.910 |  |  |  |  | Thu 16/07/09 | Mon 06/07/09
6405 | 60162 | Provision of fax service in GSM and UMTS | - | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | Ericsson | peter.bleckert@ericsson.com | CP#27: Moved to C1 on closure of T2; see TP-050062. CP#28: C1->C3 | 22.945 |  |  |  |  | Thu 23/07/09 | Tue 09/02/10
6406 | 60163 | Separating Radio Resources and Mobility Management specific parts of the MS Classmark | - | 1 | R99 | T2 | 1999-01-01 08:00 | 1999-12-31 17:00 | 100% | - | - | - | - | CP#27: change of WG as a result of closure of CN and T. | 23.814 |  |  |  |  | Thu 23/07/09 | Tue 09/02/10