## Slide 1: CT WG1 Status Report to TSG CT#87
Peter Leis
CT1 chairman, Nokia

## Slide 2: TSG CT WG1 Officials
Peter Leis
TSG CT WG1 Chairman
ETSI
peter.leis@nokia.com
Lena Chaponniere
TSG CT WG1 ViceChair
ATIS lguellec@QTI.QUALCOMM.COM
Jörgen Axell
TSG CT WG1 ViceChair
ETSI
jorgen.axell@ericsson.com
Frederic Firmin
Secretary
MCC
frederic.firmin@etsi.org

## Slide 3: Meeting Calendar
Since the last CT plenary
  CT1#121bis-e (electronic)
    Limited scope, 3 Rel-16 “protoc type” work items
  CT1#122-e (electronic)
    Limited scope, Rel-16
Upcoming Meetings
  Ordinary:
    CT1#123-e (tbc)
    CT1#124 (Wroclaw, Europe, tbc)
  bis:
    n/a

## Slide 4: TSG CT WG1 Statistics
Number of handled documents
  CT1#121bis-e: 230
  CT1#122-e: 860
Agreed CRs
  CT1#121bis-e: Cat B/C/F 69
  CT1#122-e: Cat B/C/F 194
Agreed pCRs
  CT1#121bis-e: n/a
  CT1#122-e: 107
Attendances
  CT1#121bis-e: 41 registered
  CT1#122-e: 127 registered
Other information
  CT1#121bis-e had limited scope, only 5GProtoc16, SAES16, nonIMS TEI-16 were in scope
  CT1#122-e focused on Rel-16

## Slide 5: New agreed Study/Work Items led by CT1
TDoc # | Title | Source | Objectives
n/a |  |  | 

## Slide 6: Work Plan I
Name | Acronym | Start | End | % | WID
CT1 aspects of Vertical_LAN | Vertical_LAN | 14.03.2019 | 12.03.2020 | 95% | CP-190195
CT1 aspects of 5G_CIoT | 5G_CIoT | 14.03.2019 | 12.03.2020 | 92% | CP-190198
CT1 aspects of V2XAPP | V2XAPP | 06.06.2019 | 12.03.2020 | 65% | CP-191153
CT1 aspects of eV2XARC | eV2XARC | 06.06.2019 | 12.03.2020 | 95% | CP-191154
CT1 aspects of 5G_eLCS | 5G_eLCS | 07.03.2019 | 05.12.2019 | 90% | CP-190190
CT1 aspects of RACS | RACS | 06.06.2019 | 12.03.2020 | 100% | CP-191061
CT1 aspects of 5WWC | 5WWC | 07.03.2019 | 12.03.2020 | 95% | CP-190200
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 7: Work Plan II
Name7 | Acronym | Start | End | % | WID
CT aspects of eMCData2 | eMCData2 | 14.03.2019 | 12.12.2019 | 70% | CP-192081
Protocol enhancements for Mission Critical Services | MCProtoc16 | 06.09.2018 | 20.12.2019 | 100% | CP-182110
Stage 3 for MC Communication Interworking with Land Mobile Radio Systems | MCCI_CT | 06.06.2018 | 12.09.2019 | 100% | CP-190203
Mission Critical system migration and interconnection | MCSMI_CT | 06.06.2018 | 12.12.2019 | 5% | CP-190203
Study on stages 2 and 3 of enhancements of ePWS | ePWS | 10.09.2018 | 14.06.2019 | 100% | CP-182228
CT1 aspects of ePWS | ePWS | 06.09.2018 | 12.03.2020 | 95% | CP-182228
CT1 aspects of MONASTERY2 | MONASTERY2 | 06.06.2019 | 12.03.2020 | 65% | CP-191152
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 8: Work Plan III
Name | Acronym | Start | End | % | WID
CT1 aspects of Multi-device and multi-identity | MuD | 06.09.2018 | 14.06.2019 | 100% | CP-182227
CT1 aspects of eNS | eNS | 07.03.2019 | 05.12.2019 | 95% | CP-190196
CT1 aspects of PARLOS | PARLOS | 14.03.2019 | 12.12.2019 | 100% | CP-190197
CT1 aspects of ATSSS | ATSSS | 11.03.2019 | 09.12.2019 | 70% | CP-190201
CT1 aspect of 5G_SRVCC | 5G_SRVCC | 06.06.2019 | 12.03.2020 | 100% | CP-191062
CT1 Aspects of E2E_DELAY | E2E_DELAY | 14.03.2019 | 12.12.2019 | 100% | CP-190193
CT1 aspects of VBCLTE | VBCLTE | 06.06.2019 | 12.03.2020 | 0% | CP-191110
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 9: Work Plan IV
Name | Acronym | Start | End | % | WID
Signalling Improvements for Network Efficiency in 5GS | SINE_5G | 13.12.2018 | 12.12.2019 | 100% | CP-190142
CT1 aspects of xBDT | xBDT | 06.06.2019 | 12.03.2020 | 100% | CP-191113
IMS Stage-3 IETF Protocol Alignment | IMSProtoc16 | 13.12.2018 | 19.12.2019 | 100% | CP-183084
Stage-3 5GS NAS protocol development | 5GProtoc16 | 13.12.2018 | 19.12.2019 | 98% | CP-183087
Stage-3 SAE Protocol Development for Rel16 | SAES16 | 13.12.2018 | 19.12.2019 | 100% | CP-183088
Withdrawal of TS 24.323 from Rel-11, Rel-12, Rel-13 | ISAT-MO-WITHDRAW | 06.06.2019 | 12.03.2020 | 100% | CP-191151
CT1 aspects of SEAL | SEAL | 19.09.2019 | 12.03.2020 | 80% | CP-192255
CT1 aspects of eIMS5G_SB | eIMS5G_SBA | 06.06.2019 | 12.03.2020 | 70% | CP-192023
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 10: Work Plan V
Name | Acronym | Start | End | % | WID
CT aspects of enh2MCPTT | enh2MCPTT-CT | 06.12.2019 | 12.03.2020 | 100% | CP-193148
CT1 aspects of eIMS5G_SB | eIMS5G_SBA | 06.06.2019 | 12.03.2020 | 70% | CP-192023
Video enhancement of IMS CAT/CRS/announcement services | eIMSVideo | 06:12.2019 | 12.03.2020 | 33% | CP-193149
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 11: TS sent to CT plenary
TDoc # | Title | Version | Rapporteurs | Sent for
CP-200163 | 3GPP TS 24.174 v2.0.0 on Support of multi-device and multi-identity in the IP Multimedia Subsystem (IMS); Stage 3 | 2.0.0 | Jörgen Axell | approval
CP-200164 | 3GPP TS 24.175 v2.0.0 on Multi-device and multi-Identity in the IP Multimedia Subsystem (IMS); Management Object (MO) | 2.0.0 | Jörgen Axell | approval
CP-200165 | 3GPP TS 24.486 v1.0.0 on Vehicle-to-Everything (V2X) Application Enabler (VAE) layer; Protocol aspects; Stage 3 | 1.0.0 | Christian Herrero-Veron | Information
CP-200166 | 3GPP TS 24.519 v2.0.0 on 5G System; Time-Sensitive Networking (TSN) Application Function (AF) to Device-side TSN Translator (DS-TT) and Network-side TSN Translator (NW-TT) protocol aspects; Stage 3 | 2.0.0 | Sung Hwan Won | Approval
CP-200167 | 3GPP TS 24.535 v2.0.0 on Device-side Time-Sensitive Networking (TSN) Translator (DS-TT) to network-side TSN Translator (NW-TT) protocol aspects; Stage 3 | 2.0.0 | Sung Hwan Won | Approval
CP-200168 | 3GPP TS 24.544 v2.0.0 on Group Management - Service Enabler Architecture Layer for Verticals (SEAL); Protocol specification | 2.0.0 | Sapan Shah | Approval
CP-200169 | 3GPP TS 24.545 v1.0.0 on Location Management - Service Enabler Architecture Layer for Verticals (SEAL); Protocol specification | 1.0.0 | Christian Herrero-Veron | Approval
CP-200170 | 3GPP TS 24.546 v2.0.0 on Configuration management - Service Enabler Architecture Layer for Verticals (SEAL); Protocol specification | 2.0.0 | Sapan Shah | Approval
CP-200171 | 3GPP TS 24.547 v2.0.0 on Identity management - Service Enabler Architecture Layer for Verticals (SEAL); Protocol specification | 2.0.0 | Vivek Gupta | Approval
CP-200172 | 3GPP TS 24.548 v1.0.0 on Network Resource Management - Service Enabler Architecture Layer for Verticals (SEAL); Protocol specification | 1.0.0 | Christian Herrero-Veron | Information

## Slide 12: TS sent to CT plenary
TDoc # | Title | Version | Rapporteurs | Sent for
CP-200173 | 3GPP TS 24.587 v2.0.0 on Vehicle-to-Everything (V2X) services in 5G System (5GS); Stage 3 | 2.0.0 | Christian Herrero-Veron | approval
CP-200174 | 3GPP TS 24.588 v2.0.0 on Vehicle-to-Everything (V2X) services in 5G System (5GS); User Equipment (UE) policies; Stage 3 | 2.0.0 | Sang Min Park | Approval
CP-200175 | 3GPP TS 29.582 v2.0.0 on Mission Critical Data (MCData) interworking with Land Mobile Radio (LMR) systems; Stage 3 | 2.0.0 | Kit Kilgour (Peter Monnes) | Approval

## Slide 13: Release 16 Status (I)
3 revised work items were agreed
1 revised work item was endorsed
Rel-16 progress in the two electronic meetings better than expected
still significant number of exception sheets -> 14 exception sheets are provided to CT#87-e

## Slide 14: Release 16 – Topics requiring attention
ATSSS
  the decision on protocol for Performance Management Function Protocol” is still pending
  had planned a technical voting for February meeting which was not possible in e-meeting
  with April meetings being an e-meeting and unclear situation with May meeting this becomes URGENT
CT1 plans work on UE specific DRX in NB-S1 in Q2 under work item TEI16
Mission Critical Interconnection work item MSCMI_CT
  Work is only 5% complete, no exception sheet is provided to CT#87-e.
  It is planned to shift this work to Rel-17 (no CR has so far been agreed)
VBCLTE
  Work is 0% complete
  However, WID rapporteur confirmed no impact on CT1, WID will be updated in next quarter

## Slide 15: Release 15 Status
Rel-15 was not in scope of any of the two electronic meetings in Q1

## Slide 16: Backward Incompatible Changes
In “Frozen” specification, with impact on other TSG WGs
TDoc # | Title | Source | Impacted TS | Impacted TSG WG
n/a |  |  |  | 

## Slide 17: For Information to CT (I)
CT1 shifted the decision on the need for the July ad-hoc to the CT1 meeting in April (July ad-hoc meeting is currently shown on the 3GPP web page as tbc)

## Slide 18: For Action to CT
CT plenary is asked to reject the CR in C1-200398. CR is written against 23.122, however, the CR number was requested against 24.501
CT plenary is asked to reject the CR in C1ah-200145. The CR is covered by CR in C1-200791 and its revision (CP-200139) to plenary.

## Slide 19: Experience with e-meeting (I)
number of agreed Rel-16 CRs better than expected, a bit lower than in a regular meeting
very busy, huge amount of emails to process, meeting lasted from Thursday over weekend till Friday, effectively 9 days, many parallel discussions
conference calls
  timing very hard, given that CT1 delegates span 18 timezones
  can help to find way forward
decision making over email not always easy
  sometimes slow (different timezones), no f2f offline discussion, no show of hands
  as consequence, complex topics easier get shifted out of the meeting.

## Slide 20: Experience with e-meeting (II)
we are in learning phase regarding handling of e-meeting
feedback from delegates is gathered via email with an aim to improve the efficiency of future e-meetings
February e-meeting
  Roughly 2500 emails
  Only Rel-16 in scope (protoc type work items NOT in scope)
  194 CRs agreed
  62 CRs postponed/rejected
January e-meeting
  Roughly 730 e-mails
  Only 3 work items in scope
  69 CRs agreed
Chart: CRs in recent meetings
| Wroclaw | Portoroz | Reno | Feb e-meeting
agreed CRs Rel16 | 223 | 206 | 210 | 194
postponed/rejected CRs Rel-16 | 124 | 100 | 66 | 62
agreed CRs - preREl16 | 24 | 2 | 9 | 0

## Slide 21: Acknowledgement
The CT1 Chairman wants to thank
Lena Chaponniere for chairing the breakout stream on “services” topics during CT1#122-e
Jörgen Axell for chairing the breakout stream on “IMS and MC” topics during CT1#122-e
Frédéric Firmin for his excellent support
Most important the CT1 delegates for their dedication and hard work during demanding electronic meetings

## Slide 22: Annex

## Slide 23: CRs for conditional approval I
TDoc # | Title | Spec | CR# | Dependancy
C1-201058 | Support for the signalling of the capability for receiving WUS assistance information | 24,501 | 1907 | TS 23.501 CR#2053, TS 23.502 CR#2025 (SA2)
C1-200895 | Truncated 5G-S-TMSI over NAS | 24,501 | 1932 | TS 23.501 CR#2088 TS 23.502 CR#2049 (SA2)
C1ah-200066 | EMM cause #22 for resetting registration attempt counter | 24,301 | 3322 | TS 24.501 CR#1815
C1ah-200148 | Matching of SSC mode for association between an application and a PDU session | 24,526 | 69 | TS 24.501 CR 1794
C1-200926 | Introduction of GCI and GLI | 24,501 | 1877 | TS 23.003 CR#0568, TS 23.003 CR#0567 (CT4)
C1-200978 | Registration of N5GC devices via wireline access | 24,501 | 2020 | TS/TR 23.316 CR 1835 (SA2)
C1-200981 | SUPI and SUCI for legacy wireline access | 24,502 | 118 | TS/TR TS 23.003 CR#0568, TS 23.003 CR#0567 (SA2)
C1-201044 | MA PDU session is not supported | 24,501 | 1862 | TS 23.501 CR 2036
C1-200842 | Finalizing the encoding of the UE radio capability ID | 24,501 | 1888 | TS 23.003 CR 0564 (SA2
C1-200334 | Updating length of NID | 24,502 | 115 | TS 23.003 CR 0563 (sA2)

## Slide 24: CRs for conditional approval II
TDoc # | Title | Spec | CR# | Dependancy
C1-200985 | Including CAG information list in REGISTRATION ACCEPT message | 24,501 | 1884 | TS 23.501 CR 2135, TS 23.502 CR 2091 (SA2)
C1-201031 | N1 mode capability disabling and re-enabling for SNPN | 24,501 | 2012 | TS 23.122 CR 0502

## Slide 25: Thank You!
Peter Leis
3GPP TSG CT WG1 Chairman
peter.leis@nokia.com