## General
Latest update: xx/04/2021
| Source | Qualcomm Incorporated
| Title | Work Plan: CT aspects for Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking (ID_UAS)
Agenda Item:
Document for: Discussion
Latest WID: CP-210287
Completion Status: CT#91: 0%

## CT1 Topics
Latest update: xx/04/2021
CT1 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# tdoc# | status | Notes
A | General
1 | Definition and abbreviation | TS 23.256 3.1, 3.2 | 24.501 | Qualcomm | CT1#129e C1-212379 | Agreed
2 | section 4 (General) update for UAS (5GS) | TS 23.256 4.1 | 24.501 | Qualcomm | CT1#129e C1-212379 | Agreed | Editor's Note for the definition of UAV, UAV-C, and implication of the 'UE acting as a UAV" Editor's Note for details of UUAA procedure Editor's Note for disabling C2 communication Editor's Note for detauls of the authorization of C2 communication Editor's Note for details of UAV-C pairing change Editor's Note for details of UAV flight authorization
3 | section 4 (General) update for UAS (EPS) | TS 23.256 4.1 | 24.301 | Qualcomm
4 | Whether to introduce generic container for UUAA-SM | TS 23.256 5.2.3.1 | Discussion |  |  |  | SA2 has agreed to make UUAA-SM generic service for PDU session requiring authentication/authorization for any vertical service/applications. (Editor’s Note in TS 23.256, clause 5.2.3.1: The naming for the procedures and IEs, where needed, will be updated to make them generic (i.e. not specific to ID_UAS). ) Need discussons on which information can be coded in the generic container, and which information can be UAS specific
5 | Whether to introduce common IE for both UUAA-MM and UUAA-SM | - | Discussion |  |  |  | Based on A.4 topic above, whether to introduce common IE needs to be discussed
6 | Definition of UAV UE | - | Discussion |  |  |  | Need a definition in NAS perspective
B | UUAA at Registration (UUAA-MM)
1 | Registration request for UAS services | TS 23.256 5.2.2 | 24.501 | Qualcomm IDCC | CT1#129e C1-212467 | Agreed | Editor's Note for UUAA pending indication to be coded in the container
2 | Registration reject due to lack of subscription | TS 23.256 5.2.2 | 24.501 | Qualcomm IDCC | CT1#129e C1-212467 | Agreed
3 | UE Configuration Update procedure update for UUAA | TS 23.256 5.2.2 | 24.501 | Qualcomm IDCC
C | UUAA at PDU session establishment (UUAA-SM)
1 | PDU session establishment request for UAS services | TS 23.256 5.2.3 | 24.501 | Huawei
2 | PDU session establishment reject | TS 23.256 5.2.3 | 24.501
3 | How to identify the PDU session for the UAV communication and/or C2 communication | TS 23.256 5.2.3.1 | Discussion |  |  |  | TS 23.256, clause 5.2.3.1 "The PDU Session/PDN Connection is identified by the SMF/SMF+PGW-C as being for UAV/C2 communication based on the DNN or DNN/S-NSSAI combination."
D | UUAA at PDN connection establishment (UUAA-SM)
1 | PDN connection establishment requet for UAS services | TS 23.256 5.2.3 | 24.301 | Huawei
2 | PDN connection establishment reject | TS 23.256 5.2.3 | 24.301
E | UUAA procedure
Possible update to the clause 6.3.1 or add new clause for UUAA (depending on the discussion on generalization of UUAA-SM procedure)
F | C2 pairing authorization
1 | C2 pairing authorization at PDU session establishment | TS 23.256 5.2.5 | 24.501 | Lenovo, Motorola Mobility, IDCC | CT1#130e
2 | C2 pairing authorization at PDU session modification | TS 23.256 5.2.5 | 24.501 | Lenovo, Motorola Mobility, IDCc | CT1#130e
3 | C2 pairing autorization at PDN connection establishment | TS 23.256 5.2.5 | 24.301 | Lenovo, Motorola Mobility, IDCc | CT1#130e
4 | C2 pairing authorization at PDN connection modification | TS 23.256 5.2.5 | 24.301 | Lenovo, Motorola Mobility, IDCc | CT1#130e
G | UAV Flight authorization
1 | Flight authorization at PDU session establishment | TS 23.256 5.2.6 (not yet available) | 24.501 | Lenovo, Motorola Mobility | CT1#130e
2 | Flight authorization at PDN connection establishment | TS 23.256 5.2.6 (not yet available) | 24.301 | Lenovo, Motorola Mobility | CT1#130e
H | UUAA revocation and re-authorization/authentication
| UUAA re-authentication procedure | TS 23.256 5.2.4
| UUAA revocation procedure | TS 23.256 5.2.7
I | C2 connectivity revocation
not yet available
J | AT command for UUAA-MM/UUAA-SM
-

## Others
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
Outgoing liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments