## General
Latest update: 1/Aug/2021
| Source | Qualcomm Incorporated
| Title | Work Plan: CT aspects for Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking (ID_UAS)
Agenda Item:
Document for: Discussion
Latest WID: CP-210287
Completion Status: CT#91: 0% CT#92: 20%

## CT1 Topics
Latest update: 1/Aug/2021
CT1 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# tdoc# | status | Notes
A | General
1 | Definition and abbreviation | TS 23.256 3.1, 3.2 | 24.501 | Qualcomm | CT1#129e C1-212379 | Agreed
2 | section 4 (General) update for UAS (5GS) | TS 23.256 4.1 | 24.501 | Qualcomm | CT1#129e C1-212379 | Agreed | Editor's Note for the definition of UAV, UAV-C, and implication of the 'UE acting as a UAV" Editor's Note for details of UUAA procedure Editor's Note for disabling C2 communication Editor's Note for detauls of the authorization of C2 communication Editor's Note for details of UAV-C pairing change Editor's Note for details of UAV flight authorization
3 | section 4 (General) update for UAS (EPS) | TS 23.256 4.1 | 24.301 | Qualcomm
4 | Whether to introduce generic container for UUAA-SM | TS 23.256 5.2.3.1 | 24.501 | Qualcomm Nokia |  | Agreed | Agreed at CT#92(CP-211165)
5 | Whether to introduce common IE for both UUAA-MM and UUAA-SM | - | Discussion | Qualcomm |  | Agreed | Agreed at CT#92(CP-211165)
6 | Definition of UAV UE | - | 24.501 | Oppo | CT1#130e | Agreed | UE supporting UAS services in the definition section
B | UUAA at Registration (UUAA-MM)
1 | Registration request for UAS services | TS 23.256 5.2.2 | 24.501 | Qualcomm IDCC | CT1#129e C1-212467 CT1#130e C1-213810 | Agreed
2 | Registration reject due to lack of subscription | TS 23.256 5.2.2 | 24.501 | Qualcomm IDCC | CT1#129e C1-212467 CT1#130e C1-213810 | Agreed
3 | UE Configuration Update procedure update for UUAA | TS 23.256 5.2.2 | 24.501 | Qualcomm IDCC | CT1#130e C1-213766 | Agreed
C | UUAA at PDU session establishment (UUAA-SM)
1 | PDU session establishment request for UAS services | TS 23.256 5.2.3 | 24.501 | Huawei IDCC
2 | PDU session establishment reject | TS 23.256 5.2.3 | 24.501
3 | How to identify the PDU session for the UAV communication and/or C2 communication | TS 23.256 5.2.3.1 | Discussion | Huawei IDCC | CT1#130e | Not pursued | TS 23.256, clause 5.2.3.1 "The PDU Session/PDN Connection is identified by the SMF/SMF+PGW-C as being for UAV/C2 communication based on the DNN or DNN/S-NSSAI combination." No agreement on explicit indication at CT1#130e. Current stage-2 requirement: using DNN/S-NSSAI combination
D | UUAA at PDN connection establishment (UUAA-SM)
1 | PDN connection establishment requet for UAS services | TS 23.256 5.2.3 | 24.301 | Huawei
2 | PDN connection establishment reject | TS 23.256 5.2.3 | 24.301
E | UUAA procedure
| UUAA-MM: MM NAS message for multuple round trip msg for UUAA procedure |  | 24.501 | Qualcomm
| UUAA-SM: SM NAS message for multple round trip msg for UUAA procedure |  | 24.501 | Qualcomm
F | C2 pairing authorization
1 | C2 pairing authorization at PDU session establishment | TS 23.256 5.2.5 | 24.501 | Lenovo, Motorola Mobility, IDCC, Qualcomm
2 | C2 pairing authorization at PDU session modification | TS 23.256 5.2.5 | 24.501 | Lenovo, Motorola Mobility, IDCC, Qualcomm
3 | C2 pairing autorization at PDN connection establishment | TS 23.256 5.2.5 | 24.301 | Lenovo, Motorola Mobility, IDCC, Qualcomm
4 | C2 pairing authorization at PDN connection modification | TS 23.256 5.2.5 | 24.301 | Lenovo, Motorola Mobility, IDCC, Qualcomm
G | UAV Flight authorization
1 | Flight authorization at PDU session establishment | TS 23.256 5.2.6 (not yet available) | 24.501 | Lenovo, Motorola Mobility
2 | Flight authorization at PDN connection establishment | TS 23.256 5.2.6 (not yet available) | 24.301 | Lenovo, Motorola Mobility
H | UUAA revocation and re-authorization/authentication
| UUAA re-authentication procedure | TS 23.256 5.2.4
| UUAA revocation procedure | TS 23.256 5.2.7 |  | IDCC
I | C2 connectivity revocation
not yet available
J | AT command for UUAA-MM/UUAA-SM
-

## Others
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
Outgoing liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments