## R18 RAN4-led non-spectrum WI-SI
| AI | UID | UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | SR | Revised WID/SID | TU update | Change or comment
1 | 9.2.7 | 950068 | 950068 | Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements | FS_NR_FR2_OTA_enh | 2023-12-12 | 40% | RP-230814 | 60% | RP-231211 | RP-231212 | No | Revised WID: add objective for FR2-1 OTA testing for STxMP
2 | 9.2.8 | 950067 | 950067 | Study on simplification of band combination specification for NR and LTE | FS_SimBC | 2023-06-12 | 55% | RP-222216 | 90% | RP-231102 |  | YES. 0.5 RF TU | SI is extended by one quarter. Revised SID: remove objectives for PC5+Uu and add objective to investigate relationship between Rel-17 and Rel-18 TRs.
3 | 9.2.9 | 950069 | 950069 | Study on NR base station (BS) RF requirement evolution | FS_NR_BS_RF_evo | 2023-06-12 | 80% | RP-222501 | 100% | RP-231127 |  | No | This SI completed, continued WI supposed to be discussed in RAN#100. TR 38.877 is submitted for approval.
4 | 9.2.10 |  | 991031 | Study on enhancement for sub-1GHz NR band combinations | FS_NR_sub1GHz_combo_enh | 2023-06-12 | 0% | RP-230789 | 80% | RP-231140 | RP-231141 | YES. 0.5 RF TU | SI is extended by one quarter. Revised SID: update objective of three band combination
5 | 9.3.4.1 | 941012 | 941012 | NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW | 2024-06-20 |  | RP-230186 |  | RP-231424 | RP-231043 | YES. RAN1 TU | RAN1 is extended by one quarter. WID revised by adding EMC spec
5 | 9.3.4.1 | 941012 | 941112 | Core part: NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW-Core | 2023-12-12 | 40% | RP-230186 | 70%
5 | 9.3.4.1 | 941012 | 941212 | Perf. part: NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW-Perf | 2024-06-06 | 0% | RP-230186 | 0%
6 | 9.3.4.2 | 950080 | 950080 | Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | NR_ENDC_RF_FR1_enh2 | 2024-06-06 | 40% | RP-230753 | 60% | RP-231125 | RP-231126 | No | Revised WID: Clarification on scope including 8Rx for both single and CA/DC, work on t4r8 from RAN4#108 and extend target date of internal TR to RAN#102.
6 | 9.3.4.2 | 950080 | 950180 | Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | NR_ENDC_RF_FR1_enh2-Core | 2023-12-12 | 40% | RP-230753 | 60%
6 | 9.3.4.2 | 950080 | 950280 | Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | NR_ENDC_RF_FR1_enh2-Perf | 2024-06-06 | 40% | RP-230753 | 60%
7 | 9.3.4.3 | 950076 | 950076 | NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | NR_RF_FR2_req_Ph3 | 2024-03-01 | 30% | RP-222909 | 60% | RP-230992 |  | No | Discussions on beam correspondence scope triggered by RP-231123.
7 | 9.3.4.3 | 950076 | 950176 | Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | NR_RF_FR2_req_Ph3-Core | 2023-12-12 | 30% | RP-222909 | 60%
7 | 9.3.4.3 | 950076 | 950276 | Perf. part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | NR_RF_FR2_req_Ph3-Perf | 2024-03-01 | 30% | RP-222909 | 60%
8 | 9.3.4.4 | 950077 | 950077 | Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | NR_FR2_multiRX_DL | 2024-03-21 |  | RP-223527 |  | RP-231005 | RP-231003 | No | Revised WID: add internal TR and remove CBM from WID.It is proposed to work on L3 measurement related aspects and add corresponding objectives (RP-231026).It is proposed to extend core part to Q4 2023 (RP-231113).
8 | 9.3.4.4 | 950077 | 950177 | Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | NR_FR2_multiRX_DL-Core | 2023-09-08 | 35% | RP-223527 | 75%
8 | 9.3.4.4 | 950077 | 950277 | Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | NR_FR2_multiRX_DL-Perf | 2024-03-01 | 10% | RP-223527 | 15%
9 | 9.3.4.5 | 950079 | 950079 | Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2_enh | 2024-03-03 |  | RP-222272 |  | RP-231096 |  | No
9 | 9.3.4.5 | 950079 | 950179 | Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2_enh-Core | 2023-09-08 | 30% | RP-222272 | 80%
9 | 9.3.4.5 | 950079 | 950279 | Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2_enh-Perf | 2024-03-03 | 0% | RP-222272 | 30%
10 | 9.3.4.6 | 950078 | 950078 | Even Further RRM enhancement for NR and MR-DC | NR_RRM_enh3 | 2024-06-06 |  | RP-221696 |  | RP-231112 |  | No
10 | 9.3.4.6 | 950078 | 950178 | Core part: Even Further RRM enhancement for NR and MR-DC | NR_RRM_enh3-Core | 2023-12-12 | 65% | RP-221696 | 80%
10 | 9.3.4.6 | 950078 | 950278 | Perf. part: Even Further RRM enhancement for NR and MR-DC | NR_RRM_enh3-Perf | 2024-06-06 | 0% | RP-221696 | 0%
11 | 9.3.4.7 | 950082 | 950082 | Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | NR_MG_enh2 | 2024-06-06 |  | RP-230755 |  | RP-231314 | RP-231273 | No | Revised WID: Resubmission of changes to Note 3 from RANP#99 to downscope MG objective; Proposal to change name for one of the rapporteurs.
11 | 9.3.4.7 | 950082 | 950182 | Core part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | NR_MG_enh2-Core | 2023-12-12 | 45% | RP-230755 | 65%
11 | 9.3.4.7 | 950082 | 950282 | Perf. part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | NR_MG_enh2-Perf | 2024-06-06 | 0% | RP-230755 | 0%
12 | 9.3.4.8 | 950072 | 950072 | BS/UE EMC enhancements for NR and LTE | NR_LTE_EMC_enh | 2023-12-12 | 10% | RP-220916 |  | RP-231088 |  | No
12 | 9.3.4.8 | 950072 | 950172 | Core part: BS/UE EMC enhancements for NR and LTE | NR_LTE_EMC_enh-Core | 2023-09-08 | 20% | RP-220916 | 70%
12 | 9.3.4.8 | 950072 | 950272 | Perf. part: BS/UE EMC enhancements for NR and LTE | NR_LTE_EMC_enh-Perf | 2023-12-12 | 20% | RP-220916 | 60%
13 | 9.3.4.9 | 950075 | 950075 | Air-to-ground network for NR | NR_ATG | 2024-03-01 |  | RP-230279 |  | RP-231153 |  | No
13 | 9.3.4.9 | 950075 | 950175 | Core part: Air-to-ground network for NR | NR_ATG-Core | 2023-12-12 | 40% | RP-230279 | 70%
13 | 9.3.4.9 | 950075 | 950275 | Perf. part: Air-to-ground network for NR | NR_ATG-Perf | 2024-03-01 | 5% | RP-230279 | 10%
14 | 9.3.4.10 | 950081 | 950081 | Support of intra-band non-collocated EN-DC/NR-CA deployment | NonCol_intraB_ENDC_NR_CA | 2023-12-12 |  | RP-230742 |  | RP-231065 | RP-231066 | Yes. RF TU | Revised WID: downscoping in terms of capability and band combinations
14 | 9.3.4.10 | 950081 | 950181 | Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment | NonCol_intraB_ENDC_NR_CA-Core | 2023-09-08 | 30% | RP-230742 | 90%
14 | 9.3.4.10 | 950081 | 950281 | Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment | NonCol_intraB_ENDC_NR_CA-Perf | 2023-12-12 | 20% | RP-230742 | 20%
15 | 9.3.4.11 | 950073 | 950073 | NR demodulation performance evolution | NR_demod_enh3 | 2024-03-01 | 6% | RP-230314 | 50% | RP-231187 | RP-231188 | No | Revised WID: Following agreement in RAN4, add core part for NWA signaling (RAN4, RAN1， RAN2）
15 | 9.3.4.11 | 950073 | 950273 | Perf. part: NR demodulation performance evolution | NR_demod_enh3-Perf | 2024-03-01 | 25% | RP-230314 | 50%
16 | 9.3.4.12 | 970081 | 970081 | Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs | NR_MIMO_OTA_enh | 2024-06-06 | 15% | RP-223509 |  | RP-231143 |  | No
16 | 9.3.4.12 | 970081 | 970181 | Core part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs | NR_MIMO_OTA_enh-Core | 2023-12-12 | 35% | RP-223509 | 60%
16 | 9.3.4.12 | 970081 | 970281 | Perf. part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs | NR_MIMO_OTA_enh-Perf | 2024-06-06 | 0% | RP-223509 | 20%
17 | 9.3.4.13 | 970082 | 970082 | Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh | 2024-06-06 |  | RP-223112 |  | RP-231027 |  | No
17 | 9.3.4.13 | 970082 | 970182 | Core part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh-Core | 2023-12-12 | 30% | RP-223112 | 50%
17 | 9.3.4.13 | 970082 | 970282 | Perf. Part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh-Perf | 2024-06-06 | 5% | RP-223112 | 20%
18 | 9.3.4.14 |  | 991044 | Complete the specification support for BandWidth Part operation without restriction in NR | NR_BWP_wor | 2024-06-06 | 0% | RP-230805 |  | RP-231206 | RP-231205 | No | Discussions on L3 related requirements. WID changes: editorial updates; add new specs; objective clarification "None of these options are expected to include MGs, specifically for BM/RLM/BFD." There is a mistake with WI acronym and code in SR/WID and I provided comments to Vodafone
18 | 9.3.4.14 |  | 991144 | Core part: Complete the specification support for BandWidth Part operation without restriction in NR | NR_BWP_wor-Core | 2023-12-12 | 0% | RP-230805 | 40%
18 | 9.3.4.14 |  | 991244 | Perf. part: Complete the specification support for BandWidth Part operation without restriction in NR | NR_BWP_wor-Perf | 2024-06-06 | 0% | RP-230805 | 0%
19 | 9.3.4.15 |  | 991045 | NR channel raster enhancement | NR_channel_raster_enh | 2023-09-09 | 0% | RP-230813 | 25% | RP-231090 | RP-231275 | YES | WI is extended by two quarters. In RP-231180 companies proposed to include NTN bands.
19 | 9.3.4.15 |  | 991145 | Core part: NR channel raster enhancement | NR_channel_raster_enh-Core | 2023-09-09 | 0% | RP-230813 | 25%
20 | 10.2.2 | 950074 | 950074 | NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) | LTE_NBIOT_eMTC_NTN_req | 2023-06-12 |  | RP-223437 |  | RP-231310 |  | No | WI Perf part is declared completed. TS 36.181 RP-231253 submitted for approval.
20 | 10.2.2 | 950074 | 950174 | Core part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) | LTE_NBIoT_eMTC_NTN_req-Core | 2022-12-01 | 100% | RP-223437 | Closed
20 | 10.2.2 | 950074 | 950274 | Perf. part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) | LTE_NBIoT_eMTC_NTN_req-Perf | 2023-06-12 | 45% | RP-223437 | 100%
22 |  | 981040 | 981040 | New WID: on Maximum Power Reduction Requirements for LTE Intra-band Carrier Aggregation with a Component Carrier gap larger than 35 MHz | LTE_intra_CA_MPR_35MHz_gap | 2023-06-16 | closed | RP-223511 |  | RP-230480
22 |  | 981040 | 981140 | Core part: Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz | LTE_intra_CA_MPR_35MHz_gap-Core | 2023-03-03 | closed | RP-230705
23 |  | 890040 | 890040 | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | FS_NR_eff_BW_util | 2023-03-23 | closed | RP-220461 |  | RP-230579
24 |  | 950070 | 950070 | Study on enhancement for 700/800/900MHz band combinations for NR | FS_NR_700800900_combo_enh | 2023-03-23 | closed | RP-222554 |  | RP-230388

## R18 RAN4-led spectrum WI-SI
| AI | UID | UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | SR | Revised WID/SID | TU update | Change or comment
25 | 9.4.1.1 | 960098 | 960098 | Introduction of additional 6GHz NR licensed bands | NR_6GHz_add_bands | 2023-12-12 | 0% | RP-222498 | 0% | RP-231124 |  | No | WI is on-hold
25 | 9.4.1.1 | 960098 | 960198 | Core part: Introduction of additional 6GHz NR licensed bands | NR_6GHz_add_bands-Core | 2023-12-12 | 0% | RP-222498 | 0%
25 | 9.4.1.1 | 960098 | 960298 | Perf. part: Introduction of additional 6GHz NR licensed bands | NR_6GHz_add_bands-Perf | 2023-12-12 | 0% | RP-222498 | 0%
26 | 9.4.1.2 | 960095 | 960095 | Additional NR bands for UL-MIMO in Rel-18 | NR_bands_UL_MIMO_R18 | 2023-12-12 | 25% | RP-223516 | 55% | RP-231135 | RP-231136 | No | Revised WID: Add new bands for UL-MIMO
26 | 9.4.1.2 | 960095 | 960195 | Core part: Additional NR bands for UL-MIMO in Rel-18 | NR_bands_UL_MIMO_R18-Core | 2023-12-12 | 25% | RP-223516 | 55%
26 | 9.4.1.2 | 960095 | 960295 | Perf. part: Additional NR bands for UL-MIMO in Rel-18 | NR_bands_UL_MIMO_R18-Perf | 2023-12-12 | 25% | RP-223516 | 55%
27 | 9.4.1.3 | 981043 | 981043 | Introduction of the Satellite L-/S-Band for NR | NR_NTN_Lsband | 2023-12-12 |  | RP-230706 |  | RP-231178 | RP-231179 | No | Revised WID: Update the title of internal TR
27 | 9.4.1.3 | 981043 | 981143 | Core part: Introduction of the satellite L-/S-band for NR | NR_NTN_LSband-Core | 2023-12-12 | 10% | RP-230706 | 50%
27 | 9.4.1.3 | 981043 | 981243 | Perf. part: Introduction of the satellite L-/S-band for NR | NR_NTN_LSband-Perf | 2023-12-12 | 50% | RP-230706 | 90%
28 | 9.4.1.4 | 981045 | 981045 | Introduction of 900 MHz NR band in the US | NR_900MHz_US | 2022-12-12 |  | RP-230723 |  | RP-231422 |  | No
28 | 9.4.1.4 | 981045 | 981145 | Core Part: Introduction of 900 MHz NR band in the US | NR_900MHz_US-Core | 2023-12-12 | 5% | RP-230723 | 10%
28 | 9.4.1.4 | 981045 | 981245 | Perf. part: Introduction of 900 MHz NR band in the US | NR_900MHz_US-Perf | 2023-12-12 | 0% | RP-230723 | 5%
29 | 9.4.1.5 |  | 991039 | Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18 | NR_FDD_bands_R18_redcap | 2023-12-12 | 0% | RP-230743 | 40% | RP-231048 | RP-231049 | No | Revised WID: Add TS 38.307 as impacted existing TS/TR
29 | 9.4.1.5 |  | 991139 | Core part: Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18 | NR_FDD_bands_R18_redcap-Core | 2023-12-12 | 0% | RP-230743 | 40%
30 | 9.4.1.6 |  | 991042 | Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76 | NR_FDD_ULn28_DLn75_n76 | 2023-09-09 | 0% | RP-230791 |  | RP-231207 | RP-231204 | No | Revised WID: Update the band plan and add impacted spec-s
30 | 9.4.1.6 |  | 991142 | Core part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76 | NR_FDD_ULn28_DLn75_n76-Core | 2023-09-09 | 0% | RP-230791 | 40%
30 | 9.4.1.6 |  | 991242 | Perf. part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76 | NR_FDD_ULn28_DLn75_n76-Perf | 2023-09-09 | 0% | RP-230791 | 0%
31 | 9.4.2.1 | 961001 | 961001 | Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_1BLTE_1BNR_2DL2UL | 2023-12-12 |  | RP-223078 |  | RP-231085 | RP-231086 | No | Revised WID: Update band combinations
31 | 9.4.2.1 | 961001 | 961101 | Core part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_1BLTE_1BNR_2DL2UL-Core | 2023-12-12 | 30% | RP-223078 | 60%
31 | 9.4.2.1 | 961001 | 961201 | Perf. part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_1BLTE_1BNR_2DL2UL-Perf | 2023-12-12 | 0% | RP-223078 | 0%
32 | 9.4.2.2 | 961004 | 961004 | Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_2BLTE_1BNR_3DL2UL | 2023-12-12 | 50% | RP-230473 | 65% | RP-231131 | RP-231132 | No | Revised WID: Update band combinations
32 | 9.4.2.2 | 961004 | 961104 | Core part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_2BLTE_1BNR_3DL2UL-Core | 2023-12-12 | 50% | RP-230473 | 65%
32 | 9.4.2.2 | 961004 | 961204 | Perf. part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_2BLTE_1BNR_3DL2UL-Perf | 2023-12-12 | 50% | RP-230473 | 65%
33 | 9.4.2.3 | 961005 | 961005 | Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) | DC_R18_xBLTE_1BNR_yDL2UL | 2023-12-12 |  | RP-230090 |  | RP-230984 | RP-230985 | No | Revised WID: Update band combinations
33 | 9.4.2.3 | 961005 | 961105 | Core part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) | DC_R18_xBLTE_1BNR_yDL2UL-Core | 2023-12-12 | 25% | RP-230090 | 35%
33 | 9.4.2.3 | 961005 | 961205 | Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) | DC_R18_xBLTE_1BNR_yDL2UL-Perf | 2023-12-12 | 10% | RP-230090 | 25%
34 | 9.4.2.4 | 961003 | 961003 | Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R18_xBLTE_2BNR_yDL2UL | 2023-12-12 | 30% | RP-230725 | 50% | RP-231060 | RP-231059 | No | Revised WID: Update band combinations
34 | 9.4.2.4 | 961003 | 961103 | Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R18_xBLTE_2BNR_yDL2UL-Core | 2023-12-12 | 30% | RP-230725 | 50%
34 | 9.4.2.4 | 961003 | 961203 | Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R18_xBLTE_2BNR_yDL2UL-Perf | 2023-12-12 | 30% | RP-230725 | 50%
35 | 9.4.2.5 | 961006 | 961006 | Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) | DC_R18_xBLTE_yBNR_zDL2UL | 2023-12-12 | 40% | RP-230135 | 60% | RP-231118 | RP-231117 | No | Revised WID: Update band combinations
35 | 9.4.2.5 | 961006 | 961106 | Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) | DC_R18_xBLTE_yBNR_zDL2UL-Core | 2023-12-12 | 40% | RP-230135 | 60%
35 | 9.4.2.5 | 961006 | 961206 | Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) | DC_R18_xBLTE_yBNR_zDL2UL-Perf | 2023-12-12 | 40% | RP-230135 | 60%
36 | 9.4.2.6 | 961002 | 961002 | Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) | DC_R18_xBLTE_yBNR_zDL3UL | 2023-12-12 | 30% | RP-222237 | 50% | RP-231093 |  | No
36 | 9.4.2.6 | 961002 | 961102 | Core part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) | DC_R18_xBLTE_yBNR_zDL3UL-Core | 2023-12-12 | 30% | RP-222237 | 50%
36 | 9.4.2.6 | 961002 | 961202 | Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) | DC_R18_xBLTE_yBNR_zDL3UL-Perf | 2023-12-12 | 30% | RP-222237 | 50%
37 | 9.4.3.1 | 961007 | 961007 | Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R18_Intra | 2023-12-12 | 57% | RP-230067 | 80% | RP-231029 | RP-231030 | No | Revised WID: Update band combinations
37 | 9.4.3.1 | 961007 | 961107 | Core part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R18_Intra-Core | 2023-12-12 | 57% | RP-230067 | 80%
37 | 9.4.3.1 | 961007 | 961207 | Perf. part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R18_Intra-Perf | 2023-12-12 | 57% | RP-230067 | 80%
38 | 9.4.3.2 | 961010 | 961010 | Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | NR_CADC_R18_2BDL_xBUL | 2023-12-12 | 40% | RP-230133 | 60% | RP-231116 | RP-231115 | No | Revised WID: Update band combinations
38 | 9.4.3.2 | 961010 | 961110 | Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | NR_CADC_R18_2BDL_xBUL-Core | 2023-12-12 | 40% | RP-230133 | 60%
38 | 9.4.3.2 | 961010 | 961210 | Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | NR_CADC_R18_2BDL_xBUL-Perf | 2023-12-12 | 40% | RP-230133 | 60%
39 | 9.4.3.3 | 961011 | 961011 | Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) | NR_CADC_R18_3BDL_xBUL | 2023-12-12 | 40% | RP-230084 | 60% | RP-231101 | RP-231100 | No | Revised WID: Update band combinations
39 | 9.4.3.3 | 961011 | 961111 | Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) | NR_CADC_R18_3BDL_xBUL-Core | 2023-12-12 | 40% | RP-230084 | 60%
39 | 9.4.3.3 | 961011 | 961211 | Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) | NR_CADC_R18_3BDL_xBUL-Perf | 2023-12-12 | 40% | RP-230084 | 60%
40 | 9.4.3.4 | 961008 | 961008 | Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) | NR_CADC_R18_yBDL_xBUL | 2023-12-12 | 51% | RP-230421 | 53% | RP-231035 | RP-231034 | No | Revised WID: Update band combinations
40 | 9.4.3.4 | 961008 | 961108 | Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) | NR_CADC_R18_yBDL_xBUL-Core | 2023-12-12 | 51% | RP-230421 | 53%
40 | 9.4.3.4 | 961008 | 961208 | Perf. part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) | NR_CADC_R18_yBDL_xBUL-Perf | 2023-12-12 | 51% | RP-230421 | 53%
41 | 9.4.3.5 | 961009 | 961009 | Rel-18 band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R18 | 2023-12-12 | 40% | RP-230475 | 60% | RP-231133 | RP-231134 | No | Revised WID: Update band combinations
41 | 9.4.3.5 | 961009 | 961109 | Core part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R18-Core | 2023-12-12 | 40% | RP-230475 | 60%
41 | 9.4.3.5 | 961009 | 961209 | Perf. Part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R18-Perf | 2023-12-12 | 40% | RP-230475 | 60%
42 | 9.4.3.6 | 981047 | 981047 | WID on Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells | NR_2SUL_cell_combos_R18 | 2023-12-12 | 10% | RP-230719 | 30% | RP-231161 | RP-231162 | No | Revised WID: Update band combinations
42 | 9.4.3.6 | 981047 | 981147 | Core part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells | NR_2SUL_cell_combos_R18-Core | 2023-12-12 | 10% | RP-230719 | 30%
42 | 9.4.3.6 | 981047 | 981247 | Perf. part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells | NR_2SUL_cell_combos_R18-Perf | 2023-12-12 | 10% | RP-230719 | 30%
43 | 9.4.3.7 |  | 991046 | Enhancement for 700/800/900MHz band combinations for NR | NR_700800900_combo_en | 2023-12-12 | 0% | RP-230764 |  | RP-231270 | RP-231269 | No | Revised WID: Add Acronym and UID
43 | 9.4.3.7 |  | 991146 | Core part: Enhancement for 700/800/900MHz band combinations for NR | NR_700800900_combo_enh-Core | 2023-12-12 | 0% | RP-230764 | 50%
43 | 9.4.3.7 |  | 991246 | Perf. part: Enhancement for 700/800/900MHz band combinations for NR | NR_700800900_combo_enh-Perf | 2023-12-12 | 0% | RP-230764 | 0%
44 | 9.4.4.1 | 961012 | 961012 | High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands | LTE_NR_HPUE_FWVM_R18 | 2023-12-12 | 30% | RP-223424 | 50% | RP-231252 | Rev_RP-231251 | No | Revised WID: Add new bands
44 | 9.4.4.1 | 961012 | 961112 | Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands | LTE_NR_HPUE_FWVM_R18-Core | 2023-12-12 | 35% | RP-223424 | 50%
45 | 9.4.4.2 | 970085 | 970085 | High power UE (power class 1.5) for NR FR1 TDD single band | HPUE_NR_FR1_TDD_R18 | 2023-12-12 | 30% | RP-223499 | 60% | RP-231154 |  | No
45 | 9.4.4.2 | 970085 | 970185 | Core part: High power UE (power class 1.5) for NR FR1 TDD single band | HPUE_NR_FR1_TDD_R18-Core | 2023-12-12 | 30% | RP-223499 | 60%
46 | 9.4.4.3 | 970086 | 970086 | High power UE (power class 2) for NR FR1 FDD single band | HPUE_NR_FR1_FDD_R18 | 2023-12-12 | 10% | RP-230352 | 30% | RP-231062 | RP-231064 | No | Revised WID: Add new bands
46 | 9.4.4.3 | 970086 | 970186 | Core part: High power UE (power class 2) for NR FR1 FDD single band | HPUE_NR_FR1_FDD_R18-Core | 2023-12-12 | 10% | RP-230352 | 30%
46 | 9.4.4.3 | 970086 | 970286 | Perf. part: High power UE (power class 2) for NR FR1 FDD single band | HPUE_NR_FR1_FDD_R18-Perf | 2023-12-12 | 10% | RP-230352 | 30%
47 | 9.4.4.4 | 970087 | 970087 | High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band | HPUE_NR_FR1_TDD_intra_CA_R18 | 2023-12-12 |  | RP-230479 |  | RP-231138 | RP-231139 | No | Revised WID: Update band combinations
47 | 9.4.4.4 | 970087 | 970187 | Core part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band | HPUE_NR_FR1_TDD_intra_CA_R18-Core | 2023-12-12 | 30% | RP-230479 | 50%
47 | 9.4.4.4 | 970087 | 970287 | Perf. part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band | HPUE_NR_FR1_TDD_intra_CA_R18-Perf | 2023-12-12 | 0% | RP-230479 | 0%
48 | 9.4.4.5 | 970088 | 970088 | Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) | HPUE_FR1_DC_LTE_NR_R18 | 2023-12-12 | 19% | RP-230069 | 47% | RP-231031 | RP-231032 | No | Revised WID: Update band combinations
48 | 9.4.4.5 | 970088 | 970188 | Core part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) | HPUE_FR1_DC_LTE_NR_R18-Core | 2023-12-12 | 19% | RP-230069 | 47%
48 | 9.4.4.5 | 970088 | 970288 | Perf. part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) | HPUE_FR1_DC_LTE_NR_R18-Perf | 2023-12-12 | 19% | RP-230069 | 47%
49 | 9.4.4.6 | 970089 | 970089 | Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_TDD_NR_CADC_SUL_R18 | 2023-12-12 |  | RP-223496 |  | RP-231197 | RP-231196 | No | Revised WID: Update band combinations
49 | 9.4.4.6 | 970089 | 970189 | Core part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_TDD_NR_CADC_SUL_R18-Core | 2023-12-12 | 30% | RP-223496 | 50%
49 | 9.4.4.6 | 970089 | 970289 | Perf. part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_TDD_NR_CADC_SUL_R18-Perf | 2023-12-12 | 0% | RP-223496 | 0%
50 | 9.4.4.7 | 970090 | 970090 | Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR inter-band CA/DC combinations with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_FDD_NR_CADC_R18 | 2023-12-12 | 10% | RP-222968 | 30% | RP-231061 | RP-231063 | No | Revised WID: Update band combinations
50 | 9.4.4.7 | 970090 | 970190 | Core part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR inter-band CA/DC combinations with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_FDD_NR_CADC_R18-Core | 2023-12-12 | 10% | RP-230354 | 30%
50 | 9.4.4.7 | 970090 | 970290 | Perf. part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR inter-band CA/DC combinations with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_FDD_NR_CADC_R18-Perf | 2023-12-12 | 10% | RP-230354 | 30%
51 | 9.4.5.1 | 960096 | 960096 | Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band | NR_LTE_V2X_PC5_combos_R18 | 2023-12-12 |  | RP-230390 |  | RP-231268 |  | No
51 | 9.4.5.1 | 960096 | 960196 | Core part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band | NR_LTE_V2X_PC5_combos_R18-Core | 2023-12-12 | 50% | RP-230390 | 50%
51 | 9.4.5.1 | 960096 | 960296 | Perf. part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band | NR_LTE_V2X_PC5_combos_R18-Perf | 2023-12-12 | 0% | RP-230390 | 0%
52 | 9.4.5.2 | 960093 | 960093 | Enhancements of NR shared spectrum bands | NR_unlic_enh | 2023-06-12 |  | RP-230730 | 100% | RP-231177 |  | No | WI is completed.
52 | 9.4.5.2 | 960093 | 960193 | Core part: Enhancements of NR shared spectrum bands | NR_unlic_enh-Core | 2023-06-06 | 85% | RP-230730 | 100%
53 | 9.4.5.3 | 960094 | 960094 | Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R18 | 2022-12-12 |  | RP-222288 |  | RP-231193 | RP-231194 | No | Revised WID: Update UID
53 | 9.4.5.3 | 960094 | 960194 | Core part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R18-Core | 2023-12-12 | 99% | RP-222288 | 99%
53 | 9.4.5.3 | 960094 | 960294 | Perf. part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R18-Perf | 2023-12-12 | 0% | RP-222288 | 0%
54 | 9.4.5.4 | 970083 | 970083 | Adding new channel bandwidth(s) support to existing NR bands | NR_bands_R18_BWs | 2023-12-12 | 5% | RP-230756 | 15% | RP-231009 | RP-231010 | No | Revised WID: Add new band + new CBW
54 | 9.4.5.4 | 970083 | 970183 | Core part: Adding new channel bandwidth(s) support to existing NR bands | NR_bands_R18_BWs-Core | 2023-12-12 | 5% | RP-230756 | 15%
55 | 9.4.5.5 | 970084 | 970084 | Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | LTE_NR_Simult_RxTx_R18 | 2023-12-12 | 40% | RP-223354 | 70% | RP-231137 |  | No
55 | 9.4.5.5 | 970084 | 970184 | Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | LTE_NR_Simult_RxTx_R18-Core | 2023-12-12 | 40% | RP-223354 | 70%
55 | 9.4.5.5 | 970084 | 970284 | Perf. part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | LTE_NR_Simult_RxTx_R18-Perf | 2023-12-12 | 40% | RP-223354 | 70%
56 | 9.4.5.6 | 981041 | 981041 | Low NR band 4Rx for handheld UE and 3Tx for inter-band UL CA and EN-DC | 4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC | 2023-12-12 | 10% | RP-230161 | 70% | RP-231012 | RP-231013 | No | Revised WID: confirm the feasbility of 4Rx at lower frequency band and update the band/band combinations. Discussions on how to handle increasing number of band combinations would be needed.
56 | 9.4.5.6 | 981041 | 981141 | Core part: 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | 4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-Core | 2023-12-12 | 10% | RP-230161 | 70%
57 | 9.4.5.7 | 981042 | 981042 | Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) | 4Rx_NR_bands_R18 | 2023-12-12 | 30% | RP-230137 | 35% | RP-231120 | RP-231119 | No | Revised WID: Add new band
57 | 9.4.5.7 | 981042 | 981142 | Core part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) | 4Rx_NR_bands_R18-Core | 2023-12-12 | 30% | RP-230137 | 35%
57 | 9.4.5.7 | 981042 | 981242 | Perf. part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) | 4Rx_NR_bands_R18-Perf | 2023-12-12 | 30% | RP-230137 | 35%
58 | 10.3.1 | 920071 | 920071 | New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 | LTE_terr_bcast_bands_part2 | 2023-06-12 | 30% | RP-223378 | 90% | RP-231215 | RP-231216 | No | WI needs be extended. Revised WID: change target date. Some discussions on band definition (RP-231217)
58 | 10.3.1 | 920071 | 920171 | Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 | LTE_terr_bcast_bands_part2-Core | 2023-06-12 | 50% | RP-223378 | 90%
59 | 10.3.2 | 981046 | 981046 | New WID for 900MHz LTE Band | LTE_900MHz_US | 2023-06-12 | 0% | RP-230722 | 100% | RP-231218 |  | No | WI is completed
59 | 10.3.2 | 981046 | 981146 | Core part: Introduction of 900 MHz LTE band in the US | LTE_900MHz_US-Core | 2023-06-12 | 20% | RP-230722 | 100%
59 | 10.3.2 | 981046 | 981246 | Perf. part: Introduction of 900 MHz LTE band in the US | LTE_900MHz_US-Perf | 2023-06-12 | 10% | RP-230722 | 100%
60 | 10.3.3 | 981048 | 981048 | LTE bands for UE category M1&M2 and/or NB1&NB2 in Rel-18 | LTE_bands_R18_M1_M2_NB1_NB2 | 2023-12-12 | 99% | RP-222824 | 99% | RP-231047 |  | No
60 | 10.3.3 | 981048 | 981148 | Core part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 | LTE_bands_R18_M1_M2_NB1_NB2-Core | 2023-12-12 | 99% | RP-222824 | 99%
60 | 10.3.3 | 981048 | 981248 | Perf. part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 | LTE_bands_R18_M1_M2_NB1_NB2-Perf | 2023-12-12 | 99% | RP-222824 | 99%
61 | 10.3.4 |  | 991040 | Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW | 2023-09-09 | 0% | RP-230745 | 0% | RP-231111 |  | Yes | WI is proposed to be stopped
61 | 10.3.4 |  | 991140 | Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW-Core | 2023-06-06 | 0% | RP-230745 | 0%
61 | 10.3.4 |  | 991240 | Perf. part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW-Perf | 2023-09-09 | 0% | RP-230745 | 0%
62 | 10.3.5 |  | 991041 | Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband | 2023-12-12 | 0% | RP-230790 |  | RP-231302 | RP-231301 | No | Revised WID: Add objective for additional regional requirements. Editorial changes.
62 | 10.3.5 |  | 991141 | Core part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband-Core | 2023-09-09 | 0% | RP-230790 | 10%
62 | 10.3.5 |  | 991241 | Perf. part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband-Perf | 2023-12-12 | 0% | RP-230790 | 0%
63 | 10.3.6 |  | 991043 | Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band | 2024-06-06 | 0% | RP-230792 |  | RP-231315 | RP-231317 | No | Revised WID: Add new TR. Rapporteur.
63 | 10.3.6 |  | 991143 | Core part: Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band-Core | 2023-12-12 | 0% | RP-230792 | 30%
63 | 10.3.6 |  | 991243 | Perf. part: Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band-Perf | 2024-06-06 | 0% | RP-230792 | 0%
64 | 10.3.7.1 | 960099 | 960099 | Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R18_xBDL_yBUL | 2023-12-12 | 35% | RP-230471 | 35% | RP-231129 | RP-231130 | No | Revised WID: Update band combinations
64 | 10.3.7.1 | 960099 | 960199 | Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R18_xBDL_yBUL-Core | 2023-12-12 | 35% | RP-230471 | 35%
64 | 10.3.7.1 | 960099 | 960299 | Perf. part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R18_xBDL_yBUL-Perf | 2023-12-12 | 35% | RP-230471 | 35%
65 |  | 960097 | 960097 | APT 600MHz NR band | NR_600MHz_APT | 2023-03-23 | closed | RP-223265 |  | RP-230053 | RP-230060
65 |  | 960097 | 960197 | Core part: APT 600MHz NR band | NR_600MHz_APT-Core | 2023-03-03 | closed | RP-221778
65 |  | 960097 | 960297 | Perf. part: APT 600MHz NR band | NR_600MHz_APT-Perf | 2023-03-03 | closed | RP-221778
66 |  | 981044 | 981044 | New WID: Introduction of NR TDD band in 1670 – 1675 MHz | NR_TDD_n54 | 2023-03-23 | closed | RP-223514 |  | RP-230061 | RP-230062
66 |  | 981044 | 981144 | Core part: Introduction of NR TDD band in 1670-1675 MHz (n54) | NR_TDD_n54-Core | 2023-03-03 | closed | RP-230062
66 |  | 981044 | 981244 | Perf. part: Introduction of NR TDD band in 1670-1675 MHz (n54) | NR_TDD_n54-Perf | 2023-03-03 | closed | RP-230062
67 |  | 961013 | 961013 | High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe | NR_RAIL_HPUE_n100_n101 | 2023-12-14 | Stopped | RP-221878
67 |  | 961013 | 961113 | Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe | NR_RAIL_HPUE_n100_n101-Core | 2023-12-14 | stopped | RP-221878
68 |  | 950071 | 950071 | Introduction of LTE TDD band in 1670-1675 MHz | LTE_TDD_1670_1675MHz | 2022-12-16 | closed | RP-220971
68 |  | 950071 | 950171 | Core part: Introduction of LTE TDD band in 1670-1675 MHz | LTE_TDD_1670_1675MHz-Core | 2022-12-01 | closed | RP-222831
68 |  | 950071 | 950271 | Perf. part: Introduction of LTE TDD band in 1670-1675 MHz | LTE_TDD_1670_1675MHz-Perf | 2022-12-01 | closed | RP-222831
69 |  | 961000 | 961000 | LTE intra-band contiguous Carrier Aggregation for band 8 | LTE_CA_intra_B8 | 2022-12-16 | closed | RP-221846
69 |  | 961000 | 961100 | Core part: LTE intra-band contiguous Carrier Aggregation for band 8 | LTE_CA_intra_B8-Core | 2022-12-16 | closed | RP-221846