## Band combination table
Are there any change marks? (More explanation can be found in coversheet) | Band combination configuration | UpLink configuration | Power Class | Subclass | Contact Name | Contact Company | Contact Email | Other supporting companies (min.3) | RAN Plenary in which the combination was requested | Related WI (acronym) | Supported next level fallback modes including initial status when requesting (in DL and UL) | Status (New,Ongoing,Completed,Stopped) | TR# | TPs provided as input for TR | CRs provided to RAN: RAN4 Tdoc (list all specs input) | Core. part Done? (Including all fallback combos ) yes/no | Perf. part Done? yes/no | Open issues/Comments | Note
Unchange | DC_2A-13A-66A_n77A | DC_2A_n77A, DC_13A_n77A, DC_66A_n77A | PC2 | FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-66A_n77A_UL_2A_n77A, (Ongoing) DL_2A-13A_n77A_UL_2A_n77A, (Ongoing) DL_13A-66A_n77A_UL_13A_n77A, (Ongoing) DL_2A-13A_n77A_UL_13A_n77A, (Ongoing) DL_2A-66A_n77A_UL_66A_n77A, (Ongoing) DL_13A-66A_n77A_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_48D-66A_n77A | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (New) DL_48C-66A_n77A_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-66A_n5A-n77A | DC_66A_n77A DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, LGE, MediaTek, Verizon, Qualcomm, Samsung, Ericsson | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (new) DL_2A-66A_n77A_UL_66A_n77A (new) DL_66A_n5A-n77A_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A_n5A-n77A | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, LGE, MediaTek, Verizon, Qualcomm, Samsung, Ericsson | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (Completed) DL_2A-2A_n77A_UL_2A_n77A (new) DL_2A_n5A-n77A_UL_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_13A-66A-66A_n2A-n77A | DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, LGE, MediaTek, Verizon, Qualcomm, Samsung, Ericsson | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (new) DL_13A-66A-66A_n77A_UL_13A_n77A (new) DL_13A-66A-66A_n77A_UL_66A_n77A (New) DL_13A-66A_n2A-n77A_UL_13A_n77A (New) DL_13A-66A_n2A-n77A_UL_66A_n77A (New) DL_66A-66A_n2A-n77A_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-66A-66A_n5A-n77A | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, LGE, MediaTek, Verizon, Qualcomm, Samsung, Ericsson | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (new) DL_2A-66A-66A_n77A_UL_2A_n77A (new) DL_2A-66A-66A_n77A_UL_66A_n77A (new) DL_2A-66A_n5A-n77A_UL_2A_n77A (new) DL_2A-66A_n5A-n77A_UL_66A_n77A (new) DL_66A-66A_n5A-n77A_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A-66A_n5A-n77A | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, LGE, MediaTek, Verizon, Qualcomm, Samsung, Ericsson | RAN#95 | DC_R18_xBLTE_yBNR_zDLnUL | (new) DL_2A-2A-66A_n77A_UL_2A_n77A (new) DL_2A-2A-66A_n77A_UL_66A_n77A (New) DL_2A-2A_n5A-n77A_UL_2A_n77A (new) DL_2A-66A_n5A-n77A_UL_2A_n77A (new) DL_2A-66A_n5A-n77A_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DC_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_5A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DC_5A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_13A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DC_13A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_66A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DC_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_13A-66A_n77C | DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_13A-66A_n77A_UL_13A_n77A (Complete) DL_13A-66A_n77A_UL_66A_n77A (New) DL_13A_n77C_UL_13A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-66A_n77A_UL_2A_n77A (Complete) DL_2A-66A_n77A_UL_66A_n77A (New) DL_2A_n77C_UL_2A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-13A_n77C | DC_2A_n77A DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-13A_n77A_UL_2A_n77A (Complete) DL_2A-13A_n77A_UL_13A_n77A (New) DL_2A_n77C_UL_2A_n77A (New) DL_13A_n77C_UL_13A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_66A-66A_n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_66A-66A_n77A_UL_66A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-5A_n77C | DC_2A_n77A DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-5A_n77A_UL_2A_n77A (Complete) DL_2A-5A_n77A_UL_5A_n77A (New) DL_2A_n77C_UL_2A_n77A (New) DL_5A_n77C_UL_5A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-48A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-48A_n77A_UL_2A_n77A (New) DL_2A_n77C_UL_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_48A-66A_n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_48A-66A_n77A_UL_66A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A_n77A_UL_2A_n77A (New) DL_2A_n77C_UL_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-13A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-13A-66A_n77A_UL_2A_n77A (Complete) DL_2A-13A-66A_n77A_UL_13A_n77A (Complete) DL_2A-13A-66A_n77A_UL_66A_n77A (New) DL_2A-13A_n77C_UL_2A-n77A (New) DL_2A-13A_n77C_UL_13A-n77A (New) DL_2A-66A_n77C_UL_2A-n77A (New) DL_2A-66A_n77C_UL_66A-n77A (New) DL_13A-66A_n77C_UL_13A-n77A (New) DL_13A-66A_n77C_UL_66A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_13A-66A-66A_n77C | DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_13A-66A-66A_n77A_UL_13A_n77A (Ongoing) DL_13A-66A-66A_n77A_UL_66A_n77A (New) DL_13A-66A_n77C_UL_13A-n77A (New) DL_13A-66A_n77C_UL_66A-n77A (New) DL_66A-66A_n77C_UL_66A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-5A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-5A-66A_n77A_UL_2A_n77A (Complete) DL_2A-5A-66A_n77A_UL_5A_n77A (Complete) DL_2A-5A-66A_n77A_UL_66A_n77A (New) DL_2A-5A_n77C_UL_2A-n77A (New) DL_2A-5A_n77C_UL_5A-n77A (New) DL_2A-66A_n77C_UL_2A-n77A (New) DL_2A-66A_n77C_UL_66A-n77A (New) DL_5A-66A_n77C_UL_5A-n77A (New) DL_5A-66A_n77C_UL_66A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-66A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-66A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-66A-66A_n77A_UL_66A_n77A (New) DL_2A-66A_n77C_UL_2A-n77A (New) DL_2A-66A_n77C_UL_66A-n77A (New) DL_66A-66A_n77C_UL_66A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_5A-66A-66A_n77C | DC_5A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_5A-66A-66A_n77A_UL_5A_n77A (Ongoing) DL_5A-66A-66A_n77A_UL_66A_n77A (New) DL_5A-66A_n77C_UL_5A-n77A (New) DL_5A-66A_n77C_UL_66A-n77A (New) DL_66A-66A_n77C_UL_66A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A-13A_n77C | DC_2A_n77A DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-13A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-13A_n77A_UL_13A_n77A (New) DL_2A-13A_n77C_UL_2A-n77A (New) DL_2A-13A_n77C_UL_13A-n77A (New) DL_2A-2A_n77C_UL_2A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-66A_n77A_UL_66A_n77A (New) DL_2A-66A_n77C_UL_2A-n77A (New) DL_2A-66A_n77C_UL_66A-n77A (New) DL_2A-2A_n77C_UL_2A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A-5A_n77C | DC_2A_n77A DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-5A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-5A_n77A_UL_5A_n77A (New) DL_2A-5A_n77C_UL_2A-n77A (New) DL_2A-5A_n77C_UL_5A-n77A (New) DL_2A-2A_n77C_UL_2A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_66A-66A-66A_n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_66A-66A-66A_n77A_UL_66A_n77A (New) DL_66A-66A_n77C_UL_66A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-48C_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-48C_n77A_UL_2A-n77A (New) DL_2A-48A_n77C_UL_2A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_48C-66A_n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_48C-66A_n77A_UL_66A-n77A (New) DL_48A-66A_n77C_UL_66A-n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-13A-66A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-13A-66A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-13A-66A-66A_n77A_UL_13A_n77A (Ongoing) DL_2A-13A-66A-66A_n77A_UL_66A_n77A (New) DL_2A-13A-66A_n77C_UL_2A_n77A (New) DL_2A-13A-66A_n77C_UL_13A_n77A (New) DL_2A-13A-66A_n77C_UL_66A_n77A (New) DL_2A-66A-66A_n77C_UL_2A_n77A (New) DL_2A-66A-66A_n77C_UL_66A_n77A (New) DL_13A-66A-66A_n77C_UL_13A_n77A (New) DL_13A-66A-66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-5A-66A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-5A-66A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-5A-66A-66A_n77A_UL_5A_n77A (Ongoing) DL_2A-5A-66A-66A_n77A_UL_66A_n77A (New) DL_2A-5A-66A_n77C_UL_2A_n77A (New) DL_2A-5A-66A_n77C_UL_5A_n77A (New) DL_2A-5A-66A_n77C_UL_66A_n77A (New) DL_2A-66A-66A_n77C_UL_2A_n77A (New) DL_2A-66A-66A_n77C_UL_66A_n77A (New) DL_5A-66A-66A_n77C_UL_5A_n77A (New) DL_5A-66A-66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A-13A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-13A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-13A-66A_n77A_UL_13A_n77A (Ongoing) DL_2A-2A-13A-66A_n77A_UL_66A_n77A (New) DL_2A-13A-66A_n77C_UL_2A_n77A (New) DL_2A-13A-66A_n77C_UL_13A_n77A (New) DL_2A-13A-66A_n77C_UL_66A_n77A (New) DL_2A-2A-13A_n77C_UL_2A_n77A (New) DL_2A-2A-13A_n77C_UL_13A_n77A (New) DL_2A-2A-66A_n77C_UL_2A_n77A (New) DL_2A-2A-66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A-5A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-5A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-5A-66A_n77A_UL_5A_n77A (Ongoing) DL_2A-2A-5A-66A_n77A_UL_66A_n77A (New) DL_2A-5A-66A_n77C_UL_2A_n77A (New) DL_2A-5A-66A_n77C_UL_5A_n77A (New) DL_2A-5A-66A_n77C_UL_66A_n77A (New) DL_2A-2A-5A_n77C_UL_2A_n77A (New) DL_2A-2A-5A_n77C_UL_5A_n77A (New) DL_2A-2A-66A_n77C_UL_2A_n77A (New) DL_2A-2A-66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A-66A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A-66A-66A_n77A_UL_2A_n77A (Ongoing) DL_2A-2A-66A-66A_n77A_UL_66A_n77A (New) DL_2A-2A-66A_n77C_UL_2A_n77A (New) DL_2A-2A-66A_n77C_UL_66A_n77A (New) DL_2A-66A-66A_n77C_UL_2A_n77A (New) DL_2A-66A-66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-48D_n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-48D_n77A_UL_2A_n77A (New) DL_2A-48C_n77C_UL_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_48D-66A_n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_48D-66A_n77A_UL_66A_n77A (New) DL_48C-66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_13A_n2A-n77C | DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_13A_n2A-n77A_UL_13A_n77A (New) DL_13A_n77C_UL_13A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_13A_n66A-n77C | DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_13A_n66A-n77A_UL_13A_n77A (New) DL_13A_n77C_UL_13A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A_n2A-n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A_n2A-n77A_UL_2A_n77A (New) DL_2A_n77C_UL_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_5A_n2A-n77C | DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_5A_n2A-n77A_UL_5A_n77A (New) DL_5A_n77C_UL_5A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_66A_n2A-n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_66A_n2A-n77A_UL_66A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A_n5A-n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A_n5A-n77A_UL_2A_n77A (New) DL_2A_n77C_UL_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_5A_n5A-n77C | DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_5A_n5A-n77A_UL_5A_n77A (New) DL_5A_n77C_UL_5A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_13A_n5A-n77C | DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_13A_n5A-n77A_UL_13A_n77A (New) DL_13A_n77C_UL_13A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_66A_n5A-n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_66A_n5A-n77A_UL_66A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A_n66A-n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A_n66A-n77A_UL_2A_n77A (New) DL_2A_n77C_UL_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_5A_n66A-n77C | DC_5A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_5A_n66A-n77A_UL_5A_n77A (New) DL_5A_n77C_UL_5A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_13A_n66A-n77C | DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_13A_n66A-n77A_UL_13A_n77A (New) DL_13A_n77C_UL_13A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_66A_n66A-n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_66A_n66A-n77A_UL_66A_n77A (New) DL_66A_n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_13A-66A_n2A-n77C | DC_13A_n77A DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_13A-66A_n2A-n77A_UL_13A_n77A (Complete) DL_13A-66A_n2A-n77A_UL_66A_n77A (New) DL_13A-66A_n77C_UL_13A_n77A (New) DL_13A-66A_n77C_UL_66A_n77A (New) DL_13A_n2A-n77C_UL_13A_n77A (New) DL_66A_n2A-n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_66A-66A_n2A-n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_66A-66A_n2A-n77A_UL_66A_n77A (New) DL_66A-66A_n77C_UL_66A_n77A (New) DL_66A_n2A-n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-66A_n5A-n77C | DC_66A_n77A DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_2A-66A_n5A-n77A_UL_2A_n77A (Complete) DL_2A-66A_n5A-n77A_UL_66A_n77A (New) DL_2A-66A_n77C_UL_2A_n77A (New) DL_2A-66A_n77C_UL_66A_n77A (New) DL_2A_n5A-n77C_UL_2A_n77A (New) DL_66A_n5A-n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_66A-66A_n5A-n77C | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Complete) DL_66A-66A_n5A-n77A_UL_66A_n77A (New) DL_66A-66A_n77C_UL_66A_n77A (New) DL_66A_n5A-n77C_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A_n5A-n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A_n5A-n77A_UL_2A_n77A (New) DL_2A-2A_n77C_UL_2A_n77A (New) DL_2A_n5A-n77C_UL_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-2A_n66A-n77C | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Nokia, Qualcomm, Samsung, Ericsson | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (Ongoing) DL_2A-2A_n66A-n77A_UL_2A_n77A (New) DL_2A-2A_n77C_UL_2A_n77A (New) DL_2A_n66A-n77C_UL_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_n78A-n258A/B/C/D/E/F/G/H/I/J/K/L/M | DC_n78A-n258A/G/H/I | PC2 | FR1+FR2 | Jeremy Chu | Telstra | jeremy.chu@team.telstra.com | LGE, Ericsson, Mediatek | RAN#93 | DC_R18_xBLTE_yBNR_zDLnUL | (complete) DL_n78A-n258A_UL_n78A-n258A_PC3 | Ongoing |  |  |  | No | No
Unchange | DC_5A-66A-66A_n77A | DC_5A_n77A, DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (completed) DL_5A-66A_n77A_UL_5A_n77A, (completed) DL_5A-66A_n77A_UL_66A_n77A, (completed) DL_66A-66A_n77A_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_13A-48A_n77A | DC_13A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (Completed) DL_13A_n77A_UL_13A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_2A-48A_n77A | DC_2A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (complete) DL_2A_n77A_UL_2A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_48A-66A_n77A | DC_66A_n77A | PC2 | Only FR1 | Zheng Zhao | Verizon | Zheng.zhao@verizonwireless.com | Ericsson, Nokia, Samsung, Qualcomm | RAN#94 | DC_R18_xBLTE_yBNR_zDLnUL | (complete) DL_66A_n77A_UL_66A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_1A_n77A | DC_1A_n77A | PC2 | Only FR1 | Yuanyuan Zhang | Samsung | Tina55.zhang@samsung.com | KT, Ericsson, Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_3A_n77A | DC_3A_n77A | PC2 | Only FR1 | Yuanyuan Zhang | Samsung | Tina55.zhang@samsung.com | KT, Ericsson, Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_1A-3A_n77A | DC_1A_n77A DC_3A_n77A | PC2 | Only FR1 | Yuanyuan Zhang | Samsung | Tina55.zhang@samsung.com | KT, Ericsson, Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A_n77A_UL_1A_n77A_PC2 (New)DL_3A_n77A_UL_3A_n77A_PC2 | Ongoing |  |  |  | No | No
Unchange | DC_1A-3A-41A_n28A-n77A | DC_1A_n77A DC_3A_n77A DC_41A_n77A | PC2 | 3LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A-3A-41A_n77A_UL_1A_n77A (New)DL_1A-3A-41A_n77A_UL_3A_n77A (New)DL_1A-3A-41A_n77A_UL_41A_n77A (New)DL_1A-3A_n28A-n77A_UL_1A_n77A (New)DL_1A-3A_n28A-n77A_UL_3A_n77A (New)DL_1A-41A_n28A-n77A_UL_1A_n77A (New)DL_1A-41A_n28A-n77A_UL_41A_n77A (New)DL_3A-41A_n28A-n77A_UL_3A_n77A (New)DL_3A-41A_n28A-n77A_UL_41A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_1A-3A-41A_n41A | DC_1A_n41A DC_3A_n41A DC_41A_n41A | PC2 | 3LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A-3A_n41A_UL_1A_n41A (New)DL_1A-3A_n41A_UL_3A_n41A (New)DL_1A-41A_n41A_UL_1A_n41A (New)DL_1A-41A_n41A_UL_41A_n41A (New)DL_3A-41A_n41A_UL_3A_n41A (New)DL_3A-41A_n41A_UL_41A_n41A | Ongoing |  |  |  | No | No
Unchange | DC_1A-3A-18A_n77A | DC_1A_n77A DC_3A_n77A DC_18A_n77A | PC2 | 3LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (Ongoing)DL_1A-3A-n77A_UL_1A_n77A (Ongoing)DL_1A-3A-n77A_UL_3A_n77A (New)DL_1A-18A_n77A_UL_1A_n77A (New)DL_1A-18A_n77A_UL_18A_n77A (New)DL_3A-18A_n77A_UL_3A_n77A (New)DL_3A-18A_n77A_UL_18A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_1A-3A-41A_n77(2A) | DC_1A_n77A DC_3A_n77A DC_41A_n77A | PC2 | 3LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A-3A-41A_n77A_UL_1A_n77A (New)DL_1A-3A-41A_n77A_UL_3A_n77A (New)DL_1A-3A-41A_n77A_UL_41A_n77A (Ongoing)DL_1A-3A_n77(2A)_UL_1A_n77A (Ongoing)DL_1A-3A_n77(2A)_UL_3A_n77A (New)DL_1A-41A_n77(2A)_UL_1A_n77A (New)DL_1A-41A_n77(2A)_UL_41A_n77A (New)DL_3A-41A_n77(2A)_UL_3A_n77A (New)DL_3A-41A_n77(2A)_UL_41A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_1A-3A-41A_n77A | DC_1A_n77A DC_3A_n77A DC_41A_n77A | PC2 | 3LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A-3A-n77A_UL_1A_n77A (New)DL_1A-3A-n77A_UL_3A_n77A (New)DL_1A-41A_n77A_UL_1A_n77A (New)DL_1A-41A_n77A_UL_41A_n77A (New)DL_3A-41A_n77A_UL_3A_n77A (New)DL_3A-41A_n77A_UL_41A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_1A-3A_n28A-n77A | DC_1A_n77A DC_3A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (Ongoing)DL_1A-3A_n77A_UL_1A_n77A (Ongoing)DL_1A-3A-n77A_UL_3A_n77A (New)DL_1A_n28-n77A_UL_1A_n77A (New)DL_3A_n28-n77A_UL_3A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_1A-41A_n28A-n77A | DC_1A_n77A DC_41A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A-41A_n77A_UL_1A_n77A (New)DL_1A-41A-n77A_UL_41A_n77A (New)DL_1A_n28-n77A_UL_1A_n77A (New)DL_41A_n28-n77A_UL_41A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_1A-3A_n41A | DC_1A_n41A DC_3A_n41A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A_n41A_UL_1A_n41A (New)DL_3A_n41A_UL_3A_n41A | Ongoing |  |  |  | No | No
Unchange | DC_1A-41A_n41A | DC_1A_n41A DC_41A_n41A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A_n41A_UL_1A_n41A (New)DL_41A_n41A_UL_41A_n41A | Ongoing |  |  |  | No | No
Unchange | DC_3A-41A_n41A | DC_3A_n41A DC_41A_n41A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_3A_n41A_UL_3A_n41A (New)DL_41A_n41A_UL_41A_n41A | Ongoing |  |  |  | No | No
Unchange | DC_1A-18A_n77A | DC_1A_n77A DC_18A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A_n77A_UL_1A_n77A (New)DL_18A_n77A_UL_18A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_3A-18A_n77A | DC_3A_n77A DC_18A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_3A_n77A_UL_3A_n77A (New)DL_18A_n77A_UL_18A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_1A-41A_n77(2A) | DC_1A_n77A DC_41A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A_41A_n77A_UL_1A_n77A (New)DL_1A_41A_n77A_UL_41A_n77A (Ongoing)DL_1A_n77(2A)_UL_1A_n77A (New)DL_41A_n77(2A)_UL_41A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_3A-41A_n77(2A) | DC_3A_n77A DC_41A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Samsung,Ericsson,Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_3A_41A_n77A_UL_3A_n77A (New)DL_3A_41A_n77A_UL_41A_n77A (Ongoing)DL_3A_n77(2A)_UL_3A_n77A (New)DL_41A_n77(2A)_UL_41A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_48A_n77A | n77 | PC2 | Only FR1 | Ron Borsato | AT&T | ronald.borsato@att.com | Ericsson, Qualcomm, Nokia | RAN#98 | HPUE_FR1_DC_LTE_NR_R18-Core | complete for PC3, new for PC2 | Ongoing |  |  |  | No | No
Unchange | DC_7A-7A_n78A | DC_7A_n78A | PC2 | 1LTE | Per Lindell | Ericsson | per.lindell@ericsson.com | Bell Mobility, TELUS, Nokia, Samsung | RAN#99 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | Ongoing |  |  |  | No | No
Unchange | DC_1A-18A_n28A-n77A | DC_1A_n77A DC_18A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung | RAN#99 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (Ongoing)DL_1A-18A_n77A_UL_1A_n77A (New)DL_1A-18A-n77A_UL_18A_n77A (New)DL_1A_n28A-n77A_UL_1A_n77A (New)DL_18A_n28A-n77A_UL_18A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_3A-18A_n28A-n77A | DC_3A_n77A DC_18A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung | RAN#99 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (Ongoing)DL_3A-18A_n77A_UL_3A_n77A (New)DL_3A-18A-n77A_UL_18A_n77A (New)DL_3A_n28A-n77A_UL_3A_n77A (New)DL_18A_n28A-n77A_UL_18A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_3A-18A_n41A-n77A | DC_3A_n41A DC_18A_n41A DC_3A_n77A DC_18A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung | RAN#99 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_3A-18A_n41A_UL_3A_n41A (New)DL_3A-18A_n41A_UL_18A_n41A (Ongoing)DL_3A-18A_n77A_UL_3A_n77A (Ongoing)DL_3A-18A_n77A_UL_18A_n77A (New)DL_3A_n41A-n77A_UL_3A_n41A (New)DL_18A_n41A-n77A_UL_18A_n41A (New)DL_3A_n41A-n77A_UL_3A_n77A (New)DL_18A_n41A-n77A_UL_18A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_1A-28A_n41A-n77A | DC_1A_n41A DC_28A_n41A DC_1A_n77A DC_28A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#99 | HPUE_FR1_DC_LTE_NR_R18-Core | new for PC3 (New)DL_1A-28A_n41A_UL_1A_n41A (New)DL_1A-28A_n41A_UL_28A_n41A (New)DL_1A-28A_n77A_UL_1A_n77A (New)DL_1A-28A_n77A_UL_28A_n77A (New)DL_1A_n41A-n77A_UL_1A_n41A (New)DL_28A_n41A-n77A_UL_28A_n41A (New)DL_1A_n41A-n77A_UL_1A_n77A (New)DL_28A_n41A-n77A_UL_28A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_3A-28A_n41A-n77A | DC_3A_n41A DC_28A_n41A DC_3A_n77A DC_28A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#99 | HPUE_FR1_DC_LTE_NR_R18-Core | new for PC3 (New)DL_3A-28A_n41A_UL_3A_n41A (New)DL_3A-28A_n41A_UL_28A_n41A (New)DL_3A-28A_n77A_UL_3A_n77A (New)DL_3A-28A_n77A_UL_28A_n77A (New)DL_3A_n41A-n77A_UL_3A_n41A (New)DL_28A_n41A-n77A_UL_28A_n41A (New)DL_3A_n41A-n77A_UL_3A_n77A (New)DL_28A_n41A-n77A_UL_28A_n77A | Ongoing |  |  |  | No | No
Unchange | DC_3A-3A-7A-8A_n1A-n78A | DC_3A_n78A DC_7A_n78A DC_8A_n78A | PC2 | 3LTE | Bo-Han Hsieh | CHTTL | pohanhsieh@cht.com.tw | Ericsson, Nokia, Google | RAN#99 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3, New for PC2 (New for PC2) DL_3A-3A-7A_n1A-n78A_UL_3A_n78A (New for PC2) DL_3A-3A-8A_n1A-n78A_UL_3A_n78A (New for PC2) DL_3A-7A-8A_n1A-n78A_UL_3A_n78A (PC2 completed) DL_3A-3A-7A-8A_n78A_UL_3A_n78A (New for PC2) DL_3A-3A-7A_n1A-n78A_UL_7A_n78A (New for PC2) DL_3A-7A-8A_n1A-n78A_UL_7A_n78A (PC2 completed) DL_3A-3A-7A-8A_n78A_UL_7A_n78A (New for PC2) DL_3A-7A-8A_n1A-n78A_UL_8A_n78A (New for PC2) DL_3A-3A-8A_n1A-n78A_UL_8A_n78A (PC2 completed) DL_3A-3A-7A-8A_n78A_UL_8A_n78A | Ongoing |  |  |  | No | No
Unchange | DC_8A_n78A | DC_8A_n78A | PC2 | Only FR1 | Yuanyuan Zhang | Samsung | Tina55.zhang@samsung.com | KT, Ericsson-LG, Nokia， Meditaeck | RAN#100 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_1A_n78(2A) | DC_1A_n78A | PC2 | Only FR1 | Yuanyuan Zhang | Samsung | Tina55.zhang@samsung.com | KT, Ericsson-LG, Nokia， Meditaeck | RAN#100 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (completed)DL_1A_n78A_UL_1A_n78A_PC2 | Ongoing |  |  |  | No | No
Unchange | DC_3A_n78(2A) | DC_3A_n78A | PC2 | Only FR1 | Yuanyuan Zhang | Samsung | Tina55.zhang@samsung.com | KT, Ericsson-LG, Nokia， Meditaeck | RAN#100 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (completed)DL_3A_n78A_UL_3A_n78A_PC2 | Ongoing |  |  |  | No | No
Unchange | DC_3A-8A_n78A | DC_3A_n78A DC_8A_n78A | PC2 | Only FR1 | Yuanyuan Zhang | Samsung | Tina55.zhang@samsung.com | KT, Ericsson-LG, Nokia， Meditaeck | RAN#100 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_8A_n78A_UL_8A_n78A_PC2 (completed)DL_3A_n78A_UL_3A_n78A_PC2 | Ongoing |  |  |  | No | No
Unchange | DC_1A-3A_n78(2A) | DC_1A_n78A DC_3A_n78A | PC2 | Only FR1 | Yuanyuan Zhang | Samsung | Tina55.zhang@samsung.com | KT, Ericsson-LG, Nokia， Meditaeck | RAN#100 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 (New)DL_1A-3A_n78A_UL_1A_n78A_PC2 (New)DL_1A-3A_n78A_UL_3A_n78A_PC2 (New)DL_1A_n78(2A)_UL_1A_n78A_PC2 (New)DL_3A_n78(2A)_UL_3A_n78A_PC2 | Ongoing |  |  |  | No | No
Unchange | DC_1A-11A_n77A | DC_1A_n77A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_1A-11A_n79A | DC_1A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_1A-8A_n77A | DC_1A_n77A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_1A-8A_n77A | DC_8A_n77A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_1A-8A_n79A | DC_8A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_3A_n1A-n79A | DC_3A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_3A-11A_n77A | DC_3A_n77A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_3A-11A_n79A | DC_3A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | New for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_3A-8A_n77A | DC_3A_n77A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_3A-8A_n77A | DC_8A_n77A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A_n1A-n79A | DC_8A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | New for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A_n28A-n78A | DC_8A_n78A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A_n28A-n79A | DC_8A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A_n3A-n79A | DC_8A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A_n77A-n79A | DC_8A_n77A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A_n77A-n79A | DC_8A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A_n79A | DC_8A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A-11A_n77A | DC_8A_n77A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A-11A_n79A | DC_8A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A-42A_n77A | DC_8A_n77A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | Completed for PC3 | Ongoing |  |  |  | No | No
Unchange | DC_8A-42A_n79A | DC_8A_n79A | PC2 | Only FR1 | Takehiko Narita | SoftBank | takehiko.narita@g.softbank.co.jp | Ericsson, Nokia, Huawei, HiSilicon, ZTE | RAN#101 | HPUE_FR1_DC_LTE_NR_R18 | New for PC3 | Ongoing |  |  |  | No | No
New | DC_1A-41A_n77A | DC_1A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_1A-41C_n77A | DC_1A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_3A-41C_n77A | DC_3A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_1A-3A-41C_n77A | DC_1A_n77A, DC_3A_n77A | PC2 | 3LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_1A-41C_n28A-n77A | DC_1A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_3A-41C_n28A-n77A | DC_3A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_1A-3A-41C_n28A-n77A | DC_1A_n77A, DC_3A_n77A | PC2 | 3LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_1A-41C_n77(2A) | DC_1A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_3A-41C_n77(2A) | DC_3A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_1A-3A-41C_n77(2A) | DC_1A_n77A, DC_3A_n77A | PC2 | 3LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_3A_n41A-n77A | DC_3A_n41A DC_3A_n77A | PC2 | 1LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_28A_n41A-n77A | DC_28A_n41A DC_28A_n77A | PC2 | 1LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Requested for PC3 New for PC2 | New |  |  |  | No | No
New | DC_3A-41A_n77A | DC_3A_n77A DC_41A_n77A | PC2 | 2LTE | Yasuki Suzuki | KDDI | ui-suzuki@kddi.com | Ericsson, Nokia, Samsung, Softbank | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3 New for PC2 | New |  |  |  | No | No
New | DC_8B_n78A | DC_8A_n78A DC_8B_n78A | PC2 | 1LTE | Bo-Han Hsieh | CHTTL | pohanhsieh@cht.com.tw | Ericsson, Nokia, Google | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3, New for PC2 (PC2 completed) DL_8A_n78A_UL_8A_n78A | New |  |  |  | No | No
New | DC_3A-8B_n78A | DC_3A_n78A DC_8A_n78A DC_8B_n78A | PC2 | 2LTE | Bo-Han Hsieh | CHTTL | pohanhsieh@cht.com.tw | Ericsson, Nokia, Google | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3, New for PC2 (PC2 completed) DL_3A-8A_n78A_UL_3A_n78A (PC2 completed) DL_3A-8A_n78A_UL_8A_n78A | New |  |  |  | No | No
New | DC_3A-3A-8B_n78A | DC_3A_n78A DC_8A_n78A DC_8B_n78A | PC2 | 2LTE | Bo-Han Hsieh | CHTTL | pohanhsieh@cht.com.tw | Ericsson, Nokia, Google | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3, New for PC2 (PC2 completed) DL_3A-3A-8A_n78A_UL_3A_n78A (PC2 completed) DL_3A-3A-8A_n78A_UL_8A_n78A | New |  |  |  | No | No
New | DC_7A-8B_n78A | DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | 2LTE | Bo-Han Hsieh | CHTTL | pohanhsieh@cht.com.tw | Ericsson, Nokia, Google | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3, New for PC2 (PC2 completed) DL_7A-8A_n78A_UL_7A_n78A (PC2 completed) DL_7A-8A_n78A_UL_8A_n78A | New |  |  |  | No | No
New | DC_7A-7A-8B_n78A | DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | 2LTE | Bo-Han Hsieh | CHTTL | pohanhsieh@cht.com.tw | Ericsson, Nokia, Google | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3, New for PC2 (PC2 completed) DL_7A-7A-8A_n78A_UL_7A_n78A (PC2 completed) DL_7A-7A-8A_n78A_UL_8A_n78A | New |  |  |  | No | No
New | DC_3A-7A-8B_n78A | DC_3A_n78A DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | 3LTE | Bo-Han Hsieh | CHTTL | pohanhsieh@cht.com.tw | Ericsson, Nokia, Google | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3, New for PC2 (PC2 completed) DL_3A-7A-8A_n78A_UL_3A_n78A (PC2 completed) DL_3A-7A-8A_n78A_UL_7A_n78A (PC2 completed) DL_3A-7A-8A_n78A_UL_8A_n78A | New |  |  |  | No | No
New | DC_3A-3A-7A-8B_n78A | DC_3A_n78A DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | 3LTE | Bo-Han Hsieh | CHTTL | pohanhsieh@cht.com.tw | Ericsson, Nokia, Google | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3, New for PC2 (PC2 completed) DL_3A-3A-7A-8A_n78A_UL_3A_n78A (PC2 completed) DL_3A-3A-7A-8A_n78A_UL_7A_n78A (PC2 completed) DL_3A-3A-7A-8A_n78A_UL_8A_n78A | New |  |  |  | No | No
New | DC_3A-7A-7A-8B_n78A | DC_3A_n78A DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | 3LTE | Bo-Han Hsieh | CHTTL | pohanhsieh@cht.com.tw | Ericsson, Nokia, Google | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3, New for PC2 (PC2 completed) DL_3A-7A-7A-8A_n78A_UL_3A_n78A (PC2 completed) DL_3A-7A-7A-8A_n78A_UL_7A_n78A (PC2 completed) DL_3A-7A-7A-8A_n78A_UL_8A_n78A | New |  |  |  | No | No
New | DC_3A-3A-7A-7A-8B_n78A | DC_3A_n78A DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | 3LTE | Bo-Han Hsieh | CHTTL | pohanhsieh@cht.com.tw | Ericsson, Nokia, Google | RAN#102 | HPUE_FR1_DC_LTE_NR_R18-Core | Completed for PC3, New for PC2 (PC2 completed) DL_3A-3A-7A-7A-8A_n78A_UL_3A_n78A (PC2 completed) DL_3A-3A-7A-7A-8A_n78A_UL_7A_n78A (PC2 completed) DL_3A-3A-7A-7A-8A_n78A_UL_8A_n78A | New |  |  |  | No | No