## R18 RAN4-led non-spectrum WI-SI
| AI | UID | UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | SR | Revised WID/SID | TU update | Change or comment
5 | 9.4.4.1 | 941012 | 941212 | Perf. part: NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW-Perf | 2024-06-17 | 40% | RP-234027 | 70% | RP-240063
6 | 9.4.4.2 | 950080 | 950280 | Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | NR_ENDC_RF_FR1_enh2-Perf | 2024-06-17 | 85% | RP-233186 | 90% | RP-240411
7 | 9.4.4.3 | 950076 | 950276 | Perf. part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | NR_RF_FR2_req_Ph3-Perf | 2024-03-18 | 85% | RP-232791 | 99% | RP-240734 |  |  | One CR for demodulation should be resubmitted
8 | 9.4.4.4 | 950077 | 950277 | Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | NR_FR2_multiRX_DL-Perf | 2024-06-17 | 50% | RP-234020 | 85% | RP-240297 | RP-240296 | Extend by 1Q, RD TU 0.5 | Complete date for Perf. Part is wrong in SR.In the revised WID, the completion date is shifted by one quarter.
9 | 9.4.4.5 | 950079 | 950279 | Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2_enh-Perf | 2024-06-17 | 80% | RP-233151 | 90% | RP-240367
10 | 9.4.4.6 | 950078 | 950278 | Perf. part: Even Further RRM enhancement for NR and MR-DC | NR_RRM_enh3-Perf | 2024-06-17 | 10% | RP-233496 | 50% | RP-240490 |  | Extend by 1Q, RD TU 0.25
11 | 9.4.4.7 | 950082 | 950282 | Perf. part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | NR_MG_enh2-Perf | 2024-06-17 | 10% | RP-234021 | 35% | RP-240445
13 | 9.4.4.8 | 950075 | 950275 | Perf. part: Air-to-ground network for NR | NR_ATG-Perf | 2024-03-18 | 80% | RP-234023 | 100% | RP-240158 | RP-240732 |  | In the reivsed WID, add RAN2 as the secondary group with the updated objectives: Specify signaling of the assistance information via NR ATG access [RAN2] • Specify system information enhancements • Specify MAC CE enhancements Specify measurement/mobility enhancements for ATG [RAN2]
14 | 9.4.4.9 | 950081 | 950281 | Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment | NonCol_intraB_ENDC_NR_CA-Perf | 2024-03-18 | 80% | RP-233513 | 100% | RP-240099 |  | WI Perf. closed earlier than completion date
15 | 9.4.4.10 | 950073 | 950273 | Perf. part: NR demodulation performance evolution | NR_demod_enh3-Perf | 2024-06-17 | 70% | RP-233586 | 80% | RP-240348 |  | Extend by 1Q, RD TU 0.5, 0.25
16 | 9.4.4.11 | 970081 | 970281 | Perf. part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs | NR_MIMO_OTA_enh-Perf | 2024-06-17 | 50% | RP-233742 | 70% | RP-240406 | RP-240736
17 | 9.4.4.12 | 970082 | 970282 | Perf. Part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh-Perf | 2024-06-17 | 50% | RP-234064 | 75% | RP-240137, RP-240138
18 | 9.4.4.13 |  | 991244 | Perf. part: Complete the specification support for BandWidth Part operation without restriction in NR | NR_BWP_wor-Perf | 2024-06-17 | 0% | RP-233999 | 25% | RP-240385
20 |  | 950074 | 950074 | NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) | LTE_NBIOT_eMTC_NTN_req | 2023-06-12 | 100% | RP-223437 | Closed
20 |  | 950074 | 950174 | Core part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) | LTE_NBIoT_eMTC_NTN_req-Core | 2022-12-01 | 100% | RP-223437 | Closed
20 |  | 950074 | 950274 | Perf. part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) | LTE_NBIoT_eMTC_NTN_req-Perf | 2023-06-12 | 100% | RP-223437 | Closed
22 |  | 981040 | 981040 | New WID: on Maximum Power Reduction Requirements for LTE Intra-band Carrier Aggregation with a Component Carrier gap larger than 35 MHz | LTE_intra_CA_MPR_35MHz_gap | 2023-06-12 | closed | RP-223511 | Closed | RP-230480
22 |  | 981040 | 981140 | Core part: Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz | LTE_intra_CA_MPR_35MHz_gap-Core | 2023-03-03 | closed | RP-230705 | Closed
23 |  | 890040 | 890040 | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | FS_NR_eff_BW_util | 2023-03-23 | closed | RP-220461 | Closed | RP-230579
24 |  | 950070 | 950070 | Study on enhancement for 700/800/900MHz band combinations for NR | FS_NR_700800900_combo_enh | 2023-03-23 | closed | RP-222554 | Closed | RP-230388
3 |  | 950069 | 950069 | Study on NR base station (BS) RF requirement evolution | FS_NR_BS_RF_evo | 2023-06-12 | 100% | RP-222501 | Closed | RP-231127
4 | 9.2.9 |  | 991031 | Study on enhancement for sub-1GHz NR band combinations | FS_NR_sub1GHz_combo_enh | 2023-09-11 | 100% | RP-231141 | Closed
1 |  | 950068 | 950068 | Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements | FS_NR_FR2_OTA_enh | 2023-12-11 | 100% | RP-230814 | Closed
2 |  | 950067 | 950067 | Study on simplification of band combination specification for NR and LTE | FS_SimBC | 2023-12-11 | 100% | RP-231468 | Closed
5 |  | 941012 | 941012 | NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW | 2024-06-17 |  | RP-234027
5 |  | 941012 | 941112 | Core part: NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW-Core | 2023-09-11 | 100% | RP-234027 | Closed
6 |  | 950080 | 950080 | Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | NR_ENDC_RF_FR1_enh2 | 2024-06-17 |  | RP-231490
6 |  | 950080 | 950180 | Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | NR_ENDC_RF_FR1_enh2-Core | 2023-12-11 | 100% | RP-231490 | Closed
7 |  | 950076 | 950076 | NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | NR_RF_FR2_req_Ph3 | 2024-03-18 |  | RP-222909
7 |  | 950076 | 950176 | Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | NR_RF_FR2_req_Ph3-Core | 2023-12-11 | 100% | RP-222909 | Closed
8 |  | 950077 | 950077 | Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | NR_FR2_multiRX_DL | 2024-03-18 |  | RP-233976 |  |  | v
8 |  | 950077 | 950177 | Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | NR_FR2_multiRX_DL-Core | 2023-09-11 | 100% | RP-233976 | Closed
9 |  | 950079 | 950079 | Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2_enh | 2024-03-18 |  | RP-222272
9 |  | 950079 | 950179 | Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2_enh-Core | 2023-09-11 | 100% | RP-222272 | Closed
10 |  | 950078 | 950078 | Even Further RRM enhancement for NR and MR-DC | NR_RRM_enh3 | 2024-06-17 |  | RP-221696
10 |  | 950078 | 950178 | Core part: Even Further RRM enhancement for NR and MR-DC | NR_RRM_enh3-Core | 2023-12-11 | 100% | RP-221696 | Closed
11 |  | 950082 | 950082 | Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | NR_MG_enh2 | 2024-06-17 |  | RP-231477
11 |  | 950082 | 950182 | Core part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | NR_MG_enh2-Core | 2023-12-11 | 100% | RP-231477 | Closed
12 |  | 950072 | 950072 | BS/UE EMC enhancements for NR and LTE | NR_LTE_EMC_enh | 2023-12-11 | 100% | RP-220916 | Closed
12 |  | 950072 | 950172 | Core part: BS/UE EMC enhancements for NR and LTE | NR_LTE_EMC_enh-Core | 2023-12-11 | 100% | RP-220916 | Closed
12 |  | 950072 | 950272 | Perf. part: BS/UE EMC enhancements for NR and LTE | NR_LTE_EMC_enh-Perf | 2023-12-11 | 100% | RP-220916 | Closed
13 |  | 950075 | 950075 | Air-to-ground network for NR | NR_ATG | 2024-03-18 |  | RP-230279
13 |  | 950075 | 950175 | Core part: Air-to-ground network for NR | NR_ATG-Core | 2023-12-11 | 100% | RP-230279 | Closed
14 |  | 950081 | 950081 | Support of intra-band non-collocated EN-DC/NR-CA deployment | NonCol_intraB_ENDC_NR_CA | 2024-06-17 |  | RP-233513
14 |  | 950081 | 950181 | Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment | NonCol_intraB_ENDC_NR_CA-Core | 2023-12-11 | 100% | RP-233513 | Closed
15 |  | 950073 | 950073 | NR demodulation performance evolution | NR_demod_enh3 | 2024-03-18 |  | RP-231492
|  | 950073 | 950173 | Core part: NR demodulation performance evolution | NR_demod_enh3-Core | 2023-12-11 | 100% | RP-231492 | Closed
16 |  | 970081 | 970081 | Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs | NR_MIMO_OTA_enh | 2024-06-17 |  | RP-223509
16 |  | 970081 | 970181 | Core part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) requirement for NR UEs | NR_MIMO_OTA_enh-Core | 2023-12-11 | 100% | RP-223509 | Closed
17 |  | 970082 | 970082 | Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh | 2024-06-17 |  | RP-234064
17 |  | 970082 | 970182 | Core part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh-Core | 2023-12-11 | 100% | RP-234064 | Closed
18 |  |  | 991044 | Complete the specification support for BandWidth Part operation without restriction in NR | NR_BWP_wor | 2024-06-17 |  | RP-233999
18 |  |  | 991144 | Core part: Complete the specification support for BandWidth Part operation without restriction in NR | NR_BWP_wor-Core | 2023-12-11 | 100% | RP-233999 | Closed
19 |  |  | 991045 | Channel raster enhancement | NR_channel_raster_enh | 2023-12-11 | 100% | RP-234025 | Closed
19 |  |  | 991145 | Core part: channel raster enhancement | NR_channel_raster_enh-Core | 2023-12-11 | 100% | RP-234025 | Closed

## R18 RAN4-led spectrum WI-SI
| AI | UID | UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | SR | Revised WID/SID | TU update | Change or comment
26 | 9.5.1.1 | 960095 | 960095 | Additional NR bands for UL-MIMO in Rel-18 | NR_bands_UL_MIMO_R18 | 2024-03-18 | 90% | RP-234040 | 100% | RP-240421 | RP-240422
26 | 9.5.1.1 | 960095 | 960195 | Core part: Additional NR bands for UL-MIMO in Rel-18 | NR_bands_UL_MIMO_R18-Core | 2024-03-18 | 90% | RP-234040 | 100%
26 | 9.5.1.1 | 960095 | 960295 | Perf. part: Additional NR bands for UL-MIMO in Rel-18 | NR_bands_UL_MIMO_R18-Perf | 2024-03-18 | 90% | RP-234040 | Stopped
31 | 9.5.2.1 | 961001 | 961001 | Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_1BLTE_1BNR_2DL2UL | 2024-06-17 |  | RP-233242 |  | RP-240481 | RP-240482 | Yes | WI exception RP-240483
31 | 9.5.2.1 | 961001 | 961101 | Core part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_1BLTE_1BNR_2DL2UL-Core | 2024-06-17 | 85% | RP-233242 | 90%
31 | 9.5.2.1 | 961001 | 961201 | Perf. part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_1BLTE_1BNR_2DL2UL-Perf | 2024-06-17 | 0% | RP-233242 | 50%
32 | 9.5.2.2 | 961004 | 961004 | Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_2BLTE_1BNR_3DL2UL | 2024-06-17 | 85% | RP-233987 | 90% | RP-240415 | RP-240417 | Yes | WI exception RP-240416
32 | 9.5.2.2 | 961004 | 961104 | Core part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_2BLTE_1BNR_3DL2UL-Core | 2024-06-17 | 85% | RP-233987 | 90%
33 | 9.5.2.3 | 961005 | 961005 | Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) | DC_R18_xBLTE_1BNR_yDL2UL | 2024-06-17 |  | RP-233988 |  | RP-240382 | RP-240384 | Yes | WI exception RP-240383
33 | 9.5.2.3 | 961005 | 961105 | Core part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) | DC_R18_xBLTE_1BNR_yDL2UL-Core | 2024-06-17 | 70% | RP-233988 | 90%
33 | 9.5.2.3 | 961005 | 961205 | Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) | DC_R18_xBLTE_1BNR_yDL2UL-Perf | 2024-03-18 | 80% | RP-233988 | 100%
34 | 9.5.2.4 | 961003 | 961003 | Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R18_xBLTE_2BNR_yDL2UL | 2024-06-17 | 80% | RP-233488 | 85% | RP-240325 | RP-240324 | Yes | WI exception RP-240326
34 | 9.5.2.4 | 961003 | 961103 | Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R18_xBLTE_2BNR_yDL2UL-Core | 2024-06-17 | 80% | RP-233488 | 85%
34 | 9.5.2.4 | 961003 | 961203 | Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R18_xBLTE_2BNR_yDL2UL-Perf | 2024-06-17 | 80% | RP-233488 | 85%
35 | 9.5.2.5 | 961006 | 961006 | Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) | DC_R18_xBLTE_yBNR_zDL2UL | 2024-06-17 | 85% | RP-232923 |  | RP-240250 | RP-240248 | Yes | WI exception RP-240249
35 | 9.5.2.5 | 961006 | 961106 | Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) | DC_R18_xBLTE_yBNR_zDL2UL-Core | 2024-06-17 | 85% | RP-232923 | 90%
35 | 9.5.2.5 | 961006 | 961206 | Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) | DC_R18_xBLTE_yBNR_zDL2UL-Perf | 2024-06-17 | 85% | RP-232923 | 85% |  |  |  | Perf. Part completio date is wrong
36 | 9.5.2.6 | 961002 | 961002 | Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) | DC_R18_xBLTE_yBNR_zDL3UL | 2024-06-17 | 70% | RP-233989 |  | RP-240373 | RP-240374 | Yes | WI exception RP-240375
36 | 9.5.2.6 | 961002 | 961102 | Core part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) | DC_R18_xBLTE_yBNR_zDL3UL-Core | 2024-06-17 | 70% | RP-233989 | 85%
36 | 9.5.2.6 | 961002 | 961202 | Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) | DC_R18_xBLTE_yBNR_zDL3UL-Perf | 2024-03-18 | 70% | RP-233989 | 70%
37 | 9.5.3.1 | 961007 | 961007 | Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R18_Intra | 2024-06-17 | 92% | RP-233990 | 91% | RP-240237 | RP-240238 | Yes | WI exception RP-240239
37 | 9.5.3.1 | 961007 | 961107 | Core part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R18_Intra-Core | 2024-06-17 | 92% | RP-233990 | 91%
37 | 9.5.3.1 | 961007 | 961207 | Perf. part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R18_Intra-Perf | 2024-03-18 | 92% | RP-233990 | 91% |  |  |  | Stopped
38 | 9.5.3.2 | 961010 | 961010 | Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | NR_CADC_R18_2BDL_xBUL | 2024-06-17 | 85% | RP-232920 |  | RP-240247 | RP-240245 | Yes | WI exception RP-240246
38 | 9.5.3.2 | 961010 | 961110 | Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | NR_CADC_R18_2BDL_xBUL-Core | 2024-06-17 | 85% | RP-232920 | 90%
38 | 9.5.3.2 | 961010 | 961210 | Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | NR_CADC_R18_2BDL_xBUL-Perf | 2024-03-18 | 85% | RP-232920 | 85% |  |  |  | Stopped
39 | 9.5.3.3 | 961011 | 961011 | Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) | NR_CADC_R18_3BDL_xBUL | 2024-06-17 | 85% | RP-233231 | 90% | RP-240167 | RP-240166 | Yes | WI exception RP-240168
39 | 9.5.3.3 | 961011 | 961111 | Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) | NR_CADC_R18_3BDL_xBUL-Core | 2024-06-17 | 85% | RP-233231 | 90%
39 | 9.5.3.3 | 961011 | 961211 | Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) | NR_CADC_R18_3BDL_xBUL-Perf | 2024-06-17 | 85% | RP-233231 | 90%
40 | 9.5.3.4 | 961008 | 961008 | Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) | NR_CADC_R18_yBDL_xBUL | 2024-06-17 | 67% | RP-233696 | 60% | RP-240502 | RP-240501 | Yes | WI exception RP-240504
40 | 9.5.3.4 | 961008 | 961108 | Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) | NR_CADC_R18_yBDL_xBUL-Core | 2024-06-17 | 67% | RP-233696 | 60%
40 | 9.5.3.4 | 961008 | 961208 | Perf. part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) | NR_CADC_R18_yBDL_xBUL-Perf | 2024-06-17 | 67% | RP-233696 | 60%
41 | 9.5.3.5 | 961009 | 961009 | Rel-18 Single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R18 | 2024-06-17 | 80% | RP-233197 | 90% | RP-240418 | RP-240420 | Yes | WI exception RP-240419
41 | 9.5.3.5 | 961009 | 961109 | Core part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R18-Core | 2024-06-17 | 80% | RP-233197 | 90%
41 | 9.5.3.5 | 961009 | 961209 | Perf. Part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R18-Perf | 2024-03-18 | 80% | RP-233197 | 90% |  |  |  | Stopped
42 | 9.5.3.6 | 981047 | 981047 | Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells | NR_2SUL_cell_combos_R18 | 2024-03-18 | 70% | RP-233446 | 100% | RP-240159 | RP-240160
42 | 9.5.3.6 | 981047 | 981147 | Core part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells | NR_2SUL_cell_combos_R18-Core | 2024-03-18 | 70% | RP-233446 | 100%
42 | 9.5.3.6 | 981047 | 981247 | Perf. part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells | NR_2SUL_cell_combos_R18-Perf | 2024-03-18 | 70% | RP-233446 | Stopped
44 | 9.5.4.1 | 961012 | 961012 | High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands | LTE_NR_HPUE_FWVM_R18 | 2024-06-17 | 70% | RP-233180 | 80% | RP-240362 | RP-240361 | Yes | WI exception RP-240363
44 | 9.5.4.1 | 961012 | 961112 | Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands | LTE_NR_HPUE_FWVM_R18-Core | 2024-06-17 | 70% | RP-233180 | 80%
46 | 9.5.4.2 | 970086 | 970086 | High power UE (power class 2) for NR FR1 FDD single band | HPUE_NR_FR1_FDD_R18 | 2024-06-17 | 80% | RP-233031 | 90% | RP-240119 | RP-240120 | Yes | WI exception RP-240121. RP-240511 On n28 with full band duplexer Apple
46 | 9.5.4.2 | 970086 | 970186 | Core part: High power UE (power class 2) for NR FR1 FDD single band | HPUE_NR_FR1_FDD_R18-Core | 2024-06-17 | 80% | RP-233031 | 90%
46 | 9.5.4.2 | 970086 | 970286 | Perf. part: High power UE (power class 2) for NR FR1 FDD single band | HPUE_NR_FR1_FDD_R18-Perf | 2024-06-17 | 80% | RP-233031 | 90%
47 | 9.5.4.3 | 970087 | 970087 | High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band | HPUE_NR_FR1_TDD_intra_CA_R18 | 2024-06-17 | 80% | RP-233975 | 85% | RP-240426 | RP-240428 | Yes | WI exception RP-240427
47 | 9.5.4.3 | 970087 | 970187 | Core part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band | HPUE_NR_FR1_TDD_intra_CA_R18-Core | 2024-06-17 | 80% | RP-233975 | 85%
47 | 9.5.4.3 | 970087 | 970287 | Perf. part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band | HPUE_NR_FR1_TDD_intra_CA_R18-Perf | 2024-03-18 | 80% | RP-233975 | N/A |  |  |  | Stopped
48 | 9.5.4.4 | 970088 | 970088 | High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) | HPUE_FR1_DC_LTE_NR_R18 | 2024-06-17 | 77% | RP-233977 | 75% | RP-240240 | RP-240241 | Yes | Wi exception RP-240242
48 | 9.5.4.4 | 970088 | 970188 | Core part: High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) | HPUE_FR1_DC_LTE_NR_R18-Core | 2024-06-17 | 77% | RP-233977 | 75%
48 | 9.5.4.4 | 970088 | 970288 | Perf. part: High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) | HPUE_FR1_DC_LTE_NR_R18-Perf | 2023-12-11 | 77% | RP-233977 | Stopped
49 | 9.5.4.5 | 970089 | 970089 | Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_TDD_NR_CADC_SUL_R18 | 2024-06-17 |  | RP-233561 |  | RP-240356 | RP-240355 | Yes | WI exception RP-240357
49 | 9.5.4.5 | 970089 | 970189 | Core part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_TDD_NR_CADC_SUL_R18-Core | 2024-06-17 | 80% | RP-233561 | 90%
49 | 9.5.4.5 | 970089 | 970289 | Perf. part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_TDD_NR_CADC_SUL_R18-Perf | 2024-06-17 | 0% | RP-233561 | 0%
50 | 9.5.4.6 | 970090 | 970090 | Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR inter-band CA/DC combinations with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1) | HPUE_FR1_FDD_NR_CADC_R18 | 2024-06-17 | 30% | RP-234017 |  | RP-240122 | RP-240123 | Yes | WI exception RP-240124
50 | 9.5.4.6 | 970090 | 970190 | Core part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR inter-band CA/DC combinations with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1) | HPUE_FR1_FDD_NR_CADC_R18-Core | 2024-06-17 | 30% | RP-234017 | 80%
50 | 9.5.4.6 | 970090 | 970290 | Perf. part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR inter-band CA/DC combinations with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1) | HPUE_FR1_FDD_NR_CADC_R18-Perf | 2024-03-18 | 30% | RP-234017 | 100% |  |  |  | Stopped
54 | 9.5.5.1 | 970083 | 970083 | Adding new channel bandwidth(s) support to existing NR bands | NR_bands_R18_BWs | 2024-03-18 | 70% | RP-232952 | 100% | RP-240275 |  |  | WI exception RP-232953
54 | 9.5.5.1 | 970083 | 970183 | Core part: Adding new channel bandwidth(s) support to existing NR bands | NR_bands_R18_BWs-Core | 2024-03-18 | 70% | RP-232952 | 100%
55 | 9.5.5.2 | 970084 | 970084 | Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | LTE_NR_Simult_RxTx_R18 | 2024-06-17 | 85% | RP-234002 | 90% | RP-240423 | RP-240425 | Yes | WI exception RP-240424
55 | 9.5.5.2 | 970084 | 970184 | Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | LTE_NR_Simult_RxTx_R18-Core | 2024-06-17 | 85% | RP-234002 | 90%
55 | 9.5.5.2 | 970084 | 970284 | Perf. part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | LTE_NR_Simult_RxTx_R18-Perf | 2024-03-18 | 85% | RP-234002 | Stopped
| 9.5.5.3 |  | 1010053 | Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC | R18_3Tx_NR_CA_ENDC | 2024-06-17 | 30% | RP-232941 | 70% | RP-240308 | RP-240307 | Yes | WI exception RP-240309
| 9.5.5.3 |  | 1010153 | Core part: Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC | R18_3Tx_NR_CA_ENDC | 2024-06-17 | 30% | RP-232941 | 70%
57 | 9.5.5.4 | 981042 | 981042 | Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) | 4Rx_NR_bands_R18 | 2024-03-18 | 65% | RP-234004 | 100% | RP-240252 | RP-240251
57 | 9.5.5.4 | 981042 | 981142 | Core part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) | 4Rx_NR_bands_R18-Core | 2024-03-18 | 65% | RP-234004 | 100%
57 | 9.5.5.4 | 981042 | 981242 | Perf. part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) | 4Rx_NR_bands_R18-Perf | 2024-03-18 | 65% | RP-234004 | 65% |  |  |  | Stopped
62 | 10.3.1 |  | 991041 | Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband | 2024-03-18 |  | RP-233856 | 100% | RP-240733 | RP-240741 |  | TS 36.521-4 is removed in the revised WID
62 | 10.3.1 |  | 991141 | Core part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband-Core | 2024-03-18 | 90% | RP-233856 | 100%
62 | 10.3.1 |  | 991241 | Perf. part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband-Perf | 2024-06-17 | 0% | RP-233856 | 20%
63 | 10.3.2 |  | 991243 | Perf. part: Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band-Perf | 2024-06-17 | 0% | RP-234060 | 50% | RP-240450 | RP-240451 | Yes | Rapporteur is changed in the revised WID
| 10.3.3 |  | 1010054 | High Power UE (Power Class 2) for LTE FDD Band 14 | HPUE_LTE_FDD_B14 | 2024-03-18 |  | RP-232946 | 100% | RP-240075 |  |  | TR RP-240076; WI summary RP-240077
| 10.3.3 |  | 1010154 | Core part: High Power UE (Power Class 2) for LTE FDD Band 14 | HPUE_LTE_FDD_B14 | 2024-03-18 | 50% | RP-232946 | 100%
| 10.3.3 |  | 1010254 | Perf. part: High Power UE (Power Class 2) for LTE FDD Band 14 | HPUE_LTE_FDD_B14 | 2024-03-18 | 80% | RP-232946 | 100%
64 | 10.3.4.1 | 960099 | 960099 | Rel-18 LTE-Advanced Carrier Aggregation for x bands (x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R18_xBDL_yBUL | 2024-06-17 | 43% | RP-233927 | 55% | RP-240412 | RP-240414 | Yes | WI exception RP-240413; completion date is changed to RAN#104
64 | 10.3.4.1 | 960099 | 960199 | Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R18_xBDL_yBUL-Core | 2024-06-17 | 43% | RP-233927 | 55%
64 | 10.3.4.1 | 960099 | 960299 | Perf. part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R18_xBDL_yBUL-Perf | 2024-03-18 | 43% | RP-233927 | Stopped
59 |  | 981046 | 981046 | New WID for 900MHz LTE Band | LTE_900MHz_US | 2023-06-12 | closed | RP-230722
59 |  | 981046 | 981146 | Core part: Introduction of 900 MHz LTE band in the US | LTE_900MHz_US-Core | 2023-06-12 | closed | RP-230722
59 |  | 981046 | 981246 | Perf. part: Introduction of 900 MHz LTE band in the US | LTE_900MHz_US-Perf | 2023-06-12 | closed | RP-230722
61 |  |  | 991040 | Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW | 2023-09-11 | Stopped | RP-230745
61 |  |  | 991140 | Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW-Core | 2023-06-12 | Stopped | RP-230745
61 |  |  | 991240 | Perf. part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW-Perf | 2023-09-11 | Stopped | RP-230745
52 |  | 960093 | 960093 | Enhancements of NR shared spectrum bands | NR_unlic_enh | 2023-06-12 | closed | RP-230730
52 |  | 960093 | 960193 | Core part: Enhancements of NR shared spectrum bands | NR_unlic_enh-Core | 2023-06-12 | closed | RP-230730
65 |  | 960097 | 960097 | APT 600MHz NR band | NR_600MHz_APT | 2023-03-23 | closed | RP-223265
65 |  | 960097 | 960197 | Core part: APT 600MHz NR band | NR_600MHz_APT-Core | 2023-03-03 | closed | RP-221778
65 |  | 960097 | 960297 | Perf. part: APT 600MHz NR band | NR_600MHz_APT-Perf | 2023-03-03 | closed | RP-221778
66 |  | 981044 | 981044 | New WID: Introduction of NR TDD band in 1670 – 1675 MHz | NR_TDD_n54 | 2023-03-23 | closed | RP-223514
66 |  | 981044 | 981144 | Core part: Introduction of NR TDD band in 1670-1675 MHz (n54) | NR_TDD_n54-Core | 2023-03-03 | closed | RP-230062
66 |  | 981044 | 981244 | Perf. part: Introduction of NR TDD band in 1670-1675 MHz (n54) | NR_TDD_n54-Perf | 2023-03-03 | closed | RP-230062
67 |  | 961013 | 961013 | High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe | NR_RAIL_HPUE_n100_n101 | 2023-12-11 | Stopped | RP-221878
67 |  | 961013 | 961113 | Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe | NR_RAIL_HPUE_n100_n101-Core | 2023-12-11 | stopped | RP-221878
68 |  | 950071 | 950071 | Introduction of LTE TDD band in 1670-1675 MHz | LTE_TDD_1670_1675MHz | 2022-12-16 | closed | RP-220971
68 |  | 950071 | 950171 | Core part: Introduction of LTE TDD band in 1670-1675 MHz | LTE_TDD_1670_1675MHz-Core | 2022-12-01 | closed | RP-222831
68 |  | 950071 | 950271 | Perf. part: Introduction of LTE TDD band in 1670-1675 MHz | LTE_TDD_1670_1675MHz-Perf | 2022-12-01 | closed | RP-222831
69 |  | 961000 | 961000 | LTE intra-band contiguous Carrier Aggregation for band 8 | LTE_CA_intra_B8 | 2022-12-16 | closed | RP-221846
69 |  | 961000 | 961100 | Core part: LTE intra-band contiguous Carrier Aggregation for band 8 | LTE_CA_intra_B8-Core | 2022-12-16 | closed | RP-221846
| 9.4.5.4 |  | 1000061 | 30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) | NR_NTN_CBW_30MHz | 2023-09-11 | 100% | RP-231499
| 9.4.5.4 |  | 1001061 | Core part: 30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) | NR_NTN_CBW_30MHz-Core | 2023-09-11 | 100% | RP-231499
58 | 10.3.1 | 920071 | 920071 | New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 | LTE_terr_bcast_bands_part2 | 2023-09-11 | 100% | RP-231216
58 | 10.3.1 | 920071 | 920171 | Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 | LTE_terr_bcast_bands_part2-Core | 2023-09-11 | 100% | RP-231216
25 |  | 960098 | 960098 | Introduction of additional 6GHz NR licensed bands | NR_6GHz_add_bands | 2023-12-11 | 0% | RP-222498 | Closed
25 |  | 960098 | 960198 | Core part: Introduction of additional 6GHz NR licensed bands | NR_6GHz_add_bands-Core | 2023-12-11 | 0% | RP-222498 | Closed
25 |  | 960098 | 960298 | Perf. part: Introduction of additional 6GHz NR licensed bands | NR_6GHz_add_bands-Perf | 2023-12-11 | 0% | RP-222498 | Closed
27 |  | 981043 | 981043 | Introduction of the Satellite L-/S-Band for NR | NR_NTN_LSband | 2023-12-11 | 100% | RP-234043 | Closed
27 |  | 981043 | 981143 | Core part: Introduction of the satellite L-/S-band for NR | NR_NTN_LSband-Core | 2023-12-11 | 100% | RP-234043 | Closed
27 |  | 981043 | 981243 | Perf. part: Introduction of the satellite L-/S-band for NR | NR_NTN_LSband-Perf | 2023-12-11 | 100% | RP-234043 | Closed
28 |  | 981045 | 981045 | Introduction of 900 MHz NR band in the US | NR_900MHz_US | 2023-12-11 | 100% | RP-234044 | Closed
28 |  | 981045 | 981145 | Core Part: Introduction of 900 MHz NR band in the US | NR_900MHz_US-Core | 2023-12-11 | 100% | RP-234044 | Closed
28 |  | 981045 | 981245 | Perf. part: Introduction of 900 MHz NR band in the US | NR_900MHz_US-Perf | 2023-12-11 | 100% | RP-234044 | Closed
29 |  |  | 991039 | Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18 | NR_FDD_bands_R18_redcap | 2023-12-11 | 100% | RP-232894 | Closed
29 |  |  | 991139 | Core part: Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18 | NR_FDD_bands_R18_redcap-Core | 2023-12-11 | 100% | RP-232894 | Closed
30 |  |  | 991042 | Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76 | NR_FDD_ULn28_DLn75_n76 | 2023-12-11 | 100% | RP-233245 | Closed
30 |  |  | 991142 | Core part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76 | NR_FDD_ULn28_DLn75_n76-Core | 2023-12-11 | 100% | RP-233245 | Closed
30 |  |  | 991242 | Perf. part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76 | NR_FDD_ULn28_DLn75_n76-Perf | 2023-12-11 | 100% | RP-233245 | Closed
|  |  | 1010055 | Introduction of NR bands n31 and n72 | NR_bands_n31_n72 | 2023-12-11 | 100% | RP-233950 | Closed
|  |  | 1010155 | Core part: Introduction of NR bands n31 and n72 | NR_bands_n31_n72 | 2023-12-11 | 100% | RP-233950 | Closed
|  |  | 1010255 | Perf. part: Introduction of NR bands n31 and n72 | NR_bands_n31_n72 | 2023-12-11 | 100% | RP-233950 | Closed
43 |  |  | 991046 | Enhancement for 700/800/900MHz band combinations for NR | NR_700800900_combo_enh | 2023-12-11 | 100% | RP-233991 | Closed
43 |  |  | 991146 | Core part: Enhancement for 700/800/900MHz band combinations for NR | NR_700800900_combo_enh-Core | 2023-12-11 | 100% | RP-233991 | Closed
43 |  |  | 991246 | Perf. part: Enhancement for 700/800/900MHz band combinations for NR | NR_700800900_combo_enh-Perf | 2023-12-11 | 100% | RP-233991 | Closed
45 |  | 970085 | 970085 | High power UE (power class 1.5) for NR FR1 TDD single band | HPUE_NR_FR1_TDD_R18 | 2023-12-11 | 100% | RP-223499 | Closed
45 |  | 970085 | 970185 | Core part: High power UE (power class 1.5) for NR FR1 TDD single band | HPUE_NR_FR1_TDD_R18-Core | 2023-12-11 | 100% | RP-223499 | Closed
|  | 970085 | 970285 | Core part: High power UE (power class 1.5) for NR FR1 TDD single band | HPUE_NR_FR1_TDD_R18-Core | 2023-12-11 |  | RP-223499 | Closed
51 |  | 960096 | 960096 | Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band | NR_LTE_V2X_PC5_combos_R18 | 2023-12-11 | 100% | RP-230390 | Closed
51 |  | 960096 | 960196 | Core part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band | NR_LTE_V2X_PC5_combos_R18-Core | 2023-12-11 | 100% | RP-230390 | Closed
51 |  | 960096 | 960296 | Perf. part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band | NR_LTE_V2X_PC5_combos_R18-Perf | 2023-12-11 | 100% | RP-230390 | Closed
53 |  | 960094 | 960094 | Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R18 | 2023-12-11 | 100% | RP-233588 | Closed
53 |  | 960094 | 960194 | Core part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R18-Core | 2023-12-11 | 100% | RP-233588 | Closed
53 |  | 960094 | 960294 | Perf. part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R18-Perf | 2023-12-11 | 100% | RP-233588 | Closed
56 |  | 981041 | 981041 | 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | 4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC | 2023-12-11 | 100% | RP-234046 | Closed
56 |  | 981041 | 981141 | Core part: 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | 4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-Core | 2023-12-11 | 100% | RP-234046 | Closed
60 |  | 981048 | 981048 | Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 | LTE_bands_R18_M1_M2_NB1_NB2 | 2023-12-11 | 100% | RP-232892 | Closed
60 |  | 981048 | 981148 | Core part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 | LTE_bands_R18_M1_M2_NB1_NB2-Core | 2023-12-11 | 100% | RP-232892 | Closed
60 |  | 981048 | 981248 | Perf. part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 | LTE_bands_R18_M1_M2_NB1_NB2-Perf | 2023-12-11 | 100% | RP-232892 | Closed
63 |  |  | 991043 | Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band | 2024-06-17 | 23% | RP-234060 | Closed
63 |  |  | 991143 | Core part: Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band-Core | 2023-12-11 | 100% | RP-234060 | Closed