## Cover sheet
3GPP TSG RAN Meeting #103 | [10 empty] | RP-240358
Maastricht, Netherlands, March 18-21, 2024
Agenda Item: | 13.3.12
Source: | China Telecom
Title: | WP UE Conformance – Enhancement of Private Network Support for NG-RAN including CT aspects
Work item code: | NG_RAN_PRN_enh_plus_CT-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 63% (+9%) | 12 (+3) | 20 (+4)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 63.3% (+9.2%) | 12 (+3) | 20 (+4)
FR1 |  | 63.3% (+9.2%) | 12 (+3) | 20 (+4)
FR2 |  | 63.3% (+9.2%) | 12 (+3) | 20 (+4)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100% (+5%) |  |  | 100% (+5%) |  |  | 100% (+5%)
Common ICS | 38.508-2 | 100% (+10%) |  |  | 100% (+10%) |  |  | 100% (+10%)
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 59.7% (+2.7%) | 12 (+3) | 20 (+4) | 59.7% (+2.7%) | 12 (+3) | 20 (+4) | 59.7% (+2.7%) | 12 (+3) | 20 (+4)
Applicability Protocol test cases | 38.523-2 | 80% (+51.4%) |  |  | 80% (+51.4%) |  |  | 80% (+51.4%)
Test suites (TTCN) | 38.523-3 | 0% |  |  | 0% |  |  | 0%
5 References
[1] RP-221300 | New WID on UE Conformance – Enhancement of Private Network Support for NG-RAN including CT aspects, China Telecom, RAN#96, June 2022
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Enhancement of Private Network Support for NG-RAN including CT aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | NG_RAN_PRN_enh_plus_CT-UEConTest
WP Scope: |  | <WP Scope description> | [12 empty] | vs Area
WP Resp: |  | Lei GAO |  |  | gaol8@chinatelecom.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 63.3% (+9.2%) | 63.3% (+9.2%)
[14 empty] | 29 (+5) | 29 (+5)
[14 empty] | 25.1 (+2.4) | 25.1 (+2.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
1 |  | 38.508-1 | 4 | Introduction of General and Signaling Test Environment for Rel-17 eNPN Tests | ASN.1 updates (SIB1, SIB18, other messages) | China Telecom | RAN5#98 (Feb-23) | R5-231461 R5-231560 R5-233987 R5-240349 |  | 0.5 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
TS 38.508-2: Common ICS
2 |  | 38.508-2 | A.4.3.7 | Introduction of common implementation conformance statements for Rel-17 eNPN Tests Cases | eNPN PICS | China Telecom | RAN5#99 (May-23) | R5-233471 R5-235358 R5-241581 |  | 0.5 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Idle Mode
|  | 38.523-1 | 6.5.3 | SNPN Selection | New sub-clause header |  | TBD |  |  | 0
3 | Y | 38.523-1 | 6.5.3.1 | SNPN Selection in Manual Mode / Using credentials from a credentials holder | TS 23.122, cl 4.9.3.1.0 and 4.9.3.1.2 (1) with { UE in Manual network/SNPN selection mode and supports access to an SNPN using credentials from a credentials holder and an SNPN cell is available which does not support the access using credentials from a credentials holder } ensure that { when { UE is switched on or return to coverage } then { UE does not indicate to the user any available SNPNs } } (2) with { UE in Manual network/SNPN selection mode and supports access to an SNPN using credentials from a credentials holder } ensure that { when { an SNPN is available which broadcasts the indication that access using credentials from a credentials holder is supported } then { UE indicates to the user that an SNPN is available and user selects the SNPN } } | China Telecom | RAN5#100 (Aug-23) | R5-235359 R5-236777 R5-236967 |  | 1 | 100% | 100% |  | 100% | 100%
4 | Y | 38.523-1 | 6.5.3.2 | SNPN Selection in Manual Mode / Onboarding services in SNPN | TS 23.122, cl 4.9.3.1.4 (1) with { UE in Manual network selection mode and an SNPN not supporting onboarding services is available } ensure that { when { UE is switched on or return to coverage } then { UE does not indicate to the user any available SNPN } } (2) with { UE in Manual network selection mode } ensure that { when { an SNPN indicating that onboarding is allowed is available and matches the onboarding SNPN selection information } then { UE indicates user the SNPN and user selects the SNPN } } | China Telecom | RAN5#100 (Aug-23) | R5-235360 R5-236778 R5-236968 |  | 1 | 100% | 100% |  | 100% | 100%
5 | Y | 38.523-1 | 6.5.3.3 | SNPN Selection in Manual Mode / Switch to Automatic Mode | TS 23.122, cl 4.9.3.1.2 (1) with { UE in Manual network/SNPN selection mode and has registered on an SNPN cell which does not support emergency calls } ensure that { when { a different SNPN is available and user initiates an emergency call} then { UE automatically select the SNPN } } (2) with { UE in Manual network/SNPN selection mode and has registered on an SNPN cell } ensure that { when { a different SNPN is available and user initiates an emergency call and the registration request for emergency services is rejected by the network } then { UE automatically select the SNPN } } | China Telecom | RAN5#100 (Aug-23) | R5-235361 R5-236782 |  | 1 | 100% | 100% |  | 100% | 100%
6 | Y | 38.523-1 | 6.5.3.4 | SNPN Selection in Automatic Mode / Onboarding services in SNPN | TS 23.122, cl 4.9.3.1.3 (1) with { UE in Automatic network selection mode and an SNPN supporting onboarding service is available which does not match the onboarding SNPN selection information } ensure that { when { UE is switched on or return to coverage } then { UE does not select the SNPN cell and continues searching for an allowable SNPN Cell } } (2) with { UE in Automatic network selection mode and Registration for onboarding services on an SNPN cell is unsuccessful } ensure that { when { an SNPN is available for which an entry exists in the "list of subscriber data" } then { UE performs SNPN selection not for onboarding services on the SNPN } } | China Telecom | RAN5#100 (Aug-23) | R5-235362 R5-237405 R5-236970 |  | 1 | 100% | 100% |  | 100% | 100%
7 | Y | 38.523-1 | 6.5.3.5 | SNPN Selection in Automatic Mode / Using credentials from a credentials holder | TS 23.122, cl 4.9.3.1.1 (1) with { UE in Automatic network selection mode and supports access to an SNPN using credentials from a credentials holder, using the SNPN selection parameters in the selected entry of the "list of subscriber data" } ensure that { when { SNPNs are available which broadcast the indication that access using credentials from a credentials holder is supported } then { UE selects a cell of the highest priority SNPN and UE attempts a registration on the selected cell } } (2) with { UE in Automatic network selection mode and supports access to an SNPN using credentials from a credentials holder, using the SNPN selection parameters in the selected entry of the "list of subscriber data" } ensure that { when { SNPNs are available which broadcast the indication that access using credentials from a credentials holder is supported highest priority SNPN is not available} then { UE selects a cell of the next priority available SNPN and UE attempts a registration on the selected cell } } | Lenovo China Telecom | RAN5#100 (Aug-23) | R5-235364 R5-236971 |  | 1 | 100% | 100% |  | 100% | 100%
8 | Y | 38.523-1 | 6.5.3.6 | SNPN / Limited service / No valid subscriber data | TS 23.122, cl 3.5 (1) with { UE in SNPN access mode and the "list of subscriber data" with no valid entry and UE is not configured with the default UE credentials } ensure that { when { an acceptable SNPN cell is available and UE needs to make a emergency call } then { UE selects the SNPN cell and attempts to camp on it } } (2) with { UE in SNPN access mode and the "list of subscriber data" with no valid entry and UE is configured with the default UE credentials } ensure that { when { an acceptable SNPN cell supporting onboarding services is available } then { UE selects the SNPN cell for onboardig services } } | Lenovo | RAN5#100 (Aug-23) | R5-235365 R5-237404 |  | 1 | 100% | 100% |  | 100% | 100%
9 | Y | 38.523-1 | 6.5.3.7 | SNPN / User Reselection in Automatic Mode / Using credentials from a credentials holder | TS 23.122, cl 4.9.3.2.1 (1) with { UE in Automatic SNPN selection mode and registered on an SNPN cell and supports access to an SNPN using credentials from a credentials holder, using the SNPN selection parameters in the selected entry of the "list of subscriber data" or associated with the selected PLMN subscription } ensure that { when { another SNPN is available supporting access using credentials from a credentials holder or allow registration attempts from MSs that are not explicitly configured to select the SNPN and UE is requested to initiate reselection and registration onto an available SNPN } then { UE reselects the SNPN cell } } | Lenovo | RAN5#100 (Aug-23) | R5-235366 R5-236835 |  | 1 | 100% | 100% |  | 100% | 100%
10 | Y | 38.523-1 | 6.5.3.8 | SNPN / cell reselection for IMS emergency services | TS 38.304, cl 5.2.8 (1) with { UE in SNPN access mode is in NR RRC_IDLE state and supports voice services } ensure that { when { UE receives SIB1 message indicating that the current cell does not support IMS voice calls for any SNPN(s) } then { UE perform cell selection/reselection to an acceptable cell of any available SNPN supporting emergency calls } } | Lenovo | RAN5#100 (Aug-23) | R5-235367 R5-236972 |  | 1 | 100% | 100% |  | 100% | 100%
11 | Y | 38.523-1 | 6.5.3.9 | SNPN / cell reselection / SNPN to PLMN | TS 23.122, cl 3.5 (1) with { UE in SNPN access mode is in limited service state and supports accessing a PLMN } ensure that { when { UE needs to make an emergency call and there is no available SNPN supporting emergency services } then { UE stops operating in SNPN access mode and attempts to camp on a cell of a PLMN } } | Lenovo | RAN5#100 (Aug-23) | R5-235368 R5-237403 R5-236973 |  | 1 | 100% | 100% |  | 100% | 100%
| Y | 38.523-1 | 6.3.3 | Steering of Roaming in SNPN | New sub-clause header |  |  |  |  | 1 | 0% | 0% |  | 0% | 0%
26 | Y | 38.523-1 | 6.3.3.1 | Steering of Roaming in SNPN / During registration / Security check successful / Without SOR Transparent container ACK request | TS 23.122, cl C.5 (1) with { UE being in automatic SNPN selection mode, current chosen non-subscribed SNPN is not contained in the list of "SNPNs where registration was aborted due to SOR" for the selected entry in the "list of subscriber data" or the selected PLMN subscription, and is not part of the user controlled prioritized list of preferred SNPNs for the selected entry in the "list of subscriber data" or the selected PLMN subscription and UE's ME configured with indication that the UE is to receive Steering of Roaming information due to initial registration in a non-subscribed SNPN } ensure that { when { SOR Transparent container indicates ACK has NOT been requested and security check on the steering of roaming information is successful and the UE has a list of available and allowable SNPN in the area and based on this list the UE determines that there is a higher priority SNPN than the selected SNPN } then { UE sends REGISTRATION COMPLETE message to the serving AMF without including an SOR transparent container and then either releases N1 NAS Signaling connection locally and then attempt to obtain service on a higher priority SNPN or optionally wait for network release of the NAS signalling connection and then selects higher priority SNPN } } (2) with { UE being in manual SNPN selection mode, current chosen non-subscribed SNPN is not contained in the list of "SNPNs where registration was aborted due to SOR" for the selected entry in the "list of subscriber data" or the selected PLMN subscription, and is not part of the user controlled prioritized list of preferred SNPNs for the selected entry in the "list of subscriber data" or the selected PLMN subscription and UE's ME configured with indication that the UE is to receive Steering of Roaming information due to initial registration in a non-subscribed SNPN } ensure that { when { SOR Transparent container indicates ACK has NOT been requested and security check on the steering of roaming information is successful and the UE has a list of available and allowable SNPN in the area and based on this list the UE determines that there is a higher priority SNPN than the selected SNPN } then { UE sends REGISTRATION COMPLETE message to the serving AMF without including an SOR transparent container and stays on this non-subscribed SNPN } } | China Telecom | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
27 | Y | 38.523-1 | 6.3.3.2 | Steering of Roaming in SNPN / After registration / Security check successful | TS23.122, cl C.6 (1) with { UE is in automatic SNPN selection mode and has registered onto a non-subscribed SNPN } ensure that { when { SOR Transparent container included in DL NAS TRANSPORT message contains steering of roaming information and indicates ACK has been requested and security check is successful } then { UE sends an SOR transparent container with ACK in UL NAS TRANSPORT message and waits until it moves to idle mode or 5GMM-CONNECTED mode with RRC inactive indication before attempting to obtain service on a higher priority SNPN } } (2) with { UE is in manaul SNPN selection mode and has registered onto a non-subscribed SNPN } ensure that { when { SOR Transparent container included in DL NAS TRANSPORT message contains steering of roaming information and indicates ACK has been requested and security check is successful and the current chosen non-subscribed SNPN is part of the user controlled prioritized list of preferred SNPNs } then { UE sends an SOR transparent container with ACK in UL NAS TRANSPORT message and stays on the current chosen non-subscribed } } | China Telecom | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
28 | Y | 38.523-1 | 6.3.3.3 | Steering of Roaming in SNPN / After registration / SOR-CMCI rule / match all | TS23.122, cl C.4.1, C.4.2 and C.4.3 (1) with { UE is in automatic SNPN selection mode and has registered onto a non-subscribed SNPN with an established PDU session } ensure that { when { UE receives SOR Transparent container included in DL NAS TRANSPORT message contains steering of roaming information with the SOR-CMCI field which includes Tsor-cm timer and Criterion type with setting as match all } then { UE snds an SOR transparent container with ACK in UL NAS TRANSPORT message and UE sends DEREGISTRATION REQUEST message after Tsor-cm timer expires and selects higher priority SNPN after DEREGISTRATION procedure is completed successfully } } | China Telecom | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
29 | Y | 38.523-1 | 6.3.3.4 | Steering of Roaming in SNPN / After registration / SOR-CMCI rule / match all / Emergency call | TS23.122, cl C.4.1, C.4.2, C.4.3 and C.6 (1) with { UE is in automatic SNPN selection mode and has registered onto a non-subscribed SNPN with an established PDU session } ensure that { when { UE receives SOR Transparent container included in DL NAS TRANSPORT message contains steering of roaming information with the SOR-CMCI field which includes Tsor-cm timer and Criterion type with setting as match all, and, UE sends an SOR transparent container with ACK in UL NAS TRANSPORT message, and, UE initiates Emergency call in 5GS and completes it successfully } then { UE sends RRCSetupRequest message after releasing Emergency call with expiring Tsor-cm timer and selects higher priority SNPN } } | China Telecom | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
RRC
|  | 38.523-1 | 8.1.7 | Non-public networks | Existing sub-clause header |  | RAN5#101 (Nov-23) |  |  | 0
13 |  | 38.523-1 | 8.1.7.2 | RRC connection establishment | New sub-clause header |  | RAN5#101 (Nov-23) |  |  | 0.1 | 0% | 0% |  | 0% | 0%
14 | Y | 38.523-1 | 8.1.7.2.1 | RRC connection establishment / RRC setup complete with onboarding request | TS 38.331, cl 5.3.3.4 (1) with { UE is in SNPN access mode and receives SIB1 message } ensure that { when { UE upper layers provide onboarding request indication and SIB1 message indicating that registration for onboarding in the cell is supported } then { UE includes the onboardingRequest in RRCSetupComplete message upon reception of the RRCSetup message } } | China Telecom | RAN5#101 (Nov-23) | R5-237448 |  | 1 | 100% (+20%) | 100% (+20%) |  | 100% | 100%
15 |  | 38.523-1 | 8.1.7.3 | PWS notification | New sub-clause header |  | RAN5#101 (Nov-23) |  | can be removed | 0 | 0% | 0% |  | 0% | 0%
16 | Y | 38.523-1 | 8.1.7.3.1 | PWS notification / PWS reception in NR RRC_IDLE state / Accesses an SNPN using the PLMN subscription |  | China Telecom | RAN5#101 (Nov-23) |  | can be removed | 0 | 0% | 0% |  | 0% | 0%
17 | Y | 38.523-1 | 8.1.7.3.2 | PWS notification / PWS reception in NR RRC_IDLE state / Accesses an SNPN using entries in the "list of subscriber data" | Existing sub-clause header | China Telecom | RAN5#101 (Nov-23) |  | can be removed | 0 | 0% | 0% |  | 0% | 0%
NAS
TBD |  | 38.523-1 | 9.1.11 | SNPN / Mobility management aspects | [5 empty] | 0
18 | Y | 38.523-1 | 9.1.11.4 | SNPN / Initial registration / Rejected / Tracking area not allowed / Access to an SNPN using credentials from a credentials holder | TS24.501, cl 5.5.1.2.5 (1) with { UE in Automatic SNPN selection mode and a SNPN cell is available for which an entry exists in the "list of subscriber data" and the UE in 5GMM-REGISTERED-INITIATED state } ensure that { when { the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #12 (Tracking area not allowed) } then { The UE deletes any 5G-GUTI, last visited registered TAI and ngKSI, and store the current TAI in the list of "5GS forbidden tracking areas for regional provision of service" for the selected entry of the "list of subscriber data", and enter the state 5GMM-DEREGISTERED.LIMITED-SERVICE } } | China Telecom | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
19 | Y | 38.523-1 | 9.1.11.5 | SNPN / Initial registration / Rejected / Illegal ME / Access to an SNPN for onboarding services | TS 24.501, cl 5.5.1.2.5, TS23.122, cl 4.9.3.1.3 and cl 4.9.3.1.4 (1) with { UE in Automatic SNPN selection mode and a SNPN cell is available for which an entry exists in the "list of subscriber data" and the UE in 5GMM-REGISTERED-INITIATED state for onboarding service} ensure that { when { the SS sends a REGISTRATION REJECT message to the UE including an appropriate 5GMM cause value #6 (Illegal ME) } then { The UE store the SNPN identity in the "permanently forbidden SNPNs" list for onboarding services and enter state 5GMM-DEREGISTERED.PLMN-SEARCH } } (2) with { the UE is in 5GMM-DEREGISTERED.PLMN-SEARCH state } ensure that { when { User manually selects the SNPN cell which belongs to the "permanently forbidden SNPNs" list } then { the UE attempts registration on the SNPN cell } } | China Telecom | RAN5#102 (Feb-24) | R5-241587 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
21 | Y | 38.523-1 | 9.1.11.6 | SNPN / EAP-AKA' related procedures / UE handling EAP-failure message / Access to an SNPN using credentials from a credentials holder and register for onboarding services | TS 24.501, cl 5.4.1.2.2.11 and 5.5.1.2.2 and TS23.122, cl 4.9.3.0 (1) with { The UE in 5GMM-REGISTERED-INITIATED state for onboarding service and SS initiates an EAP based primary authentication and key agreement procedure } ensure that { when { The SS sends an EAP-failure message within AUTHENTICATION REJECT } then { The UE shall store the SNPN identity in the "permanently forbidden SNPNs" list for onboarding services, enter state 5GMM-DEREGISTERED.PLMN-SEARCH, and perform SNPN selection } } (2) with { The UE in 5GMM-REGISTERED-INITIATED state using credentials from a credentials holder and SS initiates a EAP based primary authentication and key agreement procedure } ensure that { when { The SS sends an EAP-failure message within AUTHENTICATION REJECT } then { The UE shall consider the entry of the selected entry of the "list of subscriber data" as invalid for 3GPP access until the UE is switched off or the entry is updated, and the USIM is considered invalid until switching off the UE } } | China Telecom | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
22 | Y | 38.523-1 | 9.1.11.7 | SNPN / 5G AKA based primary authentication and key agreement procedure / Authentication not accepted by the network / Access to an SNPN using credentials from a credentials holder and register for onboarding services in SNPN | TS 24.501, cl 5.4.1.3.5 and 5.5.1.2.2 and TS23.122, cl 4.9.3.0 (1) with { the UE in 5GMM-REGISTERED-INITIATED state for onboarding service and SS initiates a 5G AKA based primary authentication and key agreement procedure } ensure that { when { UE receives an AUTHENTICATION REJECT message } then { UE shall store the SNPN identity in the "permanently forbidden SNPNs" list for onboarding services, enter state 5GMM-DEREGISTERED.PLMN-SEARCH, and perform SNPN selection } } (2) with { the UE in 5GMM-REGISTERED-INITIATED state using credentials from a credentials holder and SS initiates an EAP based primary authentication and key agreement procedure } ensure that { when { UE receives an AUTHENTICATION REJECT message } then { the UE shall consider the entry of the selected entry of the "list of subscriber data" as invalid for 3GPP access until the UE is switched off or the entry is updated, and the USIM is considered invalid until switching off the UE } } | China Telecom | RAN5#102 (Feb-24) |  |  | 1 | 0% | 0% |  | 0% | 0%
30 | Y | 38.523-1 | 11.4.15 | 5GMM-REGISTERED.NORMAL-SERVICE / 5GMM-IDLE / Emergency call / SNPN | TS 24.229, cl 5.1.6.2A and 5.1.6.8.3 (1) with { UE in SNPN access mode and in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-IDLE mode } ensure that { when { UE is requested to make an outgoing emergency call } then { UE performs IMS emergency registration and sets up an IMS emergency call } } (2) with { UE in SNPN access mode and in 5GMM-REGISTERED.NORMAL-SERVICE state and 5GMM-CONNECTED mode having established an Emergency call } ensure that { when { UE receives an IMS BYE message to release an emergency call } then { UE release the emergency call} } | Ericsson | RAN5#102 (Feb-24) | R5-241590 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 38.523-2: Applicability for Protocol test cases
23 |  | 38.523-2 | 4 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 | China Telecom | RAN5#100 (Aug-23) | R5-235363 R5-237449 R5-241646 R5-241185 |  | 2 | 95% (+45%) | 95% (+45%) |  | 95% | 95%
TS 38.523-3: Protocol test suites (TTCN)
24 |  | 38.523-3 | NA | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | TBD |  |  |  | 1 | 0% | 0% |  | 0% | 0%
Overall WP completion
25 |  | 38.523-2 | 4.3 | Scoping of SA NR Rel-15 applicable TCs for SNPN only UE |  | TBD | RAN5#101 (Nov-23) | R5-241589 |  | 1 | 50% (+50%) | 50% (+50%) |  | 50% | 50%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.