## R19 RAN4-led non-spectrum W-SI
| AI | UID | UID | Name | WI/SI Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | SR | Revised WID/SID | TU update | Change or comment for RAN4
1 | 9.2.3 |  | 1060078 | Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface Phase 2 | FS_NR_AIML_air_Ph2 | Sep. 2025 | 0% | RP-243245 | 50% | RP-250307 | RP-250308 |  | Rev SID: add UID, remove one-sided testability study.
3 | 9.2.4 |  | 1020084 | Study on AI (Artificial Intelligence)/ML (Machine Learning) for mobility in NR | FS_NR_AIML_Mob | Sep. 2025 | 50% | RP-242393 | 62.5% | RP-250168 |  | Yes. +1 TU RD | Adding TU by 1TU. RP-250478: Remove RLF.
2 | 9.2.5 |  | 1040100 | Study on spatial channel model for demodulation performance requirements for NR | FS_NR_demod_SCM | Sep. 2025 | 60% | RP-241848 | 45% | RP-250146 | RP-250577 | Yes. | Extend to 09/2025. Rev SID: add TS/TR number, extend to 09/2025
4 | 9.2.6 |  | 1030074 | Study on NR frequency range 2 (FR2) OTA (Over the Air) testing Phase 3 | FS_NR_FR2_OTA_Ph3 | Sep. 2025 | 90% | RP-242833 | 95% | RP-250334 | RP-250639/RP-250640 |  | The work on developing VSAT test methods following the completion in June 2024 of the core requirements specification for Ka band VSAT.RP-250640: Proposal-add VSAT ka band test
5 | 9.2.7 |  | 1030075 | Study on IMT parameters for NR for 4400 to 4800 MHz, 7125 to 8400 MHz and 14800 to 15350 MHz | FS_NR_IMT_4400_7125_14800MHz | Mar. 2025 | 95% | RP-242944 | 100% | RP-250538 |  |  | RP-250028: RAN4 reply LS. RP-250539: TR for completion of SI
6 | 9.2.8 |  | 1040101 | Study on NR FR1 DL fragmented carriers | FS_NR_FR1_DL_Frag_Carrier | Jun. 2025 | 25% | RP-243002 | 35% | RP-250469
7 | 9.3.1.1 |  | 1020089 | NR MIMO Phase 5 | NR_MIMO_Ph5 | Sep. 2025 |  | RP-242394 |  | RP-250053
8 | 9.3.1.1 |  | 1021089 | Core part: NR MIMO Phase 5 | NR_MIMO_Ph5-Core | Sep. 2025 | 70% |  | 80%
9 | 9.3.1.1 |  | 1022089 | Perf. part: NR MIMO Phase 5 | NR_MIMO_Ph5 | Mar. 2026 | 0% |  | 0%
10 | 9.3.1.2 |  | 1020090 | Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo | Sep. 2025 |  | RP-241614 |  | RP-250490 | RP-250328 |  | Rev WID: RAN3 objective modification for SRS and CLI RSSI measurement.RP-250521: Support inter-gNB coordination for SRS and CLI-RSSI.
11 | 9.3.1.2 |  | 1021090 | Core part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo | Sep. 2025 | 55% |  | 68%
12 | 9.3.1.2 |  | 1022090 | Perf. part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo | Mar. 2026 | 0% |  | 0%
13 | 9.3.1.3 |  | 1020093 | Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air | Sep. 2025 |  | RP-243244 |  | RP-250310 | RP-250311 |  | Rev WID: add one side testability and interoperability objective.[RAN4 Chair]: it seems belong to Core part.
14 | 9.3.1.3 |  | 1021093 | Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air | Sep. 2025 | 55% |  | 65%
15 | 9.3.1.3 |  | 1022093 | Perf. part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air | Mar. 2026 | 0% |  | 0%
16 | 9.3.1.4 |  | 1020094 | Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS | Sep. 2025 |  | RP-241824 |  | RP-250194
17 | 9.3.1.4 |  | 1021094 | Core part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS-Core | Sep. 2025 | 55% |  | 70%
18 | 9.3.1.4 |  | 1022094 | Perf. part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS-Perf | Mar. 2026 | 0% |  | 0%
19 | 9.3.1.5 |  | 1020095 | Enhancements of network energy savings for NR | Netw_Energy_NR_enh | Sep. 2025 |  | RP-242354 |  | RP-250342 | RP-250343 |  | Rev WID: add RAN2/RAN3 spec (38.304 and 38.401)
20 | 9.3.1.5 |  | 1021095 | Core part: Enhancements of Network energy savings for NR | Netw_Energy_NR_enh-Core | Sep. 2025 | 60% |  | 70%
21 | 9.3.1.5 |  | 1022095 | Perf. part: Enhancements of Network energy savings for NR | Netw_Energy_NR_enh-Perf | Mar. 2026 | 0% |  | 0%
| 9.3.1.7 |  | 1060084 | Solutions for Ambient IoT (Internet of Things) in NR | Ambient_IoT_Solutions | Sep. 2025 |  | RP-243326 |  | RP-250267 | RP-250268 |  | Rev WID: adding UID, RAN1 change about FEC, RAN2 change regarding temporary ID and random access solution 3, and adding new TS.
| 9.3.1.7 |  | 1060084 | Core part: Enhancements of Network energy savings for NR | Ambient_IoT_Solutions-Core | Sep. 2025 | 0% |  | 27%
| 9.3.1.7 |  | 1060084 | Perf. part: Enhancements of Network energy savings for NR | Ambient_IoT_Solutions-Perf | Mar. 2026 | 0% |  | 9%
22 | 9.3.2.1 |  | 1020091 | NR mobility enhancements Phase 4 | NR_Mob_Ph4 | Sep. 2025 |  | RP-242356 |  | RP-250338 | RP-250339 |  | Rev WID: remove intra-CU conditional LTM for DC.
23 | 9.3.2.1 |  | 1021091 | Core part: NR mobility enhancements Phase 4 | NR_Mob_Ph4-Core | Sep. 2025 | 50% |  | 65%
24 | 9.3.2.1 |  | 1022091 | Perf. part: NR mobility enhancements Phase 4 | NR_Mob_Ph4-Perf | Mar. 2026 | 0% |  | 0%
25 | 9.3.2.2 |  | 1020097 | Rel-19 Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3 | Sep. 2025 |  | RP-243300 |  | RP-250041
26 | 9.3.2.2 |  | 1021097 | Core part: Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3-Core | Sep. 2025 | 55% |  | 75%
27 | 9.3.2.2 |  | 1022097 | Perf. part: Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3-Perf | Mar. 2026 | 0% |  | 0%
28 | 9.3.2.3 |  | 1020098 | XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3 | Sep. 2025 |  | RP-243318 |  | RP-250106
29 | 9.3.2.3 |  | 1021098 | Core part: XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3-Core | Sep. 2025 | 55% |  | 67%
30 | 9.3.2.3 |  | 1022098 | Perf. part: XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3-Perf | Mar. 2026 | 0% |  | 0%
31 | 9.3.4.1 | 941012 | 1030077 | UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 | NR_ENDC_RF_Ph4 | Sep. 2025 |  | RP-241656 |  | RP-250280 |  |  | RP-250324: Reflect the agreement of RAN4 by revising the WID for 6-layer.
32 | 9.3.4.1 |  | 1031077 | Core part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 | NR_ENDC_RF_Ph4 | Sep. 2025 | 50% |  | 60%
33 | 9.3.4.1 |  | 1032077 | Perf. part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 | NR_ENDC_RF_Ph4 | Mar. 2026 | 20% |  | 20%
34 | 9.3.4.2 |  | 1030078 | NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo | Sep. 2025 |  | RP-243270 |  | RP-250436 |  |  | RP-250437: TR for approval to complete the work of EEIRP.RP-250438/RP-250439: CRs to complete EEIRP work
35 | 9.3.4.2 |  | 1031078 | Core part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo-Core | Sep. 2025 | 30% |  | 50%
36 | 9.3.4.2 |  | 1032078 | Perf. part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo-Perf | Mar. 2026 | 10% |  | 30%
37 | 9.3.4.3 |  | 1030079 | NR Radio Resource Management (RRM) Phase 5 | NR_RRM_Ph5 | Sep. 2025 |  | RP-242380 |  | RP-250320
38 | 9.3.4.3 |  | 1031079 | Core part: NR Radio Resource Management (RRM) Phase 5 | NR_RRM_Ph5-Core | Sep. 2025 | 60% |  | 75%
39 | 9.3.4.3 |  | 1032079 | Perf. part: NR Radio Resource Management (RRM) Phase 5 | NR_RRM_Ph5-Perf | Mar. 2026 | 0% |  | 0%
40 | 9.3.4.4 |  | 1030081 | NR channel BW less than 5MHz for FR1 Phase 2 | NR_FR1_lessthan_5MHz_BW_Ph2 | Dec. 2024 |  | RP-243309 |  | RP-250462 | RP-250463 |  | Rev WID: removing RAN2 spec.RP-250464:WI summary. RP-250152: Proposal-whether RAN4 shall introduce UE demodulation performance requirements for CA in Rel-19 “NR_FR1_lessthan_5MHz_BW_Ph2-Perf
41 | 9.3.4.4 |  | 1031081 | Core part: NR channel BW less than 5MHz for FR1 Phase 2 | NR_FR1_lessthan_5MHz_BW_Ph2-Core | Mar. 2025 | 99% |  | 100%
42 | 9.3.4.4 |  | 1032081 | Perf. part: NR channel BW less than 5MHz for FR1 Phase 2 | NR_FR1_lessthan_5MHz_BW_Ph2-Perf | Jun. 2025 | 0% |  | 30%
43 | 9.3.4.5 |  | 1031082 | Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) | NonCol_intraB_ENDC_NR_CA_Ph2 | Sep. 2025 |  | RP-242083 |  | RP-250279
44 | 9.3.4.5 |  | 1031082 | Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) | NonCol_intraB_ENDC_NR_CA_Ph2-Core | Sep. 2025 | 45% |  | 50%
45 | 9.3.4.5 |  | 1032082 | Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) | NonCol_intraB_ENDC_NR_CA_Ph2-Perf | Mar. 2026 | 0% |  | 30%
46 | 9.3.4.6 |  | 1030083 | Enhancements for Air-to-ground network for NR | NR_ATG_enh | Sep. 2025 |  | RP-243285 |  | RP-250271
47 | 9.3.4.6 |  | 1031083 | Core part: Enhancements for Air-to-ground network for NR | NR_ATG_enh-Core | Sep. 2025 | 55% |  | 70%
48 | 9.3.4.6 |  | 1032083 | Perf. part: Enhancements for Air-to-ground network for NR | NR_ATG_enh-Perf | Mar. 2026 | 0% |  | 0%
49 | 9.3.4.7 |  | 1030084 | NR Sidelink: Intra-band Carrier Aggregation in ITS band | NR_SL_intraB_CA_ITS-Core | Sep. 2025 |  | RP-240840 |  | RP-250166
50 | 9.3.4.7 |  | 1031084 | Core part: NR Sidelink: Intra-band Carrier Aggregation in ITS band | NR_SL_intraB_CA_ITS-Core | Sep. 2025 | 75% |  | 90%
51 | 9.3.4.8 |  | 1030085 | WI on TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 | TRP_TRS_MIMO_OTA_Ph3 | Sep. 2025 |  | RP-243277 |  | RP-250196 | RP-250197 |  | Rev WID: removing objective of requirements related to headworn XR OTA device
52 | 9.3.4.8 |  | 1031085 | Core part: TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 | TRP_TRS_MIMO_OTA_Ph3-Core | Sep. 2025 | 45% |  | 65%
53 | 9.3.4.8 |  | 1032085 | Perf. part: TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 | TRP_TRS_MIMO_OTA_Ph3-Perf | Mar. 2026 | 25% |  | 35%
54 | 9.3.4.9 |  | 1030086 | Enhanced requirements and test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh | Sep. 2025 |  | RP-242901 |  | RP-250099
55 | 9.3.4.9 |  | 1031086 | Core part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh-Core | Sep. 2025 | 50% |  | 65%
56 | 9.3.4.9 |  | 1032086 | Perf. Part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh-Perf | Mar. 2026 | 30% |  | 35%
57 | 9.3.4.10 |  | 1030080 | NR demodulation performance Phase 5 | NR_demod_Ph5 | Sep. 2025 |  | RP-241297 |  | RP-250367
58 | 9.3.4.10 |  | 1032080 | Perf. part: NR demodulation performance Phase 5 | NR_demod_Ph5-Perf | Sep. 2025 | 43% |  | 58%
| 9.3.4.11 |  | 1060082 | Low band carrier aggregation via switching | NR_LBCA_Sw | Sep. 2025 |  | RP-243317 |  | RP-250246 | RP-250247 |  | Rev WID: adding UID, adding TR number and adding RAN2 as secondary group.RP-250641: Proposal-Switch between FDD and FDD+SDL
| 9.3.4.11 |  | 1060082 | Core part: Low band carrier aggregation via switching | NR_LBCA_Sw-Core | Sep. 2025 | 0% |  | 10%
| 9.3.4.11 |  | 1060082 | Perf. part: Low band carrier aggregation via switching | NR_LBCA_Sw-Perf | Mar. 2026 | 0% |  | 0%
59 | 10.3.1 |  | 1020096 | Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 (for LTE) | IoT_NTN_Ph3 | Sep. 2025 |  | RP-243278 |  | RP-250470 | RP-250471/RP-250472 |  | Rev WID: Proposal 1: Update the WID objective to remove OCC support for NPRACH. Proposal 2: RAN1 should not work on specifying support of PWS notification monitoring for NB-IoT UEs in RRC connected mode in Rel-19. Proposal 3: Add the following note to constrain the scope of further discussion on PWS for UE originally in RRC connected mode.
60 | 10.3.1 |  | 1021096 | Core part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 | IoT_NTN_Ph3-Core | Sep. 2025 | 30% |  | 70%
61 | 10.3.1 |  | 1032087 | Perf. part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 | IoT_NTN_Ph3-Perf | Mar. 2026 | 0% |  | 0%
| 10.3.3 |  | 1060081 | LTE-based 5G Broadcast Phase 2 | LTE_terr_bcast_Ph2 | Dec. 2025 |  | RP-243290 |  | RP-250238 | RP-250239 |  | Rev WID: clarify the objectives with more details for RAN1/RAN2.
| 10.3.3 |  | 1060081 | Core part: LTE-based 5G Broadcast Phase 2 | LTE_terr_bcast_Ph2-Core | Sep. 2025 | 0% |  | 40%
| 10.3.3 |  | 1060081 | Perf. part: LTE-based 5G Broadcast Phase 2 | LTE_terr_bcast_Ph2-Perf | Dec. 2025 | 0% |  | 0%

## R19 RAN4-led spectrum WI
AI | UID | Name | WI/SI Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | SR | Revised WID/SID | TU update | Change or comment for RAN4
9.4.1.1 | 1040127 | Introduction of the NR FDD 1.4 GHz band | NR_FDD_1400MHz | Mar. 2025 |  | RP-242120 |  | RP-250403
9.4.1.1 | 1041127 | Core part: Introduction of the NR FDD 1.4GHz band | NR_FDD_1400MHz-Core | Mar. 2025 | 99% |  | 100%
9.4.1.1 | 1042127 | Perf. part: Introduction of the NR FDD 1.4GHz band | NR_FDD_1400MHz-Perf | Mar. 2025 | 99% |  | 100%
9.4.1.2 | 1040131 | Introduction of NR bands n87 and n88 | NR_bands_n87_n88 | Mar. 2025 |  | RP-242501 |  | RP-250149
9.4.1.2 | 1041131 | Core part: Introduction of NR bands n87 and n88 | NR_bands_n87_n88-Core | Mar. 2025 | 66% |  | 100%
9.4.1.2 | 1042131 | Perf. part: Introduction of NR bands n87 and n88 | NR_bands_n87_n88-Perf | Mar. 2025 | 66% |  | 100%
9.4.1.3 | 1040132 | Introduction of NR band n68 | NR_band_n68 | Mar. 2025 |  | RP-242606 |  | RP-250525
9.4.1.3 | 1041132 | Core part: Introduction of NR band n68 | NR_band_n68-Core | Mar. 2025 | 60% |  | 100%
9.4.1.3 | 1042132 | Perf. part: Introduction of NR band n68 | NR_band_n68-Perf | Mar. 2025 | 60% |  | 100%
9.4.1.4 | 1040129 | Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | NR_NTN_Sband | Jun. 2025 |  | RP-241885 |  | RP-250487 | RP-250488 |  | Extend to 06/2025. Rev WID: modifying the impacted spec
9.4.1.4 | 1041129 | Core part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | NR_NTN_Sband-Core | Jun. 2025 | 50% |  | 70%
9.4.1.4 | 1042129 | Perf. part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | NR_NTN_Sband-Perf | Jun. 2025 | 0% |  | 0%
9.4.1.5 | 1040134 | Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) | NR_NTN_combinedLband | Mar. 2025 |  | RP-241856 |  | N/A
9.4.1.5 | 1041134 | Core part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) | NR_NTN_combinedLband-Core | Mar. 2025 | 35%
9.4.1.5 | 1042134 | Perf. part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) | NR_NTN_combinedLband-Perf | Jun. 2025 | 0%
9.4.1.6 | 1040135 | Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands | Sep. 2025 |  | RP-243314 |  | RP-250466 | RP-250467 |  | Rev WID: adding both 15KHz and 30KHz SCS to FR1-NTN
9.4.1.6 | 1041135 | Core part: Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands-Core | Sep. 2025 | 30% |  | 50%
9.4.1.6 | 1042135 | Perf. part: Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands-Perf | Mar. 2026 | 0% |  | 0%
9.4.1.7 | 1040121 | Core part: Additional NR bands for NR features in Rel-19 | NR_bands_xFeature_R19-Core | Sep. 2025 | 35% | RP-242572 | 50% | RP-250212 | RP-250211 |  | Rev WID: revise the status of the requests.
9.4.1.8 | 1050127 | Introduction of additional operating NR bands for HAPS | NR_HAPS_bands-Core | Mar. 2025 | 99% | RP-242891 | 100% | RP-250407
9.4.2.1 | 1040119 | Core part: Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (x<=6) and single or two NR Supplementary Uplink (SUL) bands | DC_R19_xBLTE_yBNR-Core | Sep. 2025 | 15% | RP-243257 | 25% | RP-250142 | RP-250143
9.4.2.2 | 1040120 | Core part: Rel-19 NR Carrier Aggregation (CA)/Dual Connectivity (DC) for x bands DL with y bands UL (x<7, y<3) and Supplementary Uplink (SUL) band combinations/CA band combinations with a single SUL or two SUL cells | NR_CADC_SUL_R19-Core | Sep. 2025 | 34% | RP-242754 | 35% | RP-250213 | RP-250214 |  | Rev WID: modifying the status and adding new requests.
9.4.2.3 | 1040125 | Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 | LTE_NR_R19_Simult_RxTx-Core | Sep. 2025 | 50% | RP-243015 | 70% | RP-250283
9.4.2.4 | 1040118 | Core part: Rel-19 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R19-Core | Sep. 2025 | 20% | RP-241672 | 40% | RP-250368 | RP-250369 |  | Rev WID: adding UID, adding TR number.
9.4.3.1 | 1041122 | Core part: Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) | HPUE_DC_LTE_NR_R19-Core | Sep. 2025 | 30% | RP-242609 | 50% | RP-250428 | RP-250424 |  | Rev WID: adding new requests and modifying the requests.
9.4.3.2 | 1040123 | Core part: Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual connectivity (DC) band combinations with/without NR SUL (supplementary uplink) | HPUE_NR_CADC_SUL_R19 | Sep. 2025 | 30% | RP-242865 | 45% | RP-250371 | RP-250370 |  | Rev WID: modifying the status of requested BC
9.4.3.3 | 1040133 | Core part: NR power class 2 RedCap (Reduced Capability) UE in FR1 | NR_PC2_RedCap_UE-Core | Jun. 2025 | 50% | RP-243267 | 70% | RP-250372
9.4.3.4 | 1040124 | Core part: Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band, and high power UE operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single NR band | HPUE_NR_FR1_bands_R19-Core | Sep. 2025 | 30% | RP-243321 | 55% | RP-250272
9.4.3.5 | 1040128 | Core part: Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 | NR_n28_PC2_40MHz_CBW-Core | Mar. 2025 | 99% | RP-241930 | 100% | RP-250273 | RP-250274 |  | Rev WID (not available)
9.4.4.1 | 1041126 | Core part: Adding channel bandwidth(s) support to existing NR bands and CA/ENDC combinations in REL-19 | NR_bands_CA_ENDC_R19_BWs-Core | Sep. 2025 | 15% | RP-242604 | 25% | RP-250523 | RP-250524 |  | Rev WID: update the status of requests
9.4.4.2 | 1050126 | mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection | NR_mmWave_protect | Jun. 2025 |  | RP-242611 |  | RP-250429
9.4.4.2 | 1051126 | Core part: mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection | NR_mmWave_protect-Core | Jun. 2025 | 40% |  | 80%
9.4.4.2 | 1052126 | Perf. part: mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection | NR_mmWave_protect-Perf | Jun. 2025 | 40% |  | 80%
9.4.4.3 | 1060083 | 7MHz Channel Bandwidth for n26 and n5 | NR_FR1_7MHz_BW | Sep. 2025 |  | RP-243323 |  | RP-250374 | RP-250373 |  | Rev WID: revising title, UID, checking box for performance part,
9.4.4.3 | 1061083 | Core part: 7MHz Channel Bandwidth for n26 and n5 | NR_FR1_7MHz_BW-Core | Sep. 2025 | 0% |  | 10%
9.4.4.3 | 1062083 | Perf. part: 7MHz Channel Bandwidth for n26 and n5 | NR_FR1_7MHz_BW-Perf | Mar. 2026 | 0% |  | 0%
10.4.1 | 1040117 | Introduction of LTE FDD band in 1800–1830 MHz for Canada | LTE_FDD_1800_1830MHz_CAN | Mar. 2025 |  | RP-242461 |  | RP-250105
10.4.1 | 1041117 | Core part: Introduction of LTE FDD band in 1800–1830 MHz for Canada | LTE_FDD_1800_1830MHz_CAN-Core | Mar. 2025 | 99% |  | 100%
10.4.1 | 1042117 | Perf. part: Introduction of LTE FDD band in 1800–1830 MHz for Canada | LTE_FDD_1800_1830MHz_CAN-Perf | Mar. 2025 | 99% |  | 100%
10.4.2 | 1040130 | Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | IoT_NTN_FDD_S_band | Jun. 2025 |  | RP-242062 |  | RP-250473 | RP-250474 |  | Extend core to June 2025.The time budget needs be modified.Core: 70% 06/2025;Perf: 0% 06/2025.Rev WID: Update the impacted spec. Add the supporting company.
10.4.2 | 1041130 | Core part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | IoT_NTN_FDD_S_band-Core | Jun. 2025 | 50% |  | 70%
10.4.2 | 1042130 | Perf. part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | IoT_NTN_FDD_S_band-Perf | Jun. 2025 | 0% |  | 0%
10.4.3 | 1040116 | Core part: Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single LTE band | HPUE_LTE_bands_R19-Core | Sep. 2025 | 10% | RP-241681 | 10% | RP-250148
10.4.4 | 1040115 | Core part: Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R19_xBDL_yBUL-Core | Sep. 2025 | 31% | RP-243014 | 60% | RP-250281 | RP-250282 |  | Rev WID: Modify the requested band combinations and add new ones.
10.4.5 | 1050123 | Introduction of IoT-NTN TDD mode | IoT_NTN_TDD | Sep. 2025 |  | RP-243293 |  | RP-250045
10.4.5 | 1051123 | Core part:Introduction of IoT-NTN TDD mode | IoT_NTN_TDD-Core | Sep. 2025 | 20% |  | 30%
10.4.5 | 1052123 | Perf. part:Introduction of IoT-NTN TDD mode | IoT_NTN_TDD-Perf | Mar. 2026 | 0% |  | 0%
10.4.6 | 1061080 | Core part: New bands for LTE based 5G terrestrial broadcast for early deployments | LTE_terr_bcast_bands_sub_108-Core | Jun. 2025 | 0% | RP-243268 | 40% | RP-250235 | RP-250237 |  | Rev WID: update acronym,clarify the scope for RF core requirements, i.e., 6/7/8MHz PMCH, and change the rapporteur. No need to attach the TU spreadsheet.