3GPP TSG RAN meeting #107									           RP-250041

Incheon, Korea, March 13-14th , 2025					rev of RP-242462

## Status Report to TSG

Title:			Status report for WID: Non-Terrestrial Networks (NTN) for NR Phase 3; rapporteur: Thales, CATT

Agenda item:			9.3.2.2

| WI / SI Name | Rel-19 Non-Terrestrial Networks (NTN) for NR Phase 3 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: Yes | Performance part: Yes |  | Testing part: No |
| Acronym | NR_NTN_Ph3 |  |  |  |  |
| Unique ID | 1020097 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-243300 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: N/A | Core part: 09/2025 | Performance part: 03/2026 | Testing part: |  |
| Overall Completion level | Study Item: N/A | Core part: Overall: 75% RAN1: 75% RAN2: 75% RAN3: 80% RAN4: 70% | Performance Part: Overall: 0% RAN4: 0% | Testing part: |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | RAN2 |
| --- | --- | --- |
| Rapporteur | Name | Nicolas Chuberre |
|  | Company | Thales |
|  | Email | Nicolas.chuberre@thalesaleniaspace.com |
|  | Name | Jiancheng Sun |
|  | Company | CATT |
|  | Email | sunjiancheng@catt.cn |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

-

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

## 2.1	RAN1

#### 2.1.1	Agreements

#### 2.1.1.1 Decisions during RAN1#120

2.1.1.1.1 NR-NTN downlink coverage enhancement

Agreement

For NR NTN, support extended periodicity of the half frames with SS/PBCH blocks assumed by UE during initial access.

- The additional default value assumed by UE during initial access (apart from the existing 20ms value) is 160 ms.

Agreement

Support only inter-slot repetition for Type0 PDCCH CSS.

Agreement

For Msg4 PDSCH repetition support, RAN1 to consider:

- Option 1: UE specific repetition indication via DCI

- Option 2: Msg4 repetition is configured by SIB1

- Option 3: Msg4 PDSCH repetition is implicitly determined by SIB1 PDSCH repetition

Agreement

At least for enabling PDCCH repetition for Type0 PDCCH CSS of searchSpaceZero configured within MIB pdcch-ConfigSIB1, RAN1 to consider the following options

- Option 1: Using the spare 1 bit in MIB

- Option 2: Using reserved bit(s) in PBCH payload

- Option 3: Using codepoint(s) in PBCH payload

- Option 4: UE blind decoding without signaling from the network during initial access

Agreement

For PDCCH repetition for Type0 PDCCH CSS of searchSpaceZero configured within MIB pdcch-ConfigSIB1, consider the following:

- Option 1: Support repeated PDCCH candidates in the two consecutive slots  n0 and n0+1 associated with the same SSB index ( n0 as defined in section 13 of TS 38.213)

  - Repeated PDCCH candidates share the same aggregation level (AL), coded bits and same candidate index

  - FFS: Details including how the two PDCCH candidates are counted toward the BD limits

  - Note: with option 1, if the network repeats the Type 0 PDCCH across two consecutive slots, a legacy UE might decode the PDCCH and associated PDSCH in one slot and skip PDCCH monitoring in the other slot.

  - FFS: whether/how option 1 can be applicable for M=1 and M= ½

- Option 2: Support repeated PDCCH candidates in the two slots  n0 and n0+X [or n0+1 and n0+1+X ] associated with the same SSB index ( n0 as defined in section 13 of TS 38.213)

  - Value of X>1, predefined or configured

    - FFS: Value of X

  - Repeated PDCCH candidates share the same aggregation level (AL), coded bits and same candidate index

  - FFS: Backward compatibility to legacy UE

- Option 3:

  - The PDCCH candidates in slots n0 associated respectively with different SSB indexes are repetitions of each other and share the same aggregation level, coded bits and same candidate index

    - For M=1/2 and M=1, the repeated PDCCH candidates in two consecutive slots associated with different SSB indexes;

    - For M=2, the PDCCH candidates in slots n0+1 associated respectively with different SSB indexes are repetitions of each other and share the same aggregation level, coded bits and same candidate index

- Option 4: Option 2 with cross SSB beam repetition support

  - The PDCCH candidates in slots n0 associated respectively with different SSB indexes are repetitions of each other and share the same aggregation level, coded bits and same candidate index

Agreement

For SIB1 link level enhancement, RAN1 to consider the following options:

- Option 1: PDSCH repetition of SIB1 is transmitted within the same slot as the type0-CSS PDCCH repetition.

  - UE supporting SIB1 PDSCH coverage enhancement assumes that the PDCCH and associated PDSCH to be repeated in both slots where the corresponding PDCCHs are transmitted.

  - Each PDSCH SIB1 repetition is within the same slot of each PDCCH candidate for scheduling DCI

  - The two associated PDSCHs have the same RV

- Option 2: Option 1 and an additional PDSCH with SIB1 repetition can occur after the slot of type0-PDCCH CSS repetition.

  - FFS: How to schedule the SIB1 repetition

- Option 3: The repetition of PDSCH with SIB1 is indicated by the scheduling PDCCH

  - PDSCH is repeated in two slots

Note: Backward compatibility should be maintained

2.1.1.1.2 Support of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands

Agreement

When network indicates UL overriding DL in RRC-Connected mode for collision case 3, one UE-specific RRC parameter is used to indicate overriding for all the applicable other use cases except for collisions with Type-0/0A/1/2-PDCCH CSS.

Conclusion

For Rel-19 HD-FDD (e)Redcap UE with CG-SDT procedure ongoing in RRC-inactive mode, for collision case 3,

- Handling of collision with PDCCH CSS in RRC-inactive mode is left to UE implementation whether to prioritize UL or prioritize DL with the constraint in the following note.

Note: UE shall comply to the following existing procedure in 38.331:

- UEs in RRC_INACTIVE while SDT procedure is not ongoing shall monitor for SI change indication in its own paging occasion(s) that the UE monitors as specified in TS 38.304 [20].

- UEs in RRC_INACTIVE while SDT procedure is ongoing shall monitor for SI change indication in any paging occasion at least once per modification period, if the initial downlink BWP on which the SDT procedure is ongoing is associated with a CD-SSB.

- ETWS or CMAS capable UEs in RRC_INACTIVE while SDT procedure is not ongoing shall monitor for indications about PWS notification in its own paging occasion every DRX cycle.

- ETWS or CMAS capable UEs in RRC_INACTIVE while SDT procedure is ongoing shall monitor for indication about PWS notification in any paging occasion at least once every defaultPagingCycle.

Working assumption

For Rel-19 NTN HD-FDD (e)Redcap UE in RRC connected mode, the following handling rule for collision case 4 is supported:

- Handling of collision with PDSCH (at least for system information) scheduled by Type-0/0A[/1][/2]-PDCCH CSS in RRC-Connected mode is left to UE implementation whether to prioritize UL or prioritize DL with the constraint in the following note.

- FFS: handling of PDCCH ordered PRACH transmission

- For other use cases, default priority rule for collision case 4 in RRC-Connected mode is that [DL or UL] is prioritized.

  - Network is allowed to indicate [UL or DL] overriding [DL or UL] for all cases

    - This is signaled by one UE specific RRC parameter

  - Note: if DL is prioritized, the DL prioritization applies only if the UL cancellation timeline can be satisfied, otherwise UL is prioritized.

Note: UE shall comply to the following existing procedure in 38.331:

- UEs in RRC_CONNECTED shall monitor for SI change indication in any paging occasion at least once per modification period if the UE is provided with common search space, including pagingSearchSpace, searchSpaceSIB1 and searchSpaceOtherSystemInformation, on the active BWP to monitor paging, as specified in TS 38.213 [13], clause 13.

2.1.1.1.3 NR-NTN uplink capacity/throughput enhancement

Conclusion

For OCC time synchronization / alignment of multiplexed UEs to maintain orthogonality of the codes used for OCC, OCC group alignment is handled by network scheduling without specification impact.

Conclusion

OCC with Msg3 PUSCH is not in scope of Release 19 NR NTN Ph3.

Agreement

For RV cycling for OCC with DG-PUSCH, support Option 1

- Option 1: RV cycling is used across OCC groups.

  - Note: when option 1 is applied, RV cycling is applied when the number of repetitions is greater than the OCC length

No optimization in Rel-19 for pairing UEs with OCC2 and UEs with OCC4.

#### 2.1.2	Remaining Open issues

- Address the anticipated specs impacts due to the extended SSB periodicity up to 160ms.

The additional default value assumed by UE during initial access (apart from the existing 20ms value) is 160 ms.

- Introduce necessary features to support link level enhancements for the targeted physical channels, including: (1) PDCCH CSS for all CSS types except type 3. (2) PDSCH with Msg4. (3) PDSCH with SIB1.

- Define necessary physical layer features enabling to support of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands

- Define necessary physical layer features to support NR-NTN uplink capacity/throughput enhancement

## 2.2	RAN2

#### 2.2.1	Agreements

2.2.1.1 Decisions during RAN2#129

2.2.1.1.1 Downlink coverage enhancement

Agreements:

1.	RAN2 assumes it will be possible to have different SSB periodicity among neighbour cells in the same frequency layer

2.	RAN2 assumes that in a NR NTN cell, SSB beam sweeping in different spatial directions is possible as in a NR TN cell: the whole cell is covered by the different SSB beams in half-frame

3.	RAN2 also assumes that, with the current status of RAN1 discussion, if one cell is defined by multiple “satellite beams”, the satellite beams are all simultaneously active or inactive (“beam hopping” applies equally to all the satellite beams of a given cell)

4.	The number of SMTC/gaps a UE needs to consider at any time will not be increased further

2.1.1.1.2 Uplink capacity/throughput enhancement

-

2.1.1.1.3 Support of Broadcast

Agreements:

1.	In the new SIB, explicit network-indicated area ID is used to label an intended service area in the list

2.	It shall be possible to signal multiple service area IDs to one MBS service (we Insert a list of service area IDs in MCCH)

3.	Introduce “warning area coordinates” in ETWS Primary Notification (SIB6) and in ETWS Secondary Notification (SIB7). FFS on the signalling details for “warning area coordinates” (SIB6 is not segmented)

2.1.1.1.4 Support of Regenerative payload

-

#### 2.2.2	Remaining Open issues

NR-NTN downlink coverage enhancement

- Define procedures and related signalling for system-level power sharing following RAN1 conclusions and related signalling for link-level enhancements following RAN1 conclusion

NR-NTN uplink capacity/throughput

- Define necessary related procedures and signalling following RAN1 conclusions

Support of broadcast

- SIB content definition for intended service area and related procedures

## 2.3	RAN3

#### 2.3.1	Agreements

2.3.1.1 Decisions during RAN3#127

Endorsed as BL CRs:

- R3-250052 (BL CR to 38.410) Introduce NG Removal procedure (CMCC, Huawei, Nokia, Nokia Shanghai Bell, CATT, Ericsson, Qualcomm, Xiaomi, LG Electronics, China Telecom, Samsung, ZTE, NEC, ETRI)	CR0051r2, TS 38.410 v18.2.0, Rel-19, Cat. B

- R3-250053 (BL CR to 38.300) Support for Regenerative Payload and MBS broadcast in NR NTN (Ericsson, Thales, Deutsche Telekom, Nokia, ESA, CATT, ZTE, Sateliot, Huawei, Dish Networks, Echostar, Eutelsat Group, Xiaomi, Samsung, CMCC, LG Electronics, NEC, Lenovo, ETRI)

- R3-250054 Support for Regenerative Payload and MBS broadcast in NR NTN (CATT, Thales, Nokia, Nokia Shanghai Bell, Ericsson, Huawei, ZTE, Qualcomm, Samsung, Xiaomi, CMCC, China Telecom, Jio, LG Electronics,  NEC, ETRI, SES, ESA)	CR1212r3, TS 38.413 v18.4.0, Rel-19, Cat. B

2.3.1.1.1 Support MBS Broadcast service

Agreements:

Encode the Intended MBS service area as OCT STRING which refers to RAN2 spec.

Agreed TPs

- R3-250870 (TPs to BL CR 38.300 and 38.413) Discussion on NTN broadcast service supporting (ZTE Corporation, Nokia, Nokia Shanghai Bell, Huawei, Qualcomm, CATT)

- R3-250893 (TP for TS 38.300 and TS 38.413) Support MBS broadcast service (Huawei, Nokia, Nokia Shanghai Bell, Qualcomm Incorporated, Ericsson, Xiaomi, ZTE, CATT)

2.3.1.1.2 Support of Regenerative payload

Agreements:

Clarify the concerns mentioned in the incoming LS without any change on RAN3 previous agreements.

Agreed TP:

- R3-250308	(TP for TS 38.300 BL CR) Stage 2 Corrections (Ericsson, Huawei, Nokia, Nokia Shanghai Bell, Thales, CATT, Qualcomm Incorporated, LG Electronics)

Agreed LS:

- R3-250895 Reply LS to SA2 and SA5 on OAM requirements to support regenerative payload transport links (CATT)

  - NG Setup procedure including the supported TAs is always expected to take place according to TS38.413.

#### 2.3.2	Remaining Open issues

Support of regenerative payload:

- Whether to make any enhancement to support RRC_INACTIVE.

- Whether to support NG Suspend/Resume.

- Any Xn enhancements whether to exchange some information for location based CHO.

- Any issue left to feeder link switch (e.g. Path switch)

## 2.4	RAN4

#### 2.4.1	Agreements

2.4.1.1 Decisions during RAN4#113

2.4.1.1.1 UE RF requirements

Approved document

- R4-2502281  Way Forward for [114][310] NR_NTN_Ph3_UE_RF, 	Qualcomm

2.4.1.1.2 SAN RF requirements

-

2.4.1.1.3 RRM requirements

Agreement:

- For SDT requirement in RRC_INACTIVE state for (e)RedCap with NTN, TA validation based on the RSRP change criterion for RedCap in TN shall be removed and RAN4 can refer to the requirements on TA validation for the PUR requirements for IoT-NTN, that is,

  - Define the requirement based on cg-SDT-timeAlignmentTimer and valid values for NTA, NTA,offset, NTA,adjcommon and   NTA,adjUE , specific approach can refer to the PUR requirements for IOT-NTN.

Agreement:

- For MDT requirements in RRC_IDLE and RRC_INACTIVE state,

  - Deprioritize to define Minimization of Drive Tests (MDT) requirements in RRC_IDLE state and RRC_INACTIVE state for (e)RedCap UE with FR1-NTN.

Agreement:

- From RAN4 requirement perspective, the requirements are applicable for up to 10.24s eDRX cycle, larger than 10.24s eDRX cycle cannot be applied for (e)RedCap UE with FR1-NTN.

Agreement:

For the relaxed criteria,

- Only ‘low mobility’ and ‘not at cell edge’ relaxation criteria defined for R17 NR NTN relaxations in GSO (corresponding to the TN R16 relaxation) will be supported from RAN4 requirement perspective.

For the thresholds of relaxation criterion,

- Existing thresholds defined for relaxed measurement in R17 NTN are re-used, and threshold value is up to network configuration.

Agreement: For the relaxation factor K,

- Reuse the parameters used in R17 NR NTN relaxations in GSO (corresponding to the TN R16 relaxation), which is 3 for UE only fulfill one of the relaxation criterion, and no requirement when both relaxation criterion are fulfilled for up to 1 hour.

Agreement:

- RAN4 to define measurement requirements in cell re-selection for inter-RAT (NTN to E-UTRAN TN) measurement in IDLE/INACITVE mode for (e)RedCap UE with FR1-NTN.

Agreement:

- Use new sections and section number with new suffix X in the specification to capture requirements for (e)RedCap UE with FR1-NTN bands.

- Utilize the reference method for the requirements that can be reused. FFS details.

Agreement:

- In RRC re-establishment requirements, update is needed to the TSMTC,i value for case where the SMTC for the inter-frequency carrier is not provided.

Approved documents

- R4-2502684	Ad-hoc minutes for NR_NTN_Ph3 WI, Qualcomm, CATT

- R4-2502604	WF on RRM requirements for NR_NTN_Ph3_Part1, CATT

- R4-2502605	WF on RRM requirements for NR_NTN_Ph3_Part2, Qualcomm

#### 2.4.2	Remaining Open issues

Definition of RF and RRM requirements enabling

- NR-NTN downlink coverage enhancement covering both GSO and NGSO constellations operating in FR1-NTN or FR2-NTN

- NR-NTN uplink capacity/throughput enhancement

- Support of regenerative payload

- Support of Rel-17 RedCap and Rel-18 eRedCap UEs with NR NTN operating in FR1-NTN bands

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SA2

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention. 
-

## 4.	References

## 4.1	RAN1

RAN1#120 meeting, Athens, February 17-21st, 2025:

- R1-2501550	other	Session notes for 9.11 (Non-Terrestrial Networks for NR Phase 3 and Internet of Things Phase 3)	Ad-Hoc Chair (Huawei)

- R1-2501608	LS out	Draft Reply LS on Ku band numerology	Eutelsat Group

- R1-2501609	LS out	Reply LS on Ku band numerology	RAN1, Eutelsat Group

- R1-2500523	Work Plan	Work plan WID: introduction of IoT-NTN TDD mode	Iridium Satellite LLC

- R1-2500043	Work Plan	Work plan for Rel-19 NR_NTN_Ph3	THALES

- R1-2500039	discussion	FL Summary #1: NR-NTN downlink coverage enhancements	THALES

- R1-2500040	discussion	FL Summary #2: NR-NTN downlink coverage enhancements	THALES

- R1-2500041	discussion	FL Summary #3: NR-NTN downlink coverage enhancements	THALES

- R1-2500042	discussion	FL Summary #4: NR-NTN downlink coverage enhancements	THALES

- R1-2500037	discussion	NR NTN Downlink coverage enhancements	THALES

- R1-2500182	discussion	Discussion on NR-NTN downlink coverage enhancement	Spreadtrum, UNISOC

- R1-2500082	discussion	Discussion on downlink coverage enhancements for NR NTN	Huawei, HiSilicon

- R1-2500109	discussion	Discussions on downlink coverage enhancement for NR NTN	Fraunhofer IIS, Fraunhofer HHI

- R1-2500301	discussion	Discussion on NR-NTN DL coverage enhancement	CMCC

- R1-2500268	discussion	Discussion on NR NTN downlink coverage enhancement	China Telecom

- R1-2500207	discussion	Discussion on downlink coverage enhancement for NR NTN	CATT

- R1-2500519	discussion	Discussion on downlink coverage enhancement for NR NTN	Baicells

- R1-2500501	discussion	NR-NTN downlink coverage enhancement	InterDigital, Inc.

- R1-2500607	discussion	NR-NTN downlink coverage enhancement	NEC

- R1-2500632	discussion	Discussion on downlink coverage enhancements	Fujitsu

- R1-2500443	discussion	Discussion on NR-NTN downlink coverage enhancement	OPPO

- R1-2500366	discussion	Discussion on NR-NTN downlink coverage enhancement	vivo

- R1-2500382	discussion	Discussion on DL coverage enhancement for NR NTN	ZTE Corporation, Sanechips

- R1-2500993	discussion	Discussions on downlink coverage enhancements	Nokia, Nokia Shanghai Bell

- R1-2501029	discussion	NR-NTN downlink coverage enhancement	MediaTek Inc.

- R1-2500983	discussion	Discussion on NR-NTN downlink coverage enhancement	TCL

- R1-2501280	discussion	Discussion on Downlink Coverage Enhancements for NR NTN	CEWiT

- R1-2501229	discussion	Downlink Coverage Enhancement for NR NTN	Google Korea LLC

- R1-2501216	discussion	Discussion on DL coverage enhancement for NR-NTN	NTT DOCOMO, INC.

- R1-2501114	discussion	Discussion on NR-NTN downlink coverage enhancement	HONOR

- R1-2501122	discussion	Discussion on downlink coverage enhancement for NR-NTN	CSCN

- R1-2500800	discussion	NR-NTN Downlink Coverage Enhancement	Apple

- R1-2500716	discussion	Discussion on NR-NTN downlink coverage enhancement	Xiaomi

- R1-2500672	discussion	On NR-NTN downlink coverage enhancement	Ericsson

- R1-2500866	discussion	Discussion on downlink coverage enhancement for NR-NTN	Samsung

- R1-2500919	discussion	Discussion on NR-NTN downlink coverage enhancement	ETRI

- R1-2500878	discussion	Discussion on downlink coverage enhancements for NR NTN	CCU

- R1-2500887	discussion	Discussion on downlink coverage enhancement for NR NTN	Lenovo

- R1-2501173	discussion	Downlink coverage enhancement for NR NTN	Qualcomm Incorporated

- R1-2500924	discussion	NR-NTN Downlink Coverage Enhancement	Panasonic

- R1-2501099	discussion	Discussion on DL coverage enhancements for NR-NTN	NICT

- R1-2501040	discussion	Discussion on NR-NTN downlink coverage enhancement	LG Electronics

- R1-2501041	discussion	Discussion on support of (e)RedCap UEs with NR-NTN operating in FR1-NTN bands	LG Electronics

- R1-2501062	discussion	Support of (e)RedCap UEs with NR NTN	Sharp

- R1-2501465	discussion	Summary #1 for Support of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands	Moderator (CATT)

- R1-2501466	discussion	Summary #2 for Support of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands	Moderator (CATT)

- R1-2501467	discussion	Summary #3 for Support of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands	Moderator (CATT)

- R1-2501605	discussion	Final Summary for Support of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands	Moderator (CATT)

- R1-2501174	discussion	Support of Redcap and eRedcap UEs in NR NTN	Qualcomm Incorporated

- R1-2500893	discussion	Discussion on support of RedCap/eRedCap UEs in NTN	CAICT

- R1-2500920	discussion	Discussion on HD UEs with NR NTN	ETRI

- R1-2500867	discussion	Discussion on support of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands	Samsung

- R1-2500673	discussion	On HD-FDD Redcap UEs for NTN	Ericsson

- R1-2500717	discussion	Discussion on the support of Redcap and eRedcap UEs in NR NTN	Xiaomi

- R1-2500805	discussion	Discussion on support of RedCap UEs with NR NTN operation	Apple

- R1-2501115	discussion	Discussion on support of (e)RedCap UEs in NR NTN	HONOR

- R1-2501217	discussion	Discussion on support of RedCap and eRedCap UEs in FR1-NTN	NTT DOCOMO, INC.

- R1-2501261	discussion	Support of RedCap and eRedCap UEs in NR NTN	Nordic Semiconductor ASA

- R1-2500984	discussion	Discussion on HD-FDD Redcap UEs and eRedcap UEs for FR1-NTN	TCL

- R1-2501030	discussion	Support of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands	MediaTek Inc.

- R1-2500994	discussion	Discussion of support for RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands	Nokia, Nokia Shanghai Bell

- R1-2500383	discussion	Discussion on support of RedCap/eRedCap UEs for NR NTN	ZTE Corporation, Sanechips

- R1-2500367	discussion	Discussion on support of RedCap and eRedCap UEs with NR-NTN	vivo

- R1-2500444	discussion	Discussion on supporting of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands	OPPO

- R1-2500502	discussion	Discussion on half-duplex RedCap issues for NTN FR1 operation	InterDigital, Inc.

- R1-2500208	discussion	Discussion on the enhancement of RedCap and eRedCap UEs In NTN	CATT

- R1-2500269	discussion	Discussion on Support of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands	China Telecom

- R1-2500302	discussion	Discussion on the collision issues of HD-FDD Redcap UE in FR1-NTN	CMCC

- R1-2500083	discussion	Discussion on HD-FDD RedCap UEs and eRedCap UEs for FR1-NTN	Huawei, HiSilicon

- R1-2500183	discussion	Discussion on support of RedCap and eRedCap UEs with NR NTN operating in FR1-NTN bands	Spreadtrum, UNISOC

- R1-2500184	discussion	Discussion on NR-NTN uplink capacity/throughput enhancement	Spreadtrum, UNISOC

- R1-2500084	discussion	Discussion on uplink capacity/throughput enhancement for FR1-NTN	Huawei, HiSilicon

- R1-2500303	discussion	Discussion on the NR-NTN uplink capacity/throughput enhancements	CMCC

- R1-2500270	discussion	Discussion on NR-NTN uplink enhancement	China Telecom

- R1-2500209	discussion	Discussion on UL capacity enhancement for NR NTN	CATT

- R1-2500503	discussion	NR-NTN uplink capacity/throughput enhancement	InterDigital, Inc.

- R1-2500633	discussion	Discussion on uplink capacity/cell throughput enhancement for FR1-NTN	Fujitsu

- R1-2500608	discussion	NR-NTN uplink capacity/throughput enhancement	NEC

- R1-2500445	discussion	Discussion on NR-NTN uplink capacity/throughput enhancement	OPPO

- R1-2500368	discussion	Discussion on NR-NTN uplink capacity enhancement	vivo

- R1-2500384	discussion	Discussion on UL capacity enhancement for NR NTN	ZTE Corporation, Sanechips

- R1-2500995	discussion	Discussion of NR-NTN uplink capacity enhancements	Nokia, Nokia Shanghai Bell

- R1-2501031	discussion	NR-NTN uplink capacity and throughput enhancements	MediaTek Inc.

- R1-2500987	discussion	On uplink capacity/cell throughput enhancement for NR NTN	Ericsson

- R1-2500980	discussion	Discussion on the NR-NTN uplink capacity/throughput enhancements	TCL

- R1-2501218	discussion	Discussion on NR-NTN uplink capacity/throughput enhancement	NTT DOCOMO, INC.

- R1-2501116	discussion	Discussion on NR-NTN UL capacity/throughput enhancement	HONOR

- R1-2501090	discussion	Discussion on NR-NTN uplink capacity/throughput enhancement	Hyundai Motor Company

- R1-2500801	discussion	NR-NTN Uplink Capacity Enhancement	Apple

- R1-2500718	discussion	Discussion on NR-NTN PUSCH capacity enhancement	Xiaomi

- R1-2500868	discussion	Discussion on uplink capacity/throughput enhancement for NR-NTN	Samsung

- R1-2500921	discussion	Discussion on NR-NTN uplink capacity/throughput enhancement	ETRI

- R1-2501175	discussion	NR-NTN uplink capacity / throughput enhancement	Qualcomm Incorporated

- R1-2500890	discussion	Uplink capacity/throughput enhancement for NR-NTN	Panasonic

- R1-2501051	discussion	Discussion on NR-NTN uplink capacity/throughput enhancement	Lenovo

- R1-2501042	discussion	Discussion on NR-NTN uplink capacity/throughput enhancement	LG Electronics

- R1-2501400	discussion	Feature lead summary #1 of AI 9.11.3 on NR-NTN uplink capacity and throughput enhancements	Moderator (MediaTek)

- R1-2501401	discussion	Feature lead summary #2 of AI 9.11.3 on NR-NTN uplink capacity and throughput enhancements	Moderator (MediaTek)

- R1-2501402	discussion	Feature lead summary #3 of AI 9.11.3 on NR-NTN uplink capacity and throughput enhancements	Moderator (MediaTek)

- R1-2501074	discussion	IoT NTN OCC methods and signaling for NPUSCH and NPRACH	Sharp

- R1-2501043	discussion	Discussion on IoT-NTN uplink capacity/throughput enhancement	LG Electronics

- R1-2501481	discussion	Moderator Summary for response to LS on PWS Support for NB-IoT NTN UEs	Moderator (InterDigital, Inc.)

- R1-2501517	LS out	Draft reply LS on PWS support in RRC_CONNECTED for NB-IoT NTN	Moderator (InterDigital)

- R1-2501555	discussion	Moderator Summary#2 for response to LS on PWS Support for NB-IoT NTN UEs	Moderator (InterDigital, Inc.)

- R1-2501621	LS out	[Draft] LS on TDM DMRS for 3.75kHz SCS OCC	Moderator (Sony)

- R1-2501518	LS out	Draft reply LS on PWS support in RRC_CONNECTED for NB-IoT NTN	Moderator (InterDigital)

- R1-2501612	LS out	Draft reply LS on PWS support in RRC_CONNECTED for NB-IoT NTN	Moderator (InterDigital)

- R1-2501613	LS out	Reply LS on PWS support in RRC_CONNECTED for NB-IoT NTN	RAN1, InterDigital

- R1-2501622	LS out	LS on TDM DMRS for 3.75kHz SCS OCC	RAN1, Sony

- R1-2501176	discussion	IOT-NTN uplink capacity/throughput enhancement	Qualcomm Incorporated

- R1-2500922	discussion	Discussion on uplink capacity/throughput enhancement for IoT NTN	ETRI

- R1-2500888	discussion	Discussion on uplink capacity enhancement for IoT NTN	Lenovo

- R1-2500869	discussion	Discussion on uplink capacity/throughput enhancement for IoT-NTN	Samsung

- R1-2500719	discussion	Discussion on IoT-NTN uplink capacity enhancement	Xiaomi

- R1-2500674	discussion	On uplink capacity enhancements for IoT-NTN	Ericsson

- R1-2500806	discussion	Discussion on IoT-NTN Uplink Capacity Enhancement	Apple

- R1-2501260	discussion	IoT-NTN uplink capacity/throughput enhancement	Nordic Semiconductor ASA

- R1-2500981	discussion	Discussion on the IoT-NTN uplink capacity/throughput enhancements	TCL

- R1-2501032	discussion	IoT-NTN uplink capacity and throughput enhancement	MediaTek Inc.

- R1-2500385	discussion	Discussion on UL capacity enhancement for IoT NTN	ZTE Corporation, Sanechips

- R1-2500369	discussion	Discussion on IoT-NTN uplink capacity enhancement	vivo

- R1-2500446	discussion	Discussion on IoT-NTN uplink capacity/throughput enhancement	OPPO

- R1-2500609	discussion	IoT-NTN uplink capacity/throughput enhancement	NEC

- R1-2500664	discussion	On IoT-NTN uplink capacity enhancements	Sony

- R1-2500665	discussion	FL Summary #1 for IoT-NTN	Moderator (Sony)

- R1-2500666	discussion	FL Summary #2 for IoT-NTN	Moderator (Sony)

- R1-2500667	discussion	Final FL Summary for IoT-NTN	Moderator (Sony)

- R1-2500504	discussion	IoT-NTN uplink capacity/throughput enhancement	InterDigital, Inc.

- R1-2500508	discussion	IoT-NTN uplink capacity enhancement	Nokia, Nokia Shanghai Bell

- R1-2500210	discussion	Discussion on UL capacity enhancement for IoT NTN	CATT

- R1-2500304	discussion	Discussion on the IoT-NTN uplink capacity/throughput enhancements	CMCC

- R1-2500085	discussion	Discussion on UL capacity enhancements for IoT NTN	Huawei, HiSilicon

- R1-2500185	discussion	Discussion on IoT-NTN uplink capacity/throughput enhancement	Spreadtrum, UNISOC

- R1-2500186	discussion	Discussion on IoT-NTN TDD mode	Spreadtrum, UNISOC

- R1-2500086	discussion	Discussion on IoT-NTN TDD mode	Huawei, HiSilicon

- R1-2500038	discussion	Discussion on IoT-NTN TDD mode	THALES

- R1-2500305	discussion	Discussion on the new NB-IoT NTN TDD mode	CMCC

- R1-2500211	discussion	Physical layer design on IoT-NTN TDD mode	CATT

- R1-2500509	discussion	Discussion on IoT-NTN TDD mode	Nokia, Nokia Shanghai Bell

- R1-2500524	discussion	loT-NTN TDD mode scheduling, timing and channel decoding performance	Iridium Satellite LLC

- R1-2500447	discussion	Discussion on IoT-NTN TDD mode	OPPO

- R1-2500370	discussion	Discussion on IoT-NTN TDD mode	vivo

- R1-2500386	discussion	Discussion on the IoT-NTN TDD mode	ZTE Corporation, Sanechips

- R1-2500982	discussion	Discussion on the IoT-NTN TDD mode	TCL

- R1-2501295	other	On R19 TDD IoT-NTN	Nordic Semiconductor ASA

- R1-2501219	discussion	Discussion on IoT-NTN TDD mode	NTT DOCOMO, INC.

- R1-2500807	discussion	Discussion on IoT-NTN TDD mode	Apple

- R1-2500720	discussion	Discussion on IoT-NTN TDD mode	Xiaomi

- R1-2500870	discussion	Discussion on IoT-NTN TDD mode	Samsung

- R1-2500889	discussion	Discussion on IoT-NTN TDD mode	Lenovo

- R1-2501177	discussion	IOT-NTN TDD mode	Qualcomm Incorporated

- R1-2501614	discussion	Feature lead summary #3 on IoT-NTN TDD mode	Moderator (Qualcomm Incorporated)

- R1-2501044	discussion	Discussion on IoT-NTN TDD mode	LG Electronics

- R1-2501075	discussion	IoT NTN TDD frame structure and synchronization signal mapping	Sharp

- R1-2501366	discussion	Feature lead summary #1 on IoT-NTN TDD mode	Moderator (Qualcomm Incorporated)

- R1-2501367	discussion	Feature lead summary #2 on IoT-NTN TDD mode	Moderator (Qualcomm Incorporated)

## 4.2	RAN2

RAN2#129 meeting, Athens, February 17-21st, 2025:

- R2-2501304	draftCR	Running RRC CR for NR NTN phase 3	Ericsson

- R2-2501321	draftCR	Introduction of NTN Ph3 enhancements	THALES (Rapporteur)

- R2-2501284	CR	Introduction of stage 2 for LTE TN to NR NTN idle mode mobility	Samsung

- R2-2500529	CR	Introduction of LTE TN to NR NTN IDLE mode mobility	CATT

- R2-2500705	CR	Introduction of LTE TN to NR NTN Mobility UE Capability	vivo

- R2-2500703	discussion	Discussion on simultaneous operation between GNSS and NR NTN	Huawei, HiSilicon, Turkcell

- R2-2500584	discussion	Discussion on simultaneous GNSS and NTN operations	Apple

- R2-2500067	LS in	Reply LS on Supporting MBS broadcast service for NR NTN (S2-2501329; contact: Xiaomi)	SA2

- R2-2500045	LS in	Reply LS on requirements for ETWS primary notification (S1-244857; contact: Novamint)	SA1

- R2-2500100	discussion	Discussion on DL coverage enhancement	Xiaomi

- R2-2500219	discussion	Discussion on Downlink Coverage Enhancement	Samsung

- R2-2500582	discussion	DL coverage enhancement in NTN	Apple

- R2-2500575	discussion	Further discussion of NR NTN coverage enhancement	China Telecom

- R2-2500656	discussion	Discussion on downlink coverage enhancement	HONOR

- R2-2500615	discussion	Cell barring and reselection for NTN DL-CE	Lenovo

- R2-2500148	discussion	Discussion on downlink coverage enhancement	LG Electronics Inc.

- R2-2500459	discussion	Discussion on DL coverage enhancement for NTN	OPPO

- R2-2500532	discussion	Default extended SSB periodicity	Qualcomm Incorporated

- R2-2500749	discussion	SMTC impacts due to NTN downlink coverage enhancements	Sony

- R2-2500685	discussion	Downlink coverage enhancement	NEC

- R2-2500689	discussion	Discussion on DL coverage enhancements	Huawei, HiSilicon, Turkcell

- R2-2500524	discussion	Further discussion on downlink coverage enhancements	CATT

- R2-2500483	discussion	Discussions on downlink coverage enhancement	Fujitsu

- R2-2500727	discussion	Discussion on NTN downlink coverage enhancement	Nokia

- R2-2501010	discussion	Discussion on SMTC for NTN DL coverage enhancements	ITRI

- R2-2501037	discussion	Analysis on DL coverage enhancements due to extended SIB periodicity	CMCC

- R2-2501179	discussion	Downlink coverage enhancement for non-terrestrial networks	InterDigital Communications

- R2-2501182	discussion	Discussion on Downlink Coverage Enhancements	Sharp

- R2-2501290	discussion	Downlink coverage enhancement SMTC impacts	Sequans Communications

- R2-2501291	discussion	Downlink coverage enhancement access control	Sequans Communications

- R2-2501160	discussion	Discussion on Downlink Coverage Enhancements	CSCN

- R2-2501318	discussion	DL coverage enhancements	Ericsson

- R2-2501280	discussion	Discussion on NR NTN Downlink Coverage Enhancements	Rakuten Mobile, Inc

- R2-2501281	discussion	RAN2 related proposals for Uplink Capacity & Throughput Enhancements	Rakuten Mobile, Inc

- R2-2501032	discussion	Discussion on uplink capacity/throughput enhancement for NR NTN	CMCC

- R2-2500690	discussion	Discussion on Uplink Capacity Enhancements	Huawei, HiSilicon, Turkcell

- R2-2500770	discussion	Consideration on DL CE and UL capacity enhancement	ZTE Corporation, Sanechips

- R2-2500665	discussion	UL Capacity enhancement for NRNTN	NEC Corporation

- R2-2500675	discussion	Remaining issues on the support of broadcast service in NTN	ETRI

- R2-2500616	discussion	Further considerations on broadcast service area information in NTN	Lenovo

- R2-2500657	discussion	Discussion on the support of broadcast service	HONOR

- R2-2500576	discussion	The mapping between service area information and MBS session	China Telecom

- R2-2500583	discussion	Discussion on broadcast serivce over NTN	Apple

- R2-2500465	discussion	Discussion on the support of broadcast service	Xiaomi

- R2-2500530	discussion	Signaling of MBS broadcast service area information	Qualcomm Incorporated

- R2-2500453	discussion	Discussion on providing MBS service area in NTN network	OPPO

- R2-2500331	discussion	Further Details on MBS in Rel-19 NR NTN	Nokia, Nokia Shanghai Bell

- R2-2500220	discussion	Discussion on Broadcast Service Area	Samsung

- R2-2500252	discussion	Discussion on Support of MBS Broadcast Service	TCL

- R2-2500079	discussion	Further Discussion on MBS Broadcast Service Area Provision in NTN	vivo

- R2-2500080	discussion	Discussion on MBS Broadcast Service Continuity in NTN	vivo

- R2-2500771	discussion	Consideration on broadcast service support	ZTE Corporation, Sanechips

- R2-2500484	discussion	Discussions on supporting broadcast service	Fujitsu

- R2-2500523	discussion	Further discussion on support of broadcast service in NR NTN	CATT

- R2-2501033	discussion	Considerations on broadcast service for NR NTN	CMCC

- R2-2501005	discussion	Discussion on MII procedure in NTN	LG Electronics France

- R2-2500966	discussion	Discussion on MBS broadcast over NTN	Huawei, HiSilicon, Turkcell

- R2-2501180	discussion	Support for broadcast service in non-terrestrial networks	InterDigital Communications

- R2-2501181	discussion	Remaining issues on intended service area	Sharp

- R2-2501306	discussion	Support for broadcast services in NR NTN	Ericsson

- R2-2501097	discussion	Discussion on the impact of regenerative payload	ETRI

- R2-2501066	discussion	Discussion on regenerative payload	Fujitsu Limited

- R2-2500904	discussion	Regenerative payload for NTN for NR Ph3	TOYOTA Info Technology Center

- R2-2500750	discussion	Satellite switch with re-sync in regenerative payload	Sony

- R2-2500617	discussion	UE location verification in NTN regenerative architecture	Lenovo

## 4.3	RAN3

RAN3#127 meeting, Athens, February 17-21st, 2025:

- R3-250052	CR	(BL CR to 38.410) Introduce NG Removal procedure	CMCC, Huawei, Nokia, Nokia Shanghai Bell, CATT, Ericsson, Qualcomm, Xiaomi, LG Electronics, China Telecom, Samsung, ZTE, NEC, ETRI

- R3-250053	draftCR	(BL CR to 38.300) Support for Regenerative Payload and MBS broadcast in NR NTN	Ericsson, Thales, Deutsche Telekom, Nokia, ESA, CATT, ZTE, Sateliot, Huawei, Dish Networks, Echostar, Eutelsat Group, Xiaomi, Samsung, CMCC, LG Electronics, NEC, Lenovo, ETRI

- R3-250054	CR	Support for Regenerative Payload and MBS broadcast in NR NTN	CATT, Thales, Nokia, Nokia Shanghai Bell, Ericsson, Huawei, ZTE, Qualcomm, Samsung, Xiaomi, CMCC, China Telecom, Jio, LG Electronics, NEC, ETRI, SES, ESA

- R3-250011	LS in	Reply LS on supporting MBS broadcast service for NR NTN	RAN2(Xiaomi)

- R3-250072	LS in	Reply LS on Supporting MBS broadcast service for NR NTN	SA2(Xiaomi)

- R3-250134	discussion	Discussion on Support of MBS Broadcast Service	TCL

- R3-250151	other	(TP for TS 38.413) Support of broadcast service	Xiaomi

- R3-250106	other	(TP to BL CR for TS38.413) Support of MBS broadcast service for NR NTN	CATT

- R3-250309	other	Intended Service Area for MBS Broadcast	Ericsson, Thales, Jio Platforms Limited, Intelsat

- R3-250334	other	Support of MBS broadcast service for NTN	China Telecom

- R3-250221	other	(TP to BL CR for TS 38.300 and TS 38.413) Update on the support of MBS Broadcast Service	Nokia, Nokia Shanghai Bell

- R3-250181	discussion	(TP for TS 38.300 and TS 38.413) Discussion on NR NTN supporting MBS broadcast service	NEC

- R3-250675	other	(TP to 38.300) Discussion on Supporting MBS broadcast service for NR NTN	CMCC

- R3-250400	other	(TP for TS 38.300 and TS 38.413) Support MBS broadcast service	Huawei, Qualcomm Incorporated

- R3-250501	other	(TPs to BL CR 38.300 and 38.413) Discussion on NTN broadcast service supporting	ZTE Corporation

- R3-250633	discussion	Further discussion on support broadcast service for NR NTN	Samsung

- R3-250634	discussion	Further discussion on support of regenerative payload for NR NTN	Samsung

- R3-250502	other	(TPs to BL CR 38.410 and 38.413) Discussion on support of regenerative payload	ZTE Corporation

- R3-250310	discussion	Considerations on NG Interface Management over the Feeder Link	Ericsson, Thales, Huawei, Jio Platforms Limited, Intelsat, ESA

- R3-250311	discussion	Making the Case for Location-Based CHO in Rel-19	Ericsson, Thales, ESA, Inmarsat, Viasat, Jio Platforms Limited, Intelsat

- R3-250312	other	Location-Based CHO in Rel-19 - XnAP Impacts	Ericsson, Thales, ESA, Inmarsat, Viasat, Jio Platforms Limited, Intelsat

- R3-250401	other	(TP for TS 38.300) Support of regenerative payload	Huawei, Ericsson

- R3-250402	LS out	[draft] Reply LS on OAM requirements to support regenerative payload	Huawei

- R3-250313	discussion	Additional Background on OAM Requirements and Regenerative Payload	Ericsson

- R3-250314	discussion	Inactive UEs and NR NTN	Ericsson

- R3-250681	discussion	Discussion on Support of regenerative payload for NR NTN	CMCC

- R3-250648	discussion	Discussions on INACTIVE support from moving satellite gNBs	LG Electronics Inc.

- R3-250649	other	(TP for NR_NTN_Ph3 TS 38.300 BL CR) OAM for NG management	LG Electronics Inc.

- R3-250650	discussion	Discussion on support of regenerative payload for NR NTN	CSCN

- R3-250582	discussion	NG Interface Management with NGAP Removal	Jio Platforms JPL

- R3-250583	discussion	Discussion on Support of Inactive UE in NTN	ETRI, Ajou University

- R3-250182	discussion	(TP for TS 38.300) Discussion on regenerative payload enhancement for NR NTN	NEC

- R3-250222	other	(TP to BL CR for TS 38.300) Discussion on the support of Regenerative payload	Nokia, Nokia Shanghai Bell

- R3-250240	discussion	Discussion on Reply LS on OAM requirements to support Regenerative payload	Qualcomm Incorporated, Vodafone Group Plc, Vodafone Telekomünikasyon A.S.

- R3-250241	other	(TP for TS 38.300) Discussion on NR NTN Regenerative Payload	Qualcomm Incorporated, Nokia, Nokia Shanghai Bell, Xiaomi

- R3-250335	other	Discussion on regenerative payload enhancement	China Telecom

- R3-250350	discussion	Discussion on regenerative NTN payload enhancement	China Telecom

- R3-250351	other	(TP for TS 38.300) Support of regenerative payload	China Telecom

- R3-250308	other	(TP for TS 38.300 BL CR) Stage 2 Corrections	Ericsson, Huawei, Nokia, Nokia Shanghai Bell, Thales, CATT, Qualcomm Incorporated, LG Electronics

- R3-250107	other	(TP to NTN BL CRs) Support of regenerative payload	CATT

- R3-250152	discussion	Support of Inactive UE mobility in NTN	Xiaomi, Qualcomm Incorporated, Nokia, Nokia Shanghai Bell

- R3-250153	other	(TP for TS 38.300) Support of regenerative payload	Xiaomi

- R3-250133	discussion	Discussion on Support of NTN Regenerative Architecture	TCL

- R3-250030	LS in	LS reply on OAM requirements to support regenerative payload	SA5(CATT)

- R3-250023	LS in	LS on reply to LS on OAM requirements to support regenerative payload	SA2(Huawei)

- R3-250870	(TPs to BL CR 38.300 and 38.413) Discussion on NTN broadcast service supporting ZTE Corporation, Nokia, Nokia Shanghai Bell, Huawei, Qualcomm, CATT

- R3-250893	(TP for TS 38.300 and TS 38.413) Support MBS broadcast service Huawei, Nokia, Nokia Shanghai Bell, Qualcomm Incorporated,  Ericsson, Xiaomi, ZTE, CATT

- R3-250308	(TP for TS 38.300 BL CR) Stage 2 Corrections Ericsson, Huawei, Nokia, Nokia Shanghai Bell, Thales, CATT, Qualcomm Incorporated, LG Electronics

- R3-250895	Reply LS to SA2 and SA5 on OAM requirements to support regenerative payload transport links   To: SA2, SA5 (CATT)

## 4.4	RAN4

RAN4#114 meeting, Athens, February 17-21st, 2025:

- R4-2500414	draftCR	Draft CR to TS 38.108: Introduction of regenerative payload	NEC, THALES

- R4-2502283	draftCR	Draft CR to TS 38.108: Introduction of regenerative payload	NEC, THALES

- R4-2500319	other	On NTN RedCap UE HD-FDD REFSENS	Apple

- R4-2501003	other	Discussion on RF requirements for NTN RedCap UE	CATT

- R4-2501080	discussion	Disscussion on NTN (e)Redcap UE RF requirements	Spreadtrum,UNISOC

- R4-2501158	discussion	REFSENS for NTN Redcap and eRedcap	Sony

- R4-2502103	other	RedCap UE RF impact on HD-FDD	Ericsson

- R4-2502013	other	NR NTN RedCap UE RF requirements	Qualcomm Inc.

- R4-2501727	discussion	Discussion on Rel-19 NR-NTN RedCap UE RF requirements	MediaTek (Hefei) Inc.

- R4-2501322	discussion	Views on increasing MOP tolerance for NTN HD-FDD Redcap	NTT DOCOMO INC.

- R4-2501382	other	RedCap NTN UEs	Nokia

- R4-2501477	discussion	Discussion on RedCap UE RF requirements with NR NTN operating in FR1-NTN bands	OPPO

- R4-2501450	other	Discussion on the remaining issues for NR NTN phase 3	Huawei, HiSilicon

- R4-2502012	other	NR NTN UL Capacity Enhancements	Qualcomm Inc.

- R4-2502104	other	Other NTN UE RF impact	Ericsson, Sony

- R4-2500086	draftCR	Draft CR to TS 38.108: Introduction of regenerative payload	NEC Europe Ltd

- R4-2500239	discussion	On R19 NTN (e)RedCap RRM requirements	Apple

- R4-2500390	discussion	Discussion on NTN (e)Redcap RRM requirements	MediaTek inc.

- R4-2501130	other	Discussion on (e)RedCap RRM requirements of R19 NR NTN	OPPO

- R4-2501174	other	Discussion on RRM requirements for RedCap NTN	ZTECorporation,Sanechips

- R4-2501023	discussion	Discussion on (e)RedCap RRM requirements for Rel-19 NTN phase3	CATT

- R4-2500852	discussion	Discussion on the RRM requirement for Redcap over NTN	CMCC

- R4-2500895	discussion	Discussion on RRM requirements for (e)RedCap in NTN	LG Electronics Inc.

- R4-2500631	discussion	Discussion on (e)RedCap RRM requirements in NTN for NR Phase 3	Xiaomi

- R4-2502225	discussion	(NR_NTN_Ph3-Core) RedCap for NTN	Qualcomm Incorporated

- R4-2501466	discussion	Discussion on RRM requirements of RedCap in Rel-19 NTN phase 3	Samsung

- R4-2501486	discussion	Discussing requirements for RedCap support in NR NTN	Nokia

- R4-2501342	discussion	Discussion on RRM requirements on (e)RedCap for R19 NR NTN Phase 3	vivo

- R4-2501287	discussion	Discussion on RedCap RRM requirements for NTN for NR Phase 3	Ericsson

- R4-2501269	discussion	Discussion on RRM requirements for RedCap UE in NTN	Huawei, HiSilicon

- R4-2501270	discussion	Discussion on other RRM requirements for Rel-19 NTN	Huawei, HiSilicon

- R4-2501288	discussion	Discussion on other RRM requirements for NTN for NR Phase 3	Ericsson

- R4-2501343	discussion	Discussion on RRM impacts on DL coverage for R19 NR NTN Phase 3	vivo

- R4-2501487	discussion	On the impact of extended SSB periodicity on the main NTN cell	Nokia

- R4-2501467	discussion	Discussion on RRM requirements of other aspects in Rel-19 NTN phase 3	Samsung

- R4-2502226	discussion	(NR_NTN_Ph3-Core) Downlink coverage enhancement for NTN	Qualcomm Incorporated

- R4-2500632	discussion	Discussion on other RRM core requirements in NTN for NR Phase 3	Xiaomi

- R4-2500898	discussion	Discussion on RRM requirements for downlink coverage enhancement in NTN	LG Electronics Inc.

- R4-2500853	discussion	Discussion on the RRM requirement for NTN phase3	CMCC

- R4-2501024	discussion	Discussion on other RRM requirements for Rel-19 NTN phase3	CATT

- R4-2501131	other	Discussion on other RRM requirements of R19 NR NTN	OPPO

- R4-2500391	discussion	Discussion on NTN RRM requirements for SSB periodicity up to 160ms	MediaTek inc.

- R4-2500240	discussion	On R19 other NTN RRM requirements	Apple

- R4-2500543	other	Topic summary for [114][229] NR_NTN_Ph3_Part1	Moderator (CATT)

- R4-2500544	other	Topic summary for [114][230] NR_NTN_Ph3_Part2	Moderator (Qualcomm)

- R4-2500570	other	Topic summary for [114][309] NR_NTN_Ph3_General_SAN_RF	Moderator (Thales)

- R4-2500571	other	Topic summary for [114][310] NR_NTN_Ph3_UE_RF	Moderator (Qualcomm)

- R4-2502604	other	WF on RRM requirements for NR_NTN_Ph3_Part1	CATT

- R4-2502605	other	WF on RRM requirements for NR_NTN_Ph3_Part2	Qualcomm

- R4-2502281	other	Way Forward for [114][310] NR_NTN_Ph3_UE_RF	Qualcomm

- R4-2502684	other	Ad-hoc minutes for [NR_NTN_Ph3-Core] WI	Qualcomm Incorporated, CATT

END