## Cover sheet
3GPP TSG-RAN WG5 meeting #108 | [5 empty] | R5-254370
Bengaluru, India, 25 – 29 August 2025
Agenda Item: | 7.5.2
Source: | Nokia
Title: | WP UE Conformance – NR support for dedicated spectrum less than 5MHz for FR1
Work item code: | NR_FR1_lessthan_5MHz_BW-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WI 'NR_FR1_lessthan_5MHz_BW’, by analyzing the test case impact, applicability and test environment, and updating the relevant conformance specifications. This work item will cover RF, Signaling, Demod and RRM conformance test specifications for NR_FR1_lessthan_5MHz_BW-UEConTest (1030060).
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 95% (+17%) | 0 | 11
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 94.9% | 0 | 11
FR1 |  | 95% | 0 | 11
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 0% |  |  | 0%
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100%
NR RF/RRM
FR1 RF common parts | 38.521-1 | 100% |  |  | 100%
FR1 RF Tx test cases | 38.521-1 Tx | 100% |  |  | 100%
FR1 RF Rx test cases | 38.521-1 Rx | 100% |  |  | 100%
RF Demod/QSI test cases | 38.521-4 | 100% | 0 | 2 | 100% | 0 | 2
RRM test cases | 38.533 | 90% | 0 | 9 | 90% | 0 | 9
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 100% |  |  | 100%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 90% |  |  | 90%
Test Point analysis receiver and transmitter test cases | 38.905 | 100% |  |  | 100%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 70% |  |  | 70%
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3 | 80% |  |  | 80%
5 References
[1] RP-240044 | New WID on UE Conformance – NR support for dedicated spectrum less than 5MHz for FR1
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – NR support for dedicated spectrum less than 5MHz for FR1 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_FR1_lessthan_5MHz_BW-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance – NR support for dedicated spectrum less than 5MHz for FR1 comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Siddharth Das, Nokia |  |  | siddharth.1.das@nokia.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
94.9% (+16.9%)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 4.4 | Update to parameters of E-UTRA cells | Update SIB for 3 MHz channel bandwidth | MTK, MCC TF160 | RAN5#109 (Nov-25) | R5-254995 |  | 0.1 | 70% (+70%) | 70% (+70%) |  | 70%
5GS
5GS Common
TS 38.508-1: Common test environment
2 |  | 38.508-1 | 4.3.1.0B | Low test channel bandwidth | Add 3MHz for impacted bands | Nokia | RAN5#104 (Aug-24) | R5-243601 R5-246270 |  | 0.1 | 100% | 100% |  | 100%
3 |  | 38.508-1 | 4.3.1.0D | Bandwidth part | Add 3MHz channel bandwidth | Nokia | RAN5#104 (Aug-24) | R5-243601 R5-244923 |  | 0.1 | 100% | 100% |  | 100%
4 |  | 38.508-1 | 4.3.1.1 | Test frequencies for NR operating bands in FR1 | Add 3MHz for impacted bands | Nokia, Keysight | RAN5#105 (Nov-24) | R5-243601 R5-251674 |  | 0.1 | 100% | 100% |  | 100%
5 |  | 38.508-1 | 6 | Test environments for SIG tests | Necessary changes to SIG test environments | MCC TF160, Nokia | RAN5#106 (Feb-25) | R5-251288 |  | 0.1 | 100% | 100% |  | 100%
TS 38.508-2: Common ICS
6 |  | 38.508-2 | A.4 | ICS proforma tables | Introduction of common implementation conformance statement (ICS) for less than 5 MHz channel BW | Nokia | RAN5#107 (May-25) | R5-244553 R5-254393 |  | 0.1 | 100% | 100% |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
7 |  | 38.521-1 | 5.3.2 | Maximum transmission bandwidth configuration | Add 3 MHz Maximum transmission bandwidth configuration | Nokia | RAN5#104 (Aug-24) | R5-243639 |  | 0.1 | 100% | 100% |  | 100%
8 |  | 38.521-1 | 5.3.3 | Minimum guard band and transmission bandwidth configuration | Add Minimum guardband for 3 MHz channel bandwidth | Nokia | RAN5#104 (Aug-24) | R5-243639 |  | 0.1 | 100% | 100% |  | 100%
9 |  | 38.521-1 | 5.3.5 | UE channel bandwidth per operating band | Add 3 MHz channel bandwidth and requirement for impacted bands | Nokia | RAN5#104 (Aug-24) | R5-243639 |  | 0.1 | 100% | 100% |  | 100%
10 |  | 38.521-1 | 5.4.3.1 | Synchronization raster and numbering | Add 3 MHz frequency raster parameters and additional GSCN parameters | Nokia | RAN5#104 (Aug-24) | R5-243639 |  | 0.1 | 100% | 100% |  | 100%
11 |  | 38.521-1 | 5.4.3.3 | Synchronization raster entries for each operating band | Add SS raster entries per operating band for 3 MHz channel bandwidth for impacted bands | Nokia | RAN5#104 (Aug-24) | R5-243639 |  | 0.1 | 100% | 100% |  | 100%
12 |  | 38.521-1 | A.3.2 | DL reference measurement channels for FDD | Add 3 MHz channel bandwidth into FRC for receiver requirements | Nokia | RAN5#104 (Aug-24) | R5-243639 |  | 0.1 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
13 |  | 38.521-1 Tx | 6.1 | General | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#105 (Nov-24) | R5-243637 |  | 0.1 | 100% | 100% |  | 100%
14 |  | 38.521-1 Tx | 6.2.2 | UE maximum output power reduction | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#105 (Nov-24) | R5-243637 |  | 0.1 | 100% | 100% |  | 100%
15 |  | 38.521-1 Tx | 6.2.3 | UE additional maximum output power reduction | Add 3 MHz channel bandwidth requirements for required NS values | Nokia | RAN5#105 (Nov-24) | R5-243637 |  | 0.1 | 100% | 100% |  | 100%
16 |  | 38.521-1 Tx | 6.3.1 | Minimum output power | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#105 (Nov-24) | R5-243637 |  | 0.1 | 100% | 100% |  | 100%
17 |  | 38.521-1 Tx | 6.3.2 | Transmit OFF power | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#105 (Nov-24) | R5-243637 |  | 0.1 | 100% | 100% |  | 100%
18 |  | 38.521-1 Tx | 6.5.1 | Occupied bandwidth | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#105 (Nov-24) | R5-243637 |  | 0.1 | 100% | 100% |  | 100%
19 |  | 38.521-1 Tx | 6.5.2 | Spectrum emission mask | Add 3 MHz channel bandwidth requirements for required NS values and ACLR | Nokia | RAN5#105 (Nov-24) | R5-243637 R5-244924 |  | 0.1 | 100% | 100% |  | 100%
20 |  | 38.521-1 Tx | 6.5.3.3 | Additional spurious emissions | Add 3 MHz channel bandwidth requirements for required NS values | Nokia | RAN5#105 (Nov-24) | R5-243637 R5-246270 |  | 0.1 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Rx
21 |  | 38.521-1 Rx | 7.3.2 | Reference sensitivity power level | Add 3 MHz channel bandwidth and requirement for impacted bands | Nokia | RAN5#106 (Feb-25) | R5-243638 |  | 0.1 | 100% | 100% |  | 100%
22 |  | 38.521-1 Rx | 7.4 | Maximum input level | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#106 (Feb-25) | R5-243638 |  | 0.1 | 100% | 100% |  | 100%
23 |  | 38.521-1 Rx | 7.5 | Adjacent channel selectivity | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#106 (Feb-25) | R5-243638 |  | 0.1 | 100% | 100% |  | 100%
24 |  | 38.521-1 Rx | 7.6.2 | In-band blocking | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#106 (Feb-25) | R5-243638 |  | 0.1 | 100% | 100% |  | 100%
25 |  | 38.521-1 Rx | 7.6.3 | Out-of-band blocking | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#106 (Feb-25) | R5-243638 |  | 0.1 | 100% | 100% |  | 100%
26 |  | 38.521-1 Rx | 7.6.4 | Narrow band blocking | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#106 (Feb-25) | R5-243638 |  | 0.1 | 100% | 100% |  | 100%
27 |  | 38.521-1 Rx | 7.7 | Spurious response | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#106 (Feb-25) | R5-243638 |  | 0.1 | 100% | 100% |  | 100%
28 |  | 38.521-1 Rx | 7.8.2 | Wide band Intermodulation | Add 3 MHz channel bandwidth requirement | Nokia | RAN5#106 (Feb-25) | R5-243638 |  | 0.1 | 100% | 100% |  | 100%
TS 38.521-4: Demod/CSI reporting test cases
|  | 38.521-4 | 5.3 | PDCCH demodulation requirements
|  | 38.521-4 | 5.3.2 | 2RX Requirements
|  | 38.521-4 | 5.3.2.1 | FDD
29 | Y | 38.521-4 | 5.3.2.1.7 | 2RX FDD FR1 PDCCH antenna performance for 3 MHz channel bandwidth | Add 3 MHz channel bandwidth requirement for 1Tx antenna configuration | Ericsson | RAN5#108 (Aug-25) | R5-250640 R5-252555 |  | 1 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.3.3 | 4RX Requirements
|  | 38.521-4 | 5.3.3.1 | FDD
30 | Y | 38.521-4 | 5.3.3.1.6 | 4RX FDD FR1 PDCCH antenna performance for 3 MHz channel bandwidth | Add 3 MHz channel bandwidth requirement for 2Tx antenna configuration | Ericsson | RAN5#108 (Aug-25) | R5-255411 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
31 |  | 38.521-4 | A.3 | DL reference measurement channels | Add Reference measurement channels for PDCCH performance requirements | Ericsson | RAN5#109 (Nov-25) | R5-252556 |  | 0.1 | 100% (+50%) | 100% (+50%) |  | 100%
32 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances | Capturing the MU/TT of performance test cases | Ericsson | RAN5#109 (Nov-25) | R5-250640 R5-254641 |  | 0.1 | 100% (+50%) | 100% (+50%) |  | 100%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
33 |  | 38.522 | 4 | Recommended test case applicability | Add required new ICS statements | All companies | RAN5#107 (May-25) | R5-245915 R5-246975 R5-254392 |  | 0.1 | 100% (+10%) | 100% (+10%) |  | 100%
34 |  | 38.522 | 4.1.1 | RF / FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-1 | Nokia | RAN5#107 (May-25) |  | No impact | 0.1 | 100% | 100% |  | 100%
35 |  | 38.522 | 4.1.4 | Performance conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-4 | Ericsson | RAN5#107 (May-25) | R5-250641 R5-252559 R5-254643 |  | 0.1 | 100% (+30%) | 100% (+30%) |  | 100%
36 |  | 38.522 | 4.2 | RRM conformance test cases | Add test case applicability statements for the new test cases introduced for 38.533 | All companies | RAN5#107 (May-25) | R5-245915 R5-246975 R5-240477 R5-250532 |  | 0.1 | 100% | 100% |  | 100%
TS 38.533: RRM test cases
|  |  | 6.1 | RRC_IDLE state mobility
|  |  | 6.1.1 | NR cell re-selection
37 | Y | 38.533 | 6.1.1.9 | NR SA FR1 cell re-selection for UE operating on a cell with less than 5MHz BW | 38.133 Requirements in Annex A.6.1.1.9 | Nokia | RAN5#108 (Aug-25) | R5-245882 R5-246976 |  | 1 | 100% | 100% |  | 100%
|  | 38.533 | 6.3 | RRC_CONNECTED state mobility
|  | 38.533 | 6.3.1 | Handover
38 | Y | 38.533 | 6.3.1.18 | NR SA FR1 Intra-frequency handover with unknown target cell for UE operating on a cell with less than 5 MHz BW | 38.133 Requirements in Annex A.6.3.1.18 | Nokia | RAN5#108 (Aug-25) | R5-244556 R5-247901 |  | 1 | 100% | 100% |  | 100%
|  | 38.533 | 6.5 | Signaling characteristics
|  | 38.533 | 6.5.1 | Radio link monitoring
39 | Y | 38.533 | 6.5.1.13 | NR SA FR1 radio link monitoring out-of-sync test for PCell configured with SSB-based RLM RS in DRX mode for UE operating on a cell with less than 5MHz BW | 38.133 Requirements in Annex A.6.5.1.13 | Nokia | RAN5#108 (Aug-25) | R5-244557 R5-251749 R5-253630 |  | 1 | 100% | 100% |  | 100%
40 | Y | 38.533 | 6.5.1.14 | NR SA FR1 radio link monitoring out-of-sync test for PCell configured with SSB-based RLM RS in non-DRX mode for UE operating on a cell with less than 5MHz BW | 38.133 Requirements in Annex A.6.5.1.14 | Nokia | RAN5#108 (Aug-25) | R5-244558 R5-251749 R5-253630 |  | 1 | 100% | 100% |  | 100%
41 | Y | 38.533 | 6.5.1.15 | NR SA FR1 radio link monitoring In-sync test for PCell configured with SSB-based RLM RS in non-DRX mode for UE operating on a cell with 3MHz BW | 38.133 Requirements in Annex A.6.5.1.15 | Nokia | RAN5#108 (Aug-25) | R5-253498 |  | 1 | 100% (+30%) | 100% (+30%) |  | 100%
42 | Y | 38.533 | 6.5.1.16 | NR SA FR1 radio link monitoring In-sync test for PCell configured with SSB-based RLM RS in DRX mode for UE operating on a cell with 3MHz BW | 38.133 Requirements in Annex A.6.5.1.16 | Nokia | RAN5#108 (Aug-25) | R5-251750 R5-251847 |  | 1 | 100% | 100% |  | 100%
|  | 38.533 | 6.5.5 | Link recovery procedures
43 | Y | 38.533 | 6.5.5.8 | NR SA FR1 SSB-based beam failure detection and link recovery test in non-DRX mode for a UE operating on a cell with 3 MHz BW | 38.133 Requirements in Annex A.6.5.5.8 | Nokia | RAN5#108 (Aug-25) | R5-254352 |  | 1 | 90% (+90%) | 90% (+90%) |  | 90%
|  | 38.533 | 6.6 | Measurement procedures
|  | 38.533 | 6.6.1 | Intra-frequency measurements
44 | Y | 38.533 | 6.6.1.12 | NR SA FR1 event triggered reporting with SSB index detection without measurement gap in non-DRX mode for UE operating with 12 PRB SSB bandwidth | 38.133 Requirements in Annex A.6.6.1.12 | MTK | RAN5#108 (Aug-25) | R5-251595 R5-251832 R5-251833 |  | 1 | 100% | 100% |  | 100%
|  | 38.533 | 6.6.2 | Inter-frequency measurements
45 | Y | 38.533 | 6.6.2.15 | NR SA FR1 event triggered reporting without SSB index detection in DRX mode for UE operating on a cell with less than 5MHz BW | 38.133 Requirements in Annex A.6.6.2.15 | MTK | RAN5#108 (Aug-25) | R5-250531 R5-251832 R5-251834 |  | 1 | 100% | 100% |  | 100%
46 |  | 38.533 | Annex A | RRM test configurations | Adding RRM test and RMC configuration parameters | Nokia | RAN5#108 (Aug-25) | R5-244559 R5-250480 |  | 0.1 | 100% | 100% |  | 100%
47 |  | 38.533 | Annex E | Cell configuration mapping | Define cell configuration mapping | Nokia, MTK | RAN5#109 (Nov-25) | R5-245882 R5-244556-58 R5-251749-50 R5-251595 R5-250531 R5-254352 |  | 0.1 | 100% (+10%) | 100% (+10%) |  | 100%
48 |  | 38.533 | Annex F | Measurement uncertainties and test tolerances | Define measurement uncertainties and test tolerances |  | RAN5#109 (Nov-25) | R5-246978 R5-251833 R5-251834 R5-253630 R5-254349 R5-254351 |  | 0.1 | 90% | 90% |  | 90%
49 |  | 38.533 | Annex H | Default message contents for RRM |  |  | RAN5#109 (Nov-25) |  | No impact | 0.1 | 100% | 100% |  | 100%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
50 |  | 38.903 | 7 | Grouping of test cases defined in TS 38.521-4 | Add TT analysis for FR1 Perf Test cases | Ericsson | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
51 |  | 38.903 | 8 | Grouping of test cases defined in TS 38.533 | Add TT analysis for FR1 RRM Test cases | Nokia, MTK | RAN5#109 (Nov-25) | R5-247902 R5-247903 R5-253631 R5-253632 R5-253558 R5-253559 R5-254350 |  | 0.1 | 90% (+10%) | 90% (+10%) |  | 90%
52 |  | 38.905 | 4.1 | Test point analysis for FR1 test cases in TS 38.521-1 |  |  | RAN5#107 (May-25) |  | No impact | 0.1 | 100% | 100% |  | 100%
RAN and CN protocol
TS 38.523-1: Protocol test cases
Idle Mode
53 |  | 38.523-1 | 6.1.2.4 | Cell selection for interband operation | Update SIB4 message content to include interFreqCarrierFreqList-v1800 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
54 |  | 38.523-1 | 6.1.2.5 | Cell selection for interband operation using Pcompensation/Between FDD and TDD | Update SIB4 message content to include interFreqCarrierFreqList-v1800 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
55 |  | 38.523-1 | 6.1.2.23 | Cell reselection/MFBI | Update SIB4 message content to include interFreqCarrierFreqList-v1800 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
56 |  | 38.523-1 | 6.2.2.1 | Inter-RAT cell selection / From NR RRC_IDLE to EUTRA_Idle / Serving cell becomes non-suitable | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
57 |  | 38.523-1 | 6.2.2.2 | Inter-RAT cell selection / From E-UTRA_Idle to NR RRC_IDLE / Serving cell becomes non-suitable | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
58 |  | 38.523-1 | 6.2.3.1 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE (lower priority & higher priority, Srxlev based) | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
59 |  | 38.523-1 | 6.2.3.2 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE (lower priority & higher priority, Squal based) | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
60 |  | 38.523-1 | 6.2.3.3 | Inter-RAT cell reselection / From NR RRC_IDLE to E-UTRA_IDLE (lower priority & higher priority, Srxlev based) | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
61 |  | 38.523-1 | 6.2.3.4 | Inter-RAT cell reselection / From NR RRC_Idle to E-UTRA_IDLE (lower priority & higher priority, Squal based) | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
62 |  | 38.523-1 | 6.2.3.5 | Inter-RAT cell reselection / From NR RRC_IDLE to E-UTRA_Idle according to RAT priority provided by dedicated signalling (RRCRelease) | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
63 |  | 38.523-1 | 6.2.3.6 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE according to RAT priority provided by dedicated signalling (RRConnRelease) | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
64 |  | 38.523-1 | 6.2.3.7 | Inter-RAT cell reselection / From NR RRC_IDLE to E-UTRA RRC_Idle, Snonintrasearch | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
65 |  | 38.523-1 | 6.2.3.8 | Inter-RAT cell reselection / From E-UTRA RRC_IDLE to NR RRC_Idle, Snonintrasearch | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
66 |  | 38.523-1 | 6.2.3.10 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE / schedulingInfoList-v12j0 | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
67 |  | 38.523-1 | 6.2.3.11 | Inter-RAT cell reselection / From E-UTRA_Idle to NR RRC_IDLE / schedulingInfoListExt-r12 | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
68 |  | 38.523-1 | 6.4.3.1 | Inter-RAT cell reselection / From NR RRC_INACTIVE to E-UTRA RRC_IDLE (lower priority & higher priority, Srxlev based) | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | MTK | RAN5#109 (Nov-25) | R5-254994 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
Layer2
69 |  | 38.523-1 | 7.1.1.1.9 | Random access procedure / Successful / 2-step RACH/C-RNTI Based / Preamble selected by MAC itself | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
70 |  | 38.523-1 | 7.1.1.3.2b | Logical channel prioritization handling with Mapping restrictions | Update the test case to include N_max nPRB=15 for 3 MHz | Keysight | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
71 |  | 38.523-1 | 7.1.1.3.4 | Correct handling of MAC control information / Buffer status / UL data arrive in the UE Tx buffer / Regular BSR | Update the test case to include N_max nPRB=15 for 3 MHz | Keysight | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
72 |  | 38.523-1 | 7.1.1.3.12 | Correct Handling of UL HARQ process / PUSCH Repetition Type B | Update the test case to include N_max nPRB=15 for 3 MHz | Keysight | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
73 |  | 38.523-1 | 7.1.1.3.17.1 | Correct Handling of UL HARQ process / PUSCH Repetition / Multi-TRP / PUSCH Repetition Type A / dynamic grant | Update the test case to include N_max nPRB=15 for 3 MHz | Keysight | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
74 |  | 38.523-1 | 7.1.1.3.17.2 | Correct Handling of UL HARQ process / PUSCH Repetition / Multi-TRP / PUSCH Repetition Type B / dynamic grant | Update the test case to include N_max nPRB=15 for 3 MHz | Keysight | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
75 |  | 38.523-1 | 7.1.1.3.18 | Correct handling of MAC control information / Buffer status / UL data arrive in the UE Tx buffer / Refined BSR | Update the test case to include N_max nPRB=15 for 3 MHz | Keysight | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
76 |  | 38.523-1 | 7.1.1.3.19 | Correct handling of MAC control information / Buffer Status / UL resources are allocated / Refined BSR / Padding BSR | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
77 |  | 38.523-1 | 7.1.1.4.2.1 | UL-SCH transport block size selection / DCI format 0_0 / Transform precoding disabled disabled | Update the test case to include N_max nPRB=15 for 3 MHz | Keysight | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
78 |  | 38.523-1 | 7.1.1.6.2 | Correct handling of UL grant / configured grant Type 1 | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | R5-254996 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
79 |  | 38.523-1 | 7.1.1.6.6 | Correct handling of UL grant / Multiple CG PUSCH occasions per CG period / Configured grant Type 1 | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | R5-254992 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
80 |  | 38.523-1 | 7.1.1.6.7 | Correct handling of UL grant / Multiple CG PUSCH occasions per CG period / Configured grant Type 2 | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
81 |  | 38.523-1 | 7.1.1.6.8 | Correct handling of UL grant / Unused transmission occasion / Configured grant type 1 | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | R5-254991 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
82 |  | 38.523-1 | 7.1.1.8.1 | Bandwidth Part (BWP) operation UL/DL | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | R5-254997 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
83 |  | 38.523-1 | 7.1.1.13.5 | RA Based SDT/ CG Based SDT/ cg-SDT-TimeAlignmentTimer | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
84 |  | 38.523-1 | 7.1.2.3.6 | AM RLC / Polling for status | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
85 |  | 38.523-1 | 7.1.2.3.7 | AM RLC / Receiver status triggers | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
86 |  | 38.523-1 | 7.1.2.3.8 | AM RLC / Reconfiguration of RLC parameters by upper layers | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
87 |  | 38.523-1 | 7.1.2.3.9 | AM RLC / Reassembling of AMD PDUs | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
88 |  | 38.523-1 | 7.1.2.3.9a | NR NTN / AM RLC / t-Reassembly expiry / t-ReassemblyExt-r17 configured | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
89 |  | 38.523-1 | 7.1.2.3.10 | AM RLC / Re-transmission of RLC PDU with and without re-segmentation | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
RRC
90 |  | 38.523-1 | 8.1.1.3.7a | RRC connection release / Success / Deprioritisation / NR / T325 expiry | Update SIB24 message content to include carrierFreq-r15 and carrierFreqListNR-v1810 for LessThan5MHz | Keysight | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
91 |  | 38.523-1 | 8.1.3.1.19 | Measurement configuration control and reporting / Inter-frequency measurements/ SFTD | Update SIB4 message content to include interFreqCarrierFreqList-v1800 for LessThan5MHz | Keysight | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
92 |  | 38.523-1 | 8.1.5.9.1 | UECapabilityInformation / UL segment transfer | Update the test case to include N_max nPRB=15 for 3 MHz | Anritsu | RAN5#109 (Nov-25) |  |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
93 |  | 38.523-1 | 8.1.5.13.1 | RRC SDT/CG based SDT/Success | Update the test case to include N_max nPRB=15 for 3 MHz | Keysight | RAN5#109 (Nov-25) | R5-254998 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
94 |  | 38.523-1 | 8.1.5.13.4 | RRC MT SDT / CG based SDT / Success | Update the test case to include N_max nPRB=15 for 3 MHz | Keysight | RAN5#109 (Nov-25) | R5-254999 |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
95 |  | 38.523-1 | 8.1.3.1.14A | Measurement configuration control and reporting / SS/PBCH block based / CSI-RS based inter-frequency measurements / Measurement of Neighbour NR cell | Update the test case to include N_max nPRB=15 for 3 MHz | Keysight | RAN5#109 (Nov-25) | No impact |  | 0.1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 38.523-2: Applicability for Protocol test cases
96 |  | 38.523-2 | 4.1 | Protocol conformance test cases applicability | Add test case applicability statements for the new test cases introduced in 38.523-1 | All companies | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
97 |  | 38.523-2 | 4.2 | Protocol conformance test cases Applicability Condition | Add new ICS statements. | All companies | RAN5#109 (Nov-25) |  |  | 0.1 | 0% | 0% |  | 0%
TS 38.523-3: Protocol test suites (TTCN)
98 |  | 38.523-3 | <Clause> | Introduction of test model for 3 MHz channel bandwidth for impacted frequency bands in FR1 |  | MCC TF160 | RAN5#109 (Nov-25) | R5-250309 R5-253983 |  | 0.1 | 100% (+20%) | 100% (+20%) |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.