## Cover sheet
3GPP TSG-RAN5 Meeting #109 | [8 empty] | R5-256530
Dallas, USA, 17th November 2025 - 21st November 2025
Agenda Item: | 7.5.2
Source: | Apple, Nokia
Title: | Work Plan for UE Conformance – NR RF requirements enhancement for frequency range 2 (FR2), Phase 3
Work item code: | NR_RF_FR2_req_enh3-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work item is to define the UE conformance requirements corresponding to WID (890059) on Further enhancements of NR RF requirements for FR2. This work item will cover RF and RRM conformance test specifications for Further enhancements of NR RF requirements for FR2. At the RAN#97-e meeting in Sep 2022 the Rel-18 RAN5 work item for UE Conformance - Further enhancements of NR RF requirements for FR2 was approved [1]. The purpose of present document is to provide a workplan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items. The workplan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 80% | 0% | 0%
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR2) |  | 80% | 0% | 0.02
FR2 |  | 0% | 0 | 2
NSA Option 3 (FR2) |  | 80% | 0% | 0% | No new tests planned
FR2 |  | 0% | 0 | 0
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 80% |  |  | 80%
Common ICS | 38.508-2 | 80% |  |  | 80%
Conformance Test Function | 38.509 | 80% |  |  | 80%
NR RF/RRM
FR2 RF common parts | 38.521-2 | 80% |  |  | 80%
FR2 RF Tx test cases | 38.521-2 Tx | 80% |  | 1 | 80% |  | 1
FR2 RF Rx test cases | 38.521-2 Rx | 100% |  |  | 100%
EN-DC FR2 RF test cases | 38.521-3 | 80% |  |  | 80%
Applicability RF and RRM test cases | 38.522 | 0% |  |  | 0%
Test Tolerances analysis for RF Tx test cases | 38.903 | 80% |  |  | 80%
Test Point analysis transmitter test cases | 38.905 | 80% |  |  | 80%
5 References
[1] RP-240781 | UE Conformance – NR RF requirements enhancement for frequency range 2 (FR2), Phase 3
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance – NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_RF_FR2_req_enh3-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance – NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Ashwin Mohan, Apple Tuomo Säynäjäkangas, Nokia |  |  | ashwin_mohan@apple.com tuomo.saynajakangas@nokia.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2
80%
0
0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 4.3 | Reference test conditions | Add necessary test conditions for Rel-18 NR RF FR2 aspects |  | RAN5#107 (May-25) |  |  | 0.5 | 100% | 100% |  | 100%
2 |  | 38.508-1 | 4.6 | Default NG-RAN RRC message and information elements contents | New message and IE definition for new Rel-18 NR RF FR2 features | Apple | RAN5#107 (May-25) |  |  | 0.1 | 100% | 100% |  | 100%
3 |  | 38.508-1 | 5 | Test environments for RF test | Necessary changes to RF test environments |  | RAN5#107 (May-25) |  |  | 0.1 | 50% | 50% |  | 50%
TS 38.508-2: Common ICS
4 |  | 38.508-2 | A.4 | ICS proforma tables | Add ICS as needed for the test case applicability statements for Rel-18 NR RF FR2 aspects | Apple, … | RAN5#107 (May-25) |  | Addition of ICS on a per test case basis by contributing companies | 0.1 | 100% | 100% |  | 100%
TS 38.509: Conformance Test Functions
5 |  | 38.509 | 5.X | UBF Updates for Initial Access | Updated test function for Beam Corr during Initial Access | Apple | RAN5#107 (May-25) |  |  | 0.1 | 0% | 0% |  | 0%
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
6 |  | 38.521-2 | 2 | References | Define relevant references made in TS |  | RAN5#107 (May-25) |  |  | 0.5 | 0% | 0% |  | 0%
7 |  | 38.521-2 | 3 | Definitions, symbols and abbreviations | 3 subsections which define definitions, symbols and abbreviations respectively |  | RAN5#107 (May-25) |  |  | 0.5 | 100% | 100% |  | 100%
8 |  | 38.521-2 | Annex A | Measurement channels | Reference Measurement Channels updates for Rel-18 tests | Apple | RAN5#107 (May-25) |  |  | 0.5 | 100% | 100% |  | 100%
9 |  | 38.521-2 | Annex B | Propagation conditions | Possible propagation conditions updates in Rel-18 NR RF FR2 tests |  | RAN5#107 (May-25) |  |  | 0.5 | 100% | 100% |  | 100%
10 |  | 38.521-2 | Annex C | Downlink physical channels | Updates pertaining to Rel-18 |  | RAN5#107 (May-25) |  |  | 0.5 | 100% | 100% |  | 100%
11 |  | 38.521-2 | Annex E | Global In-Channel TX-Test | UL-256 QAM specific updates in Rel-18 |  | RAN5#107 (May-25) | R5-247849 |  | 0.5 | 100% | 100% |  | 100%
12 |  | 38.521-2 | Annex F | Measurement uncertainties and Test Tolerances | Define measurement uncertainties and TT for updated Rel-18 test cases/bands | Apple, …… | RAN5#107 (May-25) |  | Updates from TE vendors critical for MU. TT updates by companies contributing test cases updates | 0.5 | 0% | 0% |  | 0%
13 |  | 38.521-2 | Annex G | Uplink Physical Channels | Updates pertaining to Rel-18 |  | RAN5#107 (May-25) |  |  | 0.5 | 100% | 100% |  | 100%
14 |  | 38.521-2 | Annex H | Statistical Testing | Check for any Rel-18 updates |  | RAN5#107 (May-25) |  |  | 0.1 | 100% | 100% |  | 100%
15 |  | 38.521-2 | Annex K | EIRP, TRP, and EIS measurement procedures | Update procedures if needeed for Rel-18 |  | RAN5#107 (May-25) |  |  | 0.5 | 40% | 40% |  | 40%
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
16 |  | 38.521-2 Tx | 6.2.1.1 | UE maximum output power - EIRP and TRP | Minimum conformance updates for Beam Correspondence during initial access mainly indicating it is not applicable to this section - separate test was created | Apple | RAN5#107 (May-25) |  |  | 0.5 | 100% | 100% |  | 100%
17 |  |  | 6.2.1.2 | UE maximum output power - Spherical Coverage | Minimum conformance updates for Beam Correspondence during initial access | Apple
18 |  | 38.521-2 Tx | 6.2.2 | UE maximum output power reduction | Minimum conformance updates related to UL-256 QAM requirements in Rel-18 | SGS Wireless | RAN5#107 (May-25) | R5-244686 |  | 1 | 100% | 100% |  | 100%
19 |  | 38.521-2 Tx | 6.2A | Transmit power for CA | Existing sub-clause header | SGS Wireless
20 |  | 38.521-2 Tx | 6.4.2.1 | Error Vector Magnitude | Minimum conformance updates related to UL-256 QAM requirements in Rel-18 | SGS Wireless |  |  |  | 1 | 100% | 100% |  | 100%
21 |  | 38.521-2 Tx | 6.2A.2 | UE maximum output power reduction for CA | Existing sub-clause header | SGS Wireless
22 |  | 38.521-2 Tx | 6.2A.2.0.1 | Minimum conformance requirements General | Minimum conformance updates related to UL-256 QAM requirements in Rel-18 | SGS Wireless | RAN5#107 (May-25) | R5-247849 |  | 0.5 | 100% | 100% |  | 100%
23 |  | 38.521-2 Tx | 6.2A.2.0.2 | Maximum output power reduction for power class 1 | Minimum conformance updates related to UL-256 QAM requirements in Rel-18 | SGS Wireless | RAN5#107 (May-25) | R5-247849 |  | 0.5 | 100% | 100% |  | 100%
24 |  | 38.521-2 Tx | 6.2A.2.0.3 | Maximum output power reduction for power class 2 | Minimum conformance updates related to UL-256 QAM requirements in Rel-18 | SGS Wireless | RAN5#107 (May-25) |  |  | 0.5 | 100% | 100% |  | 100%
25 |  | 38.521-2 Tx | 6.2A.2.0.6 | Maximum output power reduction for power class 5 | Minimum conformance updates related to UL-256 QAM requirements in Rel-18 | SGS Wireless | RAN5#107 (May-25) |  |  | 1 | 100% | 100% |  | 100%
26 |  | 38.521-2 Tx | 6.6.1 | Beam Correspondence - EIRP | General section | Apple | RAN5#107 (May-25) | R5-243841 |  | 0.5 | 100% | 100% |  | 100%
27 |  | 38.521-2 Tx | 6.6.2 | Beam Correspondence - EIRP | Minimum conformance updates for Beam Correspondence during initial access mainly clarifying this section covers RRC_CONNECTED requireemnts | Apple | RAN5#107 (May-25) | R5-243841 | Only changes in minimum conformance requirements | 1 | 100% | 100% |  | 100%
28 | Y | 38.521-2 Tx | 6.6.3 | Beam Correspondence - Initial Access | New Rel-18 requirements for Beam Correspondence in RRC_IDLE and Initial Access | Apple | RAN5#107 (May-25) | R5-243841 R5-245998 R5-247935 |  | 1 | 40% | 40% |  | 40%
TS 38.521-2: FR2 RF test cases - Rx
|  | 38.521-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TS 38.521-3: EN-DC FR2 RF test cases - necessary updates
|  | 38.521-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
29 |  | 38.521-3 Tx | 6.2B.2 | UE maximum output power reduction for inter-band EN-DC with FR2 | Minimum conformance updates related to UL-256 QAM requirements in Rel-18 |  | RAN5#107 (May-25) |  |  | 1 | 100% | 100% |  | 100%
30 |  | 38.521-3 Tx | 6.2B.2 | UE maximum output power reduction for inter-band EN-DC with FR2 | Minimum conformance updates related to UL-256 QAM requirements in Rel-18 |  | RAN5#107 (May-25) |  |  | 1 | 100% | 100% |  | 100%
31 |  | 38.521-3 Tx | 6.4B.4 | Error Vector Magnitude for interbband EN-DC with FR2 | Minimum conformance updates related to UL-256 QAM requirements in Rel-18 |  | RAN5#107 (May-25) |  |  | 1 | 100% | 100% |  | 100%
32 |  | 38.521-3 Tx | 6.6B.1 | Beam Correspondence - EIRP for inter-band EN-DC with FR2 | General section | Apple | RAN5#107 (May-25) | R5-242790 | Only clarification needs to be added that test applies only to RRC_CONNECTED. No new requirements | 1 | 100% | 100% |  | 100%
33 |  | 38.521-3 Tx | 6.6B.2 | Beam Correspondence - EIRP for inter-band EN-DC with FR2 | Minimum conformance updates for Beam Correspondence during initial access mainly clarifying this section covers RRC_CONNECTED requireemnts | Apple | RAN5#107 (May-25) | R5-242790 | Only clarification needs to be added that test applies only to RRC_CONNECTED. No new requirements | 1 | 100% | 100% |  | 100%
TS 38.522: Applicability for RF FR2 test cases
34 |  | 38.522 | 4.1.2 | RF FR2 standalone conformance test cases | Add test case applicability statements for the test cases introduced for 38.521-2. | Apple | RAN5#107 (May-25) |  |  | 1 | 80% | 80% |  | 80%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | No RRM updates as per Core specifications |  |  |  |  | TBD
TR 38.903: Test Tolerances analysis RF test cases
[6 empty] | Apple |  | R5-247936
35 |  | 38.903 | Annex B | Acceptable uncertainty of test system for test cases defined in TS 38.521-2 for radiative testing | MU analysis for FR2 RF Test cases |  | RAN5#107 (May-25) |  | MU for new EVM and Beam Correspondence - Initial Access tests. Depending on TE Vendor contributions | 0.5 | 50% | 50% |  | 50%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
36 |  | 38.905 | 4.2 | Test point analysis for FR2 test cases in TS 38.521-2 | TP analysis for FR2 RF Test cases | Apple | RAN5#107 (May-25) | R5-247936 |  | 0.5 | 80% | 80% |  | 80%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.