## Slide 1: Time plan for the new SI proposal on LTE-based V2X
LG Electronics, CATT
3GPP TSG RAN WG Meeting #68 RP-150779
Malmö, Sweden, June 15 - 18, 2015
Agenda item: 13.1.1
Document for: Discussion

## Slide 2: SI objective in RP-150778
1) To define the evaluation methodology for LTE-based V2X services to compare the performance of different technical options, including the following aspects: [RAN1]
a) Deployment scenarios and channel models suitable for vehicular communications
b) Modeling of vehicle density and mobility and its impact on the physical layer operations and performance
c) Traffic models and performance metrics
2) To analyze whether/to which extent the existing LTE systems can fulfill the requirements of LTE-based V2X [RAN1, RAN2, RAN3].
3) To identify and evaluate technical options for enhancements to the physical layers, radio protocols, and RAN interfaces in LTE uplink, downlink, and sidelink to enable/facilitate LTE-based V2X services [RAN1, RAN2, RAN3]

## Slide 3: TU proposal in RP-150778

## Slide 4: Time plan for RAN1
Q3/2015 | RAN1#82 (1 TU) | Start discussing the evaluation methodology
Q4/2015 | RAN1#82bis (1 TU) | Conclude the evaluation methodology
 | RAN1#83 (1 TU) | Start RAN1 level gap analysis with the initial evaluation results
Q1/2016 | RAN1#84 (2 TU) | Conclude RAN1 level gap analysis with updated evaluation results Start discussing potential enhancement areas
Q2/2016 | RAN1#84bis (4 TU) | Initial identification of enhancement options Initial evaluation results of the options
 | RAN1#85 (4 TU) | Conclude the identification of enhancement options with updated evaluation results Complete the study

## Slide 5: Time plan for RAN2
Q3/2015 | RAN2#91 (0 TU) | 
Q4/2015 | RAN2#91bis (0 TU) | 
 | RAN2#92 (0 TU) | 
Q1/2016 | RAN2#93 (2 TU) | Start RAN2 level gap analysis potentially using the evaluation results in RAN1 Start discussing potential enhancement areas
Q2/2016 | RAN2#93bis (3 TU) | Conclude RAN2 level gap analysis Initial identification of enhancement options
 | RAN2#94 (3 TU) | Conclude the identification of enhancement options Complete the study

## Slide 6: Time plan for RAN3
Q3/2015 | RAN3#89 (0 TU) | 
Q4/2015 | RAN3#89bis (0 TU) | 
 | RAN3#90 (0 TU) | 
Q1/2016 | RAN3#91 (1 TU) | Start RAN3 level gap analysis potentially using the evaluation results in RAN1 Start discussing potential enhancement areas
Q2/2016 | RAN3#91bis (2 TU) | Conclude RAN3 level gap analysis Initial identification of enhancement options
 | RAN3#92 (2 TU) | Conclude the identification of enhancement options Complete the study