## Slide 1
Way Forward
on the overall 5G-NR eMBB workplan
RP-170741
3GPP RAN #75
Dubrovnik, March 2017
Alcatel-Lucent Shanghai-Bell, Alibaba, Apple, AT&T, British Telecom, Broadcom, CATT, China Telecom, China Unicom, Cisco, CMCC, Convida Wireless, Deutsche Telekom, DOCOMO, Ericsson, Etisalat, Fujitsu, Huawei, Intel, Interdigital, KDDI, KT, LG Electronics, LGU+, MediaTek, NEC, Nokia, Ooredoo, OPPO, Qualcomm, Samsung, Sierra Wireless, SK Telecom, Sony, Sprint, Swisscom, TCL, Telecom Italia, Telefonica, TeliaSonera, Telstra, Tmobile USA, Verizon, vivo, Vodafone, Xiaomi, ZTE

## Slide 2: Proposal
By December 2017: complete Stage 3 for Non-Standalone 5G-NR eMBB (incl. low latency support) with Option 3
  Ensure commonality with Standalone eMBB (incl. low latency support), as well as forward compatibility
    Complete stage-3 of all L1 and L2-User-Plane for both Non-Standalone and Standalone by December 2017
    L1 and L2-User-Plane for both Non-Standalone and Standalone is different for some aspects
  Prioritization of NR band definition (and related band combinations with LTE) will be discussed separately

## Slide 3: Proposal (cont.)
By March 2018: intermediate implementable version with frozen ASN.1 for Non-Standalone 5G NR eMBB accordingly
  Only applies to NSA deployment scenario Options 3
  Concept of intermediate implementable version with frozen ASN.1 shall not be defined to any other Rel-15 feature
  A single Rel-15 ASN.1 shall be maintained from September 2018 onwards (common to NSA and SA).
  At high level, in Dec-17 RAN-P approves NR-RRC containing NR-NSA; in Mar-18, ASN.1 of that spec is frozen; in Jun-18, RAN-P approved NR-RRC containing NR-SA & NR-NSA; in Sep-18, ASN.1 of that spec is frozen
  From March-18 onwards, if backward incompatible CRs are deemed necessary, they will be subject to consensus in RAN as per normal procedures
  UE capability aspects to be discussed in RAN2

## Slide 4: Proposal (cont.)
Maintain current schedule for Standalone 5G-NR in Rel-15
  Stage 3 completion June 2018; ASN.1 freeze September 2018
Ensure alignment of core network aspects
  Ask TSGs SA and CT to ensure completion of stage-3 for the so-called “Option 3” family by December 2017 in case modifications to the current specifications are needed
  Overall 5G Core Network already agreed to be completed by June 2018

## Slide 5: Proposal (cont.)
2016 | 2017 |  |  |  | 2018 |  |  | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
NSA = Non StandAlone = EPC core (“Option 3”) & LTE anchor
SA = StandAlone
5G study
5G NR Work Item
5G NR NSA Completion
Stage 3 completion for Non-Standalone 5G-NR
RAN #74
RAN #75
RAN #78
RAN #80 (Rel-15 completion)
Further evolution
5G NR SA Completion
Stage 3 completion for Standalone 5G-NR
NSA Option 3 family ASN.1
Rel-15 ASN.1 for SA & NSA