## Proposals
3GPP TSG RAN Meeting #87e |  | RP-200206
Electronic Meeting, March 16-19, 2020
Agenda Item: | 9.3
Source: | CMCC
Title: | Discussion on the timeplan for R16 frozen
Document for: | Discussion
Discussion
In the excel sheets, we analyze the status and open issues for each Rel-16 WI. Our observations and proposals are provided as following. Observation 1: Based on our analysis, the core functions can be completed for most WIs. Observation 2: For individual topics that cannot be finished by June (e.g. V2X), exception sheet can be allowed. Observation 3: From ASN.1 frozen perspective,RAN1 and RAN4 feature list need to be provided at least in April meeting. If there is no decision for certain feature, there will be no capability signaling supported in Rel-16, the feature will be mandatory, which basically means that a UE that sets the AccessStratumRelease in the UE capabilities to “Rel-16” must implement all such features. . Proposal: Rel-16 ASN.1 frozen is kept in June.

## MIMO
leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Comments(open issues)
RAN1 | Enhancements on MIMO for NR | Enhancements on MU-MIMO support: o Specify overhead reduction, based on Type II CSI feedback, taking into account the tradeoff between performance and overhead o Perform study and, if needed, specify extension of Type II CSI feedback to rank >2 | RAN1: CSI Enhancement for MU-MIMO Support | Yes | ★ | Issue 1: Whether Type II CSI reporting should be supported when BWP size < 24 PRBs Analysis: For CSI enhancement, most of the critical issues were resolved in RAN1#100e meeting, leaving an offline email discussion to be finalized before next meeting. Based on the email discussion, this issue is highly possible to be finished in next meeting.
|  | Enhancements on multi-TRP/panel transmission including improved reliability and robustness with both ideal and non-ideal backhaul: o Specify downlink control signalling enhancement(s) for efficient support of non-coherent joint transmission o Perform study and, if needed, specify enhancements on uplink control signalling and/or reference signal(s) for non-coherent joint transmission o Multi-TRP techniques for URLLC requirements are included in this WI | RAN1: Enhancements on Multi-TRP/Panel Transmission | Yes | ★ | Issue 1: Default TCI-state for single-PDCCH based PDSCH transmission Analysis: For multi-TRP transmission, some critical issues were discussed and good progress was made in RAN1#100e e-meeting, however, there was no consensus in RAN1#100e meeting to introduce spec change for issue 1, which may need further discussion in next meeting, or else, it will be left to UE implementation. Besides, there may be some maintenance for specification or enhancement for the feature to be discussed in next meeting. According to the good progress of discussion in RAN1#100e meeting, the feature of multi-TRP can be finished before June.
|  | Enhancements on multi-beam operation, primarily targeting FR2 operation: o Perform study and, if needed, specify enhancement(s) on UL and/or DL transmit beam selection specified in Rel-15 to reduce latency and overhead o Specify beam failure recovery for SCell with DL/UL as well as DL-only, where PCell can be operating in FR1 as well as FR2 o Specify measurement and reporting of either L1-RSRQ or L1-SINR | RAN1: Enhancements on Multi-beam Operation | Yes | ★★ | Issues 1: Application timing for the newly activated PL RS FFS: Whether/how to capture the application timing in RAN1 specification or send an LS to other WGs to suggest them to update their specifications accordingly will be decided in the next meeting. Issues 2: PL RSs for UE tracking FFS: How to capture "PL RSs for UE tracking" into the spec will be discussed at RAN1#100bis and further consider the configuration cases when the default PL RS is not enabled or enabled. Issues 3: Working assumption corresponding to CMR+IMR interference measurement for L1-SINR Issues 4: MAC-CE based spatial relation update application timing for AP-SRS Issues 5: L1-SINR measurement with reportQuantity set to none Issues 6: PDCCH reception beam after detection of gNB’s response to SCell BFR MAC CE if the UE reports no new beam found Analysis: For beam management enhancement, some critical issues were discussed in RAN1#100e meeting, leaving some details (Issue 1, 2) to be finalized in the next meeting. For L1-SINR interference measurement, a working assumption (Issue 3) was left for further discussion. Besides, some critical issues (Issue 4, 5, 6) were discussed in RAN1#100e meeting, however, no consensus was achieved, which may need further discussion in next two meetings. According to the good progress of discussion in RAN1#100e meeting, critical issues in multi-beam are highly possible to be finished within two meetings.
|  | Perform study and make conclusion in the first RAN1 meeting after start of the WI, and if needed, specify CSI-RS and DMRS (both downlink and uplink) enhancement for PAPR reduction for one or multiple layers (no change on RE mapping specified in Rel-15) | RAN1: Low PAPR RS | Yes | ★ | Issue 1: For low PAPR pi/2-BPSK PUCCH, format 3 and 4, whether and if so how the DMRS depends on the cyclic shift value α Analysis: For low PAPR RS, 90% remaining issues have been resolved in RAN1#100e meeting, however, there is no consensus for issue 1, which may need further discussion in next meeting.
|  | Specify enhancement to allow full power transmission in case of uplink transmission with multiple power amplifiers (assume no change on UE power class) | RAN1: Full TX Power UL transmission | Yes | Finished | One critical issue regarding codebook configuration in Mode2 with multiple SRS and two editorial issues were resolved in RAN1#100e meeting. Other issues are not critical.
|  | Specify higher layer support of enhancements listed above [RAN2] | RAN2 | Yes | ★ | Main function complete, waiting for ASN.1 review
|  | Specify core requirements associated with the items specified by RAN1 (RAN4) -Specify RRM requirements -Identify impact on RF requirements for reduced PAPR pi/2-BPSK DMRS and, if needed, specify RF requirements -Identify impact on RF requirements for the uplink full power transmission and, if needed, specify RF requirements | RAN4: UE RF requirements | Yes | ★★ | Issue 1: FFS new power class capability for full power transmission Issue 2: UE behavior for fallback DCI (DCI_0_0) Issue 3: MOP requirement for full power transmission with 2 TX ports configured for FR1 shall be captured Issue 4: Test Configuration and Requirement Applicability for Full Power Transmission MOP Test issues
|  |  | RAN4: RRM core requirements | Yes | ★★ | Issue 1: There are open issues for L1-SINR measurement requirements,including the value of P, and the scaling factor N for FR2 in the delay requirements, measurement restriction and scheduling availability, side condition for CMR+NZP-IMR. Issue 2: There are open issues for sCell beam failure recovery, including sharing factor for BFD evaluation period, sharing factor for CBD evaluation period, whether and how the requirement could be defined for BFRQ.

## NR-U
leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Comments(open issues)
RAN1 | NR-based Access to Unlicensed Spectrum | Physical layer aspects including [RAN1]: - Frame structure including single and multiple DL to UL and UL to DL switching points within a shared COT with associated identified LBT requirements (TR Section 7.2.1.3.1). - NR-U supports a mode of operation where for a carrier and at least for intra-band CA on serving cells on unlicensed bands, all DL channels / signals can be operated with the same numerology, and all UL channels / signals can be operated with the same numerology. - Subcarrier spacing for control and data channels supporting 15kHz, 30kHz, and 60kHz (air-interface perspective; optionality to be discussed separately). - Wide band operation (in integer multiples of 20MHz) for DL and UL for NR-U supported with multiple serving cells, and wideband operation (in integer multiples of 20MHz) for DL and UL for NR-U supported with one serving cell with bandwidth > 20MHz with potential scheduling constraint subject to input from RAN2 and RAN4 on feasibility of operating the wideband carrier when LBT is unsuccessful in one or more LBT subbands within the wideband carrier. For all wide-band operation cases, CCA is performed in units of 20MHz (at least for 5GHz). - 10MHz operation for 5GHz band via NR-U/NR-U CA or NR/NR-U CA without air-interface optimizations specific to 10MHz. NOTE: - 10MHz Pcell or SpCell is not supported in NR-U. - The absence of WiFi channels should be guaranteed. - NR-U Discovery Reference Signal (DRS) containing at least SS/PBCH block burst set transmission and possibly CSI-RS, RMSI-CORESET(s)+PDSCH(s), OSI and paging with properties and extensions from NR Rel-15 in line with the agreements during the study phase (TR 38.889, Section 7.2.1.2). 60kHz based SSB/PBCH block is outside the scope of the WI. - PRACH including possible extension of PRACH format(s) in line with agreements during the SI phase (TR 38.889, Section 7.2.1.2) to support minimum bandwidth requirement given by regulation. Determine the applicability of Rel-15 NR formats to NR-U operation.RAN1 should decide whether 60 kHz subcarrier spacing for PRACH is supported, based on a unified design with 15 kHz and 30 kHz PRACH for meeting occupied channel bandwidth (OCB) requirements. - UL control including extension of PUCCH format(s) to support PRB-based frequency block-interlaced transmission and use of Rel-15 NR PUCCH formats 2 and 3 for NR-U operation. Applicability of sub-PRB frequency block-interlaced transmission for 60kHz to be decided by RAN1. - UL data channel including extension of PUSCH to support PRB-based frequency block-interlaced transmission; support of multiple PUSCH(s) starting positions in one or multiple slot(s) depending on the LBT outcome with the understanding that the ending position is indicated by the UL grant; design not requiring the UE to change a granted TBS for a PUSCH transmission depending on the LBT outcome. The necessary PUSCH enhancements based on CP-OFDM. Applicability of sub-PRB frequency block-interlaced transmission for 60kHz to be decided by RAN1. - SRS including the introduction of additional flexibility in configuring/triggering SRS in line with agreements during the study phase. - For DL data channel, support of multiple PDSCH starting positions. - Mechanism to detect a gNB’s transmission burst in line with the TR 38.889, Section 7.2.1.2 related to UE power consumption. - DL control in line with the agreements during the study phase (TR 38.889, Section 7.2.1.2) including extensions allowing dynamic change of the time domain instances in which the UE is expected to receive PDCCH, modifications enabling DRS transmissions without gaps in the time-domain, and indication of time domain COT structure; | RAN1: Initial access signals/channels | Yes | ★ | Issue 1: PBCH scrambling, and C-RNTI monitoring when PUSCH not transmitted for 2-step RACH Regarding Issue 1, RAN1 thinks this issue is agreeable, there may not need any spec impact and can be kept for UE implementation and can also wait for RAN2 decision. Issue 2: CSI-RS transmission in DRS No consensus were achieved for Issue 2 in RAN1#100 emeeting, which is proposed to be discussed in the next meeting
|  |  | RAN1: DL signals and channels | Yes | ★ | Issue 1: Search space set monitoring/switching Remaining open issues: value range of P1 and P2
|  |  | RAN1: UL signals and channels | Yes | ★ | Issue 1: FDRA for DCI 0_0/0_1 Regarding Issue 1, some agreements were achieved with the square brackets in RAN1#100 emeeting. Remaining open issues: 1) For DCI 0_0 in a CSS, which RB set is used for PUSCH allocation; 2) For DCI 0_0 in a USS, whether or not to include Y-bits for RB set allocation A TP on the relationship between interlaced PUSCH and PT-RS is proposed by FL, to be discussed in the next meeting
|  |  | RAN1: Wide-band operation | Yes | ★ | Issue 1: TP for NR-U intra-carrier guard-band Regarding issue 1, it is an unofficial email discussion and proposed to be discussed in the next meeting.
|  | Physical layer procedure(s) including [RAN1, RAN2]: - For LBE, channel access mechanism in line with agreements from the NR-U study item (TR 38.889, Section 7.2.1.3.1). Specification work to be performed by RAN1. - For FBE, channel access mechanism in line with agreements from the NR-U study item (TR 38.889, Section 7.2.1.3.1). FBE is intended for environments where the absence of Wi-Fi is guaranteed (e.g., by level of regulations, private premises policies, etc. Further, the targeted scenario is limited to a single NR-U network (i.e. single operator) in the operating band and geographic area. Specification work to be performed by RAN1. - Initial access: specify required NR modifications to increase the maximum number of candidate SS/PBCH block positions within the DRS transmission window; to handle reduced SS/PBCH block and RMSI transmission opportunities due to LBT failure; to determine frame timing and QCL assumptions from the detected SS/PBCH block; single SS/PBCH block numerology assumed per band for Pcells in unlicensed spectrum. (RAN1) - Random access: specify required NR modifications to enhance RACH procedure in line with the agreements during the study phase, including 4-step RACH modifications to handle reduced Msg 1/2/3/4 transmission opportunities due to LBT failure (RAN1/RAN2); LBT for 2-step RACH and application of PRACH and PUSCH format improvements for NR-U to 2-step RACH. (RAN1 - Scheduling request: specify required NR modifications due to LBT failure in line with agreements during the study phase. (RAN1/RAN2) - RLM/RRM extensions for NR-U operation due to uncertain and reduced transmission opportunities for DL signals and channels due to LBT failure in line with agreements during the study phase (NR-U TR section 7.2.1.3.2), including configuring different DRS Measurement Time Configuration (DMTCs) for RRM and RLM respectively, identifying the set of RLM-RSs to measure, which set(s) are used for in-sync, out-of-sync evaluations, potential definition of a metric to accurately identify unsuccessful detection of RLM-RS. Support RSSI reporting. Define a metric to measure channel occupancy or medium contention and its corresponding reporting. (RAN1/RAN2) - HARQ operation: NR HARQ feedback mechanisms are the baseline for NR-U operation with extensions in line with agreements during the study phase (NR-U TR section 7.2.1.3.3), including immediate transmission of HARQ A/N for the corresponding data in the same shared COT as well as transmission of HARQ A/N in a subsequent COT. Potentially support mechanisms to provide multiple and/or supplemental time and/or frequency domain transmission opportunities. (RAN1) - Scheduling multiple TTIs for PUSCH in-line with agreements from the study phase (TR 38.889, Section 7.2.1.3.3). (RAN1) - Configured Grant operation: NR Type-1 and Type-2 configured grant mechanisms are the baseline for NR-U operation with modifications in line with agreements during the study phase (NR-U TR section 7.2.1.3.4). (RAN1) - CSI: NR Rel-15 CSI feedback mechanism is the baseline for NR-U operation. Enhancements can be considered in line with agreements from the NR-U study item (e.g., TR 38.889, Section 7.2.1.3.1). (RAN1) - Data multiplexing aspects (for both UL and DL) considering LBT and channel access priorities. (RAN1/RAN2) | RAN1: Channel access procedures | Yes | ★ | Issue 1: CP extension (1st symbol of a slot, application of PUCCH) Regarding Issue 1, it is agreed to can further consider how to also support CP extension values (to be) agreed for Configured Grant transmissions Issue 2: UL LBT failure indication Regarding issue 2, it will be resolved in the next meeting. Besides, RAN1 has sent a LS(R1-2001397) to request RAN2 to provide a full list of conditions under which Layer 1 must notify higher layers about UL channel access failures.
|  |  | RAN1: Enhancements to initial access procedure | Yes | ★ | Issue 1: Alignment candidate SS/PBCH block index and SS/PBCH block index terminology with RAN2/RAN4 Regarding issue 1, a LS(R1-2001357) has been sent to RAN2/4 Issue 2: Configuration of RNTI and DCI payload for IDLE UE on FBE cell to permit PRACH within FFP Regarding issue 2, it has not been supported in RAN1#100 emeeting and may not be discussed in the furture meeting due to majority companies think it is an implementation issue. Issue 3: RM/RLM including: • RSSI measurement duration • RMTC configuration in RRC signalling and FFS points for value ranges compared to LAA LTE • The need to replace Lmax with L ̅_max and add values 10, 20 for RLM in TS 38.213 subclause 5 Regarding Issue 3, many agreements were achieved and a LS(r1-2001375) on NR-U enhancements to initial access procedures has been sent to RAN2, while text proposal for section 5.1.21 in 38.215 was discussed without consensus.
|  |  | RAN1: HARQ enhancement | Yes | ★ | Issue 1: Enhanced HARQ-ACK codebook, including • Handling of non-numerical K1 (NNK1) value (TS38.213 clause 9.1.3) • TS38.213 clause 9.1.3.3: UL DAI for dynamic HARQ-ACK codebook feedback in PUSCH • TS38.213 clause 9.1.3.3: alignment of 38.213 with 38.212 • Implementation of agreement on handling reception of only DCI format 1_0 is incomplete • TS38.213 clause 9.1.3.3: when 2 T-DAI values are signaled in DCI 1_1 the second total DAI field should be used to set the T-DAI value for a non-scheduled PDSCH group Regarding Issue 1, some agreements were achieved with the square brackets in RAN1#100 emeeting. Issue 2: Type-3 HARQ-ACK codebook, including • Problem in the pseudo-code when the number of code blocks of one TB is smaller than the configured maximum number of CBGs per TB (when a TB consists of N code blocks, N<M) • Corrections on HARQ-ACK state reset in case NDI is not reported in the feedback Issue 2 has been pattially resolved in RAN1#100 emeeting. FFS: cases where the UE has not yet obtained HARQ-ACK information for a TB corresponding to a scheduled PDSCH reception.
|  |  | RAN1: Configured grant enhancement | Yes | Finished | Issue 1: Finalize RRC value ranges for multiple RRC parameters related to CG Regarding Issue 1, some agreements were achieved with the square brackets, which is for information to RAN2, no need to further discuss in RAN1. There may be other RRC parameters for which value range should be determined
|  |  | RAN2:consistent LBT failure detection | Yes | ★ | Issue 1: The UE is allowed to transmit other UL transmission after?/while? successful RA procedure triggered by UL LBT failure on SpCell.
|  | Inactive and Idle mode procedures: Rel-15 NR design is the baseline, including NR licensed measurement framework (cell and beam quality derivation for RSRP, RSRQ, and SINR, filtering and combining multiple beams). Specify necessary extensions for NR-U operation for cell selection/reselection, including enabling the possibility for the UE to camp on a non-best cell if the best cell does not belong to the registered PLMN (or E-PLMN), where the non-best cell would still be the best cell of the registered PLMN; increased paging opportunities per DRX cycle for the UE to receive the page; increased opportunities for SI delivery. | RAN2: - enabling UE to camp on a non-best cell if the best cell does not belong to the registered PLMN -increased paging opportunities -increased opportunities for SI delivery | Yes | ★ | Main function complete, waiting for ASN.1 review
|  | Introduction of access priority for control signalling (transmissions over SRBs) over unlicensed carriers (highest access priority). | RAN2:access priority for control signalling | Yes | ★ | Main function complete, waiting for ASN.1 review
|  | Mobility: For non-standalone NR-U deployments, connected mode mobility is supported on licensed spectrum using the baseline mobility procedure specified for the concerned licensed radio access technology (LTE or NR). For standalone NR-U deployments, specify mechanisms for inter-cell handover between NR-U and NR-U, inter-cell handover between NR-U and NR, and Inter-RAT handover between NR-U and LTE (connected to either EPC of 5GC). Extensions of mobility-related measurement reporting for unlicensed operation including channel occupancy indication and RSSI measurements. | RAN2:measurement reporting of channel occupancy indication and RSSI measurements. | Yes | ★ | Issue 1:RAN2 should further discuss the ASN.1 modelling of RSSI reporting.
|  | Paging: specify required NR modifications to enhance paging opportunities by increasing time-domain paging occasions or paging monitoring occasions while taking UE power consumption into account. | RAN2:increased paging opportunities | Yes | ★ | Main function complete, waiting for ASN.1 review
|  | System information: specify required NR modifications to enhance acquisition of system information in NR-U including increased transmission opportunities in time domain for SI transmission. | RAN2:increased opportunities for SI delivery | Yes | ★ | Main function complete, waiting for ASN.1 review
|  | Specify new unlicensed band(s) for the 5 GHz and 6 GHz frequency ranges (see Note 1). The band(s) definition should include UL/DL operation. - 10MHz channel definition by means of bands spelled out like LTE LAA (main target is 5GHz band in a certain country) | RAN4: system parameters | Yes | ★★ | Issue 1: Wideband operation, including handling 60kHz SCS and guard band, guardband grid and shift and testing for spectral utilization Issue 2: band definition, including whether to include band n46 in TS 38.104/38.101-1 Issue 3: Intra-band operation and raster definitions, including NR CA bandwidth classes definition Issue 4: Spectrum emission mask, including SEM measurement procedure, LO leakage exception
|  | Specify gNB and UE RF core requirements for the band(s) in the above frequency range, including a limited set of example band combinations (see Note 2). Band combinations for scenario A, B and C are attached in Annex A. Investigate the feasibility of increasing the number of usable PRBs for different numerologies and channel bandwidths in unlicensed bands, and if found feasible, specify such support. | RAN4: UE RF requirements | Yes | ★★★ | Issue 1: Tx requirements, including in-band emissions, additional spurious requirements, enabling PC3 requirements RAN4 Feb meeting aggree to start with the eLAA definition, some extra work is still needed to verify or modify if needed for NR-U Issue 2: Rx requirements including REFSENS, ACS, In-band and out-of-band blocking, Maximum input level, wideband intermodulation. Issue 3: MPR/A-MPR Issue 4: other issues like MSD Not all fundamental requirements are agreed yet, and extensive simulations are needed with results aligned between multiple companies to derive MPR and A-MPR tables for all NR-U waveforms to meet general and deployment-specific requirements for each power class to be specified. It is challenging to complete the work in Q2.
|  |  | RAN4: BS RF requirements | Yes | ★★ | Issue 1: FRCs simulation results for REFSENSE, ICS and Dynamic range Issue 2: BS receiver requirements since RAN4 just finished a supplement with correct FRC interlacing to simulation assumption for BS Rx requirements Simulation is also needed to estimate required SNR, but progress on the basesatation side is not expected to hinder the completion schedule.
|  | Specify RRM/RLM core requirements. | RAN4: RRM/RLM core requirements | Yes | ★★★ | Issue 1: Applicability rules for NR-U RRM Issue 2: SI acquisition time in paging interruption, RRC re-direction and RRC re-establishment in NR-U Issue 3: RRC Re-establishment and RRC-release: UE behaviour upon exceeding max number of missed PRACH occasions: Wait for RAN2 LS reply Issue 4: SCell activation, including UE behaviour and the SCell activation delay extension due to any LBT failures when sCellDeactivationTimer is not configured, and condition on the delay due UL LBT failures for HARQ in SCell activation delay Issue 5: UL BWP switch requirements triggered by consistent UL LBT failures Issue 6: SSB based RLM including the set of SSB that UE is required to monitor and OOC evaluation period Issue 7: CSI-based RLM Issue 8: BFD and CBD Issue 9: L1 RSRP measurement period Issue 10: Inter-RAT SFTD measurement period Issue 11: RSSI and channel occupancy measurements, including intra/inter-frequency definition, new gap pattern, report mapping, RSSI measurement accuracy and report normalization Issue 12: Measurement in connected mode, including set of SSB that UE is required to monitor, UE behaviour upon exceeding the maximum number of DL LBT failure during PSS/SSS detection, UE behaviour in case of successive DL LBT failures during measurements and how to consider the QCL-ed beams during cell identification stage. At lot of issues are still open. Due to the high workload and remaining open issues, it is challenging to complete the work in Q2.

## Positioning
leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Comments(open issues)
RAN1 | NR Positioning Support | Specify NR DL and UL reference signals to facilitate support of NR positioning techniques (DL-TDOA, DL-AoD, UL-TDOA, UL-AoA, multi-cell RTT and E-CID) [RAN1] ○ Support E-CID downlink measurements based on at least RRM measurements defined in NR Rel. 15 ○ Identify whether and which Rel-15 NR reference signals can be used for different NR positioning techniques ○ Define new DL positioning reference signals applicable at least for DL-TDOA, DL-AoD, RTT ○ Define UL SRS with possible enhancements for positioning which is applicable at least for RTT, UL-TDOA, UL-AoA | RAN1: DL Reference Signals for NR Positioning | Yes | ★ | There is only one remaining critical issue to be discussed: Issue 1: The UE DL PRS processing capability. Status: In RAN1#100e meeting, companies shared diverse opinions on aspects including the parameters to be reported, the capability related to measurement gap configuration, etc., and proposals were agreed with remaining FFS points. Comments: This issue is important for positioning feature, without companies' consensus and agreements, the UE feautre will be negatively affected. According to the good progress of discussion in RAN1#100e emeeting, this critical issue is highly possible to be finished during the next April meeting.
|  |  | RAN1: UL Reference Signals for NR Positioning | Yes | ★ | There are still some remaining issues to be discussed: Issue 1: Collision rule of UL SRS for positioning with PUSCH Issue 2: MAC CE update of spatial relation info for SRS for positioning. Status: These issues were discussed in RAN1#100e meeting, however, no consensus was achieved. Comments: The remaining issues are performance enhancement and optimization, which have trivial impact on objective deployment and implementation. Besides, according to the good progress of RAN1#100e meeting, the remaining issues are highly possible to be finished during the next April meeting
|  | Define UE measurements based on DL reference signals applicable for NR positioning. The following UE measurements are specified for serving, reference, and neighboring cells [RAN1] ○ DL RSTD (reference signal time difference) measurements for NR positioning ○ DL RSRP (reference signal received power) measurements for NR positioning ○ UE RX-TX time difference measurements for NR positioning Define gNB measurements based on UL reference signals applicable for NR positioning. The following gNB measurements are specified [RAN1]: ○ UL RTOA (relative time of arrival) measurements for NR positioning ○ UL Angle of Arrival (AoA) measurements (including Azimuth and Zenith Angles) for NR positioning ○ UL RSRP (reference signal received power) measurements for NR positioning ○ gNB RX-TX time difference measurements for NR positioning | RAN1: UE and gNB measurements for NR Positioning | Yes | Finished | RAN1 has completed this subagenda. There is no remaining/open issues and the objectives are met.
|  | If necessary, define physical-layer procedures to support UE/gNB measurements for NR positioning [RAN1] | RAN1: Necessity and details for physical-layer procedures to support UE/gNB measurements | Yes | Finished | RAN1 has completed this subagenda. There is no remaining/open issues and the objectives are met.
|  | RAN2 centric objectives - Define functional interfaces, signaling and procedures including UE reporting, to support NR RAT-dependent positioning for the NR positioning techniques listed in RAN1 objectives [RAN2] - Define extensions of LPP protocol for NR RAT-dependent positioning [RAN2] - Define extensions of LPP protocol to support GNSS SSR (PPP-RTK support) based on the “Compact SSR” definitions specified for QZSS for both LTE and NR[RAN2] ○ Note: Both, PPP and RTK, are already supported in Rel-15 LPP. The extensions are for PPP-RTK which requires additional info in Rel-16. - Study and, if agreed, specify system level aspects of the DL-only UE based positioning [RAN2] RAN2 + RAN3 centric objectives - Resolve open aspects on architecture and proceed with normative work for the following items [RAN2/RAN3]: ○ Location of the transmission measurement function - Define signaling for broadcast assistance data delivery [RAN2/RAN3/SA2/SA3] | RAN2:Define functional interfaces, signaling and procedures including UE reporting, to support NR RAT-dependent positioning for the NR positioning techniques listed in RAN1 objectives | Yes | ★ | Issue 1:FFS if we take steps to reduce the duplicate configuration between RRC and LPP for methods involving both DL and LPP for methods involving both DL and UL measurements. Issue 2:FFS Aperiodic and Spatial Relations
|  |  | RAN2:Define extensions of LPP protocol for NR RAT-dependent positioning | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:Define extensions of LPP protocol to support GNSS SSR (PPP-RTK support) based on the “Compact SSR” definitions specified for QZSS for both LTE and NR | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:Study and, if agreed, specify system level aspects of the DL-only UE based positioning | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:Resolve open aspects on architecture and proceed with normative work for the following items RAN2/RAN3:Location of the transmission measurement function. Define signaling for broadcast assistance data delivery | Yes | ★ | Issue 1:RAN2 is waiting for RAN4's input on the range and granularity of some parameters like measurement quantities. The procedure of parameter type definition in 36.331/38.331 would be affected.
|  | RAN4 centric objectives -Define corresponding core requirements for NR positioning [RAN4] | RAN4: RRM core requirements(UE) | Yes | ★★★ | Issue 1: Definition of intra-frequency and inter-frequency RSTD measurements Issue 2: PRS-RSTD report mapping table, measurement period, reporting criteria, reporting capability and side conditions. Issue 3: PRS-RSRP report mapping table, reporting criteria, reporting capability and side conditions Issue 4: UE Rx-Tx time difference report mapping table, accuracy requirements, Proximity of SRS and PRS, reporting criteria and reporting capability A lot of issues are still open. Report mapping tables also impact RAN2. Due to the high workload and open issues, it is chanllenging to complete the work in Q2.
|  |  | RAN4: gNB requirements | Yes | ★★★ | Issue 1: Whether to define accuracy requirements for UL RTOA and/or AoA/ZoA gNB measurements Issue 2: Detailed conditions and scenarios for gNB accuracy requirements Issue 3: Reporting mapping for SRS-RSRP, NB Tx-Tx time difference, UL RTOA and AoA/ZoA Issue 4: Optionality of gNB accuracy requirement A lot of issues are still open. RAN4 provide initial agreements of the report mapping table to RAN2 in RAN4#94e, further input to RAN2 on the mappting table is still needed. it is chanllenging to complete the work in Q2.

## Power Saving
Leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Open issues
RAN1 | Power Saving | 1) Specify power saving techniques with PDCCH-based power saving signal/channel triggering UE adaptation in RRC_CONNECTED mode [RAN1, RAN2, RAN4] a) Specify procedures triggering a MAC entity to “wake up” to monitor PDCCH at reception of the PDCCH-based power saving signal/channel for the next occurrence(s) of the drx-onDurationTimer [RAN2, RAN1] NOTE: Any change of PDCCH channel coding and payload interleaver is not in the scope b) Specify the procedure of cross-slot scheduling power saving techniques [RAN1, RAN4] | RAN1: PDCCH-based power saving signals/channel | Yes | ★ | Issue 1: Values of minimum time gap
|  |  | RAN1: Procedure of cross-slot scheduling power saving techniques | Yes | ★ | Issue 1: Whether and how to apply the minimum scheduling offset restriction to all configured BWPs (including active and inactive ones) Issue 2: Whether and how to decide the applied minimum scheduling offset restriction for the slots after BWP switch and before the application delay is ended
|  |  | RAN2: PDCCH-based power saving signals/channel | Yes | ★ | Issue 1:FFS what the UE actually monitors if it misses DCP when configured with SCell dormancy Issue 2:FFS UE behavior when a DCP occasion occurs during RAR window will be decided at the next meeting
|  |  | RAN4: RRM core requirements | Yes | ★★ | Issue 1. Scaling factor of measurement interval for RRM relaxation is open Issue 2. RRM measurement relaxation for inter-frequency layer with higher priority is open Issue 3. transition period between different scenario Issue 4. EMR impact Issue 5. RRM impact due to cross-slot scheduling Issue 6. reducing the number of frequency layers are still open
|  | 2) Specify the power saving techniques of UE adaptation to the maximum number of MIMO layers [RAN1, RAN2, RAN4] a) Specify configuration of a different MIMO layer configuration of the initial/default BWP compared with other BWPs of a Serving Cell. [RAN2, RAN4] i) Discuss whether to also extend this to define per-BWP MIMO layer configuration [RAN1, RAN2] b) Evaluate if switching and interruption times for UE dynamic adaptation to the maximum number of MIMO layers are needed and which case assuming a relationship between the number of RF ports and the MIMO layer configuration [RAN4] NOTE: Switching on/off the RF is part of the evaluation | RAN1: UE adaptation to maximum number of MIMO layers | Yes | Finished
|  |  | RAN2:MIMO layer adaptation | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN4: switching and interruption time | Yes | Finished | No open issues
|  | 3) Specify a mechanism for a UE to indicate its preference of transitioning out of RRC_CONNECTED state. [RAN2] | RAN2:Efficient transition from RRC_CONNECTED to RRC_IDLE/RRC_INACTIVE | Yes | ★ | Main function complete, waiting for ASN.1 review
|  | 4) Specify, if agreed, the mechanism to provide UE assistance information [RAN2, RAN1]: - Study and select among the following UE assistance information for RAN2 by RAN#85: power preferred information (baseline LTE PPI in a well-defined manner) and UE's preference on C-DRX, BWP and SCell configuration [RAN2]. NOTE: additional UE assistance information for RAN1-specific power saving techniques to indicate what setting of parameters related to this Work Item will lead to power savings for the UE can be included if agreed in RAN1. | RAN2:UE assistance information | Yes | ★ | Issue 1:FFS if UAI can also be reported for power saving directly via SRB3 if configured. FFS on the signalling details.
|  | 5) Specify network-configured mechanism to relax intra and inter-frequency RRM measurement for neighbour cells for RRC_IDLE/INACTIVE with minimal mobility performance impacts [RAN2, RAN4] a) Specify RRM measurement relaxation by allowing measurements with longer intervals, and/or by reducing the number of cells/carriers to be measured [RAN4, RAN2] b) Define triggering criteria for the UE to move between relaxed and normal RRM measurements, that considers at least if UE is not at cell edge, or if UE is stationary or with low mobility [RAN2, RAN4]. i) Evaluate and specify requirements (if needed) depending on RAN2 criteria [ RAN4] NOTE: No new measurement quantities should be introduced | RAN2:RRM measurement relaxation 1)Measurement relaxation for low mobility and not-at-cell-edge UEs | Yes | ★ | Issue 1:RAN2 is waiting for RAN4's input on whether the measurement relaxation for high priority frequency indicated by highPriorityMeasRelax is controlled by the triggering criteria for measurement relaxation.
|  |  | RAN2:RRM measurement relaxation 2)Measurement relaxation for reducing number of carriers or frequencies | Yes | ★ | Issue 1:RAN4 didn't reach consensus on the benefit for reducing the number of carriers. RAN2 will not specify anything.

## URLLC
leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Comments(open issues)
RAN1 | Physical Layer Enhancements for NR URLLC | • Specification of PDCCH enhancements [RAN1] o DCI format(s) with configurable sizes for some fields, with a minimum DCI size targeting a reduction of 10~16 bits relative to Rel-15 DCI format 0_0/1_0 and a maximum DCI size that can be larger than Rel-15 DCI format 0_0/1_0, and provide the possibility to align with the size of the DCI format 0_0/1_0 (including possible zero padding if any) o Increased PDCCH monitoring capability on at least the maximum number of non-overlapped CCEs per slot for channel estimation for at least one SCS subject to restrictions including, but not necessary limited to, those identified in TR 38.824. Enhancements for PDCCH monitoring capability on the maximum number of monitored PDCCH candidates per slot (with potential restrictions) can be further considered. | RAN1: PDCCH enhancements | Yes | ★★ | Issue 1: Remaining issues on DCI format: (a)Remaining issues on DCI size alignment Issue 2: Remaining issues on PDCCH candidate overbooking and dropping: (a)Remaining issues on span based PDCCH candidate overbooking and dropping Issue 3: Remaining issue on enhanced PDCCH monitoring capability: (a)Scaling PDCCH monitoring capability if the number of CCs configured is larger than the reported capability for span non-aligned case Issue 4: Remaining issues on BD/CCE limit per span. (a) CCE limit for the combinations (2, 2) (4, 3) with 15kHz and 30kHz (b) BD limit for the combinations (2, 2) (4, 3) (7, 3) with 15kHz and 30kHz (c) The limit on the number of CCs to be supported with R16 UE capability Status: The first three set of critical issues as proposed by FL was discussed in February meeting, i.e., DCI format, PDCCH candidate overbooking and dropping, and enhanced PDCCH monitoring capability, and most of the critical issues have been addressed in the email discussions. According to the progress of email discussions, some bullets have achieved agreements/work assumptions and been captured in TPs, while other bullets leave several options or alternatives to be selected and cannot be comprised , such as DCI size alignment, span based PDCCH candidate overbooking and dropping. In addition, whether/how to do further optimization for non-aligned spans case on enhanced PDCCH monitoring capability still needs to be FFS. There are also some critical issues haven't been discussed yet in Feb e-meeting, e.g, remaining issues on BD/CCE limit per span. Comments: It seems to be very time-consuming for above remaining critical issues, and they are expected to be further discussed and solved in the next two meetings. However, it is possible to finish the remaining issues before June.
|  | • Specification of UCI enhancements [RAN1] o More than one PUCCH for HARQ-ACK transmission within a slot o At least two HARQ-ACK codebooks simultaneously constructed, intended for supporting different service types for a UE | RAN1: UCI enhancements | Yes | ★★ | Issue 1: issues which are discussed in RAN1 #100e but no consensus was reached, i.e. a) the priority of A-SRS b) Type-1 HARQ-ACK codebook book construction in case both DCI format 1_1 and 1_2 are configured. Issue 2: other issues which have not been discussed in RAN1 #100e a) intra-UE collision handling related issue, i.e. cancelation timeline, WA for high-priority SR/PUSCH collision, more than one PUCCH carrying HARQ-ACK overlapping with a PUSCH or another PUCCH with the same priority... b) PHY priority related issues, i.e. WA for PHY priority indication in DCI... c) sub-slot related issues, i.e. Clarifications for applicability of sub-slot to other UCIs... d) others, i.e. PUCCH resource determination for reduced size of PRI field... In February e-meeting, issues which may have RAN2 impacts and earier to reach consensus were discussed and relative good progress is made except the discussion of priority of A-SRS and type-1 HARQ-ACK codebook construction in case both DCI format 1_1 and 1_2 are configured. There are still some critical issues to be discussed as listed above and considering the complexity of intra-UE collision handling related issue, it is assumed that the feature design would last two meetings.
|  | • Specification of PUSCH enhancements for both grant-based PUSCH and configured grant based PUSCH [RAN1] o For a transport block, one dynamic UL grant or one configured grant schedules two or more PUSCH repetitions that can be in one slot, or across slot boundary in consecutive available slots | RAN1: PUSCH enhancements | Yes | ★ | Issue 1: PUSCH repetition Type B transmission collision with resource other than DL/UL, including SSB, CORESET #0 in MIB, PRACH and behavior for half-duplex CA Issue 2: UCI multiplexing on PUSCH for PUSCH repetition type B Issue 3: Power control issue for PUSCH repetition type B In February e-meeting, good progress has been achieved on finalizing remaining open points on RRC parameters, determining frequency hopping, interactions with DL/UL directions and handling of orphan symbols for PUSCH repetition type B. The remaining issues are still fundamental for URLLC framework, yet according to the current progress, major part of the remaining issues are highly possible to be finished in the next meeting and the feature can be finished by June.
|  | • Specification of enhancements to scheduling/HARQ [RAN1] o Out-of-order HARQ-ACK associated with PDSCHs with different HARQ process IDs o Out-of-order PUSCH scheduling associated with different HARQ process IDs, including overlapping PUSCHs and non-overlapping PUSCHs in time-domain o Methods to handle DL data/data resource conflicts for overlapping PDSCHs in time-domain, scheduled by dynamic DL assignments | RAN1: Enhancements to scheduling/HARQ | Yes | ★★ | Issue 1: if overlapping PUCCHs carrying HARQ-ACK with different priorities scheduling is supported. This issue has been widely discussed via RAN1 #99 email discussion but no consensus was reached. In February no email discussion is assigned according to FL suggestion that it is a bit difficult to come to conclusion through email discussion. Although much debate is conducted on this issue, we think it can be finished before June considering that this is the only one remaining issue.
|  | • Specification of enhanced inter UE Tx prioritization/multiplexing [RAN1] o UL cancelation scheme (see section 7.2.1 in TR 38.824) o Enhanced UL power control scheme (see section 7.2.2 in TR 38.824) | RAN1: Enhanced inter UE Tx prioritization/multiplexing | Yes | ★★ | Issue 1: RRC parameters: - Up to X BDs can be configured per UL CI monitoring occasion, X to be decided between X=1 or X=2 in RAN1#100bis; - FFS The UE is not expected to be configured with a time duration for CI less than the time different (in symbols) between any adjacent monitoring occasions in a slot Issue 2: UE behavious: - A UL channel with which priority level can be cancelled by UL CI? - UE behaviour in case of simultaneous UL prioritization/multiplexing for intra-UE and inter-UE cancellation - Whether another UL transmission can be scheduled in non-pre-empted resource - scheduling and cancellation at the same time Issue 3: Text proposals In February e-meeting, good progress was made, leaving some details to be finalized in the next meeting. Some of the current remaining issues are fundamental, including RRC parameter and UE behaviour, without agreements the URLLC framework cannot work well. According to the good progress of discussion in February emeeting, critical issues in this feature are highly possible to be finished within two meetings.
|  | • Specification of enhanced UL configured grant transmission [RAN1, RAN2] o Multiple active configured grant type 1 and type 2 configurations for a given BWP of a serving cell  Note: V2X use cases are also considered | RAN1: Enhanced UL configured grant transmission | Yes | ★ | Issue 1: DMRS configuration for Type 2 CG activated by DCI format 0_2 Issue 2: Agreements not captured in spec In February e-meeting, good progress was made, leaving some details to be finalized in the future meeting, i.e. the first issue is highly related with PDCCH discussion and postpone to the next meeting, which seems essential without agreements URLLC framework cannot work well. According to the good progress of discussion in February emeeting, we think this feature can be finished within one meeting.

## V2X
Leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Open issues
RAN1 | 5G V2X with NR sidelink | 1. NR sidelink: Specify NR sidelink solutions necessary to support sidelink unicast, sidelink groupcast, and sidelink broadcast for V2X services, considering in-network coverage, out-of-network coverage, and partial network coverage.  Support of sidelink signals, channels, bandwidth part, and resource pools [RAN1, RAN2] | RAN1: Physical layer structure | Yes | ★★ | Issue 1: FFS of TBS determination for PSSCH Issue 2: FFS of Resource pool configuration Issue 3: Initial value of scrambling sequence Issue 4: Details of SCI related aspects, including SCI format 0-1 and SCI format 0-2 Issue 5: MCS table determination Issue 6: Frequency-domain OCC of PSCCH Issue 7: Resource mapping of SL CSI-RS and SL PT-RS Issue 8: BWP related aspects Status: The first 2 issues were discussed in RAN1#100e meeting, however, the proposals are either proposed as working assumption or left with FFS, which are behind the schedule. Comments: For the remaining 6 issues and FFS points listed above, such as the initial value of scrambling sequence, CRC length of SCI format 0-2, and MCS table determination, etc., are all very fundamental and important, without agreements and solutions the whole V2X framework cannot work. Note that for issues such as the intial value of scrambling sequence, there are some NR design bases, if companies are willing to follow the NR design principle as baseline and compromise due to the tight schedule and heavy workload, it is still possible to finish the PHY structure remaining issues with the next 2 meetings.
|  |  Resource allocation [RAN1, RAN2]  Mode 1  NR sidelink scheduling by NR Uu and LTE Uu as per the study outcome  Mode 2  Sensing and resource selection procedures based on sidelink pre-configuration and configuration by NR Uu and LTE Uu as per the study outcome  Support for simultaneous configuration of Mode 1 and Mode 2 for a UE  Transmitter UE operation in this configuration is to be discussed after the design of mode 1 only and mode 2 only.  Receiver UE can receive the transmissions without knowing the resource allocation mode used by the transmitter UE.  UE relaying resource pool configuration or resource configuration is not supported in this work in Rel-16. | RAN1: Mode-1 resource allocation | Yes | ★★ | Issue 1: DCI aspects: a) DCI contents: i. Sizes of the existing fields. ii. Additional fields. iii. Assign one combination of “timing and resource for PUCCH” to indicate that PUCCH resource is not provided (to implement an existing agreement). iv. Indication of activation/release for a SL configured grant type-2 b) Alignment of DCI formats i. Alignment of format 3_0 for dynamic grant and configured grant type-2. ii. Alignment of format 3_0 to other DCI formats. Issue 2: HARQ reporting to gNB a) HARQ-ACK codebook design including type-1 HARQ codebook and type-2 HARQ codebook b) Collisions with Uu HARQ-ACK reports c) Details for transmission of HARQ-ACK reports on PUSCH Issue 2: Processing times: a) PSCCH/PSSCH preparation time. b) HARQ-ACK reporting to gNB. Status: Issues which were may have RAN2 impacts or easier to reach agreements via email discussions are selected as critical issues in RAN1#100e meeting. Relatively good progress has been made while leaving some FFS to discuss next meeting. Comments: Almost all the current remaining issues are very fundamental and important, without agreements and solutions the whole V2X framework cannot work. Some of the remaining issues are complicated, i.e. the HARQ-ACK codebook construction and it may be difficult to reach agreements via e-meetings. So it is a little risky to finish all features two e-meetings. If companies are constructive with appropriate compromise, it would be of high possibility to finish mode-1 design before June.
|  |  | RAN1: Mode-2 resource allocation | Yes | ★★★ | Issue 1: SCI aspects: a) Resource index signalling (backward signalling) b) Period values used for exclusion once SCI received: actual or all configured Issue 2: Processing times: a) Tproc,0 b) Tproc,1 c) T0 d) T3 Issue 3: Remaining details for resource allocation including pre-emption, (re)evaluation, (re)selection and so on: a) FFSs in RAN1 #100-e meetings b) Re-selection triggers c) Maximum RSRP threshold d) X% ratio configurability (20% in brackets) e) Handling of reserved but unused resources (PSFCH monitoring, different RSRP thresholds, etc.) f) Prioritization of earlier in time resources for selection g) Handling of parallel selection processes Status: In February e-meeting, issues which were may have RAN2 impacts or easier to reach agreements via email discussions are selected as critical issues in RAN1#100e meeting. According to the current progress of RAN1#100e meeting, it is heavily behind the schedule. For the pre-emption and re-evaluation issue, the proposals are still under discussion and not stable untill Wednesday, many FFSs were left to discuss next meeting. For SCI related aspects, some agreements were reached while for other indications, company views were controversial and further study is needed. Comments: Most of the current remaining issues are fundamental, i.e. the processing times, SCI contents and the necessary details for resource (re)selection, without agreements and solutions the whole V2X framework cannot work. While there also exists some features to be enhancement, i.e. the pre-emption, the resource index, handling of reserved but unused resources… these are not essential to some extend and just to guarantee better work of V2X. According to the previous progress of this agenda, it is possible to complete mode-2 design with giving up some features for enhancement or allocationg more email threads.
|  |  Sidelink synchronization mechanism as per the study outcome [RAN1, RAN2]  Procedures selecting synchronization reference  S-SSB and procedures to transmit and receive it, including when GNSS and gNB/eNB are unavailable  Use of RS for sidelink synchronization if specification impact is identified | RAN1:Synchronization mechanism | Yes | ★★ | Issue 1: PSBCH payload size and content, including details on indication of TDD configuration, and indicaiton of S-SSB index or slot number Issue 2: DM-RS sequence initialization for PSBCH Issue 3: Details on S-SSB transmission power control Issue 4: Limitation on the S-SSB interval Issue 5: Resource sets for S-SSB transmission Issue 6: QCL for S-SSB transmission a) Whether/how to define QCL for S-SSB transmission Issue 7: Synchronization to multiple sources Issue 8: PSBCH rate matching for ECP a) Correction on number of coded bits for S-SSB rate matching Status: In RAN1 #100e meeting, the first 3 issues were discussed and good progress was made, leaving some details to be finalized in the next meeting. Comments: Some of the current remaining issues are fundamental, including PSBCH content and DMRS initialization, S-SSB power control details and S-SSB transmission resource limitation/configuration, without agreements the whole V2X framework cannot work. While there are other enhancements, e.g., QCL for S-SSB transmission, synchronization to multiple sources, etc, which are not so essential to some extent. According to the good progress of discussion in February emeeting, critical issues in sidelink synchronization are highly possible to be finished within two meetings.
|  |  Solutions for ‘not co-channel’ in-device coexistence between LTE and NR sidelinks  TDM-based solutions as per the study outcome [RAN1, RAN2, RAN4]  FDM-based solutions with static power allocation as per the study outcome [RAN4]  This will not consider the case where LTE and NR sidelinks are in the same frequency band.  No impact to LTE specifications at least from RAN1 and RAN2 perspective. | RAN1: In-device coexistence between LTE and NR sidelinks | Yes | ★ | Issue 1: the priority indicated by the SCI is used in the prioritization rules for in-device coexistence. As this issue is simple to resolve and seems to be a general understanding, it can be easily resolved within one meeting.
|  |  Sidelink physical layer procedures as per the study outcome  HARQ procedures [RAN1, RAN2]  CSI acquisition for unicast [RAN1]  CQI/RI reporting is supported and they are always reported together. No PMI reporting is supported in this work. Multi-rank PSSCH transmission is supported up to two antenna ports.  In sidelink, CSI is delivered using PSSCH (including PSSCH containing CSI only) using the resource allocation procedure for data transmission.  Power control [RAN1, RAN2] | RAN1: Physical layer Procedure | Yes | ★★ | Issue 1: Power control formula for PSCCH/PSSCH/PSFCH a) Multiple PSFCH TXs and PSD of each PSFCH Issue 2: Indicate GC HARQ feedback Option 1/2 to RX UE Issue 3: Groupcast HARQ: whether/how to handle the case when the location information is not available at TX UE and/or RX UE Issue 4: Handling SL and UL transmissions a)How to define priority of UL transmission and SL transmission b)When to prioritize which TX in case of simultaneous TXs of UL and SL Issue 5: SL CSI a)How to configure a latency bound for SL CSI reporting MAC CE b)How to define SL CSI reference resource c)How to configure CQI table used for CSI reporting Status: According to the progress after RAN1 #100 emeeting, some issues are still not compromised in the email discussions, e.g., multiple PSFCH TXs and PSD of each PSFCH, indicating GC HARQ feedback Option 1/2, etc. In addition, RAN1 assumes RAN2 will handle selection of appropriate groupcast HARQ feedback option as well as the case the RX UE’s location is not available, which needs to send an LS to RAN2. The other two issues about handling SL and UL transmission, and SL CSI are not included in the email discussion at RAN1 #100-e. Comments: There are still some remaining issues to be addressed, and some critical issues are not compromised in RAN1 #100-e. If companies are constuctive and not introducing new features, it is possilble to finished this feature within two meetings before June
|  |  Congestion control [RAN1, RAN2] Specify support for QoS management [RAN2, RAN3, RAN1] | RAN1: QoS management | Yes | ★ | Issue 1: Sidelink Congestion Control a) CR – in future window, leave out resources reserved, but then released due to HARQ feedback b) Semi-persistent resource reservation disabled by congestion control Issue 2: TX Parameter restriction based on speed a) TX Power restriction based on speed Status: Some issues related to sidelink congestion control issue are addressed in email discussions in RAN1 #100-e, including constraints on past/future window in CR evaluation，when CR_limit is applied，congestion control processing time and physical/logical slots, and agreements have been achieved. Other details needs to be further discussed. Comments: Only detailed issues are remained, and it should be okay to be finished in the next meeting.
|  | 2. Specify support for NR Uu to provide control for LTE sidelink  Sidelink mode 4 as per the study outcome [RAN2, RAN1]; and  Sidelink mode 3-like RRC-configured SPS scheduling with either RRC-based activation/deactivation as per the study outcome or DCI-based activation/deactivation [RAN1, RAN2].  RAN1 to make a decision on which option is supported until RAN#84. | RAN1: NR Uu control LTE sidelink | Yes | ★ | Issue 1: DCI format size. Status: In February e-meeting, 3 issues (timing, DCI format size, the value of X) were discussed and good progress was made, leaving some details to be finalized in the next meeting, i.e.which NR Uu DCI size to match DCI format 3_1 with, this topic is widely discussed in RAN1 #100e meeting and some progress has been made, this is highly related to the design of DCI format 3_0 and once the size of DCI 3_0 is finalized, the discussion can be automatically settled. Comments: This issue is fundamental and important, without agreements and solutions the feature for NR Uu control LTE sidelink cannot well work. According to the previous progress of this agenda, it is of high probability to complete the feature design.
|  |  Sidelink L2/L3 protocols and signalling  Support of sidelink transmission and reception in RRC, MAC, RLC, PDCP, and SDAP [RAN2]  AS level link management for unicast [RAN2, RAN1]  Define the criteria of PC5 availability/unavailability for unicast based on this functionality. | RAN2:Control Plane &6.4.3 User Plane | Yes | ★★ | open issues:  Issues on HARQ for NR V2X sidelink communication:  RAN2 needs to close the remaining issues on HARQ operation based on RAN1 #100-e agreements.  Issues on security for NR V2X Sidelink communication:  RAN2 needs to finish the remaining security issues based on the results of the next SA3 meeting.
|  | 3. Specify UE report to assist gNB scheduling [RAN2, RAN1] | RAN2:User plane | Yes | Finished | no open issues
|  | • UE Tx and Rx RF requirement [RAN4]  -This requirement should ensure  -coexistence between sidelink and Uu interface in the same and adjacent channels in licensed spectrum  -coexistence with other V2X technologies in the adjacent channel in ITS spectrum in 5.9 GHz, without assuming that 5.9 GHz spectrum will be universally available nor that it will be universally available in sufficient quantity to support NR V2X advanced use cases  | RAN4: co-existence study | Yes | ★★★ | Issue 1: co-existence study between NR V2X UE and LTE BS when NR V2X UE and LTE BS both operating in FR1 licensed bands Issue 2: co-existence study between NR V2X UE and NR BS when NR V2X UE and NR BS both operating in FR2 licensed bands Based on the agreed priority for RAN4 operating scenarios, all these open issues are not high priority. Downscoping seems necessary in order to complete the work in Q2.
|  |  | RAN4: system parameters | Yes | ★★ | Issue 1:introducing Band and channel bandwidth for NR V2X and 30MHz issue for NR V2X licensed band n38. If the licensed band is introduced for SL operation with the non-V2X service in the same licensed band, then at least two meetings are needed to specify the mechanisim of the sychronization operation. Issue 2:the impact on BS side and whether to introduce CR on system parameters for NR V2X in TS 38.104
|  |  | RAN4: UE TX RF requirements | Yes | ★★★ | Issue 1:MPR/A-MPR for each transmitted channel, including simultaneous PSFCH transmission, S-SSB transmission, and detail MPR/A-MPR requirements for PSSCH/PSCCH Issue 2: A-SEM requirements according to regional regulations. Issue 3.switching period relative requirements such as the switch postion, switching period, transmit off during the switching period for intra and inter con-current operation Issue 4: other issues such as the MPR/A-MPR for PC2 UE, SL-MIMO It is challenging to complete the work in Q2 and extensive simulations are still needed
|  |  | RAN4: UE RX RF requirements | Yes | ★ | Issue 1: REFSENS requirements Issue 2: maxinmum input level
|  | • RRM core requirement [RAN4] | RAN4: RRM core requirements | Yes | ★ | Issue 1: Terminology ‘S-RSRP’ vs ‘PSBCH-RSRP’ and ‘V2X’ vs ‘SideLink’ Issue 2: Measurement related-Core requirement  -Whether to define or not RRM requirement in case that V2X UE can schedule data on both Uu and SL for SL+Uu band combination Issue 3: Interruption requirements for the scenarios  -SL UE is switching between LTE SL and NR SL  -SL UE is changing its sync source from GNSS to a syncRef UE that is synchronized to GNSS directly or in-directly  -SL UE is changing its sync source from gNB to eNB or eNB to gNB
|  | Network solutions to support NR sidelink  V2X service authorization [RAN3]  F1 signalling for support of NR V2X [RAN3]  Resource coordination between NG-RAN nodes for V2X sidelink communication, taking into consideration previous RAN3 discussions [RAN3] | RAN3: Authorization / UE Sidelink AMBR / PC5 QoS Parameters | Yes | Finished
|  |  | RAN3: V2X support over F1 | Yes | ★ | Issue 1：F1 signalling design on sidelink resource request and resource allocation  - The way of transmission of the sidelink resource request from CU to DU  - Parameters on the SL DRB setup/modification/release, Parameters on sidelink QoS  - Parameters on V2X SIBs
|  |  | RAN3: Resource Coordination | Yes | ★ | Issue 1：Investigate more how the exchange of V2X configuration is beneficial for mobility
|  |  | RAN3: Alternative QoS | Yes | ★ | Issue 1：Remaining issues on how to support alternative QoS profiles and the corresponding CRs  - QoS parameters to be included in alternative QoS profiles  - The limit of the number of alternative QoS profiles  - Alternative profile in handover case

## 2-step RACH
Leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Open issues
RAN1 | 2-step RACH | 2-step RACH [RAN1, RAN2] - 2-step RACH shall be able operate regardless of whether the UE has valid TA or not. - 2-step RACH is applicable to any cell size supported in Rel-15 NR; - 2-step RACH is applied for RRC_INACTIVE , RRC_CONNECTED and RRC_IDLE state - Specify contention-based 2-step RACH procedure (RAN2) - Specify contention-free 2-step RACH procedure (dedicated preamble and dedicated PUSCH) for handover (RAN2) o RAN1 work addresses only CBRA (i.e. not considering CFRA) - Channel structure of msgA is Preamble and PUSCH carrying payload (RAN1) o Only reuse the Rel-15 NR PRACH Preambles design. o Only reuse the Rel-15 NR PUSCH including Rel-15 DMRS for transmission of payload of msgA  No new CP length and no sub-PRB guard subcarrier(s) Note 1: The above sub-bullet is to ensure that signal structure optimizations for any specific cell size (e.g. cells with RTT larger than Rel-15 PUSCH CP duration) are not pursued. o Specify the mapping between the PRACH preamble and the time-frequency resource of PUSCH in msgA+ DMRS  PRACH Preamble and PUSCH in a msgA is TDMed o Specify the supported MCS(s) and time-frequency resource size(s) of PUSCH in msgA  Consider the msgA payload contents determined by RAN2 o Specify power control of PUSCH of msgA - Specify msgA’s content: to include the equivalent contents of msg3 of 4-step RACH (RAN2/RAN1) o Inclusion of UCI in msgA is not precluded - Specify msgB’s content: to include the equivalent contents of msg2 and msg4 of 4-step RACH (RAN1/RAN2) - Contention resolution for 2-step RACH (RAN2) - Design of RNTI for msgB of 2-step RACH (RAN2) - Specify the fall back procedure from 2-step RACH to 4-step RACH (RAN2/RAN1) - All triggers for Rel-15 NR 4-step RACH are applied for 2-step RACH (this includes triggers for SI Request and BFR as agreed by RAN2) o No new triggers for 2 step RACH o Contention-free 2 step RACH is only supported for the handover case For unlicensed operation: - After PRACH and PUSCH design enhancements are completed for NR-U in the Rel-16 NR-U WI, identify and specify the necessary modification of 2-step RACH design for its application in NR-U(RAN1/RAN2) Note 2: UP data transmission in RRC_IDLE and RRC_INACTIVE state is not in the scope. UP data transmission in RRC_CONNECTED mode as in Rel-15 NR is supported. Note 3: The work on contention-free 2-step RACH procedure is of lower priority and should be pursued in RAN2 only if there is time. | RAN1: Channel Structure for Two-Step RACH | Yes | ★ | Issue 1: msgA PRACH configurations and validation • Long PRACH preamble supported for 2-step RACH in shared spectrum (to be discuss in April, based on RAN2 LS, should be easy) Issue 2: msgA PUSCH configurations and validation • MsgA PUSCH configuration for CFRA (to be discuss in April, based on RAN2 LS)
|  |  | RAN1: Procedure for Two-step RACH | Yes | ★ | Issue 1: Interpretation of 2bits LSB of SFN and the corresponding descriptions • Capture the related description of the 2bits LSB of SFN in 38.212 and 213 (to be discuss in April, based on RAN2 LS, should be easy) Issue 2: Miscellaneous issues for msgB, power control and CFRA • Content of UL grant in MsgB for UE with C-RNTI (to be discuss in April) • CSI-RS based CFRA (to be discuss in April, based on RAN2 LS, should be easy) • Tx beam of msgB PDCCH and PDSCH (to be discuss in April, based on RAN2 LS, should be easy) • Reference point of msgB monitering window in case of preamble-only transmission (to be discuss in April, based on RAN2 LS)
|  |  | RAN2:contention-based 2-step RACH procedure (RAN2) | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:contention-free 2-step RACH procedure (dedicated preamble and dedicated PUSCH) for handover (RAN2) | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:Specify msgA’s content: to include the equivalent contents of msg3 of 4-step RACH (RAN2/RAN1) | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:Specify msgB’s content: to include the equivalent contents of msg2 and msg4 of 4-step RACH (RAN1/RAN2) | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:Contention resolution for 2-step RACH (RAN2) | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:Design of RNTI for msgB of 2-step RACH (RAN2) | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:Specify the fall back procedure from 2-step RACH to 4-step RACH (RAN2/RAN1) | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:Triggers for 2-step RA | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:For unlicensed operation: After PRACH and PUSCH design enhancements are completed for NR-U in the Rel-16 NR-U WI, identify and specify the necessary modification of 2-step RACH design for its application in NR-U(RAN1/RAN2) | Yes | ★ | Issue 1:RAN2 send a LS to RAN1 to ask whether the newly introduced NR-U PRACH root sequences (of length 571 and 1151) are applicable to 2-step RA.If 2-step RA shall support the newly introduced NR-U PRACH root sequences as for the current 4-step RRC configuration, then it needs to be explicitly configurable for 2-step RA.

## IAB
Leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Open issues
RAN2 | Integrated Access and Backhaul for NR | Specification of SSB/RMSI periodicity for NR initial access assumed by an IAB-node | RAN1: SSB/RMSI periodicity for NR initial access | Yes | Finished | RAN1 has completed this subagenda. There is no remaining/open issues and the objectives are met.
|  | Specification of extensions to Rel. 15 to support the use of SSBs orthogonal to SSBs used for UEs (via TDM and/or FDM), for inter-IAB-node discovery and measurements, including additional SMTC periodicities and time-domain mapping of SSB locations (e.g. enable muting patterns to deal with half-duplex constraint). | RAN1: Extensions of SSBs for inter-IAB-node discovery and measurements | Yes | Finished | RAN1 has completed this subagenda. There is no remaining/open issues and the objectives are met.
|  | Specification of extension of RACH occasions and periodicities for backhaul RACH resources. w.r.t. access RACH resources, and associated network coordination mechanisms for selection of such parameters (in order to orthogonalize access and BH due to the half-duplex constraints) | RAN1: Extension of RACH occasions and periodicities for backhaul RACH resources | Yes | Finished | RAN1 has completed this subagenda. There is no remaining/open issues and the objectives are met.
|  | Specification of mechanisms for resource multiplexing among backhaul and access links. This includes: o Specification of semi-static configuration for IAB-node/IAB-donor DU resources in case of TDM operation subject to half-duplex constraint. This shall be forward compatible to allow the support of half-duplex scenarios with FDM and SDM resource sharing among backhaul and access links. o Specification of time resource types for the DU’s child links: DL hard, DL soft, UL hard, UL soft, Flexible hard, Flexible soft, Not Available o Specification of dynamic indication (L1 signalling) of the availability of soft resources for a child IAB-node DU o Specification of required transmission/reception rules for IAB-nodes and associated behaviours regarding time resource utilization as discussed in TR 38.874 clause 7.3.3. | RAN1: Mechanisms for resource multiplexing among backhaul and access links | Yes | ★ | There is only one remaining issue: Issue 1: The DU resource configuration for paired spectrum. Comments: This issue is important, without agreements the IAB node operation in paired spectrum is not complete and clearly defined. According to the good progress of discussion in RAN1#100e meeting, this critical issue is highly possible to be finished by the next April meeting.
|  | Specification of mechanism to support the “case-1” OTA timing alignment | RAN1: Mechanism to support the “case-1” OTA timing alignment | Yes | Finished | RAN1 has completed this subagenda. There is no remaining/open issues and the objectives are met.
|  | Specify core requirements associated with the items specified by RAN1 (RAN4) -Specify RRM requirements -Identify impact on RF requirements for reduced PAPR pi/2-BPSK DMRS and, if needed, specify RF requirements -Identify impact on RF requirements for the uplink full power transmission and, if needed, specify RF requirements | RAN4: UE RF requirements | Yes | ★★ | Issue 1: FFS new power class capability for full power transmission Issue 2: UE behavior for fallback DCI (DCI_0_0) Issue 3: MOP requirement for full power transmission with 2 TX ports configured for FR1 shall be captured Issue 4: Test Configuration and Requirement Applicability for Full Power Transmission MOP Test issues
|  |  | RAN4: RRM core requirements | Yes | ★★ | Issue 1: There are open issues for L1-SINR measurement requirements,including the value of P, and the scaling factor N for FR2 in the delay requirements, measurement restriction and scheduling availability, side condition for CMR+NZP-IMR. Issue 2: There are open issues for sCell beam failure recovery, including sharing factor for BFD evaluation period, sharing factor for CBD evaluation period, whether and how the requirement could be defined for BFRQ.
|  | • Specification of an IAB-node following architecture 1a including [RAN2-led, RAN3]: o Routing function on IAB-node to support forwarding across the multi-hop topology based on routing identifier. o Hop-by-hop propagation of signalling to support low latency scheduling (e.g. TR 38.874 clause 8.6), BH RLF handling (e.g. TR 38.874 clause 9.7.14-15) and resource coordination across the multi-hop topology (e.g. TR 38.874 clause 7.3.3). o UE-bearer to BH RLC-channel mapping and mapping between ingress and egress BH RLC channels functions for support of one-to-one and many-to-one bearer mapping. • Enhancements to gNB functionality to serve as an IAB-donor following architecture 1a [RAN3, RAN2] o Functions on gNB CU-CP for topology, route and resource management [RAN3-led]. o Support for IP routability to IAB-node (e.g. from CU, OAM) [RAN3-led]. o Bearer mapping function on gNB DU to map downlink traffic of one or many UE-bearers to a BH RLC-channel [RAN2-led]. • Specification of possible enhancements to E1, F1 and X2/Xn interfaces [RAN3-led, RAN2]: o On F1:  security protection over the wireless backhaul links.  setting up and reconfiguring IAB-nodes and IAB-donor DUs o On X2 and Xn, necessary functions to enable DC operation with IAB. o On E1, configuration of necessary IAB-specific transport and/or security protection of F1-U. • Specification of procedures for IAB-node integration and topology adaptation, including [RAN3-led, RAN2]: o Procedures for IAB-node integration for SA and NSA modes, including enhancements needed to E-UTRAN for NSA mode. o Specification of IAB-node migration underneath the same IAB-donor (with or without a change of IAB-donor DU),. Migration of IAB-node could be network-controlled or could be due to BH RLF. o Support for route redundancy and route selection based on multi-connectivity (e.g. TR 38.874 clause 9.7), leveraging existing NR solutions as well as NR-NR DC, without additional RAN1 work. (see NOTE1). • Specification of enhancements to L2 wireless transport [RAN2-led, RAN3]: o Specification of an adaptation layer above RLC layer. The adaptation layer supports routing across the wireless backhaul and IP as next protocol layer. o Extension of LCID space and potentially LCG space to support one-to-one mapping of UE bearers to BH RLC channels. The extension of LCID space and LCG space is applicable only to IAB-nodes. o Specification of a flow control mechanism (for DL and, if necessary, for UL) to handle congestion. o Specification of mechanisms to enable lossless delivery in hop-by-hop ARQ. • Specification of signalling for L2 transport and resource management [RAN2-led, RAN3, RAN1]: o Specification of RRC and F1-AP procedures and messages for: the setup and release of IAB-nodes; configuration of adaptation layer at the IAB-nodes and IAB-donor DU; configuration of BH RLC channels, QoS information, routing tables, bearer-mappings; configuration of means for network synchronization; and configuration for sharing of time-domain resources among backhaul and access links (see physical layer specification). o Specification of an IP address allocation mechanism for the IAB-nodes [RAN3]. o Specification of enhancements to bearer context setup/release procedures to support flow QoS across multiple hops. o Specification of enhancement for uplink resource request procedure and related signalling to enable low latency uplink data scheduling. o Specification of BH RLF handling (e.g. downstream BH RLF notification). | RAN3: Architecture and L2 based protocol stack | Yes | Finished | The following objectives require further stage-3 work. • Enhancements to gNB functionality to serve as an IAB-donor following architecture • Specification of procedures for IAB-node integration and topology adaptation • Specification of enhancements to L2 wireless transport • Specification of signalling for L2 transport and resource management Issue 1: BAP routing ID configuration in donor DU Issue 2: Capture mapping configuration in F1AP for intermediate IAB and IAB donor DU. Issue 3: IP address update using RRC message; IP address request in EN-DC case; determine IP address for CP/UP Issue 4：feasible solution for IPsec tunnel mode, and solution for IAB obtain IP address from OAM. Note:E2E flow control enhancement, and CP based congestion control may be discussed in Rel-17
|  |  | RAN3: BAP layer function and configuration | Yes | ★
|  |  | RAN3: Flow control and congestion control | Yes | ★
|  |  | RAN3：BH RLF handling | Yes | ★
|  |  | RAN3：IAB integration | Yes | ★
|  |  | RAN3：Topology update | Yes | ★
|  |  | RAN2: − routing function on IAB-node based on routing identifier − Hop-by-hop propagation, BH RLF handling and resource coordination − UE-bearer to BH RLC-channel mapping | Yes | ★ | The following objectives require further stage-3 work (From Status report). • Specification of procedures for IAB-node integration and topology adaptation, incuding o IP address request for IAB-node using ENDC. o IP address assignment by CU. o Potential follow up on the support of F1-C transport of X2AP/LTE (dependent on RAN3 work). • Specification of signalling for L2 transport and resource management
|  |  | RAN2 − adaptation layer above RLC layer supports routing − extension of LCID | Yes | ★
|  |  | RAN2 − RRC and F1-AP procedures and messages − bearer context setup/release procedures − uplink resource request procedure and related signalling − BH RLF handling | Yes | ★

## IIOT
Leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Open issues
RAN2 | Support of NR Industrial Internet of Things (IoT) | 1. The detailed objectives for NR PDCP duplication enhancements are: • Specify PDCP duplication with up to 4 RLC entities configured by RRC in architectural combinations including CA only and NR-DC in combination with CA [RAN2, RAN3]. • Specify mechanisms relating to dynamic control of how a set or subset of configured RLC entities or legs are used for PDCP duplication [RAN2, RAN3]. • Specify enhancements for more efficient DL PDCP duplication without impacting the UE, provided that gains can be confirmed with a reasonable complexity. [RAN3]. • Specify enhancements to address potential impacts of higher-layer multi-connectivity based on SA2 progress and request [RAN3]. | RAN2:Network controlled PDCP duplication | Yes | ★ | Issue 1:If and how Rel-15 MAC CE is used for Rel-16 Duplication
|  |  | RAN3：PDCP Duplication Enhancements | Yes | ★ | Issue 1：Dynamic Control of UL/DL duplication for up to 4 RLC entities: UP solution or CP solution (to be resolved in Rel-16) Issue 2：The discarding timer solution is FFS (to be resolved in Rel-16) Issue 3： handling of new tunnels
|  |  | RAN3:Higher Layer Multi-Connectivity | Yes | ★ | Issue 1: For solution 1, whether E1 or F1 CRs are needed, whether to inform the redundant setup in the response. Issue 2：For solution 4: whether and how to clarify the start/stop scenario and failure of QoS flow redundancy.
|  | 2. The detailed objectives for NR intra-UE prioritization/multiplexing are: • Specify enhancements to address resource conflicts between dynamic grant (DG) and configured grant (CG) PUSCH and conflicts involving multiple CGs [RAN2, RAN1]. o Specify PUSCH grant prioritization based on LCH priorities and LCP restrictions for the cases where MAC prioritizes the grant [RAN2]. • Address UL data/control and control/control resource collision by (L1 multiplexing of services of different priority is out of scope): o specifying a method to address resource collision between SR associating to high-priority traffic and uplink data of lower-priority traffic for the cases where MAC determines the prioritization [RAN2]. o specifying prioritization behaviour among HARQ-ACK/SR/CSI and PUSCH for traffic with different priorities, including the cases with UCI on PUCCH and UCI on PUSCH [RAN1, RAN2]. | RAN2:Handling of deprioritized transmissions | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:Data Data prioritization and SR Data Prioritization | Yes | ★ | Issue 1: whether data vs. data and SR vs. data prioritization can be configured separately.
|  | 3. The detailed objectives for NR TSC-related enhancements include: • Specify accurate reference timing delivery from gNB to UE using broadcast and unicast RRC signalling (with EUTRA Rel-15 signalling solution as baseline) for synchronization requirements defined in TS 22.104) [RAN2, RAN3]. • Specify enhancements to satisfy QoS for wireless Ethernet when using TSC traffic patterns, including o Support of provisioning, from Core Network to RAN and between RAN nodes (e.g. upon handover), of UE’s TSC traffic pattern related information such as message periodicity, message size, message arrival time at gNB (DL) and UE (UL) [RAN3]. o Support for multiple simultaneous active semi-persistent scheduling (SPS) configurations for a given BWP of a UE. [RAN2, RAN1]. o Support for shorter SPS periodicities than the existing ones [RAN2, RAN1]. • Address support for TSC message periodicities with non-integer multiple of NR supported CG/SPS periodicities, as captured in TR 38.825, section 6.5.2. [RAN2, RAN1]. • Specify Ethernet header compression based on structure-aware algorithm [RAN2]. Ethernet header compression solution for LTE to be specified once the design principle for NR is agreed | RAN2:accurate reference timing | Yes | ★ | Issue 1:It is FFS if UE in RRC Connected can request SIB9 using on-demand SI request (by reusing OSI mechanism defined for RRC Connected UEs, with assumption of no additional work is needed in IIOT WI).
|  |  | RAN3:Time Sensitive Communication Related Enhancements | Yes | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN2:scheduling enhancement | Yes | ★ | Issue 1:Collision between SPS PDSCH and DG PDSCH Issue 2:SPS PDSCH release for UEs not indicating a capability to receive more than one unicast PDSCH per slot
|  |  | RAN2:Ethernet Header Compression | Yes | ★ | Main function complete, waiting for ASN.1 review

## MBE
Leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Open issues
RAN2 | Mobility enhancement | • To specify the following solutions agreed during the study phase. [RAN2/RAN1/RAN3/RAN4]: o To reduce interruption time during HO: - Dual active protocol stack based HO interruption time reduction solution; o To improve HO/SCG change reliability and robustness: - Conditional handover for NR PCell change; - Conditional handover based NR PSCell addition/change for any architecture option with NR PSCell; - T312 based fast failure recovery (similar to LTE) | RAN2:Dual active protocol stack based HO interruption time reduction solution; | No | ★ | Issue 1:FFS, check whether “source ” is suitable for all DAPS related changes, or “source SpCell” should be used in some places, e.g. the timer T310.
|  |  | RAN3:DAPS Handover | Yes | ★ | Issue 1: Finalization of DAPS HO indicator business and fallback handling during preparation in X2/Xn/S1/NG and E1 Issue 2: HO SUCCESS support over S1/NG
|  |  | RAN2:Conditional handover for NR PCell change; | No | ★ | RAN2 still need to discuss details in configuration, execution and failure handling. Issue 1:FFS: Only same measurement object is allowed for a candidate cell when 2 trigger events are configured for the execution condition for the candidate cell. Issue 2:FFS CHO (MCG) configuration contains SCG configuration and clarify in the specification only PCell can be candidate cell. Issue 3:FFS How to handle stored CHO related configurations when the UE is released to IDLE e.g. delete stored configurations. Issue 4:FFS Whether mobilityControlInfo may be included at the same time as a CHO. Editor’s note: FFS whether there are issues with configuration of different events (e.g. A3+A5) and how to handle the “and” of two triggering events in RRC. Issue 5:FFS How to handle stored CHO related configurations when the UE is released to IDLE e.g. delete stored configurations.
|  |  | RAN3:CHO | Yes | ★ | Issue 1: Finalization of target-initiated CHO modification, whether by an explicit indicator or a new cause in CHO CANCEL. Issue 2: Support for CHO setup/modify/cancel over E1 Issue 3: Details of the E1AP Bearer Context Modification procedure to retrieve/provide DL COUNT values related for early data forwarding with the source/target CU-UPs; Whether to have a new IE or reuse an existing one Issue 4: Whether the EARLY FORWARDING TRANSFER message be distinguished by the associated candidate cell Note:Inter-SN Pscell Change, may be discussed in Rel-17 MR-DC enhancement WI
|  |  | RAN2:Conditional handover based NR PSCell addition/change for any architecture option with NR PSCell; | No | ★ | Open issue: FFS: how many candidate cells (UE and network impacts should be clarified). FFS whether the number of candidate cells for CPAC different from that of CHO. FFS on UE capability on measuement configuration. FFS: In case of SRB3, the MN is not informed of CPC-intra-SN execution by the UE. Editor’s note: FFS on whether to inform MN upon the CPC execution if CPC configured via SRB3
|  |  | RAN2:T312 based fast failure recovery (similar to LTE) | No | ★ | Main function complete, waiting for ASN.1 review
|  |  | RAN4: RRM core requirements | Yes | ★ | Issue 1. Interruption requirements in intra-frequency DAPS HO for 60KHz SCS. Issue 2. Synchronization assumption for intra-frequency DAPS handover. A few open issues are left. 1 meeting is needed to complete the open issues and CRs.

## MR-DCCA
Leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Open issues
RAN2 | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | 1. Support of asynchronous and synchronous NR-NR Dual Connectivity [RAN1, RAN2, RAN4] o UE power control [RAN1] o RRC signalling to support of enhanced NR-NR DC [RAN2] o Core requirements to support enhanced NR-NR DC [RAN4] Note: Synchronous DC enhancements in this WID considers only cases not covered in Rel-15 exception sheet for NR WI NR_newRAT-Core. | RAN1: Uplink Power Control for Supporting NR-NR Dual-Connectivity | Yes | ★ | Issue 1:T_offset determination for DPS; Issue 2: Look-ahead Operation for UL transmissions without scheduling DCI; Issue 3: DPS without Look-ahead Operation There are 6 remaining issues justified in RAN1#100 e-meeting, and the three issues listed here together with another issue "Applicable scenario for Dynamic Power Sharing (DPS) scheme" that has been settled in this meeting are treated with high priority. Another 2 maintenance or editorial issues has reached agreements with accepted TP or no change to Spec. Issue 1 listed here are fully discussed, but no agreement has been reached since there are concerns as following, -MN is required to look at SCG configuration to identify the T-offset used by the UE (if it doesn’t, it has to assume worst case T_offset). This part i.e., “requiring the MN to look at SCG configuration” may be not consistent with RAN2 framework. A working assumption is made to send a LS to RAN2 to check whether the solution is consistent with RAN2 MR-DC framework related to MN requirement(s) for understanding SCG configuration, and the adopt alternative in RAN1 will subject to confirmation from RAN2. A CR based on the working assumption has been provided. Issue 2 and 3 listed here will be checked after agreements of issue 1. The remaining issue may take one or two additional meetings, depending on the feedback from RAN2.
|  |  | RAN2:RRC signalling to support of enhanced NR-NR DC | Yes | ★ | Issue 1:For NR-DC power control, need an IE to indicate the semi-static TDD pattern of MCG to SN when semi-static power control Alt 1-2 is set by MN (may already be present).Send an LS to check and ask for this to RAN3.
|  | 2. Early Measurement reporting: Early and fast reporting of measurements information availability from neighbor and serving cells to reduce delay setting up MR-DC and/or CA. [RAN2, RAN4] o This objective applies to MR-DC, NR-NR DC and CA o The objective should consider measurements in IDLE, INACTIVE mode and CONNECTED mode o The impacts on UE power consumption should be minimized o The LTE Rel-15 euCA work should be utilized, when applicable | RAN2:Early and fast reporting of measurements information availability from neighbor and serving cells to reduce delay setting up MR-DC and/or CA. | Yes | ★ | Issue 1:The number of carries to be measured, to be reported, and the number of beams to be included in the NR results. Send LS to R4.
|  | 3. Efficient and low latency serving cell configuration/activation/setup: Minimizing signalling overhead and latency needed for initial cell setup, additional cell setup and additional cell activation for data transmission. [RAN2, RAN1, RAN4, RAN3] o This objective applies to MR-DC, NR-NR DC and CA o The objective should consider enhancements when starting from IDLE, INACTIVE mode and CONNECTED mode | RAN1: Efficient and low latency serving cell configuration/activation/setup | Yes | ★ | Issue 1: Whether ‘the DCI format 1-1 on primary cell with CIF≠0’ can be used for Case 2 Scell dormancy indication. Different companies have diferent views on it and has no consesus. It needs to be discussed in next meeting. Issue 2: HARQ-ACK feedback with Case 2 Scell dormancy indication DCI in Type 2 HARQ-ACK codebook. The current TP does not fully capture it and need further discussion in next meeting. It still needs one more meeting to discuss these two issues. In addition, there was lots of email discussion about whether Scell dormancy indication is supported in DCI format 0_2/1_2 or not, but has no consensus. Considering the support of DCI format 0_2/1_2 is an enhancement of Scell dormancy feature, if companies still have no consensus on it, this discussion can be pushed to Rel-17.
|  |  | RAN2:Minimizing signalling overhead and latency needed for initial cell setup, additional cell setup and additional cell activation for data transmission. | Yes | ★ | Issue 1:Some issues about dormant BWP configuration needs R1 response: TCI state configuration, support BFR,not support aperiodic CSI reporting for dormant BWP and not support SRS transmission on dormant BWP
|  | 4. Fast recovery: Support fast recovery of MCG link e.g. by utilizing the SCG link and split SRBs for recovery during MCG failure while operating under MR-DC. [RAN2, RAN3] o This objective applies to MR-DC and NR-NR DC | RAN2:Support fast recovery of MCG link e.g. by utilizing the SCG link and split SRBs for recovery during MCG failure while operating under MR-DC. | Yes | ★ | Issue 1:SN change during the fast MCG recovery in an email discussion to the next meeting, Issue 2:the supported MR-DC handover scenarios for the fast MCG recovery.
|  | 5. Cross-carrier scheduling with different numerologies on the scheduling and scheduled carriers [RAN1, RAN2, RAN4] o This objective applies to CA only. o Target completion by RAN#84. | RAN1: Cross-carrier scheduling with different numerology | Yes | ★ | Issue 1: Type 1 HARQ-ACK codebook of cross-carrier SPS release. Companies have no consensus on the principle of reference slot, it will need one further meeting to be discussed. Issue 2: UE capability about default beam determination. Although companies agreed to introduce a RRC parameter to differentiate R15 or R16 default beam determination for cross-carrier scheduling, it seems that companies still have different preferences for the corresponding UE capability, which may further change the current spec.
|  |  | RAN2:Cross-carrier scheduling with different numerologies on the scheduling and scheduled carriers | Yes | ★ | Main function complete, waiting for ASN.1 review
|  | 6. Study and, if found beneficial over the existing single Tx switched uplink solution, specify enhancements to single Tx switched uplink solution for EN-DC, such as allowing all DL and UL subframes for data transmission for both NR and LTE. [RAN1]. Note: UE in single Tx switched uplink mode is not expected to be scheduled simultaneous transmission on MCG and SCG | RAN1: Potential Enhancements to Single Tx Switched Uplink Solution for EN-DC | Yes | ★ | Issue 1: Current 38.213 section 7.6.1 does not accurately capture the desired behavior for 'single-tx' case; Issue 2: Whether to capture RAN1 agreement that UL/DL configuration 0/6 is not supported for EN-DC with DL-reference configuration in RAN1 spec.; Issue 3: Clarify type 2 UE’s assumption on “other than offset-UL subframes”. For issue 1, all company agree that the current TS needs modification, but there are two options for the TP, down selection will be done in next meeting. For issue 2, the proposal is to wait for RAN2 CRs, then decide whether introduce the change in RAN1 spec. For issue 3, TP proposed follows R15 discription "the UE is not expected to transmit any uplink physical channel...", companies agree that it is more clear to use "the UE is not expected to be configured or indicated to transmit any uplink physical channel...", but if R16 use the new description, R15 will also needs update. And R15 change seems not the scope of this discussion. So no consensus has been reached for the TP update. It is likely that it will be solved in next meeting. Besides above remaining issues, two clarification issues in TS36.213 are proposed, but no discussion for these since they are not functional issue. All the issues are in TP phase or only clarifications are needed, no big issues left and one more meeting is needed to resolve them.
|  | 7. Enable the Release 15 behaviour of “DL HARQ timing for FDD Scell for LTE TDD-FDD CA with TDD Pcell, applied to FDD Pcell” to apply to dual uplink EN-DC, possibly including any conclusions on the previous objective (6) for LTE FDD Pcells [RAN1]. | RAN1: Potential Enhancements to Single Tx Switched Uplink Solution for EN-DC | Yes | Finished | An optimization for UL transmission of dual Tx operation is proposed in one contribution, but it is not discussed as an optimization, may be discussed in next meeting or leave it as it is.
|  | 9. Introduce support for aperiodic CSI-RS triggering with different numerology between CSI-RS and triggering PDCCH [RAN1] | RAN1: Aperiodic CSI-RS triggering with different numerology between CSI-RS and triggering PDCCH | Yes | Finished | The current agreement about default A-CSI-RS QCL assumption is for the condition that A-CSI-RS configuration contains QCL-typeD information. It may need further clarification what the UE behaviour is if A-CSI-RS configuration does not contain QCL-typeD information, but the criticality is unclear.
|  | 10. Introduce support for unaligned frame boundary with slot alignment and partial SFN alignment for R16 NR inter-band CA [RAN1, RAN2] o Misalignment should be limited to ±76800Ts o Signaling support for slot offset if necessary Note: Unaligned frame boundary is only allowed for certain band combination Note: Necessity of signaling support of slot offset should be discussed in RAN1 Note: Blind detection of slot offset is not in scope Note: No optimization for MAC Note: Feature is optional and capability signaling is introduced by RAN2 | RAN1: Unaligned frame boundary with slot alignment and partial SFN alignment for R16 NR inter-band CA | Yes | Finished
|  | 1. Support of asynchronous and synchronous NR-NR Dual Connectivity [RAN1, RAN2, RAN4] o Core requirements to support enhanced NR-NR DC [RAN4] 2. Early Measurement reporting: Early and fast reporting of measurements information availability from neighbor and serving cells to reduce delay setting up MR-DC and/or CA. [RAN2, RAN4] o This objective applies to MR-DC, NR-NR DC and CA o The objective should consider measurements in IDLE, INACTIVE mode and CONNECTED mode o The impacts on UE power consumption should be minimized o The LTE Rel-15 euCA work should be utilized, when applicable 3. Efficient and low latency serving cell configuration/activation/setup: Minimizing signalling overhead and latency needed for initial cell setup, additional cell setup and additional cell activation for data transmission. [RAN2, RAN1, RAN4, RAN3] o This objective applies to MR-DC, NR-NR DC and CA o The objective should consider enhancements when starting from IDLE, INACTIVE mode and CONNECTED mode 8. Specify the interruption requirements for EN-DC and NE-DC related to features added during the Rel-15 LTE euCA WI [RAN4] | RAN4: RRM core requirements | Yes | ★★ | Issue 1. UE requirements related to number of overlapping and non-overlapping carrier for EMR in NR SA idle mode Issue 2. Cell detection, measurement requirements and accuracy requirements on EMR carriers Issue 3. Whether to define UE EMR requirements for EMR carriers while T331 timer is active and/or when T331 has expired Issue 4. How to apply a serving cell-based threshold condition for EMR carrier measurement Issue 5. How to capture the measurement assumption for EMR carrier when cell type changes due to cell change Issue 6. Number of LTE EMR carriers and NR inter-RAT carriers to support Issue 7. Conditions when the detected cell status remain detected during transitioning from connected to idle or inactive mode Issue 8. Measurement requirements for NR inter-RAT EMR carrier Issue 9. Dormancy BWP switch delay requirements Issue 10. UE requirements and interruption requirements for a dormancy SCell

## NPN
Leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Open issues
RAN3 | Non-public network | • Support NPN functionality in NG-RAN:  - CAG/SNPN relevant parameter broadcast from SIB [RAN2]  - CAG/SNPN cell selection/reselection [RAN2]  - CAG/SNPN cell access control [RAN2/3]  - For CAG, in the case of Intra-RAT intra-system and inter-RAT intra-system, the connected mode mobility support [RAN2/3]  - The connected mode mobility support within SNPN[RAN2/3] | RAN2: Cell selection and reselection | Yes | ★ | Issue 1: Emergency call - support in CAG-only cells Issue 2: PCI range – how is signaling done Issue 3: Cell ranking – for non-CAG member cells Issue 4: AS-NAS interaction Issue 5：NPN-related SIB UAC – per CAG or per PLMN
|  |  | RAN2: Connected mode aspects (RAN2) | Yes | ★ | Issue 1：Manual CAG selection Issue 2：Indexing on PNI-NPN Measurement – which UEs are supposed to report
|  |  | RAN3: Access Control/Initial UE Message | Yes | ★ | Issue 1：FFS impact of manual CAG selection (To be resolved in Rel-16)
|  |  | RAN3: Connected mobility（RAN3） | Yes | ★ | Issue 1： FFS Mobility in inactive state, e.g. whether the anchor node or the new serving node performs access control Issue 2： FFS to transfer the CAG ID in handover procedure.
|  | • For CAG/SNPN, necessary modifications to NG-C and Xn interfaces to communicate the CAG-ID/NID related parameters to NG-RAN nodes, respectively [RAN3] | RAN3: Configuration Aspects over NG | Yes | ★ | Issue 1： FFS to send supported CAG list to the AMF
|  |  | RAN3: Paging | Yes | Finished
|  |  | RAN3: Self-Configuration Aspects (Xn) | Yes | ★ | Issue 1：FFS to include the SNPN/PNI-NPN information in the Neighbor cell information Issue 2：FFS to include the NID IE in TAI Support List Issue 3：FFS how to introduce new cause value on handover failure
|  |  | RAN3: Multi-connectivity | Yes | ★ | Issue 1：FFS whether to add some descriptions in TS 37.340 (To be resolved in Rel-16)
|  |  | RAN3: Others | Yes | ★ | Issue 1：Whether multiple SNPNs can support the same or different set of slices? (related to LS to SA2)
|  | • Support CAG/SNPN functionality with CU-DU split[RAN3] | RAN3: F1 aspects | Yes | ★ | Issue 1：Agree to transfer the PNI-NPN information in interface messages, details are FFS. Issue 2; FFS to include the serving NID/selected CAG ID in the UE context related messages Issue 3: FFS to transfer the Human Readable Name Issue 4: FFS about the exact location of NPN support information in the served cell information.
|  | • Support CAG/SNPN functionality with CP-UP split, if any[RAN3] | RAN3: E1 aspects | Yes | ★ | Issue 1: FFS to transfer the PNI-NPN information in interface messages Issue 2: FFS to include the serving NID/selected CAG ID in the UE context related messages (Note that to transfer the selected CAG ID can be further discussed in Rel-17)

## SON MDT
Leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Open issues
RAN3 | SON/MDT Support for NR | • Support of SON features, including MRO (intra and inter-system), MLB (intra-system), and RACH optimization. [RAN3, RAN2] − Specification of the UE reporting necessary to enhance the network configuration [RAN2]. − Specification of the inter-node information exchange, including possible enhancements to S1/NG, X2/Xn, and F1/E1 interfaces [RAN3] | RAN2/3: MRO | Yes | ★ | RAN3: Issue 1： CU DU aspects for MRO Note： There is consensus that SN change failure optimization may be discussed in Rel-17
|  |  | RAN2/3: MLB | Yes | ★ | RAN3: Issue 1：FFSs on whether to introduce hardware capacity, TNL capacity and number of active Ues as load metrics and corresponding granularity
|  |  | RAN2/3: RACH optimization | Yes | ★ | RAN3: Issue 1： PRACH parameters exchange between netwrk interfaces Issue 2：RACH configuration conflicts detection and resolution in CU-DU architecture
|  | • Support of MDT features for identified use cases, including coverage optimization, QoS verification via MDT, indoor MDT improvement, location information reporting, and sensor data collection [RAN2, RAN3] − Specification of Logged MDT for both RRC_IDLE and RRC_INACTIVE UEs [RAN2, RAN3, RAN4] − Specification of Immediate MDT for RRC_CONNECTED UEs[RAN2, RAN3] − Specification of reporting e.g. RLF and accessibility measurements [RAN2, RAN4] − Specification of MDT for standalone, NR-DC and EN-DC scenario including CU-DU split architecture [RAN2, RAN3] | RAN2/3: MDT | Yes | ★ | RAN2： Complete from functional point of view Remaining tasks: Further clean-up and potential CR corrections RAN3： Issue 1: Management based MDT should not overwrite signaling based MDT (see LS from RAN2 in R3-200096) Issue 2: FFS on whether to add the NR CGI in S1AP Cell Traffic Trace message Issue 3: FFS how to support M5~M7 in S-gNB in EN-DC case and pending to RAN2 discussion
|  | • Specification of L2 measurements [RAN2, RAN3] | RAN2/3: L2 measurement | Yes | Finished
|  | • Specification of mobility history information stored by UE for RRC_IDLE, RRC_INACTIVE and RRC_CONNECTED UEs, taking LTE mobility history information as a baseline (see TR 38.840) [RAN2, RAN3 may be needed depending on RAN2 progress] | RAN2/3: UE mobility history | Yes | ★ | RAN2： Complete from functional point of view Remaining tasks: ASN.1 review
|  | − Specification of Logged MDT for both RRC_IDLE and RRC_INACTIVE UEs [RAN2, RAN3, RAN4] − Specification of reporting e.g. RLF and accessibility measurements [RAN2, RAN4] | RAN4: MDT related RRM requirements | Yes | Finished

## RAN4 WIs
Leading WG | WI | Objective | Sub Agenda | Critical or not for WI | ★: 1 meeting is expected ★★: 2 meetings are expected ★★★: >2 meetings are expected | Open issues
RAN4 | Add support of NR DL 256QAM for FR2 | Specify BS and UE requirements for NR DL 256QAM for FR2 if applicable scenarios and feasible requirements are identified 1) The requirements for BS include Tx modulation quality, Tx power dynamic range etc. 2) The requirements for UE include Rx maximum input power level, FRC etc. | RAN4: RF requirements | Yes | ★ | Issue 1: how to define the UE maximum input level for 256QAM in the next meeting. Issue 2: In 256QAM WI, UE demod performance requirements and testability will be discussed in the performance part of this WI.
RAN4 | RF requirements for NR frequency range 1 (FR1) | Complete UE requirements for almost contiguous allocations for CP-OFDM UL for FR1, which is optional feature • UE requirements for Intra-band contiguous DL CA for FR1 • UE requirements for Intra-band non-contiguous DL CA for FR1 -Including generic and band specific requirements for intra-band non-contiguous CA in n77 and n78 • Corresponding CA configuration will be removed from basket WID • UE requirements Intra-band contiguous UL CA for FR1 power class 3 • UE requirements Intra-band non-contiguous UL CA for FR1 power class 3 • Specify UE requirements to allow switching between case 1 and case 2 as below for two uplink carriers case inter-band EN-DC without SUL, inter-band UL CA and standalone SUL for UE supporting maximum two concurrent transmission | RAN4: Almost contiguous allocations for CP-OFDM UL for FR1 | Yes | Finished | No open issues
|  |  | RAN4: Intra-band contiguous DL CA for FR1 | Yes | Finished | No open issues
|  |  | RAN4: Intra-band non-contiguous DL CA for FR1 for generic and n77 and n78 | Yes | Finished | No open issues
|  |  | RAN4: Intra-band contiguous UL CA for FR1 power class 3 | Yes | ★ | Issue 1: Emission and MPR requirement for intra-band contiguous UL CA
|  |  | RAN4: Intra-band non-contiguous UL CA for FR1 power class 3 | Yes | ★ | Issue 1:Investigate MPR impact, UL MIMO capability, and feasibility as a function of CABW, CCBW, and Wgap for the following architectures Issue 2:Investigate need for any additional UL MIMO capability for release 16 At least 1 meeting is necessary to complete the work.
|  |  | RAN4: Switching period between case 1 and case 2 | Yes | ★★ | Issue 1: Switching period requirements: good progress, values of switching period are agreed. Issue 2:Interruption requirements: RAN1 feedback on interruption is required to complete the interruption requirements. UE capability will also impact RAN2. Considering the coordination with other WGs, at least 2 meetings are necessary to complete the work.
|  |  | RAN4: Transient period capability | Yes | ★ | Issue 1: Testability related issues will be further discussed in RAN4 and test case for transient period capability is introduced in Rel-17 after the testability issues are solved.
RAN4 | NR RF requirement enhancements for frequency range 2 (FR2) | • Enhancements methods for avoiding radio link failures and connection releases due to significant and unpredictable UE P-MPRs due to the FR2 UE RF exposure compliance reasons [RAN4, RAN1, RAN2] • FR2 UE Beam Correspondence requirements to ensure that UE performs beam correspondence based on DL reference signal (SSB or CSI-RS) configured by the network [RAN4] • FR2 UE requirements for contiguous intra-band DL CA for aggregated bandwidth larger than 1400 MHz [RAN4] • FR2 UE requirements for non-contiguous intra-DL CA for aggregated bandwidth larger than 1400 MHz FR2 UE requirements for contiguous UL CA [RAN4] • FR2 UE requirements for non-contiguous intra-band UL CA [RAN4] • FR2 UE requirements for inter-band DL CA [RAN4] • Enhance FR2 UE MPR requirements by balancing with in-band emission requirements [RAN4] • This work item will also study if FR2 UE spherical coverage requirements for PC3 for >20%-tile can be defined. [RAN4] | RAN4: FR2 MPE | Yes | ★★ | Issue 1:PMPR reporting values.The provided valus have been merged into two options in Feb meeting. At least one meeting is needed for further down selection between agreed two options and focus on the PMPR values that is needed to solve RLF issue. Issue 2:PMPR reporting: report before or after it is applied. Issue 3:PMPR reporting: Periodic or triggered report.No conclusions has been reached on introducing periodic reporting. Issue 4: Dynamic duty cycle.The benefit of dynamic duty cycle from improving UE performance and helping gNB scheduling perspective needs to be further discussed. Issue 5:Reference PCMAX.Further discuss the necessity of introducing “reference PCMAX” UE capability. At least two meetings are needed to complete the PMPR reporting and the relative UE behaviour.
|  |  | RAN4: Beam correspondence based on configured DL RS | Yes | ★★ | Open issues: 1. Beam correspondence based on SSB: whether and how much performance relaxation is feasible 2. Beam correspondence based on CSI-RS: - deployment scenario for testing - the method to achieve CSI-RS only condition 3. Whether to introduce the Initial access beam correspondence and feasibility of the requirements 4. Additional beam correspondence enhancement: - feasibility of utilizing the existing UE measurement including RSRP and/or L1-SINR 5. Beam correspondence capability aspects: - Whether the Rel-15 UE bit0/bit1 BC capability is applicable to Rel-16 enhancements - Whether a new capability for Rel-16 enhanced beam correspondence is needed - Test applicability rule
|  |  | RAN4: Intra-band cont DL CA for aggregated BW larger than 1400 MHz | Yes | ★★ | Issue 1: whether to define new contiguous BW classes. Some companies prefer to continue studying the relative technical issues and then decide whether to continue this topic.
|  |  | RAN4: Intra-band non-cont DL CA for aggregated BW larger than 1400 MHz | Yes | ★★ | Issue 1: DL-only spectrum type supported by UE. Issue 2: the EIS relaxation ΔRIB, including EIS relaxation table breaks, EIS relaxation values and clarification Issue 3: Relaxation for Beam squint
|  |  | RAN4: Intra-band non-contiguous UL CA | Yes | ★★ | Issue 1: whether to define Non-simultaneous UL for non-contiguous UL CA in FR2 in Rel-16 Issue 2: Simultaneous UL for non-contiguous UL CA in FR2, including MPR and A-MPR tables changes and Beam squint analysis for FR2 PC3 UEs
|  |  | RAN4: Inter-band DL CA | Yes | ★★ | Issue 1: Quantifying spherical coverage for inter-band CA.Two options have been proposed. Though most companies prefer option 1, there is still no convergence. Issue 2: LB + LB, HB + HB inter-band CA including PSD difference, Beam Management Issue 3:LB + HB inter-band CA including PSD difference capability signaling,LB + HB PSD difference, LB + HB EIS relaxation framework Issue 4: Split item in WID to separate L+H from L+L/H+H Issue 5: testing considerations for inter-band CA including allowing offset antennas as equivalent to single AoA for IBB and allowing offset antennas for TRx requirements
|  |  | RAN4: Improvement of UE MPR | Yes | ★★ | Issue 1:Output power boosting when IBE is suspended for PI/2 PBSK and QPSK Issue 2: Simplification of In-Band Emissions Requirements Issue 3: FR2 ACLR MBW
|  |  | RAN4: Improvement of spherical coverage requirements for PC3 | Yes | ★ | Issue 1: Multi-band requirement framework
RAN4 | NR RRM requirements for CSI-RS based L3 measurement | • Assumptions on Synchronization • Single FFT is assumed for multiple cell measurements per frequency layer for both intra- and inter-frequency measurements. • Measurement bandwidth of CSI-RS for the minimum requirements • CSI-RS based intra-frequency and inter-frequency definition • Intra-frequency and inter-frequency measurement requirements • Evaluate and specify CSI-RS based L3 measurement accuracy • Introduce new UE measurement capability, including number of frequency layer and number of cells etc., for CSI-RS based measurement | RAN4: CSI-RS measurement bandwidth | Yes | ★★★ | Issue 1: CSI-RS configuration for measurement requirement is still open. Companies have different views on specifing the requirements based on one set of configuration or two sets of confihuration. This issue has been discussed for 3 meetings,little progress has been made. Taking this situation into consideration, compromise is necessary,otherwise, it is difficult to move forward.
|  |  | RAN4: CSI-RS based intra-frequency and inter-frequency measurement definition | Yes | ★★★ | Issue 1: CSI-RS based intra-frequency and inter-frequency measurement definition is still open. Companies have different views on the definition of intra-frequency measurement. This issue is a fundamental issue and has impacts on other open issues. However, it has been discussed for 3 meetings,little progress has been made. Taking this situation into consideration, compromise is necessary,otherwise, it is difficult to move forward.
|  |  | RAN4: Measurement capability | Yes | ★★★ | Issue 1: UE measurement capability is open, including number of frequancy layers,number of cells, number of CSI-RS resources/beams. This issue is related to the deinition of intra-frequency measurement. However, the definitio of intra-frequency measurement is still under discussio.
|  |  | RAN4: intra-frequency/inter-frequency measurement requirements | Yes | ★★★ | Issue 1: intra-frequency/inter-frequency measurement requirements are open. This issue is related to the definition of intra-frequency measurement. However, the definitio of intra-frequency measurement is still under discussio.
RAN4 | NR support for high speed train scenario | Investigate and specify the UE RRM core requirements for: - Idle and inactive mode: • Cell reselection including cell identification and measurement requirements - Connected mode • Cell identification requirements • Measurement delay requirements • Study whether to introduce beam management related requirements, e.g. L1-RSRP measurement • Study the impact on RLM and UL timing. - If needed other requirements are not precluded. If needed, signalling impact should be discussed in RAN2. | RAN4: cell reselection | Yes | ★ | Issue 1: Whether to keep M2, M3, M4 for cell re-selection with DRX cycle =0.32s is open. At least 1 meeting is necessary to complete the work.
|  |  | RAN4: cell identification delay | Yes | ★★ | Issue 1:Whether to keep the relaxation factor of 1.5 for DRX cycle <= 0.32s in connected mode is open. Issue 2: Measurement delay in connected mode is open
|  |  | RAN4: RLM | Yes | ★ | Issue 1: Whether 1.5x relaxation factor for RLM shall be kept is open.
|  |  | RAN4: Beam management | Yes | ★ | Issue 1: Whether to keep the keep the 1.5x scaling factor for BFD is open. Issue 2: Whether to keep the keep the 1.5x scaling factor for L1-RSRP is open.
|  |  | RAN4: inter-RAT measurement | Yes | ★★ | Issue 1: NR- EUTRA Inter-RAT measurement requirements to support HST are open. Issue 2: EUTRA - NR Inter-RAT measurement requirements to support HST are open.
RAN4 | NR RRM requirement enhancement | (1) RRM requirement of SRS carrier switching requirements for NR SA, NR-DC, EN-DC and NE-DC including o Delay and interruption requirements of the following cases - LTE SRS carrier switching impacting NR CC - NR SRS carrier switching impacting LTE CC - NR SRS carrier switching impacting NR CC (2) RRM requirements of multiple Scell activation/deactivation in both FR1 and FR2 o Scell activation and deactivation delay and interruption requirements for multiple SCell activation/deactivation in FR1, and FR2, and FR1+FR2 - the corresponding delay requirements for both FR1 and FR2 should be power class agnostic (3) CGI reading requirements with autonomous gap for NR capable UE o CGI reading for NR cell (NR capable UE in LTE SA, NR SA UE, EN-DC UE, NE-DC UE, and NR-DC) o CGI reading for LTE cell (NR SA UE, EN-DC UE, NE-DC UE, and NR-DC UE) (4) RRM requirements of BWP switching o The Interruption requirement and BWP switching delay requirement when UE is configured or indicated to change BWP on multiple CCs (5) Inter-band CA requirement for FR2 UE measurement capability of independent Rx beam and/or common beam o UE measurement capability o Scell activation requirement, o Interruption requirement, o Scheduling restriction requirement Note: applies for inter-band CA for 28 GHz + 39 GHz combinations according to RF conclusions in R4-1916024. (6) Inter-frequency measurement requirement without MG o RRM requirements for inter-frequency measurement without MG when the SSB is completely contained in the active BWP of the UE (7) Mandating more measurement gap patterns for R16 RRM o Discuss on the possible benefits and network/UE complexity aspects of mandating additional measurement gap pattern(s) for R16 RRM based on R15 measurement gap applicability requirements. o If the conclusion is to mandate additional gap pattern(s), inform RAN2 by LS. | RAN4: SRS carrier switching | Yes | ★ | Open issues: 1. There are open issues on the impact on NR measurement requirements due to LTE SRS carrier switching. 2. There are open issues on the impact on E-UTRA measurement requirements due to NR SRS carrier switching . 3. There are open issues on interruptions due to SRS carrier switching in different frequency range.
|  |  | RAN4: multiple Scell activation/deactivation | Yes | ★★ | Open issues: 1. Delay extension due to interruption on L1-RSRP measurement resource. 2. scaling factor for cell detection time of target being-activated Scell. 3. Interruption requirements. 4. Activation requirement for mixed types of to-be-activated Scells.
|  |  | RAN4: CGI reading requirements with autonomous gap | Yes | ★★ | Open issues: 1. How does UE meet the existing RRM requirements during CGI reading. 2. MIB decoding delay for FR2. 3. SIB1 decoding delay. 4. interruption core requirements. 5. Known cell condition.
|  |  | RAN4: BWP switching on multiple CCs | Yes | ★★ | Open issues: 1. Delay requirements for DCI/timer/RRC based BWP switch. 2. Interruption requirements for simultaneous BWP switch.
|  |  | RAN4: inter-frequency measurement requirement without MG | Yes | ★ | Open issues: 1. UE behaviour in the case SMTC is partially overlapped with MG. 2. UE capability
|  |  | RAN4: mandatory gap patterns | Yes | ★★ | Open issues: 1. Definition of NR only measurement. 2. Applicable scenarios of UE capability for NR only measurement. 3. Applicable scenarios for additional mandatory gap patterns. 4. Additional mandatory gap patterns.
|  |  | RAN4: UE-specific CBW change | Yes | ★★ | Open issues: 1. UE processing time for UE specific channel BW switch. 2. Interruption requirement on UE-specific CBW change.
|  |  | RAN4: Spatial relation switch for uplink | Yes | ★★ | Open issues: 1. delay requirement for spatial relation info switching need to be further studied case by case,including whether to define delay requirments and how to define the delay requirements. 2. UE behaviour when the UL signal has spatial relation to an unknown TCI-state.
|  |  | RAN4: Non-simultaneous UL carrier operation in FR2 | Yes | ★★ | The feasilbity has not been concluded in RF session yet.
|  |  | RAN4: Inter-band CA requirement for FR2 UE measurement capability of independent Rx beam and/or common beam | Yes | ★★ | Open issues: 1. scaling factor CSSF_outside_gap for FR2 inter-band CA. 2. interruption requirements. 3. Beam management requirements. 4. Scheduling restriction requirement. 5. measurement restriction requirements. 6. SCell activation delay requirements.