## Slide 1: 3GPP Release timelines
Source: RAN Chairman,
RAN1 Chairman,
RAN2 Chairman,
RAN3 Chairman,
RAN4 Chairman
RAN5 Chairman
RP-200430

## Slide 2: Introduction
These slides present a proposal to adjust the 3GPP RAN milestones in light of the recent cancellation of WG and TSG face-to-face meetings
Note that the proposal has been coordinated across all TSGs

## Slide 3: Overall timeline
Q2
Q3
Q4
2021
Q2
Q3
Q4
Q1
2022
Q1
2020
Q1
2019
Q4
Rel-16 RAN1 freeze
Rel-16 stage-3 freeze*
Rel-16 ASN.1 freeze
Rel-16 RAN4
performance completion*
Rel-17 RAN1,2,3 package approval
Rel-17 RAN4 RF package approval*
Rel-17 RAN1 freeze*
Rel-17 stage-3 freeze*
Rel-17 ASN.1 freeze*
Rel-17 RAN4
performance completion*
Release 17 timeline
Release 16 completion
Rel-17 RAN4 RRM/Demod package approval*
* These milestones show a 3-month shift compared to previously approved timelines

## Slide 4: Key points
Release-16 stage-3 freeze moved to June/2020
Release-16 ASN.1 freeze remains in June/2020
Release-16 RAN4 performance completion moved to Dec/2020
Start of Release-17 work
  RAN1 will start in May WG meeting. Exact scope TBD
  RAN 2-3-4 will start in August meeting. Exact scope TBD.
Release-17 package approved for RAN1-2-3 at RAN#86 is unchanged
  Overall number of TUs allocated for the different items assumed to be unchanged, but the exact distribution across meetings and quarters will be re-evaluated at RAN#88
Release-17 RAN4 package approval will be done in 2 phases: in June and September 2020
  RAN4 package approval for RF proposals in June/2020
  RAN4 package approval for RRM and Demod proposals in September/2020
Release-17 RAN1 freeze moved to June/2021
Relase-17 stage-3 freeze moved to September/2021
Release-17 ASN.1 freeze moved to December/2021
Release-17 RAN4 performance completion moved to March/2022

## Slide 5: Proposal
It is proposed to endorse the milestones shown in these slides

## Slide 6: Thank You !