## Slide 1: Release, Meeting and TU planning
Source: TSG RAN Chairman, RAN1 Chairman, RAN2 Chairman, RAN3 Chairman, RAN4 Chairman, RAN5 Chairman
RP-202111

## Slide 2: Outline
Proposed meeting timeplan until June 2021
Release 17 timeline considerations
TU handling until June 2021

## Slide 3: Proposed RAN meeting plan
INACTIVE
RAN1
RAN2
RAN3
RAN4
Q
U
I
E
T
P
E
R
I
O
D
WG
WG
TSG
I
N
A
C
T
I
V
E
P
E
R
I
O
D
October
December
November
January
February
March
TSG
WG
WG
TSG
WG
WG
T
S
G
#
9
1
RAN1 (4+4+5)
T
S
G
#
9
0
RAN5
RAN4
RAN3
RAN2
Confirmed as E-meetings by default
12-16
19-23
26-30
2-6
9-13
16-20
23-27
30-4
7-11
18-22
25-29
1-5
8-12
15-19
22-26
1-5
8-12
15-19
22-26
RAN5
RAN1
RAN4
RAN3
RAN2
April
June
May
29-2
5-9
12-16
19-23
26-30
3-7
10-14
17-21
24-28
31-4
7-11
14-18
5-9
T
S
G
#
9
2
RAN5
RAN4 (3+4)
RAN3
RAN2 (5+2)
RAN1 (5+2)
RAN1 (3+4)
I
N
A
C
T
I
V
E
P
E
R
I
O
D
I
N
A
C
T
I
V
E
P
E
R
I
O
D
RAN2 (3+4)
INACTIVE
RAN1
RAN2
RAN3
RAN4
Q
U
I
E
T
P
E
R
I
O
D
RAN4 (5+2)
INACTIVE
RAN1
RAN2
RAN3
RAN4
Q
U
I
E
T
P
E
R
I
O
D

## Slide 4: Key elements of the proposed plan (1/2)
Quarters with multiple WG meetings may have staggered handling of items
  Initial soft-staggering of topics is shown in the TU allocation tables, subject to further refining in future RAN plenaries
Inactive periods are installed between meetings to allow proper internal preparation and observe key regional holidays
  No email discussions are allowed on any WG reflector or TSG_RAN or TSG_RAN_Drafts reflector during these periods. No GTW sessions are allowed, not even informal ones.
  23-29/Nov (Thanksgiving)
  21/Dec – 3/January (Christmas+New Year)
  8-21/Feb (Lunar New Year)
  29/March – 5/April (Easter)
  26/April-9/May

## Slide 5: Key elements of the proposed plan (2/2)
Tightening of scope for some existing WIs may be addressed at December plenary to ensure timely progress
  Potential follow-on Work Items of Study Items will need a very well defined tight scope!
TSG#91 may have 2 days set aside exclusively for conducting election rounds on Thursday and Friday before the normal meeting week
Submissions deadlines
  RAN1
    103-e: 16Oct for maintenance & Rel-17 4 SIs (RedCap, ePos, CovEnh, 60GHz); 23Oct for other Rel-17 items
    104-e: 18Jan; 104b-e: 6April; 105-e: 11May
  RAN2
    112-e: 22Oct (23.59 PST); 113-e: 14Jan (23.59 PST); 113b-e: 6April (23.59 PST); 114-e: 11May (23.59 PST)
  RAN3: business as usual
  RAN4
    97-e: 23Oct; 98-e: 15Jan; 98b-e: 6April; 99-e: 11May
  RAN5
    90-e: 8Feb

## Slide 6: Release 17 timeline
Expect Electronic era to last throughout 2021 in the worst case
The leadership is committed to facilitate delivering Rel-17 with minimal additional delay
  Detailed analysis still needed to understand what is feasible  Overall timeline decision to be taken only in December
  Leadership will provide detailed analysis (TUs, etc…) for December with the goal of keeping the additional delay at 6 months max.
Firmly commit to a new timeline (in December), and endorse a detailed planning (meetings and TUs) to achieve it
2021
Q2
Q3
Q4
Q1
2022
Q1
Rel-17 RAN1 freeze
Rel-17 stage-3 freeze
Rel-17 ASN.1 freeze
Rel-17 RAN4
performance completion
Current Release 17 timeline as per RAN#87E decision
2021
Q4
Q1
Q2
Q3
2022
Q3
Rel-17 RAN1 freeze
Rel-17 stage-3 freeze
Rel-17 ASN.1 freeze
Rel-17 RAN4
performance completion
Potential new timeline to be committed to latest in Dec

## Slide 7: RAN1 TU Management for 4Q’20 & 1Q/2Q’21
Assumptions: all RAN1 meetings in the next 3 quarters are e-meetings
Due to the natural difference between a physical meeting and an e-Meeting, the absolute values of the TUs herein should not be interpreted the same as in a physical meeting in terms of RAN1 capacity
  Note that different e-meetings may have different durations
The TU #s herein are primarily for gauging the ratio of email threads and GTW session times for different topics
Total TUs:
  27 + 4 (reserved for maintenance)=31
  For RAN1#103-e, a total of 40 TUs is assumed
    The 4 Rel-17 SIs are allocated with 4 TUs each, targeting for completion by Dec’2020
    Meeting planning: staggering for different items
      Rel-17 4 SIs: all the 3 weeks; Maintenance: primarily first 2 weeks; Other Rel-17 items: primarily last 2 weeks
The TU #s for Q2’21 are in yellow color, to be confirmed/refined in RAN#91-e
For Q4’20, also to start XR and NB-IoT/eMTC over NTN by email only (no GTW hours)
  Detailed scope – see next slide

## Slide 8: Scope for XR and NB-IoT/eMTC in Q4/2020
Study on XR Evaluations for NR (RAN1)
  Applications, Traffic Model and Evaluation Methodology Focus on applications and evaluation methodology including identification of KPIs of interest for relevant deployment scenarios
  Others
  NOTE: SA4 has ongoing work in the XR area, RAN1 will not address these SA4 aspects but will wait for SA4’s outcome
Study on NB-IoT/eMTC support for Non-Terrestrial Network
RAN1
  Scenarios applicable to NB-IoT/eMTC
  Necessary changes to support NB-IoT and eMTC over satellite A placeholder only: contributions may be submitted but will not be formally handled
  Others
RAN2
  Start identifying the extent parts of “NR over NTN” TR can be re-used or not re-used for NB-IoT/eMTC over NTN (using scenarios defined by RAN1, possibly complemented by RAN2)

## Slide 9: RAN2 TUs
- R2 Early SIs end after 21Q1.
- For Quarters with 2 meetings
the meetings will be 70% of
an ordinary meeting (5+2)
- Proposal to make the difference
visible at RP, i.e. Nominal
R2 capacity for such meetings
28 TUs instead of 40 TUs.
- Q4: Assume that 50% is used
for maintenance
Approximately for R2
1 TU = 1.5h online + CB time
1 TU = 1-3 AT-email disc.
1 TU = 1-3 input tdocs.
 | 20Q3 | 20Q4 | 21Q1 | 21Q2 | 
Rel 17 | 111 | 112 | 113 | 113B | 114
NR Sidelink relay SI + WI | 2 | 1.5 | 1.5 | 1.5 | 1
[R1] NR positioning enhancements SI + WI | 1 | 1 | 1 | 2 | 2
[R1] Reduced Capability SI = WI | 2 | 1 | 1 | 0.5 | 1
RAN slicing SI + WI | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
NR Multicast | 2 | 2 | 2 | 1.5 | 1.5
[R1] NR Non-Terrestrial Networks (NTN) | 2 | 2 | 2 | 1.5 | 1.5
UE Power Saving | 1 | 1 | 1 | 0 | 1
MR DC/CA enhancements | 1 | 1 | 1 | 1 | 0
Small Data enhancements | 1 | 1.5 | 1.5 | 1 | 0.5
NR IIoT/URLLC | 1 | 1 | 1 | 0 | 1
[R1] NB-IoT / eMTC enhancements | 1 | 1 | 1 | 1 | 1
[R3] SON/MDT | 1 | 1 | 1 | 1 | 0.5
NR IAB enhancements |  | 1 | 1 | 1 | 1
Multi SIM |  | 1 | 1 | 1 | 0.5
Non-Public Networks (NPN) |  | 0 | 1 | 1 | 1
[R1] IoT NTN SI |  | 0 | 1 | 0.5 | 0.5
[R1] NR Sidelink enhancements |  | 1.5 | 2 | 1 | 1
[R1] NR MIMO fe |  |  |  |  | 
[R3] NR QoE SI and WI |  |  | 0.5 | 0.5 | 0.5
[R1] NR up to 71GHz |  |  |  |  | 
[R1] Misc R1 items, Cov Enh, DSS sched enh etc |  |  |  |  | 
R17 Other | 1.5 | 2 | 2 | 0.5 | 1
TEI17 |  |  |  |  | 
R17 Total | 17 | 20 | 23 | 17 | 17
Rel 16 Total | 18 | 15 | 14 | 9 | 9
NR Rel 15 Total | 3 | 3 | 2 | 1 | 1
EUTRA R15 and earlier Total | 2 | 2 | 1 | 1 | 1
RAN2 Total (40) | 40 | 40 | 40 | 28 | 28
20Q4: If “R17 Other” time is not required, or needed for maintenance, it will be shared between SIs and extra time needed for reply to essential LSes.

## Slide 10: RAN2 TUs and Agenda limitations for Q2
Maintenance: Most of maintenance topics, both R16 and R15 and earlier are staggered across two meetings, only few selected problematic topics treated fully at both meetings (e.g. likely UE capabilities). Method of staggering still TBD, Alt 1: clear split of topics, Alt 2: decide what to correct in Meeting 1, address the CR details in Meeting 2. Resulting TU: 11 per meeting (instead of 15-16)
R17 Staggering
  IIOT/URLLC NT in Meeting 1
  Power Saving NT in Meeting 1
  DCCA f Enh NT in Meeting 2
  SONMDT 0.5 TU reduced Meeting 2
  NPN 0.5 TU reduced Meeting 2
  IoT NTN 0.5 TU reduced Meeting 1 and 2 (was already plan from Dec).
  SL Enhancements 0.5-1 TU reduced Meeting 1 and 2
  Red Cap 0.5 TU reduced Meeting 1
  Small Data Enh 0.5 TU reduced in Meeting 2
NOTE: For Rel-17 it is assumed that the relation TU – number of topics (input tdocs, email disc etc) is kept, to enforce the staggering.
Result: Both meetings in Q2, Total TU = 28 per meeting.

## Slide 11: RAN3 TU Management Until Q2/21
Assumption: all RAN3 meetings in the next 3 quarters are e-meetings
Plan assumes 12 “f2f TUs” per meeting
1 f2f TU ↔ ~7 e-mail discussions + ~40 min. online time
Actual allocation of e-mail discussions and online sessions in an e-meeting continues to be up to the Chairman’s discretion
In principle, no TEI17 discussed before Q2 2021
2 meetings/quarter are assumed in Q4/21 in order to keep the Rel-17 deadline
Study item * RAN3-led
changes

## Slide 12: RAN4 TU projection for R17
  Once R16 perf part work is done, the following is planned for RAN4:
Topics | RF | RD | Notes
RAN4 R15/R16 maintenance | 2 | 2 | 
RAN1/2/3 led R17 WIs | 8 | 10 | Assuming 18 TUs are required and roughly 40% for RF, 60% for RD. Precise TU budget remains to be clearly defined and justified
RAN4 R17 basket and other spectrum WIs | 6 |  | 4 for basket WIs and 2 for other spectrum WIs
Remaining TUs for RAN4 R17 non-spectrum WIs | 8.5 | 8.5 | Assuming a total of 45 TUs, and 24.5 TUs for RF and 20.5 TUs for RD

## Slide 13: Proposal
It is proposed to endorse the RAN meeting plan presented in slides 3,4,5.
It is proposed to endorse the TU planning shown in 7,8, 9, 10, 11, 12
For Release 17 timeline it is proposed to task the RAN leadership to present to RAN#90-E a detailed plan and analysis for achieving a timeline with an additional 6 months delay (max). Formal decision on the new Release 17 timeline would then be made at TSG#90-E

## Slide 14: Thank you!

## Slide 15: Appendix: RAN2 TUs entire R17
- At end of the release, there
will be additional R1 and R4
induced work, and TEI17.
Suggest to end some smaller
items early, as shown.
 | 20Q3 | 20Q4 | 21Q1 | 21Q2 |  | 21Q3 | 21Q4 |  | 22Q1 | 
Rel 17 | 111 | 112 | 113 | 113B | 114 | 115 | 115B | 116 | 116B | 117
NR Sidelink relay SI + WI | 2 | 1.5 | 1.5 | 1.5 | 1 | 2 | 1 | 1 | 1.5 | 1.5
[R1] NR positioning enhancements SI + WI | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1
[R1] Reduced Capability SI = WI | 2 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5
RAN slicing SI + WI | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 |  | 
NR Multicast | 2 | 2 | 2 | 1.5 | 1.5 | 2 | 2 | 1 | 1 | 1
[R1] NR Non-Terrestrial Networks (NTN) | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1 | 1.5 | 1 | 1.5
UE Power Saving | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0.5 | 0.5
MR DC/CA enhancements | 1 | 1 | 1 | 1 | 0 | 1 | 0.5 | 1 | 1 | 1
Small Data enhancements | 1 | 1.5 | 1.5 | 1 | 0.5 | 1.5 | 0 | 1.5 | 1 | 1
NR IIoT/URLLC | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0.5 | 1
[R1] NB-IoT / eMTC enhancements | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
[R3] SON/MDT | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 0.5
NR IAB enhancements |  | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
Multi SIM |  | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 |  | 
Non-Public Networks (NPN) |  | 0 | 1 | 1 | 1 | 1 | 1 | 0.5 |  | 
[R1] IoT NTN SI |  | 0 | 1 | 0.5 | 0.5 | 1 |  |  |  | 
[R1] NR Sidelink enhancements |  | 1.5 | 2 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1.5
[R1] NR MIMO fe |  |  |  |  |  |  | 0.5 | 0.5 | 0.5 | 1
[R3] NR QoE SI and WI |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 |  | 
[R1] NR up to 71GHz |  |  |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
[R1] Misc R1 items, Cov Enh, DSS sched enh etc |  |  |  |  |  | 1 | 1 | 1 | 1 | 1
R17 Other | 1.5 | 2 | 2 | 0.5 | 1 | 2.5 | 1.5 | 1 | 3.5 | 1.5
TEI17 |  |  |  |  |  | 1 | 1 | 2 | 2 | 2
R17 Total | 17 | 20 | 23 | 17 | 17 | 26 | 18 | 19 | 19 | 19
Rel 16 Total | 18 | 15 | 14 | 9 | 9 | 11 | 7 | 6 | 6 | 6
NR Rel 15 Total | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2
EUTRA R15 and earlier Total | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
RAN2 Total (40) | 40 | 40 | 40 | 28 | 28 | 40 | 28 | 28 | 28 | 28

## Slide 16: Appendix: RAN3 TUs entire Rel-17
Study item * RAN3-led
changes