## Slide 1: Rel-18 Considerations Timeline, Content
MediaTek Inc.
3GPP TSG RAN 93E RP-212316
September 13th-17th, 2021 Agenda Item 9.0.1

## Slide 2: Timeline [1/2]
3GPP to deliver stable releases in a timely predictable manner
Careful release planning required for:
  Content
  Timing
  Release transition: often overlooked
Observations
  Rel-16 stabilization has taken too long
  The pandemic has caused major delays to Rel-17
  Starting Rel-18 in Q1 (RAN1) and Q2 (others), even if by email only, will hamper Rel-17 stabilization
Completing and stabilizing Rel-17 is of utmost priority before 3GPP resources shift to Rel-18
Proposal 1: Defer the start of Rel-18 by one quarter
Proposal 2: 18 months* from start to freeze (not from freeze to freeze) *15 months in SA2
 | Rel-17 | Rel-18 “normal” | Proposal Rel-18 “+3mo”
Stage 2 (SA2) | Jun 2021** | Dec 2022 | Jan 2022 – Mar 2023
PHY | Dec 2021 | Jun 2023 | Mar 2022 – Sep 2023
L3/Core | Mar 2022 | Sep 2023 | Jun 2022 – Dec 2023
ASN.1 | Jun 2022 | Dec 2023 | Mar 2024
RAN4 perf | Sep 2022 | Mar 2024 | Jun 2024
** 14 exception sheets. Q3/Q4 full with Rel-17 |  |  | 
2021 | 2022 |  |  |  | 2023 |  |  |  | 2024 | 
Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Buffer | System Architecture Stage 2 |  |  |  |  |  |  |  |  | 
 | Buffer | Stage 3 PHY |  |  |  |  |  |  |  | 
 |  | buffer | Stage 3 Others |  |  |  |  |  | ASN.1 | Perf

## Slide 3: Timeline [2/2]
2021 | 2022 |  |  |  | 2023 |  |  |  | 2024 | 
Q4 #94 | Q1 #95 | Q2 #96 | Q3 #97 | Q4 #98 | Q1 #99 | Q2 #100 | Q3 #101 | Q4 #102 | Q1 #103 | Q2 #104
Rel-17 PHY |  |  |  |  |  |  |  |  |  | 
Rel-17 Stage 3 Others |  | Rel-17 ASN.1 | Rel-17 Perf |  |  |  |  |  |  | 
 |  | No Rel-18 interference |  |  |  |  |  |  |  | 
6mo buffer | Rel-18 System Architecture Stage 2 [15 months] |  |  |  |  |  |  |  |  | 
 | 3mo buffer | Rel-18 Stage 3 PHY [18 months] |  |  |  |  |  |  |  | 
 |  | 3mo buffer | Rel-18 Stage 3 Others [18 months] |  |  |  |  |  | Rel-18 ASN.1 | Rel-18 Perf.
Rel-18 Package (SA2/RAN)
9 months

## Slide 4: Content
Email discussions have considerably helped refining proposals
  though a number of controversial issues remain
Time is necessary to “digest” the email discussions’ outcome and identify a coherent package i.e. technical- and TU budget- wise
Proposal 4: Identify the TU budgets for the agreed Rel-18 timeline
Proposal 5: Each post-RAN#94e email discussion to identify TU needs i.e.
  Overall TU needs for the topic; and
  TU needs per “Work Task” in a topic (for in topic prioritization)
  (a work task is self-consistent but may be dependent on other work task(s) e.g. Work Task A is independent, Work Task B is dependent on Work Task A i.e. deprioritizing Work Task B does not impact Work Task A, but deprioritizing Work Task A also deprioritizes Work Task B)
Proposal 6:
  Treat discussions as a package i.e. no early endorsement of individual proposals (no early “prioritization”)
  Note the conclusions of the email discussions
  Avoid reopening “objectives” that are ~stable as a result of July/August discussions (this does not necessarily imply such objectives would end up in the package)
Proposal 7:
  RAN#94e to confirm a (promising) set of high-level topic areas (based on RWS-210659) to proceed into the next phase of email discussion
Proposal 8:
  RAN#94e to identify proposals for which no further email discussion will take place prior RAN#94e
  This does not automatically imply “out of Rel-18”

## Slide 5: Thank You!