## Proposed TU budgets Q2,Q3 2022
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN | R4RF | R4RD | RAN | R4RF | R4RD | RAN | Final column of TU total. Insert new quarters before this column. Do not remove this column
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 94 Dec.21 | 107bis | 116bis | 114bis | 101bis | 101bis | 108 | 117 | 115 | 102 | 102 | 95 Mar.22 | 103 | 103 | 96 June.22 | 104 | 104 | 97 Sep.22
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-212535 | Samsung | Mar 22 | 4 | REL-17 |  |  | 0.5 |  | 0.25 | 1 |  | 1 |  | 0.25 | 1
R4 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-212535 | Samsung | Sept 22 | 2.75 | REL-17 | [5 empty] | 0.25 |  |  |  |  | 0.5 |  |  | 1 |  |  | 1
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-212637 | Qualcomm | Mar 22 | 7 | REL-17 |  |  | 0.5 |  | 2 | 1 |  | 0.5 |  | 2 | 1
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-212637 | Qualcomm | Sep 22 | 4 | REL-17 | [9 empty] | 0.5 | 0.5 |  | 0.5 | 1 |  | 0.5 | 1
R1 | NR | NR_pos_enh-Core | WI | Core Part: NR positioning enhancements | RP-210903 | Intel, CATT, Ericsson | Mar 22 | 8 | REL-17 |  |  | 2 | 1 |  | 1 |  | 2 | 1 |  | 1
R4 | NR | NR_pos_enh-Perf | WI | Perf Part: NR positioning enhancements | RP-210903 | Intel, CATT, Ericsson | Sept 22 | 1 | REL-17 | [13 empty] | 0.5 |  |  | 0.5
R1 | NR | NR_redcap-Core | WI | Core Part: support of reduced capability NR devices | RP-211574 | Ericsson | Mar 22 | 6 | REL-17 |  |  | 1 | 0.5 | 0.5 | 1 |  | 1 | 0.5 | 0.5 | 1
R4 | NR | NR_redcap-Perf | WI | Perf Part: support of reduced capability NR devices | RP-211574 | Ericsson | Sept 22 | 2.25 | REL-17 | [5 empty] | 0.25 |  |  |  |  | 0.5 |  |  | 0.75 |  |  | 0.75
R1 | NR | NR_cov_enh-Core | WI | Core Part: NR coverage enhancements | RP-211566 | China Telecom | Mar 22 | 2 | REL-17 |  |  | 0.5 |  | 0.5 |  |  | 0.5 |  | 0.5
R4 | NR | NR_cov_enh-Perf | WI | NR coverage enhancements | RP-211566 | China Telecom | Sept 22 | 1.75 | REL-17 | [5 empty] | 0.25 |  |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-211340 | Huawei, Ericsson | Mar 22 | 5 | REL-17 |  |  | 1 | 0.5 | 0.5 | 0.5 |  | 1 | 0.5 | 0.5 | 0.5
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf part: Additional enhancements for NB-IoT and LTE-MTC | RP-211340 | Huawei, Ericsson | Sept 22 | 1.25 | REL-17 | [5 empty] | 0.25 |  |  |  |  | 0.5 |  |  | 0.25 |  |  | 0.25
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-202846 | LG Electronics | Mar 22 | 7.5 | REL-17 |  |  | 1.5 |  | 1 | 1 |  | 2 |  | 1 | 1
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-202846 | LG Electronics | Sept 22 | 1.25 | REL-17 | [10 empty] | 0.25 |  |  | 0.5 |  |  | 0.5
R1 | NR | FS_NR_XR_eval | SI | Study on XR (Extended Reality) evaluations for NR | RP-210460 | Qualcomm | Dec 21 | 0 | REL-17
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-202689 | MediaTek | Jun 21 | 0 | REL-17
R1 | LTE | LTE_NBIOT_eMTC_NTN | WI | NB-IoT/eMTC support for Non-Terrestrial Networks | RP‑211601 | MediaTek, Eutelsat, ZTE | Mar 22 | 1 | REL-17 |  |  | 0.5 |  |  |  |  | 0.5
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-211345 | Ericsson | Mar 22 | 0 | REL-17
R4 | NR | NR_DSS-Perf | WI | Perf part: NR Dynamic spectrum sharing (DSS) | RP-211345 | Ericsson | Sept 22 | 0 | REL-17
R1 | LTE | LTE_terr_bcast_bands-Core | WI | Revised WID for New bands and bandwidth allocation for 5G terrestrial broadcast (Part 1) | RP-211144 | EBU | Mar 22 | 0 | REL-17
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Dec 19 | 0 | REL-17
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-210854 | Nokia | Mar 22 | 4 | REL-17 |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5
R4 | NR | NR_IIOT_URLLC_enh-Perf | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-210854 | Nokia | Sept 22 | 0.5 | REL-17 | [5 empty] | 0 |  |  |  |  | 0 |  |  | 0.25 |  |  | 0.25
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-211784 | Thales | Mar 22 | 9 | REL-17 |  |  | 1.5 | 0.5 | 2 | 0.5 |  | 2 |  | 2 | 0.5
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-211784 | Thales | Sept 22 | 3.25 | REL-17 | [5 empty] | 0.25 |  |  |  |  | 0.5 |  | 0.75 | 0.5 |  | 0.75 | 0.5
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-212630 | MediaTek | Mar 22 | 3 | REL-17 |  |  | 1 |  |  | 0.5 |  | 1 |  |  | 0.5
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-212630 | MediaTek | Sept 22 | 0.75 | REL-17 | [10 empty] | 0.25 |  |  | 0.25 |  |  | 0.25
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-211548 | Qualcomm | Mar.22 | 8 | REL-17 |  |  | 1 | 1 | 1 | 0.5 |  | 1 | 2 | 1 | 0.5
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-211548 | Qualcomm | Sept 22 | 2.25 | REL-17 | [9 empty] | 0.5 | 0.25 |  | 0.5 | 0.25 |  | 0.5 | 0.25
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-201038 | Huawei | Mar.22 | 5.5 | REL-17 |  |  | 1.5 | 1 |  |  |  | 2 | 1
R4 | NR | NR_MBS_Perf | WI | Perf. part: NR multicast and broadcast services | RP-201038 | Huawei | Sept 22 | 0 | REL-17
R2 | NR | NR_SL_relay-Core | WI | NR Sidelink Relay | RP-212601 | OPPO | Mar.22 | 6 | REL-17 |  |  | 2 | 0.5 |  | 0.5 |  | 2 | 0.5 |  | 0.5
R2 | NR | NR_SL_Relay-Performance | WI | NR Sidelink Relay | RP-212601 | OPPO | Sep.22 | 0.5 | REL-17 | [13 empty] | 0.25 |  |  | 0.25
R2 | NR | NR_Slice | WI | Enhancement of RAN Slicing for NR WID | RP-212534 | CMCC | Mar.22 | 2 | REL-17 |  |  | 0.5 | 0.5 |  |  |  | 0.5 | 0.5
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-211290 | CMCC | Jun.21 | 0 | REL-17
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | Huawei | Mar.22 | 4 | REL-17 |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | Huawei | Dec.21 | 1 | REL-17 | [13 empty] | 0.5 |  |  | 0.5
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-212594 | ZTE | Mar.22 | 5.5 | REL-17 |  |  | 1.5 | 1 |  | 0.5 |  | 1 | 1 |  | 0.5
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-212594 | ZTE | Dec.21 | 0.5 | REL-17 | [13 empty] | 0.25 |  |  | 0.25
R2 | NR, LTE | LTE_NR_MUSIM | WI | Support for Multi-SIM devices in Rel-17 | RP-212610 | vivo | Mar 22 | 1.5 | REL-17 |  |  | 1 |  |  |  |  | 0.5
R2 | NR | NR_UDC-Core | WI | NR UDC | RP-211203 | CATT | Mar 22 | 0.5 | REL-17 |  |  | 0.5
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-192188 | Qualcomm | Jun 21 | 0 | REL-16
R4 | NR | LTE_NR_DC_CA_enh-Perf | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-192336 | Ericsson | Jun 21 | 0 | REL-16
R2 | NR |  |  | R1 Misc items (DSS etc) |  |  |  | 1 | REL-17 |  |  | 0.5 |  |  |  |  | 0.5
R2 | NR, LTE |  |  | R17 Other (R4 items etc) |  |  |  | 3 | REL-17 |  |  | 1.5 |  |  |  |  | 1.5
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei | Jun 18 | 0
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-201281 | CMCC | Mar 22 | 4 | REL-17 |  |  | 1 | 1 |  |  |  | 1 | 1
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP-211409 | China Unicom | Mar 22 | 0 | REL-17
R3 | NR | FS_NR_ENDC_data_collect | SI | Further Enhancments to Data Collection SI | RP-201620 | CMCC | Mar 22 | 1.5 | REL-17 |  |  |  | 0.5 |  |  |  |  | 1
R3 | NR | NR_QoE | WI | NR QoE management and optimizations for diverse services | RP-211406 | China Unicom | Mar 22 | 3 | REL-17 |  |  | 0.5 | 1 |  |  |  | 0.5 | 1
R3 | NR | NG_RAN_PRN_enh | WI | NR Private Networks Enhancement WI | RP-212585 | China Telecom | Mar 22 | 1.5 | REL-17 |  |  | 0.5 | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_FR2_enhTestMethods | SI | Study on enhanced test methods for FR2 in NR | RP-211600 | Apple，CAICT | Mar 22 | 1 | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_NR_eff_BW_util | SI | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | RP-212287 | Ericsson | Dec 21 | 2 | REL-17 |  |  |  |  | 1 |  |  |  |  | 1
R4 | NR | FS_NR_PC2_UE_FDD | SI | Study on high power UE (power class 2) for one NR FDD band | RP-202870 | China Unicom | Sep 21 | 0 | REL-17
R4 | NR | FS_NR_600MHz_ext | SI | Study on extended 600MHz NR band | RP-202924 | Spark NZ Ltd | Sep 21 | 0 | REL-17
R4 | NR | NR_MIMO_OTA-Core | WI | MIMO OTA requirements for NR UEs | RP-212603 | CAICT | Mar 22 | 1 | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_MIMO_OTA-Perf | WI | MIMO OTA requirements for NR UEs | RP-212603 | CAICT | Sep 22 | 3 | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  | 1 |  |  | 1
R4 | NR | NR_demod_enh2-Perf | WI | Further enhancement on NR demodulation performance | RP-212636 | China Telecom | Mar 22 | 4.5 | REL-17 | [5 empty] | 1.5 |  |  |  |  | 1 |  |  | 1 |  |  | 1
R4 | NR | NR_DL1024QAM_FR1-Core | WI | Introduction of DL 1024QAM for NR FR1 | RP-202886 | Ericsson | Dec 21 | 0 | REL-17
R4 | NR | NR_DL1024QAM_FR1-Perf | WI | Introduction of DL 1024QAM for NR FR1 | RP-202886 | Ericsson | Jun 22 | 1.5 | REL-17 |  |  |  |  | 0.25 | 0.25 |  |  |  | 0.25 | 0.25 |  | 0.25 | 0.25
R4 | NR | NR_RRM_enh2-Core | WI | Further RRM enhancement for NR and MR-DC | RP-202874 | Apple | Mar 22 | 2.5 | REL-17 | [5 empty] | 1.5 |  |  |  |  | 1
R4 | NR | NR_RRM_enh2-Perf | WI | Further RRM enhancement for NR and MR-DC | RP-202874 | Apple | Sep 22 | 1 | REL-17 | [13 empty] | 0.5 |  |  | 0.5
R4 | NR | NR_HST_FR1_enh-Core | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | CMCC | Mar 22 | 1 | REL-17 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_HST_FR1_enh-Perf | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | CMCC | Sep 22 | 2 | REL-17 | [5 empty] | 0.5 |  |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
R4 | NR | NR_RF_FR2_req_enh2-Core | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-212092 | Nokia | Mar 22 | 6 | REL-17 |  |  |  |  | 2 | 1 |  |  |  | 2 | 1
R4 | NR | NR_RF_FR2_req_enh2-Perf | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-212092 | Nokia | Jun 22 | 1 | REL-17 | [13 empty] | 0.5 |  |  | 0.5
R4 | NR | NR_HST_FR2-Core | WI | NR support for high speed train scenario in FR2 | RP-210800 | Samsung | Mar 22 | 2.25 | REL-17 |  |  |  |  | 0.25 | 1 |  |  |  | 0.25 | 0.75
R4 | NR | NR_HST_FR2-Perf | WI | NR support for high speed train scenario in FR2 | RP-210800 | Samsung | Sep 22 | 3.75 | REL-17 | [5 empty] | 1 |  |  |  |  | 0.75 |  |  | 1 |  |  | 1
R4 | NR | NR_MG_enh-Core | WI | NR and MR-DC measurement gap enhancements | RP-211591 | MediaTek | Mar 22 | 3 | REL-17 |  |  | 0.5 |  |  | 1 |  | 0.5 |  |  | 1
R4 | NR | NR_MG_enh-Perf | WI | NR and MR-DC measurement gap enhancements | RP-211591 | MediaTek | Sep 22 | 1 | REL-17 | [13 empty] | 0.5 |  |  | 0.5
R4 | NR | NR_RF_FR1_enh-Core | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-212527 | Huawei | Mar 22 | 4 | REL-17 |  |  |  |  | 1.5 | 0.5 |  |  |  | 1.5 | 0.5
R4 | NR | NR_RF_FR1_enh-Perf | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-212527 | Huawei | Sep 22 | 1.25 | REL-17 | [5 empty] | 0.5 |  |  |  |  | 0.5 |  |  | 0.25
R4 | NR | NR_repeaters-Core | WI | NR Repeaters | RP-212129 | Qualcomm, Commscope | Mar 22 | 2 | REL-17 |  |  |  |  | 1 |  |  |  |  | 1
R4 | NR | NR_repeaters-Perf | WI | NR Repeaters | RP-212129 | Qualcomm, Commscope | Sep 22 | 1 | REL-17 | [12 empty] | 0.5 |  |  | 0.5
R4 | NR | NR_BCS4-Core | WI | Core part: Introduction of bandwidth combination set 4 (BCS4) for NR | RP-202832 | Ericsson | Mar 22 | 2 | REL-17 |  |  |  |  | 1 |  |  |  |  | 1
R4 | NR | NR_FR1_TRP_TRS-Core | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP-212030 | vivo, OPPO, CMCC | Mar 22 | 1 | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_FR1_TRP_TRS-Perf | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP-212030 | vivo, OPPO, CMCC | Sep 22 | 2 | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5 |  |  | 0.5 |  |  | 0.5
R4 | NR | FS_NR_Opt_pi2BPSK | SI | New study on optimizations of pi/2 BPSK uplink power in NR | RP-210910 | Qualcomm | Mar 22 | 1 | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_RF_TxD-Core | WI | New WI: UE RF requirements for Transparent Tx Diversity (TxD) for NR | RP-211940 | Qualcomm, Huawei | Mar 22 | 0.5 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | NR_RF_TxD-Perf | WI | New WI: UE RF requirements for Transparent Tx Diversity (TxD) for NR | RP-211940 | Qualcomm, Huawei | Mar 22 | 0.1 | [10 empty] | 0.1
R4 | LTE | LTE_terr_bcast_bands_part2-Core | WI | New WID: New bands and bandwidth allocation for 5G terrestrial broadcast (Part 2) | RP-211145 | EBU | Mar 23 | 1 | [13 empty] | 0.5 |  |  | 0.5
R4 | LTE | LTE_NR_HPUE_FWVM-Core |  | High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, Band 13, Band n5, Band n13, and Band n71 | RP-212533 | Nokia | Mar 22 | 0.5 | REL-17 |  |  |  |  | 0.25 |  |  |  |  | 0.25
R4 | LTE | LTE_NR_HPUE_FWVM-Perf |  | High-power UE operation for fixed-wireless/vehicle-mounted use cases in Band 12, Band 5, Band 13, Band n5, Band n13, and Band n71 | RP-212533 | Nokia | Mar 22 | 0.5 | REL-17 | [12 empty] | 0.25 |  |  | 0.25
R4 | NR | R17 NR Basket Wis |  | RP-211757 Rel-17 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) Ericsson RP-212511 Rel-17 NR Inter-band CA/DC for 2 bands DL with x bands UL (x=1,2) ZTE RP-212239 Rel-17 NR inter-band CA for 3 bands DL with 1 band UL CATT RP-212512 Rel-17 NR inter-band CA/DC for 3 bands DL with 2 bands UL ZTE RP-211759 Rel-17 NR inter-band CA for 4 bands DL with 1 band UL Ericsson RP-212110 Rel-17 NR inter-band CA/DC for DL 4 bands and 2UL bands Samsung RP-212176 Rel-17 NR inter-band CA for 5 bands DL with x bands UL (x=1, 2) Huawei RP-212096 Rel-17 DC of 1 LTE band (1DL/1UL) and 1 NR band (1DL/1UL) CHTTL RP-212174 Rel-17 DC of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) Huawei RP-211758 Rel-17 DC of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) Ericsson RP-212532 Rel-17 DC of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) Nokia RP-210300 Dual connectivity (DC) of 5 bands LTE inter-band CA (5DL/1L) and 1 NR band (1DL/1UL) Samsung RP-202542 Dual Connectivity (DC) of x bands (x=2,3,4) LTE inter-band CA (xDL/1UL) and 1 NR FR1 band (1DL/1UL) and 1 NR FR2 band (1DL/1UL) Samsung RP-211750 Rel-17 DC of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)inter-band CA (2DL/1UL) LG RP-211803 Rel-17 DC of x bands (x=1,2) LTE inter-band CA (xDL/xUL) and y bands (y=3-x) NR inter-band CA (yDL/yUL) ZTE RP-211805 Rel-17 DC of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL) ZTE RP-212606 Rel-17 DC of x bands (x=1,2) LTE inter-band CA (xDL/1UL) and 4 bands NR inter-band CA (4DL/1UL) Huawei RP-212178 Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) Huawei RP-210773 Study on band combination handling in RAN4 ZTE RP-212531 Rel-17 Adding CH BW support to existing NR bands Ericsson RP-212187 Addition of MSD (Maximum Sensitivity Degradation) for inter-band EN-DC combinations (1 band LTE+1 band NR FR1) due to added channel bandwidths Huawei RP-210890 Simultaneous Rx/Tx band combinations Huawei RP-210588 Band combinations on co-current operation between Uu frequency bands and V2X bands CATT RP-212184 Additional NR bands for UL-MIMO PC3 in Rel-17 Huawei RP-210478 Downlink interruption for band combinations to conduct dynamic Tx Switching China Telecom, CATT RP-211831 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2) China Telecom RP-211853 Rel-17 High power UE (PC2) for EN-DC with 1 LTE band + 1 NR TDD band China Unicom RP-212182 Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL Huawei, China Unicom RP-211760 Rel-17 Power Class 2 for EN-DC with xLTE band + yNR DL with 1LTE+1(TDD) NR UL band (x= 2, 3, 4, y=1; x=1, 2, y=2) Ericsson RP-212180 High power UE for NR TDD intra-band Carrier Aggregation in frequency range FR1 Huawei |  |  |  | 6 | REL-17 |  |  |  |  | 3 |  |  |  |  | 3
R4 | NR | R17 NR spectrum related WI/SI |  | RP-202844 Introduction of 6GHz NR licensed bands Huawei, Ericsson, Nokia, ZTE RP-212625 Introduction of lower 6GHz NR unlicensed operation for Europe Nokia RP-212302 Introduction of operation in full unlicensed band 5925-7125MHz Apple RP-210878 Introduction of 900 MHz spectrum to 5G NR applicable for Rail Mobile Radio (RMR) Union Inter. Chemins de Fer RP-210879 Introduction of 1900 MHz spectrum to 5G NR applicable for Rail Mobile Radio (RMR) Union Inter. Chemins de Fer RP-212622 Core part: Increasing UE power high limit for CA and DC, Qualcomm, China Telecom RP-212633 High power UE (power class 2) for one NR FDD band, China Unicom |  |  |  | 4 | REL-17 |  |  |  |  | 2 |  |  |  |  | 2
R4 | LTE | R17 LTE basket WIs |  | RP-211859 Rel-17 LTE inter-band CA for 2 bands DL with 1 band UL Qualcomm RP-212192 Rel-17 LTE inter-band CA for 3 bands DL with 1 band UL Huawei RP-212194 Rel-17 LTE inter-band CA for 2 bands DL with 2 band UL Huawei RP-211885 Rel-17 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL Nokia RP-211748 Rel-17 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 bands UL LG |  |  |  | 2 | REL-17 |  |  |  |  | 1 |  |  |  |  | 1
R4 | LTE | R17 LTE spectrum related WI/SI |  | RP-211857 Additional LTE bands for UE cat. M1/M2/NB1/NB2 in Rel-17 Ericsson RP-212618 Introduction of upper 700MHz A block E-UTRA band for the US,Puloli |  |  |  | 1 | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | LTE,NR | R17 LTE/NR spectrum Perf part |  | All potential performance part for WIs in R17 NR Basket Wis, R17 NR spectrum related WI/SI, R17 LTE basket Wis,R17 LTE/NR spectrum Perf part |  |  |  | 0.5 | REL-17 | [5 empty] | 0.25 |  |  |  |  | 0.25
R4 | NR | R17 LS activities | [5 empty] | 0 | REL-17
R4 | NR | R16 NR Maintenance and TEI | [5 empty] | 7 | REL-16 |  |  |  |  | 1.5 | 1 |  |  |  | 1.5 | 1 |  | 0.5 | 0.5 |  | 0.5 | 0.5
R4 | NR | R15 NR Maintenance | [5 empty] | 0
R4 | LTE | LTE Maintenance | [5 empty] | 1.5 | [5 empty] | 0.5 | 0.25 |  |  |  | 0.5 | 0.25
R5 | NR | FS_UE_5GNR_App_Data_Perf | SI | Study on 5G NR UE Application Layer Data Throughput Performance | RP-210710 | Qualcomm, AT&T |  | 0 | REL-17
| NR |  |  | allocated above | [5 empty] | 0 | 0 | 24.5 | 10.5 | 26.75 | 21 | 0 | 24.5 | 11.5 | 27.85 | 22 | 0 | 5.25 | 11.75 | 0 | 5 | 11.25 | 0
| NR |  |  | Legacy | [7 empty] | 0 |  |  |  |  | 13
| NR |  |  | TEI and other not planned issues | [7 empty] | 2 | 0.5 |  |  |  | 2
| NR |  |  | Reserve | [7 empty] | 1.5 | 0.5 |  |  |  | 1.5 | 0.5
| NR |  |  | total used capacity | [5 empty] | 0 | 0 | 28 | 11.5 | 26.75 | 21 | 0 | 41 | 12 | 27.85 | 22 | 0 | 5.25 | 11.75 | 0 | 5 | 11.25 | 0
| NR |  |  | available capacity | [7 empty] | 28 | 12 | 24.5 | 20.5 |  | 40 | 12 | 24.5 | 20.5 |  | 24.5 | 20.5 |  | 24.5 | 20.5
| NR |  |  | remaining/exceeded capacity | [6 empty] | 0 | 0 | 0.5 | -2.25 | -0.5 | 0 | -1 | 0 | -3.35 | -1.5 |  | 19.25 | 8.75 |  | 19.5 | 9.25
| LTE |  |  | allocated above
| LTE |  |  | Legacy
| LTE |  |  | TEI and other not planned issues
| LTE |  |  | Reserve
| LTE |  |  | total used capcaity
| LTE |  |  | available capacity
| LTE |  |  | remaining/exceeded capacity
| UTRA |  |  | allocated above
| UTRAN |  |  | Legacy
| UTRAN |  |  | TEI and other not planned issues
| UTRAN |  |  | Reserve
| UTRAN |  |  | total used capacity
| UTRAN |  |  | available capacity
| UTRAN |  |  | remaining/exceeded capacity
| GERAN |  |  | allocated above
| GERAN |  |  | Legacy
| GERAN |  |  | TEI and other not planned issues
| GERAN |  |  | Reserve
| GERAN |  |  | total used capacity
| GERAN |  |  | available capacity
| GERAN |  |  | remaining/exceeded capacity
R3 |  |  |  | RAN3 overall Status | [8 empty] | 0.5 |  |  |  |  | 0