## Cover sheet
3GPP TSG-RAN5 Meeting #93-e | [8 empty] | R5-216535
Online, , 8th Nov 2021 - 19th Nov 2021
Agenda Item: | 7.4.2
Source: | Ligado Networks
Title: | Work plan for Modification of LTE Band 24 Specifications to comply with updated regulatory emission limit
Work item code: | LTE_B24_mod-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#91-e meeting in June 2021, a RAN5 work item for conformance test aspects related to the modification of the LTE Band 24 Specifications to comply with updated regulatory emission limits was approved [1]. The scope of this work is to assess and update affected conformance test cases related to LTE Band 24 in relevant conformance technical specifications. The purpose of present document is to provide a work plan and status for the RAN5 work item related to updates necessary to the conformance specification as result of updates approved for LTE Band 24 in TS 36.101. The work plan will be updated after each RAN5 meeting to give the status of the work item until the work is fully completed.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+61%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (FDD) |  | 100% (+61.3%)
FDD |  | 100% (+61.3%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 100% |  |  | 100%
LTE RF/RRM
RF common parts | 36.521-1 | 100% (+50%) |  |  | 100% (+50%)
RF Rx test cases | 36.521-1 Rx | 100% |  |  | 100%
RF Tx test cases | 36.521-1 Tx | 100% (+68.2%) |  |  | 100% (+68.2%)
Test Point analysis receiver and transmitter test cases | 36.905 | 100% (+100%) |  |  | 100% (+100%)
LTE RAN and CN protocols
Protocol Test Cases | 36.523-1 | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 36.523-3 | 100% |  |  | 100%
5 References
[1] RP-212497 | Revised WID: UE Conformance – Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Work plan for Modification of LTE Band 24 Specifications to comply with updated regulatory emission limit | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_B24_mod-UEConTest
WP Scope: |  | Assess and determine test environments and cases affected by updates to LTE Band 24 and update them in relevant conformance technical specifications
WP Resp: |  | Ojas Choksi |  |  | ojas.choksi@ligado.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD
100% (+61.3%)
31 (+2)
6.4 (+0.4)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 4.3.1 | Test frequencies | Update the test frequencies based on the consraints placed on use of the entire band 24 as well as addition of a new Tx-Rx spacing | Ligado Networks | RAN5#92 (Aug-21) | R5-216082 |  | 0.1 | 100% | 100% |  | 100%
2 |  | 36.508 | 6.2.3.1 | Test frequencies for signaling test | Update the test frequencies based on the consraints placed on use of the entire band 24 as well as specifying the Tx-Rx spacing for protocol testing | Ligado Networks | RAN5#92 (Aug-21) | R5-216335 |  | 0.1 | 100% | 100% |  | 100%
LTE RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
1 |  | 36.521-1 | 5.2 | Updating Operating Band 24 in 36.101 | Updating operating bond with a note that constrains use of DL and UL frequencies | Ligado Networks | RAN5#92 (Aug-21) | R5-215993 |  | 0.1 |  |  |  | 100%
2 |  | 36.521-1 | 5.3 | Addition of a Tx-Rx spacing for Band 24to align with 36.101 | Updating Tx-Rx spacing to include an additional value of -120.5 MHz | Ligado Networks | RAN5#92 (Aug-21) | R5-215993 |  | 0.1 |  |  |  | 100%
TS 36.521-1: RF test cases - Tx
1 |  | 36.521-1 Tx | 6.2.2 | UE Maximum Output Power | Update the conformance (clause 6.2.2.3) and test requirements (clause 6.2.2.5) due to updates to the lower tolerance value for Band 24 PC3 UE | Ligado Networks | RAN5#93 (Nov-21) | RAN5#92e: R5-215994 | RAN5#92e: Need to review if update to message content exception required for SIB2 RAN5#93e: No contributions/comments received implying no updates necessary | 0.1 | 100% | 100% |  | 100%
2 |  | 36.521-1 Tx | 6.2.2_s | UE Maximum Output Power for subslot/slot TTI | Update the test requirement (clause 6.2.2_s.3) due to changes to the lower tolerance value for PC3 B24 UE | Ligado Networks | RAN5#93 (Nov-21) | RAN5#92e: R5-215994 | RAN5#92e: Need to review if update to message content exception required for SIB2 RAN5#93e: No contributions/comments received implying no updates necessary | 0.1 |  |  |  | 100%
3 |  | 36.521-1 Tx | 6.2.3 | Maximum Power Reduction (MPR) | Update the test requirement (clause 6.2.3.5) due to changes to the lower tolerance value for PC3 B24 UE | Ligado Networks, Rohde & Schwarz | RAN5#93 (Nov-21) | RAN5#92e: R5-215994 | RAN5#92e: Need to review if update to message content exception required for SIB2 RAN5#93e: No contributions/comments received implying no updates necessary | 0.1 |  |  |  | 100%
4 |  | 36.521-1 Tx | 6.2.3_2 | Maximum Power Reduction (MPR) for Multi-Cluster PUSCH | Update the test requirement (clause 6.2.3_2.5) due to changes to the lower tolerance value for PC3 B24 UE | Ligado Networks, Rohde & Schwarz | RAN5#93 (Nov-21) | RAN5#92e: R5-215994 | RAN5#92e: Need to review if update to message content exception required for SIB2 RAN5#93e: No contributions/comments received implying no updates necessary | 0.1 |  |  |  | 100%
5 |  | 36.521-1 Tx | 6.2.3_3 | Maximum Power Reduction (MPR) for UL 64QAM | Update the test requirement (clause 6.2.3_3.5) due to changes to the lower tolerance value for PC3 B24 UE | Ligado Networks, Rohde & Schwarz | RAN5#93 (Nov-21) | RAN5#92e: R5-215994 | RAN5#92e: Need to review if update to message content exception required for SIB2 RAN5#93e: No contributions/comments received implying no updates necessary | 0.1 |  |  |  | 100%
6 |  | 36.521-1 Tx | 6.2.3_4 | Maximum Power Reduction (MPR) for Multi-Cluster PUSCH with UL 64QAM | Update the test requirement (clause 6.2.3_4.5) due to changes to the lower tolerance value for PC3 B24 UE | Ligado Networks, Rohde & Schwarz | RAN5#93 (Nov-21) | RAN5#92e: R5-215994 | RAN5#92e: Need to review if update to message content exception required for SIB2 RAN5#93e: No contributions/comments received implying no updates necessary | 0.1 |  |  |  | 100%
7 |  | 36.521-1 Tx | 6.2.3_5 | Maximum Power Reduction (MPR) for UL 256QAM | Update the test requirement (clause 6.2.3_5.5) due to changes to the lower tolerance value for PC3 B24 UE | Ligado Networks, Rohde & Schwarz | RAN5#93 (Nov-21) | RAN5#92e: R5-215994 | RAN5#92e: Need to review if update to message content exception required for SIB2 RAN5#93e: No contributions/comments received implying no updates necessary | 0.1 |  |  |  | 100%
8 |  | 36.521-1 Tx | 6.2.3.D | Maximum Power Reduction (MPR) for UL ProSe Discovery | Update the test requirement (clause 6.2.D_1.5) due to changes to the lower tolerance value for PC3 B24 UE | Ligado Networks, Rohde & Schwarz | RAN5#93 (Nov-21) | RAN5#92e: R5-215994 | RAN5#92e: Need to review if update to message content exception required for SIB2 RAN5#93e: No contributions/comments received implying no updates necessary | 0.1 |  |  |  | 100%
9 |  | 36.521-1 Tx | 6.2.4 | Additional Maximum Power Reduction (A-MPR) | Updates test applicability (6.2.4.2), conformance requirements (6.2.4.3), test description (6.2.4.4) and test requirement (6.2.4.5) for the new NS_56 and associated A-MPR table for B24 in 36.101 | Nokia | RAN5#93 (Nov-21) | RAN5#92e: R5-215995; RAN5#93e: R5-216427 | RAN5#92e: Only placeholders for test description and test requirement are being introduced. The actual configurations and associated test requirements to be introduced in RAN5#93e RAN5#93e: Actual configuration and associated test requirements introduced | 0.5 |  |  |  | 100%
10 |  | 36.521-1 Tx | 6.2.4_2 | Additional Maximum Power Reduction (A-MPR) for UL 64QAM | Updates test applicability (6.2.4_2.2), test description (6.2.4_2.4) and test requirement (6.2.4_2.5) for the new NS_56 and associated A-MPR table for B24 in 36.101 | Nokia | RAN5#93 (Nov-21) | RAN5#92e: R5-215995; RAN5#93e: R5-218374 | RAN5#92e: Only placeholders for test description and test requirement are being introduced. The actual configurations and associated test requirements to be introduced in RAN5#93e RAN5#93e: Actual configuration and associated test requirements introduced | 0.5 |  |  |  | 100%
11 |  | 36.521-1 Tx | 6.2.4_3 | Additional Maximum Power Reduction (A-MPR) with PUSCH frequency hopping | Updates test applicability (6.2.4_3.2,), test description (6.2.4_3.4) and test requirement (6.2.4_3.5) for the new NS_56 and associated A-MPR table for B24 in 36.101 | Nokia | RAN5#93 (Nov-21) | RAN5#92e: R5-215995; RAN5#93e: R5-216429 | RAN5#92e: Only placeholders for test description and test requirement are being introduced. The actual configurations and associated test requirements to be introduced in RAN5#93e RAN5#93e: Actual configuration and associated test requirements introduced | 0.5 |  |  |  | 100%
12 |  | 36.521-1 Tx | 6.2.4_4 | Additional Maximum Power Reduction (A-MPR) for UL 256QAM | Updates test applicability (6.2.4_4.2), test description (6.2.4_4.4) and test requirement (6.2.4_4.5) for the new NS_56 and associated A-MPR table for B24 in 36.101 | Nokia | RAN5#93 (Nov-21) | RAN5#92e: R5-215995 RAN5#93e: R5-218375 | RAN5#92e: Only placeholders for test description and test requirement are being introduced. The actual configurations and associated test requirements to be introduced in RAN5#93e RAN5#93e: Actual configuration and associated test requirements introduced | 0.5 |  |  |  | 100%
13 |  | 36.521-1 Tx | 6.2.4B | Additional Maximum Power Reduction (A-MPR) for UL-MIMO | Updates test applicability (6.2.4B.2), test description (6.2.4B.4) and test requirement (6.2.4B.5) for the new NS_56 and associated A-MPR table for B24 in 36.101 | Nokia | RAN5#93 (Nov-21) | RAN5#92e: R5-215995 RAN5#93e: R5-216431 | RAN5#92e: Only placeholders for test description and test requirement are being introduced. The actual configurations and associated test requirements to be introduced in RAN5#93e RAN5#93e: Actual configuration and associated test requirements introduced | 0.5 |  |  |  | 100%
14 |  | 36.521-Tx | 6.2.4_s | Additional Maximum Power Reduction (A-MPR) for subslot/slot TTI | Updates test applicability (6.2.4_s.2), conformance requirements (6.2.4_s.3) for the new NS_56 and associated A-MPR table for B24 in 36.101 | Ligado Networks | RAN5#92 (Aug-21) | R5-215995 |  | 0.2 |  |  |  | 100%
15 |  | 36.521-Tx | 6.6.3.3 | Additional Spurious Emissions | Updates conformance requirements (6.6.3.3.3), test description (6.6.3.3.4) and test requirements (6.6.3.3.5) for the new NS_56 and associated additional spurious emssions for B24 in 36.101 | Ligado Networks, Nokia | RAN5#93 (Nov-21) | RAN5#92e: R5-215996 RAN5#93e: R5-216433 | RAN5#92e: Only placeholders for test description and test requirement are being introduced. The actual configurations and associated test requirements to be introduced in RAN5#93e RAN5#93e: Actual configuration and associated test requirements introduced | 0.2 |  |  |  | 100%
16 |  | 36.521-Tx | 6.6.3.3_1 | Additional Spurious Emissions for UL 64QAM | Updates test requirements (6.6.3.3_1.4) for the new NS_56 and associated additional spurious emissions for B24 in 36.101 | Ligado Networks, Nokia | RAN5#93 (Nov-21) | RAN5#92e: R5-215996 RAN5#93e: R5-218376 | RAN5#92e: Only placeholders for test description and test requirement are being introduced. The actual configurations and associated test requirements to be introduced in RAN5#93e RAN5#93e: Actual configuration and associated test requirements introduced | 0.2 |  |  |  | 100%
17 |  | 36.521-Tx | 6.6.3.3_2 | Additional Spurious Emissions for UL 256QAM | Updates test requirements (6.6.3.3_2.4) for the new NS_56 and associated additional spurious emissions for B24 in 36.101 | Ligado Networks, Nokia | RAN5#93 (Nov-21) | RAN5#92e: R5-215996 RAN5#93e: R5-218377 | RAN5#92e: Only placeholders for test description and test requirement are being introduced. The actual configurations and associated test requirements to be introduced in RAN5#93e RAN5#93e: Actual configuration and associated test requirements introduced | 0.2 |  |  |  | 100%
18 |  | 36.521-Tx | 6.6.3B.3 | Additional Spurious Emissions for UL-MIMO | Updates test requirements (6.6.3B.3.4) for the new NS_56 and associated additional spurious emissions for B24 in 36.101 | Ligado Networks, Nokia | RAN5#93 (Nov-21) | RAN5#92e: R5-215996 RAN5#93e: R5-216436 | RAN5#92e: Only placeholders for test description and test requirement are being introduced. The actual configurations and associated test requirements to be introduced in RAN5#93e RAN5#93e: Actual configuration and associated test requirements introduced | 0.2 |  |  |  | 100%
19 |  | 36.521-1 | Annex F.3.2 | Derivation of Test Requirements for A-MPR for NS_56 | Once configuration Ids are identified for A-MPR test case for NS_56, formulas identified for row 6.2.4 in Table F.3.2-1 need to be mapped | Nokia | RAN5#93 (Nov-21) | RAN5#93e: R5-216432 | RAN5#92e: Updates to be provided at the next meeting RAN5#93e: Updates provided | 0.2 |  |  |  | 100%
20 |  | 36.521-1 | 6.2.2B | UE Maximum Output Power for UL-MIMO | Update the conformance (clause 6.2.2B.3) and test requirements (clause 6.2.2B.5) due to updates to the lower tolerance value for Band 24 PC3 UE | Ligado Networks | RAN5#93 (Nov-21) | RAN5#93e: R5-216527 | RAN5#93e: UL-MIMO MOP updates for B24 were made to 36.101 in RAN4#100e | 0.2 |  |  |  | 100%
21 |  | 36.521-1 | 6.2.3B | Maximum Power Reduction (MPR) for UL-MIMO | Update the test requirement (clause 6.2.3B.5) due to changes to the lower tolerance value for PC3 B24 UE | Ligado Network | RAN5#93 (Nov-21) | RAN5#93e: R5-216527 | RAN5#93e: UL-MIMO MOP updates for B24 were made to 36.101 in RAN4#100e | 0.2 |  |  |  | 100%
TS 36.521-1: RF test cases - Rx
1 |  | 36.521-1 Rx | 7.3 | Reference Senstivity | Update conformance requirements (7.3.3) due to introduction of NS_56 for B24; update test description (7.3.4) due to addition of a new Tx-Rx spacing | Ligado Networks | RAN5#92 (Aug-21) | RAN5#92e: R5-215997 RAN5#93e: R5-216528 | RAN5#93e: Corrected the IE for Band 24 | 0.1 |  |  |  | 100%
2 |  | 36.521-1 Rx | 7.6.1 | In-band Blocking | Update conformance requirements (7.6.1.3) and test requirements (7.6.1.5) to include B24 | Ligado Networks | RAN5#92 (Aug-21) | RAN5#92e: R5-215998 |  | 0.1 |  |  |  | 100%
TR 36.905: Test Point analysis receiver and transmitter test cases
1 |  | 36.905 | <Clause> | TP for NS_56 | TP analysis for NS_56 | Nokia | RAN5#93 (Nov-21) | RAN5#93e: R5-218378 |  | 0.5 | 100% (+100%) | 100% (+100%) |  | 100%
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
1 |  | 36.523-1 | <Clause> | <Title> |  | Ligado Networks | RAN5#93 (Nov-21) | RAN5#93e: R5-217954, R5-217955 | Prose related affected test cases were updated to reflect the different Tx-Rx spacing for High range | 0.2 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.523-3: Protocol test suites (TTCN)
1 |  | 36.523-3 | 11.1 | Updates to guidelines on test execution for LTE Band 24 | Update guidelines to test executions given that only 2 5 MHz channels can be operated due to constraints on DL frequency range operation | Ligado Networks | RAN5#92 (Aug-21) | RAN5#92e: R5-216336 |  | 0.1 | 100% | 100% |  | 100%
2 |  | 36.523-3 | 11.2 | EUTRA - UTRAN - GERAN | Update guidelines for IRAT test execution | Ligado Networks | RAN5#92 (Aug-21) | RAN5#92e: R5-216336 |  | 0.1 |  |  |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.