## Slide 1: Additional Guidelines for RAN1#110bis e-Meeting Management
RAN1 Chair
R1-2208324
3GPP TSG RAN WG1 #110bis-e
e-Meeting, October 10th – October 19th, 2022

## Slide 2: General Aspects
RAN1#110bis-e has the same full decision power as in a regular physical meeting
RAN1#110bis-e will handle
  Critical issues for LS
  Maintenance for Rel-17 & earlier
  Rel-18 work/study items
Primarily based on emails and GTW conference calls
  Detailed schedule for each GTW conference call is expected to be announced as early as possible
    Typically, around 20 hours before the call
No preparation phase before RAN1#110bis-e

## Slide 3: Contribution Submission Deadlines
Tdoc number request: September 30th (Friday), 15:00 UTC
Tdoc submission: September 30th (Friday), 23:59 UTC
Link to draft agenda folder: https://www.3gpp.org/ftp/TSG_RAN/WG1_RL1/TSGR1_110b-e/Inbox/Agenda

## Slide 4: Preparation Phase
No preparation phase outside of RAN1#110bis-e meeting period
  First two days of RAN1#110bis-e will be used to determine which maintenance/LS issues to handle during the rest of the meeting

## Slide 5: LTE/NR Maintenance
Individual draft CRs will be used for all releases
  Final endorsed CR will be sourced by Moderator (company name) and other co-sourcing companies
For Rel-17, FLs will provide the initial tdoc summaries – preferably before the start of RAN1#110bis-e
  First two days of RAN1#110bis-e will be used to determine which issues to handle during the rest of the meeting
  FLs are same as in RAN1#110 unless announced otherwise
  Companies are recommended to provide their initial views by 23:59 (UTC) on Day1 of RAN1#110bis-e
For Rel-16 and previous releases, Chair/VCs will provide further guidance after initial review of tdocs
REMINDER for ALL CRs
  Please make sure the cover page has necessary/correct information (WI code, category, reason for change, summary of change, …). Many people outside of RAN1 depend on these cover pages.
  DO NOT upload the final CR before endorsement. Please give other delegates enough time to check cover pages, add their company as a co-sourcing company, etc.

## Slide 6: Email/GTW Discussions during RAN1#110bis-e
For Rel-18, GTW and email discussions will be used
  For CovEnh, LP-WUS, Mobility, UAV, email discussions are to be kicked off after the initial round of GTW discussions
  For all other WI/SIs, FL’s summaries (capturing list of tdocs, key points, and focus areas) are to be prepared before GTW
For Rel-17, email discussions will be primarily used and GTW is to be used only for selective SI/WIs with controversial issues
  Chair/VCs will announce in advance which Rel-17 WI(s) will be handled using GTW
  Before the GTW sessions, FL’s summaries (capturing list of tdocs, key points, and focus areas) are to be prepared
  GTW session time will be assigned to Rel-17 UE features to expedite the relevant work
For Rel-16 and before, maintenance work will be handled using email discussions unless noted otherwise
The detailed deadline for each email thread is to be announced on a per email thread basis
  Some staggering of deadlines for email threads is possible.
FL’s summary
  For source of each summary, please use “Moderator (Company name)”
  Each summary should have sufficient information about background of the issues, alternatives, & proposals
Please DO NOT send out announcements over the reflector that you have updated the tdoc summaries with your inputs

## Slide 7: GTW Time Slots
Week 1 (October 10 ~ October 14)
  GTW time slot for Day1~4: UTC 12:00 ~ 15:00
  GTW time slot for Day5: UTC 03:00 ~ 06:00
Week 2 (October 17 ~ October 19)
  GTW time slot for Day6 ~ Day8: UTC 03:00 ~ 06:00

## Slide 8: Checkpoints and Comment Deadlines
For each email thread, session chair will assign one or more checkpoints during the meeting
  Checkpoints will be used to endorse stable proposals so that discussions can move forward more efficiently
For each check point, the following deadlines apply
  1st deadline: Companies to provide initial set of comments by the 1st deadline (preferably earlier)
    Delegates should provide the comments before the deadline. Note that it will be very difficult to take into account comments received after the deadline and such comments could make the decision-making process very inefficient.
    FL’s summary taking into account the company comments is expected after the 1st deadline ASAP (while accounting for time differences across regions)
  2nd deadline: conclusion/agreements are to be made at the 2nd deadline
    2nd deadline may be substituted by a GoToWebinar decision making session
  Deadlines are to be observed for all email threads as much as possible, while it’s also up to Chairman’s judgement whether it’s necessary to extend the deadline for some email threads for best progress
  The deadlines will be set such that delegates in all regions can provide their comments during their working hours
  Deadline time reference: UTC 16:59

## Slide 9: Logistics
It’s important to emphasize using an appropriate email thread title for easy tracking (the title for each thread is to be announced)
  E.g., if not done appropriately, after a while an email thread may become something like:
    RE: xxxx
    RE: RE: xxxx
    回复:RE: xxxx
    [External] RE: xxxx
    Etc.
  which makes it very hard to track. PLEASE fix it to RE: xxxx!
  > E.g., do not branch into or use different sub-titles!
All attachments for email discussion are to be uploaded to/downloaded from a server – PLEASE ZIP THEM before uploading
For all email discussion, please make sure the discussion stay technical
  To ensure professional conduct as a community especially during these difficult times

## Slide 10: Email Thread Budget
LTE and NR maintenance for Rel-17 and before
  # of email threads on a per need basis
  Each email thread to handle a specific maintenance issue
    A moderator will be assigned by Chair/Vice-Chair for each email thread
  All CRs, unless decided otherwise, will be sourced by the moderator and possibly co-signed by supporting companies
LTE and NR UE-features
  Generally, 1 email thread per sub-agenda item (i.e. one for UE features topics 1 and one for UE features topics 2)
    Additional email threads may be added if needed
LTE and NR for Rel-18: generally, up to 1 email thread per sub-agenda
  Possible to have >1 email thread per agenda, depending on the necessity
  Details to be announced

## Slide 11: Quiet Period for Email Discussions
To ensure delegates’ rest during the weekends, the following quiet period is mandated
  UTC 11:59pm October 14th – UTC 11:59pm October 16th (48 hours)
During the mandated quiet period, please NO EMAILS & No upload of updated draft documents
  Including moderators for the email threads
Chair/VCs/Patrick may send emails during the quiet period
  Chair/Vice Chairs may use the window of quiet periods to process the email threads based on the information available till the quiet period following the same rules for email approval – no surprises are to be expected for any agreements/conclusions
    If there is any discrepancy, you can always comment after the quiet period

## Slide 12: Conference calls
To use GoToWebinar + TOHRU as the official tool
Some key points
  Please register for all teleconferences as follows:
    First name: “COMPANY – FirstName”
    Last name: “LastName”
  Raise your hands before you talk, and start to talk only after permission from the Chair/VC using TOHRU
  Please, MUTE yourself when not talking
    A clear and noise-free conference bridge is crucial for the entire group
Additional guidance:
  Session management:
    Session chair will call the speaker’s company name and the speaker’s name when granting him/her the permission to talk
    For discussing a proposal, session chair may also call the list of companies who raised hands for the group to understand the overall situation
    When necessary, two or more people may be allowed to talk for more active discussion
  Note that the message function seems to only allow the sender to send to the session chairs, not among attendees
    Session chairs may not always be on alert for messages, but messages can be used to raise questions if/when necessary