3GPP TSG RAN WG1 #110bis-e			R1-2210547

e-Meeting, October 10th – 19th, 2022                            (revision of R1-2208783)

Agenda item:		9.14

Source:	China Telecom

Title:	Work plan for Rel-18 WI on Further NR coverage enhancements

Document for:		Discussion and decision

Introduction

In RAN #94 e-meeting, a new Rel-18 work item on further NR coverage enhancements was approved [1] and updated in RAN #96 [2]. The objective of the work item is to specify further uplink coverage enhancements for PRACH, power domain and DFT-S-OFDM. Detailed objectives are listed as follows:

- Specify following PRACH coverage enhancements (RAN1, RAN2) - Multiple PRACH transmissions with same beams for 4-step RACH procedure - Study, and if justified, specify PRACH transmissions with different beams for 4-step RACH procedure - Note 1: The enhancements of PRACH are targeting for FR2, and can also apply to FR1 when applicable. - Note 2: The enhancements of PRACH are targeting short PRACH formats, and can also apply to other formats when applicable. - Study and if necessary specify following power domain enhancements - Enhancements to realize increasing UE power high limit for CA and DC based on Rel-17 RAN4 work on “Increasing UE power high limit for CA and DC”, in compliance with relevant regulations (RAN4, RAN1) - Enhancements to reduce MPR/PAR, including frequency domain spectrum shaping with and without spectrum extension for DFT-S-OFDM and tone reservation (RAN4, RAN1) - Specify enhancements to support dynamic switching between DFT-S-OFDM and CP-OFDM (RAN1)

This contribution provides the work plan for Rel-18 WI on Further NR coverage enhancements.

Work Plan

The overall work plan for each meeting is shown in Table 1 based on the objectives in [2] and the TU allocation given in [3].

Table 1 Work plan

| Schedule | WG and TU | Work plan |
| --- | --- | --- |
| Oct. 2022 RAN1 #110b-e RAN4 #104b-e | RAN1 (1TU) | - Discuss PRACH coverage enhancement, including: - Multiple PRACH transmission with same beam, including resource configurations, RAR window design and etc. - Multiple PRACH transmission with different beams, including SSB association. - Discuss power domain enhancements, including enhancements to realize increasing UE power high limit for CA and DC, and enhancements to reduce MPR/PAR from RAN1 perspective. - Discuss potential solutions, and identify RAN1 spec. impact. - Send LS to RAN4, if necessary. - Discuss enhancements to support dynamic switching between DFT-S-OFDM and CP-OFDM. |
|  | RAN4 (0.25TU) | - Discuss power domain enhancements. - Send LS to RAN1, if possible. |
| Nov. 2022 RAN1 #111 RAN4 #105 | RAN1 (1TU) | - Further discuss PRACH coverage enhancement, including: - Further discuss the detailed design for multiple PRACH transmissions with the same beam. - Discuss resource configurations for multiple PRACH transmission, and PRACH transmission pattern. - Discuss the candidate number of PRACH transmissions, as well as the indication and the determination of the number of PRACH transmissions. - Discuss RAR window design and related RA-RNTI calculation issues. - Further discuss multiple PRACH transmissions with different beam. - Discuss multiple PRACH transmissions and SSB association. - Discuss and justify if it is needed to specify multiple PRACH transmissions with the different beam. - Discuss the spec. impact. - Further discuss power domain enhancements, including enhancements to realize increasing UE power high limit for CA and DC, and enhancements to reduce MPR/PAR from RAN1 perspective. - Identify RAN1 spec. impact. - Send LS to RAN4, if necessary. - Further discuss enhancements to support dynamic switching between DFT-S-OFDM and CP-OFDM. - Further discuss the indication mechanism of dynamic switching between DFT-S-OFDM and CP-OFDM. - Further discuss the cases whether dynamic switching is supported, e.g., PUSCH scheduled by RAR UL grant, PUSCH scheduled by DCI, PUSCH scheduled by configure grant. - Further discuss the impact on DCI size determination. |
|  | RAN4(0.25TU) | - Further discuss power domain enhancements. - Send LS to RAN1. |
| Feb. 2023 RAN1 #112 RAN4 #106 | RAN1 (1TU) | - Further discuss PRACH coverage enhancement, including: - Further discuss the detailed design for multiple PRACH transmissions with the same beam. - Down-selection on resource configurations for multiple PRACH transmission, and PRACH transmission pattern. - Down-selection on the candidate number of PRACH transmissions, as well as the indication and the determination of the number of PRACH transmissions. - Down-selection on RAR window design and related RA-RNTI calculation issues. - Further discuss multiple PRACH transmissions with different beam. - Conclude whether to specify multiple PRACH transmissions with the different beam. - Further discuss power domain enhancements, including enhancements to realize increasing UE power high limit for CA and DC, and enhancements to reduce MPR/PAR from RAN1 perspective. - Identify RAN1 spec. impact. - Send LS to RAN4, if necessary. - Further discuss enhancements to support dynamic switching between DFT-S-OFDM and CP-OFDM. - Down-selection on the indication mechanism of dynamic switching between DFT-S-OFDM and CP-OFDM. - Further discuss the cases whether dynamic switching is supported, e.g., PUSCH scheduled by RAR UL grant, PUSCH scheduled by DCI, PUSCH scheduled by configure grant. - Further discuss the impact on DCI size determination. |
|  | RAN4 (0.25TU) | - Check whether to conclude to specify enhancements to realize increasing UE power high limit for CA and DC with RAN1 spec. impact. - Check whether to conclude to specify enhancements to reduce MPR/PAR with RAN1 spec. impact. - Send LS to RAN1, if necessary. |
| Apr. 2023 RAN1 #112b-e RAN2 #121b-e RAN4 #106b-e | RAN1 (1TU) | - Further discuss the detailed design for multiple PRACH transmissions with the same beam. - Conclude on resource configurations for multiple PRACH transmission, and PRACH transmission pattern. - Conclude on the candidate number of PRACH transmissions, as well as the indication and the determination of the number of PRACH transmissions. - Conclude on RAR window design and related RA-RNTI calculation issues. - Further discuss the detailed design for multiple PRACH transmissions with different beam. - Conclude, if specified, on the detailed transmission schemes for multiple PRACH transmissions associated with the same SSB or different SSBs. - If power domain enhancement with RAN1 spec. impact is specified, further discuss detailed design on power domain enhancements from RAN1 perspective. - Further discuss enhancements to support dynamic switching between DFT-S-OFDM and CP-OFDM. - Conclude on the indication mechanism of dynamic switching between DFT-S-OFDM and CP-OFDM. - Conclude on the cases whether dynamic switching is supported, e.g., PUSCH scheduled by RAR UL grant, PUSCH scheduled by DCI, PUSCH scheduled by configure grant. - Conclude on DCI size determination. |
|  | RAN2 (0.5TU) | - Address potential RAN2 impacts depending on RAN1 and RAN4 progress. |
|  | RAN4 (0.5TU) | - Conclude whether to specify enhancements to realize increasing UE power high limit for CA and DC. - Conclude whether to specify enhancements to reduce MPR/PAR. - Send LS to RAN1, if necessary. |
| May 2023 RAN1 #113 RAN2 #122 RAN4 #107 | RAN1 (1TU) | - Discuss the remaining aspects of PRACH coverage enhancement. - If power domain enhancement with RAN1 spec. impact is specified, discuss the remaining aspects of power domain enhancements. - Discuss the remaining aspects of enhancements to support dynamic switching between DFT-S-OFDM and CP-OFDM. - Discuss draft CRs. |
|  | RAN2 (0.5TU) | - Address potential RAN2 impacts depending on RAN1 and RAN4 progress. |
|  | RAN4 (0.5TU) | - If power domain enhancement is specified, discuss draft CRs. |
| Aug. 2023 RAN1 #114 RAN2 #123 RAN4 #108 | RAN1 (1TU) | - Conclude on PRACH coverage enhancement. - Conclude on power domain enhancements. - Conclude on enhancements to support dynamic switching between DFT-S-OFDM and CP-OFDM. - Finalize RAN1 CRs. |
|  | RAN2 (0.5TU) | - Address potential RAN2 impacts depending on RAN1 and RAN4 progress. - Discuss draft CRs. |
|  | RAN4 (1TU) | - If power domain enhancement is specified, further discuss draft CRs. |
| Oct. 2023 RAN2 #123b-e RAN4 #108b-e | RAN2 (0.5TU) | - Address potential RAN2 impacts depending on RAN1 and RAN4 progress. - Further discuss draft CRs. |
|  | RAN4 (1 TU) | - If power domain enhancement is specified, further discuss draft CRs. |
| Nov. 2023 RAN2 #124 RAN4 #109 | RAN2 (0.5TU) | - Finalize RAN2 CRs. |
|  | RAN4 (1TU) | - Finalize RAN4 CRs. |

References

- 3GPP RP-213579, “New WI: Further NR coverage enhancements”, China Telecom, RAN#94e, December 6-17, 2021.

- 3GPP RP-221858, “Revised WID on Further NR coverage enhancements”, China Telecom, RAN #96, Budapest, Hungary, June 6-9, 2022.

- 3GPP RP-221060, “Status of time budgets for RAN1/2/3/4 ongoing and new WIs/SIs after RAN #96”, RAN1 Chair (Samsung), RAN2 Chair (MediaTek), RAN3 Chair (ZTE), RAN4 Chair (Huawei), RAN #96, Budapest, Hungary, June 6-9, 2022.