3GPP TSG RAN WG2 #123bis	R2-2310407

Xiamen, China, 9 - 13 Oct, 2023

Agenda Item:	7.3.1

Source:	Rapporteur (Huawei)

Title:	WI Work plan for R18 network energy savings

Document for:	Information

Introduction

A new work item for network energy savings has been approved in RAN#98e as in [1], with objectives as follows

### 4.1	Objective of SI or Core part WI or Testing part WI

The objectives of the work item are the following:

- Specify SSB-less SCell operation for inter-band CA for FR1 and co-located cells, if found feasible by RAN4 study, where a UE measures SSB transmitted on PCell or another SCell for an SCell’s time/frequency synchronization (including downlink AGC), and L1/L3 measurements, including potential enhancement on SCell activation procedures if necessary [RAN4, RAN2]

- Specify enhancement on cell DTX/DRX mechanism including the alignment of cell DTX/DRX and UE DRX in RRC_CONNECTED mode, and inter-node information exchange on cell DTX/DRX [RAN2, RAN1, RAN3]

- Note: No change for SSB transmission due to cell DTX/DRX.

- Note: The impact to IDLE/INACTIVE UEs due to the above enhancement should be avoided.

- Specify the following techniques in spatial and power domains

- Specify necessary enhancements on CSI and beam management related procedures including measurement and report, and signaling to enable efficient adaptation of spatial elements (e.g. antenna ports, active transceiver chains) [RAN1, RAN2]

- Specify necessary enhancements on CSI related procedures including measurement and report, and signaling to enable efficient adaptation of power offset values between PDSCH and CSI-RS [RAN1, RAN2]

- Note: Above objectives are only for UE specific channels/signals

- Note: Legacy UE CSI/CSI-RS capabilities applies when considering total number of CSI reports and requirements

- Specify mechanism(s) to prevent legacy UEs camping on cells adopting the Rel-18 NES techniques, if necessary [RAN2]

- Specify CHO procedure enhancement(s) in case source/target cell is in NES mode [RAN2]

- Specify inter-node beam activation and enhancements on restricting paging in a limited area [RAN3].

- Specify the corresponding RRM/RF core requirements, if necessary, for the above features [RAN4]

### 4.2	Objective of Performance part WI

- Specify corresponding RRM performance requirements and test cases for the network energy saving techniques [RAN4].

- Specify the necessary demodulation performance and CSI reporting requirements [RAN4].

- Specify the BS conformance tests, if necessary [RAN4].

The work plan for this new work item is provided in section 2.

Work Plan

The work plan for WGs is provided in Table 1.

Table 1: WI plan for Network energy savings for NR

| Schedule, WG meeting (TU) | Plan |
| --- | --- |
| Q1, 2023 - RAN1#112 (1 TU) - RAN2#121 (1 TU) - RAN3#119 (0.5 TU) | Initiate the discussion on techniques in spatial and power domains. Initiate the discussion on enhancement related to cell DTX/DRX mechanism. |
|  | Initial discussion on SSB-less SCell operation, cell DTX/DRX mechanism, cell selection/reselection, and CHO enhancement(s) as well as assessment of RAN2 impacts of the potential solutions. |
|  | Initial discussion on the techniques including inter-node beam activation, enhancements on restricting paging in a limited area and inter-node information exchange on cell DTX/DRX. |
| April, 2023 - RAN1#112bis-e (2 TU) - RAN2#121bis-e (1 TU) - RAN3#119bis-e (0.5 TU) - RAN4#106bis-e (0.25+0.25 TU) | Continue the discussion on techniques in spatial and power domains. Continue the discussion on enhancement related to cell DTX/DRX mechanism. |
|  | Continue the discussion and conclude stage-2 details on the following: - DTX/DRX mechanism, including gNB and UE behaviors, configuration/activation/deactivation and alignment - Solution for CHO procedure enhancement(s). |
|  | Continue the discussion on the techniques including inter-node beam activation, enhancements on restricting paging in a limited area and inter-node information exchange on cell DTX/DRX. Start drafting and endorse BLCRs. |
|  | Discuss on SSB-less SCell operation for inter-band CA and potential enhancement on SCell activation procedures and the corresponding RRM/RF core requirements for relevant objectives. |
| May, 2023 - RAN1#113 (2 TU) - RAN2#122 (1 TU) - RAN3#120 (0.5 TU) - RAN4#107 (0.5+0.5 TU) | Continue the discussion into further details, identify any remaining issues including RAN1 impact for - techniques in spatial and power domains - mechanism related to cell DTX/DRX. |
|  | Continue the discussion on the stage-2 and stage-3 details of the solutions and RAN2 impacts. Start drafting and endorsing stage-2 skeleton CRs. |
|  | Continue the discussion on the stage-2 and stage-3 details of the solutions and RAN3 impacts. Further work and endorse BLCRs. |
|  | Conclude the feasibility of SSB-less SCell operation for inter-band CA and identify necessary enhancements SCell activation procedures. Discuss further on the corresponding RRM/RF core requirements. |
| August, 2023 - RAN1#114 (2 TU) - RAN2#123 (1 TU) - RAN3#121 (0.5 TU) - RAN4#108 (0.5+0.5 TU) | Finalize the discussion for techniques in spatial and power domains, and mechanism related to cell DTX/DRX from RAN1 perspective. Endorse the corresponding draft CRs. |
|  | Finalize the solutions for cell DTX/DRX, spatial and power domain techniques, cell selection/reselection, and CHO enhancement. Update and endorse running stage-2 CRs. Initiate drafting stage-3 running CRs. |
|  | Continue the discussion on the stage-2 and stage-3 details of the solutions and RAN3 impacts, including: - inter-node beam activation, enhancements on restricting paging in a limited area and exchange of cell DTX/DRX. Address the questions in the reply LS from SA2, and provide feedback. Further work on and endorse BLCRs. |
|  | Resolve the remaining issues for SSB-less SCell operation including SCell activation enhancements, and the corresponding RRM/RF core requirements for relevant objectives. Provide draft CRs. |
| October, 2023 - RAN2#123bis-e (1 TU) - RAN3#121bis-e (0.5 TU) - RAN4#108bis-e (0.5+0.5 TU) | Resolve remaining issues, and update running CRs. |
|  | Send reply LS to SA2 to answer the questions. Resolve remaining issues, and endorse the BLCRs. |
|  | Discuss further on draft CRs and formulate formal CRs. |
| November, 2023 - RAN2#124 (1 TU) - RAN3#122 (0.5 TU) - RAN4#109 (0.5+0.5 TU) | Resolve remaining issues, if any, and approve stage-2 and stage-3 CRs. |
|  | Finalize remaining issues, and endorse the BLCRs. |
|  | Endorse CRs for RRM/RF core requirements. |

- References

RP-223540, Huawei, New WID: Network energy savings for NR.