## Combined_Tables
RIL Id | WI | Class | Title | Tdoc | Delegate | Misc | File version | Status | Rapportaur comments
V230 | LTE to NR NTN mobility | 1 | Clarification for SMTC offset adjustment for LTE TN to NR NTN mobility | N | vivo (Stephen) |  | v002 | PropAgree | Rapporteur’s comments: Thanks for raising this RIL. Agree, the modification will be captured in the CR for companies to further comment on. The suggested wording is slightly different from [V230]’s version, the purpose is to align with the field description of measTimingConfig in SIB24.
S905 | LTE to NR NTN mobility | 1 | Clarify which neighSatelliteInfoList to use for redirection | Y | Samsung (Jonas) |  | v003 | ToDo | Thanks for raising this RIL. This RIL is related with TEI19 for TN to NTN redirection. We can further discuss how to solve it based on companies’ contributions.
X500 | LTE to NR NTN mobility | 1 | Clarify the smtc in the CarrierInforNR-r19 | Y | Xiaomi (Xiaolong Li) |  | v005 | ToDo | Thanks for raising this RIL. This RIL is one of open issues based on last meeting progress. We can further discuss based on companies’ contributions.
O711 | LTE to NR NTN mobility | 1 | Include the satellite information for dedicated priority | Y | OPPO (Haocheng Wang) |  | v005 | ToDo | Thanks for raising this RIL. This RIL is one of open issues based on last meeting progress. We can further discuss based on companies’ contributions.
E801 | LTE to NR NTN mobility | 1 | Unnecessary complexity by including multiple satellite IDs for a single carrier frequency | Y | Ericsson (Ignacio) |  | v007 | ToDo | Thanks for raising this RIL. This RIL was raised during post email discussion phase after RAN2#131. We can further discuss based on companies’ contributions.