3GPP TSG-RAN WG4 Meeting #114	R4-2500818

Athens, Greece, Feb 17th – Feb 21st, 2025

Source:	Nokia

Title:	Discussion on General Aspects on SCM SI

Agenda item:	7.16.1

Document for:	Discussion

Introduction

During RAN#104 the study item on Spatial Channel Model was agreed, whereby the SI started during RAN4#112, within this contribution we present some views on the work plan of the Study Item as well as details of what Nokia believes should be included in TR 38.753.

Discussion

Work Plan

To provide a reminder the following table is the work plan agreed during RAN4#112 and captured in the way forward from there [2].

| Meeting No. | Date | Details |
| --- | --- | --- |
| RAN4#112 | August 24 | Identify Existing Limitations (Phase 1): Scenario Discussed and early Alignment Initial Scenario Configuration Alignment Explore Modelling Approaches (Phase 2): Potential approaches to channel modelling discussed |
| RAN #105 (September 25) |  |  |
| RAN4#112-bis | October 24 | Identify Existing Limitations (Phase 1): Scenarios agreed Explore Modelling Approaches (Phase 2): Initial simulation parameter alignment Considered channel model alignment |
| RAN4#113 | November 24 | Explore Modelling Approaches (Phase 2): Simulation parameters agreed Develop Test Methodology (Phase 3): Testability Discussions Initial simulations Document Conclusions (Phase 4): Draft TR structure agreed Work split agreed |
| RAN #106 (December 25) |  |  |
| RAN4#114 | Feb 25 | Develop Test Methodology (Phase 3): Simulation Alignment Document Conclusions (Phase 4): Initial discussion on potential conclusions Draft TPs |
| RAN #107 (March 25) |  |  |
| RAN4#114-bis | March 25 | Develop Test Methodology (Phase 3): Further Simulation Alignment Document Conclusions (Phase 4): Draft conclusions Draft TPs |
| RAN4#115 | May 25 | Document Conclusions (Phase 4): big pCR |
| RAN #108 (June 25) |  |  |

As can be seen, the Study Item is due for completion by RAN#108, therefore it is imperative that the plan which was agreed during RAN4#112 is stuck to in order to maintain progress in the SI.

During RAN4#113 significant efforts were made to drive forward both the SU-MIMO scenarios (with some aspects left open) and to have some down selection on MU-MIMO scenarios

During RAN4#113 significant progress was achieved on SU-MIMO scenarios, however further down-selection of MU-MIMO is required at RAN4#114

Furthermore, during RAN4#112-bis and RAN4#113 there was also significant progress made on spatial channel modelling methodologies, however there are still some open issues, notably AAV candidates for CDL models, and down selection of TDL Variants.

During RAN4#112-bis and RAN4#113 significant progress was achieved on spatial channel modelling methodologies, however there are several open issues, notably AAV candidates for CDL models, and downselection of TDL Variants.

In order to maintain good progress of the Study Item during RAN4#113 the demodulation contingent of RAN4 should aim to align the Spatial Channel Model approach using the stable SU-MIMO cases. If alignment cannot be made, a series of assumptions could be shared offline and during RAN4#113 companies should attempt to identify a route to alignment.

and make strong progress on MU-MIMO.

RAN4 shall align SCM candidates during RAN4#114 using previously agreed SU-MIMO cases

RAN4 shall attempt to finalise the MU-MIMO cases during RAN4#114

Technical Report

During RAN4#112-bis the skeleton of TR 38.753 was agreed, for which RAN4 should now drive progress on.

During RAN4#113 the TR structure was agreed along with a work split, therefore Nokia proposes that during RAN4#114 delegates bring pCRs in order to provide information and have further information to the TR skeleton of [3] along with assessing whether further clauses or refinement are required

RAN4 shall start to develop the TR of 38.753 and whether further clauses are required, or refinement is required.

Conclusion

The paper discusses general items relating to the topic of Spatial Channel Modelling into RAN4 and presents some of the Nokia views on this topic for discussion during RAN4#112-bis.

The following Observations and Proposals were made:

Observation 1: During RAN4#113 significant progress was achieved on SU-MIMO scenarios, however further down-selection of MU-MIMO is required at RAN4#114

Observation 2: During RAN4#112-bis and RAN4#113 significant progress was achieved on spatial channel modelling methodologies, however there are several open issues, notably AAV candidates for CDL models, and downselection of TDL Variants.

Proposal 1: RAN4 shall align SCM candidates during RAN4#114 using previously agreed SU-MIMO cases

Proposal 2: RAN4 shall attempt to finalise the MU-MIMO cases during RAN4#114

Proposal 3: RAN4 shall start to develop the TR of 38.753 and whether further clauses are required, or refinement is required.

- References

- RP-241610; “Study on spatial channel model for demodulation performance requirements”, Nokia, BT Plc et al, RAN#104, Shanghai, June 2024.

- R4-2413606, “Way Forward for [112][327] FS_NR_demod_SCM”, Moderator (Nokia), RAN4#112, Maastricht, August 2024

- R4-2416549, “TR 38.753 Skeleton”, Nokia, Ericsson, Qualcomm, RAN4#112-bis, Hefei, October 2024