3GPP TSG RAN WG4 Meeting #114	 								                 R4-2502291

Athens, Greece, February 17 – 21, 2025

Title:	Work plan for WID: introduction of IoT-NTN TDD mode

Source:	Iridium

For:	Information

Agenda Item:	7.31

Release:	Release-19

WI:	Introduction of IoT-NTN TDD mode

# Introduction

A new WID Introduction of IoT-NTN TDD mode [1] was approved in RAN #105. That WID has been revised in RAN #106, as the study phase had been completed.

In this contribution, a work plan for Revised WID on Introduction of IoT-NTN TDD mode [2] is proposed for RAN 1, 2, and 4.

# WID Objective

Core part WI

The work item aims to specify enhancements for NB-IoT NTN to enable NTN operation with a NB-IoT TDD mode leveraging commonalities with half-duplex NB-IoT FDD NTN, by defining a new NB-IoT TDD mode for NTN based on minimum necessary changes to the NB-IoT NTN FDD frame structure and procedures for the NB-IoT operation in the targeted unpaired MSS allocated band (TN deployment is not expected in this band). The feature is not intended to be applicable to existing 3GPP bands.

The work objectives assume the following:

- LEO @600 km and @1200 km orbit respectively, with set-1 satellite parameters as reference scenarios (See 3GPP TR 36.763)

- Target the 1616-1626.5 MHz MSS allocated band

- Standalone deployment with anchor and non-anchor carriers (i.e. operating in carrier(s) used only for NB-IoT)

- Operate with Earth fixed Tracking area, with either Earth fixed cells or Earth moving cells for NGSO

- The new NB-IoT NTN TDD mode allows configuring the usage of radio resources in the targeted MSS allocated band with a periodic subset of the UL and DL subframes in N radio frames. The periodic pattern should consist of non-overlapping set of usable contiguous UL subframes (U) and set of usable contiguous DL subframes (D), and guard periods, which is periodic every N radio frames, with N=9 for the target MSS allocated band.

This work item includes the following objectives:

- Specify a new NB-IoT TDD NTN mode based on minimum necessary changes to the NB-IoT NTN FDD frame structure and procedures, including:

  - Definition, configuration (if needed) and signaling (if needed) of the periodic pattern, necessary adaptation (if needed) and associated UE procedures [RAN1, RAN2]

      - Support a pattern with a period of 9 radio frames for the target MSS allocated band, where D=U=8 with a fixed guard period. RAN1 to consider whether there is a need for a mechanism to achieve an adjustable guard period for the purpose of allowing deployment with the TDD frame structure of the legacy system operating in the target MSS allocated band.

  - Other necessary impacts on higher layers [RAN2]

  - RRM and RF core requirements [RAN4]

- Specify a new NB-IoT TDD operating NTN band for the MSS allocation spanning 1616-1626.5 MHz for DL and UL, based on the outcome of the study, to be used as example band for this WI [RAN4].

  - Specify band numbering

  - Specify SAN and UE RF characteristics

  - Specify DL and UL channelization.

  - Specify channel bandwidth as 200 kHz

  - Note1: No NTN-NTN coexistence study needed.

  - Note2: Leverage existing work as much as possible for TN-NTN coexistence of adjacent bands

Note3: Reuse the existing RAN4 requirements as much as possible (no intention to have any relaxation of the RF emissions requirements)

Performance part WI

Specify the following:

- RRM performance requirements, as needed [RAN4]

- Necessary SAN and UE demodulation requirements [RAN4]

- SAN conformance testing requirements [RAN4]

# Work Plan

The Work Plan for RAN1, 2, and 4 is provided in Table 1:

Table 1: RAN1, 2, and 4 Work Plan

| Quarter | Meeting # | TU | Work plan |
| --- | --- | --- | --- |
| RAN#105 (Sep. 2024) | RAN1#118bis | 0.5 | - Agree on assumptions and parameters to be used in the evaluation of TDD periodic pattern, by considering N=9 as a baseline - Define the evaluation methodology and relevant metrics for evaluations - Evaluate the impact due to the periodic pattern, particularly on UE downlink synchronization - Commence the work from Oct’24 and aim to complete the study phase by RAN#106 checkpoint |
|  | RAN2#127bis |  |  |
|  | RAN4#112bis |  |  |
|  | RAN1#119 | 0.5 | - Continue to evaluate the impact due to the periodic pattern, particularly on UE downlink synchronization - Confirm the value of N and TDD pattern parameters - Conclude the evaluation and assessments |
|  | RAN2#128 | 0 | - Work Plan submission for Information. |
|  | RAN4#113 | 0 | - Start specifying a new NB-IoT TDD operating NTN band for the MSS allocation spanning 1616-1626.5 MHz for DL and UL. This includes detailing: - Band numbering & band definition (including EARFCN, raster etc.), DL and UL channelization, and specifying a channel bandwidth of 200 kHz (180 kHz occupied bandwidth) - Start discussion on SAN & UE RF requirements that can be re-used from previously defined S/L band. Address RRM and RF core requirements associated with the new NB-IoT TDD NTN mode Discuss requirements stemming from introduction of TDD mode for NB-IoT NTN and potential impact of the periodic pattern to RRM: contiguous subframes used, DL-UL gap |
| RAN#106 (Dec. 2024) | RAN1#120 | 0.5 | - Agree on the set of TDD pattern parameters - Complete analysis of SI decoding, NPD/PUSCH, NPRACH, NPDCCH - Identify potential specification impacts |
|  | RAN2#129 | 0.5 | - Start discussion on TDD support for NB IoT NTN - Identify potential impacts on higher layers |
|  | RAN4#114 | 0.5+0.25 | - Decide on RF, discuss on RRM requirements that can be re-used from previously defined S/L band. - Conclude on requirements stemming from introduction of TDD mode for NB-IoT NTN and potential impact of the periodic pattern: contiguous subframes used, DL-UL gap. |
| RAN#107 (Mar. 2025) | RAN1#120bis | 0.5 | - Discuss remaining aspects on the TDD support in NB IoT NTN - Discuss (if needed) related RRC parameters and send LS to RAN2 - Discuss Draft CRs |
|  | RAN2#129bis | 0.5 | - Further discuss and down-select solutions to support TDD for NB IoT NTN - Conclude on potential impacts on higher layers - Start the definition and configuration of signalling of the periodic pattern, and associated UE procedures (if any) |
|  | RAN4#114bis | 0.5+0.25 | - Discuss the UE AMPR, UE frequency error requirement, - Discuss repetition number to be considered (associated with D/U=8 for 8 ms Rx/Tx time and N=9 for 90 ms periodicity) for both UE and SAN - Discuss (at least) FRC for REFSENS, in-channel selectivity, dynamic range, and related parameters such as number of tones, Tx/Rx time, related SNR target for specific FRC configuration. - Discuss (if needed) the equations to be used to derive (at least) above mentioned requirements based on different FRC configurations discussed. - Discuss work split for UE and SAN RF part (TS 36.102, TS 36.108 and prepare TS 36.181 work split according to potential impacts) |
|  | RAN1#121 | 0.5 | - Conclude on the solutions for the TDD support in NB IoT NTN - Further discuss (if needed) related RRC parameters and send LS to RAN2 - Finalize RAN1 CRs |
|  | RAN2#130 | 0.5 | - Complete the definition and RRC configuration of signaling of the periodic pattern, and associated UE procedures (if any) - Conclude support of TDD mode in NB IoT NTN - Discuss stage-2 design of TDD support in NB IoT NTN - Discuss RAN2 CRs |
|  | RAN4#115 | 0.5+0.25 | - Continue discussion on the UE AMPR, UE frequency error requirement - Continue discussion on repetition number to be considered (associated with D/U=8 for 8 ms Rx/Tx time and N=9 for 90 ms periodicity) for both UE and SAN, - Continue discussion (at least) FRC for REFSENS, in-channel selectivity, dynamic range, and related parameters such as number of tones, Tx/Rx time, related SNR target for specific FRC configuration, - Derive related values for the at least for previous mentioned requirements: REFSENS, in-channel selectivity, dynamic range, etc., - Start discussion on UE and SAN CRs for RF part and SAN conformance testing, - Start CR split to prepare Draft CRs for the Core requirements |
| RAN#108 (Jun. 2025) | RAN1#122 |  |  |
|  | RAN2#131 | 0.5 | - Finalize stage-2 design on support of TDD in NB IoT NTN - Finalize RAN2 CRs - Conclude on the remaining aspects, if any |
|  | RAN4#116 | 0.5+0.25 | - Finish CRs for RF part - Finish CRs for RRM part |
| RAN#109 (Sep. 2025) | RAN1#123 |  |  |
|  | RAN2#132 |  |  |
|  | RAN4#117 | 0.25 | - Start discussion on demodulation performance and specific configuration related to the new TDD pattern |
| RAN#110 (Dec. 2025) | RAN1#123bis |  |  |
|  | RAN2#132bis |  |  |
|  | RAN4#117bis | 0.25 | - Continue discussion and drafting CRs for demodulation performance - Start drafting demodulation performance CRs |
|  | RAN1#124 |  |  |
|  | RAN2#133 |  |  |
|  | RAN4#118 | 0.25 | - Finish demodulation performance CR |

# References

- RP-242415 	New WID on introduction of IoT-NTN TDD mode, 3GPP TSG RAN Meeting #105,  Melbourne, Australia, September 9-12, 2024

- RP-243293		Revised WID on introduction of IoT-NTN TDD mode, 3GPP TSG RAN Meeting  #106,  Madrid, Spain, December 9-12, 2024