## Slide 1: RAN4#97-e E-meeting Arrangements and Guidelines
RAN4 Chair: Steven Chen
Vice Chairs: Haijie Qiu, Andrey Chervyakov
3GPP TSG-RAN WG4 Meeting #97-e R4-201xxxx
Electronic Meeting, Nov. 2 - 13, 2020
Agenda Item: 2

## Slide 2: General Aspects
The tdoc submission deadline is 11:59pm UTC on Friday Oct. 23, 2020
The E-meeting will take place during Nov. 2 – 13.
  Email discussions consisting of a number of email threads moderated by designated moderators will be the main means.
  GoToWebinar (GTW) conference calls will be used and are considered online sessions.
Email discussions will be carried out on RAN4 email reflector 3GPP_TSG_RAN_WG4@LIST.ETSI.ORG
Please register for RAN4#97-e. Being registered to the meeting is a prerequisite to join the GoToWebinar conference calls
The focus is on R16 maintenance, completion of R16 core part (for NR-U) and R16 perf part, and further updating of UE feature list.
This E-meeting shall have full decision power. Note that “Annex I: Special procedures for exceptional situations restricting travel” of the 3GPP Working Procedures has been activated to enable the use of the formal Working Agreement mechanism.

## Slide 3: General Aspects
Chair/session chairs announcement on meeting management will be shared on a dedicated email thread
  Including tdoc request and assignment, meeting report update, GTW schedule and agenda
  [100] for Main session, [200] for RRM session, [300] for BS/Testing/Demod session
Please refer to RAN4 Meeting Efficiency Improvements slides (available at ftp://3gpp.org/tsg_ran/WG4_Radio/TSGR4_96_e/Inbox/Meeting_Arrangements/RAN4%20meeting%20improvements%20v1.6%20-%20Final.pptx ) for tdoc submission and handling
When bringing the official CRs for the Draft CRs endorsed in previous meeting:
  Include information on the endorsed Draft CR in the CR coversheet: “Resubmission of endorsed Draft CR R4-200xxxx”).
  In case of additional changes, use track changes with different tracking ID i.e. (“Endorsed RAN4#94-e-bis” and “Additional Changes RAN4#95-e” ) and summarize the changes in coversheet

## Slide 4: Email discussion procedures/timelines
Week before the E-meeting (Oct. 26 - 30)
  Monday (Oct. 26): email discussion moderators will be announced by session chairs (aligned template will be provided and used)
  Monday – Friday (Oct. 26 - 30): moderators prepare summary materials for email discussion
    Moderators should identify key open issues, summarize proposals and recommend topics/questions to be handled via email discussions. Moderators are encouraged to provide recommendation on prioritization of discussion and whether any issues should be postponed.
    Moderators should provide the summary on the RAN4 reflector by UTC 23:59 PM Thursday Oct. 29
    Friday Oct. 30: Companies provide comments on initial summaries

## Slide 5: Email discussion procedures/timelines
  E-meeting (Nov. 2-13)
  Stage 0: Session chairs announce the set of email threads (no later than Monday 8am UTC, Nov. 2)
  Stage 1: Moderators kick off email discussion (Monday Nov. 2)
  Stage 2: Companies provide comments for the 1st round (Nov. 2 – Wednesday 6pm UTC Nov. 4)
  Stage 3: Moderators summarize the status and possible proposals, recommending what decisions can be made for 1st round. A formal t-doc will be used (Thursday 6pm UTC, Nov. 5)
  Stage 4: After receiving the summary from moderators, session chair may approve documents, make agreements or assign new CRs, WFs, LSs, etc. (no later than Monday 8am UTC, Nov. 9)
  Stage 5: Companies provide comments for 2nd round.
    Draft WF/LS and revised CRs/TPs shall be shared by Wednesday 1am UTC, Nov. 11.
    Commenting shall stop by Wednesday 11pm UTC, Nov. 11.
    Formal tdocs of WF/LS/CRs/TPs shall be uploaded to the Inbox (except Cat A CRs) by Thursday 1am UTC, Nov. 12.
    Draft moderator summary shall be shared by Thursday 9am UTC, Nov. 12, but moderators are strongly encouraged to share it earlier if possible and delegates to comment as early as possible.

## Slide 6: Email discussion procedures/timelines
  E-meeting (Nov. 2-13)
  Stage 6: Moderators provide 2nd round summary with a formal tdoc by Thursday 6pm UTC, Nov. 12.
  Stage 7: Session chairs announce close of sessions (no later than 6pm UTC, Nov. 13). Final decisions will be captured in Chairman meeting report (to be shared after the meeting is closed)
Note that the above deadlines will be strictly enforced. Comments, tdocs, or drafts submitted after the deadlines will not be considered.

## Slide 7: Use of GoToWebinar
GoToWebinar conference calls are scheduled on
  Nov. 3 - 6 (4am-7am UTC)
  Nov. 9 - 13 (1pm-4pm UTC)
  Those calls are considered online sessions
GoToWebinar conference calls are to be formally announced about 16 hours before the conference call pending session chairs’ arrangement.
In GoToWebinar sessions, session chairs will mainly treat WF, LS, or other critical issues. So please share such tdocs before the call
  Moderators can recommend to sessions chairs which topics to treat
  Agenda will be shared in advance by session chair
For each session, i.e. Main session, RRM session, BS/Testing/Demod session, there will be a dedicated folder. Tdocs/drafts to be treated in GTW should be uploaded to this folder before the start of the session.

## Slide 8: [To be updated] E-meeting timelines in a nutshell
2nd round
1st round
Pre-meeting
Mon (8.17th)
Meeting starts
8:00 am
Tue (8.18th)
Wed (8.19th)
Thu (8.20th)
Fri (8.21th)
Quiet Period
Mon (8.24th )
Tue (8.25th )
Wed (8.26th)
Thu (8.27th)
Fri (8.28th)
Sat/Sun
0:00 (UTC)
8:00 (UTC)
16:00 (UTC)
24:00 (UTC)
12:00 (UTC)
1st round comments
5:00 pm
1st round summary
5:00 pm
Session chairs update report and t-doc assignment
Quiet period
3:00 am
Sat
~
11:00 pm Sun
2nd round summary
5:00 pm
Meeting closes
5:00 pm
Thu (8.13th)
Fri (8.14th)
Initial summary 11:59 pm
Comments on initial summary
GTW session
3:30 -6:00 am
GTW session
12:30 -3:00 pm
GTW session
12:30 -3:00 pm
GTW session
12:30 -3:00 pm
GTW session
12:30 -3:00 pm
GTW session
12:30 -3:00 pm
Timeline for moderator summary
Timeline for comments and t-doc
GTW session
Note: 1) all times are in UTC; 2) Basket WIs Email discussion procedures/timelines are not included.
GTW session
3:30 -6:00 am
GTW session
3:30 -6:00 am
GTW session
3:30 -6:00 am
2nd round
final t-doc submission
1:00 am
2nd round comments
11:00 pm
Draft WF/LS and revised CRs/TPs
Shared by 1:00 am

## Slide 9: Basket WIs Email discussion procedures/timelines
Handling of basket WIs (LTE baskets, i.e. AI 14.1-14.5, and NR baskets, i.e. AI 10.1 – 10.17) related draft CRs/TPs will follow the following process and timelines. Note: there is only one round of email discussion for basket WIs.
Tuesday Oct. 27: basket WI moderator will provide a list of contributions for flagging. The flag deadline is Friday 6pm UTC Oct. 30
Companies can flag contributions using the basket email thread title and the specific reason(s) of flag in the email, e.g.,
Tdoc Title Reason for discussion
R4-20xxxxx xxxx xxxx

## Slide 10: Basket WIs Email discussion procedures/timelines (cont.)
Monday Nov. 2: basket WI moderator will provide the updated list of contributions, in which:
  those that were not flagged will be considered “agreeable”
  those that were flagged will be revised. The authors are encouraged to share the revisions as soon as possible for further comments.
By Thursday 6pm UTC, Nov. 5, all revised tdocs need to be available and final comments be received
By Friday 6pm UTC, Nov. 6, basket WI moderators will provide a summary of the status of those flagged and revised tdocs. This summary should capture the following info:
  the reason for flagging
  if the revision is available
  if the revision is agreeable by addressing received comments).
Based on the summary, session chair will announce decisions by Tuesday 6pm UTC, Nov. 10
Revised WIDs and big CRs need to be available by 6pm UTC, Nov. 16 for email approval.

## Slide 11: Notes on email discussions
Delegates are strongly encouraged to provide comments/concerns asap
  Silence within a reasonable timeframe means no objection
It is strongly encouraged that each company/delegate consolidate their comments/views and send them out in one email for each email thread

## Slide 12: Notes on email discussions (cont.)
Each email thread needs to use a clear and consistent thread title for easy tracking (the title for each thread is to be announced)
      E.g., if not done appropriately, after a while an email thread may become something like:
        RE: xxxx
        RE: RE: xxxx
        回复:RE: xxxx
        [External] RE: xxxx
        Etc.
        which makes it very hard to track. PLEASE fix it to RE: xxxx!
Some instruction how to get “RE:” in Word:
https://www.extendoffice.com/documents/outlook/4495-outlook-reply-subject-prefix.html

## Slide 13: Notes on email discussions (cont.)
Please upload your drafts or formal tdocs to the online server. Avoid using email attachment (especially large attachments) for sharing drafts, which may cause email problems. In the Drafts folder, each email discussion thread will have its own sub-folder
  Note if delegates experience persistent problems or issues when uploading the drafts, they can email it to Kai-Erik.
Length of file names shall be reduced, e.g.
  Old: / ftp / tsg_ran / WG4_Radio / TSGR4_96_e / Inbox / Drafts / [96e][227] FS_NR_MIMO_OTA_test\Email discussion summary for [96e][227] FS_NR_MIMO_OTA_test 2nd round_QC_RS_KS_CAICT_Samsung_RS_Spirent_KS_QC_RS.docx
  New: / ftp / tsg_ran / WG4_Radio / TSGR4_96_e / Inbox / Drafts / [96e][227] FS_NR_MIMO_OTA_test\Summary_227_2nd round_QC_RS_KS_CAICT_SS_RS_Spirent_KS_QC_RS.docx

## Slide 14: Notes on GoToWebinar sessions
GTW session invites will be sent to delegates registered to the RAN4 #96-e meeting only. No invitations for the GTW sessions will be sent to RAN4 reflector.
Meeting registration deadline is encouraged to be able to generate the invitee list early. It is set to 22h UTC Friday Aug 14 for this meeting.
Please make sure your name in GoToWebinar is shown as “company name – first name last name”
GTW phone dial-in numbers will be provided in the invitation
GTW phone customer support number at URL https://support.goto.com/webinar/help/how-do-i-contact-gotowebinar-customer-support-g2w090151

## Slide 15: Quiet period for the e-meeting
Quiet period: 3am UTC Saturday Nov. 7 – 11pm UTC Sunday Nov. 8 (44 hours)
  Delegates are not expected to read or send emails during this period.
  Session chair can communicate decisions during this period, but these are expected to be read only after the quiet period ends.

## Slide 16: Role of Moderators
Moderator is a neutral technical competent facilitator of the discussion, provides timely summaries
Feedback on moderator performance is expected to be given privately to the Chair
Tdoc of a moderator summary is sourced “Moderator (company name)”