## WP scope
Work plan for introduction of NR FR2 bands and/or CBW extensions to existing bands into 3GPP UE conformance test specifications
| WP template: | WP NR band and CBW FR2 v1.14.0
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed.
Workplan scope
| Workplan Name |  | WP NR CA PC3 FR1 v1.14.0 | [5 empty] | <= Default workplan name is the filename. To change replace the formula with preferred text.
| Company (Contact) | [7 empty] | <= Enter Responsible Company and Contact for the configurations in the WP
| Target completion |  | TBD | [5 empty] | <= Enter target completion date here. Format RAN5#<xx>, where <xx> is the RAN5 meeting, e.g. RAN5#94-e>
Comments
Overall completion
Target configurations
Copy target configuration(s) for the WP from the "PRD21 NR bands and 5G NR CADC list" as values in the table below by: 1. Select and copy the complete rows of the target configuration(s) in the "PRD21 NR bands and 5G NR CADC list". 2. Select cell A15 in the table below and right-click. 3. Select paste option "Paste as values" (see picture). It may take a few seconds before the pasted information is shown. 4. To include additional configurations, repeat steps 1 to 3, but in step 2 select the cell in column A next below the last configuration in the list.
Marked config | Release introduced in TS 38.101-x | Type of band | TS and Source Table | NR band / NR band CBW Extension | CBWs SCS[kHz]:[MHz]+...+[MHz] | PC3 Status | Completed Power Class(es) | RAN5 Completion Meeting (PC3) | Completion Reference (PC3) | Interested operator (PC3) | Responsible Company (contact) (PC3) | Assignment [RAN5 meeting] (PC3) | Applicable RAN5 WI code(s) for CRs | Band Sort Key | Comments | Introduced in PRD version
[6 empty] | Ongoing | PC3 | [6 empty] | n258 |  | v1.0.0

## WP NR band and CBW FR2
Work plan for introduction of NR FR2 bands and/or CBW extensions to existing bands into 3GPP UE conformance test specifications
Note! A copy of this work plan shall be included in a Completion Declaration Statement (CDS) to be submitted as a TDOC to the RAN5 meeting when the configuration(s) are completed. | [13 empty] | WP template: WP NR band and CBW FR2 v1.14.0
1. Configurations covered by the work plan
|  | Type of CA configurations |  |  |  | WP item Applicability Label | CA configurations [DL/UL]
|  | New NR band(s) |  |  |  | New Band
|  | New CBW(s) to existing band(s) |  |  |  | New CBW
|  | All configurations |  |  |  | All
2. Overall status vs WP steps
[7 empty] | Overall Sub-WI |  | Handling of not applicable WP item rows: - WP item rows not applicable for the target configurations are indicated as being strikethrough text. You can hide those not applicable WP items by filtering on excluding "(Blanks)" in column "Impacted config(s)". - Some WP items may still not be applicable for the target configurations based on the applicability information in the "Task" column. To NOT include those WP items in the overall status calculations You need to clear the "Detailed Completion Status" cells for the WP item row and state "N/A" in the comments field. Note: It is not recomended to completly delete not applicable WP item rows in case additional target configurations added at a later stage may require those WP Item rows.
Overall completeness
Step 1: Work plan pre-requisite
Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations
Step 3.1: CR(s) to common test environment (TS 38.508-1)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-2)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-2, clause 6)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-2, clause 7)
Step 3.5: CR(s) for RRM and Location Services test cases (TS 38.533 and TS 37.571-1)
Step 3.6: CRs to protocol test cases (TS 38.523-3)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
3. Details
Do not edit | [7 empty] | WP item columns to be filled in |  |  |  | Do not edit |  |  | WP item columns to be filled in
Step 1: Work plan pre-requisite
WP item applicability | WP item ID | Area | TS/PRD | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
Bands completed
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
New CBW | 1-1 | Pre-requisite | PRD21 | NR bands worksheet | NR band completed for initial set of CBWs |  | Set status in column "Bands completed" to 100% if NR band and its initial set of CBWs is confirmed as completed in RAN5 PRD21 worksheet "NR bands". |  | TBD |  |  | 1 |  |  | 0%
New Band | 1-2 | Pre-requisite | 38.521-2 | 6, 7 | All applicable Transmitter (clause 6), Receiver (clause 7) test cases have been completed including MU/TT analysis for the Frequency sub-range (as defined in 38.521-2, Table 5.1-2. Note! With exception of the specific band aspects that are covered by the WP items in step 3.3 (Tx) and 3.4 (Rx) |  | Set status in column "TCs available" to 100% when all applicable test cases in 38.521-2 ihave been completed ncluding MU/TT analysis for the Frequency sub-range the band belongs to with the exceptions stated in the "Task" column. If the relevant test cases are not completed for the frequency sub-range then contact the TS rapporteur or the rapporteur of the WI introducing the test case (see RAN5 PRD17) and consider to support to get the test case(s) completed. |  | TBD |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 2: Complete Test Point (TP) analysis for impacted NR CA configurations
WP item applicability | WP item ID | Area | TR | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
TP analysis
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
New Band | 2-1a | TP Analysis | 38.905 | 4.2.2 | Test point (TP) analysis for A-MPR - New band |  | If new NS value is introduced by the new band then document the test point analysis A-MPR and single carrier else clear the status column. |  | TBD |  |  | 1 |  |  | 0%
New CBW | 2-1b | TP Analysis | 38.905 | 4.2.2 | Test point (TP) analysis for A-MPR - New CBW |  | Check if there is a need to updated the test point analysis for A-MPR and single carrier case due to the addition of the new channel bandwidth |  | TBD |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3: CRs to impacted TSs areas
Step 3.1: CR(s) to common test environment (TS 38.508-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
Test Freq.
1
New Band | 3.1-1a | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.2.x | Test frequencies for New band(s) |  | Add test frequencies for the new band(s). |  | TBD |  |  | 1 |  |  | 0%
New CBW | 3.1-1b | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.2.x | Test frequencies for new CBW(s) |  | Add test frequencies for the new CBW(s). |  | TBD |  |  | 1 |  |  | 0%
New Band | 3.1-2a | 38.508-1 - (4) Common | 38.508-1 | 4.3.1.2.x | Low, Mid, High test channel bandwidth for RF testing |  | Specify the Low, Mid and High Test Channel bandwidths for the NR band used for RF testing. |  | TBD |  |  | 1 |  |  | 0%
New CBW | 3.1-2b | 38.508-1 - (4) Common | 38.508-1 | Tables 4.3.1.0A-2, 4.3.1.0B-2, 4.3.1.0C-2 | Low, Mid, High test channel bandwidth for RF testing |  | Check if the new CBW impacts the selection of Low, Mid and High Test Channel bandwidths used for RF testing. |  | TBD |  |  | 1 |  |  | 0%
New Band | 3.1-3 | 38.508-1 - (6) Common SIG | 38.508-1 | 6.2.3.1 | Test frequencies for protocol testing for New band |  | Add test frequencies for protocol testing and the new band for the chosen default channel bandwidth. |  | TBD |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.2: CR(s) to common clauses for RF / Performance testing area (TS 38.521-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Clause 5 | Discussion paper
[15 empty] | 1 | 1
New Band | 3.2-1 | 38.521-2- General | 38.521-2 | 5.2 | Operating band |  | Add the operating band Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 |  |  | 0%
New CBW | 3.2-2 | 38.521-2- General | 38.521-2 | 5.3.2 | Minimum guard band |  | Add the minimu m guard band for the new CBW if not already specified. Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 |  |  | 0%
All | 3.2-3 | 38.521-2- General | 38.521-2 | 5.3.5 | Channel bandwidth |  | Add the channel bandwidths for the band Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 |  |  | 0%
New Band | 3.2-4 | 38.521-2- General | 38.521-2 | 5.4.2.3 | NR-ARFCN |  | Add the applicable NR-ARFCN for the band Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 |  |  | 0%
New Band | 3.2-5 | 38.521-2- General | 38.521-2 | 5.4.3.3 | SS raster |  | Add the applicable SS raster for the band Note! Check if changes should be merged into "jumbo" CR (email sent out before meeting by responsible "jumbo" CR author). |  | TBD |  |  | 1 |  |  | 0%
New CBW | 3.2-6 | 38.521-2- General | 38.521-2 | Annex A | Measurement channels |  | Check if there is a need to add the new channel bandwidth to UL or DL RMC. |  | TBD |  |  | 1 |  |  | 0%
New CBW | 3.2-7 | 38.521-2- General | 38.521-2 | Annex C | Downlink physical channels |  | Check if there is a need to add the new channel bandwidth to default downlink power levels |  | TBD |  |  | 1 |  |  | 0%
New CBW | 3.2-8 | 38.521-2- General | 38.521-2 | Annex D | Characteristics of the Interfering Signal |  | Check if there is a need to add the new channel bandwidth to description of interference signals. |  | TBD |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.3: CR(s) for RF transmitter test cases (TS 38.521-2, clause 6)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
New CBW | 3.3-1 | 38.521-2- RF Tx | 38.521-2 | 6.1 | General |  | Check if need to add new channel bandwidth to common uplink configuration. |  | TBD |  |  | 1 | [8 empty] | 0%
New Band | 3.3-2 | 38.521-2- RF Tx | 38.521-2 | 6.2.1 | UE maximum output power |  | Add minimum requirement and test requirement for the band |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New Band | 3.3-3a | 38.521-2- RF Tx | 38.521-2 | 6.2.2 | UE maximum output power reduction - New band |  | Add test requirement vs appliable power classes for the band. |  | TBD |  |  | 1 | [5 empty] | 0%
New CBW | 3.3-3b | 38.521-2- RF Tx | 38.521-2 | 6.2.2 | UE maximum output power reduction - New CBW |  | Check if need to add new channel bandwidth to uplink configuration for almost contiguous allocation. |  | TBD |  |  | 1 | [8 empty] | 0%
New Band | 3.3-4a | 38.521-2- RF Tx | 38.521-2 | 6.2.3 | UE additional maximum output power reduction - New Band Note! This WP item is dependent on A-MPR TP analysis (Step 2, WP item 2-1a) |  | Add minimum requirement and test requirement for the band. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item 2-2a for TR 38.905). |  | TBD |  |  | 1 |  |  | 0% |  | 0% | 0%
New CBW | 3.3-4b | 38.521-2- RF Tx | 38.521-2 | 6.2.3 | UE additional maximum output power reduction - New CBW Note! This WP item is dependent on A-MPR TP analysis (Step 2, WP item 2-1b) |  | Check if need to add new channel bandwidth to minimum requirement, test configuration and test requirement. Add relevant test points (TPs) based on the TP analysis if the new channel bandwidth has impact to an NS value and corresponding emission requirements (see check item 2-2b for TR 38.905). |  | TBD |  |  | 1 |  |  | 0% |  | 0% | 0%
New Band | 3.3-8 | 38.521-2- RF Tx | 38.521-2 | 6.2D.1 | UE maximum output power for UL MIMO |  | For bands supporting UL MIMO: Add minimum requirement and test requirement for the band. For other bands: Clear the status column. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New Band | 3.3-9 | 38.521-2- RF Tx | 38.521-2 | 6.2D.2 | UE maximum output power reduction for UL MIMO |  | For bands supporting UL MIMO: Add test requirement for the band. For other bands: Clear the status column. |  | TBD |  |  | 1 | [5 empty] | 0%
New Band | 3.3-10 | 38.521-2- RF Tx | 38.521-2 | 6.2D.3 | UE additional maximum output power reduction for UL MIMO |  | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column |  | TBD |  |  | 1 |  |  | 0% |  | 0% | 0%
New CBW | 3.3-11 | 38.521-2- RF Tx | 38.521-2 | 6.3.1 | Minimum output power |  | Check if need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-12 | 38.521-2- RF Tx | 38.521-2 | 6.3.2 | Transmit OFF power |  | Check if need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-13 | 38.521-2- RF Tx | 38.521-2 | 6.3.3.2 | General ON/OFF time mask |  | Check if need to add new channel bandwidth to test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-14 | 38.521-2- RF Tx | 38.521-2 | 6.3.3.6 | SRS time mask |  | Check if need to add new channel bandwidth to test configuration and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-15 | 38.521-2- RF Tx | 38.521-2 | 6.3.4.2 | Absolute power tolerance |  | Check if need to add new channel bandwidth to test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-16 | 38.521-2- RF Tx | 38.521-2 | 6.3.4.3 | Power Control Relative power tolerance |  | Check if need to add new channel bandwidth to test configuration and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-22 | 38.521-2- RF Tx | 38.521-2 | 6.3D.1 | Minimum output power for UL MIMO |  | For bands supporting UL MIMO: Check if need to add new channel bandwidth to minimum requirement and test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-23 | 38.521-2- RF Tx | 38.521-2 | 6.3D.2 | Transmit OFF power for UL MIMO |  | For bands supporting UL MIMO: Check if need to add new channel bandwidth to minimum requirement and test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-24 | 38.521-2- RF Tx | 38.521-2 | 6.3D.3 | Transmit ON/OFF time mask for UL MIMO |  | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | [5 empty] | 0%
New CBW | 3.3-25 | 38.521-2- RF Tx | 38.521-2 | 6.3.D.4.1 | Absolute power tolerance for UL MIMO |  | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | [5 empty] | 0%
New CBW | 3.3-26 | 38.521-2- RF Tx | 38.521-2 | 6.3.D.4.2 | Power Control Relative power tolerance for UL MIMO |  | For bands supporting UL MIMO: Check if need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | [5 empty] | 0%
New CBW | 3.3-27 | 38.521-2- RF Tx | 38.521-2 | 6.5.1 | Occupied bandwidth |  | Check if need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-28 | 38.521-2- RF Tx | 38.521-2 | 6.5.2.1 | Spectrum Emission Mask |  | Check if need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New Band | 3.3-29a | 38.521-2- RF Tx | 38.521-2 | 6.5.2.3 | Adjacent channel leakage ratio |  | Add minimum requirement and test requirement for the band. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-29b | 38.521-2- RF Tx | 38.521-2 | 6.5.2.3 | Additional spectrum emission mask - New CBW |  | Check if there is a need to add the new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New Band | 3.3-30 | 38.521-2- RF Tx | 38.521-2 | 6.5.3.2 | Spurious emissions for UE co-existence |  | Add protection requirements for the new bands and existing bands against the new band |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-31 | 38.521-2- RF Tx | 38.521-2 | 6.5.2.4.1 | NR ACLR |  | Check if there is a need to add the new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-32 | 38.521-2- RF Tx | 38.521-2 | 6.5.2.4.2 | UTRA ACLR |  | Check if there is a need to add new channel bandwidth to test requirement. |  | TBD |  |  | 1 | [5 empty] | 0%
New Band | 3.3-33a | 38.521-2- RF Tx | 38.521-2 | 6.5.3.3 | Additional spurious emissions - New band |  | If new NS value introduced by the band and additional requirement is specified for the NS value then add requirements for the new NS value as needed. If not then clear the status column. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.3-33b | 38.521-2- RF Tx | 38.521-2 | 6.5.3.3 | Additional spurious emissions - New CBW |  | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New Band | 3.3-40a | 38.521-2- RF Tx | 38.521-2 | 6.5D.1 | Occupied bandwidth for UL MIMO - New band |  | For bands supporting UL MIMO: Check if there is a need to add the band's channel bandwidths to the test requirement.1. Check if band need to be added to Table 6.5D.1.4.1-2: Test frequency exceptions for Occupied Bandwidth. For other bands: Clear the status column |  | TBD |  |  | 1 | [5 empty] | 0%
New CBW | 3.3-40b | 38.521-2- RF Tx | 38.521-2 | 6.5D.1 | Occupied bandwidth for UL MIMO - New CBW |  | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | [5 empty] | 0%
New CBW | 3.3-41 | 38.521-2- RF Tx | 38.521-2 | 6.5D.2.1 | Spectrum Emission Mask for UL MIMO |  | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | [5 empty] | 0%
New Band | 3.3-42a | 38.521-2- RF Tx | 38.521-2 | 6.5D.2.2 | Adjacent channel leakage ratio for UL MIMO - New band Additional spectrum emission mask for UL MIMO- New band Note! This WP item is dependent on A-MPR TP analysis (Step 2, WP item 2-1a) |  | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band and CBWs. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column |  | TBD |  |  | 1 |  |  |  |  | 0% | 0%
New CBW | 3.3-42b | 38.521-2- RF Tx | 38.521-2 | 6.5D.2.2 | Adjacent channel leakage ratio for UL MIMO - New CBW Additional spectrum emission mask for UL MIMO - New CBW |  | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | [5 empty] | 0%
New CBW | 3.3-43 | 38.521-2- RF Tx | 38.521-2 | 6.5D.2.4.1 | NR ACLR for UL MIMO |  | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD |  |  | 1 | [5 empty] | 0%
New Band | 3.3-44a | 38.521-2- RF Tx | 38.521-2 | 6.5D.2.4.2 | UTRA ACLR for UL MIMO - New band Note! This WP item is dependent on A-MPR TP analysis (Step 2, WP item 2-1a) |  | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column |  | TBD
New CBW | 3.3-44b | 38.521-2- RF Tx | 38.521-2 | 6.5D.2.4.2 | UTRA ACLR for UL MIMO - New CBW |  | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD
New Band | 3.3-45a | 38.521-2- RF Tx | 38.521-2 | 6.5D.3.3 | Additional spurious emissions for UL MIMO - New band |  | For bands supporting UL MIMO: 1. Add minimum requirement and test requirement for the band. 2. If new NS value introduced by the band: Add test points and test configuration for the new NS value as per test points analysis (see check item for TR 38.905). For other bands: Clear the status column |  | TBD
New CBW | 3.3-45b | 38.521-2- RF Tx | 38.521-2 | 6.5D.3.3 | Additional spurious emissions for UL MIMO - New CBW |  | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column |  | TBD
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.4: CR(s) for RF receiver test cases (TS 38.521-2, clause 7)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | Min. Req. | Test proc. | Test Pts | Test Req |  |  | Other Areas
[15 empty] | 1 | 5 | 5 | 2 |  |  | 2
New Band | 3.4-1a | 38.521-2-RF Rx | 38.521-2 | 7.3.2 | Reference sensitivity power level - New band |  | Add minimum requirement, test configuration, and test requirement for the band |  | TBD |  |  | 1 |  |  | 0% |  | 0% | 0%
New CBW | 3.4-1b | 38.521-2-RF Rx | 38.521-2 | 7.3.2 | Reference sensitivity power level - New CBW |  | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.4-2 | 38.521-2-RF Rx | 38.521-2 | 7.4 | Maximum input level |  | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.4-3 | 38.521-2-RF Rx | 38.521-2 | 7.4D | Maximum input level for UL MIMO |  | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column. |  | TBD |  |  | 1 | [5 empty] | 0%
New CBW | 3.4-4 | 38.521-2-RF Rx | 38.521-2 | 7.5 | Adjacent channel selectivity |  | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New Band | 3.4-5a | 38.521-2-RF Rx | 38.521-2 | 7.6.2 | In-band blocking - New band |  | Add minimum requirement and test requirement for the band |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.4-5b | 38.521-2-RF Rx | 38.521-2 | 7.6.2 | In-band blocking - New CBW |  | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New Band | 3.4-6a | 38.521-2-RF Rx | 38.521-2 | 7.6.3 | Out-of-band blocking - New band |  | Add minimum requirement and test requirement for the band |  | TBD
New CBW | 3.4-6b | 38.521-2-RF Rx | 38.521-2 | 7.6.3 | Out-of-band blocking - New CBW |  | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD
New CBW | 3.4-7 | 38.521-2-RF Rx | 38.521-2 | 7.7 | Spurious response |  | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
New CBW | 3.4-8 | 38.521-2-RF Rx | 38.521-2 | 7.7D | Spurious response for UL MIMO |  | For bands supporting UL MIMO: Check if there is a need to add new channel bandwidth to test requirement. For other bands: Clear the status column. |  | TBD |  |  | 1 | [5 empty] | 0%
New CBW | 3.4-9 | 38.521-2-RF Rx | 38.521-2 | 7.8 | Intermodulation characteristics |  | Check if there is a need to add new channel bandwidth to minimum requirement and test requirement. |  | TBD |  |  | 1 |  |  | 0% |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.5: CR(s) for RRM and Location Services test cases (TS 38.533 and TS 37.571-1)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
[15 empty] | New band group | [5 empty] | Other Areas
[15 empty] | 1 | [5 empty] | 2
New band | 3.5-1 | 38.533-RRM | 38.533 | 3A.4.2 | NR band group RRM |  | Add band to NR band groups in clause 3A.4. If the NR bands introduces a new NR Band group, an analysis of the impact should be provided |  | TBD |  |  | 1 |  |  | 0%
New band | 3.5-1 | 37.571-1-LCS | 37.571-1 | 4.12.3 | NR band group Location Services |  | No need to add NR band groups in TS 37.571-1 for location services test cases as clause 4.12.2 refers to TS 38.533 clause 3A.4 for the NR band groups. |  | TBD |  | No change needed
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 3.6: CRs to protocol test cases (TS 38.523-3)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
38.623-3
1
| 3.6-1 | 38.523-1 | [8 empty] | No change needed | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Step 4: CR(s) for new ICS/capabilities (TS 38.508-2)
WP item applicability | WP item ID | Area | TS | TC / Clause Number | Description / Title | Impacted New band(s) and New CBW(s) | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Item Overall Completeness |  | Detailed Completion Status per area
ICS / TC appli.
1
New Band | 4-1 | 38.508-2 - ICS | 38.508-2 | A.4.3.1 | Band ICS |  | Add Baseline Implementation Capabilities for the new band to the relevant table in Table A.4.3.1-3 |  | TBD |  |  | 1 |  |  | 0%
New Band | 4-1 | 38.508-2 - ICS | 38.508-2 | A.4.3.1 | Power class capability |  | If power classes PC1 or PC2 covered by the band addition work item then add the applicable NR power class Baseline Implementation Capabilities to the relevant table in clause A.4.3.1. PC1, PC2: Tables A.4.3.1-4x |  | TBD |  |  | 1 |  |  | 0%
New Band | 4-1 | 38.508-2 - ICS | 38.508-2 | A.4.3.9 | Additional capabilities for UE declared capability |  | Add the additional applicable capabilities for the NR band in Tables A.4.3.9-4x. |  | TBD |  |  | 1 |  |  | 0%
End list sub-area WP items (insert any additional WP items for this area above this row)
Note on N27: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N35: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N44: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1. If a more work intesive item is added set to value >1.
Note on N55: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N69: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N114: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N132: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N140: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.
Note on N147: Used to calculate item's relative impact on work item's completeness. Should be set from a WI overall perspective. Default value is 1.

## Revision History WP template
Revision history for WP template only Note! Cell A3 shall always include the version of the latest version of the WP as used to set the WP template version in the WP scope worksheet.
Version | Date | Comment
v1.14.0 | RAN5#108 | No changes. Same as v1.13.0.
v1.13.0 | RAN5#107 | No changes. Same as v1.12.0.
v1.12.0 | RAN5#106 | No changes. Same as v1.11.0.
v1.11.0 | RAN5#105 | 1. Editorial correction to all the incorrect spec IDs from TS 38.521-1 to TS 38.521-2 since this WP is for FR2 band.
v1.10.0 | RAN5#104 | No changes. Same as v1.9.0.
v1.9.0 | RAN5#103 | No changes. Same as v1.8.0.
v1.8.0 | RAN5#102 | No changes. Same as v1.7.0.
v1.7.0 | RAN5#101 | No changes. Same as v1.6.0.
v1.6.0 | RAN5#100 | No changes. Same as v1.5.0.
v1.5.0 | RAN5#99 | No changes. Same as v1.4.0.
v1.4.0 | RAN5#98 | No changes. Same as v1.3.0.
v1.3.0 | RAN5#97 | 1. WP item ID 1-2: Clarified dependency on MU/TT analysis for test frequency sub-range the band belongs to
v1.2.0 | RAN5#96-e | 1. Extended the number of rows in the input table to cope with the case when multiple cut and paste of NR bands or CBW extensions from PRD21 NR Bands list are done. 2: Removed all WP Items for SUL as SUL Is not applciable for FR2. 3: Added new pre-requisite WP item 1-2 to confirm that all applicable NR FR1 test cases are completed for at least one existing NR band. 4: WP item 3.3-28: Corrected TC / Clause Number from 6.5.2.2 to 6.5.2.1. 5: WP item 3.3-29a and 3.3-29b: Corrected test case title and action for test case 6.5.2.3. 6: WP item 3.3-40a: Updated the action to reflect 38.521-2 test case. 7: WP item 3.3-41: Corrected test case number from 6.5D.2.1 to 6.5D.2.2 8: WP Items 3.3-42a and 3.3-42b: Corrected test case number from 6.5D.2.2 to 6.5D.2.3; corrected teh title, and updated the action to reflect the test case in 38.521-2. 9: Removed WP items 3.3-44a and 3.3-44b as test case 6.5D.2.4.2 does not exist for FR2. 10: Removed WP items 3.3-45a and 3.3-45b as test case 6.5D.3.3 refers back to 6.5.3.3 for which actions for adding the band or CBW is covered by WP items 3.3-33a and 3.3-33b. 11: Removed WP items 3.4-6a and 3.4-6b as test case 7.6.3 does not exist for FR2. 12. Clarify references to TP analysis in dependent test cases.
v1.1.0 | RAN5#95-e | 1. Updated WP template version in WP scope worksheet to get version number from cell A3 in the "Revision History WP template" worksheet. 2. Correcting TS reference in "area" and "TS" columns from 36.521-1/38.521-1 to 38.521-2. 3. Added a note to WP-items 3.2-1 to 3.2-5 to remind about merge with "jumbo" CR.
v1.0.0 | RAN5#94-e | Initial version