## Cover
Proposal for VoLTE Work Plan
GSMA Terminal Steering Group / Field Test Subgroup
Document Number | FT44_033
Meeting Date | 27-28 November 2013
Meeting Venue | Düsseldorf, Germany
For Approval | X
For Information
Version | 2.0
Security Restrictions | Project Team, Group or Committee

## 2. VoLTE Work Plan Consolidated
2. VoLTE Consolidated Work Plan
This is the FTDG Deliverable
Forum: |  | GSMA |  |  |  | GSMA | [6 empty] | 3GPP | [5 empty] | IMTC
Subgroup: |  | IREG, RiLTE |  |  |  | TSG FTDG | [6 empty] | RAN WG5 | [5 empty] | IMS Activity Group
Doc. Title: |  | "IMS Profile for Voice and SMS" | "IMS Profile for Conversational Video Service" | "IMS Service Centralization and Continuity Guidelines" |  | "Proposal for VoLTE Work Plan" | [6 empty] | "Reply LS to GSMA on VoLTE Test Cases" | [5 empty] | "Test Cases-IMS Profile for Voice and SMS"
Doc. Nr: |  | IR.92 | IR.94 | IR.64 | [8 empty] | R5-134968 | [5 empty] | iMTC_Test_Cases
Version: |  | 7.0 | 6.0 | 7.0 |  | V1 | [6 empty] | n/a | [5 empty] | 1.2
Date: |  | 4th March 2013 | 3rd May 2013 | 3rd May 2013 | [8 empty] | 15th November 2013 | [5 empty] | 4th October 2013
Relationship (Standards): |  | 3GPP
3GPP Release: |  | Release 8, 9 and 10
Notes:
PRD | Section | Title |  | Comments | IREG VoLTE UNI TC | Prio | Work assigned to | Section | Test Case Title | Comments of Actability to GSMA TS11 | Field Test | Lab Test | TS Reference | Section | Test Case Title | Comments | GCF Work Item | Status (GCF) Dec 13 | TS Reference | Section | Test Case Title | Comments
IR.92 - IMS Profile for Voice & SMS
IMS Feature Set
IR.92 | 2.2.1 | Registration |  |  | X | Phase1 |  | 51.1.1 | Registration and Authentication to IMS |  |  |  | TS 34.229-1 | 8 | e.g.: 8.1 Initial registration |  | WI-103/WI-128 | Active |  | 2.1 | Registration & Authentication
[8 empty] | 51.1.1.1 | SIP Registration and Authentication Procedure – via “well known IMS” APN (IR.88) |  | X | [8 empty] | 2.1.3 | UE de- registration from IMS core network
initial registration (including ICSI, SMSoIP feature tag if SMSoIP supported )
NW initiated de-registration
subscribe to registration event package
IMEI URN in Instance ID
public user ID -must be alias userID and include Tel URI, …
IR.92 | 2.2.2 | Authentication |  |  | X | Phase1 |  | 51.1.1.1 | SIP Registration and Authentication Procedure – via “well known IMS” APN (IR.88) |  | X |  | TS 34.229-1 | 8, 9 | e.g.: 9.1 Invalid behavior - MAC parameter invalid | covered in various TC | WI-103 | Not Active |  | 2.1.1 | ISIM based UE authentication to IMS core network, using IMS-AKA
IMS-AKA, Sec- Agree and Ipsec
integrity protection
|  |  |  | USIM based | [15 empty] | 2.1.2 | USIM based UE authentication to IMS core network, using IMS-Aka
Authentication at Ut reference point
Generic Auth.Arcchutecture Process
2xx response to HTTP
IR.92 | 2.2.3 | Addressing (using MSISDN-based and alphanumeric URIs) |  |  | X | Phase1 |  | TBD |  | suitable for TS.11 |  |  | TS 34.229-1 | Annex A |  | Both allowed
Alphanumeric SIP-URI
MSISDN as SIP URI
MSISDN as Tel URI
local numners dial string
phone context parameter
P-called-Party-ID header field
IR.92 | 2.2.4 | Call Establishment and Termination |  |  | X | Phase1 |  | 51.1.2 | Basic Voice cases - PS |  |  |  | TS 34.229-1 | 12 | e.g.: 12.13 MT MTSI speech call | Covered in various TC | WI-103 | Not Active |  | 2.2 | Call establishment and termination
INVITE request w/o SDP offer
SDP offer w/ audio media
ICSI value, also indicate IMS Multimedia Telephony service
[8 empty] | 51.1.2.1a | Mobile Originated Voice over IMS (VoLTE) call - Voice set up first - Voice Only | To be To be modified: Check voice quality in both devices. Check RTCP traffic is exchanged in the log | X | [8 empty] | 2.2.1 | Originating -Voice call set-up
[8 empty] | ? | Mobile Originated Voice over IMS (VoLTE) call - Voice set up first - Voice Only | This should be also a Terminal to Terminal(T2T) test case. Tested against 5 different SW implementations preferable on other SW platform | x | x
[8 empty] | 51.1.2.1b | Mobile Originated Voice over IMS (VoLTE) call - Voice set up first - Voice & FTP Downlink | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X | [8 empty] | 2.2.2 | Terminating -Voice call set-up
[8 empty] | 51.1.2.1c | Mobile Originated Voice over IMS (VoLTE) call - Voice set up first - Voice & FTP Uplink | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X | [8 empty] | 2.2.3 | Terminating -video call set-up to a UE which only supports audio
[8 empty] | 51.1.2.1d | Mobile Originated Voice over IMS (VoLTE) call - Voice set up first - Voice & FTP Uplink & Downlink | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X | [8 empty] | 2.2.4 | Terminating-audio to video upgrade to a UE which only support audio
[8 empty] | 51.1.2.2a | Mobile Terminated Voice over IMS (VoLTE) call - Voice set up first - Voice Only |  | X | [8 empty] | 2.2.5 | Originating -voice call set-up( SIP precondition not used in network)
[8 empty] | 51.1.2.2b | Mobile Terminated Voice over IMS (VoLTE) call - Voice set up first - Voice & FTP Downlink | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X | [8 empty] | 2.2.6 | Terminating-Voice call set-up ( IP precondition not used in network)
[8 empty] | 51.1.2.2c | Mobile Terminated Voice over IMS (VoLTE) call - Voice set up first - Voice & FTP Uplink | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X | [8 empty] | 2.2.7
[8 empty] | 51.1.2.2d | Mobile Terminated Voice over IMS (VoLTE) call - Voice set up first - Voice & FTP Uplink & Downlink | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X | [8 empty] | 2.2.8 | UE originated call to Home-Local Number
[8 empty] | 51.1.2.3b | Mobile Originated Voice over IMS (VoLTE) call - FTP set up first - FTP Downlink & Voice | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X | [8 empty] | 2.2.9 | UE originated call to Geo-Local Number
[8 empty] | 51.1.2.3c | Mobile Originated Voice over IMS (VoLTE) call - FTP set up first - FTP Uplink & Voice | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X
[8 empty] | 51.1.2.3d | Mobile Originated Voice over IMS (VoLTE) call - FTP set up first - FTP Uplink & Downlink & Voice | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X
[8 empty] | 51.1.2.4b | Mobile Terminated Voice over IMS (VoLTE) call - FTP set up first - FTP Downlink & Voice | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X
[8 empty] | 51.1.2.4c | Mobile Terminated Voice over IMS (VoLTE) call - FTP set up first - FTP Uplink & Voice | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X
[8 empty] | 51.1.2.4d | Mobile Terminated Voice over IMS (VoLTE) call - FTP set up first - FTP Uplink & Downlink & Voice | To be modified: Check voice quality in both devices. FTP traffic is ongoing throughout the test Check RTCP traffic is exchanged in the log | X
IR.92 | 2.2.5 | Forking (and multi-device operation ) |  |  | X | Phase 2 |  |  |  | forking out of scope in IR.92, but UE must be ready … |  |  | No | - | - | No
UE must be ready to receive responses
UE must be able to maintain at least 7 parallel early dialogues and support reception of media of 1 of the dialogues
IR.92 | 2.2.6 | Tracing of Signaling |  | not required in IR.92 | [5 empty] | … not required in IR.92 |  |  | N/A | - | - | TS 24.229 void
IR.92 | 2.2.7 | Signaling Compression |  | SIGCOMP not used in E-UTRAN but can be used in other IP connection accesses. |  | Phase 2 |  |  |  | not suitable for TS.11 |  |  | N/A | - | - | IR.92 must not use. TS 24.229 not recommended.
IR.92 | 2.2.8 | Early Media and Announcements |  |  | X | Phase1 |  | TBD |  | suitable for TS.11 |  |  | No | - | -
"early-media" inband information from NW shall overrie locally generated communication
Supplementary Services
[8 empty] | 51.1.4 | Supplementary Services according GSMA IR.92 | [10 empty] | 2.3 | Supplementary Services Test Cases
IR.92 | 2.3.2 | Supplementary Service Configuration |  |  | X | Phase1 | DoCoMo & Sony Mobile | TBD - proposed section 51.1.4 ff |  | recommended, suitable for TS.11 |  |  | TS 34.229-1 | Annex C | [5 empty] | 2.3.1 | Originating Identification Presentation not subscribed
XCAP at Ut reference point
XCAP Root URI
default public user ID as XUI
IR.92 | 2.3 ff | supplementary service, 18 cases |  |  | X |  |  | 51.1.4 ff |  | partly in headlines, coverage needs to be discussed in GSMA | [9 empty] | 2.3.2 | Originating Identification Presentation subscribed
IR.92 | 2.3.3 | Ad-hoc Multiparty Conference |  |  |  | Phase1 | DoCoMo & Sony Mobile |  |  | suitable for TS.11 |  |  | TS 34.229-1 | 15 | e.g.: 15.17 Creating and leaving a conference | Covered in various TC | WI-103 | Not Active |  | 2.3.3 | Originating Identification Restriction
3-way Session Creation
Invitation procedure
REFER method
Elements / Attributes
Audio media types
IR.92 | 2.3.4 | Communication Waiting |  |  |  | Phase1 | DoCoMo & Sony Mobile |  |  | suitable for TS.11 |  |  | TS 34.229-1 | 15 | e.g.: 15.27 Communication Waiting and answering the call | Covered in various TC | WI-103 | Not Active |  | 2.3.4 | Terminating Identification Presentation subscribed
terminal based service
Alert Info
IR.92 | 2.3.5 | Message Waiting Indication |  |  |  | Phase1 | DoCoMo & Sony Mobile |  |  | suitable for TS.11 |  |  | TS 34.229-1 | 15 | e.g.: 15.15 Subscription to the MWI event package | Covered in various TC | WI-103 | Not Active |  | 2.3.5 | Terminating Identification Restriction
MWI event package
IR.92 | 2.3.6 | Originating Identification Restriction |  | SIP procedures |  | Phase1 | DoCoMo & Sony Mobile | 51.1.4.1 | Originating Identification Presentation (OIP) |  |  |  | TS 34.229-1 | 15 | 15.2 Originating Identification Restriction | Covered in various TC | WI-103 | Not Active |  | 2.3.6 | Communication Forwarding unconditional
[8 empty] | 51.1.4.1.1 | OIP Active |  | X
[8 empty] | 51.1.4.1.2 | OIP Inactive |  | X
IR.92 | 2.3.7 | Terminating Identification Restriction |  | SIP procedures |  | Phase1 | DoCoMo & Sony Mobile |  |  | suitable for TS.11 |  |  | TS 34.229-1 | 15 | 15.4 Terminating Identification Restriction |  | WI-103 | Not Active |  | 2.3.7 | Originating-communication HOLD
IR.92 | 2.3.8 | Communication Diversion |  |  |  | Phase1 | DoCoMo & Sony Mobile |  |  | suitable for TS.11 |  |  | TS 34.229-1 | 15 | e.g.: 15.5 Communication Forwarding unconditional (also 15.7 … 15.10a) | Covered in various TC | WI-103 | Not Active |  | 2.3.8 | Terminating -Communication HOLD
SIP procedures for CDIV
XML rules for CFU
IR.92 | 2.3.9 | Communication Barring |  |  |  | Phase1 | DoCoMo & Sony Mobile |  |  | suitable for TS.11 |  |  | TS 34.229-1 | 15 | e.g.: 15.13 Incoming Communication Barring except for a specific user (also 15.14 Incoming communication - barring for anonymous users; and 15.14a Communication Barring while roaming) | Covered in various TC | WI-103 (TC 15.14a) | Not Active |  | 2.3.9 | Communication Forwarding on no Reply : limited ringing duration
SIP procedures for CB
XML rules for XCAP operations
[20 empty] | 2.3.10 | Originating-Creating a conference
[20 empty] | 2.3.11 | Terminating-Joining a conference call after receiving an invitation
[20 empty] | 2.3.12 | Communication Forwarding on busy
Call Set-up Considerations
IR.92 | 2.4.1 | SIP Preconditions |  | to be defined, operator depending, e.g. QoS (RFC 3312, 4032), | X | Phase1 |  | - |  | to be defined, operator depending, e.g. QoS (RFC 3312, 4032), |  |  | TS 34.229-1 | 12 | e.g.: 12.13 MT MTSI speech call | Covered in various TC | WI-103 | Not Active |  | 2.3.14 | Barring of All Incoming Calls
[20 empty] | 2.3.15 | Barring of All Outgoing Calls
[20 empty] | 2.3.16 | Barring of Outgoing Internatonal Calls
IR.92 | 2.4.2 | Integration of resource management and SIP | [17 empty] | 2.3.17 | Barring of Incoming Calls when Roaming
IR.92 | 2.4.2.1 | Loss of PDN connectivity |  |  | X | Phase1 |  | - |  | conformance testing |  |  | TS 36.523-1 | 10 | 10.4.2 EPS bearer context deactivation / Re-establishment |  | WI-103 | Not Active |  | 2.3.18 | Communicating forwarding on not Reachable
re-establlishment of PDN connection due to loss of PDN connection, e.g PCSCF abort
initial registration in case of IP address change or registration expiry at PDN connection loss
IR.92 | 2.4.2.23 | Loss of media bearer and loss of radio connection |  |  | X | Phase1 |  | - |  | loss of radio connection suitable for TS.11, loss of media bearer -> conformance testing |  |  | N/A | - | - | IR.92 void |  |  |  | 2.3.19 | Communication Waiting
termmination of SIP session when GBR /Radio bearer lost
NW option to allow session on other media, e.g failed video continues as voice
UE logic to decide to terminate, modiefy or maintain session depending on bearer/radio connection loss.
initial registration after IMS registration expiry upon loss of radio bearer
IR.92 | 2.4.3 | Voice Media Considerations | [7 empty] | TBD |  |  | TS 34.229-1 | 12 | e.g.: 12.13 MT MTSI speech call | Covered in various TC | WI-103 | Not Active
SDP offer/answer
IR.92 | 2.4.4 | Multimedia Considerations |  |  | X | Phase1 | DoCoMo & Sony Mobile |  |  | TBD |  |  | No
full set of media functions by sending multiple "m="lines in SDP offer -> setup advanced profile. Setup or modify session
IR.92 | 2.5 | SMS over IP |  |  | X | Phase1 |  | 51.3 | SMS over IMS |  |  |  | TS 34.229-1 | 18 | e.g.: 18.1 Mobile Originating SMS | Covered in various TC | WI-128 | Active |  | 2.4 | SMS over IP
roles of SM-overIP sender and receiver
status reports and notifications
[8 empty] | 51.3.1 | MO-SMS over IMS |  | X | [8 empty] | 2.4.1 | Originating -SMS over IP
[8 empty] | 51.3.2 | MT-SMS over IMS |  | X | [8 empty] | 2.4.2 | Terminating -SMS over IP
[8 empty] | 51.3.3 | Multiple (Concatenated) MO-SMS over IMS |  | X | [8 empty] | 2.4.3 | Originating -SMS over IP ( more than 160 characters)
[20 empty] | 2.4.4 | Terminating-SMS over IP ( more than 160 characters)
[20 empty] | 2.4.5 | Originating over IP: destination UE not reachable , SMS stored in SMSC. Destination UE becomes reachable, stored SMS is delivered. Delivery report is sent to originating UE
[20 empty] | 2.4.6 | Terminating -SMS over IP : destination UE not reachable , SMS sorted in SMSC. Destination UE becomes reachable , stored SMS is delivered.
[20 empty] | 2.5 | SMS over SGs | New Section ?
[20 empty] | 2.5.1 | Originating -SMS over SGs during EMM-IDE state
[20 empty] | 2.5.2 | Originating over SG during EMM-CONNECTED state
[20 empty] | 2.5.3 | Terminating -SMS over SGs during EMM-IDE state
[20 empty] | 2.5.4 | Terminating-SMS over SGs during EMM-CNNECTED state
IMS Media
IR.92 | 3.2.1 | Codecs |  |  | X | Phase1 | Sony Mobile | 51.1.2.1a | Mobile Originated Voice over IMS (VoLTE) call - Voice set up first - Voice Only | Could be modified to our needs, adding “ Test against other SW implementation” Check that codec best matches allocated bandwidth is selected by both devices. Check that UDP is used as Transport for RTP traffic in the log Check RTCP traffic is exchanged in the log All different Codecs checked at Conformance Test? |  |  | TS 34.229-1 | 12, Annex C | e.g.: 12.13 MT MTSI speech call | Covered in various TC | WI-103 | Not Active
[8 empty] | ? | Mobile Originated Voice over IMS (VoLTE) call - Voice set up first - Voice Only | This should be also a Terminal to Terminal(T2T) test case. Tested against 5 different SW implementations preferable on other SW platform | x | x
AMR speech codec incl all 8 modes
ANR-WB incl all 9 modes
transmitting: alingning of codec mode changes
receiving: allow codec mode changes
[8 empty] | 51.1.2.2a | Mobile Terminated Voice over IMS (VoLTE) call - Voice set up first - Voice Only | To be modified:Check voice quality in both devices. Check RTCP traffic is exchanged in the log | X |  | TS 34.229-1 | 12, Annex C | e.g.: 12.13 MT MTSI speech call | Covered in various TC | WI-103 | Not Active
[8 empty] | ? | Mobile Terminated Voice over IMS (VoLTE) call - Voice set up first - Voice Only | This should be also a Terminal to Terminal(T2T) test case. Tested against 5 different SW implementations preferable on other SW platform | X | X
[8 empty] | ? | MO VoLTE to GSM | Check voice quality in both devices. Check RTCP traffic is exchanged in the log | X |  | No
[8 empty] | ? | MT GSM to VoLTE | Check voice quality in both devices. Check RTCP traffic is exchanged in the log | X |  | TS 34.229-1 | 12, Annex C | e.g.: 12.13 MT MTSI speech call | Covered in various TC | WI-103 | Not Active
[8 empty] | ? | MO VoLTE to PSTN | Check voice quality in both devices. Check RTCP traffic is exchanged in the log | X |  | TS 34.229-1 | 12, Annex C | e.g.: 12.13 MT MTSI speech call | Covered in various TC | WI-103 | Not Active
[8 empty] | ? | MT PSTN to VoLTE | Check voice quality in both devices. Check RTCP traffic is exchanged in the log | X |  | No | - | -
[8 empty] | ? | DUT on VoLTE call VoLTE Client, Client HO to GSM | check that DUT can handle codec change | X |  | No | - | -
[13 empty] | TS 34.229-1 | 12, Annex C | e.g.: 12.13 MT MTSI speech call | Covered in various TC | WI-103 | Not Active
IR.92 | 3.2.2 | RTP Profile and SDP Considerations |  |  |  | Phase1 | Sony Mobile |  |  | Client to Client scenarios, same as above test cases
RTP profile
SDP offer considerations
SDP answer considerations
IR.92 | 3.2.3 | Data Transport |  |  |  | Phase1 | Sony Mobile |  |  | Client to Client scenarios, same as above test cases
RTP over UDP
IR.92 | 3.2.4 | RTCP Usage |  |  |  | Phase1 | Sony Mobile | ? | DUT on VoLTE, Call Hold 60 s | If it fail check less time. Lab Test, short interruption and long Check that RTCP traffic continues on DUT. If it fail check less time. Lab Test, short interruption and long | X
[8 empty] | ? | DUT on VoLTE, Client 2 Out of Coverage. | Lab Test, short interruption and long interruption, Check RTCP traffic is exchanged Check that RTCP traffic continues on DUT. If it fail check less time. Lab Test, short interruption and long | X | X
IR.92 | 3.2.5 | AMR Payload format Considerations |  |  |  | Phase1 | Sony Mobile |  |  | Also checked in above test case but not specified. Conformance test to check that ptime and Maxptime set
IR.92 | 3.2.6 | Jitter Buffer Management Handling |  |  | X | Phase1 | Sony Mobile | - |  | Conformance Test
IR.92 | 3.2.7 | Front End Handling |  |  |  | Phase1 | Sony Mobile |  |  | Conformance Test
IR.92 | 3.3 | DTMF Events |  |  |  | Phase1 | Sony Mobile | 40.4 | DTMF emission | rewritten to suite also VoLTE. Do we need a VoLTE test number? Check that it's possible to use DTMF in VoLTE. | X
Radio and Packet Core Feature Set
IR.92 | 4.1 | Robust Header Compression |  |  |  | Phase1 | [6 empty] | TS 36.523-1, TS 36.508 | 8 | e.g.: 8.2.1.8 RRC connection reconfiguration / Radio bearer establishment / Success / Dedicated bearer / ROHC configured |  | WI-150-xx (xx=band) | Active
IR.92 | 4.2.1 | Radio Bearers |  |  |  | Phase1 | [6 empty] | TS 36.523-1, TS 36.508 | 4 | e.g.: 4.5A.6 Generic Test Procedure for IMS MO speech call establishment in E-UTRA | Covered in various TC | WI-103 | Not Active
IR.92 | 4.2.2 | DRX Mode of Operation |  |  |  | Phase1 | [6 empty] | TS 36.523-1, TS 36.508 | 7.1.6 | e.g.: 7.1.6 DRX operation | Covered in various TC | WI-081-xx (xx=band) | Active
IR.92 | 4.2.3 | RLC Configuration |  |  |  | Phase1 |  |  |  | TBD |  |  | TS 36.523-1, TS 36.508 | 7.2, 7.3 | e.g.: 7.2.2 for Unacknowledged Mode and 7.2.3 for Acknowledged Mode as well as 7.3 within PDCP test cases | Covered in various TC | WI-081-xx (xx=band) | Active
IR.92 | 4.2.4 | GBR & NGBR Services |  |  |  | Phase1 |  |  |  | TBD |  |  | TS 36.523-1, TS 36.508 | 8 | e.g.: in section 8.1 RRC connection management and 8.3 measurement configuration control and reporting | Covered in various TC | WI-081-xx (xx=band) | Active
IR.92 | 4.3.1 | EPS Bearer Considerations for SIP Signaling and XCAP |  |  |  | Phase1 |  | 51.1.8 | Early Media and Announcements | suitable for TS.11 |  |  | TS 36.523-1, TS 36.508 | 10 | e.g.: section 10 in EPS session management (QCI) | Covered in various TC | WI-082-xx (xx=band) | Active
IR.92 | 4.3.2 | EPS Bearer Considerations for Voice |  |  |  | Phase1 |  | 51.1.8.x | Test Cases TBD | suitable for TS.11 |  |  | TS 36.523-1, TS 36.508 | 4 | e.g.: 4.5A.6 Generic Test Procedure for IMS MO speech call establishment in E-UTRA |  | WI-103 | Not Active
IR.92 | 4.4 | P-CSCF Discovery |  |  |  | Phase1 |  |  |  | suitable for TS.11 (included in 51.1.1.1) |  |  | TS 36.508
Common Functionalities
IR.92 | 5.1 | IP version | [7 empty] | TBD |  |  | TS 36.523-1, TS 36.508 | 15 | e.g.: Section 9.2.1 Attach Procedures; 10.9 UE routing of uplink packets; and 15 Mobility management based on Dual Stack Mobile IPv6 | Covered in various TC | WI-082-xx (xx=band), e.g 9.2.1.1.3, 9.2.1.1.4 and 10.9.1 | Active (10.9.1 active, 9.2.1.1.3 and 9.2.1.1.4 not yet validated)
IR.92 | 5.2, A.5 | Emergency Services |  |  | X | Phase1 |  | 51.1.3 | Emergency Calls |  |  |  | TS 34.229-1, TS 36.523-1, TS 36.508 | 19 8 | e.g.: (34.229-1) 19.1.1 Emergency call with emergency registration / Success / Location information available and (36.523-1) 8.1.2.11 RRC connection establishment of emergency call | 20+ Test cases. Different scenarios. | WI-154 | Not Active |  | 2.7 | Emergency Service
[8 empty] | 51.1.3.1 | Domain selection for Emergency calls / UE settings IMS PS Voice preferred / EMS supported by the network |  | X | [8 empty] | 2.7.1 | Emergency Call
[8 empty] | 51.1.3.2 | Domain selection for Emergency calls / UE settings IMS PS Voice preferred / EMS not supported by the network |  | X | [8 empty] | 2.7.2 | emergency call in Limited service
[8 empty] | 51.1.3.3 | Domain selection for Emergency calls / UE settings IMS PS Voice only / EMS supported by the network |  | X
[8 empty] | 51.1.3.4 | Domain selection for Emergency calls / UE settings IMS PS Voice only / EMS not supported by the network |  | X
IR.92 | 5.3, A.6, A.2 | Roaming Considerations |  |  | X | Phase 2 |  | 51.5 | Roaming | scenarios should be discussed, maybe first test w/o roaming agreement… |  |  | No | - | -
[8 empty] | 51.5.x | Test Cases TBD
Complementing IMS with CS
IR.92 | A.2 |  |  |  | X | Phase1 |  | included in 51.1.3, 51.1.5, |  | included in call establishment |  |  | TS 36.523-1, TS 36.508 | 11.2 | e.g.: 11.2.10 LIMITED-SERVICE / EPS does not support IMS Emergency / Emergency call using the CS domain | Covered in various TC | WI-154 | Not Active
IR.92 | A.3 |  |  |  | X | Phase1 |  | 51.1.6 ff |  | only basic, more test appreciated |  |  | TS 34.229.1, TS 36.523-1, TS 36.508 | 11.2 | e.g.: (36.523-1) 11.2.11 LIMITED-SERVICE / Inter-system mobility / E-UTRA to UTRA CS / SRVCC Emergency Call Handover to UTRAN | Covered in various TC | WI-154 | Not Active
IR.92 | A.4 | IMS voice service settings management when using CS access | [10 empty] | No | - | -
IR.92 | A.7 | SMS support using SGs (IR.92: A.7) |  |  | X | Phase1 |  | 51.4 | SMS over SGs | should be included (current tests are under LTE only, same test cases under VoLTE – covering also “Domain Selection” ) |  |  | TS 36.523-1 | 11 | e.g.: 11.1.1 MT-SMS over SGs / Idle mode | Covered in various TC | WI-082-xx (xx=band) | Active
[8 empty] | 51.4.x | Test Cases TBD
| Features needed in Certain Markets |  |  |  | X |  |  | - |  | local specific services - input contribution driven
IR.92 | B.2 | Global Text Telephony |  |  |  | Phase 2 |  |  |  | TBD |  |  | TS 34.229-1 | 12 | e.g.: 12.16 MO MTSI Text call | Covered in various TC | WI-103 | Not Active
IR.92 | B.3 | Service Specific Access Control |  |  |  | Phase 2 |  |  |  | TBD |  |  | TS 34.229-1 | 12 | e.g.: 12.18 MTSI MO speech call / SSAC / 0% access probability for MTSI MO speech call | Covered in various TC | WI-171 | Not Active
(IR.94 - Conversational Video Service) |  |  |  |  | X
Support of Generic IMS Functions (addition to IR.92)
IR.94 | 2.2.1 | SIP Registration Procedures |  |  |  | Phase 1 | Samsung |  |  | suitable for TS.11 |  |  | TS 34.229-1 | 8 | e.g.: 8.1 Initial registration | Covered in various TC | WI-128/WI-103 | Active
[8 empty] | 51.1.7 | VoLTE according GSMA IR.94 - Video Calls
IR.94 | 2.2.2 | Call Establishment and Termination |  |  |  | Phase 1 | Samsung | 51.1.7.1 | MO video call | suitable for TS.11 | X |  | TS 34.229-1 | 12 | e.g. 12.21 MO MTSI Video call | Covered in various TC |  | No GCF WI for MTSI /IR.94 Video Call yet
[8 empty] | 51.1.7.2 | MT video call |  | X
[8 empty] | 51.1.7.6 | MO video call to voice-only party (Voice only call shall be established) |  | X
Supplementary Services (addition to IR.92)
IR.94 | 2.3.2 | Communication Hold |  |  |  | Phase 1 | Samsung |  |  | suitable for TS.11 |  |  | No | - | -
IR.94 | 2.3.3 | Ad-hoc Multi-Party Conferance |  |  |  | Phase 1 | Samsung |  |  | suitable for TS.11 |  |  | No | - | -
Call Set-up Considerations for Calls with Video Media (addition to IR.92)
IR.94 | 2.4.1 | Integration of Resource Management and SIP |  |  |  | Phase 2 |  |  |  | TBD
IR.94 | 2.4.2 | Video Media Considerations |  |  |  | Phase 2 |  |  |  | TBD |  |  | TS 34.229-1 | 17 | e.g.: 17.1 MO Speech, add video remove video | Covered in various TC |  | No GCF WI for MTSI add/remove media yet
IMS Media (addition to IR.92)
IR.94 | 3.3.1 | Video Codec |  |  |  | Phase 2 |  |  |  | TBD |  |  | TS 34.229-1 | 12, Annex C | e.g.: 12.21 MO MTSI Video call | Covered in various TC |  | No GCF WI for MTSI /IR.94 Video Call yet
IR.94 | 3.3.2 | RTP Profile and Data Transport |  |  |  | Phase 2 |  |  |  | TBD |  |  | TS 34.229-1 | 12, Annex C | e.g.: 12.21 MO MTSI Video call | Covered in various TC |  | No GCF WI for MTSI /IR.94 Video Call yet
IR.94 | 3.3.3 | RTCP Usage |  |  |  | Phase 2 |  |  |  | TBD |  |  | TS 34.229-1 | 12, Annex C | e.g.: 17.2 MT Speech, add video remove video | Covered in various TC |  | No GCF WI for MTSI add/remove media yet
IR.94 | 3.3.4 | RTP Payload Format Considerations for Video |  |  |  | Phase 2 |  |  |  | TBD |  |  | TS 34.229-1 | 12, Annex C
Bearer Considerations for Video (addition to IR.92)
IR.94 | 4.2.1 | E-UTRAN |  |  |  | Phase 1 |  |  |  | TBD |  |  | TS 36.523-1, TS 36.508 | 4 | e.g.: 4.5A.8 Generic Test Procedure for IMS MO video call establishment in E-UTRA | Covered in various TC |  | No GCF WI for MTSI /IR.94 Video Call yet
IR.94 | 4.2.2 | UTRAN | [7 empty] | TBD |  |  | No | - | -
IR.94 | 4.3 | LTE Radio Capabilities | [7 empty] | TBD |  |  | TS 36.523-1, TS 36.508 | 12 | e.g.: 12.3.3 Data transfer of E-UTRA radio bearer combinations 5,8,11 and 12 / MIMO | Covered in various TC | WI-081-xx (xx=band) | Active
IR.94 | 4.4 | HSPA Radio Capabilities | [7 empty] | TBD |  |  | No | - | -
Complementing IMS with CS (addition to IR.92)
IR.94 | A.2 | SR-VCC |  |  |  | Phase 1 |  | 51.1.6 | VoLTE according GSMA IR.64 - SR-VCC | suitable for TS.11 |  |  | No | - | - | NW dependent |  |  |  | 2.8 | SRVCC
[8 empty] | 51.1.6.1a | SR-VCC to UTRAN | To be modified: check that DUT can handle codec change | X | [8 empty] | 2.8.1 | SRVCC from E-UTRAN to GERAN without DTM support
[8 empty] | 51.1.6.1b | SR-VCC to UTRAN + PS Data | To be modified: check that DUT can handle codec change | X | [8 empty] | 2.8.2 | SRVCC from E-UTRAN to GERAN with DTM support but without DTM HO support
[8 empty] | 51.1.6.2a | SR-VCC to GSM/GERAN | To be modified: check that DUT can handle codec change | X | [8 empty] | 2.8.3 | SRVCC from E-UTRAN to GERAN with DTM HO support
[8 empty] | 51.1.6.2b | SR-VCC to GSM/GERAN + PS Data (w/o DTM) | To be modified: check that DUT can handle codec change | X | [8 empty] | 2.8.4 | SRVCC from E-UTRAN to UTRAN without PS HO
[8 empty] | 51.1.3.5 | Emergency Call - SRVCC to UTRAN |  | X | [8 empty] | 2.8.5 | SRVCC from E-UTRAN to UTRAN with PS HO support
[8 empty] | 51.1.3.6 | Emergency Call - SRVCC to GSM |  | X
(IR.64 - SR-VCC) |  |  |  |  | X
IR.64 | 4.1 | General |  |  |  | Phase1 |  |  |  | suitable for TS.11 |  |  | No | - | - | NW dependent
IR.64 | 4.2 | Impacted entities |  |  |  | Phase1 |  |  |  | suitable for TS.11 |  |  | No | - | - | NW dependent
IR.64 | 4.4 | Support of mid-call state and calls in alerting state |  |  |  | Phase1 |  |  |  | suitable for TS.11 |  |  | No | - | - | NW dependent
IR.64 | 4.5 | SRVCC Architecture for emergency calls |  |  |  | Phase1 |  |  |  | suitable for TS.11 |  |  | No | - | - | NW dependent
IR.64 | 4.6 | Handling of non-voice media during SRVCC |  |  |  | Phase1 |  |  |  | suitable for TS.11 |  |  | No | - | - | NW dependent
Performance (not in GSMA PRD) | [7 empty] | 51.2 | PS Performances
[8 empty] | 51.2.1 | PS Performances (good coverage - relative measurement) |  | X
[8 empty] | 51.2.2 | PS Performances (good coverage - absolute measurement) |  | X
[8 empty] | 51.2.3 | PS Performances (During Mobility Drive Tests - relative Measurement) |  | X
[8 empty] | 51.2.4 | PS Stability - loss of Radio Coverage |  | X
[8 empty] | 51.2.4.x | Test Cases TBD

## Revision History
Revision History of GSMA VoLTE work plan
Date | Version | Summary of Changes
2013-11-24 | V2-20131124 | initial version presented on FTDG#44 meeting
2013-11-28 | V2-20131217 | revised version after FTDG#44 meeting: "backup" working sheets removed
2013-12-20 | V2-20131220 | additional column (“S”) for the GCF work items added
priorities changed according to the agreement of the conf call (Phase1 = Voice and SMS, Phase2 = Video)
NTT DoCoMo and Sony Mobile added as supporting companies for supplementary services and media
2014-01-10 | V2-20140110 | GCF status added
result of IMS media test case analysis added