## Cover sheet
3GPP TSG-RAN WG5 meeting#69 |  |  |  |  | R5-15xxxx
Anaheim, US, 16 – 20 Nov 2015
Agenda Item: | 7.3
Source: | [Rapporteur (Ericsson)]
Title: | UE Conformance Test Aspects – UE Conformance Test Aspects – Rel-13 CA configurations Work Plan
Work item code: | [LTE_CA_Rel13-UEConTest]
Document for:
1. Introduction
At the RAN#70 meeting in December 2015 the Rel-13 RAN5 work item for UE Conformance Test Aspects of Rel-13 CA configurations was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item on the conformance test cases for the core requirement introduced by the core and performance work items for Rel-13 CA configurations. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. The work sheet Summary Work Plan Table shows the status for each Rel-13 CA configuration. For the not yet completed CA configurations where responsible company have been assigned a specific work sheet per CA configuration is porvided.
2. Work item status
Estimation of WI overall completeness:
Area |  | Current Completeness | Comments | History
Overall completeness |  | 0% | 0 out of 202 ongoing or completed
Estimation of completeness per area:
Area |  | Current Completeness | Comments | History
2DL/1UL CA Configurations |  | 0% | 0 out of 24 ongoing or completed
2DL/1UL Additional bandwidth combination set |  | 0% | 0 out of 5 ongoing or completed
2DL/2UL(A1-A4) CA Configurations |  | 0% | 0 out of 6 ongoing or completed
3DL/1UL CA Configurations |  | 0% | 0 out of 85 ongoing or completed
3DL/1UL Additional bandwidth combination sets |  | 0% | 0 out of 2 ongoing or completed
3DL/2UL CA Configurations |  | 0% | 0 out of 13 ongoing or completed
3DL/3UL CA Configurations |  | 0% | 0 out of 2 ongoing or completed
4DL/1UL CA Configurations |  | 0% | 0 out of 54 ongoing or completed
5DL/1UL CA Configurations |  | 0% | 0 out of 11 ongoing or completed
5 References
[1] RP-15xxxx | New WI proposal: UE Conformance Test Aspects - Rel-13 CA configurations Work Plan; Supporting companies: TBD

## Summary Work Plan Table
RAN4 work item status @ RAN#69 | [6 empty] | RAN5 status |  |  |  | # configs |  | Compl per area | # >0% | # 100%
UID | CA Type |  |  | Overall | Details | CA config. | RAN5 rapporteur | Target / Completed | Completion status | Comments | 202 | 0 | 0% | 0 | 0
2DL/1UL CA Configurations | [10 empty] | 24 | 0 | 0% | 0 | 0
680075 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 32% | TeliaSonera Core part: 80% Perf.part: 0% WID: RP-150861 | CA_20A-67A | Ericsson | RAN5#71 | 0%
620023 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 30% | KT Core part: 30% Perf.part: 30% WID: RP-140120 | CA_8A-27A |  |  | 0%
630033 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 100% | Orange, Ericsson WID: RP-140094 | CA_7A-22A |  |  | 0%
650037 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 100% | Nokia Networks WID: RP-141129 | CA_3A-38A |  |  | 0%
650038 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 100% | Huawei WID: RP-141145 | CA_2A-28A |  |  | 0%
650039 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 100% | Huawei WID: RP-141146 | CA_4A-28A |  |  | 0%
650040 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 75% | Ericsson Core part: 75% Perf.part: 75% WID: RP-141168 | CA_20A-40A |  |  | 0%
650041 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 80% | KT Core part: 80% Perf.part: 80% WID: RP-141312 | CA_1A-40A |  |  | 0%
650042 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 100% | KT WID: RP-141674 | CA_3A-40A |  |  | 0%
650043 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 100% | Huawei WID: RP-141336 | CA_20A-31A |  |  | 0%
650044 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 100% | Huawei WID: RP-141337 | CA_3A-31A |  |  | 0%
650045 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 100% | SK Telecom WID: RP-141675 | CA_5A-40A |  |  | 0%
660081 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 100% | Sprint WID: RP-142020 | CA_25A-26A |  |  | 0%
660082 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 95% | China Telecom Core part: 95% Perf.part: 95% WID: RP-142239 | CA_3A-41A |  |  | 0%
670081 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 90% | KDDI Core part: 90% Perf.part: 90% WID: RP-150064 | CA_1A-42A |  |  | 0%
681003 | 2DL/1UL | New CA config. | Intra-band C (2) | 20% | Intel Core part: 20% Perf.part: 20% WID: RP-151035 | CA_5B |  |  | 0%
681004 | 2DL/1UL | New CA config. | Intra-band NC (1+1) | 100% | Nokia Networks WID: RP-151034 | CA_4A-4A |  |  | 0%
681005 | 2DL/1UL | New CA config. | Intra-band NC (1+1) | 20% | Intel Core part: 20% Perf.part: 20% WID: RP-151036 | CA_5A-5A |  |  | 0%
690073 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 0% | Huawei Core part: 0% Perf.part: 0% WID: RP-151367 | CA_5A-38A |  |  | 0%
681005 | 2DL/1UL | New CA config. | Intra-band NC (1+1) | 20% | Intel Core part: 20% Perf.part: 20% WID: RP-151036 | CA_5A-5A |  |  | 0%
680074 | 2DL/1UL | New BW set | Inter-band (1)+(1) | 100% | Nokia Networks WID: RP-150585 | CA_2A-12A |  |  | 0%
680076 | 2DL/1UL | New BW set | Inter-band (1)+(1) | 100% | Nokia Networks WID: RP-150947 | CA_4A-12A |  |  | 0%
690073 | 2DL/1UL | New CA config. | Inter-band (1)+(1) | 0% | Huawei Core part: 0% Perf.part: 0% WID: RP-151367 | CA_5A-38A |  |  | 0%
690095 | 2DL/1UL | New BW set | Intra-band NC (1+1) | 0% | Huawei Core part: 0% Perf.part: 0% WID: RP-151462 | CA_7A-7A |  |  | 0%
2DL/1UL Additional bandwidth combination set | [10 empty] | 5 | 0 | 0% | 0 | 0
670063 | 2DL/1UL | New BW set | Inter-band (1)+(1) | 100% | Nokia Networks WID: RP-150171 | CA_5A-7A |  |  | 0%
670064 | 2DL/1UL | New BW set | Inter-band (1)+(1) | 100% | Samsung WID: RP-150425 | CA_3A-5A |  |  | 0%
680074 | 2DL/1UL | New BW set | Inter-band (1)+(1) | 100% | Nokia Networks WID: RP-150585 | CA_2A-12A |  |  | 0%
680076 | 2DL/1UL | New BW set | Inter-band (1)+(1) | 100% | Nokia Networks WID: RP-150947 | CA_4A-12A |  |  | 0%
690095 | 2DL/1UL | New BW set | Intra-band NC (1+1) | 0% | Huawei Core part: 0% Perf.part: 0% WID: RP-151462 | CA_7A-7A |  |  | 0%
2DL/2UL(A1-A4) CA Configurations | [10 empty] | 6 | 0 | 0% | 0 | 0
661010 | 2DL/2UL (A1) | New CA config. | Inter-band (1)+(1) | 80% | Huawei Core part: 80% Perf.part: 80% WID: RP-141935 | CA_1A-18A |  |  | 0%
| 2DL/2UL (A1) | New CA config. | Inter-band (1)+(1) |  |  | CA_1A-26A |  |  | 0%
661011 | 2DL/2UL (A2) | New CA config. | Inter-band (1)+(1) | 50% | Qualcomm Core part: 50% Perf.part: 50% WID: RP-141975 | CA_1A-28A |  |  | 0%
661012 | 2DL/2UL (A3) | New CA config. | Inter-band (1)+(1) | 75% | Ericsson Core part: 75% Perf.part: 75% WID: RP-142010 | CA_18A-28A |  |  | 0%
670082 | 2DL/2UL (A4) | New CA config. | Inter-band (1)+(1) | 75% | Nokia Networks Core part: 75% Perf.part: 75% WID: RP-150410 | CA_1A-26A |  |  | 0%
| 2DL/2UL (A4) | New CA config. | Inter-band (1)+(1) |  |  | CA_4A-5A |  |  | 0%
3DL/1UL CA Configurations | [10 empty] | 85 | 0 | 0% | 0 | 0
620032 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 25% | KT Core part: 25% Perf.part: 25% WID: RP-131754 | CA_3A-8A-27A |  |  | 0%
640022 | 3DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1) | 100% | U.S. Cellular WID: RP-141232 | CA_2A-2A-12A |  |  | 0%
640025 | 3DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1) | 100% | CHTTL WID: RP-140692 | CA_3A-3A-8A |  |  | 0%
640032 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 100% | Huawei WID: RP-140974 | CA_41A-42C |  |  | 0%
650049 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1) | 100% | China Mobile WID: RP-141290 | CA_8A-41C |  |  | 0%
650049 | 2DL/1UL | New Fallback | Inter-band (1)+(1) | 100% | China Mobile WID: RP-141290 | CA_8A-41A |  |  | 0%
650051 | 3DL/1UL | New CA config. | Inter-band + Intra-band NC (1)+(2) | 100% | Samsung WID: RP-141655 | CA_38A-40A-40A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band + Intra-band C (1)+(2) |  |  | CA_38A-40C |  |  | 0%
| 2DL/1UL | New Fallback | Intra-band C (2) |  |  | CA_40C |  |  | 0%
650053 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 100% | Huawei WID: RP-141667 | CA_2A-5A-29A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_5A-29A |  |  | 0%
660083 | 3DL/1UL | New CA config. | Inter-band + Intra-band NC (1)+(1+1) | 99% | China Unicom Core part: 100% Perf.part: 100% WID: RP-141777 | CA_1A-3A-3A |  |  | 0%
660084 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 99% | NTT DOCOMO Core part: 100% Perf.part: 100% WID: RP-141791 | CA_1A_19A_28A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_19A_28A |  |  | 0%
660085 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 100% | NTT DOCOMO WID: RP-141792 | CA_21A_42C |  |  | 0%
| 2DL/1UL | New Fallback | Intra-band C (2) |  |  | CA_42C |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_21A_42A |  |  | 0%
660086 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 99% | ZTE Core part: 100% Perf.part: 100% WID: RP-141802 | CA_7A-40C |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_7A-40A |  |  | 0%
660087 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 40% | Softbank Mobile Core part: 40% Perf.part: 40% WID: RP-141826 | CA_1A-8A-28A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_8A-28A |  |  | 0%
660088 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 100% | Ericsson WID: RP-141881 | CA_3A-7C |  |  | 0%
| 3DL/1UL | New CA config. | Inter-band + Intra-band C (2)+(1) |  |  | CA_3A-7B |  |  | 0%
660089 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (2)+(1) | 100% | Ericsson WID: RP-141882 | CA_7C-28A |  |  | 0%
| 3DL/1UL | New CA config. | Inter-band + Intra-band C (2)+(1) |  |  | CA_7B-28A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band + Intra-band C (2) |  |  | CA_7B |  |  | 0%
| 2DL/1UL | New Fallback | Intra-band C (2) |  |  | CA_7C |  |  | 0%
660090 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 80% | KT Core part: 80% Perf.part: 80% WID: RP-141946 | CA_1A-3A-40A |  |  | 0%
660091 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 80% | KT Core part: 80% Perf.part: 80% WID: RP-141947 | CA_1A-8A-40A |  |  | 0%
660092 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 93% | KT Core part: 95% Perf.part: 90% WID: RP-141949 | CA_3A-8A-40A |  |  | 0%
660093 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 100% | Ericsson WID: RP-142013 | CA_3A-7A-8A |  |  | 0%
660094 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 100% | Nokia Networks WID: RP-142038 | CA_1A-3A-28A |  |  | 0%
660095 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 40% | Softbank Mobile Core part: 40% Perf.part: 40% WID: RP-142193 | CA_3A-8A-28A |  |  | 0%
660096 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 40% | Softbank Mobile Core part: 40% Perf.part: 40% WID: RP-142194 | CA_8A-42C |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_8A-42A |  |  | 0%
660097 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1) | 30% | Huawei Core part: 60% Perf.part: 0% WID: RP-142206 | CA_28A-40C |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_28A-40A |  |  | 0%
660098 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 100% | Huawei WID: RP-142207 | CA_3A-40C |  |  | 0%
660099 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 100% | Huawei WID: RP-142208 | CA_1A-7A-28A |  |  | 0%
661000 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 25% | Huawei Core part: 50% Perf.part: 0% WID: RP-142209 | CA_1A-3A-7A |  |  | 0%
661001 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (2)+(1) | 100% | Intel WID: RP-142238 | CA_3C-5A |  |  | 0%
661002 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 100% | Ericsson WID: RP-142244 | CA_3A-7A-28A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_3A-7A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_7A-28A |  |  | 0%
670065 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 100% | NTT DOCOMO, INC. WID: RP-150121 | CA_1A-3A-42A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_1A-3A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_1A-42A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_3A-42A |  |  | 0%
670066 | 3DL/1UL | New CA config. | Inter-band | 100% | NTT DOCOMO, INC. WID: RP-150122 | CA_1A-19A-42A |  |  | 0%
670067 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 100% | NTT DOCOMO, INC. WID: RP-150123 | CA_1A-21A-42A |  |  | 0%
670068 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 100% | NTT DOCOMO, INC. WID: RP-150124 | CA_3A-19A-42A |  |  | 0%
670069 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 100% | NTT DOCOMO, INC. WID: RP-150125 | CA_19A-21A-42A |  |  | 0%
670072 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 0% | Rogers Communications Core part: 0% Perf.part: 0% WID: RP-150431 | CA_2A-7A-12A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_2A-7A |  |  | 0%
670073 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 0% | Rogers Communications Core part: 0% Perf.part: 0% WID: RP-150432 | CA_2A-4A-7A |  |  | 0%
670074 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 60% | Nokia Networks Core part: 60% Perf.part: 60% WID: RP-150433 | CA_7A-20A-38A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_20A-38A |  |  | 0%
670084 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 100% | Huawei WID: RP-150246 | CA_42A-42C |  |  | 0%
| 3DL/1UL | New CA config. | Inter-band + Intra-band C (2)+(1) |  |  | CA_42C-42A |  |  | 0%
670085 | 2DL/1UL | New Fallback | Intra-band (2) | 70% | CMCC Core part: 90% Perf.part: 50% WID: RP-150437 | CA_8B |  |  | 0%
670086 | 4DL/1UL | New Fallback | Intra-band (4) | 80% | CATT Core part: 80% Perf.part: 80% WID: RP-150438 | CA_42E |  |  | 0%
680077 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 100% | Softbank Mobile WID: RP-150609 | CA_1A-8A-11A |  |  | 0%
| 2DL/1UL | New Fallback BW set | Inter-band (1)+(1) |  |  | CA_1A-8A |  |  | 0%
| 2DL/1UL | New Fallback BW set | Inter-band (1)+(1) |  |  | CA_1A-11A |  |  | 0%
| 2DL/1UL | New Fallback BW set | Inter-band (1)+(1) |  |  | CA_8A-11A |  |  | 0%
680078 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 50% | Ericsson Core part: 50% Perf.part: 50% WID: RP-150864 | CA_3A-20A-32A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_3A-32A |  |  | 0%
| 3DL/1UL | New Fallback BW set | Inter-band (1)+(1) |  |  | CA_20A-32A |  |  | 0%
680079 | 3DL/1UL | New CA config. | Inter-band + Intra-band NC (1)+(1+1) | 70% | Huawei Core part: 70% Perf.part: 70% WID: RP-151012 | CA_7A-42A-42A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_7A-42A |  |  | 0%
680080 | 3DL/1UL | New CA config. | Inter-band + Intra-band NC (1)+(1+1) | 100% | Huawei WID: RP-151013 | CA_20A-42A-42A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_20A-42A |  |  | 0%
680081 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 60% | Nokia Networks Core part: 60% Perf.part: 60% WID: RP-151014 | CA_3A-7A-38A |  |  | 0%
680082 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 25% | KDDI Core part: 50% Perf.part: 0% WID: RP-151111 | CA_28A_41C |  |  | 0%
| 2DL/1UL | New Fallback | Intra-band C (2) |  |  | CA_41C |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_28A_41A |  |  | 0%
680083 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 20% | KDDI Core part: 40% Perf.part: 0% WID: RP-151112 | CA_28A_42C |  |  | 0%
| 2DL/1UL | New Fallback | Intra-band C (2) |  |  | CA_42C |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_28A_42A |  |  | 0%
690074 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 0% | KDDI Core part: 0% Perf.part: 0% WID: RP-151156 | CA_1A-11A-18A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_1A-18A |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1) |  |  | CA_11A-18A |  |  | 0%
690075 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 0% | ZTE Core part: 0% Perf.part: 0% WID: RP-151200 | CA_5A-40C |  |  | 0%
690076 | 3DL/1UL | New CA config. | Inter-band (1)+(1)+(1) | 0% | Huawei Core part: 0% Perf.part: 0% WID: RP-151365 | CA_3A-41A-42A |  |  | 0%
690077 | 3DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 0% | ZTE Core part: 0% Perf.part: 0% WID: RP-151448 | CA_3A-41C |  |  | 0%
3DL/1UL Additional bandwidth combination sets | [10 empty] | 2 | 0 | 0% | 0 | 0
670070 | 3DL/1UL | New BW set | Inter-band + Intra-band NC (1+1)+(1) | 0% | Rogers Communications Core part: 0% Perf.part: 0% WID: RP-150429 | CA_4A-4A-7A |  |  | 0%
670071 | 3DL/1UL | New BW set | Inter-band (1)+(1)+(1) | 0% | Rogers Communications Core part: 0% Perf.part: 0% WID: RP-150430 | CA_4A-7A-12A |  |  | 0%
3DL/2UL CA Configurations | [10 empty] | 13 | 0 | 0% | 0 | 0
650047 | 3DL/2UL | New CA config. | Intra-band C (3) | 100% | CATT WID: RP-141677 | CA_42D |  |  | 0%
670083 | 3DL/2UL | New CA config. | Inter-band (1)+(1)+(1) | 75% | Nokia Corporation Core part: 75% Perf.part: 75% WID: RP-150479 | CA_1A-3A-5A |  |  | 0%
| 3DL/2UL | New CA config. | Inter-band (1)+(1)+(1) |  |  | CA_1A-3A-8A |  |  | 0%
| 3DL/2UL | New CA config. | Inter-band (1)+(1)+(1) |  |  | CA_1A-3A-19A |  |  | 0%
| 3DL/2UL | New CA config. | Inter-band (1)+(1)+(1) |  |  | CA_1A-5A-7A |  |  | 0%
| 3DL/2UL | New CA config. | Inter-band (1)+(1)+(1) |  |  | CA_1A-18A-28A |  |  | 0%
| 3DL/2UL | New CA config. | Inter-band (1)+(1)+(1) |  |  | CA_1A-19A-21A |  |  | 0%
| 3DL/2UL | New CA config. | Inter-band (1)+(1)+(1) |  |  | CA_2A-4A-12A |  |  | 0%
| 3DL/2UL | New CA config. | Inter-band (1)+(1)+(1) |  |  | CA_2A-5A-13A |  |  | 0%
| 3DL/2UL | New CA config. | Inter-band (1)+(1)+(1) |  |  | CA_3A-7A-20A |  |  | 0%
| 3DL/2UL | New CA config. | Inter-band (1)+(1)+(1) |  |  | CA_4A-5A-13A |  |  | 0%
681002 | 3DL/2UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 13% | Nokia Networks Core part: 25% Perf.part: 0% WID: RP-150817 | CA_3A-7C |  |  | 0%
| 3DL/2UL | New CA config. | Inter-band + Intra-band C (2)+(1) |  |  | CA_3C-7A |  |  | 0%
3DL/3UL CA Configurations | [10 empty] | 2 | 0 | 0% | 0 | 0
690093 | 3DL/3UL | New CA config. | Inter-band + Intra-band C (1)+(2) | 0% | CATT Core part: 0% Perf.part: 0% WID: RP-151402 | CA_39A-41C |  |  | 0%
690094 | 3DL/3UL | New CA config. | Inter-band + Intra-band C (2)+(1) | 0% | CATT Core part: 0% Perf.part: 0% WID: RP-151403 | CA_39C-41A |  |  | 0%
4DL/1UL CA Configurations | [10 empty] | 54 | 0 | 0% | 0 | 0
661003 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1)+(1) | 95% | AT&T Core part: 95% Perf.part: 95% WID: RP-142198 | CA_2A-2A-12A-30A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band + Intra-Band NC (2)+(1) |  |  | CA_2A-2A-30A |  |  | 0%
661004 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1)+(1) | 95% | AT&T Core part: 95% Perf.part: 95% WID: RP-142199 | CA_2A-2A-5A-30A |  |  | 0%
661005 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1)+(1) | 95% | AT&T Core part: 95% Perf.part: 95% WID: RP-142200 | CA_2A-2A-29A-30A |  |  | 0%
661006 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 95% | AT&T Core part: 95% Perf.part: 95% WID: RP-142201 | CA_2A-4A-12A-30A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band (1)+(1)+(1) |  |  | CA_2A-4A-30A |  |  | 0%
661007 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 95% | AT&T Core part: 95% Perf.part: 95% WID: RP-142202 | CA_2A-4A-5A-30A |  |  | 0%
661008 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 95% | AT&T Core part: 95% Perf.part: 95% WID: RP-142203 | CA_2A-4A-29A-30A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band (1)+(1)+(1) |  |  | CA_2A-4A-29A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band (1)+(1)+(1) |  |  | CA_2A-4A-30A |  |  | 0%
661009 | 4DL/1UL | New CA config. | Inter-band + Intra-Band C (1)+(3) | 88% | Alcatel-Lucent Core part: 95% Perf.part: 80% WID: RP-142204 | CA_25A-41D |  |  | 0%
661013 | 4DL/1UL | New CA config. | Intra-band C + Intra-band NC (2+2) | 65% | Alcatel-Lucent Core part: 80% Perf.part: 50% WID: RP-142022 | CA_41C-41C |  |  | 0%
| 4DL/1UL | New CA config. | Intra-band C + Intra-band NC (1+3) |  |  | CA_41A-41D |  |  | 0%
| 4DL/1UL | New CA config. | Intra-band NC (3+1) |  |  | CA_41D-41A |  |  | 0%
670075 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1)+(1+1)+(1) | 95% | Nokia Networks Core part: 95% Perf.part: 95% WID: RP-150073 | CA_2A-4A-4A-12A |  |  | 0%
670076 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1)+(1) | 95% | Nokia Networks Core part: 95% Perf.part: 95% WID: RP-150074 | CA_2A-2A-4A-12A |  |  | 0%
670077 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1+1) | 95% | Nokia Networks Core part: 95% Perf.part: 95% WID: RP-150075 | CA_2A-2A-4A-4A |  |  | 0%
670078 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 30% | SK Telecom Core part: 60% Perf.part: 0% WID: RP-150434 | CA_1A-3A-5A-40A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band (1)+(1)+(1) |  |  | CA_1A-5A-40A |  |  | 0%
670079 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 23% | Nokia Networks Core part: 45% Perf.part: 0% WID: RP-150435 | CA_1A-3A-7A-8A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band (1)+(1)+(1) |  |  | CA_1A-7A-8A |  |  | 0%
670080 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 95% | Huawei Core part: 95% Perf.part: 95% WID: RP-150436 | CA_2A-4A-5A-29A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band (1)+(1)+(1) |  |  | CA_4A-5A-29A |  |  | 0%
680085 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 0% | Rogers Communications Core part: 0% Perf.part: 0% WID: RP-150628 | CA_2A-4A-7A-12A |  |  | 0%
680086 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 95% | NTT DOCOMO, INC. Core part: 95% Perf.part: 95% WID: RP-150632 | CA_1A-3A-19A-42A |  |  | 0%
680087 | 4DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1)+(2) | 95% | NTT DOCOMO, INC. Core part: 95% Perf.part: 95% WID: RP-150633 | CA_1A-3A-42C |  |  | 0%
680088 | 4DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1)+(2) | 95% | NTT DOCOMO, INC. Core part: 95% Perf.part: 95% WID: RP-150634 | CA_1A-19A-42C |  |  | 0%
680089 | 4DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1)+(2) | 95% | NTT DOCOMO, INC. Core part: 95% Perf.part: 95% WID: RP-150635 | CA_3A-19A-42C |  |  | 0%
680090 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 95% | NTT DOCOMO, INC. Core part: 95% Perf.part: 95% WID: RP-150636 | CA_1A-19A-21A-42A |  |  | 0%
680091 | 4DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1)+(2) | 95% | NTT DOCOMO, INC. Core part: 95% Perf.part: 95% WID: RP-150637 | CA_1A-21A-42C |  |  | 0%
680092 | 4DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1)+(2) | 95% | NTT DOCOMO, INC. Core part: 95% Perf.part: 95% WID: RP-150638 | CA_19A-21A-42C |  |  | 0%
680093 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 40% | U.S. Cellular Core part: 40% Perf.part: 40% WID: RP-150728 | CA_2A-4A-5A-12A |  |  | 0%
680094 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (2)+(1)+(1) | 40% | U.S. Cellular Core part: 40% Perf.part: 40% WID: RP-150731 | CA_2A-2A-4A-5A |  |  | 0%
680095 | 4DL/1UL | New CA config. | Inter-band + Intra-band C + Intra-band NC (2)+(1+1) | 40% | U.S. Cellular Core part: 40% Perf.part: 40% WID: RP-150732 | CA_2A-2A-12B |  |  | 0%
680096 | 4DL/1UL | New CA config. | Inter-band (1)+(1)+(1)+(1) | 0% | AT&T Core part: 0% Perf.part: 0% WID: RP-151015 | CA_4A_4A_5A_30A |  |  | 0%
680097 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1)+(1) | 0% | AT&T Core part: 0% Perf.part: 0% WID: RP-151016 | CA_4A_4A_12A_30A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band + Intra-band NC (1+1)+(1) |  |  | CA_4A_4A_30A |  |  | 0%
680098 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1)+(1) | 0% | AT&T Core part: 0% Perf.part: 0% WID: RP-151017 | CA_4A_4A_29A_30A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band + Intra-band NC (1+1)+(1) |  |  | CA_4A_4A_29A |  |  | 0%
681000 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1)+(1) | 40% | U.S. Cellular Core part: 40% Perf.part: 40% WID: RP-151018 | CA_2A-2A-5A-12A |  |  | 0%
681001 | 4DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1)+(2) | 40% | U.S. Cellular Core part: 40% Perf.part: 40% WID: RP-151019 | CA_2A-5A-12B |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band + Intra-band C (1)+(2) |  |  | CA_5A-12B |  |  | 0%
681006 | 4DL/1UL | New CA config. | Intra-band C + Intra-band NC (1+3) | 25% | Huawei Core part: 50% Perf.part: 0% WID: RP-151102 | CA_42A-42D |  |  | 0%
| 4DL/1UL | New CA config. | Intra-band C + Intra-band NC (3+1) |  |  | CA_42D-42A |  |  | 0%
| 4DL/1UL | New CA config. | Intra-band C + Intra-band NC (2+2) |  |  | CA_42C-42C |  |  | 0%
680084 | 4DL/1UL | New CA config. | Intra-band C + Intra-band NC (2+2) | 40% | ZTE Core part: 40% Perf.part: 40% WID: RP-150627 | CA_41C-42C |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band + Intra-band C (2)+(1) |  |  | CA_41C-42A |  |  | 0%
690078 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1)+(3) | 0% | CMCC Core part: 0% Perf.part: 0% WID: RP-151175 | CA_39A-41D |  |  | 0%
690079 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (2)+(2) | 0% | CMCC Core part: 0% Perf.part: 0% WID: RP-151176 | CA_39C-41C |  |  | 0%
690082 | 4DL/1UL | New CA config. | Inter-band + Intra-band NC (1+1)+(1)+(1) | 0% | KT Core part: 0% Perf.part: 0% WID: RP-151262 | CA_1A-3A-8A-40A |  |  | 0%
690083 | 4DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1)+(2) | 0% | Huawei Core part: 0% Perf.part: 0% WID: RP-151363 | CA_3A-28A-40C |  |  | 0%
| 2DL/1UL | New Fallback | Inter-band (1)+(1)+(1) |  |  | CA_3A-28A-40A |  |  | 0%
690084 | 4DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(3) | 0% | Huawei Core part: 0% Perf.part: 0% WID: RP-151364 | CA_28A-40D |  |  | 0%
690085 | 4DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(2)+(1) | 0% | Telstra Core part: 0% Perf.part: 0% WID: RP-151511 | CA_3A-7C-28A |  |  | 0%
5DL/1UL CA Configurations | [10 empty] | 11 | 0 | 0% | 0 | 0
690089 | 5DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1)+(1)+(2) | 0% | NTT DOCOMO Core part: 0% Perf.part: 0% WID: RP-151159 | CA_1A-3A-19A-42C |  |  | 0%
690090 | 5DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1)+(1)+(2) | 0% | NTT DOCOMO Core part: 0% Perf.part: 0% WID: RP-151160 | CA_1A-19A-21A-42C |  |  | 0%
690091 | 5DL/1UL | New CA config. | Inter-band + Intra-band C (1)+(1)+(2)+(1) | 0% | Telstra Core part: 0% Perf.part: 0% WID: RP-151512 | CA_1A-3A-7C-28A |  |  | 0%
| 4DL/1UL | New Fallback | Inter-band (1)+(1)+(1)+(1) |  |  | CA_1A-3A-7A-28A |  |  | 0%
| 4DL/1UL | New Fallback | Inter-band + Intra-band C (1)+(2)+(1) |  |  | CA_1A-3A-7C |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band + Intra-band C (1)+(2) |  |  | CA_1A-7C |  |  | 0%
690092 | 5DL/1UL | New CA config. | Inter-band + Intra-band C (2)+(2)+(1) | 0% | Telstra Core part: 0% Perf.part: 0% WID: RP-151513 | CA_3C-7C-28A |  |  | 0%
| 4DL/1UL | New Fallback | Inter-band + Intra-band C (1)+(2)+(1) |  |  | CA_3A-7C-28A |  |  | 0%
| 4DL/1UL | New Fallback | Inter-band + Intra-band C (2)+(2) |  |  | CA_3C-7C |  |  | 0%
| 4DL/1UL | New Fallback | Inter-band + Intra-band C (2)+(1)+(1) |  |  | CA_3C-7A-28A |  |  | 0%
| 3DL/1UL | New Fallback | Inter-band + Intra-band C (2)+(1) |  |  | CA_3C-28A |  |  | 0%