## Sheet1
Priority [1: RAN4#AH1807, 2: RAN4#88, 3: RAN4#88bis, 4: RAN4#89, 5: RAN4#90~]
No. | Priority | TC | Title | Items pending on RAN4 | R4 part | Status after RAN4#87 | R4 Status after RAN4 87 | Status after RAN4 #AH1807 | R4 Status after RAN4 AH 1807 | R5 Status | Action Point | R5 target (except for MU/TT)
[RAN4] TS 38.101-1 <-> [RAN5] TS 38.521-1
1.1 | 1 | 6.2.1 | UE maximum output power | UL RMC | Demod | Not defined | open | In progress: - UL RMCs defined - FFS if additional UL RMCs are needed - FFS on UL RMCs applicability for UE RF requirements | open | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share recommended paramters to R4 (R5-183932r1). [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
1.2 | 1 | 6.3.3 | Transmit ON/OFF time mask | UL RMC | Demod | Not defined | open | In progress: - UL RMCs defined - FFS if additional UL RMCs are needed - FFS on UL RMCs applicability for UE RF requirements | open | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share recommended paramters to R4 (R5-183932r1). [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
1.3 | - | 6.3.3.2 | General ON/OFF time mask | Finalized requirement | RF | Completed | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
1.4 | 2 | 6.3.3.4 | PRACH time mask | Finalized requirement | RF | requirements are TBD | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
1.5 | 2 | 6.3.3.5 | PUCCH time mask | Finalized requirement | RF | Not defined | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
1.6 | - | 6.3.3.6 | SRS time mask | Finalized requirement | RF | Completed | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
1.7.1 | 1 | 7.3 | General Reference Sensitivity | DL RMC | Demod | Not defined | open | Completed (DL RMC defined) | close | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share recommended paramters to R4 (R5-183932r1). [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
1.7.2 | 1 |  |  | UL RMC | Demod | Not defined | open | In progress: - UL RMCs defined - FFS if additional UL RMCs are needed - FFS on UL RMCs applicability for UE RF requirements | open | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share recommended paramters to R4 (R5-183932r1). [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
1.7.3 | 1 |  |  | OCNG | Demod | Not defined | open | Completed (OCNG defined) | close | open | [R4] [#AH1807] To complete items. [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
1.8.1 | 2 | Annex C |  | Connection for Rx TCs (PDSCH, PDCCH) - complete Annex C.3.1 in TS 38.101-1? | RF | Not defined | open | Completed (Connection for Measurement of Receiver Characteristics defined) | close | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
1.8.2 | 1 |  |  | Set-up. (Refer to Annex C.2 in TS 36.521-1) | RF | Not defined | open | Not defined | open | open | [R4] [#AH1807] To complete items. [R5] [#80] Complete EPRE Ratio based on RAN4 specified Physical Channel | RAN5#80 (Aug-2018)
1.9.1 | - | 6.4.1 | Frequency error | Finalized requirement | RF | Completed - [TBD] -> 1ms | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
1.9.2 | 1 |  |  | DL RMC | RF | Not defined | open | Completed (DL RMCs for REFSENS can be used based on RAN5 assumptions in R5-183950) | close | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share recommended paramters to R4 (R5-183932r1). [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
1.10 | - | 6.4.2.1 | EVM | Finalized requirement | RF | Partly Completed - [ ] was removed from req. table. - 256QAM paramter is still TBD. "UE Output Power for 256 QAM" in table 6.4.2.1-2 is not defined | open |  | open | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
1.11 | - | Annex F | Except for F.5 | Not defined | RF | Completed | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this item. | RAN5#80 (Aug-2018)
1.12 | 2 |  | F.5 (Window length) | Not defined | RF | FFS are still remain. | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
|  |  | Maximum input level | DL RMC | RF/Demod |  | open | In progress. DL RMCs defined. FFS whether 256QAM only or both 256QAM and 64QAM will be used for FR1 Maximum input level RMC | open | open
[RAN4] TS 38.101-2 <-> [RAN5] TS 38.521-2
2.1 | 1 | 6.2.1.1 | UE MOP for PC1 | Finalized MOP and MPR requirement | RF | MPR requirement is still open | open |  | open | open | [R4] [#AH1807] Clarify whether MPR requirements apply to TRP and EIRP CDF metrics [R5] [#80] To prepare CR for this item. | RAN5#80 (Aug-2018)
2.2 | 1 | 6.2.1.2 | UE MOP for PC2 | Finalized MOP and MPR requirement | RF | MPR requirement is still open | open |  | open | open | [R4] [#AH1807] Finalize MPR requirements. Clarify whether MPR requirements apply to TRP and EIRP CDF metrics [R5] [#80] To prepare CR for this item. | RAN5#80 (Aug-2018)
2.3.1 | 1 | 6.2.1.3 | UE MOP for PC3 | Finalized MOP and MPR requirement (EIRP, TRP) | RF | MPR requirement is still open | open |  | open | open | [R4] [#AH1807] Finalize MPR requirements. Clarify whether MPR requirements apply to TRP and EIRP CDF metrics [R5] [#80] To prepare CR for this item. | RAN5#80 (Aug-2018)
2.3.2 | 1 |  |  | Finalized MOP and MPR requirement (Spherical cov.) | RF | MPR requirement is still open | open |  | open | open | [R4] [#AH1807] To complete items. Clarify whether MPR requirements apply to TRP and EIRP CDF metrics. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.4 | 1 | 6.2.1.4 | UE MOP for PC4 | Finalized MOP and MPR requirement | RF | MPR requirement is still open | open |  | open | open | [R4] [#AH1807] Finalize MPR requirements. Clarify whether MPR requirements apply to TRP and EIRP CDF metrics [R5] [#80] To prepare CR for this item. | RAN5#80 (Aug-2018)
2.5.1 | 2 | 6.2.2 | MPR | Finalized requirement (PC1) | RF | [ ] is still remain. | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.5.2 | 2 |  |  | Finalized requirement (PC2,3,4) | RF | requirements are TBD | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.6 | 2 | 6.2.4 | Configured transmitted power | Finalized requirement | RF | [ ] is still remain. | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
| 3 | 6.2.3 | AMPR for EESS | Regulatory requirements not available | RF | requirements are TBD | open |  | open | open
2.6.1 | 2 | 6.2A.4 | Configured transmitted power | Formulas for Pcmax and Pumax | RF | requirements are TBD | open |  | open | open
| 3 | 6.2A.3 | AMPR for EESS for CA | Regulatory requirements not available | RF | requirements are TBD | open |  | open | open
2.7 | 2 | 6.3.1 | Minimum output power | Finalized requirement requirement is not testable | RF | Pending | open |  | open | open | [R4] [#88 (Aug-18)] Finalize if requirement can be changed or skipped [R5] [#80] To prepare RAN4 depended CR | RAN5#80 (Aug-2018)
2.8 | 2 | 6.3.2 | Transmit OFF power | Finalized requirement requirement is not testable | RF | Pending | open |  | open | open | [R4] [#88 (Aug-18)] Finalize if requirement can be changed or skipped [R5] [#80] To prepare RAN4 depended CR | RAN5#80 (Aug-2018)
2.9 | 2 | 6.3.3.2 | General ON/OFF time mask | Finalized requirement for OFF Power | RF | Pending | open |  | open | open | [R4] [#88 (Aug-18)] Finalize if requirement can be changed or skipped [R5] [#80] To prepare RAN4 depended CR | RAN5#80 (Aug-2018)
2.10 | 2 | 6.3.3.4 | PRACH time mask | Finalized requirement | RF | req. values are TBD | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.11 | 2 | 6.3.3.5 | PUCCH time mask | Finalized requirement | RF | Not defined | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.12 | - | 6.3.3.6 | SRS time mask | Finalized requirement | RF | Completed | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
2.13 | 2 | 6.3.4.2 | Absolute power tolerance | Finalized requirement | RF | [ ] is still remain. | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.14 | 2 | 6.3.4.3 | Relative power tolerance | Finalized requirement | RF | [ ] is still remain. | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.15.1 | 2 | 6.3.4.4 | Aggregate power tolerance | Finalized requirement | RF | [ ] is still remain. | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.15.2 | 2 | 6.3A.4.2 | Absolute power tolerance for CA | Finalized requirement | RF |  | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.15.3 | 2 | 6.3A.4.3 | Relative power tolerance for CA | Finalized requirement | RF |  | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.15.4 | 2 | 6.3A.4.4 | Aggregate power tolerance for CA | Finalized requirement | RF |  | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.16.1 | 2 | 7.3.2.1 | REFSENS for PC1 | Finalized requirement | RF | [ ] is still remain. | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.16.2 | - | 7.3.2.x | REFSENS for PC2,3,4 | Finalized requirement | RF | Completed | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
2.16.3 | 2 | 7.3.? | REFSENS (Spherical coverage) | Finalized requirement | RF | Not defined | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.17 | - | 7.4 | Maximum input level | Finalized requirement | RF | Completed | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
|  |  |  | DL RMC | RF/Demod |  | open | In progress Maximum input level DL RMCs for FR2 is FFS | open | open
2.18 | - | 7.5 | Adjacent channel selectivity | Finalized requirement | RF | Completed | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
2.19 | 1 | 6.2 | MOP (EIRP, TRP) | UL RMC | RF/Demod | Not defined | open | In progress: - Possible UL RMCs defined - FFS if additional UL RMCs are needed - FFS on UL RMCs applicability for UE RF requirements | open | open | [R4] [#AH1807] To complete items. MPR needs to be finalized first to determine the number of RB's for the MOP test points [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
|  |  |  | OCNG | Demod | Not defined | open | Completed (OCNG defined) | close | open | [R4] [#AH1807] To complete items. [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
2.20.1 | 1 | 7.3 | REFSENS (beam peak, EIS) | DL RMC | Demod | Not defined | open | Completed (DL RMCs defined) | close | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share recommended paramters to R4 (R5-183932r1). [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
2.20.2 | 1 |  |  | UL RMC | Demod | Not defined | open | In progress: - UL RMCs defined - FFS if additional UL RMCs are needed - FFS on UL RMCs applicability for UE RF requirements | open | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share recommended paramters to R4 (R5-183932r1). [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
|  |  |  | OCNG | Demod | Not defined | open | Completed (OCNG defined) | close | open | [R4] [#AH1807] To complete items. [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
2.21 | 2 | 7.6.3 | Out of band blocking | All |  | not defined | open |  | open | open
|  | Annex C |  | Connection for Rx TCs (PDSCH, PDCCH) - complete Annex C.3.1 in TS 38.101-1? | RF | Not defined | open | Completed (Connection for Measurement of Receiver Characteristics defined) | close | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
|  |  |  | Set-up. (Refer to Annex C.2 in TS 36.521-1) | RF | Not defined | open | Not defined | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] Complete EPRE Ratio based on RAN4 specified Physical Channel | RAN5#80 (Aug-2018)
|  | Annex F | Transmit modulation |  | RF | Not defined | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
2.22 | - |  | RSRP accuracy requirements |  | RRM | Not defined | open | In progress. Initial agreements reached. Detailed information provided in R4-1809345. | open | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share which items to be completed in RAN5 MU analysis. [R5] [#80] To prepare CR for this items.
[RAN4] TS 38.133 (for MU analysis of REFSENS)
2.21.1 | 2 | 10.1.3 | Intra-frequency RSRP accuracy requirements with beamforming | Finalized requirement | RRM | Not defined | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#81] To prepare MU analysis based on RAN4 agreemetns. | RAN5#81 (Nov-2018)
2.21.2 | 2 | 10.1.3.1 | Intra-frequency [SS block RSRP] accuracy requirements | Finalized requirement | RRM | Not defined | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#81] To prepare MU analysis based on RAN4 agreemetns. | RAN5#81 (Nov-2018)
2.21.3 | 2 | 10.1.3.2 | Intra-frequency [CSI-RS RSRP] accuracy requirements | Finalized requirement | RRM | Not defined | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#81] To prepare MU analysis based on RAN4 agreemetns. | RAN5#81 (Nov-2018)
[RAN4] TS 38.101-3 <-> [RAN5] TS 38.521-3
3.1.1 | 2 | 6.2B.1 | UE maximum output power for EN-DC | Finalized requirement | RF | [ ] is still remain. | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
3.1.2 | 1 |  |  | UL RMC | Demod | Not defined | open | Not defined. [RAN4 assumption is that RMC from 38.101-1 and 38.101-2 can be reused.] | open | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share recommended paramters to R4 (R5-183932r1). [R5] [#80] To prepare CR for this items. | RAN5#80 (Aug-2018)
3.1.2 | - | 6.2B.2.1 | MPR and EN-DC (Intra C) | Finalized requirement | RF | Completed (same as standalone) | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
3.1.3 | - | 6.2B.2.2 | MPR and EN-DC (Intra NC) | Finalized requirement | RF | Completed (same as standalone) | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
3.1.4 | - | 6.2B.2.3 | MPR and EN-DC (Inter FR1) | Finalized requirement | RF | Completed (same as standalone) | close |  | close | open | [R4] None [R5] [#80] To prepare CR for this TC. | RAN5#80 (Aug-2018)
3.1.5 | 2 | 6.2B.2.4 | MPR and EN-DC (Inter FR2) | Finalized requirement | RF | ENDC FR2 req is pending | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
3.1.6 | 2 | 6.2B.2.5 | MPR and EN-DC (Inter FR1 and FR2) | Finalized requirement | RF | ENDC FR2 req is pending | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
3.2.1 | 2 | 6.2B.4.1.1 | PCMAX (Intra C) | Finalized requirement | RF | req. is TBD | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
3.2.2 | 2 | 6.2B.4.1.2 | PCMAX (Intra NC) | Finalized requirement | RF | req. is TBD | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
3.2.3 | 2 | 6.2B.4.1.3 | PCMAX (Inter FR1) | Finalized requirement | RF | req. is TBD | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
3.2.4 | 2 | 6.2B.4.1.4 | PCMAX (Inter FR2) | Finalized requirement | RF | req. is TBD | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
3.2.5 | 2 | 6.2B.4.1.5 | PCMAX (Inter FR1 and FR2) | Finalized requirement | RF | req. is TBD | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [#80] To prepare RAN4 depended CR. | RAN5#80 (Aug-2018)
3.4.1 | 1 | 7.3B.2 | General Reference Sensitivity | DL RMC | Demod | Not defined | open | Not defined. [RAN4 assumption is that RMC from 38.101-1 and 38.101-2 can be reused.] | open | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share recommended paramters to R4 (R5-183932r1). [R5] [AH#3] To prepare CR for this items. | RAN5 AH#3 (Oct-2018)
3.4.2 | 1 | 7.3B.2 | General Reference Sensitivity | UL RMC | Demod | Not defined | open | Not defined. [RAN4 assumption is that RMC from 38.101-1 and 38.101-2 can be reused.] | open | open | [R4] [#AH1807] To complete items. [R5] [ASAP] To share recommended paramters to R4 (R5-183932r1). [R5][AH#3] To prepare CR for this items. | RAN5 AH#3 (Oct-2018)
3.5.1 | 2 | 6.3B.2 | EN-DC Output power dynamics | Finalize requirement | RF | Some inital details are added but some parameters (EN-DC specific switching time)are in []. Section structure not complete. | open |  | open | open | [R4] [#88 (Aug-18)] To complete items. [R5] [AH#3] To prepare RAN4 depended CR. | RAN5 AH#3 (Oct-2018)
[RAN4] TS 38.810 <-> [RAN5] TS 38.903
4.1.1 | - |  | TRP Measurement grid | Determine the minimum number of grid points for constant step size and constant density grids. | Testabiliy | Completed (LS; R4-1808410) | close |  | close | open | [R4] None [R5] [#80] To prepare MU analysis and complete FR2 MOP and REFSENS. [R5] [#NR3] To prepare MU analysis and complete FR2 Priority 2 TCs.
4.1.2 | - |  |  | Clarify whether the TRP mean error for constant step size grid will be avoided in the test procedure for TRP measurements, e.g., by pointing the beam peak towards the equator. If yes, finalize the test procedure of TRP measurement for constant step size grid. If no, provide the additional MU due to the mean TRP error. | Testabiliy | Completed (LS; R4-1808410) | close |  | close | open | [R4] None [R5] [#80] To prepare MU analysis and complete FR2 MOP and REFSENS. [R5] [#NR3] To prepare MU analysis and complete FR2 Priority 2 TCs.
4.1.3 | - |  |  | Provide baseline MU associated with the minimally acceptable grid for constant step size and constant density grids. | Testabiliy | Completed (LS; R4-1808410) | close |  | close | open | [R4] None [R5] [#80] To prepare MU analysis and complete FR2 MOP and REFSENS. [R5] [#NR3] To prepare MU analysis and complete FR2 Priority 2 TCs.
4.2.1 | - |  | Tx and Rx Beam peak search grid | Determine the minimum number of grid points for Tx beam peak search for constant step size and constant density grids. | Testabiliy | Completed (LS; R4-1808410) | close |  | close | open | [R4] None [R5] [#80] To prepare MU analysis and complete FR2 MOP and REFSENS. [R5] [#NR3] To prepare MU analysis and complete FR2 Priority 2 TCs.
4.2.2 | - |  |  | Determine the minimum number of grid points for Rx beam peak search for constant step size and constant density grids. | Testabiliy | Completed (LS; R4-1808410) | close |  | close | open | [R4] None [R5] [#80] To prepare MU analysis and complete FR2 MOP and REFSENS. [R5] [#NR3] To prepare MU analysis and complete FR2 Priority 2 TCs.
4.2.3 | - |  | Tx part | Provide baseline MU associated with the minimally acceptable grid for constant step size and constant density grids. | Testabiliy | Completed (LS; R4-1808410) | close |  | close | open | [R4] None [R5] [#80] To prepare MU analysis and complete FR2 MOP. [R5] [#NR3] To prepare MU analysis and complete FR2 Priority 2 TCs.
4.2.4 | 2 |  | Rx part | Provide baseline MU associated with the minimally acceptable grid for constant step size and constant density grids. | Testabiliy | Not defined (LS; R4-1808410) | open |  | open | open | [R4] [#80] To complete items. Depends on the RSRP accuracy requirements to be finalized (item# 2.21.1,2.21.2, 2.21.3) [R5] [#81] To prepare MU analysis and complete REFSENS. [R5] [#NR3] To prepare MU analysis and complete FR2 Priority 2 TCs. | RAN5#81 (Nov-2018)