## Slide 1: RAN5 5G NR STATUS, DELIVERY phases and targets (February-19)
3GPP TSG-RAN5#82 R5-191295
Spokane, US, 12th - 16th Nov 2018

## Slide 2: Introduction & CONTENT
The purpose of this document is to give high level status of RAN5 completed 5GS test cases and the targets for the next RAN5 5GS delivery phases.
Content
Definitions of RAN5 5GS delivery phases and target dates
Completed deliveries
  NSA Option 3 (EN-DC)
  SA Option 2 (SA NR)
Planning content for next deliveries
  NSA Option 3 (EN-DC)
  SA Option 2 (SA NR)
  SA Option 5, NSA Option 4 (NE-DC), NSA Option 7 (NGEN-DC)

## Slide 3: Definitions of RAN5 5GS delivery phases and target dates
Overview: Time line - RAN5 5G NR deliveries versus RAN5 meeting
  Due to RAN5 workload for options 2 and 3 RAN5#82 agreed to defer the first phase for options 4,5 and 7 to RAN5#84.

## Slide 4
Definitions of RAN5 5GS delivery phases and targets
RF MU/TT Priority 1 test cases (regulatory):
  Max Output Power
  Ref Sensitivity
RF MU/TT Priority 2 test cases (regulatory):
  Transmit OFF power
  Occupied bandwidth
  Adjacent Channel Leakage Ratio
  Spurious emissions for UE co-existence
  Spectrum emission mask
  General spurious emissions
  Receiver Spurious emissions
RF MU/TT Priority 3 test cases: all other test cases
  The RAN5 targets for completing FR2 Measurement Uncertainty (MU) / Test Tolerances (TT) (Updated at RAN5#82, Ref: R5-192686)

## Slide 5: completed TEST CASES
Overview of completed test cases up to RAN5#82 (Feb-19)
  See attached document “5GS WP complete test cases v5.1” for details
Remarks:
  The reason for the decrease of 10 positioning test cases for EN-DC is that the existing LTE test cases can be used for EN-DC UEs and no specific variants for EN-DC are needed.
  The reason for the decrease of three (3) layer 2 test cases for SA NR is due to that additional changes are needed for SA NR for some PDCP test cases have been identified.

## Slide 6
RAN5 completed NSA Option 3 (EN-DC) Phase 3 at RAN5#82 (Feb-19)
Content:
  EN-DC configurations: LTE 1CC + NR FR1 1CC
  29 additional test cases completed
    EN-DC configurations: LTE 1xCC + NR FR1 1CC
    12 additional RF FR1 (7 Tx and 5 Rx) test cases
    First 2 RRM test cases
    15 additional RRC test cases
  See attached document “5GS WP complete test cases v5.1” for list of all completed NSA Option 3 test cases (including all delivery phases up to phase 3)
History:
  Phase 1 completed at RAN#79 (May-18)
  Phase 1.5 completed at RAN5#80 (Aug-18)
  Phase 2 completed at RAN5#81 (Nov-18)
completed NSA Option 3 (EN-DC) deliveries

## Slide 7
RAN5 completed NSA Option 2 Phase 2 at RAN5#82 (Feb-19)
Content:
  Test environment
    Various generic procedure enhancements e.g. for IMS registration and multi-PDU
    Current version limited to one network slice of type eMBB and two PDU sessions
  RF, Demod/CSI reporting and RRM:
    22 additional RF FR1 (17 Tx and 5 Rx) test cases
    First RF FR2 (Tx) test case
  Protocol:
    26 additional Idle Mode test cases
    1 additional Layer 2 SDAP test case
    24 additional RRC test cases
    23 additional 5GC NAS test cases
  See attached document “5GS WP complete test cases v5.1” for the list of all completed SA Option 2 test cases NSA Option 2 Phase1 & Phase 2)
History:
  Phase 1 completed at RAN5#81 (Nov-18)
completed SA Option 2 (SA NR) deliveries

## Slide 8
General considerations & Definitions
The RF, Demod/CSI reporting and RRM test cases can be divided into the following parts
  Test definition Test case description excluding MU (FR2) and TT (FR1 and FR2) part(s) i.e. non MU/TT parts of minimum requirements, Initial conditions, Test points, Test procedure, Specific message content etc.
  MU Measurement Uncertainty
  TT Test Tolerances
  Complete FR1 test case Test definition + MU + TT
  Complete FR2 test case Test definition + MU + TT
NOTE!
  The completion targets for EN-DC FR2 RF test cases are set based on the RAN5 MU/TT targets as described in R5-192686.
  Until the MU/TT becomes available it is important that the parts of test definition of the FR2 test cases that are NOT dependent on MU/TT are progressed as far as possible.
Planning CONTENT for next deliveries

## Slide 9
PlannED CONTENT:
NSA Option 3 (EN-DC) Phase 4 - Target RAN5#83 MAY-19
EN-DC configurations: LTE xCC + NR FR1/FR2 yCC, where x <= 3, y <=2
Test case completion targets
  RF LTE+NR FR1 test cases not completed in Phase 3 (TS 38.521-3)
  RF LTE+NR FR2 priority 1 and 2 test cases including MU/TT (TS 38.521-3), Note 1
  LTE+NR FR1 part of Demod/CSI reporting test cases (TS 38.521-4) where RAN4 requirements completed by April-19
  RRM LTE + NR FR1 test cases (TS 38.533) where RAN4 requirements completed by April-19
  Remaining protocol test cases (TS 38.523-1) not completed in NSA Opt.3 Phase 3
  Multi cell FR2 protocol test cases, Note 2
Other targets
  Test definition for LTE+NR FR2 Demod/CSI reporting (TS 38.521-4) and RRM (TS 38.533) test cases not completed in Phase 3
  Progress positioning performance test cases (TS 37.571-1)
  Test coverage enhancement for L1 configurations.
  Common test environment (TS 38.508-1) to enable LTE xCC + NR FR1/FR2 yCC test cases, where x <= 3, y <=2
Note 1: See slide 4 for MU/TT targets and definition of RF FR2 priority 1, 2 and 3 test cases.
Note 2: FR2 default levels for multi-cell protocol test cases was technically endorsed in R5-191347 at RAN5#82, but is dependent on RAN4 agreements at RAN4#90-Bis or RAN4#91.

## Slide 10
Planning for next deliveries:
NSA Option 3 (EN-DC) - Phase 5 content - Target RAN5#84 AUG-19
EN-DC configurations: LTE xCC + NR FR1/FR2 yCC, where x <= 4, y <=2
Test case completion targets
  RF LTE + NR FR2 priority 3 test cases including MU/TT (TS 38.521-3), Note 1
  LTE+NR FR1 part of Demod/CSI reporting test cases (TS 38.521-4) not completed in Phase 4
  LTE+NR FR2 part of Demod/CSI reporting (TS 38.521-4) test cases where MU/TT are completed
  and RRM (TS 38.533)
  RRM LTE + NR FR1 test cases (TS 38.533) where RAN4 requirements completed by Aug-19
  Positioning performance test cases (TS 37.571-1)
  IMS IR.92 EN-DC test cases, Note 2
Other targets
  MU/TT for LTE+NR FR2 Demod/CSI reporting (TS 38.521-4) and RRM (TS 38.533)
  Test coverage enhancement for L1 configurations.
  Common test environment (TS 38.508-1) to enable LTE xCC + NR FR1/FR2 yCC test cases, where x <= 4, y <=2
Note 1: See slide 4 for MU/TT targets and definition of RF FR2 priority 1, 2 and 3 test cases.
Note 2: The need for EN-DC IMS test cases on top of the existing E-UTRA IMS test cases depends on if GSMA adds any additional EN-DC specific requirements in IR.92 v13.0 and/or IR.94 v14.0 for EN-DC.

## Slide 11
Planned content:
SA Option 2 (SA NR) - Phase 3 - Target RAN5#83 MAY-19
SC FR1, SC FR2 and CA configurations for FR1 xCC, where x<=4
Test case completion targets
  RF FR1 priority 1 test cases (TS 38.521-1) for SC, UL-MIMO and CA, Note 1
  Demod FR1 priority 1 test cases (TS 38.521-4), Note 1
  RRM NR FR1 priority 1 test cases (TS 38.533), Note 1
  RF FR2 priority 1 and 2 test cases including MU/TT (TS 38.521-3), Note 2
  SA NR protocol test cases for FR1, Note 3
    NR Voice service fallback to E-UTRAN (EPS Fallback), Note 7
    SMS over NAS
    Inter-RAT between NR and LTE, for both Idle Mode, RRC connected state, NAS
    NR-NR Measurements and Handover (Intra and Inter Frequency and Inter-band)
    CA
    5GC Single Registration (with N26 interworking)
    5GC Mobility Management priority 1 test cases, Note 5
    5GC Session Management priority 1 test cases, Note 5
    5GC Authentication, 5G AKA
    Multi-PDU
  Multi cell FR2 protocol test cases, Note 8
Other targets
  Test definition for NR FR2 Demod/CSI reporting (TS 38.521-4), Note 6
  Test definition for NR FR2 RRM (TS 38.533), Note 6
  Completion of test frequencies for FR1 1CC Bands and Freq Tables, Note 3
  Protocol test case definition of, Note 3:
    SMS over IP , Note 4
    VoNR, Note 4
    Emergency Services, Note 7
Note 1: RF/Demod/RRM FR1 priority 1 test cases are test cases with only RAN5 dependencies, i.e. completed in RAN4 by March-19. RF/Demod/RRM FR1 priority 2 test cases are test cases not completed in RAN4 by March-19 (RF/Demod/RRM priorities as agreed at RAN5#82, ref: R5-192832).
Note 2: See slide 4 for MU/TT targets and definition of RF FR2 priority 1, 2 and 3 test cases.
Note 3: RAN5 agreed priorities for RAN5#83 targets for SA Option 2 and protocol test cases at RAN5#82 (ref: R5-192869).
Note 4: Dependent on availability of GSMA NG.114 profile by April-19.
Note 5: See R5-192829 for details of priority 1 5GC Mobility Management and Session Management test cases.
Note 6: Dependency: RAN4 progress until RAN4#91 (May-19)
Note 7: Will be part of new sub-area work plan for Multilayer covering 5GC/EPC fallback, Emergency, Unified Access Control (UAC) and SDAP+5GSM interaction.
Note 8: FR2 default levels for multi-cell protocol test cases was technically endorsed in R5-191347 at RAN5#82, but is dependent on RAN4 agreements at RAN4#90-Bis or RAN4#91.

## Slide 12
SC FR1+ SC FR2 + CA configurations and Synchronous NR-NR DC for FR1 xCC,FR2 xCC, (FR1+FR2) xCC:, where x<=4
Test case completion targets
  RF FR1 priority 2 test cases (TS 38.521-1), Note 1
  Demod/CSI reporting FR1 priority 2 test cases (TS 38.521-4), Note 1
  RRM NR FR1 priority 2 test cases (TS 38.533), Note 1
  RF FR2 priority 3 test cases including MU/TT (TS 38.521-3), Note 2
  Protocol test case definition of, Note 3:
    SMS over IP
    VoNR
    Emergency Services
    UAC
Further targets to be set at RAN5#83
Note 1: RF/Demod/RRM FR1 priority 1 test cases are test cases with only RAN5 dependencies, i.e. completed in RAN4 by March-19. RF/Demod/RRM FR1 priority 2 test cases are test cases not completed in RAN4 by March-19 (RF/Demod/RRM priorities as agreed at RAN5#82, ref: R5-192832).
Note 2: See slide 4 for MU/TT targets and definition of RF FR2 priority 1, 2 and 3 test cases.
Note 3: RAN5 agreed priorities for RAN5#83 targets for SA Option 2 and protocol test cases at RAN5#82 (ref: R5-192869).
Planned content:
SA Option 2 (SA NR) - Phase 4 - Target RAN5#84 AUG-19

## Slide 13
RAN5#82 decided to defer SA Option 5 Phase 1 by 3 months to RAN5#84
Content: FFS
Planned content:
SA Option 5 (SA E-UTRA) - Phase 1 - Target RAN5#84 AUG-19

## Slide 14
RAN5#82 decided to defer NSA Option 4 & 7 Phase 1 by 3 months to RAN5#84
Content: FFS
Planned content:
SA Option 4 & 7 (NE-DC & NGEN-DC) - Phase 1 - Target RAN5#84 AUG-19