## R5#87-e
3GPP TSG RAN WG5 (RAN5) Meeting #87-e | [9 empty] | R5-201313 (Draft)
Electronic Meeting, 18 - 29 May 2020
WI Progress and Target Completion Date Review
Source: RAN5 Chair
To: RAN5
Purpose: For Endorsement
UIC | WI Name | Rel | Tdoc# | Pre TCD | pre % | post % | post TCD | change (mths) | Rapporteur | other comments
720098 | UE Conformance Test Aspects – Rel-14 CA configurations | Rel-14 | R5-203119 | 2020-06-01 | 36% | 37% | 2020-12-01 | +6 | Ericsson
760087 | UE Conformance Test Aspects - 5G system with NR and LTE | Rel-15 | R5-201560 | 2020-12-01 | 69% |  |  |  | Ericsson
770064 | UE Conformance Test Aspects – Rel-15 CA configurations | Rel-15 | R5-201556 | 2020-09-01 | 20% | 21% | 2020-12-01 | +3 | Ericsson
780065 | UE Conformance Test Aspects - Add UE Power Class 2 to band 41 intra-band contiguous LTE Carrier Aggregation | Rel-15 | R5-201774 | 2020-06-01 | 29% | 100% |  |  | Sprint
790052 | UE Conformance Test aspects -Mission Critical Improvements | Rel-14 | R5-202369 | 2020-06-01 | 60% | 95% | 2020-09-01 | +3 | NIST
810061 | UE Conformance Test aspects - Rel-16 LTE CA configurations | Rel-16 | R5-201558 | 2020-12-01 | 7% | 7% | 2020-12-01 |  | Ericsson
820064 | UE Conformance Test aspects - Shortened TTI and processing time for LTE | Rel-15 | R5-201865 | 2020-12-01 | 5% | 70% | 2020-12-01 |  | Huawei
820066 | UE Conformance Test aspects - Enhancing LTE CA Utilization | Rel-15 | R5-202480 | 2020-06-01 | 35% | 35% | 2020-12-01 | +6 | Nokia
830083 | UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | Rel-16 | R5-201914 | 2020-06-01 | 6% | 6% | 2020-12-01 | +6 | CMCC
830085 | UE Conformance Test Aspects - Enhancements on Full-Dimension (FD) MIMO for LTE | Rel-14 | R5-202373 | 2020-06-01 | 5% | 5% | 2020-12-01 | +6 | Ericsson
840090 | Study on 5G NR User Equipment (UE) Application Layer Data Throughput Performance | Rel-16 | R5-202467 | 2020-06-01 | 75% | 80% | 2020-09-01 | +3 | Qualcomm
850061 | UE Conformance Test Aspects - LTE Advanced high power TDD UE (power class 2) for Rel-15 | Rel-15 | R5-202510 | 2020-09-01 | 5% | 15% | 2020-12-01 | +3 | Huawei
850062 | UE Conformance Test Aspects - New Rel-16 NR bands and extension of existing NR bands | Rel-16 | R5-201564 | 2020-06-01 | 16% | 28% | 2020-12-01 | +6 | Ericsson
860030 | UE Conformance Test Aspects - Addition of Power Class 2 UE for LTE bands 31 and 72 | Rel-16 | R5-202507 | 2020-06-01 | 0% | 0% | 2020-09-01 | +3 | Airbus
860031 | UE Conformance Test Aspects - Further NB-IoT enhancements | Rel-15 | R5-202168 | 2020-12-01 | 1% | 5% | 2020-12-01 |  | CATT
860032 | UE Conformance Test Aspects - Even further enhanced MTC for LTE | Rel-15 | R5-202015 | 2020-12-01 | 1% | 10% | 2020-12-01 |  | Ericsson
870061 | UE Conformance Test Aspects - RF requirements for NR frequency range 1 (FR1) | Rel-16 | R5-201867 | 2021-12-01 |  |  |  |  | Huawei
870062 | UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band) | Rel-16 | R5-201920 | 2021-03-01 |  | 80% | 2021-03-01 |  | CMCC