## Cover sheet
3GPP TSG-RAN WG5 Meeting #90-e | [10 empty] | R5-210759
Electronic Meeting, 22nd February - 5th March 2021
Agenda Item: | 7.4.2
Source: | Huawei
Title: | WP - Shortened TTI and processing time for LTE
Work item code: | LTE_sTTIandPT-UEConTest
Release: | Rel-15
Document for: | Information
RAN5 WP template v2.0
1. Introduction
At the RAN#82 meeting in Sorrento, Italy a Rel-15 RAN5 work item for LTE shortened TTI and short processing time (LTE_sTTIandPT-UEConTest) was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 100% (+7%) | 33 (+21) | 33 (+1)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE |  | 100% (+7.4%) | 33 (+21) | 33 (+1)
FDD |  | 100% (+7.4%) | 27 (+15) | 27 (+1)
TDD |  | 100% (+7.4%) | 27 (+15) | 27 (+1)
FDD + TDD
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FDD |  |  | TDD |  |  | FDD + TDD
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 100% |  |  | 100% |  |  | 100%
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1 | 100% |  |  | 100% |  |  | 100%
RF Rx test cases | 36.521-1 Rx | 100% (+5%) | 10 (+10) | 10 | 100% (+5%) | 5 (+5) | 5 | 100% (+5%) | 5 (+5) | 5
RF Tx test cases | 36.521-1 Tx | 100% (+28.7%) | 9 (+9) | 9 (+1) | 100% (+28.7%) | 9 (+9) | 9 (+1) | 100% (+28.7%) | 9 (+9) | 9 (+1)
RF Demod test cases | 36.521-1 Demod
Applicability RF, Demod/QSI and RRM test cases | 36.521-2 | 100% (+10%) |  |  | 100% (+10%) |  |  | 100% (+10%)
RRM test cases | 36.521-3
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 100% | 12 | 12 | 100% | 12 | 12 | 100% | 12 | 12
Applicability Protocol test cases | 36.523-2 | 100% |  |  | 100% |  |  | 100%
Test suites (TTCN) | 36.523-3
5 References
[1] RP-182429 | New WID on UE Conformance Test Aspects - Shortened TTI and short processing time for LTE
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance Test Aspects - Shortened TTI and short processing time for LTE | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_sTTIandPT-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item Shortened TTI and short processing time for LTE comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [12 empty] | vs Area
WP Resp: |  | Chunying Gu, Huawei |  |  | guchunying@huawei.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FDD | TDD | FDD + TDD
[14 empty] | 100% (+7.4%) | 100% (+7.4%)
[14 empty] | 45 (+1) | 45 (+1) | 0
[14 empty] | 35 (+1) | 35 (+1) | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE - RAN and CN
LTE Common
TS 36.508: Common test environment
|  | 36.508 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 36.508 | 4, 5, 6 and 7 | <Title of new sub-clause header> | Introduction of RF, Signaling and RRM Test Environment for LTE sTTI testing. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203049, R5-203922, R5-205761 |  | 1 | 100% | 100% |  | 100% | 100%
TBD |  | 36.508 | Annex A | <Title of task> | Introduction of Connection diagrams for sTTI testing | Huawei, Hisilicon | TBD |  | No need to change | 0
TS 36.509: UE specific testing functions
|  | 36.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.508 | <Clause> | <Title of new sub-clause header> | Introduction of UE test loop modes to support sTTI testing. |  | TBD |  | No need to change | 0
E-UTRA RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
|  | 36.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 36.521-1 | 3, 4 | Definitions, Abbreviations, Applicability | Introduce sTTI related definitions. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203927 | TS 36.101 3, 4 | 1 | 100% | 100% |  | 100% | 100%
3 |  | 36.521-1 | Annex A | Measurement Channels |  | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203936 | TS 36.133 A.3.1, A.3.26 | 1 | 100% | 100% |  | 100% | 100%
4 |  | 36.521-1 | Annex I | Conditions for sTTI |  | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-205768 | TS 36.133 Annex B.7 | 1 | 100% | 100% |  | 100% | 100%
5 |  | 36.521-1 | Annex E | Global In-Channel TX-Test | Adding the calculation of EVM for subslot/slot TTI | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-201895 |  | 1 | 100% | 100% |  | 100% | 100%
TS 36.521-1: RF test cases - Tx
|  | 36.521-1 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
6 | Y | 36.521-1 Tx | 6.2.2_s | UE Maximum Output Power for subslot/slot TTI |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202855, R5-203928, R5-205764, R5-206877，R5-210776 | TS 36.101 6.2.2 | 1 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
7 | Y | 36.521-1 Tx | 6.2.3_s | UE maximum output power for modulation / channel bandwidth for subslot/slot TTI |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-203090, R5-203928, R5-205764, R5-206877, R5-210776 | TS 36.101 6.2.3 | 1 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
8 | Y | 36.521-1 Tx | 6.2.4_s | UE maximum output power with additional requirements for subslot/slot TTI |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202856, R5-203928, R5-205764, R5-206877, R5-210776 | TS 36.101 6.2.4 | 1 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
9 | Y | 36.521-1 Tx | 6.2.5_s | Configured transmitted power for subslot/slot TTI |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202767, R5-203928, R5-205764, R5-206877, R5-210776 | TS 36.101 6.2.5 | 1 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
10 | Y | 36.521-1 Tx | 6.3.4.1_s | General ON/OFF time mask for sTTI |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202768, R5-203928, R5-205764, R5-206877, R5-210776 | TS 36.101 6.3.4.1 | 1 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
11 | Y | 36.521-1 Tx | 6.5.2.1_s | Error Vector Magnitude for subslot/slot TTI |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202857, R5-203928, R5-205764, R5-206877, R5-210776 | TS 36.101 6.5.2.1 | 1 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
12 | Y | 36.521-1 Tx | 6.6.2.1_s | Spectrum Emission Mask for subslot/slot TTI |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211755 | TS 36.101 6.2.3 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
13 | Y | 36.521-1 Tx | 6.6.2.3_s | Adjacent Channel Leakage power Ratio for subslot/slot TTI |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211756 | TS 36.101 6.2.3 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
14 | Y | 36.521-1 Tx | 6.6.2.2_s | Additional Spectrum Emission Mask for subslot/slot TTI |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-211903 | TS 36.101 6.2.4 | 1 | 100% (+100%) | 100% (+100%) |  | 100% | 100%
TS 36.521-1: RF test cases - Rx
|  | 36.521-1 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.521-1 Demod | <Clause> | <Title of new sub-clause header> | New sub-clause header | Huawei, Hisilicon | TBD |  |  | 0
TBD |  | 36.521-1 Demod | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | TBD
TBD | Y | 36.521-1 Demod | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1
TS 36.521-1: Demod/QSI reporting test cases
|  | 36.521-1 Demod |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  | Huawei, Hisilicon |  |  |  | TBD
14 |  | 36.521-1 Rx | 8.14 | Demodulation (UE supporting Short TTI) | New sub-clause header |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
15 |  | 36.521-1 Rx | 8.14.1 | Slot-PDSCH and Subslot-PDSCH | New sub-clause header |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
16 |  | 36.521-1 Rx | 8.14.1.1 | FDD | New sub-clause header |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% (+5%) | 100% (+5%) |  | 100%
17 | Y | 36.521-1 Rx | 8.14.1.1.1 | FDD slot/subslot-PDSCH Open-loop spatial multiplexing performance |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202770, R5-204892, R5-205765, R5-206877, R5-210777 | TS 36.101 8.14.1.1.1 | 1 | 100% (+5%) | 100% (+5%) |  | 100%
18 | Y | 36.521-1 Rx | 8.14.1.1.2 | FDD slot/subslot-PDSCH Closed-loop spatial multiplexing performance (User-Specific Reference Signals) |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202771, R5-204892, R5-205765, R5-206877, R5-210777 | TS 36.101 8.14.1.1.2 | 1 | 100% (+5%) | 100% (+5%) |  | 100%
19 |  | 36.521-1 Rx | 8.14.1.2 | TDD | New sub-clause header |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% (+5%) | 100% (+5%) |  |  | 100%
20 | Y | 36.521-1 Rx | 8.14.1.2.1 | TDD slot/subslot-PDSCH Open-loop spatial multiplexing performance |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202772, R5-204892, R5-205765, R5-206877 | TS 36.101 8.14.1.2.1 | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
21 | Y | 36.521-1 Rx | 8.14.1.2.2 | TDD slot/subslot-PDSCH Closed-loop spatial multiplexing performance (User-Specific Reference Signals) |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202773, R5-204892, R5-205765, R5-206877 | TS 36.101 8.14.1.2.2 | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
22 |  | 36.521-1 Rx | 8.14.2 | SPDCCH | New sub-clause header |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
23 | Y | 36.521-1 Rx | 8.14.2.1 | FDD SPDCCH Transmit diversity performance |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202774, R5-204892, R5-205765, R5-206877, R5-210777 | TS 36.101 8.14.2.1 | 1 | 100% (+5%) | 100% (+5%) |  | 100%
24 | Y | 36.521-1 Rx | 8.14.2.2 | TDD SPDCCH Transmit diversity performance |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202775, R5-204892, R5-205765, R5-206877 | TS 36.101 8.14.2.2 | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
25 |  | 36.521-1 Rx | 9.12 | CSI reporting (UE supporting Short TTI) | New sub-clause header |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
26 |  | 36.521-1 Rx | 9.12.1 | Cell-Specific Reference Symbol | New sub-clause header |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
27 | Y | 36.521-1 Rx | 9.12.1.1 | FDD CQI reporting under fading conditions (UE supporting Short TTI) (Cell-Specific Reference Symbol) |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202776, R5-203930, R5-205765, R5-206877, R5-210778 | TS 36.101 9.12.1.1 | 1 | 100% (+5%) | 100% (+5%) |  | 100%
28 | Y | 36.521-1 Rx | 9.12.1.2 | TDD CQI reporting under fading conditions (UE supporting Short TTI) (Cell-Specific Reference Symbol) |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202777, R5-203930, R5-205765, R5-206877, R5-210778 | TS 36.101 9.12.1.2 | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
29 |  | 36.521-1 Rx | 9.12.2 | CSI Reference Symbol | New sub-clause header |  | RAN5#90-e (Feb-21) |  |  | 0 | 100% (+5%) | 100% (+5%) |  | 100% | 100%
30 | Y | 36.521-1 Rx | 9.12.2.1 | FDD CQI reporting under fading conditions (UE supporting Short TTI) (CSI Reference Symbol) |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202778, R5-203930, R5-205765, R5-206877, R5-210778 | TS 36.101 9.12.2.1 | 1 | 100% (+5%) | 100% (+5%) |  | 100%
31 | Y | 36.521-1 Rx | 9.12.2.2 | TDD CQI reporting under fading conditions (UE supporting Short TTI) (CSI Reference Symbol) |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-202779, R5-203930, R5-205765, R5-206877, R5-210778 | TS 36.101 9.12.2.2 | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
TS 36.521-2: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 36.521-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
32 |  | 36.521-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. | Huawei, Hisilicon | RAN5#90-e (Feb-21) |  |  | 0.5 | 100% (+10%) | 100% (+10%) |  | 100% | 100%
TS 36.521-3: RRM test cases
|  | 36.531-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
33 |  | 36.531-3 | 3 | Definitions, symbols and abbreviations | Introduce sTTI related definitions, symbols and abbreviations | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203933 | TS 36.133 cl 3. | 0.5 | 100% | 100% |  | 100% | 100%
34 | Y | 36.531-3 | 7.2.13 | E-UTRAN FDD – UE Timing Advance Adjustment delay Test for sTTI and Short Processing Time |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-204798, R5-206710, R5-206878, R5-206711 | TS 36.133 A.7.2.13 | 1 | 100% (+5%) | 100% (+5%) |  | 100%
35 | Y | 36.531-3 | 7.2.14 | E-UTRAN TDD – UE Timing Advance Adjustment delay Test for sTTI and Short Processing Time |  | Huawei, Hisilicon | RAN5#90-e (Feb-21) | R5-204799, R5-206710, R5-206878, R5-206711 | TS 36.133 A.7.2.14 | 1 | 100% (+5%) | 100% (+5%) |  |  | 100%
36 |  | 36.531-3 | Annex A | Measurement Channels |  | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203936 | TS 36.133 A.3.1, A.3.26 | 0.6 | 100% | 100% |  | 100% | 100%
37 |  | 36.531-3 | Annex I | Conditions for sTTI |  | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-205768 | TS 36.133 Annex B.7 | 0.6 | 100% | 100% |  | 100% | 100%
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
|  | 36.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
38 |  | 36.523-1 | 3 | Definitions, symbols and abbreviations | Introduce sTTI related definitions, symbols and abbreviations | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-206387 |  | 0.3 | 100% | 100% |  | 100% | 100%
Layer 2
39 | Y | 36.523-1 | 7.1.3.22 | Short Processing Time / Correct handling of DL assignment / HARQ process sharing | 1. Verify that the UE DL HARQ RTT is set to 6 subframes when the HARQ process is using Short Processing Time. 2. Verify that the processing time of initial transmission and retransmission of the same HARQ process can be different. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203050 R5-203055, R5-204494, R5-204495 | TS 36.321 subclause 7.7 | 1 | 100% | 100% |  | 100% | 100%
40 | Y | 36.523-1 | 7.1.4.37 | Short Processing Time / Correct handling of UL assignment | Verify that the UE UL HARQ RTT is set to 6 subframes when the HARQ process is using Short Processing Time. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203051 R5-203055, R5-203924, R5-204495 | TS 36.321 subclause 7.7 | 1 | 100% | 100% |  | 100% | 100%
41 | Y | 36.523-1 | 7.1.3.18 | Short TTI / Correct handling of DL assignment / Collision handling | 1. Verify the UE performs PDSCH transmission with slot/subslot operation. 2. Verify the UE performs both CRS-based and DMRS-based SPDCCH with slot/subslot operation. 3. Verify the UE DL HARQ RTT with different min-processingTimeTA-set1/set2 configurations. 4. Verify that when collision occurs between SPUCCH and PUCCH/PUSCH, SPUCCH is transmitted while the transmission of PUCCH/PUSCH is dropped. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203080 R5-203055, R5-204494, R5-204495, R5-205762 | TS 36.321 subclause 7.7 | 1 | 100% | 100% |  | 100% | 100%
42 | Y | 36.523-1 | 7.1.3.19 | Short TTI / Correct handling of DL assignment / HARQ sharing between PDSCH and slot/subslot-PDSCH | Verify that the TTI length of initial transmission and retransmission of the same DL HARQ process can be different. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203081 R5-203055, R5-204494, R5-204495, R5-205762 | TS 36.321 subclause 7.7 | 1 | 100% | 100% |  | 100% | 100%
43 | Y | 36.523-1 | 7.1.3.20 | Short TTI / Correct handling of DL assignment / multiplexing of SPDCCH and slot/subslot-PDSCH | Verify the UE transmits slot/subslot-PDSCH and sPDCCH by multiplexing the SPDCCH resources. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203082 R5-203055, R5-204494, R5-204495, R5-205762 | TS 36.321 subclause 7.7 | 1 | 100% | 100% |  | 100% | 100%
44 | Y | 36.523-1 | 7.1.3.21 | Short TTI / Correct handling of DL assignment / DMRS sharing | Verify the DMRS shared across downlink subslots within a subframe. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203083 R5-203055, R5-204494, R5-204495, R5-205762 | TS 36.213 subclause 7.1 | 1 | 100% | 100% |  | 100% | 100%
45 | Y | 36.523-1 | 7.1.4.38 | Short TTI / Correct handling of UL assignment / Collision handling | 1. Verify the UE performs PUSCH transmission with slot/subslot operation. 2. Verify the UE UL HARQ RTT with different min-processingTimeTA-set1/set2 configurations. 3. Verify that when collision occurs between slot/subslot-PUSCH and PUCCH/PUSCH, slot/subslot-PUSCH is transmitted while the transmission of PUCCH/PUSCH is dropped. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203084 R5-203055, R5-203924, R5-204495, R5-205762 | TS 36.321 subclause 7.7 | 1 | 100% | 100% |  | 100% | 100%
46 | Y | 36.523-1 | 7.1.4.39 | Short TTI / Correct handling of UL assignment / DMRS sharing | Verify the DMRS shared by different UEs across uplink subslots within a subframe. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203052 R5-203055, R5-203924, R5-204495 | TS 36.321 subclause 7.7 | 1 | 100% | 100% |  | 100% | 100%
47 | Y | 36.523-1 | 7.1.4.40 | Short TTI / Correct handling of MAC control information / Scheduling requests and SPUCCH | Verify the UE transmits SR on SPUCCH. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203085 R5-203055, R5-203924, R5-204495 | TS 36.321 subclause 7.7 | 1 | 100% | 100% |  | 100% | 100%
48 | Y | 36.523-1 | 7.1.4.41 | Short TTI / Correct handling of UL assignment / HARQ sharing between PUSCH and slot/subslot-PUSCH | Verify that the TTI length of initial transmission and retransmission of the same UL HARQ process can be different. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203053 R5-203055, R5-203924, R5-204495 | TS 36.211 subclause 5.5.2 | 1 | 100% | 100% |  | 100% | 100%
RRC
49 | Y | 36.523-1 | 8.2.2.11 | Short Processing Time / SRS configuration / Aperiodic | Verify that the UE transmits aperiodic SRS with Short Processing Time. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203086 R5-203055, R5-203925, R5-204495 | TS 36.213 subclause 8.2 | 1 | 100% | 100% |  | 100% | 100%
50 | Y | 36.523-1 | 8.2.2.12 | Short TTI / SRS configuration / TDD / Aperiodic | Verify that the UE transmits aperiodic SRS corresponds with sTTI configuration. | Huawei, Hisilicon | RAN5#89-e (Nov-20) | R5-203054 R5-203055, R5-203925, R5-204495 | TS 36.213 subclause 8.2 | 1 | 100% | 100% |  | 100% | 100%
TS 36.523-2: Applicability for Protocol test cases
TBD |  | 36.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
51 |  | 36.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 | Huawei, Hisilicon | RAN5#89-e (Nov-20) |  |  | 0.5 | 100% | 100% |  | 100% | 100%
TS 36.523-3: Protocol test suites (TTCN)
|  | 36.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 36.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.