## Summary
Work plan summary:
NR RF Performance (TS 38.521-4)
Completion
|  |  | Overall | FR1 | FR2 | FR1+FR2
| NR RF Performance (TS 38.521-4) | SA Option 2 (SA NR) | 98.41% | 99.83% | 92.99%
|  | NSA Option 3 (EN-DC) | 99.74% | 99.83% | 99.36%
SA Option 5
|  | NSA Option 4 (NE-DC) | 98.33% | 98.11% | 99.27%
|  | NSA Option 7 (NGEN-DC) | 99.83%
Test case statistics
|  |  | Overall number of test cases |  | Number of test cases applicable for FR1 |  | Number of test cases applicable for FR2 |  | Number of FR1+FR2 specific test cases
|  |  | Overall | Completed for at least one of FR1, FR2 or FR1+FR2 | Overall | Completed | Overall | Completed | Overall | Completed
| NR RF Performance (TS 38.521-4) | SA Option 2 (SA NR) | 62 | 61 | 53 | 53 | 9 | 8 | 0 | 0
|  | NSA Option 3 (EN-DC) | 62 | 62 | 53 | 53 | 9 | 9 | 0 | 0
|  | SA Option 5 | 0 | 0
|  | NSA Option 4 (NE-DC) | 61 | 60 | 53 | 52 | 8 | 8 | 0 | 0
|  | NSA Option 7 (NGEN-DC) | 60 | 60

## RF Perf
WP Title: | NR RF Performance (TS 38.521-4) | [12 empty] | WP item applicability | [14 empty] | End of work plan columns. Note! Do not remove this column.
RAN-CN interface options dependency
WP Scope: | NR RF Performance (TS 38.521-4) | [12 empty] | 5GC/NR |  |  |  | 5GC/LTE | EPC/LTE |  |  |  | 5GC/NR master |  |  |  | 5GC / LTE master
WP Resp: | Balasubramanian, Vijay, Qualcomm |  |  |  | vijayb@qti.qualcomm.com
TS Resp: | Balasubramanian, Vijay, Qualcomm |  |  |  | vijayb@qti.qualcomm.com | [8 empty] | SA |  |  |  |  | NSA
[14 empty] | Opt.2 |  |  |  | Opt.5 | Opt.3 |  |  |  | Opt.4 |  |  |  | Opt.7
WP Item ID | Is test case | TS | Clause | Title | Test id | Company | Target | TDOC(s) | custom | Comments | RAN4 completion | Weight | WP item compl. | 1st Target | FR1 | FR2 | FR1+FR2 |  | 1st Target | FR1 | FR2 | FR1+FR2 | 1st Target | FR1 | FR2 | FR1+FR2
[13 empty] | Overall |  | 98.41% |  |  |  |  | 99.74% |  |  |  | 98.33% |  |  | 99.83%
[15 empty] | 99.83% | 92.99% |  |  |  | 99.83% | 99.36% |  |  | 98.11% | 99.27%
[13 empty] | Phase 1 | [10 empty] | 99.81% | 99.27% |  | 99.83%
[13 empty] | Phase 2 | [10 empty] | 0%
[13 empty] | Phase 3 |  | 100%
[13 empty] | Phase 4 |  | 100% | 100% |  |  |  | 100%
[13 empty] | Phase 5 |  | 100% | 100% |  |  |  | 100% | 100%
[13 empty] | Phase 6 |  | 100% |  |  |  |  | 100% | 100%
[13 empty] | Phase 7 |  | 100% |  |  |  |  | 100%
[13 empty] | Phase 8 |  | 100% |  |  |  |  | 100%
[13 empty] | Phase 9 |  |  | 100% |  |  |  | 100%
[13 empty] | Phase 10 |  |  | 100% |  |  |  |  | 100%
[13 empty] | Phase 11 |  |  | 100% |  |  |  |  | 100%
[13 empty] | Phase 12 |  | 100% | 100% |  |  |  |  | 100%
[13 empty] | Phase 13 |  | 90% | 45% |  |  |  | 100% | 100%
[13 empty] | Phase 14 | [6 empty] | 90% | 90%
[7 empty] | Overall #WP items: Phase 1 #WP items: Phase 2 #WP items: Phase 3 #WP items:: Phase 4 #WP items: Phase 5 #WP items: Phase 6 #WP items: Phase 7 #WP items: Phase 8 #WP items: Phase 9 #WP items: Phase 10 #WP items: Phase 11 #WP items: Phase 12 #WP items: Phase 13 #WP items: Phase 14 #WP items: | [7 empty] | 66 0 0 18 26 9 8 1 2 0 0 0 1 1 0 | 17 0 0 0 2 3 0 0 0 5 1 2 2 2 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 |  | 66 0 0 0 20 25 8 8 1 2 0 0 0 1 1 | 17 0 0 0 0 2 3 0 0 0 5 1 2 3 1 | 0 0 0 0 0 0 0 0 0 0 0 0 0 0 0 |  | 65 64 1 | 15 15 0 | 0 0 0 | 74 74 0
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [13 empty] | Phase number (1,2 etc) and completion (%) per option
|  | 4 | General
1 |  | 38.521-4 | 4.1, 4.2, 4.3 | General |  | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  |  |  | 0.1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
2 |  | 38.521-4 | 4.4 | Conducted requirements |  | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS |  |  |  |  | 0.1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
3 |  | 38.521-4 | 4.5 | Radiated requirements |  | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-206833 |  |  |  | 0.1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
4 |  | 38.521-4 | 4.6 | Test coverage across 5G NR architecture options |  | Qualcomm | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-215666 |  |  |  | 0.1 | 95% | 5 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 90% |  |  | 1 | 90%
|  | 5 | Demodulation performance requirements (Conducted requirements)
5 |  | 38.521-4 | 5.1 | General |  | All companies | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193337 R5-194680 R5-196498 R5-197374 R5-200682 R5-203298 |  |  |  | 0.1 | 100% | 4 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
6 |  | 38.521-4 | 5.2 | PDSCH demodulation requirements |  |  | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193329 R5-196498 R5-198409 R5-199421 R5-200450 |  |  |  | 0.1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
7 |  | 38.521-4 | 5.2.1 | 1RX requirements (Void) | [7 empty] | 0.1 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
8 |  | 38.521-4 | 5.2.2 | 2RX requirements | [7 empty] | 0.1 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
9 |  | 38.521-4 | 5.2.2.1 | FDD | [7 empty] | 0.1 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
10 |  | 38.521-4 | 5.2.2.1.1 | 2Rx FDD FR1 PDSCH mapping Type A performance | [7 empty] | 0.1 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
11 | Y | 38.521-4 | 5.2.2.1.1_1 | 2Rx FDD FR1 PDSCH mapping Type A performance - 2x2 MIMO with baseline receiver for both SA and NSA | [1-1, 1-2, 1-3, 1-4, 2-1, 2-2] | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188009 R5-190932 R5-193329 R5-195003 R5-197375 R5-197377 R5-200453 R5-202832 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
12 | Y | 38.521-4 | 5.2.2.1.1_2 | 2Rx FDD FR1 PDSCH Mapping Type A performance - 2x2 MIMO with enhanced receiver type 1 for both SA and NSA | [3-1] | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188009 R5-190932 R5-193330 R5-194989 R5-197375 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
13 |  | 38.521-4 | 5.2.2.1.2 | 2Rx FDD FR1 PDSCH mapping Type A and CSI-RS overlapped with PDSCH performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
14 | Y | 38.521-4 | 5.2.2.1.2_1 | 2Rx FDD FR1 PDSCH mapping Type A and CSI-RS overlapped with PDSCH performance - 2x2 MIMO with baseline receiver for both SA and NSA | [1-1] | Ericsson | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192467 R5-193324 R5-194999 R5-202832 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
15 |  | 38.521-4 | 5.2.2.1.3 | 2Rx FDD FR1 PDSCH mapping Type B performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
16 | Y | 38.521-4 | 5.2.2.1.3_1 | 2Rx FDD FR1 PDSCH mapping Type B performance - 2x2 MIMO with baseline receiver for both SA and NSA | [1-1] | Huawei | Opt 2: RAN5#86 (Feb-20) Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199382 R5-200710 R5-202832 R5-204774 R5-211716 |  |  |  | 1 | 100% | 6 | 100% |  |  | 1 | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
17 |  | 38.521-4 | 5.2.2.1.4 | 2Rx FDD FR1 PDSCH Mapping Type A and LTE-NR coexistence performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
18 | Y | 38.521-4 | 5.2.2.1.4_1 | 2Rx FDD FR1 PDSCH Mapping Type A and LTE-NR coexistence performance - 4x2 MIMO with baseline receiver for both SA and NSA | [1-1, 1-2] | Anritsu | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-195169 R5-195558 R5-202832 R5-204064 R5-210521 R5-206666 R5-205925 R5-211716 R5-213342 R5-216040 R5-216041 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
19 |  | 38.521-4 | 5.2.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
20 |  | 38.521-4 | 5.2.2.2.1 | 2Rx TDD FR1 PDSCH mapping Type A performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
21 | Y | 38.521-4 | 5.2.2.2.1_1 | 2Rx TDD FR1 PDSCH mapping Type A performance - 2x2 MIMO with baseline receiver for both SA and NSA | [1-1, 1-2, 1-3, 1-4, 1-5, 1-6, 2-1, 2-2] | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188006 R5-190054 R5-192673 R5-193334 R5-194979 R5-197573 R5-197574 R5-200453 R5-202832 R5-206163 R5-210520 R5-213341 R5-215345 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
22 | Y | 38.521-4 | 5.2.2.2.1_2 | 2Rx TDD FR1 PDSCH Mapping Type A performance - 2x2 MIMO with enhanced receiver type 1 for both SA and NSA | [3-1] | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190054 R5-193334 R5-194979 R5-197574 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
23 |  | 38.521-4 | 5.2.2.2.2 | 2Rx TDD FR1 PDSCH mapping Type A and CSI-RS overlapped with PDSCH performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
24 | Y | 38.521-4 | 5.2.2.2.2_1 | 2Rx TDD FR1 PDSCH mapping Type A and CSI-RS overlapped with PDSCH performance - 2x2 MIMO with baseline receiver for both SA and NSA | [1-1] | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192468 R5-193331 R5-194990 R5-197375 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
25 |  | 38.521-4 | 5.2.2.2.3 | 2Rx TDD FR1 PDSCH mapping Type B performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
26 | Y | 38.521-4 | 5.2.2.2.3_1 | 2Rx TDD FR1 PDSCH mapping Type B performance - 2x2 MIMO with baseline receiver for both SA and NSA | [1-1] | Qualcomm | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-204870 R5-211716 |  |  |  | 1 | 100% | 8 | 100% |  |  | 1 | 9 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
27 |  | 38.521-4 | 5.2.3 | 4RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
28 |  | 38.521-4 | 5.2.3.1 | FDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
29 |  | 38.521-4 | 5.2.3.1.1 | 4Rx FDD FR1 PDSCH mapping Type A performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
30 | Y | 38.521-4 | 5.2.3.1.1_1 | 4Rx FDD FR1 PDSCH mapping Type A performance - 2x4 MIMO with baseline receiver for both SA and NSA | [1-1, 1-2, 1-3, 2-1, 2-2, 1-4] | LGE | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190926 R5-195170 R5-197379 R5-198281 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
31 | Y | 38.521-4 | 5.2.3.1.1_2 | 4Rx FDD FR1 PDSCH mapping Type A performance - 4x4 MIMO with baseline receiver for both SA and NSA | [3-1, 4-1] | LGE | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190927 R5-194982 R5-197379 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
32 |  | 38.521-4 | 5.2.3.1.1_3 | 4Rx FDD FR1 PDSCH mapping Type A performance - 2x4 MIMO with enhanced receiver type 1 for both SA and NSA | none | LGE |  |  |  |  | currently no test id defined | 0 |  | 4 |  |  |  | 1 | 5 |  |  |  | 1 |  |  |  | 1
33 | Y | 38.521-4 | 5.2.3.1.1_4 | 4Rx FDD FR1 PDSCH mapping Type A performance - 4x4 MIMO with enhanced receiver type 1 for both SA and NSA | [5-1] | LGE | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190928 R5-194983 R5-197379 R5-198281 R5-201816 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
34 |  | 38.521-4 | 5.2.3.1.2 | 4Rx FDD FR1 PDSCH mapping Type A and CSI-RS overlapped with PDSCH performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
35 | Y | 38.521-4 | 5.2.3.1.2_1 | 4Rx FDD FR1 PDSCH mapping Type A and CSI-RS overlapped with PDSCH performance - 4x4 MIMO with baseline receiver for both SA and NSA | [1-1] | Huawei | Opt 2: RAN5#86 (Feb-20) Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199383 R5-200711 R5-203670 |  |  |  | 1 | 100% | 6 | 100% |  |  | 1 | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
36 |  | 38.521-4 | 5.2.3.1.3 | 4Rx FDD FR1 PDSCH mapping Type B performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
37 | Y | 38.521-4 | 5.2.3.1.3_1 | 4Rx FDD FR1 PDSCH mapping Type B performance - 2x4 MIMO with baseline receiver for both SA and NSA | [1-1] | Huawei | Opt 2: RAN5#86 (Feb-20) Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199414 R5-200712 R5-204774 R5-211716 |  |  |  | 1 | 100% | 6 | 100% |  |  | 1 | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
38 |  | 38.521-4 | 5.2.3.1.4 | 4Rx FDD FR1 PDSCH mapping Type A and LTE-NR coexistence performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
39 | Y | 38.521-4 | 5.2.3.1.4_1 | 4Rx FDD FR1 PDSCH Mapping Type A and LTE-NR coexistence performance - 4x4 MIMO with baseline receiver for both SA and NSA | [1-1, 1-2] | Anritsu | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-195168 R5-206667 R5-205925 R5-210521 R5-211716 R5-212635 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
40 |  | 38.521-4 | 5.2.3.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
41 |  | 38.521-4 | 5.2.3.2.1 | 4Rx TDD FR1 PDSCH mapping Type A performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
42 | Y | 38.521-4 | 5.2.3.2.1_1 | 4Rx TDD FR1 PDSCH mapping Type A performance - 2x4 MIMO with baseline receiver for both SA and NSA | [1-1, 1-2, 1-3, 1-5, 1-6, 2-1, 2-2] [1-4] | Qualcomm | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190931 R5-197372 R5-197372 R5-200271 R5-206163 R5-210520 R5-213341 R5-215345 R5-216041 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
43 | Y | 38.521-4 | 5.2.3.2.1_2 | 4Rx TDD FR1 PDSCH mapping Type A performance - 4x4 MIMO with baseline receiver for both SA and NSA | [3-1, 4-1] | Qualcomm | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190931 R5-197572 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
44 |  | 38.521-4 | 5.2.3.2.1_3 | 4Rx TDD FR1 PDSCH mapping Type A performance - 2x4 MIMO with enhanced receiver type 1 for both SA and NSA | none | Qualcomm |  |  |  |  | currently no test id defined | 0 |  | 4 |  |  |  | 1 | 5 |  |  |  | 1 |  |  |  | 1
45 | Y | 38.521-4 | 5.2.3.2.1_4 | 4Rx TDD FR1 PDSCH mapping Type A performance - 4x4 MIMO with enhanced receiver type 1 for both SA and NSA | [5-1] | Qualcomm | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190931 R5-197572 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
46 |  | 38.521-4 | 5.2.3.2.2 | 4Rx TDD FR1 PDSCH mapping Type A and CSI-RS overlapped with PDSCH performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
47 | Y | 38.521-4 | 5.2.3.2.2_1 | 4Rx TDD FR1 PDSCH mapping Type A and CSI-RS overlapped with PDSCH performance - 2x4 MIMO with baseline receiver for both SA and NSA | [1-1] | Huawei | Opt 2: RAN5#86 (Feb-20) Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199415 R5-200713 |  |  |  | 1 | 100% | 6 | 100% |  |  | 1 | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
48 |  | 38.521-4 | 5.2.3.2.3 | 4Rx TDD FR1 PDSCH mapping Type B performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
49 | Y | 38.521-4 | 5.2.3.2.3_1 | 4Rx TDD FR1 PDSCH mapping Type B performance - 2x4 MIMO with baseline receiver for both SA and NSA | [1-1] | Huawei | Opt 2: RAN5#86 (Feb-20) Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199416 R5-200714 R5-204774 R5-211716 |  |  |  | 1 | 100% | 6 | 100% |  |  | 1 | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
50 |  | 38.521-4 | 5.3 | PDCCH demodulation requirements |  |  |  | R5-200456 R5-214112 R5-213306 R5-215470 |  |  |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
51 |  | 38.521-4 | 5.3.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
52 |  | 38.521-4 | 5.3.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
53 |  | 38.521-4 | 5.3.2.1 | FDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
54 | Y | 38.521-4 | 5.3.2.1.1 | 2Rx FDD FR1 PDCCH 1 Tx antenna performance for both SA and NSA |  | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188010 R5-190934 R5-192470 R5-193332 R5-194991 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
55 | Y | 38.521-4 | 5.3.2.1.2 | 2Rx FDD FR1 PDCCH 2 Tx antenna performance for both SA and NSA |  | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190934 R5-192470 R5-193333 R5-194992 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
56 |  | 38.521-4 | 5.3.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
57 | Y | 38.521-4 | 5.3.2.2.1 | 2Rx TDD FR1 PDCCH 1 Tx antenna performance for both SA and NSA |  | KTL | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192672 R5-194993 R5-197376 R5-196247 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
58 | Y | 38.521-4 | 5.3.2.2.2 | 2Rx TDD FR1 PDCCH 2 Tx antenna performance for both SA and NSA |  | KTL | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192463 R5-194994 R5-197376 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
59 |  | 38.521-4 | 5.3.3 | 4RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
60 |  | 38.521-4 | 5.3.3.1 | FDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
61 | Y | 38.521-4 | 5.3.3.1.1 | 4Rx FDD FR1 PDCCH 1 Tx antenna performance for both SA and NSA |  | KTL | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192462 R5-194995 R5-197373 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
62 | Y | 38.521-4 | 5.3.3.1.2 | 4Rx FDD FR1 PDCCH 2 Tx antenna performance for both SA and NSA |  | KTL | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192464 R5-194996 R5-197373 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
63 |  | 38.521-4 | 5.3.3.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
64 | Y | 38.521-4 | 5.3.3.2.1 | 4Rx TDD FR1 PDCCH 1 Tx antenna performance for both SA and NSA |  | KTL | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192465 R5-194997 R5-197373 R5-196247 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
65 | Y | 38.521-4 | 5.3.3.2.2 | 4Rx TDD FR1 PDCCH 2 Tx antenna performance for both SA and NSA |  | KTL | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192466 R5-194998 R5-197373 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
66 |  | 38.521-4 | 5.4 | PBCH demodulation requirements |  |  |  | R5-194689 |  | No test case in RAN5 due to testability issue |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
67 |  | 38.521-4 | 5.4.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
68 |  | 38.521-4 | 5.4.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
69 |  | 38.521-4 | 5.4.2.1 | FDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
70 |  | 38.521-4 | 5.4.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
71 |  | 38.521-4 | 5.5 | Sustained downlink data rate provided by lower layers | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
72 | Y | 38.521-4 | 5.5.1 | FR1 Sustained downlink data rate performance for single carrier |  | Qualcomm | Opt 2: RAN5#84 (Aug-19) | R5-194684 R5-197512 R5-199525 R5-206098 R5-206165 R5-211717 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 |  |  |  | 1
|  | 6 | CSI reporting requirements (Conducted requirements)
73 |  | 38.521-4 | 6.1 | General |  |  | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193009 R5-200682 R5-203298 |  |  |  | 0.2 | 100% | 5 | 100% |  |  | 1 | 6 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
74 |  | 38.521-4 | 6.2 | Reporting of Channel Quality Indicator (CQI) |  |  |  | R5-195088 R5-199387 R5-199422 R5-200455 |  |  |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
75 |  | 38.521-4 | 6.2.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
76 |  | 38.521-4 | 6.2.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
77 |  | 38.521-4 | 6.2.2.1 | FDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
78 |  | 38.521-4 | 6.2.2.1.1 | CQI reporting definition under AWGN conditions | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
79 | Y | 38.521-4 | 6.2.2.1.1.1 | 2Rx FDD FR1 periodic CQI reporting under AWGN conditions for both SA and NSA |  | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193335 R5-194678 R5-198407 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
80 |  | 38.521-4 | 6.2.2.1.2 | CQI reporting under fading conditions | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
81 | Y | 38.521-4 | 6.2.2.1.2.1 | 2Rx FDD FR1 periodic wideband CQI reporting under fading conditions for both SA and NSA |  | Ericsson | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192461 R5-193323 R5-193544 R5-197370 R5-204063 R5-206668 R5-211718 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
82 | Y | 38.521-4 | 6.2.2.1.2.2 | 2Rx FDD FR1 aperiodic subband CQI reporting under fading conditions for both SA and NSA |  | Ericsson | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-194981 R5-196190 R5-202737 R5-206097 R5-215343 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
83 |  | 38.521-4 | 6.2.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
84 |  | 38.521-4 | 6.2.2.2.1 | CQI reporting definition under AWGN conditions | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
85 | Y | 38.521-4 | 6.2.2.2.1.1 | 2Rx TDD FR1 periodic CQI reporting under AWGN conditions for both SA and NSA |  | Qualcomm | Opt 2: RAN5#83 (May-19) Opt 3: RAN5#83 (May-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192103 R5-193336 R5-194679 R5-196245 |  |  |  | 1 | 100% | 3 | 100% |  |  | 1 | 4 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
86 |  | 38.521-4 | 6.2.2.2.2 | CQI reporting under fading conditions |  |  |  | R5-215665 |  |  |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
87 | Y | 38.521-4 | 6.2.2.2.2.1 | 2Rx TDD FR1 periodic wideband CQI reporting under fading conditions for both SA and NSA |  | Ericsson | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193325 R5-194466 R5-197371 R5-206668 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
88 | Y | 38.521-4 | 6.2.2.2.2.2 | 2Rx TDD FR1 aperiodic subband CQI reporting under fading conditions for both SA and NSA |  | Ericsson | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193943 R5-196192 R5-202737 R5-206097 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
89 |  | 38.521-4 | 6.2.3 | 4RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
90 |  | 38.521-4 | 6.2.3.1 | FDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
91 |  | 38.521-4 | 6.2.3.1.1 | CQI reporting definition under AWGN conditions | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
92 | Y | 38.521-4 | 6.2.3.1.1.1 | 4Rx FDD FR1 periodic CQI reporting under AWGN conditions for both SA and NSA |  | Huawei | Opt 2: RAN5#86 (Feb-20) Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199384 R5-200660 R5-200455 |  |  |  | 1 | 100% | 6 | 100% |  |  | 1 | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
93 |  | 38.521-4 | 6.2.3.1.2 | CQI reporting under fading conditions | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
94 | Y | 38.521-4 | 6.2.3.1.2.1 | 4Rx FDD FR1 periodic wideband CQI reporting under fading conditions for both SA and NSA |  | Ericsson | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199386 R5-202297 R5-202300 R5-206668 R5-206670 |  |  |  | 1 | 100% | 5 | 100% |  |  | 1 | 6 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
95 | Y | 38.521-4 | 6.2.3.1.2.2 | 4Rx FDD FR1 aperiodic subband CQI reporting under fading conditions for both SA and NSA |  | Ericsson | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199418 R5-202737 R5-206097 |  |  |  | 1 | 100% | 5 | 100% |  |  | 1 | 6 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
96 |  | 38.521-4 | 6.2.3.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
97 |  | 38.521-4 | 6.2.3.2.1 | CQI reporting definition under AWGN conditions | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
98 | Y | 38.521-4 | 6.2.3.2.1.1 | 4Rx TDD FR1 periodic CQI reporting under AWGN conditions for both SA and NSA |  | Huawei | Opt 2: RAN5#86 (Feb-20) Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199417 R5-200660 R5-200455 |  |  |  | 1 | 100% | 6 | 100% |  |  | 1 | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
99 |  | 38.521-4 | 6.2.3.2.2 | CQI reporting under fading conditions | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
100 | Y | 38.521-4 | 6.2.3.2.2.1 | 4Rx TDD FR1 periodic wideband CQI reporting under fading conditions for both SA and NSA |  | Ericsson | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199419 R5-202300 |  |  |  | 1 | 100% | 5 | 100% |  |  | 1 | 6 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
101 | Y | 38.521-4 | 6.2.3.2.2.2 | 4Rx TDD FR1 aperiodic subband CQI reporting under fading conditions for both SA and NSA |  | Ericsson | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199420 R5-202737 R5-206668 R5-206097 |  |  |  | 1 | 100% | 5 | 100% |  |  | 1 | 6 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
102 |  | 38.521-4 | 6.3 | Reporting of Precoding Matrix Indicator (PMI) |  |  |  | R5-215342 |  |  |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
103 |  | 38.521-4 | 6.3.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
104 |  | 38.521-4 | 6.3.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
105 |  | 38.521-4 | 6.3.2.1 | FDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
106 | Y | 38.521-4 | 6.3.2.1.1 | 2Rx FDD FR1 Single PMI with 4Tx Type I - SinglePanel codebook for both SA and NSA |  | 7Layers | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192474 R5-195167 R5-197575 R5-206092 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
107 | Y | 38.521-4 | 6.3.2.1.2 | 2Rx FDD FR1 Single PMI with 8Tx Type I - SinglePanel codebook for both SA and NSA |  | 7Layers | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192475 R5-194984 R5-197576 R5-202738 R5-206092 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
108 |  | 38.521-4 | 6.3.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
109 | Y | 38.521-4 | 6.3.2.2.1 | 2Rx TDD FR1 Single PMI with 4Tx Type I - SinglePanel codebook for both SA and NSA |  | Samsung | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190552 R5-193293 R5-197566 R5-198408 R5-206092 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
110 | Y | 38.521-4 | 6.3.2.2.2 | 2Rx TDD FR1 Single PMI with 8Tx Type I - SinglePanel codebook for both SA and NSA |  | Samsung | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193294 R5-197567 R5-202738 R5-206092 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
111 |  | 38.521-4 | 6.3.3 | 4RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
112 |  | 38.521-4 | 6.3.3.1 | FDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
113 | Y | 38.521-4 | 6.3.3.1.1 | 4Rx FDD FR1 Single PMI with 4Tx Type I - SinglePanel codebook for both SA and NSA |  | 7Layers | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-194985 R5-197577 R5-198408 R5-202300 R5-206092 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
114 | Y | 38.521-4 | 6.3.3.1.2 | 4Rx FDD FR1 Single PMI with 8Tx Type I - SinglePanel codebook for both SA and NSA |  | 7Layers | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-194986 R5-197578 R5-202738 R5-206092 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
115 |  | 38.521-4 | 6.3.3.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
116 | Y | 38.521-4 | 6.3.3.2.1 | 4Rx TDD FR1 Single PMI with 4Tx Type I - SinglePanel codebook for both SA and NSA |  | 7Layers | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-194987 R5-197579 R5-202300 R5-206092 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
117 | Y | 38.521-4 | 6.3.3.2.2 | 4Rx TDD FR1 Single PMI with 8Tx Type I - SinglePanel codebook for both SA and NSA |  | 7Layers | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-194988 R5-197580 R5-202738 R5-206092 R5-206092 |  |  |  | 1 | 100% | 4 | 100% |  |  | 1 | 5 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
118 |  | 38.521-4 | 6.4 | Reporting of Rank Indicator (RI) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
119 |  | 38.521-4 | 6.4.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
120 |  | 38.521-4 | 6.4.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
121 |  | 38.521-4 | 6.4.2.1 | FDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
122 | Y | 38.521-4 | 6.4.2.1_1 | 2Rx FDD FR1 RI reporting for both SA and NSA |  | Huawei | Opt 2: RAN5#86 (Feb-20) Opt 3: RAN5#86 (Feb-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199385 R5-201068 R5-202739 R5-206094 R5-210773 |  |  |  | 1 | 100% | 6 | 100% |  |  | 1 | 7 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
123 |  | 38.521-4 | 6.4.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
124 | Y | 38.521-4 | 6.4.2.2_1 | 2Rx TDD FR1 RI reporting for both SA and NSA |  | Qualcomm | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190553 R5-192472 R5-195000 R5-197582 R5-202739 R5-206094 |  |  |  | 1 | 100% | 5 | 100% |  |  | 1 | 6 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
125 |  | 38.521-4 | 6.4.3 | 4RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
126 |  | 38.521-4 | 6.4.3.1 | FDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
127 | Y | 38.521-4 | 6.4.3.1_1 | 4Rx FDD FR1 RI reporting for both SA and NSA |  | Qualcomm | Opt 2: RAN5#88 (Aug-20) Opt 3: RAN5#88 (Aug-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-204871 R5-206094 |  |  |  | 1 | 100% | 8 | 100% |  |  | 1 | 9 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
128 |  | 38.521-4 | 6.4.3.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
129 | Y | 38.521-4 | 6.4.3.2_1 | 4Rx TDD FR1 RI reporting for both SA and NSA |  | CAICT | Opt 2: RAN5#87 (May-20) Opt 3: RAN5#87 (May-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-194980 R5-202831 R5-202739 R5-206094 |  |  |  | 1 | 100% | 7 | 100% |  |  | 1 | 8 | 100% |  |  | 1 | 100% |  |  | 1 | 100%
|  | 7 | Demodulation performance requirements (Radiated requirements)
130 |  | 38.521-4 | 7.1 | General |  | Qualcomm | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-200682 R5-202908 R5-214058 R5-216096 R5-215609 |  |  | text and table addition | 0.2 | 100% | 9 |  | 100% |  | 2 | 10 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
131 |  | 38.521-4 | 7.2 | PDSCH demodulation requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
132 |  | 38.521-4 | 7.2.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
133 |  | 38.521-4 | 7.2.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
134 |  | 38.521-4 | 7.2.2.1 | FDD (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
135 |  | 38.521-4 | 7.2.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
136 |  | 38.521-4 | 7.2.2.2.1 | 2Rx TDD FR2 PDSCH mapping Type A performance | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
137 | Y | 38.521-4 | 7.2.2.2.1_1 | 2Rx TDD FR2 PDSCH mapping Type A performance - 2x2 MIMO with baseline receiver for SA and NSA |  | Qualcomm | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-188008 R5-190458 R5-194690 R5-199527 R5-202740 R5-204936 R5-206830 R5-210520 R5-211929 |  | n259 is currently not testable. Some of the test points not testable for n260. |  | 1 | 100% | 9 |  | 100% |  | 1 | 10 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
138 | Y | 38.521-4 | 7.2.2.2.1_2 | 2Rx TDD FR2 PDSCH mapping Type A performance - 2x2 MIMO with enhanced type 1 receiver for SA and NSA |  | Qualcomm | Opt 2: RAN5#92 (Aug-21) Opt 3: RAN5#92 (Aug-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190458 R5-194690 R5-199425 R5-204936 R5-206830 R5-210520 R5-211929 |  | Test point currently not testable for any of the FR2 bands |  | 1 | 100% | 12 |  | 100% |  | 1 | 13 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
139 |  | 38.521-4 | 7.3 | PDCCH demodulation requirements |  |  |  | R5-214112 |  |  |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
140 |  | 38.521-4 | 7.3.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
141 |  | 38.521-4 | 7.3.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
142 |  | 38.521-4 | 7.3.2.1 | FDD (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
143 |  | 38.521-4 | 7.3.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
144 | Y | 38.521-4 | 7.3.2.2.1 | 2Rx TDD FR2 PDCCH 1 Tx antenna performance for both SA and NSA |  | Qualcomm | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190461 R5-199532 R5-202304 R5-206831 R5-211929 R5-213308 |  | 1 test point not testable for n260. No test points currently testable for n259 |  | 1 | 100% | 9 |  | 100% |  | 1 | 10 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
145 | Y | 38.521-4 | 7.3.2.2.2 | 2Rx TDD FR2 PDCCH 2 Tx antenna performance for both SA and NSA |  | Qualcomm | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190461 R5-199532 R5-202304 R5-206831 R5-210770 R5-211929 R5-213308 |  | Test points not testable for n259 |  | 1 | 100% | 9 |  | 100% |  | 1 | 10 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
146 |  | 38.521-4 | 7.4 | PBCH demodulation requirements |  |  |  | R5-194692 |  | No test case in RAN5 due to testability issues |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
147 |  | 38.521-4 | 7.4.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
148 |  | 38.521-4 | 7.4.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
149 |  | 38.521-4 | 7.4.2.1 | FDD (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
150 |  | 38.521-4 | 7.4.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
151 |  | 38.521-4 | 7.5 | Sustained downlink data rate provided by lower layers |  | Qualcomm | [5 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
152 | Y | 38.521-4 | 7.5.1 | FR2 Sustained downlink data rate performance for single carrier |  | Qualcomm | Opt 2: RAN5#93 (Nov-21) |  |  |  |  | 1 | 0% | 13 |  | 0% |  | 1 | 6 |  |  |  | 1
|  | 8 | CSI reporting requirements (Radiated requirements)
153 |  | 38.521-4 | 8.1 | General |  |  |  | R5-193295 R5-200682 R5-202908 |  |  |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
154 |  | 38.521-4 | 8.1.1 | Applicability of requirements |  |  |  | R5-214058 R5-216096 R5-215609 |  |  |  | 0.2 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
155 |  | 38.521-4 | 8.1.2 | Common test param | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
156 |  | 38.521-4 | 8.2 | Reporting of Channel Quality Indicator (CQI) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
157 |  | 38.521-4 | 8.2.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
158 |  | 38.521-4 | 8.2.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
159 |  | 38.521-4 | 8.2.2.1 | FDD (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
160 |  | 38.521-4 | 8.2.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
161 |  | 38.521-4 | 8.2.2.2.1 | CQI reporting under AWGN conditions | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
162 | Y | 38.521-4 | 8.2.2.2.1.1 | 2Rx TDD FR2 periodic CQI reporting under AWGN performance for both SA and NSA |  | Ericsson | Opt 2: RAN5#89 (Nov-20) Opt 3: RAN5#89 (Nov-20) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199570 R5-200914 R5-206832 R5-206093 R5-210520 R5-211929 |  | Editor's Note: The following aspects are pending further analysis: - The maximum testable SNRBB for IFF based Test System for n259 is TBD. - Test 1 is not testable for FR2b with the current assumption of maximum testable SNRBB Current assumption of maximum testable SNRBB for IFF based Test System for FR2a: [19.2] dB, FR2b: [7.3 dB], FR2c: TBD. Test 1 is fully testable for FR2a, FR2b for 100MHz CBW. |  | 1 | 100% | 9 |  | 100% |  | 2 | 10 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
163 |  | 38.521-4 | 8.2.2.2.2 | CQI reporting under fading conditions | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
164 | Y | 38.521-4 | 8.2.2.2.2.1 | 2Rx TDD FR2 aperiodic wideband CQI reporting under fading performance for both SA and NSA |  | Ericsson | Opt 2: RAN5#91 (May-21) Opt 3: RAN5#91 (May-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-199570 R5-206092 R5-206093 R5-210520 R5-211929 R5-213920 |  |  |  | 1 | 100% | 11 |  | 100% |  | 1 | 12 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
165 |  | 38.521-4 | 8.3 | Reporting of Precoding Matrix Indicator (PMI) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
166 |  | 38.521-4 | 8.3.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
167 |  | 38.521-4 | 8.3.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
168 |  | 38.521-4 | 8.3.2.1 | FDD (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
169 |  | 38.521-4 | 8.3.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
170 | Y | 38.521-4 | 8.3.2.2.1 | 2Rx TDD FR2 Single PMI with 2Tx Type I - SinglePanel codebook for both SA and NSA |  | Samsung, Anritsu | Opt 2: RAN5#90 (Feb-21) Opt 3: RAN5#90 (Feb-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-193295 R5-210523 |  |  |  | 1 | 100% | 10 |  | 100% |  | 1 | 11 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
171 |  | 38.521-4 | 8.4 | Reporting of Rank Indicator (RI) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
172 |  | 38.521-4 | 8.4.1 | 1RX requirements (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
173 |  | 38.521-4 | 8.4.2 | 2RX requirements | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
174 |  | 38.521-4 | 8.4.2.1 | FDD (Void) | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
175 |  | 38.521-4 | 8.4.2.2 | TDD | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
176 | Y | 38.521-4 | 8.4.2.2.1 | 2Rx TDD FR2 RI reporting for both SA and NSA |  | Anritsu | Opt 2: RAN5#91 (May-21) Opt 3: RAN5#91 (May-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-206092 R5-206093 R5-211929 R5-212254 R5-215901 R5-216021 |  |  |  | 1 | 100% | 11 |  | 100% |  | 1 | 12 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
|  | 9 | Demodulation performance requirements for interworking
177 |  | 38.521-4 | 9.1 | General |  | Qualcomm |  | R5-190979 R5-202908 |  |  |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
178 |  | 38.521-4 | 9.2 | Void | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
179 |  | 38.521-4 | 9.2A | PDSCH demodulation for CA | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
180 |  | 38.521-4 | 9.2A.1 | NR CA between FR1 and FR2 | [6 empty] | No RAN4 requirements so far | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
181 |  | 38.521-4 | 9.2B | PDSCH demodulation for DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
182 |  | 38.521-4 | 9.2B.1 | EN-DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
183 |  | 38.521-4 | 9.2B.1.1 | EN-DC within FR1 |  |  |  | R5-193134 |  | Only NR cell needs to verified per section 5.2. test case covered in section 5.2 |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
184 |  | 38.521-4 | 9.2B.1.2 | EN-DC including FR2 NR carrier |  |  |  | R5-193134 |  | Only NR cell needs to verified per section 7.2. test case covered in section 7.2 |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
185 |  | 38.521-4 | 9.2B.1.3 | EN-DC including FR1 and FR2 NR carriers |  |  |  | R5-193134 |  | NR FR1 and NR Fr2 cell needs to be verified separately as per section 5.2 and 7.2. test case already covered in respective sections |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
186 |  | 38.521-4 | 9.2B.2 | NR DC between FR1 and FR2 | [6 empty] | No RAN4 requirements so far | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
187 |  | 38.521-4 | 9.3 | Void | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
188 |  | 38.521-4 | 9.3A | PDCCH demodulation for CA | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
189 |  | 38.521-4 | 9.3A.1 | NR CA between FR1 and FR2 |  |  |  | R5-193134 |  | Only NR cell needs to verified per section 7.3. test case covered in section 7.3 |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
190 |  | 38.521-4 | 9.3B | PDCCH demodulation for DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
191 |  | 38.521-4 | 9.3B.1 | EN-DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
192 |  | 38.521-4 | 9.3B.1.1 | EN-DC within FR1 |  |  |  | R5-193134 |  | Only NR cell needs to verified per section 5.3. test case covered in section 5.3 |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
193 |  | 38.521-4 | 9.3B.1.2 | EN-DC including FR2 NR carrier |  |  |  | R5-193134 |  | Only NR cell needs to verified per section 7.3. test case covered in section 7.3 |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
194 |  | 38.521-4 | 9.3B.1.3 | EN-DC including FR1 and FR2 NR carriers |  |  |  | R5-193134 |  | NR FR1 or NR FR2 cell needs to be verified per section 5.3, 7.3 respectively. No demod requirements for NR FR1 or LTE cell defined for EN-DC including FR2 |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
195 |  | 38.521-4 | 9.3B.2 | NR DC between FR1 and FR2 | [6 empty] | No RAN4 requirements so far | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
196 |  | 38.521-4 | 9.4 | Void | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
197 |  | 38.521-4 | 9.4A | SDR test for CA | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
198 |  | 38.521-4 | 9.4A.1 | Sustained downlink data rate performance for NR CA between FR1 and FR2 |  |  |  | R5-193134 |  | Only NR FR2 carrier needs to be verified per section 7.5 |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
199 |  | 38.521-4 | 9.4B | SDR test for DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
200 |  | 38.521-4 | 9.4B.1 | EN-DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
201 | Y | 38.521-4 | 9.4B.1.1 | Sustained downlink data rate performance for EN-DC within FR1 |  | Qualcomm | Opt 3: RAN5#84 (Aug-19) | R5-194686 R5-197513 R5-199526 R5-206098 R5-206165 R5-206091 R5-211717 R5-214059 R5-215610 |  |  |  | 1 | 100% | 4 |  |  |  | 1 | 5 | 100% |  |  | 1 |  |  |  | 1
202 | Y | 38.521-4 | 9.4B.1.2 | Sustained downlink data rate performance for EN-DC including FR2 NR carrier |  |  | Opt 3: RAN5#92 (Aug-21) | R5-201180 R5-211929 R5-216118 |  |  |  | 1 | 100% | 11 |  |  |  | 1 | 13 |  | 100% |  | 1 |  |  |  | 1
203 |  | 38.521-4 | 9.4B.1.3 | Sustained downlink data rate performance for EN-DC including FR1 and FR2 NR carriers | [5 empty] | Only NR FR1 or NR FR2 cell needs to be verified per section 5.5, 7.5 respectively. No SDR requirements for NR FR1 or LTE cell to be tested for EN-DC including FR2. To be covered as part of Rel16 NR performance enhancement requirements WI |  | 0 |  | 9 |  |  |  | 1 | 10 |  |  |  | 1 |  |  |  | 1
204 |  | 38.521-4 | 9.4B.2 | Sustained downlink data rate performance for NR DC between FR1 and FR2 | [6 empty] | No RAN4 requirements so far | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
205 | Y | 38.521-4 | 9.4B.3.1 | Sustained downlink data rate performance for NE-DC within FR1 |  |  | Opt 4: FFS |  |  |  |  | 1 | 0% | 4 |  |  |  | 1 |  |  |  |  | 2 | 0% |  |  | 1
|  | 10 | CSI reporting requirements for interworking
207 |  | 38.521-4 | 10.1 | General |  | Qualcomm |  | R5-190979 |  |  | subsections added | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
208 |  | 38.521-4 | 10.2 | Void | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
209 |  | 38.521-4 | 10.2A | Reporting of Channel Quality Indicator (CQI) for CA | [6 empty] | No RAN4 requirements so far | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
210 |  | 38.521-4 | 10.2B | Reporting of Channel Quality Indicator (CQI) for DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
211 |  | 38.521-4 | 10.2B.1 | EN-DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
212 |  | 38.521-4 | 10.2B.1.1 | EN-DC within FR1 |  |  |  | R5-193134 |  | Only NR cell CQI requirements needs to be verified per section 6.2. |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
213 |  | 38.521-4 | 10.2B.1.2 | EN-DC including FR2 NR carrier |  |  |  | R5-193134 |  | Only NR cell CQI requirements needs to be verified per section 8.2. |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
214 |  | 38.521-4 | 10.2B.1.3 | EN-DC including FR1 and FR2 NR carriers | [6 empty] | No RAN4 requirements so far | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
215 |  | 38.521-4 | 10.3 | Void | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
216 |  | 38.521-4 | 10.3A | Reporting of Precoding Matrix Indicator (PMI) for CA | [6 empty] | No RAN4 requirements so far | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
217 |  | 38.521-4 | 10.3B | Reporting of Precoding Matrix Indicator (PMI) for DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
218 |  | 38.521-4 | 10.3B.1 | EN-DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
219 |  | 38.521-4 | 10.3B.1.1 | EN-DC within FR1 |  |  |  | R5-193134 |  | Only NR cell PMI requirements needs to be verified per section 6.3. |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
220 |  | 38.521-4 | 10.3B.1.2 | EN-DC including FR2 NR carrier |  |  |  | R5-193134 |  | Only NR cell PMI requirements needs to be verified per section 8.3. |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
221 |  | 38.521-4 | 10.3B.1.3 | EN-DC including FR1 and FR2 NR carriers | [6 empty] | No RAN4 requirements so far | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
222 |  | 38.521-4 | 10.4 | Void | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
223 |  | 38.521-4 | 10.4A | Reporting of Rank Indicator (RI) for CA | [6 empty] | No RAN4 requirements so far | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
224 |  | 38.521-4 | 10.4B | Reporting of Rank Indicator (RI) for DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
225 |  | 38.521-4 | 10.4B.1 | EN-DC | [7 empty] | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
226 |  | 38.521-4 | 10.4B.1.1 | EN-DC within FR1 |  |  |  | R5-193134 |  | Only NR cell RI requirements needs to be verified per section 6.4. |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
227 |  | 38.521-4 | 10.4B.1.2 | EN-DC including FR2 NR carrier |  |  |  | R5-193134 |  | Only NR cell RI requirements needs to be verified per section 8.4. |  | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
228 |  | 38.521-4 | 10.4B.1.3 | EN-DC including FR1 and FR2 NR carriers | [6 empty] | No RAN4 requirements so far | 0 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1
Annex
229 |  | 38.521-4 | Annex A | Measurement channels |  | Bureau Veritas | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190291 R5-193327 R5-193476 R5-195001 R5-194622 R5-196495 R5-198560 R5-200672 R5-206671 R5-215065 |  |  |  | 1 | 100% | 4 | 100% | 100% |  | 1 | 5 | 100% | 100% |  | 1 | 100% | 100% |  | 1 | 100%
230 |  | 38.521-4 | Annex B | Propagation conditions |  | Bureau Veritas | Opt 2: RAN5#84 (Aug-19) Opt 3: RAN5#84 (Aug-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190292 R5-196496 R5-198560 R5-200672 R5-201945 |  |  |  | 1 | 100% | 4 | 100% | 100% |  | 1 | 5 | 100% | 100% |  | 1 | 100% | 100% |  | 1 | 100%
231 |  | 38.521-4 | Annex C | Downlink physical channels |  | Qualcomm | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190933 R5-190935 R5-192469 R5-193476 R5-194159 R5-194622 R5-202742 R5-211081 |  |  |  | 1 | 100% | 5 | 100% | 100% |  | 1 | 6 | 100% | 100% |  | 1 | 100% | 100% |  | 1 | 100%
232 |  | 38.521-4 | Annex D | LTE link setup details for NSA testing |  | Qualcomm | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-190929 R5-193326 R5-195089 R5-198395 R5-204101 R5-211719 R5-212632 |  |  |  | 1 | 100% | 5 | 100% | 100% |  | 1 | 6 | 100% | 100% |  | 1 | 100% | 100% |  | 1 | 100%
233 |  | 38.521-4 | Annex H | Approach for finding UE direction for FR2 Demod and CSI Testing |  | Qualcomm | Opt 2: RAN5#85 (Nov-19) Opt 3: RAN5#85 (Nov-19) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-182036 R5-199531 R5-200322 R5-202743 |  |  |  | 0.5 | 100% | 5 |  | 100% |  | 1 | 6 |  | 100% |  | 1 |  | 100% |  | 1 | 100%
234 |  | 38.521-4 | Annex F | Measurement uncertainties and test tolerances |  | All companies | Opt 2: RAN5#93 (Nov-21) Opt 3: RAN5#93 (Nov-21) Opt 4: RAN5#93 (Nov-21) Opt 7: FFS | R5-192473 R5-195171 R5-197378 R5-197380 R5-198248 R5-200455 R5-200718 R5-202766 R5-204933 R5-204935 R5-204937 R5-204938 R5-206829 R5-210868 |  |  |  | 1 | 90% | 13 | 90% | 90% |  |  | 14 | 90% | 90% |  | 1 | 90% | 90% |  | 1 | 90%
235 |  | 38.521-4 | Annex G | Statistical testing |  | Qualcomm | Opt 2: RAN5#92 (Aug-21) Opt 3: RAN5#92 (Aug-21) | R5-190930 R5-192460 R5-193328 R5-195172 R5-197564 R5-197565 R5-199388 R5-203902 R5-214088 |  |  |  | 1 | 100% | 12 | 100% | 100% |  |  | 13 | 100% | 100% |  | 1 |  |  |  | 1
End of work plan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A7: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B7: Y = the WP Pitem is a test case.
Note on M7: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.